## FP&A & QC Project Report
Northstar Heritage, LLC
FP&A & QC Project Report (In USD)
As of September 29, 2026
Reporting Book: | ACCRUAL
As of Date: | 09/29/2026
Location: | Northstar
Project: | All Projects
[7 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Original Budget | Total Budget Adjustment | Total Costs |  | Recognized % |  |  |  | Total Costs | Total Costs | Invoiced Amount
[7 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Inception To Date | REV REC % | Budget Spent % | Gross profit | Margin % | Year To Date | Month Ending | Year To Date
[7 empty] | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 |  |  |  | 09/29/2026 | 09/30/2026 | 09/29/2026
| Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | On-Track As of Date | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Actual | Summary | Summary | Summary | Actual | Actual | Actual
All Projects | All Projects
Active Projects | Active Projects
26-PC-44319 | Dove Canyon Harbor Dredging Cultural Resources Monitoring | Pending Billing Activation | Fixed fee | Big Sky | Javier Estrada |  | 124500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 124500 | 100% | 0 | 0 | 0
26-PC-44322 | Sage Flat Mixed-Use Development Cultural Resources Assessment | Pending Billing Activation | Time and material | Cascade | Jeff Spence |  | 55500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 55500 | 100% | 0 | 0 | 0
26-PC-44325 | Raven Rock Cell Tower GIS Mapping | Pending Billing Activation | Fixed fee | Cascade | Jean Cooke |  | 35500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 35500 | 100% | 0 | 0 | 0
26-PC-44328 | Juniper Wash Transmission Line Maritime Remote Sensing Survey | Pending Billing Activation | Time and material | Chesapeake | Sandy Kerr |  | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 10500 | 100% | 0 | 0 | 0
26-PC-44331 | Stone Mill Bridge Replacement Built Environment Survey | Pending Billing Activation | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 85000 | 100% | 0 | 0 | 0
26-PC-44334 | Heron Marsh Substation Class III Survey | Pending Billing Activation | Fixed fee | Great Lakes | Brendan Padilla |  | 48500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 48500 | 100% | 0 | 0 | 0
26-PC-44337 | Heron Marsh School Campus Data Recovery | Pending Billing Activation | Time and material | Gulf Coast | Sean Jennings |  | 214000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 214000 | 100% | 0 | 0 | 0
26-PC-44340 | Granite Pass Pipeline Section 106 Consultation | Pending Billing Activation | Time and material | Hill Country | Marcus Shea |  | 227500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 227500 | 100% | 0 | 0 | 0
26-PC-44343 | Sparrow Hill Water Main Data Recovery | Pending Billing Activation | Time and material | Piedmont | Jody Chung |  | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 47500 | 100% | 0 | 0 | 0
26-PC-44346 | Stone Mill Housing Development Curation | Pending Billing Activation | Time and material | Prairie | Sherry Lloyd |  | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 64000 | 100% | 0 | 0 | 0
26-PC-44349 | Riverbend Bridge Replacement Architectural History Survey | Pending Billing Activation | Time and material | Red Rock | Jeanette Chung |  | 41500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 41500 | 100% | 0 | 0 | 0
26-PC-44352 | Pine Hollow Bridge Replacement Phase I Survey | Pending Billing Activation | Fixed fee | Red Rock | Tina Aguirre |  | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 11500 | 100% | 0 | 0 | 0
26-PC-44355 | Coyote Springs Canal Lining Cultural Resources Monitoring | Pending Billing Activation | Fixed fee | Red Rock | Lydia Cisneros |  | 166000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 166000 | 100% | 0 | 0 | 0
26-PC-44358 | Windmill Flat Transmission Line Phase I Survey | Pending Billing Activation | Time and material | Sierra | Benjamin Mathis |  | 84500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 84500 | 100% | 0 | 0 | 0
26-PC-44361 | Tamarack Fiber Route Archaeological Testing | Pending Billing Activation | Fixed fee | Coastal Bend | Duane Ballard |  | 284500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 284500 | 100% | 0 | 0 | 0
26-PC-44364 | Raven Rock Cell Tower Historic Resources Evaluation | Pending Billing Activation | Fixed fee | Coastal Bend | Steve Rubio |  | 211500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 211500 | 100% | 0 | 0 | 0
26-PC-44367 | Lantern Bay Housing Development Built Environment Survey | Pending Billing Activation | Time and material | Maritime | Rita Ayala |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 90000 | 100% | 0 | 0 | 0
26-PC-44370 | Granite Pass Fiber Route Curation | Pending Billing Activation | Fixed fee | Meridian Central | Raymond Hensley |  | 73000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 73000 | 100% | 0 | 0 | 0
26-PC-44373 | North Fork Battery Storage Phase I Survey | Pending Billing Activation | Time and material | Meridian Central | Clinton Solis |  | 78500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 78500 | 100% | 0 | 0 | 0
26-PC-44376 | Sumac Ridge Park Improvements Phase I Survey | Pending Billing Activation | Time and material | NH Gulf (USD) | Randy Cantu |  | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 108000 | 100% | 0 | 0 | 0
Total Active Projects | Total Active Projects | [5 empty] | 2061500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2061500 | 100% | 0 | 0 | 0
All Other Projects | All Other Projects
23-PC-30060 | Lone Pine Pipeline - Cultural Resources Monitoring | Final Billing/Invoice | Fixed fee | Big Sky | Javier Estrada |  | 397800 | 397800 | 397800 | 312273 | 312273 | 0 | 376882.23 | -64609.23 | 100% | 120.7% | 20917.77 | 5.26% | 0 | 0 | 0
23-PC-30163 | Timber Gap Phase I Survey | Completed | Fixed fee | Big Sky | Bob Frye |  | 33300 | 33300 | 33300 | 22510.8 | 22510.8 | 0 | 22797.57 | -286.77 | 100% | 101.3% | 10502.43 | 31.54% | 0 | 0 | 0
23-PC-30307 | Quail Run Wastewater Plant Cultural Resources Assessment | Transferred Entity | Fixed fee | Big Sky | Javier Estrada |  | 240100 | 157553.62 | 157553.62 | 136256.75 | 136256.75 | 0 | 89412.87 | 46843.88 | 65.6% | 65.62% | 150687.13 | 62.76% | 0 | 0 | 0
23-PC-30372 | Phase I: Lone Pine Reservoir Architectural History Survey | In Progress | Time and material | Big Sky | Bob Frye |  | 27100 | 18428 | 18428 | 19864.3 | 19864.3 | 0 | 11402.28 | 8462.02 | 68% | 57.4% | 15697.72 | 57.93% | 0 | 0 | 0
23-PC-30543 | Phase III: Riverbend Rail Siding Maritime Remote Sensing Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 08/28/2026 | 320600 | 225766.52 | 225766.52 | 255628.66 | 192683.15 | 62945.51 | 180013.95 | 75614.71 | 70.4% | 70.42% | 140586.05 | 43.85% | 0 | 0 | 0
23-PC-30644 | Phase II: Millbrook Wastewater Plant Data Recovery | In Progress | Time and material | Bluegrass | Alice Galloway |  | 108100 | 73508 | 73508 | 72102.7 | 72102.7 | 0 | 46653.03 | 25449.67 | 68% | 64.7% | 61446.97 | 56.84% | 0 | 0 | 0
23-PC-30667 | North Fork Canal Lining Data Recovery | Completed | Time and material | Bluegrass | Kiara Gillespie |  | 210500 | 143140 | 143140 | 144045.15 | 144045.15 | 0 | 154304.59 | -10259.44 | 68% | 107.1% | 56195.41 | 26.7% | 0 | 0 | 0
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | In Progress | Time and material | Bluegrass | Kiara Gillespie |  | 49800 | 33864 | 33864 | 34501.44 | 34501.44 | 0 | 28656.36 | 5845.08 | 68% | 83.06% | 21143.64 | 42.46% | 0 | 0 | 0
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 08/07/2026 | 86200 | 58616 | 58616 | 58650.48 | 58650.48 | 0 | 61318.15 | -2667.67 | 68% | 104.6% | 24881.85 | 28.87% | 0 | 0 | 0
23-PC-30933 | Lantern Bay Water Main - Phase I Survey | On Hold | Time and material | Bluegrass | Kiara Gillespie |  | 703200 | 478176 | 478176 | 461299.2 | 461299.2 | 0 | 382697.29 | 78601.91 | 68% | 82.96% | 320502.71 | 45.58% | 0 | 0 | 0
23-PC-31003 | Windmill Flat Environmental Review Support | In Progress | Fixed fee | Bluegrass | Kiara Gillespie |  | 19300 | 15445.79 | 15445.79 | 10568.68 | 10568.68 | 0 | 8458.51 | 2110.17 | 80% | 80.03% | 10841.49 | 56.17% | 0 | 0 | 0
23-PC-31042 | Stone Mill Historic Resources Evaluation | In Progress | Time and material | Cascade | Donald Lutz | 09/18/2026 | 299700 | 203796 | 203796 | 202896.9 | 202896.9 | 0 | 147919.88 | 54977.02 | 68% | 72.9% | 151780.12 | 50.64% | 0 | 0 | 0
23-PC-31076 | Wildrye Rail Siding - Archaeological Testing | Final Reporting/Review | Time and material | Cascade | Cassidy Gay |  | 95100 | 64668 | 64668 | 65561.94 | 65561.94 | 0 | 41531.43 | 24030.51 | 68% | 63.35% | 53568.57 | 56.33% | 0 | 0 | 0
23-PC-31344 | Timber Gap Battery Storage Archaeological Testing | In Progress | Fixed fee | Cascade | Cassidy Gay |  | 331600 | 194516.56 | 194516.56 | 264351.52 | 264351.52 | 0 | 155057.32 | 109294.2 | 58.7% | 58.66% | 176542.68 | 53.24% | 0 | 0 | 0
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | In Progress | Time and material | Cascade | Donald Lutz |  | 255700 | 173876 | 173876 | 168225.03 | 168225.03 | 0 | 202903.45 | -34678.42 | 68% | 120.6% | 52796.55 | 20.65% | 0 | 0 | 0
23-PC-31389 | Juniper Wash Highway Widening Archaeological Testing | Final Billing/Invoice | Time and material | Cascade | Preston Duarte |  | 30700 | 20876 | 20876 | 20958.95 | 17285.12 | 3673.83 | 27246.63 | -6287.68 | 68% | 130% | 3453.37 | 11.25% | 0 | 0 | 0
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | In Progress | Fixed fee | Cascade | Jeff Spence | 08/07/2026 | 108000 | 76528.8 | 76528.8 | 82404 | 82404 | 0 | 58391.35 | 24012.65 | 70.9% | 70.86% | 49608.65 | 45.93% | 0 | 0 | 0
23-PC-31604 | Timber Gap Pipeline - Cultural Resources Assessment | Final Billing/Invoice | Time and material | Cascade | Cassidy Gay |  | 180800 | 122944 | 122944 | 124607.36 | 124607.36 | 0 | 161989.57 | -37382.21 | 68% | 130% | 18810.43 | 10.4% | 0 | 0 | 0
23-PC-31765 | Saltgrass Phase I Survey | Final Reporting/Review | Fixed fee | Cascade | Jean Cooke |  | 32700 | 18707.67 | 18707.67 | 27114.84 | 27114.84 | 0 | 15513.28 | 11601.56 | 57.2% | 57.21% | 17186.72 | 52.56% | 0 | 0 | 0
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | In Progress | Fixed fee | Cascade | Gene Nixon |  | 34800 | 34800 | 34800 | 28779.6 | 28779.6 | 0 | 31540.76 | -2761.16 | 100% | 109.6% | 3259.24 | 9.37% | 0 | 0 | 0
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | In Progress | Fixed fee | Cascade | Jeff Spence |  | 460600 | 348674.2 | 348674.2 | 390957.28 | 390957.28 | 0 | 295973.9 | 94983.38 | 75.7% | 75.7% | 164626.1 | 35.74% | 0 | 0 | 0
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Jeff Spence | 08/07/2026 | 175300 | 175300 | 175300 | 93481.01 | 71376.84 | 22104.17 | 112759.17 | -19278.16 | 100% | 120.6% | 62540.83 | 35.68% | 0 | 0 | 0
23-PC-31944 | Phase I: Goldfinch Airport Apron Class III Survey | Final Billing/Invoice | Fixed fee | Cascade | Preston Duarte |  | 76000 | 76000 | 76000 | 54636.4 | 54636.4 | 0 | 67585.21 | -12948.81 | 100% | 123.7% | 8414.79 | 11.07% | 0 | 0 | 0
23-PC-31976 | Foxglove Cell Tower GIS Mapping | Completed | Time and material | Chesapeake | Jason Oconnor |  | 72100 | 49028 | 49028 | 51263.1 | 51263.1 | 0 | 37578.85 | 13684.25 | 68% | 73.31% | 34521.15 | 47.88% | 0 | 0 | 0
23-PC-32015 | Copper Flats Harbor Dredging - Class III Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor |  | 89300 | 40524.34 | 40524.34 | 65024.25 | 59234.48 | 5789.77 | 29508.22 | 35516.03 | 45.4% | 45.38% | 59791.78 | 66.96% | 0 | 0 | 0
23-PC-32135 | Sage Flat Levee Repair Architectural History Survey | Final Billing/Invoice | Fixed fee | Chesapeake | Bryan Mann |  | 171600 | 171600 | 171600 | 128744.02 | 105103.15 | 23640.87 | 90120.81 | 38623.21 | 100% | 70% | 81479.19 | 47.48% | 0 | 0 | 51480
23-PC-32278 | Coyote Springs Highway Widening Paleontological Monitoring | Lab/Curation | Time and material | Chesapeake | Ian Maddox |  | 3500 | 2380 | 2380 | 2281.3 | 2281.3 | 0 | 1738.97 | 542.33 | 68% | 76.23% | 1761.03 | 50.32% | 0 | 0 | 0
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 08/14/2026 | 149100 | 132892.83 | 132892.83 | 111109.32 | 111109.32 | 0 | 99032.78 | 12076.54 | 89.1% | 89.13% | 50067.22 | 33.58% | 566.34 | 0 | 760.41
23-PC-32443 | Tamarack Battery Storage - Cultural Resources Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann |  | 152600 | 117078.5 | 117078.5 | 107415.14 | 107415.14 | 0 | 63511.77 | 43903.37 | 76.7% | 59.13% | 89088.23 | 58.38% | 7800.54 | 0 | 13310.5
23-PC-32474 | Slate Ridge Cell Tower - Phase I Survey | Completed | Fixed fee | Chesapeake | Ian Maddox |  | 52900 | 52900 | 52900 | 42882.38 | 39826.28 | 3056.1 | 44741.34 | -1858.96 | 100% | 104.3% | 8158.66 | 15.42% | 0 | 0 | 0
23-PC-32520 | Tamarack Battery Storage GIS Mapping | Lab/Curation | Time and material | Chesapeake | Ian Maddox |  | 1116300 | 759084 | 759084 | 767567.88 | 767567.88 | 0 | 601405.25 | 166162.63 | 68% | 78.35% | 514894.75 | 46.13% | 0 | 0 | 0
23-PC-32635 | Rushgrass Draw Curation | Cost Tracking on Closed Project | Time and material | Chesapeake | Jason Oconnor | 08/07/2026 | 36800 | 25024 | 25024 | 24644.96 | 24644.96 | 0 | 27323.95 | -2678.99 | 68% | 110.9% | 9476.05 | 25.75% | 0 | 0 | 0
23-PC-33001 | Heron Marsh Environmental Review Support | In Progress | Time and material | Front Range | Dean Velazquez |  | 356400 | 242352 | 242352 | 221573.88 | 221573.88 | 0 | 127558.9 | 94014.98 | 68% | 57.57% | 228841.1 | 64.21% | 0 | 0 | 0
23-PC-33043 | Phase II: Copper Flats Fiber Route Data Recovery | Completed | Fixed fee | Front Range | Reginald Vargas |  | 508800 | 508800 | 508800 | 282312.26 | 244330.7 | 37981.56 | 340194.25 | -57881.99 | 100% | 120.5% | 168605.75 | 33.14% | 0 | 0 | 0
23-PC-33070 | Meadowlark Curation | In Progress | Fixed fee | Front Range | Reginald Vargas |  | 55100 | 46377.67 | 46377.67 | 34299.75 | 34299.75 | 0 | 28871.53 | 5428.22 | 84.2% | 84.17% | 26228.47 | 47.6% | 0 | 0 | 0
23-PC-33151 | Sandpiper Class III Survey | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 08/28/2026 | 637100 | 540961.61 | 540961.61 | 497638.81 | 497638.81 | 0 | 422546.87 | 75091.94 | 84.9% | 84.91% | 214553.13 | 33.68% | 0 | 0 | 0
23-PC-33193 | Falcon Mesa Transmission Line - Environmental Review Support | On Hold | Fixed fee | Front Range | Devon Pitts |  | 10900 | 7656.16 | 7656.16 | 8531.43 | 8531.43 | 0 | 5992.26 | 2539.17 | 70.2% | 70.24% | 4907.74 | 45.03% | 0 | 0 | 0
23-PC-33218 | Plover Cove Class III Survey | On Hold | Time and material | Front Range | Jeremy Tran |  | 57000 | 38760 | 38760 | 36256.05 | 27900.6 | 8355.45 | 29341.56 | 6914.49 | 68% | 80.93% | 27658.44 | 48.52% | 0 | 0 | 0
23-PC-33299 | Fern Valley Fiber Route - Curation | On Hold | Fixed fee | Front Range | Reginald Vargas |  | 71300 | 55927.72 | 55927.72 | 47214.86 | 47214.86 | 0 | 37033.01 | 10181.85 | 78.4% | 78.44% | 34266.99 | 48.06% | 0 | 0 | 0
23-PC-33395 | Lone Pine Environmental Review Support | Final Billing/Invoice | Time and material | Front Range | Jeremy Tran |  | 186900 | 127092 | 127092 | 122438.19 | 122438.19 | 0 | 159169.65 | -36731.46 | 68% | 130% | 27730.35 | 14.84% | 0 | 0 | 0
23-PC-33428 | Hackberry Bend Archaeological Testing | Final Billing/Invoice | Fixed fee | Front Range | Reginald Vargas |  | 293900 | 293900 | 293900 | 208874.73 | 208874.73 | 0 | 271537.15 | -62662.42 | 100% | 130% | 22362.85 | 7.61% | 0 | 0 | 0
23-PC-33471 | Sandpiper Park Improvements - Environmental Review Support | Lab/Curation | Time and material | Front Range | Devon Pitts |  | 113200 | 76976 | 76976 | 80813.48 | 80813.48 | 0 | 61581.06 | 19232.42 | 68% | 76.2% | 51618.94 | 45.6% | 0 | 0 | 0
23-PC-33551 | Heron Marsh Airport Apron GIS Mapping | Final Reporting/Review | Time and material | Front Range | Reginald Vargas | 08/21/2026 | 95400 | 64872 | 64872 | 62019.54 | 62019.54 | 0 | 47726 | 14293.54 | 68% | 76.95% | 47674 | 49.97% | 0 | 0 | 0
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | In Progress | Fixed fee | Front Range | Kimberly Daugherty |  | 21600 | 21600 | 21600 | 15245.28 | 15245.28 | 0 | 16551.79 | -1306.51 | 100% | 108.6% | 5048.21 | 23.37% | 0 | 0 | 0
23-PC-33605 | Rushgrass Draw Highway Widening - Class III Survey | Completed | Fixed fee | Front Range | Kimberly Daugherty |  | 309100 | 309100 | 309100 | 188427.36 | 188427.36 | 0 | 187603 | 824.36 | 100% | 99.56% | 121497 | 39.31% | 0 | 0 | 1360.04
23-PC-33695 | On-Call: Windmill Flat Highway Widening Phase I Survey | On Hold | Fixed fee | Great Lakes | Jeff Pugh |  | 42600 | 23749.5 | 23749.5 | 34191.4 | 27729 | 6462.4 | 19060.38 | 15131.02 | 55.7% | 55.75% | 23539.62 | 55.26% | 0 | 0 | 0
23-PC-33803 | Willow Springs Pipeline Cultural Resources Assessment | On Hold | Time and material | Great Lakes | Brendan Padilla |  | 66400 | 45152 | 45152 | 40244.88 | 34873.88 | 5371 | 20144.95 | 20099.93 | 68% | 50.06% | 46255.05 | 69.66% | 0 | 0 | 0
23-PC-33858 | Phase II: Cedar Hollow Pipeline Section 106 Consultation | Final Billing/Invoice | Fixed fee | Great Lakes | Jeff Pugh |  | 68500 | 68500 | 68500 | 46737.55 | 46737.55 | 0 | 44645.58 | 2091.97 | 100% | 95.52% | 23854.42 | 34.82% | 0 | 0 | 3068.8
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | In Progress | Time and material | Great Lakes | Jeff Pugh |  | 300600 | 204408 | 204408 | 219257.64 | 219257.64 | 0 | 176674.59 | 42583.05 | 68% | 80.58% | 123925.41 | 41.23% | 0 | 0 | 0
23-PC-33998 | Phase II: Granite Pass Reservoir Class III Survey | In Progress | Time and material | Great Lakes | Nathan Lambert |  | 238800 | 162384 | 162384 | 156891.6 | 156891.6 | 0 | 95556.7 | 61334.9 | 68% | 60.91% | 143243.3 | 59.98% | 0 | 0 | 0
23-PC-34054 | Slate Ridge Wastewater Plant - Maritime Remote Sensing Survey | Final Billing/Invoice | Time and material | Great Lakes | Angelica Cervantes |  | 99000 | 67320 | 67320 | 67052.7 | 67052.7 | 0 | 66496.14 | 556.56 | 68% | 99.17% | 32503.86 | 32.83% | 0 | 0 | 0
23-PC-34135 | Falcon Mesa Architectural History Survey | Completed | Fixed fee | Great Lakes | Kathleen Galvan |  | 108800 | 108800 | 108800 | 84537.6 | 84537.6 | 0 | 97602.11 | -13064.51 | 100% | 115.5% | 11197.89 | 10.29% | 0 | 0 | 0
23-PC-34171 | Timber Gap Rail Siding - Built Environment Survey | In Progress | Time and material | Great Lakes | Jeff Pugh |  | 221100 | 150348 | 150348 | 154858.44 | 154858.44 | 0 | 75735.59 | 79122.85 | 68% | 48.91% | 145364.41 | 65.75% | 0 | 0 | 0
23-PC-34229 | Creosote Draw Mixed-Use Development Paleontological Monitoring | In Progress | Time and material | Great Lakes | Jeff Pugh | 09/04/2026 | 48800 | 33184 | 33184 | 34427.85 | 31880.18 | 2547.67 | 25157.23 | 9270.62 | 68% | 73.07% | 23642.77 | 48.45% | 0 | 0 | 0
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | In Progress | Time and material | Great Lakes | Kathleen Galvan | 08/07/2026 | 373100 | 253708 | 253708 | 247626.47 | 247626.47 | 0 | 184659.6 | 62966.87 | 68% | 74.57% | 188440.4 | 50.51% | 0 | 0 | 0
23-PC-34403 | Plover Cove Built Environment Survey | In Progress | Time and material | Great Lakes | Kathleen Galvan | 09/11/2026 | 46200 | 31416 | 31416 | 30187.08 | 30187.08 | 0 | 23628.2 | 6558.88 | 68% | 78.27% | 22571.8 | 48.86% | 0 | 0 | 0
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes |  | 477000 | 347303.7 | 347303.7 | 333756.9 | 333756.9 | 0 | 243019.93 | 90736.97 | 72.8% | 72.81% | 233980.07 | 49.05% | 0 | 0 | 0
23-PC-34473 | Aspen Ridge Cell Tower Phase I Survey | In Progress | Time and material | Great Lakes | Leonard Mejia |  | 52300 | 35564 | 35564 | 36353.73 | 36353.73 | 0 | 23508.92 | 12844.81 | 68% | 64.67% | 28791.08 | 55.05% | 0 | 0 | 0
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Final Reporting/Review | Time and material | Great Lakes | Geoffrey Fernandez | 09/11/2026 | 70000 | 47600 | 47600 | 50246 | 50246 | 0 | 45814.41 | 4431.59 | 68% | 91.18% | 24185.59 | 34.55% | 0 | 0 | 0
23-PC-34522 | Foxglove GIS Mapping | In Progress | Time and material | Great Lakes | Brendan Padilla |  | 192200 | 130696 | 130696 | 131503.24 | 131503.24 | 0 | 75113.75 | 56389.49 | 68% | 57.12% | 117086.25 | 60.92% | 0 | 0 | 0
23-PC-34567 | Foxglove School Campus Phase II Testing | On Hold | Fixed fee | Great Lakes | Brendan Padilla |  | 17900 | 9055.61 | 9055.61 | 14103.41 | 14103.41 | 0 | 7134.41 | 6969 | 50.6% | 50.59% | 10765.59 | 60.14% | 0 | 0 | 0
23-PC-34745 | Slate Ridge Battery Storage Environmental Review Support | In Progress | Fixed fee | Great Lakes | Robin Mercado |  | 614200 | 408504.42 | 408504.42 | 440258.56 | 440258.56 | 0 | 292800.8 | 147457.76 | 66.5% | 66.51% | 321399.2 | 52.33% | 0 | 0 | 0
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Sean Jennings |  | 46100 | 32472.84 | 32472.84 | 31721.41 | 31721.41 | 0 | 22343.25 | 9378.16 | 70.4% | 70.44% | 23756.75 | 51.53% | 0 | 0 | 0
23-PC-34811 | Task Order 2: Saltgrass Airport Apron Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Gulf Coast West | Courtney Daugherty | 09/18/2026 | 112600 | 92917.52 | 92917.52 | 80883.68 | 67188.42 | 13695.26 | 66744.54 | 14139.14 | 82.5% | 82.52% | 45855.46 | 40.72% | 0 | 0 | 0
23-PC-34826 | Task Order 13: Foxglove Canal Lining Cultural Resources Monitoring | In Progress | Time and material | Gulf Coast East | Bernard Erickson |  | 168500 | 114580 | 114580 | 109642.95 | 109642.95 | 0 | 61763.3 | 47879.65 | 68% | 56.33% | 106736.7 | 63.35% | 0 | 0 | 0
23-PC-34891 | Saltgrass GIS Mapping | Final Billing/Invoice | Fixed fee | Gulf Coast West | Bernard Erickson |  | 26600 | 26600 | 26600 | 20891.64 | 20891.64 | 0 | 16379.36 | 4512.28 | 100% | 78.4% | 10220.64 | 38.42% | 0 | 0 | 5745.6
23-PC-34902 | Sumac Ridge Built Environment Survey | Final Reporting/Review | Time and material | Gulf Coast | Sean Jennings |  | 37000 | 25160 | 25160 | 26270 | 26270 | 0 | 17779.33 | 8490.67 | 68% | 67.68% | 19220.67 | 51.95% | 0 | 0 | 0
23-PC-34939 | Maple Fork Maritime Remote Sensing Survey | In Progress | Time and material | Gulf Coast West | Bernard Erickson |  | 145800 | 99144 | 99144 | 104172.04 | 89950 | 14222.04 | 74711.94 | 29460.1 | 68% | 71.72% | 71088.06 | 48.76% | 0 | 0 | 0
23-PC-34947 | Aspen Ridge Cell Tower Architectural History Survey | In Progress | Fixed fee | Gulf Coast West | Wyatt Erickson |  | 285900 | 192753.78 | 192753.78 | 199615.38 | 199615.38 | 0 | 134588.76 | 65026.62 | 67.4% | 67.42% | 151311.24 | 52.92% | 0 | 0 | 0
23-PC-35003 | Creosote Draw Archaeological Testing | In Progress | Time and material | Gulf Coast West | Bernard Erickson |  | 187900 | 127772 | 127772 | 127170.72 | 127170.72 | 0 | 85671.58 | 41499.14 | 68% | 67.37% | 102228.42 | 54.41% | 0 | 0 | 0
23-PC-35098 | On-Call: Larkspur Reservoir Environmental Review Support | Final Billing/Invoice | Fixed fee | Gulf Coast East | Sean Jennings |  | 120000 | 120000 | 120000 | 100560 | 100560 | 0 | 92975.9 | 7584.1 | 100% | 92.46% | 27024.1 | 22.52% | 0 | 0 | 9048
23-PC-35126 | Falcon Mesa Rail Siding Built Environment Survey | In Progress | Time and material | Gulf Coast West | Wyatt Erickson |  | 273100 | 185708 | 185708 | 197014.34 | 197014.34 | 0 | 105573.3 | 91441.04 | 68% | 53.59% | 167526.7 | 61.34% | 0 | 0 | 0
23-PC-35176 | Plover Cove Mine Expansion Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Bernard Erickson |  | 74700 | 49496.22 | 49496.22 | 53388.09 | 53388.09 | 0 | 35373.34 | 18014.75 | 66.3% | 66.26% | 39326.66 | 52.65% | 0 | 0 | 0
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | In Progress | Fixed fee | Gulf Coast East | Wyatt Erickson | 08/28/2026 | 407900 | 303355.23 | 303355.23 | 321139.67 | 321139.67 | 0 | 238828.33 | 82311.34 | 74.4% | 74.37% | 169071.67 | 41.45% | 0 | 0 | 0
23-PC-35425 | Yarrow Point Trail - GIS Mapping | Lab/Curation | Time and material | High Desert | Eileen Poole |  | 24000 | 16320 | 16320 | 15998.4 | 15998.4 | 0 | 13187.18 | 2811.22 | 68% | 82.43% | 10812.82 | 45.05% | 0 | 0 | 0
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | In Progress | Time and material | High Desert | Jody Wang |  | 116200 | 79016 | 79016 | 87219.72 | 87219.72 | 0 | 78190.34 | 9029.38 | 68% | 89.65% | 38009.66 | 32.71% | 0 | 0 | 0
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | In Progress | Fixed fee | High Desert | Eileen Poole | 09/11/2026 | 11400 | 8681.1 | 8681.1 | 8206.86 | 8206.86 | 0 | 6249.46 | 1957.4 | 76.2% | 76.15% | 5150.54 | 45.18% | 0 | 0 | 0
23-PC-35568 | Phase II: Coyote Springs Wind Farm Environmental Review Support | In Progress | Fixed fee | High Desert | Bridget Maddox |  | 253600 | 144374.48 | 144374.48 | 168365.04 | 168365.04 | 0 | 95853.64 | 72511.4 | 56.9% | 56.93% | 157746.36 | 62.2% | 0 | 0 | 0
23-PC-35682 | Lantern Bay Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 07/31/2026 | 290400 | 277361.04 | 277361.04 | 252938.4 | 252938.4 | 0 | 241578.4 | 11360 | 95.5% | 95.51% | 48821.6 | 16.81% | 0 | 0 | 0
23-PC-35715 | Saltgrass Cell Tower Historic Resources Evaluation | On Hold | Fixed fee | High Desert | Jody Wang |  | 44500 | 37068.5 | 37068.5 | 33802.2 | 33802.2 | 0 | 28157.72 | 5644.48 | 83.3% | 83.3% | 16342.28 | 36.72% | 0 | 0 | 0
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 08/21/2026 | 114600 | 104870.46 | 104870.46 | 77893.62 | 77893.62 | 0 | 71277.07 | 6616.55 | 91.5% | 91.51% | 43322.93 | 37.8% | 0 | 0 | 0
23-PC-36108 | Pebble Beach Road Maritime Remote Sensing Survey | On Hold | Fixed fee | High Desert | Jody Wang |  | 50200 | 32941.24 | 32941.24 | 40154.98 | 40154.98 | 0 | 26350.13 | 13804.85 | 65.6% | 65.62% | 23849.87 | 47.51% | 0 | 0 | 0
23-PC-36231 | Phase II: Rushgrass Draw Airport Apron GIS Mapping | Final Billing/Invoice | Time and material | Island | Briana Melton |  | 436500 | 296820 | 296820 | 298453.59 | 253244.6 | 45208.99 | 384508.62 | -86055.03 | 68% | 128.8% | 51991.38 | 11.91% | 0 | 0 | 0
23-PC-36385 | On-Call: Cedar Hollow Transmission Line Paleontological Monitoring | In Progress | Time and material | Island | Maurice Dodson | 08/28/2026 | 392900 | 267172 | 267172 | 262008.61 | 207890.28 | 54118.33 | 185677.7 | 76330.91 | 68% | 70.87% | 207222.3 | 52.74% | 0 | 0 | 0
23-PC-36422 | Hawk Point Phase I Survey | In Progress | Time and material | Island | Joan Mathis |  | 50700 | 34476 | 34476 | 36579.06 | 32790.93 | 3788.13 | 37409.59 | -830.53 | 68% | 102.3% | 13290.41 | 26.21% | 0 | 0 | 0
23-PC-36426 | On-Call: Fern Valley Wastewater Plant Environmental Review Support | Final Billing/Invoice | Fixed fee | Island | Maurice Dodson |  | 76300 | 76300 | 76300 | 52730.93 | 52730.93 | 0 | 51196.02 | 1534.91 | 100% | 97.09% | 25103.98 | 32.9% | 0 | 0 | 2220.33
23-PC-36530 | Lone Pine Architectural History Survey | In Progress | Time and material | Island | Joan Mathis | 09/11/2026 | 141100 | 95948 | 95948 | 102823.29 | 89657.45 | 13165.84 | 97024.26 | 5799.03 | 68% | 94.36% | 44075.74 | 31.24% | 0 | 0 | 0
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 09/04/2026 | 201000 | 170226.9 | 170226.9 | 151513.8 | 151513.8 | 0 | 128322.24 | 23191.56 | 84.7% | 84.69% | 72677.76 | 36.16% | 0 | 0 | 0
23-PC-36734 | Raven Rock Curation | In Progress | Fixed fee | Lakeshore | Terrence Gillespie | 08/21/2026 | 38600 | 36284 | 36284 | 27753.4 | 27753.4 | 0 | 26089.14 | 1664.26 | 94% | 94% | 12510.86 | 32.41% | 9057.72 | 0 | 12595.18
23-PC-36776 | On-Call: Twin Buttes Trail Phase I Survey | In Progress | Time and material | Hill Country | Danielle Villanueva |  | 457300 | 310964 | 310964 | 338564.86 | 268622.72 | 69942.14 | 214892.1 | 123672.76 | 68% | 63.47% | 242407.9 | 53.01% | 0 | 0 | 0
23-PC-37105 | Foxglove Housing Development - Data Recovery | In Progress | Fixed fee | Hill Country | Theresa Fernandez |  | 110800 | 82955.96 | 82955.96 | 80165.21 | 73023.16 | 7142.05 | 60019.34 | 20145.87 | 74.9% | 74.87% | 50780.66 | 45.83% | 19055.96 | 0 | 26337.16
23-PC-37245 | Rushgrass Draw Wind Farm Archaeological Testing | In Progress | Fixed fee | Hill Country | Gail Meza |  | 425700 | 238392 | 238392 | 306248.58 | 306248.58 | 0 | 171495.1 | 134753.48 | 56% | 56% | 254204.9 | 59.71% | 2115.65 | 0 | 2937.33
23-PC-37301 | Coyote Springs Highway Widening Cultural Resources Monitoring | Final Billing/Invoice | Fixed fee | Hill Country | Glen Delacruz |  | 71900 | 71900 | 71900 | 50775.78 | 50775.78 | 0 | 52725.53 | -1949.75 | 100% | 103.8% | 19174.47 | 26.67% | 0 | 0 | 0
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | In Progress | Fixed fee | Piedmont - Inactive | Maria Parrish | 09/18/2026 | 44500 | 31902.05 | 31902.05 | 35070.45 | 35070.45 | 0 | 25141.75 | 9928.7 | 71.7% | 71.69% | 19358.25 | 43.5% | 0 | 0 | 0
23-PC-37590 | On-Call: Rushgrass Draw Water Main Environmental Review Support | In Progress | Fixed fee | PIEDMONT - INACTIVE | Annette Vaughan |  | 46500 | 28425.45 | 28425.45 | 36232.8 | 36232.8 | 0 | 22148.93 | 14083.87 | 61.1% | 61.13% | 24351.07 | 52.37% | 0 | 0 | 0
23-PC-37642 | Quail Run Solar Curation | Final Billing/Invoice | Fixed fee | PIEDMONT - INACTIVE | Megan Pineda |  | 286500 | 286500 | 286500 | 185422.8 | 185422.8 | 0 | 174327.06 | 11095.74 | 100% | 94.02% | 112172.94 | 39.15% | 0 | 0 | 17132.7
23-PC-37648 | Phase III: Thistle Down Mixed-Use Development Phase I Survey | Final Billing/Invoice | Time and material | PIEDMONT - INACTIVE | Annette Vaughan |  | 49100 | 33388 | 33388 | 32995.2 | 32995.2 | 0 | 28734.29 | 4260.91 | 68% | 87.09% | 20365.71 | 41.48% | 0 | 0 | 0
23-PC-37740 | Sandpiper Trail Archaeological Testing | Final Billing/Invoice | Fixed fee | PIEDMONT - INACTIVE | Megan Pineda |  | 33900 | 33900 | 33900 | 20068.8 | 20068.8 | 0 | 14048.16 | 6020.64 | 100% | 70% | 19851.84 | 58.56% | 0 | 0 | 10170
23-PC-37763 | Bramble Creek School Campus - Environmental Review Support | In Progress | Time and material | PIEDMONT - INACTIVE | Megan Pineda |  | 35000 | 23800 | 23800 | 25056.5 | 25056.5 | 0 | 15144.42 | 9912.08 | 68% | 60.44% | 19855.58 | 56.73% | 0 | 0 | 0
23-PC-38089 | Lone Pine Wastewater Plant - Phase I Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 110100 | 75132.24 | 75132.24 | 84001.75 | 72763.92 | 11237.83 | 57321.44 | 26680.31 | 68.2% | 68.24% | 52778.56 | 47.94% | 0 | 0 | 0
23-PC-38159 | Badger Hollow Data Recovery | Completed | Time and material | Prairie | Sherry Lloyd |  | 8000 | 5440 | 5440 | 5319.2 | 5319.2 | 0 | 6409.99 | -1090.79 | 68% | 120.5% | 1590.01 | 19.88% | 0 | 0 | 0
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | In Progress | Time and material | Prairie | Sherry Lloyd | 08/07/2026 | 128200 | 87176 | 87176 | 90073.32 | 90073.32 | 0 | 73724.08 | 16349.24 | 68% | 81.85% | 54475.92 | 42.49% | 0 | 0 | 0
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 79800 | 57918.84 | 57918.84 | 53434.08 | 53434.08 | 0 | 38783.48 | 14650.6 | 72.6% | 72.58% | 41016.52 | 51.4% | 0 | 0 | 0
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | In Progress | Fixed fee | Red Rock | Shelia Horne |  | 67700 | 56556.58 | 56556.58 | 44688.77 | 44688.77 | 0 | 37332.05 | 7356.72 | 83.5% | 83.54% | 30367.95 | 44.86% | 0 | 0 | 0
23-PC-38520 | On-Call: Larkspur Park Improvements Built Environment Survey | In Progress | Time and material | Red Rock | Marisa Odom |  | 148500 | 100980 | 100980 | 97074.45 | 97074.45 | 0 | 56211.48 | 40862.97 | 68% | 57.91% | 92288.52 | 62.15% | 0 | 0 | 0
23-PC-38666 | Tamarack Paleontological Monitoring | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 390300 | 212479.32 | 212479.32 | 243898.47 | 243898.47 | 0 | 132781.77 | 111116.7 | 54.4% | 54.44% | 257518.23 | 65.98% | 0 | 0 | 0
23-PC-38759 | Saltgrass Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Red Rock | Tina Aguirre | 08/28/2026 | 52400 | 35632 | 35632 | 36847.68 | 36847.68 | 0 | 40372.44 | -3524.76 | 68% | 109.6% | 12027.56 | 22.95% | 0 | 0 | 0
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | In Progress | Fixed fee | Red Rock | Tina Aguirre | 09/11/2026 | 109400 | 86962.06 | 86962.06 | 83089.3 | 83089.3 | 0 | 66048.24 | 17041.06 | 79.5% | 79.49% | 43351.76 | 39.63% | 0 | 0 | 0
23-PC-39011 | Fern Valley Solar Curation | Final Billing/Invoice | Time and material | Red Rock | Tina Aguirre |  | 189300 | 128724 | 128724 | 142126.44 | 142126.44 | 0 | 140658.85 | 1467.59 | 68% | 98.97% | 48641.15 | 25.7% | 0 | 0 | 0
23-PC-39063 | Task Order 21: Badger Hollow Substation Historic Resources Evaluation | Lab/Curation | Time and material | Red Rock | Lydia Cisneros |  | 24200 | 16456 | 16456 | 17235.24 | 17235.24 | 0 | 12296.83 | 4938.41 | 68% | 71.35% | 11903.17 | 49.19% | 0 | 0 | 0
23-PC-39111 | On-Call: Sage Flat Housing Development Section 106 Consultation | Final Billing/Invoice | Time and material | Red Rock | Marisa Odom |  | 414500 | 281860 | 281860 | 281113.9 | 281113.9 | 0 | 292132.6 | -11018.7 | 68% | 103.9% | 122367.4 | 29.52% | 0 | 0 | 0
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | In Progress | Fixed fee | Red Rock | Jeanette Chung | 08/21/2026 | 27800 | 20777.72 | 20777.72 | 18214.56 | 18214.56 | 0 | 13614.39 | 4600.17 | 74.7% | 74.74% | 14185.61 | 51.03% | 0 | 0 | 0
23-PC-39280 | Eagle Bend Architectural History Survey | Final Billing/Invoice | Fixed fee | Red Rock | Javier Newman |  | 122700 | 122700 | 122700 | 84258.09 | 84258.09 | 0 | 74439.03 | 9819.06 | 100% | 88.35% | 48260.97 | 39.33% | 0 | 0 | 14294.55
23-PC-39323 | Silver Lake Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre |  | 550600 | 423136.1 | 423136.1 | 444994.92 | 444994.92 | 0 | 341994.21 | 103000.71 | 76.8% | 76.85% | 208605.79 | 37.89% | 0 | 0 | 0
23-PC-39502 | Ember Valley Housing Development - Phase II Testing | Final Billing/Invoice | Time and material | Red Rock | Marisa Odom |  | 352700 | 239836 | 239836 | 238918.98 | 238918.98 | 0 | 310594.67 | -71675.69 | 68% | 130% | 42105.33 | 11.94% | 0 | 0 | 0
23-PC-39608 | Tansy Flat Historic Resources Evaluation | Completed | Time and material | Red Rock | Bruce Suarez |  | 166700 | 113356 | 113356 | 118140.29 | 118140.29 | 0 | 100389.47 | 17750.82 | 68% | 84.97% | 66310.53 | 39.78% | 0 | 0 | 0
23-PC-39840 | Kestrel Butte Cell Tower - Curation | In Progress | Time and material | Red Rock | Bruce Suarez |  | 237700 | 164750.75 | 164750.75 | 173575 | 132634.88 | 40940.12 | 88754.16 | 84820.84 | 69.3% | 51.13% | 148945.84 | 62.66% | 2036.55 | 0 | 3114.75
23-PC-39856 | Phase II: Thistle Down Transmission Line Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez |  | 91300 | 46718.21 | 46718.21 | 72285.79 | 62922.2 | 9363.59 | 36987.95 | 35297.84 | 51.2% | 51.17% | 54312.05 | 59.49% | 0 | 0 | 0
23-PC-39857 | Copper Flats Highway Widening - Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 69000 | 40358.1 | 40358.1 | 58157.02 | 42210.52 | 15946.5 | 34016 | 24141.02 | 58.5% | 58.49% | 34984 | 50.7% | 0 | 0 | 0
23-PC-39918 | Elk Meadow Transmission Line - Data Recovery | Completed | Time and material | Red Rock | Javier Newman |  | 75300 | 51204 | 51204 | 51437.43 | 51437.43 | 0 | 50643.39 | 794.04 | 68% | 98.46% | 24656.61 | 32.74% | 0 | 0 | 0
23-PC-39996 | Plover Cove Trail - Data Recovery | On Hold | Fixed fee | Red Rock | Bruce Suarez |  | 611900 | 397000.72 | 397000.72 | 419273.88 | 419273.88 | 0 | 272035.22 | 147238.66 | 64.9% | 64.88% | 339864.78 | 55.54% | 0 | 0 | 0
23-PC-40028 | Phase II: Sumac Ridge Mixed-Use Development Section 106 Consultation | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 100900 | 67905.7 | 67905.7 | 70256.67 | 70256.67 | 0 | 47284.49 | 22972.18 | 67.3% | 67.3% | 53615.51 | 53.14% | 0 | 0 | 0
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | In Progress | Time and material | Red Rock | Javier Newman | 09/11/2026 | 119500 | 103480.5 | 103480.5 | 80196.45 | 80196.45 | 0 | 70430.41 | 9766.04 | 86.6% | 87.82% | 49069.59 | 41.06% | 15959.94 | 0 | 22220.5
23-PC-40150 | Juniper Wash Curation | In Progress | Time and material | Sierra North | Benjamin Mathis |  | 114700 | 90325.75 | 90325.75 | 73316.24 | 73316.24 | 0 | 47860.76 | 25455.48 | 78.7% | 65.28% | 66839.24 | 58.27% | 7996.31 | 0 | 12329.75
23-PC-40387 | Copper Flats Trail Paleontological Monitoring | Lab/Curation | Fixed fee | Sierra North | Louis Huff |  | 145000 | 82244 | 82244 | 97266 | 97266 | 0 | 55173.29 | 42092.71 | 56.7% | 56.72% | 89826.71 | 61.95% | 0 | 0 | 0
23-PC-40402 | Pebble Beach Road Architectural History Survey | In Progress | Fixed fee | Sierra North | Louis Huff | 08/28/2026 | 411600 | 333190.2 | 333190.2 | 302937.6 | 302937.6 | 0 | 245232.54 | 57705.06 | 80.9% | 80.95% | 166367.46 | 40.42% | 0 | 0 | 0
23-PC-40406 | Maple Fork Airport Apron Environmental Review Support | In Progress | Time and material | Sierra | Louis Huff | 09/11/2026 | 60100 | 40868 | 40868 | 40631.14 | 34425.27 | 6205.87 | 33352.18 | 7278.96 | 68% | 82.09% | 26747.82 | 44.51% | 0 | 0 | 0
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | In Progress | Fixed fee | Sierra South | Benjamin Mathis |  | 53900 | 38516.94 | 38516.94 | 40910.1 | 40910.1 | 0 | 29233.55 | 11676.55 | 71.5% | 71.46% | 24666.45 | 45.76% | 0 | 0 | 0
23-PC-40493 | Phase III: Quail Run Rail Siding Phase I Survey | In Progress | Fixed fee | Sierra | Benjamin Mathis |  | 84700 | 53513.46 | 53513.46 | 57130.15 | 57130.15 | 0 | 36092.25 | 21037.9 | 63.2% | 63.18% | 48607.75 | 57.39% | 0 | 0 | 0
23-PC-40519 | Windmill Flat Mixed-Use Development - Class III Survey | In Progress | Fixed fee | Sierra South | Donna Herring | 08/28/2026 | 194700 | 140203.47 | 140203.47 | 157875.18 | 136847.52 | 21027.66 | 113693.31 | 44181.87 | 72% | 72.01% | 81006.69 | 41.61% | 0 | 0 | 0
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Lab/Curation | Fixed fee | Sierra | Louis Huff | 09/11/2026 | 76500 | 76500 | 76500 | 58746.94 | 55119.6 | 3627.34 | 63236.56 | -4489.62 | 100% | 107.6% | 13263.44 | 17.34% | 0 | 0 | 0
23-PC-40627 | Ember Valley Solar - Phase I Survey | In Progress | Fixed fee | Sierra | Louis Huff |  | 71300 | 44163.22 | 44163.22 | 38273.84 | 38273.84 | 0 | 23707.44 | 14566.4 | 61.9% | 61.94% | 47592.56 | 66.75% | 0 | 0 | 0
23-PC-40688 | Sparrow Hill Historic Resources Evaluation | On Hold | Time and material | Coastal Bend | Jared Choi |  | 70500 | 47940 | 47940 | 43731.15 | 43731.15 | 0 | 29728.69 | 14002.46 | 68% | 67.98% | 40771.31 | 57.83% | 0 | 0 | 0
23-PC-40963 | Wildrye Archaeological Testing | On Hold | Fixed fee | Coastal Bend | Diane Daniels |  | 58000 | 40507.2 | 40507.2 | 34689.8 | 34689.8 | 0 | 24226.81 | 10462.99 | 69.8% | 69.84% | 33773.19 | 58.23% | 0 | 0 | 0
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | In Progress | Time and material | Coastal Bend | Steve Rubio |  | 56300 | 38284 | 38284 | 42714.81 | 42714.81 | 0 | 47948.89 | -5234.08 | 68% | 112.2% | 8351.11 | 14.83% | 0 | 0 | 0
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 09/11/2026 | 33100 | 24874.65 | 24874.65 | 29128 | 29128 | 0 | 21890.46 | 7237.54 | 75.1% | 75.15% | 11209.54 | 33.87% | 0 | 0 | 0
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 09/18/2026 | 349600 | 349600 | 349600 | 221087.04 | 221087.04 | 0 | 229204.35 | -8117.31 | 100% | 103.7% | 120395.65 | 34.44% | 0 | 0 | 0
23-PC-41314 | Raven Rock Transmission Line - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi |  | 38800 | 28161.04 | 28161.04 | 29503.45 | 22168.08 | 7335.37 | 21412.36 | 8091.09 | 72.6% | 72.58% | 17387.64 | 44.81% | 0 | 0 | 0
23-PC-41361 | Juniper Wash Substation - Cultural Resources Assessment | Final Billing/Invoice | Time and material | Coastal Bend | Alexis Nixon |  | 240700 | 163676 | 163676 | 180645.35 | 180645.35 | 0 | 201492.26 | -20846.91 | 68% | 111.5% | 39207.74 | 16.29% | 0 | 0 | 0
23-PC-41378 | Thistle Down Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Duane Ballard |  | 170800 | 95511.36 | 95511.36 | 91151.1 | 67330.2 | 23820.9 | 50973.67 | 40177.43 | 55.9% | 55.92% | 119826.33 | 70.16% | 0 | 0 | 0
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 07/31/2026 | 132000 | 92584.8 | 92584.8 | 108108 | 108108 | 0 | 75830.35 | 32277.65 | 70.1% | 70.14% | 56169.65 | 42.55% | 0 | 0 | 0
23-PC-41429 | Meadowlark Housing Development - Phase II Testing | In Progress | Time and material | Coastal Bend | Duane Ballard |  | 1924200 | 1308456 | 1308456 | 1334625.12 | 1334625.12 | 0 | 884955.35 | 449669.77 | 68% | 66.31% | 1039244.65 | 54.01% | 0 | 0 | 0
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Lab/Curation | Fixed fee | Coastal Bend | Alexis Nixon |  | 755000 | 705170 | 705170 | 444695 | 444695 | 0 | 415325.46 | 29369.54 | 93.4% | 93.4% | 339674.54 | 44.99% | 0 | 0 | 0
23-PC-41613 | Tamarack School Campus Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 09/04/2026 | 151900 | 128659.3 | 128659.3 | 105099.61 | 105099.61 | 0 | 89014.21 | 16085.4 | 84.7% | 84.7% | 62885.79 | 41.4% | 0 | 0 | 0
23-PC-41787 | Copper Flats Phase I Survey | Completed | Time and material | Built Environment | Rickey Salas |  | 48000 | 32640 | 32640 | 31929.6 | 31929.6 | 0 | 27473.21 | 4456.39 | 68% | 86.04% | 20526.79 | 42.76% | 0 | 0 | 0
23-PC-41802 | Plover Cove Paleontological Monitoring | In Progress | Fixed fee | Built Environment | Melody Holloway |  | 102400 | 67051.52 | 67051.52 | 66672.64 | 66672.64 | 0 | 43658.58 | 23014.06 | 65.5% | 65.48% | 58741.42 | 57.36% | 0 | 0 | 0
23-PC-41827 | Task Order 9: Dove Canyon Bridge Replacement Section 106 Consultation | In Progress | Fixed fee | Built Environment | Rickey Salas |  | 646100 | 375771.76 | 375771.76 | 414881.21 | 355093.99 | 59787.22 | 241290.96 | 173590.25 | 58.2% | 58.16% | 404809.04 | 62.65% | 0 | 0 | 0
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | In Progress | Time and material | Built Environment | Jesse Maynard |  | 18800 | 12784 | 12784 | 12705.04 | 12705.04 | 0 | 12736.47 | -31.43 | 68% | 100.2% | 6063.53 | 32.25% | 0 | 0 | 0
23-PC-41934 | Sea Oat Bridge Replacement - GIS Mapping | Final Reporting/Review | Fixed fee | Built Environment | Rickey Salas |  | 364700 | 208900.16 | 208900.16 | 228812.78 | 228812.78 | 0 | 131064.99 | 97747.79 | 57.3% | 57.28% | 233635.01 | 64.06% | 0 | 0 | 0
23-PC-42054 | Task Order 25: Meadowlark Water Main Curation | Completed | Time and material | Built Environment | Rickey Salas |  | 35600 | 24208 | 24208 | 24350.4 | 24350.4 | 0 | 23894.23 | 456.17 | 68% | 98.13% | 11705.77 | 32.88% | 0 | 0 | 0
23-PC-42154 | Task Order 25: Goldfinch School Campus Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Rickey Salas |  | 29200 | 19856 | 19856 | 20127.56 | 20127.56 | 0 | 12454.55 | 7673.01 | 68% | 61.88% | 16745.45 | 57.35% | 0 | 0 | 0
23-PC-42199 | Sandpiper Highway Widening GIS Mapping | Completed | Fixed fee | Built Environment | Rickey Salas |  | 270200 | 270200 | 270200 | 196621.63 | 146297.83 | 50323.8 | 186167.87 | 10453.76 | 100% | 94.68% | 84032.13 | 31.1% | 0 | 0 | 14374.64
23-PC-42237 | Foxglove Historic Resources Evaluation | In Progress | Time and material | Paleontology | Charlene Sparks |  | 82300 | 55964 | 55964 | 55519.51 | 46719.77 | 8799.74 | 30299.65 | 25219.86 | 68% | 54.57% | 52000.35 | 63.18% | 0 | 0 | 0
23-PC-42377 | Sumac Ridge Curation | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 68300 | 39088.09 | 39088.09 | 47215.79 | 47215.79 | 0 | 27022.26 | 20193.53 | 57.2% | 57.23% | 41277.74 | 60.44% | 0 | 0 | 0
23-PC-42405 | Task Order 23: Silver Lake Levee Repair Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Paleontology | Travis Delgado |  | 757500 | 757500 | 757500 | 494268.75 | 494268.75 | 0 | 636741.85 | -142473.1 | 100% | 128.8% | 120758.15 | 15.94% | 0 | 0 | 0
23-PC-42451 | Phase I: Oak Terrace Cell Tower Data Recovery | In Progress | Time and material | Paleontology | Travis Delgado |  | 101800 | 69224 | 69224 | 72208.06 | 64989 | 7219.06 | 49547.32 | 22660.74 | 68% | 68.62% | 52252.68 | 51.33% | 0 | 0 | 0
23-PC-42496 | Silver Lake Paleontological Monitoring | Completed | Fixed fee | Paleontology | Travis Delgado |  | 254000 | 254000 | 254000 | 143230.6 | 143230.6 | 0 | 131932.2 | 11298.4 | 100% | 92.11% | 122067.8 | 48.06% | 0 | 0 | 20040.6
23-PC-42771 | Redbud Housing Development GIS Mapping | In Progress | Fixed fee | Maritime | Kyle Maynard | 08/21/2026 | 25200 | 19124.28 | 19124.28 | 18799.2 | 18799.2 | 0 | 14265.92 | 4533.28 | 75.9% | 75.89% | 10934.08 | 43.39% | 0 | 0 | 0
23-PC-42907 | Heron Marsh Historic Resources Evaluation | In Progress | Fixed fee | Maritime | Rita Ayala |  | 1637200 | 1057303.76 | 1057303.76 | 977458.87 | 712768.92 | 264689.95 | 631212.64 | 346246.23 | 64.6% | 64.58% | 1005987.36 | 61.45% | 0 | 0 | 0
23-PC-42981 | Hawk Point Architectural History Survey | In Progress | Fixed fee | Maritime | Kyle Maynard |  | 175800 | 133203.66 | 133203.66 | 129494.28 | 129494.28 | 0 | 98123.54 | 31370.74 | 75.8% | 75.77% | 77676.46 | 44.18% | 0 | 0 | 0
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | In Progress | Time and material | Maritime | Rita Ayala | 08/14/2026 | 139700 | 94996 | 94996 | 93543.12 | 93543.12 | 0 | 67047.93 | 26495.19 | 68% | 71.68% | 72652.07 | 52.01% | 0 | 0 | 0
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | In Progress | Fixed fee | Geospatial | Priscilla Pennington | 09/11/2026 | 73300 | 66563.73 | 66563.73 | 53362.4 | 53362.4 | 0 | 48458.95 | 4903.45 | 90.8% | 90.81% | 24841.05 | 33.89% | 0 | 0 | 0
23-PC-43209 | Sea Oat Harbor Dredging Curation | In Progress | Fixed fee | Meridian | Seth Zavala |  | 247500 | 137090.25 | 137090.25 | 178398 | 178398 | 0 | 98806.54 | 79591.46 | 55.4% | 55.39% | 148693.46 | 60.08% | 0 | 0 | 0
23-PC-43238 | Thistle Down Fiber Route - Data Recovery | In Progress | Fixed fee | Meridian | Clinton Solis |  | 454300 | 283028.9 | 283028.9 | 287491.13 | 227977.2 | 59513.93 | 179098.38 | 108392.75 | 62.3% | 62.3% | 275201.62 | 60.58% | 0 | 0 | 0
23-PC-43356 | Granite Pass Wastewater Plant - Phase II Testing | Final Billing/Invoice | Fixed fee | Meridian | Seth Zavala |  | 66500 | 66500 | 66500 | 43863.4 | 43863.4 | 0 | 31972.52 | 11890.88 | 100% | 72.89% | 34527.48 | 51.92% | 0 | 0 | 18028.15
23-PC-43408 | Wildrye Solar - Built Environment Survey | In Progress | Time and material | Meridian | Mathew Shea |  | 176300 | 119884 | 119884 | 121964.34 | 121964.34 | 0 | 65842.99 | 56121.35 | 68% | 53.99% | 110457.01 | 62.65% | 0 | 0 | 0
23-PC-43477 | On-Call: Meadowlark Levee Repair Cultural Resources Monitoring | Completed | Time and material | Meridian | Mathew Shea |  | 69800 | 47464 | 47464 | 51233.2 | 51233.2 | 0 | 57791.37 | -6558.17 | 68% | 112.8% | 12008.63 | 17.2% | 0 | 0 | 0
23-PC-43564 | Willow Springs Levee Repair - Curation | Final Billing/Invoice | Fixed fee | Meridian | Mathew Shea |  | 277000 | 277000 | 277000 | 174842.4 | 174842.4 | 0 | 168435.86 | 6406.54 | 100% | 96.34% | 108564.14 | 39.19% | 0 | 0 | 10138.2
23-PC-43612 | Maple Fork Wind Farm Class III Survey | In Progress | Time and material | Meridian | Seth Zavala |  | 201800 | 137224 | 137224 | 135120.77 | 112489.92 | 22630.85 | 73233.08 | 61887.69 | 68% | 54.2% | 128566.92 | 63.71% | 0 | 0 | 0
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran | 09/04/2026 | 112600 | 91374.9 | 91374.9 | 77637.7 | 77637.7 | 0 | 63002.79 | 14634.91 | 81.1% | 81.15% | 49597.21 | 44.05% | 0 | 0 | 0
23-PC-43788 | Sandpiper Cell Tower - GIS Mapping | Final Billing/Invoice | Fixed fee | Meridian Southwest | Reginald Kerr |  | 57800 | 57800 | 57800 | 39628.4 | 30648.74 | 8979.66 | 39255.29 | 373.11 | 100% | 99.06% | 18544.71 | 32.08% | 0 | 0 | 543.32
23-PC-43811 | Phase I: Thistle Down Fiber Route Section 106 Consultation | On Hold | Fixed fee | Meridian Southwest | Alan Gay |  | 34600 | 19971.12 | 19971.12 | 28596.9 | 28596.9 | 0 | 16505.25 | 12091.65 | 57.7% | 57.72% | 18094.75 | 52.3% | 0 | 0 | 0
23-PC-43829 | Task Order 34: Ember Valley Wastewater Plant Architectural History Survey | In Progress | Fixed fee | Meridian Southwest | Harold Chaney |  | 166500 | 100016.55 | 100016.55 | 125557.65 | 125557.65 | 0 | 75422.97 | 50134.68 | 60.1% | 60.07% | 91077.03 | 54.7% | 0 | 0 | 0
23-PC-44023 | Phase I: Sandpiper Pipeline Archaeological Testing | Transferred Entity | Time and material | Global LLC International | Randy Cantu | 08/28/2026 | 0 | 0 | 0 | 196796.95 | 179738.24 | 17058.71 | 154364.16 | 42432.79 | 0% | 78.44% | -154364.16 | 0% | 0 | 0 | 0
23-PC-44147 | Phase II: Wren Hollow Harbor Dredging Historic Resources Evaluation | Transferred Entity | Fixed fee | Global LLC International | Randy Cantu | 08/14/2026 | 0 | 0 | 0 | 115907.33 | 115907.33 | 0 | 138824.03 | -22916.7 | 0% | 119.8% | -138824.03 | 0% | 0 | 0 | 0
24-PC-30017 | Sparrow Hill Data Recovery | Final Billing/Invoice | Time and material | Big Sky | Carl Barajas |  | 24800 | 10788 | 10788 | 17553.44 | 17553.44 | 0 | 21304.8 | -3751.36 | 43.5% | 121.4% | 3495.2 | 14.09% | 0 | 0 | 0
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 08/07/2026 | 93300 | 93300 | 90265.16 | 59544.06 | 59544.06 | 0 | 93708.96 | -34164.9 | 100% | 157.4% | -408.96 | -0.44% | 60605.29 | 2332.54 | 38390.36
24-PC-30378 | Phase III: Eagle Bend Rail Siding Class III Survey | Completed | Fixed fee | Big Sky | Brendan Melton |  | 133000 | 133000 | 133000 | 107304.4 | 107304.4 | 0 | 75113.08 | 32191.32 | 100% | 70% | 57886.92 | 43.52% | 0 | 0 | 39900
24-PC-30448 | Maple Fork Substation - Data Recovery | In Progress | Fixed fee | Big Sky | Bob Frye |  | 142600 | 97709.52 | 97709.52 | 105894.76 | 105894.76 | 0 | 72554.14 | 33340.62 | 68.5% | 68.52% | 70045.86 | 49.12% | 0 | 0 | 0
24-PC-30509 | On-Call: Yarrow Point Mine Expansion Cultural Resources Monitoring | Lab/Curation | Fixed fee | Big Sky | Javier Estrada |  | 682700 | 417402.78 | 417402.78 | 517281.79 | 517281.79 | 0 | 316284.4 | 200997.39 | 61.1% | 61.14% | 366415.6 | 53.67% | 0 | 0 | 0
24-PC-30620 | Task Order 31: Sumac Ridge Trail GIS Mapping | Lab/Curation | Fixed fee | Bluegrass | Kiara Gillespie | 08/21/2026 | 104400 | 88729.56 | 88729.56 | 78268.68 | 78268.68 | 0 | 66519.65 | 11749.03 | 85% | 84.99% | 37880.35 | 36.28% | 0 | 0 | 0
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 08/07/2026 | 60600 | 60600 | 60600 | 45577.26 | 45577.26 | 0 | 50596.88 | -5019.62 | 100% | 111% | 10003.12 | 16.51% | 20214.7 | 0 | 20204.04
24-PC-30751 | Windmill Flat Section 106 Consultation | In Progress | Fixed fee | Bluegrass | Kiara Gillespie |  | 90800 | 63314.84 | 63314.84 | 72034.09 | 57699.75 | 14334.34 | 50229.44 | 21804.65 | 69.7% | 69.73% | 40570.56 | 44.68% | 0 | 0 | 0
24-PC-30843 | North Fork Highway Widening - Built Environment Survey | Final Billing/Invoice | Time and material | Bluegrass | Alice Galloway |  | 108600 | 73848 | 73848 | 82210.2 | 82210.2 | 0 | 75334.1 | 6876.1 | 68% | 91.64% | 33265.9 | 30.63% | 0 | 0 | 0
24-PC-30850 | Tamarack Transmission Line - Data Recovery | Final Reporting/Review | Time and material | Bluegrass | Alice Galloway |  | 991800 | 674424 | 674424 | 689995.26 | 689995.26 | 0 | 423701.35 | 266293.91 | 68% | 61.41% | 568098.65 | 57.28% | 0 | 0 | 0
24-PC-31134 | Blue Heron Built Environment Survey | On Hold | Time and material | Cascade | Jeff Spence |  | 59300 | 40324 | 40324 | 41670.11 | 41670.11 | 0 | 27663.45 | 14006.66 | 68% | 66.39% | 31636.55 | 53.35% | 0 | 0 | 0
24-PC-31224 | Quail Run Harbor Dredging - Architectural History Survey | Final Billing/Invoice | Fixed fee | Cascade | Preston Duarte |  | 64800 | 64800 | 64800 | 37720.08 | 37720.08 | 0 | 49036.1 | -11316.02 | 100% | 130% | 15763.9 | 24.33% | 0 | 0 | 0
24-PC-31267 | Coyote Springs Built Environment Survey | On Hold | Fixed fee | Cascade | Cassidy Gay |  | 97500 | 61688.25 | 61688.25 | 73905 | 73905 | 0 | 46761.91 | 27143.09 | 63.3% | 63.27% | 50738.09 | 52.04% | 0 | 0 | 0
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Cost Tracking on Closed Project | Time and material | Cascade | Preston Duarte | 09/04/2026 | 94000 | 63920 | 63920 | 65640.2 | 65640.2 | 0 | 73270.02 | -7629.82 | 68% | 111.6% | 20729.98 | 22.05% | 0 | 0 | 0
24-PC-31358 | Dove Canyon Archaeological Testing | Final Reporting/Review | Fixed fee | Cascade | Donald Lutz |  | 595100 | 572605.22 | 572605.22 | 484590.9 | 358002.83 | 126588.07 | 466249.95 | 18340.95 | 96.2% | 96.22% | 128850.05 | 21.65% | 0 | 0 | 0
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Jean Cooke |  | 18200 | 13335.14 | 13335.14 | 12417.86 | 12417.86 | 0 | 9098.08 | 3319.78 | 73.3% | 73.27% | 9101.92 | 50.01% | 0 | 0 | 0
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | In Progress | Time and material | Cascade | Gene Nixon | 09/11/2026 | 18300 | 12444 | 12444 | 11931.6 | 11931.6 | 0 | 9112.04 | 2819.56 | 68% | 76.37% | 9187.96 | 50.21% | 0 | 0 | 0
24-PC-31503 | North Fork Wind Farm Curation | Lab/Curation | Time and material | Cascade | Preston Duarte |  | 129900 | 88332 | 88332 | 87825.39 | 87825.39 | 0 | 98773.26 | -10947.87 | 68% | 112.5% | 31126.74 | 23.96% | 0 | 0 | 0
24-PC-31514 | On-Call: Harbor View Highway Widening Curation | Final Billing/Invoice | Fixed fee | Cascade | Gene Nixon |  | 111700 | 111700 | 111700 | 98296 | 98296 | 0 | 107941.44 | -9645.44 | 100% | 109.8% | 3758.56 | 3.36% | 0 | 0 | 0
24-PC-31534 | Willow Springs Wastewater Plant - Architectural History Survey | Completed | Fixed fee | Cascade | Donald Lutz |  | 156900 | 156900 | 156900 | 93967.41 | 93967.41 | 0 | 113173.46 | -19206.05 | 100% | 120.4% | 43726.54 | 27.87% | 0 | 0 | 0
24-PC-31663 | Fern Valley Section 106 Consultation | In Progress | Fixed fee | Cascade | Jean Cooke |  | 52600 | 43847.36 | 43847.36 | 37714.2 | 37714.2 | 0 | 31436.99 | 6277.21 | 83.4% | 83.36% | 21163.01 | 40.23% | 0 | 0 | 0
24-PC-31750 | Kestrel Butte Park Improvements - Phase I Survey | Final Reporting/Review | Fixed fee | Cascade | Cassidy Gay |  | 257200 | 217488.32 | 212721.72 | 200024.44 | 200024.44 | 0 | 169133.72 | 30890.72 | 84.6% | 84.56% | 88066.28 | 34.24% | 63337.27 | 616.99 | 76688.64
24-PC-31819 | Plover Cove Reservoir - Curation | Final Reporting/Review | Time and material | Cascade | Gene Nixon |  | 38600 | 26248 | 26248 | 26703.48 | 26703.48 | 0 | 15843.15 | 10860.33 | 68% | 59.33% | 22756.85 | 58.96% | 0 | 0 | 0
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | In Progress | Time and material | Cascade | Gene Nixon |  | 15200 | 10871.15 | 10871.15 | 10676.48 | 10676.48 | 0 | 7665.21 | 3011.27 | 71.5% | 71.8% | 7534.79 | 49.57% | 1311.34 | 0 | 1872.75
24-PC-31924 | Cedar Hollow Wind Farm - Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Gene Nixon |  | 186800 | 123811.04 | 123811.04 | 147262.72 | 122646.08 | 24616.64 | 97605.67 | 49657.05 | 66.3% | 66.28% | 89194.33 | 47.75% | 0 | 0 | 0
24-PC-32088 | Elk Meadow Phase I Survey | In Progress | Time and material | Chesapeake | Jason Oconnor |  | 305100 | 207468 | 207468 | 228062.25 | 228062.25 | 0 | 135703.34 | 92358.91 | 68% | 59.5% | 169396.66 | 55.52% | 0 | 0 | 0
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor |  | 51800 | 51800 | 50026.67 | 36731.38 | 36731.38 | 0 | 59530.75 | -22799.37 | 100% | 162.1% | -7730.75 | -14.92% | 35921.67 | 0 | 16734.81
24-PC-32209 | Saltgrass Wastewater Plant - Phase I Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox |  | 13000 | 12785.5 | 12785.5 | 9029.25 | 7229.76 | 1799.49 | 8880.11 | 149.14 | 98.4% | 98.35% | 4119.89 | 31.69% | 2453.07 | 0 | 3532.1
24-PC-32210 | Badger Hollow Transmission Line - Class III Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 114400 | 79496.56 | 79496.56 | 91211.12 | 91211.12 | 0 | 63386.97 | 27824.15 | 69.5% | 69.49% | 51013.03 | 44.59% | 0 | 0 | 0
24-PC-32270 | Creosote Draw School Campus Data Recovery | Final Billing/Invoice | Time and material | Chesapeake | Alexandria Wilkinson |  | 42200 | 28696 | 28696 | 29472.48 | 29472.48 | 0 | 28972.81 | 499.67 | 68% | 98.3% | 13227.19 | 31.34% | 0 | 0 | 0
24-PC-32479 | Riverbend Transmission Line Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 94000 | 62594.6 | 62594.6 | 66890.4 | 66890.4 | 0 | 44542.3 | 22348.1 | 66.6% | 66.59% | 49457.7 | 52.61% | 1051.62 | 0 | 1475.8
24-PC-32591 | Larkspur Fiber Route - Cultural Resources Assessment | Final Billing/Invoice | Time and material | Chesapeake | Sandy Kerr |  | 41000 | 27880 | 27880 | 27478.2 | 27478.2 | 0 | 33999.85 | -6521.65 | 68% | 123.7% | 7000.15 | 17.07% | 0 | 0 | 0
24-PC-32640 | Badger Hollow Harbor Dredging Architectural History Survey | Transferred Entity | Time and material | Chesapeake | Alexandria Wilkinson |  | 39000 | 26520 | 26520 | 28130.47 | 21303 | 6827.47 | 22328.99 | 5801.48 | 68% | 79.38% | 16671.01 | 42.75% | 0 | 0 | 0
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Chesapeake | Alexandria Wilkinson | 08/21/2026 | 84000 | 84000 | 83888.35 | 70198.8 | 70198.8 | 0 | 85361.67 | -15162.87 | 100% | 121.6% | -1361.67 | -1.62% | 61108.1 | 104.21 | 54866.35
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox | 08/14/2026 | 51700 | 44730.84 | 44730.84 | 45206.48 | 45206.48 | 0 | 39111.36 | 6095.12 | 86.5% | 86.52% | 12588.64 | 24.35% | 0 | 0 | 0
24-PC-32954 | Redbud Substation - Historic Resources Evaluation | In Progress | Time and material | Front Range | Kimberly Daugherty |  | 331200 | 225216 | 225216 | 217532.16 | 217532.16 | 0 | 114290.35 | 103241.81 | 68% | 52.54% | 216909.65 | 65.49% | 0 | 0 | 0
24-PC-33384 | Phase III: Pine Hollow Rail Siding Maritime Remote Sensing Survey | In Progress | Time and material | Front Range | Dean Velazquez |  | 288100 | 195908 | 195908 | 207230.33 | 207230.33 | 0 | 139777.64 | 67452.69 | 68% | 67.45% | 148322.36 | 51.48% | 0 | 0 | 0
24-PC-33394 | Foxglove Park Improvements Cultural Resources Assessment | In Progress | Time and material | Front Range | Joanna Herrera |  | 298200 | 202776 | 202776 | 197617.14 | 197617.14 | 0 | 102377.3 | 95239.84 | 68% | 51.81% | 195822.7 | 65.67% | 0 | 0 | 0
24-PC-33448 | Ember Valley Solar Architectural History Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 07/31/2026 | 681000 | 563868 | 560235.94 | 419972.7 | 419972.7 | 0 | 347755.54 | 72217.16 | 82.8% | 82.8% | 333244.46 | 48.93% | 54560.78 | 2799.26 | 84829.84
24-PC-33531 | North Fork Park Improvements - Curation | Lab/Curation | Fixed fee | Front Range | Dean Velazquez |  | 31500 | 23965.2 | 23965.2 | 23760.45 | 23760.45 | 0 | 18077.06 | 5683.39 | 76.1% | 76.08% | 13422.94 | 42.61% | 1244.31 | 0 | 1650.6
24-PC-33575 | On-Call: North Fork Trail Architectural History Survey | Final Reporting/Review | Time and material | Front Range | Devon Pitts | 08/28/2026 | 589600 | 384232.95 | 369763.26 | 433356 | 433356 | 0 | 309438.42 | 123917.58 | 65.2% | 71.41% | 280161.58 | 47.52% | 79367.75 | 4875 | 115056.06
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Karl Valenzuela |  | 64500 | 59346.45 | 57224.04 | 49568.25 | 49568.25 | 0 | 45606.09 | 3962.16 | 92% | 92.01% | 18893.91 | 29.29% | 21753.01 | 2008.13 | 26186.64
24-PC-33927 | Aspen Ridge Solar Class III Survey | Final Reporting/Review | Fixed fee | Great Lakes | Nathan Lambert |  | 104000 | 57012.8 | 57012.8 | 77001.6 | 77001.6 | 0 | 42209.16 | 34792.44 | 54.8% | 54.82% | 61790.84 | 59.41% | 746.78 | 0 | 1008.8
24-PC-33981 | Yarrow Point Airport Apron - Phase II Testing | Lab/Curation | Time and material | Great Lakes | Nathan Lambert | 08/07/2026 | 47500 | 36664.5 | 36664.5 | 29944 | 29944 | 0 | 26339.43 | 3604.57 | 77.2% | 87.96% | 21160.57 | 44.55% | 3002.99 | 0 | 4364.5
24-PC-33985 | Thistle Down Substation Curation | In Progress | Time and material | Great Lakes | Angelica Cervantes | 08/07/2026 | 78300 | 53244 | 53244 | 57863.7 | 57863.7 | 0 | 50630.38 | 7233.32 | 68% | 87.5% | 27669.62 | 35.34% | 0 | 0 | 0
24-PC-34015 | Sea Oat Mixed-Use Development Environmental Review Support | Final Billing/Invoice | Fixed fee | Great Lakes | Karl Valenzuela |  | 16200 | 16200 | 16200 | 10449 | 10449 | 0 | 8825.53 | 1623.47 | 100% | 84.46% | 7374.47 | 45.52% | 0 | 0 | 2517.48
24-PC-34211 | Quail Run Substation - Cultural Resources Monitoring | On Hold | Time and material | Great Lakes | Gina Beltran |  | 70900 | 48212 | 48212 | 50537.52 | 50537.52 | 0 | 37357.74 | 13179.78 | 68% | 73.92% | 33542.26 | 47.31% | 0 | 0 | 0
24-PC-34263 | Cedar Hollow Airport Apron Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Robin Mercado |  | 199300 | 127292.91 | 127292.91 | 147800.88 | 147800.88 | 0 | 94406.95 | 53393.93 | 63.9% | 63.87% | 104893.05 | 52.63% | 0 | 0 | 0
24-PC-34274 | Lantern Bay Rail Siding - Environmental Review Support | Completed | Fixed fee | Great Lakes | Angelica Cervantes |  | 61900 | 61900 | 61900 | 48195.34 | 48195.34 | 0 | 57257.25 | -9061.91 | 100% | 118.8% | 4642.75 | 7.5% | 0 | 0 | 0
24-PC-34320 | Sage Flat Canal Lining Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert |  | 388400 | 279492.64 | 279492.64 | 253927.23 | 209652.52 | 44274.71 | 182728.59 | 71198.64 | 72% | 71.96% | 205671.41 | 52.95% | 0 | 0 | 0
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Karl Valenzuela |  | 38700 | 26316 | 26316 | 26644.95 | 26644.95 | 0 | 19241.81 | 7403.14 | 68% | 72.22% | 19458.19 | 50.28% | 0 | 0 | 0
24-PC-34422 | Silver Lake Historic Resources Evaluation | Completed | Fixed fee | Great Lakes | Angelica Cervantes |  | 183900 | 183900 | 183900 | 106036.74 | 106036.74 | 0 | 137847.76 | -31811.02 | 100% | 130% | 46052.24 | 25.04% | 0 | 0 | 0
24-PC-34458 | Badger Hollow Built Environment Survey | Completed | Time and material | Great Lakes | Leonard Mejia |  | 78300 | 53244 | 53244 | 57511.35 | 57511.35 | 0 | 65133.46 | -7622.11 | 68% | 113.2% | 13166.54 | 16.82% | 0 | 0 | 0
24-PC-34499 | Dove Canyon Trail - GIS Mapping | In Progress | Time and material | Great Lakes | Brendan Padilla | 09/11/2026 | 104200 | 70856 | 70856 | 76427.58 | 70842.85 | 5584.73 | 75193.06 | 1234.52 | 68% | 98.38% | 29006.94 | 27.84% | 0 | 0 | 0
24-PC-34593 | Riverbend Park Improvements - Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Leonard Mejia |  | 43500 | 25308.3 | 25308.3 | 33447.15 | 33447.15 | 0 | 19459.27 | 13987.88 | 58.2% | 58.18% | 24040.73 | 55.27% | 0 | 0 | 0
24-PC-34654 | Timber Gap Phase II Testing | Final Reporting/Review | Time and material | Great Lakes | Brendan Padilla |  | 115400 | 82959.15 | 82899.95 | 87787.28 | 70825.08 | 16962.2 | 47046.35 | 40740.93 | 71.9% | 53.59% | 68353.65 | 59.23% | 15044.61 | 60.42 | 23930.55
24-PC-34663 | Redbud Airport Apron - GIS Mapping | In Progress | Time and material | Great Lakes | Kathleen Galvan | 09/11/2026 | 505100 | 343468 | 343468 | 342760.86 | 342760.86 | 0 | 286062.16 | 56698.7 | 68% | 83.46% | 219037.84 | 43.37% | 0 | 0 | 0
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | In Progress | Time and material | Gulf Coast | Courtney Daugherty |  | 176500 | 120020 | 120020 | 121414.35 | 121414.35 | 0 | 122080.25 | -665.9 | 68% | 100.6% | 54419.75 | 30.83% | 0 | 0 | 0
24-PC-34919 | Fern Valley Levee Repair Class III Survey | Completed | Fixed fee | Gulf Coast West | Sean Jennings |  | 20000 | 20000 | 20000 | 13582 | 13582 | 0 | 12468.14 | 1113.86 | 100% | 91.8% | 7531.86 | 37.66% | 0 | 0 | 1640
24-PC-34975 | Foxglove Fiber Route GIS Mapping | In Progress | Fixed fee | Gulf Coast West | Bernard Erickson |  | 205900 | 175159.13 | 175159.13 | 181192 | 181192 | 0 | 154132.44 | 27059.56 | 85.1% | 85.07% | 51767.56 | 25.14% | 0 | 0 | 0
24-PC-35267 | Falcon Mesa Trail - Phase II Testing | Final Reporting/Review | Fixed fee | Gulf Coast | Sean Jennings |  | 56700 | 33226.2 | 33226.2 | 42581.7 | 42581.7 | 0 | 24952.14 | 17629.56 | 58.6% | 58.6% | 31747.86 | 55.99% | 0 | 0 | 0
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | In Progress | Time and material | High Desert | Kathy Hurley | 08/14/2026 | 301200 | 204816 | 204816 | 217496.52 | 217496.52 | 0 | 196030.1 | 21466.42 | 68% | 90.13% | 105169.9 | 34.92% | 0 | 0 | 0
24-PC-35419 | Yarrow Point Pipeline - Class III Survey | Completed | Time and material | High Desert | Bridget Maddox |  | 24800 | 16864 | 16864 | 16359.63 | 14370.56 | 1989.07 | 14431.84 | 1927.79 | 68% | 88.22% | 10368.16 | 41.81% | 0 | 0 | 0
24-PC-35474 | Larkspur Curation | In Progress | Fixed fee | High Desert | Eileen Poole |  | 369600 | 284148.48 | 284148.48 | 278295.85 | 215699.64 | 62596.21 | 213962.17 | 64333.68 | 76.9% | 76.88% | 155637.83 | 42.11% | 0 | 0 | 0
24-PC-35559 | Phase III: Fern Valley Battery Storage Curation | Final Reporting/Review | Fixed fee | High Desert | Eileen Poole | 08/14/2026 | 218200 | 185797.3 | 185797.3 | 144252.02 | 144252.02 | 0 | 122823.72 | 21428.3 | 85.2% | 85.15% | 95376.28 | 43.71% | 0 | 0 | 0
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | In Progress | Fixed fee | High Desert | Eileen Poole | 08/07/2026 | 119200 | 90150.96 | 90150.96 | 88243.76 | 88243.76 | 0 | 66735.14 | 21508.62 | 75.6% | 75.63% | 52464.86 | 44.01% | 0 | 0 | 0
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | In Progress | Time and material | High Desert | Kathy Hurley |  | 69900 | 69900 | 66597.48 | 49013.31 | 40696.6 | 8316.71 | 53862.59 | -4849.28 | 100% | 109.9% | 16037.41 | 22.94% | 27379.3 | 1166.52 | 34233.78
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | In Progress | Time and material | High Desert | Kathy Hurley |  | 225100 | 200102.05 | 200102.05 | 153743.3 | 153743.3 | 0 | 140872.8 | 12870.5 | 88.9% | 91.63% | 84227.2 | 37.42% | 38618.79 | 0 | 62115.75
24-PC-35881 | Wren Hollow Transmission Line - Architectural History Survey | Final Billing/Invoice | Fixed fee | High Desert | Bridget Maddox |  | 154200 | 154200 | 154200 | 112673.94 | 112673.94 | 0 | 89889.66 | 22784.28 | 100% | 79.78% | 64310.34 | 41.71% | 0 | 0 | 31179.24
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 09/11/2026 | 12900 | 10859.22 | 10859.22 | 9094.5 | 9094.5 | 0 | 7655.43 | 1439.07 | 84.2% | 84.18% | 5244.57 | 40.66% | 0 | 0 | 0
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Cost Tracking on Closed Project | Fixed fee | High Desert | Kathy Hurley | 09/04/2026 | 58300 | 58300 | 58300 | 39072.66 | 39072.66 | 0 | 45518.79 | -6446.13 | 100% | 116.5% | 12781.21 | 21.92% | 0 | 0 | 0
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | In Progress | Time and material | High Desert | Kathy Hurley | 09/11/2026 | 5700 | 3876 | 3876 | 4244.79 | 4244.79 | 0 | 3255.04 | 989.75 | 68% | 76.68% | 2444.96 | 42.89% | 0 | 0 | 0
24-PC-36184 | Juniper Wash Pipeline Maritime Remote Sensing Survey | On Hold | Fixed fee | High Desert | Eileen Poole |  | 3500 | 2329.6 | 2329.6 | 2062.55 | 2062.55 | 0 | 1372.9 | 689.65 | 66.6% | 66.56% | 2127.1 | 60.77% | 0 | 0 | 0
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Island | Rodney Mcguire |  | 56300 | 52077.5 | 52077.5 | 37721 | 37721 | 0 | 34891.33 | 2829.67 | 92.5% | 92.5% | 21408.67 | 38.03% | 0 | 0 | 0
24-PC-36445 | Tamarack Archaeological Testing | On Hold | Time and material | Island | Briana Melton |  | 63600 | 43248 | 43248 | 43330.68 | 43330.68 | 0 | 44727.96 | -1397.28 | 68% | 103.2% | 18872.04 | 29.67% | 0 | 0 | 0
24-PC-36559 | Stone Mill Airport Apron - Class III Survey | Completed | Fixed fee | Island | Becky Velazquez |  | 11800 | 11800 | 11800 | 8903.1 | 8903.1 | 0 | 6324.69 | 2578.41 | 100% | 71.04% | 5475.31 | 46.4% | 0 | 0 | 3417.28
24-PC-36620 | Silver Lake Cultural Resources Assessment | In Progress | Time and material | Lakeshore | Terrence Gillespie |  | 368100 | 290535 | 290535 | 252295.74 | 252295.74 | 0 | 163066.37 | 89229.37 | 78.9% | 64.63% | 205033.63 | 55.7% | 24338.6 | 0 | 40227
24-PC-36676 | Task Order 38: Ember Valley Wastewater Plant Paleontological Monitoring | Final Billing/Invoice | Time and material | Lakeshore | Lucas Benson |  | 93200 | 63376 | 63376 | 62093.62 | 58555.2 | 3538.42 | 55674.87 | 6418.75 | 68% | 89.66% | 37525.13 | 40.26% | 0 | 0 | 0
24-PC-36710 | Phase III: Twin Buttes Cell Tower Section 106 Consultation | On Hold | Fixed fee | Lakeshore | Jeanette Riddle |  | 138500 | 93321.3 | 93321.3 | 97600.95 | 97600.95 | 0 | 65764.21 | 31836.74 | 67.4% | 67.38% | 72735.79 | 52.52% | 0 | 0 | 0
24-PC-36932 | Badger Hollow Canal Lining - Section 106 Consultation | Final Reporting/Review | Time and material | Hill Country | Marcus Shea | 09/11/2026 | 12200 | 9992.5 | 9992.5 | 7733.58 | 7733.58 | 0 | 6430.16 | 1303.42 | 81.9% | 83.15% | 5769.84 | 47.29% | 989.21 | 0 | 1696.5
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | In Progress | Fixed fee | Hill Country | Glen Delacruz |  | 141000 | 141000 | 141000 | 113970.3 | 113970.3 | 0 | 138124.06 | -24153.76 | 100% | 121.2% | 2875.94 | 2.04% | 0 | 0 | 0
24-PC-37107 | Hawk Point Mixed-Use Development Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza |  | 259400 | 176106.66 | 176106.66 | 186117.89 | 175095.48 | 11022.41 | 126346.85 | 59771.04 | 67.9% | 67.89% | 133053.15 | 51.29% | 0 | 0 | 0
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | In Progress | Fixed fee | Hill Country | Gail Meza | 08/21/2026 | 1259200 | 928785.92 | 928785.92 | 853989.44 | 853989.44 | 0 | 629919.62 | 224069.82 | 73.8% | 73.76% | 629280.38 | 49.97% | 0 | 0 | 0
24-PC-37167 | Saltgrass Curation | Lab/Curation | Time and material | Hill Country | Marcus Shea |  | 65600 | 44608 | 44608 | 48603.04 | 48603.04 | 0 | 33605.6 | 14997.44 | 68% | 69.14% | 31994.4 | 48.77% | 0 | 0 | 0
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | In Progress | Time and material | Hill Country | Samuel Wilkerson | 08/07/2026 | 67000 | 51564 | 51564 | 40709.2 | 40709.2 | 0 | 34240.46 | 6468.74 | 77% | 84.11% | 32759.54 | 48.89% | 7462.83 | 0 | 10560
24-PC-37266 | Granite Pass Cell Tower Phase I Survey | In Progress | Time and material | Hill Country | Marcus Shea |  | 41400 | 29169.9 | 29169.9 | 24587.46 | 24587.46 | 0 | 17096.42 | 7491.04 | 70.5% | 69.53% | 24303.58 | 58.7% | 1417.54 | 0 | 2218.5
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 08/07/2026 | 298500 | 213069.3 | 213069.3 | 243904.35 | 243904.35 | 0 | 174092.01 | 69812.34 | 71.4% | 71.38% | 124407.99 | 41.68% | 42378.81 | 0 | 51879.3
24-PC-37372 | Harbor View Harbor Dredging Paleontological Monitoring | Final Reporting/Review | Fixed fee | Piedmont - Inactive | Maria Parrish |  | 272100 | 244563.48 | 237896.12 | 221924.76 | 221924.76 | 0 | 199459.24 | 22465.52 | 89.9% | 89.88% | 72640.76 | 26.7% | 70482.99 | 3076.38 | 79751.6
24-PC-37415 | Sage Flat Mine Expansion Maritime Remote Sensing Survey | In Progress | Fixed fee | PIEDMONT - INACTIVE | Megan Pineda |  | 191000 | 115994.3 | 115994.3 | 147948.6 | 147948.6 | 0 | 89853.11 | 58095.49 | 60.7% | 60.73% | 101146.89 | 52.96% | 0 | 0 | 0
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | In Progress | Time and material | PIEDMONT - INACTIVE | Jody Chung |  | 309400 | 210392 | 210392 | 184093 | 184093 | 0 | 149432.06 | 34660.94 | 68% | 81.17% | 159967.94 | 51.7% | 0 | 0 | 0
24-PC-37686 | Twin Buttes Mixed-Use Development Paleontological Monitoring | In Progress | Fixed fee | Piedmont - Inactive | Annette Vaughan | 08/28/2026 | 50600 | 41385.74 | 41385.74 | 39155.85 | 28376.76 | 10779.09 | 32027.2 | 7128.65 | 81.8% | 81.79% | 18572.8 | 36.71% | 0 | 0 | 0
24-PC-37823 | Granite Pass Pipeline Cultural Resources Monitoring | Lab/Curation | Fixed fee | Piedmont - Inactive | Jody Chung |  | 28900 | 21070.99 | 21070.99 | 21651.88 | 21651.88 | 0 | 15787.12 | 5864.76 | 72.9% | 72.91% | 13112.88 | 45.37% | 0 | 0 | 0
24-PC-37942 | Task Order 39: Meadowlark Mine Expansion Curation | Final Reporting/Review | Time and material | Piedmont - Inactive | Annette Vaughan |  | 241400 | 199259.4 | 199259.4 | 173542.46 | 173542.46 | 0 | 141494.45 | 32048.01 | 82.5% | 81.53% | 99905.55 | 41.39% | 28949.16 | 0 | 46936
24-PC-38054 | On-Call: Willow Springs Highway Widening GIS Mapping | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd |  | 60700 | 41373.12 | 41373.12 | 51516.09 | 51516.09 | 0 | 35113.87 | 16402.22 | 68.2% | 68.16% | 25586.13 | 42.15% | 0 | 0 | 0
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Prairie | Sherry Lloyd | 09/04/2026 | 132200 | 121663.66 | 121663.66 | 95580.6 | 95580.6 | 0 | 87961.2 | 7619.4 | 92% | 92.03% | 44238.8 | 33.46% | 0 | 0 | 0
24-PC-38374 | On-Call: Riverbend Highway Widening Archaeological Testing | In Progress | Time and material | Prairie | Sherry Lloyd |  | 481100 | 327148 | 327148 | 330082.71 | 330082.71 | 0 | 229684.73 | 100397.98 | 68% | 69.58% | 251415.27 | 52.26% | 0 | 0 | 0
24-PC-38426 | Elk Meadow Mine Expansion Phase II Testing | Final Billing/Invoice | Fixed fee | Prairie | Sherry Lloyd |  | 203000 | 203000 | 203000 | 167048.7 | 167048.7 | 0 | 176034.28 | -8985.58 | 100% | 105.4% | 26965.72 | 13.28% | 0 | 0 | 0
24-PC-38469 | Falcon Mesa Harbor Dredging - Built Environment Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 08/14/2026 | 656700 | 527658.45 | 515845.1 | 435290.48 | 364918.68 | 70371.8 | 349739.21 | 85551.27 | 80.3% | 80.35% | 306960.79 | 46.74% | 35156.33 | 7781.94 | 41248.01
24-PC-38486 | Kestrel Butte Phase I Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 08/14/2026 | 153600 | 153600 | 153600 | 105043.81 | 77500.98 | 27542.83 | 119866.24 | -14822.43 | 100% | 114.1% | 33733.76 | 21.96% | 0 | 0 | 0
24-PC-38579 | Kestrel Butte Harbor Dredging - Data Recovery | Final Billing/Invoice | Time and material | Red Rock | Javier Newman |  | 59100 | 40188 | 40188 | 39502.44 | 39502.44 | 0 | 34682.96 | 4819.48 | 68% | 87.8% | 24417.04 | 41.31% | 0 | 0 | 0
24-PC-38687 | Lantern Bay GIS Mapping | In Progress | Time and material | Red Rock | Javier Newman |  | 68600 | 46648 | 46648 | 49542.92 | 49542.92 | 0 | 28559.72 | 20983.2 | 68% | 57.65% | 40040.28 | 58.37% | 0 | 0 | 0
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Red Rock | Marisa Odom | 08/21/2026 | 168200 | 168200 | 168200 | 130489.56 | 130489.56 | 0 | 132230.67 | -1741.11 | 100% | 101.3% | 35969.33 | 21.38% | 0 | 0 | 0
24-PC-38795 | Meadowlark Class III Survey | Final Billing/Invoice | Time and material | Red Rock | Javier Newman |  | 684500 | 465460 | 465460 | 462838.34 | 389103.36 | 73734.98 | 454739.93 | 8098.41 | 68% | 98.25% | 229760.07 | 33.57% | 0 | 0 | 0
24-PC-38817 | Phase III: Wildrye Fiber Route Built Environment Survey | Completed | Fixed fee | Red Rock | Bruce Suarez |  | 1966200 | 1966200 | 1966200 | 1268002.38 | 1268002.38 | 0 | 1321460.02 | -53457.64 | 100% | 104.2% | 644739.98 | 32.79% | 0 | 0 | 0
24-PC-38847 | Pine Hollow School Campus - Environmental Review Support | On Hold | Fixed fee | Red Rock | Tina Aguirre |  | 118600 | 78003.22 | 78003.22 | 93456.8 | 93456.8 | 0 | 61462.32 | 31994.48 | 65.8% | 65.77% | 57137.68 | 48.18% | 0 | 0 | 0
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 07/31/2026 | 100200 | 100200 | 93737.19 | 72685.08 | 72685.08 | 0 | 103671 | -30985.92 | 100% | 142.6% | -3471 | -3.46% | 79996.98 | 3298.4 | 61102.05
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | In Progress | Time and material | Red Rock | Lydia Cisneros |  | 126600 | 86088 | 86088 | 82581.18 | 82581.18 | 0 | 59856.61 | 22724.57 | 68% | 72.48% | 66743.39 | 52.72% | 0 | 0 | 0
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Javier Newman | 09/04/2026 | 597800 | 458990.84 | 458990.84 | 435557.08 | 435557.08 | 0 | 334422.57 | 101134.51 | 76.8% | 76.78% | 263377.43 | 44.06% | 91632.16 | 0 | 125777.12
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Red Rock | Shelia Horne | 08/14/2026 | 11000 | 11000 | 11000 | 7227 | 7227 | 0 | 7427.79 | -200.79 | 100% | 102.8% | 3572.21 | 32.47% | 0 | 0 | 0
24-PC-39405 | Wren Hollow Harbor Dredging - Section 106 Consultation | Final Billing/Invoice | Time and material | Red Rock | Javier Newman |  | 159700 | 70906.8 | 70906.8 | 107248.85 | 90563.75 | 16685.1 | 82820.14 | 24428.71 | 44.4% | 77.22% | 76879.86 | 48.14% | 0 | 0 | 0
24-PC-39479 | Granite Pass Solar - Cultural Resources Assessment | Final Reporting/Review | Time and material | Red Rock | Javier Newman | 08/28/2026 | 233000 | 165185 | 165185 | 164777.6 | 164777.6 | 0 | 116733.87 | 48043.73 | 70.9% | 70.84% | 116266.13 | 49.9% | 3953.99 | 0 | 6745
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | In Progress | Time and material | Red Rock | Tina Aguirre | 08/14/2026 | 33000 | 29186 | 29186 | 23227.58 | 20462.4 | 2765.18 | 29633.53 | -6405.95 | 88.4% | 127.6% | 3366.47 | 10.2% | 4525.7 | 0 | 7472
24-PC-39533 | Elk Meadow Architectural History Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung |  | 67000 | 63536.1 | 63536.1 | 52641.9 | 52641.9 | 0 | 49919.2 | 2722.7 | 94.8% | 94.83% | 17080.8 | 25.49% | 0 | 0 | 0
24-PC-39694 | Task Order 35: Sandpiper Trail Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 09/18/2026 | 136500 | 92820 | 92820 | 93075.52 | 70843.68 | 22231.84 | 77289.3 | 15786.22 | 68% | 83.04% | 59210.7 | 43.38% | 0 | 0 | 0
24-PC-39789 | Meadowlark Airport Apron Archaeological Testing | On Hold | Fixed fee | Red Rock | Marisa Odom |  | 126000 | 62458.2 | 62458.2 | 101029.58 | 81799.74 | 19229.84 | 50075.41 | 50954.17 | 49.6% | 49.57% | 75924.59 | 60.26% | 0 | 0 | 0
24-PC-39822 | On-Call: Redbud Wind Farm Class III Survey | Completed | Fixed fee | Red Rock | Lydia Cisneros |  | 109500 | 109500 | 109500 | 87460.32 | 72226.32 | 15234 | 78994.88 | 8465.44 | 100% | 90.32% | 30505.12 | 27.86% | 0 | 0 | 10599.6
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 17800 | 17800 | 17800 | 14308.95 | 10538.95 | 3770 | 14659.16 | -350.21 | 100% | 102.5% | 3140.84 | 17.65% | 0 | 0 | 0
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | In Progress | Time and material | Red Rock | Lydia Cisneros | 08/21/2026 | 414900 | 339174.65 | 331243.28 | 270722.25 | 270722.25 | 0 | 215589.53 | 55132.72 | 81.7% | 79.63% | 199310.47 | 48.04% | 106896.03 | 4696.56 | 171091.88
24-PC-39940 | Riverbend Levee Repair - Curation | In Progress | Fixed fee | Red Rock | Marisa Odom |  | 20400 | 13135.56 | 13135.56 | 16397.52 | 16397.52 | 0 | 10559.17 | 5838.35 | 64.4% | 64.39% | 9840.83 | 48.24% | 0 | 0 | 0
24-PC-40067 | Saltgrass Fiber Route Class III Survey | In Progress | Time and material | Red Rock | Marisa Odom | 08/28/2026 | 218100 | 148308 | 148308 | 163684.05 | 163684.05 | 0 | 137568.33 | 26115.72 | 68% | 84.05% | 80531.67 | 36.92% | 0 | 0 | 0
24-PC-40078 | Task Order 32: Heron Marsh Highway Widening Paleontological Monitoring | Completed | Time and material | Sierra North | Donna Herring |  | 1820100 | 1237668 | 1237668 | 1155945.51 | 1155945.51 | 0 | 897222.7 | 258722.81 | 68% | 77.62% | 922877.3 | 50.7% | 0 | 0 | 0
24-PC-40091 | Stone Mill Canal Lining Curation | Completed | Fixed fee | Sierra South | Angelica Poole |  | 121900 | 121900 | 121900 | 105126.56 | 105126.56 | 0 | 117486.47 | -12359.91 | 100% | 111.8% | 4413.53 | 3.62% | 0 | 0 | 0
24-PC-40102 | Redbud Class III Survey | Final Reporting/Review | Fixed fee | Sierra | Benjamin Mathis | 07/31/2026 | 453900 | 453900 | 453900 | 322187.01 | 278794.4 | 43392.61 | 359994.61 | -37807.6 | 100% | 111.7% | 93905.39 | 20.69% | 39793.68 | 0 | 2814.18
24-PC-40218 | North Fork Bridge Replacement - Built Environment Survey | In Progress | Time and material | Sierra North | Angelica Poole |  | 141000 | 95880 | 95880 | 95626.2 | 95626.2 | 0 | 51169.2 | 44457 | 68% | 53.51% | 89830.8 | 63.71% | 0 | 0 | 0
24-PC-40271 | Millbrook Rail Siding Phase II Testing | Final Billing/Invoice | Fixed fee | Sierra | Louis Huff |  | 1146200 | 1146200 | 1146200 | 757124.2 | 596393.12 | 160731.08 | 922496.97 | -165372.77 | 100% | 121.8% | 223703.03 | 19.52% | 0 | 0 | 0
24-PC-40317 | Sumac Ridge Harbor Dredging Curation | In Progress | Time and material | Sierra | Angelica Poole |  | 225800 | 153544 | 153544 | 153318.2 | 153318.2 | 0 | 86572.73 | 66745.47 | 68% | 56.47% | 139227.27 | 61.66% | 0 | 0 | 0
24-PC-40427 | On-Call: Harbor View Trail Built Environment Survey | Completed | Fixed fee | Sierra South | Louis Huff |  | 121700 | 121700 | 121700 | 90556.97 | 90556.97 | 0 | 103112.89 | -12555.92 | 100% | 113.9% | 18587.11 | 15.27% | 0 | 0 | 0
24-PC-40479 | Quail Run Rail Siding - Built Environment Survey | In Progress | Fixed fee | Sierra North | Donna Herring |  | 139600 | 89036.88 | 89036.88 | 110619.04 | 110619.04 | 0 | 70556.04 | 40063 | 63.8% | 63.78% | 69043.96 | 49.46% | 0 | 0 | 0
24-PC-40561 | Task Order 39: Aspen Ridge Housing Development GIS Mapping | In Progress | Fixed fee | Sierra | Benjamin Mathis | 07/31/2026 | 2335800 | 1666359.72 | 1651216.14 | 1746045.15 | 1301909.91 | 444135.24 | 1245666.04 | 500379.11 | 71.3% | 71.34% | 1090133.96 | 46.67% | 128489.61 | 5823.43 | 156771.3
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Angelica Poole | 08/07/2026 | 460500 | 326540.55 | 326540.55 | 381017.7 | 381017.7 | 0 | 270177.47 | 110840.23 | 70.9% | 70.91% | 190322.53 | 41.33% | 10527.4 | 0 | 12709.8
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Sierra North | Louis Huff | 09/18/2026 | 50300 | 46200.55 | 46200.55 | 35350.84 | 35350.84 | 0 | 32471.24 | 2879.6 | 91.8% | 91.85% | 17828.76 | 35.44% | 0 | 0 | 0
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Sierra North | Donna Herring | 08/21/2026 | 22100 | 22100 | 22100 | 17918.68 | 17918.68 | 0 | 33602.1 | -15683.42 | 100% | 187.5% | -11502.1 | -52.05% | 23258.96 | 0 | 9343.88
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Alexis Nixon | 09/04/2026 | 48400 | 48400 | 47376.63 | 37137.32 | 37137.32 | 0 | 47362.38 | -10225.06 | 100% | 127.5% | 1037.62 | 2.14% | 20970.72 | 687.65 | 20369.43
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard |  | 31800 | 31800 | 31800 | 20975.28 | 20975.28 | 0 | 22323.11 | -1347.83 | 100% | 106.4% | 9476.89 | 29.8% | 0 | 0 | 0
24-PC-40836 | Task Order 12: Saltgrass Highway Widening Curation | On Hold | Fixed fee | Coastal Bend | Alexis Nixon |  | 17000 | 14868.2 | 14868.2 | 11633.1 | 11633.1 | 0 | 10174.53 | 1458.57 | 87.5% | 87.46% | 6825.47 | 40.15% | 0 | 0 | 0
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Lab/Curation | Fixed fee | Coastal Bend | Diane Daniels |  | 579300 | 579300 | 579300 | 392475.75 | 392475.75 | 0 | 413750.74 | -21274.99 | 100% | 105.4% | 165549.26 | 28.58% | 0 | 0 | 0
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels |  | 8800 | 8800 | 8800 | 6914.16 | 6914.16 | 0 | 7269.9 | -355.74 | 100% | 105.2% | 1530.1 | 17.39% | 0 | 0 | 0
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | In Progress | Time and material | Coastal Bend | Alexis Nixon | 09/04/2026 | 60600 | 41208 | 41208 | 39983.88 | 39983.88 | 0 | 31771.04 | 8212.84 | 68% | 79.46% | 28828.96 | 47.57% | 0 | 0 | 0
24-PC-41066 | Task Order 31: Yarrow Point Wind Farm Curation | Final Billing/Invoice | Time and material | Coastal Bend | Steve Rubio |  | 30400 | 17571.2 | 17571.2 | 19493.63 | 15437.88 | 4055.75 | 17863.22 | 1630.41 | 57.8% | 91.64% | 12536.78 | 41.24% | 0 | 0 | 0
24-PC-41067 | On-Call: Goldfinch Wastewater Plant Cultural Resources Monitoring | Final Billing/Invoice | Fixed fee | Coastal Bend | Duane Ballard |  | 364100 | 364100 | 364100 | 243619.31 | 243619.31 | 0 | 273109.81 | -29490.5 | 100% | 112.1% | 90990.19 | 24.99% | 0 | 0 | 0
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Alexis Nixon | 08/14/2026 | 18000 | 18000 | 15244.1 | 12312 | 12312 | 0 | 22722.22 | -10410.22 | 100% | 184.5% | -4722.22 | -26.23% | 14218.55 | 69.72 | 2811.5
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 08/21/2026 | 194900 | 187591.25 | 187591.25 | 131089.74 | 131089.74 | 0 | 126178.41 | 4911.33 | 96.3% | 96.25% | 68721.59 | 35.26% | 0 | 0 | 0
24-PC-41534 | Badger Hollow Architectural History Survey | On Hold | Fixed fee | Coastal Bend | Duane Ballard |  | 795200 | 467736.64 | 467736.64 | 579859.84 | 579859.84 | 0 | 341062.79 | 238797.05 | 58.8% | 58.82% | 454137.21 | 57.11% | 0 | 0 | 0
24-PC-41555 | Phase III: Pine Hollow Solar Built Environment Survey | Final Billing/Invoice | Time and material | Coastal Bend | Alexis Nixon |  | 38200 | 25976 | 25976 | 27011.22 | 27011.22 | 0 | 33706.85 | -6695.63 | 68% | 124.8% | 4493.15 | 11.76% | 0 | 0 | 0
24-PC-41572 | Task Order 13: Plover Cove Water Main Architectural History Survey | On Hold | Fixed fee | Coastal Bend | Steve Rubio |  | 126800 | 89432.04 | 89432.04 | 95391.63 | 89204.36 | 6187.27 | 67280.28 | 28111.35 | 70.5% | 70.53% | 59519.72 | 46.94% | 0 | 0 | 0
24-PC-41701 | Cedar Hollow Wastewater Plant - Data Recovery | On Hold | Fixed fee | Built Environment | Kathleen Cabrera |  | 189100 | 161718.32 | 161718.32 | 119908.31 | 119908.31 | 0 | 102542.43 | 17365.88 | 85.5% | 85.52% | 86557.57 | 45.77% | 0 | 0 | 0
24-PC-41886 | On-Call: Pebble Beach Road Canal Lining Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Melody Holloway |  | 67500 | 43694 | 43694 | 46824.75 | 46824.75 | 0 | 29307.2 | 17517.55 | 64.7% | 62.59% | 38192.8 | 56.58% | 1553.29 | 0 | 2114
24-PC-41904 | Falcon Mesa Battery Storage - Architectural History Survey | Final Billing/Invoice | Fixed fee | Built Environment | Jesse Maynard |  | 31500 | 31500 | 31500 | 21889.35 | 21889.35 | 0 | 21624.49 | 264.86 | 100% | 98.79% | 9875.51 | 31.35% | 0 | 0 | 381.15
24-PC-41969 | Windmill Flat Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Built Environment | Melody Holloway |  | 216500 | 143864.25 | 143864.25 | 161335.8 | 161335.8 | 0 | 107206.67 | 54129.13 | 66.4% | 66.45% | 109293.33 | 50.48% | 791.09 | 0 | 1060.85
24-PC-42121 | Oak Terrace Substation Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Kathleen Cabrera | 08/07/2026 | 267300 | 240703.65 | 240703.65 | 208453.84 | 189453.96 | 18999.88 | 187719.43 | 20734.41 | 90% | 90.05% | 79580.57 | 29.77% | 9687.18 | 0 | 12402.72
24-PC-42174 | Thistle Down Section 106 Consultation | On Hold | Time and material | Built Environment | Rickey Salas |  | 20800 | 14144 | 14144 | 14431.04 | 14431.04 | 0 | 6766.62 | 7664.42 | 68% | 46.89% | 14033.38 | 67.47% | 0 | 0 | 0
24-PC-42184 | Phase II: Granite Pass Substation Environmental Review Support | In Progress | Fixed fee | Built Environment | Rickey Salas |  | 25600 | 11246.08 | 11246.08 | 17986.56 | 17986.56 | 0 | 7901.19 | 10085.37 | 43.9% | 43.93% | 17698.81 | 69.14% | 0 | 0 | 0
24-PC-42267 | Aspen Ridge Bridge Replacement Paleontological Monitoring | On Hold | Fixed fee | Paleontology | Charlene Sparks |  | 49000 | 19325.6 | 19325.6 | 32797.59 | 30901.5 | 1896.09 | 12936.54 | 19861.05 | 39.4% | 39.44% | 36063.46 | 73.6% | 0 | 0 | 0
24-PC-42338 | Silver Lake Wastewater Plant Paleontological Monitoring | Final Billing/Invoice | Time and material | Paleontology | Travis Delgado |  | 21700 | 14756 | 14756 | 14751.66 | 14751.66 | 0 | 14816.12 | -64.46 | 68% | 100.4% | 6883.88 | 31.72% | 0 | 0 | 0
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 07/31/2026 | 263500 | 179180 | 179180 | 173567.45 | 173567.45 | 0 | 177335 | -3767.55 | 68% | 102.2% | 86165 | 32.7% | 0 | 0 | 0
24-PC-42495 | Kestrel Butte Battery Storage - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Paleontology | Charlene Sparks |  | 45900 | 28875.69 | 28875.69 | 35246.61 | 35246.61 | 0 | 22172.99 | 13073.62 | 62.9% | 62.91% | 23727.01 | 51.69% | 0 | 0 | 0
24-PC-42527 | Heron Marsh Maritime Remote Sensing Survey | Final Billing/Invoice | Time and material | Paleontology | Charlene Sparks |  | 31700 | 21556 | 21556 | 20415.55 | 16100.16 | 4315.39 | 18789.61 | 1625.94 | 68% | 92.04% | 12910.39 | 40.73% | 0 | 0 | 0
24-PC-42550 | Yarrow Point Paleontological Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 301300 | 201810.74 | 200636.36 | 216936 | 216936 | 0 | 145304.58 | 71631.42 | 67% | 66.98% | 155995.42 | 51.77% | 40547.32 | 381.59 | 55138.59
24-PC-42638 | Task Order 21: Plover Cove Transmission Line Maritime Remote Sensing Survey | On Hold | Fixed fee | Paleontology | Charlene Sparks |  | 417200 | 224578.76 | 224578.76 | 310521.96 | 310521.96 | 0 | 167147.98 | 143373.98 | 53.8% | 53.83% | 250052.02 | 59.94% | 0 | 0 | 0
24-PC-42674 | Foxglove Canal Lining Architectural History Survey | Lab/Curation | Time and material | Maritime | Rita Ayala |  | 156100 | 106148 | 106148 | 111589.34 | 92586.34 | 19003 | 57675.71 | 53913.63 | 68% | 51.69% | 98424.29 | 63.05% | 0 | 0 | 0
24-PC-42697 | On-Call: Dove Canyon Airport Apron GIS Mapping | Final Billing/Invoice | Time and material | Maritime | Rita Ayala |  | 120000 | 81600 | 81600 | 85241.3 | 67102.71 | 18138.59 | 69173.64 | 16067.66 | 68% | 81.15% | 50826.36 | 42.36% | 0 | 0 | 0
24-PC-42846 | On-Call: Juniper Wash Airport Apron Historic Resources Evaluation | Completed | Fixed fee | Maritime | Kyle Maynard |  | 161200 | 161200 | 161200 | 115644.05 | 95931.15 | 19712.9 | 119214.99 | -3570.94 | 100% | 103.1% | 41985.01 | 26.05% | 0 | 0 | 0
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 08/14/2026 | 639100 | 451268.51 | 451268.51 | 498050.63 | 498050.63 | 0 | 351673.07 | 146377.56 | 70.6% | 70.61% | 287426.93 | 44.97% | 0 | 0 | 0
24-PC-43116 | On-Call: Larkspur Airport Apron Phase II Testing | Final Reporting/Review | Fixed fee | Geospatial | Sylvia Callahan |  | 424400 | 287318.8 | 287318.8 | 314395.52 | 314395.52 | 0 | 212843.45 | 101552.07 | 67.7% | 67.7% | 211556.55 | 49.85% | 19742.13 | 0 | 26652.32
24-PC-43150 | Rushgrass Draw Architectural History Survey | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 07/31/2026 | 301500 | 244848.15 | 244848.15 | 222689.15 | 196120.08 | 26569.07 | 180855.17 | 41833.98 | 81.2% | 81.21% | 120644.83 | 40.01% | 20296.91 | 0 | 27466.65
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Geospatial | Sylvia Callahan | 07/31/2026 | 19700 | 13396 | 13396 | 14170.21 | 14170.21 | 0 | 18919.28 | -4749.07 | 68% | 133.5% | 780.72 | 3.96% | 0 | 0 | 0
24-PC-43251 | Phase III: Maple Fork Fiber Route Maritime Remote Sensing Survey | Final Billing/Invoice | Time and material | Meridian | Seth Zavala |  | 163100 | 110908 | 110908 | 112751.03 | 112751.03 | 0 | 96362.11 | 16388.92 | 68% | 85.46% | 66737.89 | 40.92% | 0 | 0 | 0
24-PC-43406 | Pine Hollow Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | Meridian | Seth Zavala |  | 38700 | 38700 | 38700 | 27987.84 | 27987.84 | 0 | 24661.43 | 3326.41 | 100% | 88.11% | 14038.57 | 36.28% | 0 | 0 | 4601.43
24-PC-43670 | Granite Pass Archaeological Testing | Final Reporting/Review | Fixed fee | Meridian Southwest | Lynn Tran | 07/31/2026 | 220400 | 155514.24 | 155514.24 | 168565.52 | 153066.64 | 15498.88 | 118945.86 | 49619.66 | 70.6% | 70.56% | 101454.14 | 46.03% | 0 | 0 | 0
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | In Progress | Time and material | Meridian Southwest | Lynn Tran | 09/11/2026 | 1003600 | 682448 | 682448 | 771166.24 | 771166.24 | 0 | 614867.84 | 156298.4 | 68% | 79.73% | 388732.16 | 38.73% | 0 | 0 | 0
24-PC-43719 | On-Call: Juniper Wash Wastewater Plant Historic Resources Evaluation | Final Reporting/Review | Time and material | Meridian Southwest | Harold Chaney | 08/07/2026 | 382100 | 259828 | 259828 | 239599.17 | 197376 | 42223.17 | 170624.75 | 68974.42 | 68% | 71.21% | 211475.25 | 55.35% | 0 | 0 | 0
24-PC-43782 | Stone Mill Cultural Resources Assessment | Completed | Time and material | Meridian Southwest | Harold Chaney |  | 571500 | 388620 | 388620 | 411773.03 | 332471.04 | 79301.99 | 443050.33 | -31277.3 | 68% | 107.6% | 128449.67 | 22.48% | 0 | 0 | 0
24-PC-43786 | Task Order 3: Wren Hollow Canal Lining Architectural History Survey | Lab/Curation | Fixed fee | Meridian Southwest | Alan Gay |  | 220400 | 144053.44 | 144053.44 | 123791.36 | 113687.28 | 10104.08 | 80906.2 | 42885.16 | 65.4% | 65.36% | 139493.8 | 63.29% | 0 | 0 | 0
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 0 | 0 | 0 | 187528 | 187528 | 0 | 134454.77 | 53073.23 | 0% | 71.7% | -134454.77 | 0% | 0 | 0 | 0
24-PC-44022 | Sea Oat Historic Resources Evaluation | Transferred Entity | Time and material | NH Gulf (USD) | Vanessa Duarte |  | 0 | 0 | 0 | 625022.97 | 541701.35 | 83321.62 | 345106.15 | 279916.82 | 0% | 55.21% | -345106.15 | 0% | 0 | 0 | 0
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 09/18/2026 | 0 | 0 | 0 | 194222.35 | 194222.35 | 0 | 243036.39 | -48814.04 | 0% | 125.1% | -243036.39 | 0% | 90133.75 | 0 | 0
24-PC-44158 | Saltgrass Environmental Review Support | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 0 | 0 | 0 | 15583.44 | 15583.44 | 0 | 16044.04 | -460.6 | 0% | 103% | -16044.04 | 0% | 7265.52 | 0 | 0
25-PC-30034 | On-Call: Wren Hollow Wastewater Plant GIS Mapping | Final Reporting/Review | Fixed fee | Big Sky | Bob Frye |  | 101900 | 69842.26 | 69842.26 | 74162.82 | 74162.82 | 0 | 50829.46 | 23333.36 | 68.5% | 68.54% | 51070.54 | 50.12% | 18207.71 | 0 | 25016.45
25-PC-30077 | Phase II: Tamarack Housing Development Phase I Survey | In Progress | Time and material | Big Sky | Carl Barajas |  | 103400 | 103400 | 103400 | 71293.1 | 51740.95 | 19552.15 | 65644.01 | 5649.09 | 100% | 92.08% | 37755.99 | 36.51% | 32939.73 | 0 | 46633.4
25-PC-30140 | Windmill Flat Cell Tower - GIS Mapping | In Progress | Time and material | Big Sky | Carl Barajas |  | 257200 | 121129.05 | 121129.05 | 165353.88 | 165353.88 | 0 | 95517.33 | 69836.55 | 47.1% | 57.77% | 161682.67 | 62.86% | 13430.87 | 0 | 22364.25
25-PC-30204 | Maple Fork Phase I Survey | Final Billing/Invoice | Time and material | Big Sky | Brendan Melton |  | 179400 | 121992 | 121992 | 124220.26 | 114471 | 9749.26 | 96161.49 | 28058.77 | 68% | 77.41% | 83238.51 | 46.4% | 0 | 0 | 0
25-PC-30254 | Task Order 16: Coyote Springs Reservoir Class III Survey | Final Reporting/Review | Time and material | Big Sky | Brendan Melton | 08/14/2026 | 77100 | 51372.6 | 51372.6 | 49529.04 | 49529.04 | 0 | 35308.95 | 14220.09 | 66.6% | 71.29% | 41791.05 | 54.2% | 10753.98 | 0 | 18528
25-PC-30345 | Wildrye Phase II Testing | In Progress | Fixed fee | Big Sky | Brendan Melton |  | 160400 | 130998.68 | 130998.68 | 92631 | 92631 | 0 | 75656.14 | 16974.86 | 81.7% | 81.67% | 84743.86 | 52.83% | 29819.29 | 0 | 51632.76
25-PC-30348 | Phase II: Pine Hollow Wind Farm Environmental Review Support | In Progress | Fixed fee | Big Sky | Carl Barajas |  | 20800 | 13345.28 | 13345.28 | 15194.4 | 15194.4 | 0 | 9749.45 | 5444.95 | 64.2% | 64.16% | 11050.55 | 53.13% | 0 | 0 | 0
25-PC-30418 | Dove Canyon Wind Farm Class III Survey | Final Reporting/Review | Fixed fee | Big Sky | Brendan Melton |  | 344800 | 249221.44 | 249221.44 | 233309.47 | 170518.18 | 62791.29 | 168637.5 | 64671.97 | 72.3% | 72.28% | 176162.5 | 51.09% | 25174.49 | 0 | 37203.92
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway | 09/18/2026 | 19700 | 19700 | 17105.05 | 13027.61 | 13027.61 | 0 | 13683.52 | -655.91 | 100% | 105% | 6016.48 | 30.54% | 9615.92 | 3045.55 | 10954.71
25-PC-30694 | Rushgrass Draw Class III Survey | Completed | Fixed fee | Bluegrass | Kiara Gillespie |  | 358200 | 358200 | 358200 | 267073.92 | 267073.92 | 0 | 347196.1 | -80122.18 | 100% | 130% | 11003.9 | 3.07% | 0 | 0 | 0
25-PC-30717 | Phase II: Riverbend Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 08/21/2026 | 324100 | 274771.98 | 255801.54 | 205678.64 | 166411.98 | 39266.66 | 174373.12 | 31305.52 | 84.8% | 84.78% | 149726.88 | 46.2% | 160894.15 | 8562.22 | 234572.99
25-PC-30725 | Slate Ridge Paleontological Monitoring | Completed | Time and material | Bluegrass | Kiara Gillespie |  | 7400 | 5032 | 5032 | 4916.56 | 4916.56 | 0 | 6391.53 | -1474.97 | 68% | 130% | 1008.47 | 13.63% | 0 | 0 | 0
25-PC-30739 | Saltgrass Solar Class III Survey | Final Reporting/Review | Fixed fee | Bluegrass | Alice Galloway |  | 244200 | 124346.64 | 124346.64 | 214896 | 214896 | 0 | 109432.28 | 105463.72 | 50.9% | 50.92% | 134767.72 | 55.19% | 36309 | 0 | 41245.38
25-PC-30772 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 07/31/2026 | 63300 | 63300 | 63300 | 43065.84 | 35870.85 | 7194.99 | 56416.91 | -13351.07 | 100% | 131% | 6883.09 | 10.87% | 37575.79 | 0 | 35606.25
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 09/11/2026 | 131000 | 131000 | 122522.64 | 85464.4 | 85464.4 | 0 | 90183.9 | -4719.5 | 100% | 105.5% | 40816.1 | 31.16% | 85328 | 6012.38 | 115081.84
25-PC-30824 | Task Order 2: Lantern Bay Fiber Route Environmental Review Support | In Progress | Fixed fee | Bluegrass | Alice Galloway |  | 206400 | 142477.92 | 142477.92 | 145641.07 | 109553 | 36088.07 | 100541.75 | 45099.32 | 69% | 69.03% | 105858.25 | 51.29% | 0 | 0 | 0
25-PC-30928 | Tansy Flat Bridge Replacement Cultural Resources Monitoring | On Hold | Fixed fee | Bluegrass | Kiara Gillespie |  | 71900 | 57757.27 | 57757.27 | 53817.15 | 53817.15 | 0 | 43233.51 | 10583.64 | 80.3% | 80.33% | 28666.49 | 39.87% | 0 | 0 | 0
25-PC-31024 | Rushgrass Draw Environmental Review Support | On Hold | Fixed fee | Bluegrass | Alice Galloway |  | 770600 | 16567.9 | 16567.9 | 514826.47 | 380598.76 | 134227.71 | 11092.84 | 503733.63 | 2.1% | 2.15% | 759507.16 | 98.56% | 0 | 0 | 0
25-PC-31109 | Riverbend GIS Mapping | In Progress | Time and material | Cascade | Cassidy Gay | 07/31/2026 | 174700 | 174700 | 154905.3 | 109484.49 | 109484.49 | 0 | 162892.26 | -53407.77 | 100% | 148.8% | 11807.74 | 6.76% | 143057.91 | 12144.67 | 132194.3
25-PC-31114 | Granite Pass Built Environment Survey | In Progress | Time and material | Cascade | Jean Cooke | 08/28/2026 | 229400 | 179308.8 | 179308.8 | 157964.84 | 157964.84 | 0 | 127618.8 | 30346.04 | 78.2% | 80.79% | 101781.2 | 44.37% | 31586.76 | 0 | 43504
25-PC-31144 | Heron Marsh Bridge Replacement Section 106 Consultation | Completed | Time and material | Cascade | Jeff Spence |  | 78700 | 53516 | 53516 | 54208.56 | 54208.56 | 0 | 48724.57 | 5483.99 | 68% | 89.88% | 29975.43 | 38.09% | 0 | 0 | 0
25-PC-31180 | Blue Heron Environmental Review Support | In Progress | Fixed fee | Cascade | Preston Duarte | 07/31/2026 | 80000 | 80000 | 69747.43 | 60701.89 | 45712.3 | 14989.59 | 64096.36 | -3394.47 | 100% | 105.6% | 15903.64 | 19.88% | 44681.46 | 4542.45 | 44163.43
25-PC-31242 | Sage Flat Fiber Route - Class III Survey | In Progress | Fixed fee | Cascade | Gene Nixon |  | 398600 | 143216.98 | 139744.36 | 273446.93 | 244020.48 | 29426.45 | 98245.95 | 175200.98 | 35.9% | 35.93% | 300354.05 | 75.35% | 70242.38 | 1438.14 | 98927.72
25-PC-31263 | Dove Canyon Water Main Phase I Survey | Lab/Curation | Time and material | Cascade | Cassidy Gay | 08/28/2026 | 203400 | 177142 | 173315.81 | 139410.36 | 139410.36 | 0 | 122334.3 | 17076.06 | 87.1% | 87.75% | 81065.7 | 39.86% | 65569.69 | 549.7 | 108227.81
25-PC-31275 | Sage Flat Highway Widening Environmental Review Support | Final Billing/Invoice | Time and material | Cascade | Gene Nixon |  | 24900 | 7320.6 | 7320.6 | 18435.96 | 18435.96 | 0 | 23832.99 | -5397.03 | 29.4% | 129.3% | 1067.01 | 4.29% | 0 | 0 | 0
25-PC-31298 | On-Call: Lone Pine Water Main Class III Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 08/21/2026 | 48100 | 41495.87 | 41495.87 | 35361.72 | 33111 | 2250.72 | 30507.93 | 4853.79 | 86.3% | 86.27% | 17592.07 | 36.57% | 7983.17 | 0 | 10856.17
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 08/14/2026 | 23500 | 23500 | 23419.06 | 17263.1 | 17263.1 | 0 | 22123.1 | -4860 | 100% | 128.2% | 1376.9 | 5.86% | 19660.53 | 95.54 | 20067.96
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 08/28/2026 | 52000 | 52000 | 49983.77 | 38781.6 | 38781.6 | 0 | 51500.29 | -12718.69 | 100% | 132.8% | 499.71 | 0.96% | 36899.38 | 177.39 | 30405.77
25-PC-31420 | Cedar Hollow Wind Farm Archaeological Testing | Final Reporting/Review | Fixed fee | Cascade | Jeff Spence |  | 102200 | 55310.64 | 48011.31 | 68753.09 | 50928.84 | 17824.25 | 37206.7 | 31546.39 | 54.1% | 54.12% | 64993.3 | 63.59% | 36783.04 | 2726.29 | 47377.67
25-PC-31555 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 09/18/2026 | 69300 | 66417.12 | 60877.3 | 53097.66 | 53097.66 | 0 | 50888.1 | 2209.56 | 95.8% | 95.84% | 18411.9 | 26.57% | 45761.16 | 2736.81 | 54182.92
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 08/28/2026 | 16800 | 16800 | 16756.9 | 11810.4 | 11810.4 | 0 | 15531.6 | -3721.2 | 100% | 131.5% | 1268.4 | 7.55% | 12246.24 | 26.09 | 12083.14
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Final Reporting/Review | Time and material | Cascade | Jeff Spence |  | 30300 | 30300 | 30300 | 22049.31 | 22049.31 | 0 | 34568.28 | -12518.97 | 100% | 156.8% | -4268.28 | -14.09% | 13459.87 | 0 | 12665.4
25-PC-31775 | Task Order 26: Pine Hollow Bridge Replacement Cultural Resources Monitoring | In Progress | Time and material | Cascade | Cassidy Gay |  | 163200 | 89880 | 89880 | 98279.04 | 98279.04 | 0 | 45032.99 | 53246.05 | 55.1% | 45.82% | 118167.01 | 72.41% | 4888.73 | 0 | 8280
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | In Progress | Fixed fee | Cascade | Preston Duarte | 09/18/2026 | 216800 | 216800 | 202009.7 | 171337.04 | 171337.04 | 0 | 185663.62 | -14326.58 | 100% | 108.4% | 31136.38 | 14.36% | 152704.28 | 5948.27 | 160297.38
25-PC-31821 | Millbrook Environmental Review Support | Final Reporting/Review | Fixed fee | Cascade | Preston Duarte |  | 211400 | 171635.66 | 156607.64 | 183932.36 | 145726.92 | 38205.44 | 149340.49 | 34591.87 | 81.2% | 81.19% | 62059.51 | 29.36% | 140789.27 | 11346.68 | 146777.54
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 07/31/2026 | 40900 | 13987.8 | 13987.8 | 28728.16 | 28728.16 | 0 | 33002.57 | -4274.41 | 34.2% | 114.9% | 7897.43 | 19.31% | 0 | 0 | 0
25-PC-31905 | Raven Rock Mixed-Use Development Phase II Testing | Final Reporting/Review | Time and material | Cascade | Cassidy Gay |  | 331600 | 201880.85 | 185324.62 | 228107.64 | 228107.64 | 0 | 134532.55 | 93575.09 | 60.9% | 58.98% | 197067.45 | 59.43% | 122816.66 | 6303.62 | 170071.02
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Jason Oconnor | 08/21/2026 | 35200 | 35200 | 35200 | 24481.6 | 24481.6 | 0 | 39794.35 | -15312.75 | 100% | 162.5% | -4594.35 | -13.05% | 31652.01 | 0 | 22844.8
25-PC-31983 | Task Order 29: Juniper Wash Housing Development Cultural Resources Assessment | Final Billing/Invoice | Time and material | Chesapeake | Ian Maddox |  | 271500 | 152583 | 152583 | 186004.65 | 186004.65 | 0 | 189698.17 | -3693.52 | 56.2% | 102% | 81801.83 | 30.13% | 0 | 0 | 0
25-PC-32000 | Twin Buttes Built Environment Survey | On Hold | Fixed fee | Chesapeake | Ian Maddox |  | 61200 | 23910.84 | 23910.84 | 50312.52 | 50312.52 | 0 | 19654.73 | 30657.79 | 39.1% | 39.07% | 41545.27 | 67.88% | 0 | 0 | 0
25-PC-32021 | Oak Terrace Cultural Resources Monitoring | In Progress | Time and material | Chesapeake | Alexandria Wilkinson |  | 148200 | 97677.05 | 95737.05 | 111253.74 | 111253.74 | 0 | 57713.28 | 53540.46 | 65.9% | 51.88% | 90486.72 | 61.06% | 33298.92 | 652.15 | 52166.25
25-PC-32024 | Pine Hollow Historic Resources Evaluation | In Progress | Time and material | Chesapeake | Ian Maddox |  | 79500 | 57058 | 51094.33 | 57637.5 | 57637.5 | 0 | 41962.52 | 15674.98 | 71.8% | 72.8% | 37537.48 | 47.22% | 39066.22 | 960.51 | 47993.83
25-PC-32112 | Foxglove School Campus Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Chesapeake | Jason Oconnor |  | 37600 | 37600 | 37600 | 26165.84 | 26165.84 | 0 | 25192.3 | 973.54 | 100% | 96.28% | 12407.7 | 33% | 0 | 0 | 1398.72
25-PC-32144 | Ember Valley Archaeological Testing | Completed | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 12100 | 12100 | 12100 | 9169.38 | 9169.38 | 0 | 11920.19 | -2750.81 | 100% | 130% | 179.81 | 1.49% | 0 | 0 | 0
25-PC-32241 | Sumac Ridge Canal Lining Cultural Resources Monitoring | Final Reporting/Review | Time and material | Chesapeake | Bryan Mann |  | 331500 | 258073.5 | 253304.76 | 231983.7 | 231983.7 | 0 | 169942.8 | 62040.9 | 77.9% | 73.26% | 161557.2 | 48.74% | 86661.84 | 0 | 123688.26
25-PC-32264 | Tansy Flat Wastewater Plant Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Sandy Kerr | 09/18/2026 | 736000 | 500480 | 500480 | 420550.4 | 420550.4 | 0 | 341293.64 | 79256.76 | 68% | 81.15% | 394706.36 | 53.63% | 0 | 0 | 0
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | In Progress | Time and material | Chesapeake | Ian Maddox | 07/31/2026 | 201300 | 196916.6 | 185059.24 | 150874.35 | 150874.35 | 0 | 161800.48 | -10926.13 | 97.8% | 107.2% | 39499.52 | 19.62% | 118006.96 | 10127.94 | 153455.14
25-PC-32346 | Phase II: Aspen Ridge Mixed-Use Development Historic Resources Evaluation | Final Billing/Invoice | Time and material | Chesapeake | Jason Oconnor |  | 40200 | 27336 | 27336 | 29157.06 | 29157.06 | 0 | 26522.7 | 2634.36 | 68% | 90.96% | 13677.3 | 34.02% | 0 | 0 | 0
25-PC-32402 | Hawk Point Highway Widening - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Chesapeake | Sandy Kerr |  | 401300 | 237088.04 | 229423.8 | 353144 | 353144 | 0 | 208637.11 | 144506.89 | 59.1% | 59.08% | 192662.89 | 48.01% | 50595.49 | 5362.36 | 49842.05
25-PC-32447 | Pebble Beach Road Archaeological Testing | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 08/07/2026 | 88200 | 88200 | 88200 | 61772.24 | 55626.38 | 6145.86 | 76703.23 | -14930.99 | 100% | 124.2% | 11496.77 | 13.03% | 24839.21 | 0 | 14147.28
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | In Progress | Time and material | Chesapeake | Sandy Kerr |  | 118800 | 118800 | 111029.5 | 85013.28 | 85013.28 | 0 | 117591.53 | -32578.25 | 100% | 138.3% | 1208.47 | 1.02% | 110195.64 | 4367.02 | 103069.9
25-PC-32500 | On-Call: Dove Canyon Cell Tower Environmental Review Support | Final Billing/Invoice | Time and material | Chesapeake | Bryan Mann |  | 95700 | 38567.1 | 38567.1 | 67273.36 | 50743.55 | 16529.81 | 69534.49 | -2261.13 | 40.3% | 103.4% | 26165.51 | 27.34% | 0 | 0 | 0
25-PC-32630 | Wildrye Archaeological Testing | On Hold | Fixed fee | Chesapeake | Sandy Kerr |  | 865400 | 458229.3 | 458229.3 | 644117.22 | 644117.22 | 0 | 341055.04 | 303062.18 | 52.9% | 52.95% | 524344.96 | 60.59% | 0 | 0 | 0
25-PC-32750 | Elk Meadow Fiber Route Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Bryan Mann |  | 35500 | 27132.65 | 27028.9 | 25187.75 | 22000.77 | 3186.98 | 19250.92 | 5936.83 | 76.4% | 76.43% | 16249.08 | 45.77% | 9768.3 | 100.57 | 13663.15
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran | 08/28/2026 | 86500 | 83279.75 | 75767.65 | 62245.4 | 62245.4 | 0 | 49276.48 | 12968.92 | 96.3% | 79.16% | 37223.52 | 43.03% | 46675.78 | 8101 | 72307.65
25-PC-32795 | North Fork Water Main Architectural History Survey | In Progress | Time and material | Front Range | Reginald Vargas | 08/21/2026 | 16900 | 16900 | 16900 | 11650.86 | 11650.86 | 0 | 12884.7 | -1233.84 | 100% | 110.6% | 4015.3 | 23.76% | 5273.62 | 0 | 7537.4
25-PC-32819 | Eagle Bend Maritime Remote Sensing Survey | Final Billing/Invoice | Fixed fee | Front Range | Joanna Herrera |  | 49800 | 49800 | 49800 | 32021.4 | 32021.4 | 0 | 30314.49 | 1706.91 | 100% | 94.67% | 19485.51 | 39.13% | 0 | 0 | 2654.34
25-PC-32838 | Aspen Ridge Canal Lining - Curation | In Progress | Fixed fee | Front Range | Jeremy Tran | 08/07/2026 | 42600 | 39204.78 | 39204.78 | 33543.24 | 33543.24 | 0 | 30870.45 | 2672.79 | 92% | 92.03% | 11729.55 | 27.53% | 10294.53 | 0 | 13073.94
25-PC-32861 | Yarrow Point Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 09/11/2026 | 59200 | 59200 | 54224.79 | 41555.52 | 31694.67 | 9860.85 | 49895.36 | -8339.84 | 100% | 120.1% | 9304.64 | 15.72% | 35030.25 | 4644.01 | 33048.95
25-PC-32867 | Larkspur Levee Repair Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Devon Pitts |  | 144100 | 87944.23 | 85641.73 | 82727.81 | 82727.81 | 0 | 50486.75 | 32241.06 | 61% | 61.03% | 93613.25 | 64.96% | 36764.21 | 2209.06 | 61735.54
25-PC-32885 | Maple Fork Reservoir Historic Resources Evaluation | In Progress | Fixed fee | Front Range | Kimberly Daugherty |  | 1706300 | 419067.28 | 394166.15 | 1213962.27 | 1090543.53 | 123418.74 | 298115.17 | 915847.1 | 24.6% | 24.56% | 1408184.83 | 82.53% | 108418.75 | 7853.46 | 127471.46
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | In Progress | Fixed fee | Front Range | Jeremy Tran |  | 59600 | 59600 | 57228.13 | 51399.04 | 51399.04 | 0 | 74823.59 | -23424.55 | 100% | 145.6% | -15223.59 | -25.54% | 36560.81 | 1175.75 | 12861.89
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Lab/Curation | Time and material | Front Range | Jeremy Tran |  | 13300 | 13300 | 13300 | 8727.43 | 6386.48 | 2340.95 | 16463.41 | -7735.98 | 100% | 188.6% | -3163.41 | -23.79% | 15601.71 | 0 | 12369
25-PC-32926 | Tamarack Pipeline - Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran |  | 328400 | 68635.6 | 68635.6 | 212343.44 | 212343.44 | 0 | 61274.18 | 151069.26 | 20.9% | 28.86% | 267125.82 | 81.34% | 0 | 0 | 0
25-PC-32952 | Eagle Bend Wastewater Plant - Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty |  | 299000 | 149649.5 | 143659.49 | 202368.34 | 160514.68 | 41853.66 | 101282.84 | 101085.5 | 50% | 50.05% | 197717.16 | 66.13% | 55154.11 | 3024.02 | 75517.39
25-PC-33065 | Wren Hollow GIS Mapping | In Progress | Fixed fee | Front Range | Dean Velazquez | 08/07/2026 | 50400 | 45596.88 | 45596.88 | 40748.4 | 40748.4 | 0 | 36866.22 | 3882.18 | 90.5% | 90.47% | 13533.78 | 26.85% | 0 | 0 | 0
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | In Progress | Fixed fee | Front Range | Reginald Vargas |  | 767800 | 603874.7 | 603874.7 | 553046.34 | 553046.34 | 0 | 434972.87 | 118073.47 | 78.6% | 78.65% | 332827.13 | 43.35% | 1087.26 | 0 | 1535.6
25-PC-33105 | Redbud Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 08/07/2026 | 3500 | 3500 | 0 | 2324 | 2324 | 0 | 9006.2 | -6682.2 | 100% | 387.5% | -5506.2 | -157.3% | 8215.08 | 3306.43 | 0
25-PC-33136 | North Fork Historic Resources Evaluation | In Progress | Time and material | Front Range | Dean Velazquez |  | 33200 | 18065.15 | 17533.17 | 22378.06 | 19895.67 | 2482.39 | 12542.52 | 9835.54 | 54.4% | 56.05% | 20657.48 | 62.22% | 11611.32 | 419.65 | 16138.77
25-PC-33183 | Saltgrass Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez |  | 104500 | 101009.7 | 95400.33 | 79399.1 | 79399.1 | 0 | 76745.43 | 2653.67 | 96.7% | 96.66% | 27754.57 | 26.56% | 61530.5 | 1749.12 | 75378.13
25-PC-33206 | Larkspur Water Main - Phase II Testing | In Progress | Fixed fee | Front Range | Mindy Galvan |  | 48800 | 27459.76 | 25370.03 | 39449.92 | 39449.92 | 0 | 22196.74 | 17253.18 | 56.3% | 56.27% | 26603.26 | 54.51% | 13025.66 | 2489.61 | 14024.03
25-PC-33238 | Phase I: Foxglove Battery Storage Section 106 Consultation | Final Billing/Invoice | Time and material | Front Range | Reginald Vargas |  | 949900 | 545242.6 | 545242.6 | 642400.18 | 561552.6 | 80847.58 | 669394.35 | -26994.17 | 57.4% | 104.2% | 280505.65 | 29.53% | 0 | 0 | 0
25-PC-33294 | Fern Valley Substation - Built Environment Survey | In Progress | Fixed fee | Front Range | Joanna Herrera |  | 137200 | 83746.88 | 77650.18 | 91032.2 | 91032.2 | 0 | 55566.27 | 35465.93 | 61% | 61.04% | 81633.73 | 59.5% | 46954.11 | 4609 | 64671.06
25-PC-33321 | Hawk Point Section 106 Consultation | Final Billing/Invoice | Fixed fee | Front Range | Devon Pitts |  | 87200 | 87200 | 87200 | 61258 | 61258 | 0 | 52967.28 | 8290.72 | 100% | 86.47% | 34232.72 | 39.26% | 0 | 0 | 11798.16
25-PC-33332 | Willow Springs Cultural Resources Assessment | In Progress | Fixed fee | Front Range | Dean Velazquez |  | 91000 | 57721.3 | 54760.99 | 69587.7 | 69587.7 | 0 | 44141.81 | 25445.89 | 63.4% | 63.43% | 46858.19 | 51.49% | 28814.36 | 3951.06 | 34713.69
25-PC-33348 | Dove Canyon Cell Tower Phase II Testing | In Progress | Fixed fee | Front Range | Mindy Galvan |  | 161700 | 90374.13 | 90374.13 | 117749.94 | 117749.94 | 0 | 65815.88 | 51934.06 | 55.9% | 55.89% | 95884.12 | 59.3% | 15903.18 | 0 | 21829.5
25-PC-33367 | Slate Ridge Rail Siding Archaeological Testing | Lab/Curation | Time and material | Front Range | Dean Velazquez |  | 150800 | 55445.9 | 52242.62 | 100689.16 | 100689.16 | 0 | 32787.21 | 67901.95 | 36.8% | 32.56% | 118012.79 | 78.26% | 26804.91 | 2463.31 | 38972.22
25-PC-33412 | Tansy Flat Bridge Replacement - GIS Mapping | Final Billing/Invoice | Time and material | Front Range | Mindy Galvan |  | 1336200 | 428920.2 | 428920.2 | 914495.28 | 914495.28 | 0 | 868502.17 | 45993.11 | 32.1% | 94.97% | 467697.83 | 35% | 0 | 0 | 0
25-PC-33414 | On-Call: Falcon Mesa Substation Historic Resources Evaluation | Completed | Fixed fee | Front Range | Jeremy Tran |  | 81800 | 81800 | 81800 | 64082.12 | 64082.12 | 0 | 71490.79 | -7408.67 | 100% | 111.6% | 10309.21 | 12.6% | 0 | 0 | 0
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Front Range | Devon Pitts | 08/14/2026 | 41600 | 32406.4 | 32210.19 | 29136.64 | 29136.64 | 0 | 22697.51 | 6439.13 | 77.9% | 77.9% | 18902.49 | 45.44% | 6715 | 0 | 9392.59
25-PC-33522 | Yarrow Point Architectural History Survey | Final Reporting/Review | Time and material | Front Range | Jeremy Tran | 07/31/2026 | 61800 | 52972.45 | 50630.64 | 42270.22 | 36352.08 | 5918.14 | 34825.45 | 7444.77 | 85.7% | 82.39% | 26974.55 | 43.65% | 31991.96 | 0 | 47911.44
25-PC-33528 | Bramble Creek Wastewater Plant - Environmental Review Support | Final Billing/Invoice | Time and material | Front Range | Joanna Herrera |  | 138500 | 9695 | 9695 | 104844.5 | 104844.5 | 0 | 84801.75 | 20042.75 | 7% | 80.88% | 53698.25 | 38.77% | 0 | 0 | 0
25-PC-33535 | Sage Flat Data Recovery | On Hold | Fixed fee | Front Range | Joanna Herrera |  | 120500 | 78843.15 | 78843.15 | 91326.95 | 91326.95 | 0 | 59752.78 | 31574.17 | 65.4% | 65.43% | 60747.22 | 50.41% | 0 | 0 | 0
25-PC-33561 | Task Order 22: Badger Hollow Wastewater Plant Paleontological Monitoring | Final Billing/Invoice | Time and material | Front Range | Mindy Galvan |  | 132200 | 44551.4 | 44551.4 | 85348.32 | 85348.32 | 0 | 79206.42 | 6141.9 | 33.7% | 92.8% | 52993.58 | 40.09% | 0 | 0 | 0
25-PC-33640 | Tamarack Canal Lining - Cultural Resources Assessment | In Progress | Fixed fee | Front Range | Dean Velazquez |  | 1444500 | 432049.95 | 417334.9 | 1192145.85 | 1192145.85 | 0 | 356520.28 | 835625.57 | 29.9% | 29.91% | 1087979.72 | 75.32% | 104435.2 | 7329.26 | 111823.15
25-PC-33680 | Quail Run School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Front Range | Kimberly Daugherty |  | 106800 | 42570.48 | 37483.28 | 80014.56 | 80014.56 | 0 | 31893.67 | 48120.89 | 39.9% | 39.86% | 74906.33 | 70.14% | 21355.84 | 3731.02 | 23417.72
25-PC-33744 | Blue Heron Canal Lining - Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert |  | 87100 | 64332.06 | 64332.06 | 60133.84 | 60133.84 | 0 | 44412.55 | 15721.29 | 73.9% | 73.86% | 42687.45 | 49.01% | 17210.98 | 0 | 24928.02
25-PC-33750 | Kestrel Butte Archaeological Testing | Transferred Entity | Fixed fee | Great Lakes | Kathleen Galvan |  | 69600 | 69600 | 64460.42 | 51302.16 | 51302.16 | 0 | 60286.74 | -8984.58 | 100% | 117.5% | 9313.26 | 13.38% | 57738.45 | 2533.28 | 61001.3
25-PC-33795 | Phase I: Sage Flat Park Improvements Cultural Resources Monitoring | Final Billing/Invoice | Fixed fee | Great Lakes | Jeff Pugh |  | 174500 | 174500 | 174500 | 106392.65 | 106392.65 | 0 | 103920.48 | 2472.17 | 100% | 97.68% | 70579.52 | 40.45% | 0 | 0 | 4048.4
25-PC-33798 | On-Call: Harbor View Wind Farm Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Great Lakes | Brendan Padilla |  | 155300 | 82914.67 | 80025.19 | 128215.68 | 128215.68 | 0 | 68449.64 | 59766.04 | 53.4% | 53.39% | 86850.36 | 55.92% | 34369.76 | 1535.96 | 38746.45
25-PC-33827 | Millbrook Transmission Line - Built Environment Survey | On Hold | Fixed fee | Great Lakes | Nathan Lambert |  | 132500 | 18086.25 | 18086.25 | 103820.06 | 80475.2 | 23344.86 | 14173.73 | 89646.33 | 13.7% | 13.65% | 118326.27 | 89.3% | 0 | 0 | 0
25-PC-33841 | Juniper Wash Built Environment Survey | In Progress | Fixed fee | Great Lakes | Kathleen Galvan |  | 586500 | 366034.65 | 366034.65 | 416356.35 | 416356.35 | 0 | 259867.95 | 156488.4 | 62.4% | 62.41% | 326632.05 | 55.69% | 19199.02 | 0 | 27037.65
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Final Reporting/Review | Fixed fee | Great Lakes | Geoffrey Fernandez |  | 15200 | 15200 | 15200 | 11021.49 | 9579.99 | 1441.5 | 11383.28 | -361.79 | 100% | 103.3% | 3816.72 | 25.11% | 3923.51 | 0 | 4912.64
25-PC-33855 | Creosote Draw Rail Siding - Paleontological Monitoring | Final Reporting/Review | Time and material | Great Lakes | Karl Valenzuela |  | 34000 | 19618 | 18919.13 | 23930.44 | 21188.35 | 2742.09 | 13640.31 | 10290.13 | 57.7% | 57% | 20359.69 | 59.88% | 6317.48 | 225.62 | 10249.13
25-PC-33915 | Sage Flat Archaeological Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes |  | 272400 | 183216.24 | 176595.09 | 198225.48 | 198225.48 | 0 | 133333.04 | 64892.44 | 67.3% | 67.26% | 139066.96 | 51.05% | 61959.21 | 1200.28 | 78503.85
25-PC-33919 | Task Order 18: Coyote Springs Water Main Curation | Completed | Fixed fee | Great Lakes | Kathleen Galvan |  | 45500 | 45500 | 45500 | 26949.65 | 26949.65 | 0 | 30677.44 | -3727.79 | 100% | 113.8% | 14822.56 | 32.58% | 0 | 0 | 0
25-PC-33922 | Slate Ridge Data Recovery | In Progress | Fixed fee | Great Lakes | Nathan Lambert |  | 22100 | 22100 | 22100 | 16113.11 | 16113.11 | 0 | 33890.09 | -17776.98 | 100% | 210.3% | -11790.09 | -53.35% | 33271.16 | 0 | 21251.36
25-PC-33969 | Sumac Ridge Archaeological Testing | In Progress | Fixed fee | Great Lakes | Leonard Mejia |  | 13200 | 7814.4 | 7814.4 | 10134.96 | 10134.96 | 0 | 5999.73 | 4135.23 | 59.2% | 59.2% | 7200.27 | 54.55% | 191.14 | 0 | 249.48
25-PC-34036 | Kestrel Butte Battery Storage - Phase I Survey | Lab/Curation | Time and material | Great Lakes | Gina Beltran |  | 62300 | 54230.15 | 47936.1 | 41495.74 | 36709.53 | 4786.21 | 38677.3 | 2818.44 | 87% | 93.21% | 23622.7 | 37.92% | 30152.07 | 3152.12 | 36223.7
25-PC-34077 | Sage Flat Levee Repair Class III Survey | In Progress | Fixed fee | Great Lakes | Leonard Mejia |  | 580500 | 289843.65 | 272107.91 | 459697.95 | 459697.95 | 0 | 229510.93 | 230187.02 | 49.9% | 49.93% | 350989.07 | 60.46% | 181052.46 | 16093.64 | 210923.21
25-PC-34088 | Timber Gap Harbor Dredging Cultural Resources Monitoring | In Progress | Time and material | Great Lakes | Leonard Mejia |  | 47300 | 32164 | 32164 | 29041.82 | 26577.06 | 2464.76 | 17359.62 | 11682.2 | 68% | 59.77% | 29940.38 | 63.3% | 0 | 0 | 0
25-PC-34090 | Thistle Down Data Recovery | In Progress | Time and material | Great Lakes | Geoffrey Fernandez |  | 66200 | 34066.3 | 34066.3 | 46862.98 | 46862.98 | 0 | 24068 | 22794.98 | 51.5% | 51.36% | 42132 | 63.64% | 10098.36 | 0 | 13279.5
25-PC-34144 | On-Call: Dove Canyon School Campus Phase II Testing | Final Billing/Invoice | Fixed fee | Great Lakes | Karl Valenzuela |  | 23400 | 23400 | 23400 | 16230.24 | 16230.24 | 0 | 19243.13 | -3012.89 | 100% | 118.6% | 4156.87 | 17.76% | 0 | 0 | 0
25-PC-34151 | Bramble Creek Fiber Route Cultural Resources Monitoring | In Progress | Time and material | Great Lakes | Angelica Cervantes |  | 505100 | 190049.9 | 181895.54 | 334224.67 | 334224.67 | 0 | 126809.68 | 207414.99 | 37.6% | 37.94% | 378290.32 | 74.89% | 48838.98 | 3597.88 | 71278.64
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Geoffrey Fernandez |  | 53000 | 53000 | 53000 | 36718.4 | 36718.4 | 0 | 42629.29 | -5910.89 | 100% | 116.1% | 10370.71 | 19.57% | 21352.45 | 0 | 24380
25-PC-34374 | Tansy Flat Reservoir Cultural Resources Assessment | In Progress | Time and material | Great Lakes | Gina Beltran |  | 14100 | 5160.6 | 5160.6 | 9871.41 | 9871.41 | 0 | 3661.74 | 6209.67 | 36.6% | 37.09% | 10438.26 | 74.03% | 0 | 0 | 0
25-PC-34382 | Meadowlark Paleontological Monitoring | Completed | Time and material | Great Lakes | Gina Beltran |  | 34600 | 415.2 | 415.2 | 26125.87 | 21533.61 | 4592.26 | 33963.63 | -7837.76 | 1.2% | 130% | 636.37 | 1.84% | 0 | 0 | 0
25-PC-34451 | North Fork Curation | In Progress | Time and material | Great Lakes | Robin Mercado |  | 46400 | 46400 | 46400 | 32526.4 | 32526.4 | 0 | 41685.4 | -9159 | 100% | 128.2% | 4714.6 | 10.16% | 37409.56 | 0 | 40228.8
25-PC-34537 | Raven Rock Harbor Dredging - Paleontological Monitoring | On Hold | Fixed fee | Great Lakes | Jeff Pugh |  | 78900 | 34787.01 | 34787.01 | 63481.3 | 57549.32 | 5931.98 | 27987.47 | 35493.83 | 44.1% | 44.09% | 50912.53 | 64.53% | 0 | 0 | 0
25-PC-34652 | Coyote Springs Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Gina Beltran | 07/31/2026 | 210700 | 176145.2 | 157854.18 | 180928.09 | 180928.09 | 0 | 151256.79 | 29671.3 | 83.6% | 83.6% | 59443.21 | 28.21% | 142347.68 | 8043.53 | 147487.74
25-PC-34681 | Hawk Point Pipeline Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Brendan Padilla |  | 715200 | 264695.52 | 240939.56 | 430908 | 430908 | 0 | 159498.08 | 271409.92 | 37% | 37.01% | 555701.92 | 77.7% | 150827.24 | 13252.41 | 226564.04
25-PC-34732 | Thistle Down Trail Architectural History Survey | In Progress | Fixed fee | Great Lakes | Geoffrey Fernandez |  | 101800 | 62433.94 | 62433.94 | 76441.62 | 76441.62 | 0 | 46880.67 | 29560.95 | 61.3% | 61.33% | 54919.33 | 53.95% | 0 | 0 | 0
25-PC-34768 | On-Call: Oak Terrace Wastewater Plant Section 106 Consultation | Final Billing/Invoice | Time and material | Great Lakes | Angelica Cervantes |  | 119400 | 29730.6 | 29730.6 | 88654.5 | 88654.5 | 0 | 114603.2 | -25948.7 | 24.9% | 129.3% | 4796.8 | 4.02% | 0 | 0 | 0
25-PC-34772 | Windmill Flat Paleontological Monitoring | Final Reporting/Review | Time and material | Great Lakes | Brendan Padilla |  | 186900 | 20889.75 | 18840.73 | 126437.85 | 126437.85 | 0 | 11925.12 | 114512.73 | 11.2% | 9.43% | 174974.88 | 93.62% | 2874 | 1999.88 | 2019.73
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | In Progress | Time and material | Great Lakes | Gina Beltran | 09/04/2026 | 82200 | 82200 | 65071.92 | 51638.04 | 51638.04 | 0 | 83204.3 | -31566.26 | 100% | 161.1% | -1004.3 | -1.22% | 69024.31 | 12320.78 | 43699.92
25-PC-34843 | Elk Meadow Highway Widening Data Recovery | Final Billing/Invoice | Fixed fee | Gulf Coast | Bernard Erickson |  | 188000 | 188000 | 188000 | 136544.4 | 136544.4 | 0 | 132593.97 | 3950.43 | 100% | 97.11% | 55406.03 | 29.47% | 0 | 0 | 5433.2
25-PC-34850 | Thistle Down Section 106 Consultation | In Progress | Time and material | Gulf Coast East | Wyatt Erickson | 08/21/2026 | 201300 | 129963.25 | 120850.25 | 117035.82 | 117035.82 | 0 | 94500.26 | 22535.56 | 64.6% | 80.74% | 106799.74 | 53.06% | 84456.18 | 6139.94 | 105752.75
25-PC-34871 | Willow Springs GIS Mapping | Lab/Curation | Fixed fee | Gulf Coast East | Sean Jennings |  | 338100 | 194779.41 | 173584.4 | 260979.39 | 260979.39 | 0 | 150361.8 | 110617.59 | 57.6% | 57.61% | 187738.2 | 55.53% | 144811.96 | 12430.72 | 166382.87
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Wyatt Erickson |  | 224400 | 157798.08 | 157798.08 | 165046.2 | 165046.2 | 0 | 116067.93 | 48978.27 | 70.3% | 70.32% | 108332.07 | 48.28% | 6815.89 | 0 | 9267.72
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 09/04/2026 | 71400 | 71400 | 71400 | 48880.44 | 48880.44 | 0 | 56947.79 | -8067.35 | 100% | 116.5% | 14452.21 | 20.24% | 24380.62 | 0 | 23419.2
25-PC-35084 | On-Call: Fern Valley Wastewater Plant Class III Survey | Final Reporting/Review | Fixed fee | Gulf Coast East | Bernard Erickson |  | 204900 | 142528.44 | 137085.87 | 133588.01 | 98343.72 | 35244.29 | 92924.36 | 40663.65 | 69.6% | 69.56% | 111975.64 | 54.65% | 63901.45 | 2122.06 | 92561.1
25-PC-35131 | Tamarack Phase II Testing | In Progress | Fixed fee | Gulf Coast | Bernard Erickson |  | 311900 | 130966.81 | 130966.81 | 227562.24 | 227562.24 | 0 | 95549.55 | 132012.69 | 42% | 41.99% | 216350.45 | 69.37% | 16807.68 | 0 | 23049.41
25-PC-35138 | Foxglove Mixed-Use Development - Data Recovery | In Progress | Time and material | Gulf Coast East | Sean Jennings |  | 815000 | 593702.25 | 590691.86 | 517757.75 | 477272.64 | 40485.11 | 425247 | 92510.75 | 72.8% | 82.13% | 389753 | 47.82% | 170708.85 | 0 | 255726.86
25-PC-35168 | Quail Run Park Improvements - GIS Mapping | Completed | Time and material | Gulf Coast | Bernard Erickson |  | 330300 | 14202.9 | 14202.9 | 212151.69 | 212151.69 | 0 | 204097.59 | 8054.1 | 4.3% | 96.2% | 126202.41 | 38.21% | 0 | 0 | 0
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | In Progress | Time and material | Gulf Coast | Wyatt Erickson | 08/07/2026 | 33200 | 33200 | 31529.2 | 23495.64 | 23495.64 | 0 | 28098.77 | -4603.13 | 100% | 119.6% | 5101.23 | 15.37% | 20831.98 | 74.03 | 24291.6
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson |  | 49900 | 49900 | 47494.52 | 35982.89 | 35982.89 | 0 | 42125.73 | -6142.84 | 100% | 117.1% | 7774.27 | 15.58% | 39238 | 1683.19 | 43752.02
25-PC-35295 | Copper Flats Architectural History Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson |  | 80400 | 54672 | 54672 | 54551.4 | 54551.4 | 0 | 39686.68 | 14864.72 | 68% | 72.75% | 40713.32 | 50.64% | 0 | 0 | 0
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 08/21/2026 | 19400 | 19400 | 15409.48 | 13919.5 | 13919.5 | 0 | 36287.62 | -22368.12 | 100% | 260.7% | -16887.62 | -87.05% | 29011.93 | 3407.17 | 5269.1
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Courtney Daugherty |  | 25100 | 25100 | 24927.65 | 20032.31 | 20032.31 | 0 | 27206.94 | -7174.63 | 100% | 135.8% | -2106.94 | -8.39% | 22109.08 | 0 | 18539.7
25-PC-35431 | Task Order 26: Wildrye Mine Expansion Environmental Review Support | On Hold | Fixed fee | High Desert | Eileen Poole |  | 304700 | 8135.49 | 8135.49 | 252565.83 | 252565.83 | 0 | 6736.99 | 245828.84 | 2.7% | 2.67% | 297963.01 | 97.79% | 0 | 0 | 0
25-PC-35442 | Pebble Beach Road Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | High Desert | Eileen Poole |  | 86600 | 86600 | 86600 | 65071.24 | 65071.24 | 0 | 72181.81 | -7110.57 | 100% | 110.9% | 14418.19 | 16.65% | 0 | 0 | 0
25-PC-35470 | Lantern Bay Reservoir Data Recovery | Final Billing/Invoice | Time and material | High Desert | Jody Wang |  | 484000 | 47916 | 47916 | 325683.6 | 325683.6 | 0 | 348164.43 | -22480.83 | 9.9% | 106.9% | 135835.57 | 28.07% | 0 | 0 | 0
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | In Progress | Time and material | High Desert | Kathy Hurley | 08/07/2026 | 136900 | 136900 | 132838.07 | 90994.45 | 78522.66 | 12471.79 | 119032.95 | -28038.5 | 100% | 130.8% | 17867.05 | 13.05% | 111742.05 | 2047.58 | 123255.07
25-PC-35496 | Silver Lake Airport Apron Class III Survey | In Progress | Time and material | High Desert | Kathy Hurley |  | 15200 | 14910.4 | 14910.4 | 10132.32 | 10132.32 | 0 | 10426.69 | -294.37 | 98.1% | 102.9% | 4773.31 | 31.4% | 7557.98 | 0 | 10776
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox |  | 98800 | 77370.28 | 77370.28 | 78447.2 | 78447.2 | 0 | 61430.39 | 17016.81 | 78.3% | 78.31% | 37369.61 | 37.82% | 58511.36 | 0 | 73694.92
25-PC-35553 | Rushgrass Draw Rail Siding - Data Recovery | In Progress | Time and material | High Desert | Eileen Poole |  | 589900 | 446922.5 | 421582.2 | 444589.27 | 356163.6 | 88425.67 | 314340.18 | 130249.09 | 75.8% | 70.7% | 275559.82 | 46.71% | 190665.38 | 16213.73 | 280006.2
25-PC-35620 | Task Order 24: Hackberry Bend Solar Class III Survey | Completed | Time and material | High Desert | Jody Wang |  | 2007200 | 1364896 | 1364896 | 1423506.24 | 1423506.24 | 0 | 1286006.12 | 137500.12 | 68% | 90.34% | 721193.88 | 35.93% | 0 | 0 | 0
25-PC-35740 | Oak Terrace Transmission Line - Historic Resources Evaluation | In Progress | Fixed fee | High Desert | Kathy Hurley |  | 28600 | 572 | 572 | 15121.1 | 12638.3 | 2482.8 | 303.1 | 14818 | 2% | 2% | 28296.9 | 98.94% | 0 | 0 | 0
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 09/11/2026 | 204800 | 204800 | 187347.98 | 136396.8 | 136396.8 | 0 | 140077.69 | -3680.89 | 100% | 102.7% | 64722.31 | 31.6% | 117321.67 | 9399.63 | 153187.34
25-PC-35779 | Task Order 9: Juniper Wash Wastewater Plant Built Environment Survey | In Progress | Fixed fee | High Desert | Bridget Maddox | 08/21/2026 | 124800 | 103584 | 101478.5 | 84973.75 | 63196.65 | 21777.1 | 70526.09 | 14447.66 | 83% | 83% | 54273.91 | 43.49% | 48934.45 | 1131.52 | 69766.82
25-PC-35850 | Pebble Beach Road Environmental Review Support | Cost Tracking on Closed Project | Time and material | High Desert | Bridget Maddox |  | 53400 | 36312 | 36312 | 37978.08 | 37978.08 | 0 | 32074.27 | 5903.81 | 68% | 84.45% | 21325.73 | 39.94% | 0 | 0 | 0
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | In Progress | Fixed fee | High Desert | Jody Wang | 09/11/2026 | 83700 | 76761.27 | 76761.27 | 61050.78 | 61050.78 | 0 | 55992.16 | 5058.62 | 91.7% | 91.71% | 27707.84 | 33.1% | 8370.59 | 0 | 11475.27
25-PC-35958 | Task Order 20: Pebble Beach Road Levee Repair Class III Survey | Final Billing/Invoice | Fixed fee | High Desert | Jody Wang |  | 67300 | 67300 | 67300 | 54896.61 | 54896.61 | 0 | 61901.7 | -7005.09 | 100% | 112.8% | 5398.3 | 8.02% | 0 | 0 | 0
25-PC-35963 | Quail Run Substation - Section 106 Consultation | In Progress | Time and material | High Desert | Kathy Hurley | 08/21/2026 | 320000 | 290771 | 290771 | 216192 | 216192 | 0 | 202041.59 | 14150.41 | 90.9% | 93.45% | 117958.41 | 36.86% | 81231.37 | 0 | 131731
25-PC-35970 | Eagle Bend Wind Farm Phase II Testing | In Progress | Fixed fee | High Desert | Bridget Maddox |  | 53200 | 16359 | 16359 | 38886.26 | 35417.28 | 3468.98 | 11957.7 | 26928.56 | 30.7% | 30.75% | 41242.3 | 77.52% | 4999.65 | 0 | 6841.52
25-PC-36007 | Larkspur Rail Siding Phase II Testing | On Hold | Fixed fee | High Desert | Eileen Poole |  | 21700 | 212.66 | 212.66 | 16244.62 | 16244.62 | 0 | 159.18 | 16085.44 | 1% | 0.98% | 21540.82 | 99.27% | 0 | 0 | 0
25-PC-36030 | Stone Mill Solar Cultural Resources Monitoring | Completed | Time and material | High Desert | Bridget Maddox |  | 89200 | 46384 | 46384 | 57064.52 | 52267.27 | 4797.25 | 60255.01 | -3190.49 | 52% | 105.6% | 28944.99 | 32.45% | 0 | 0 | 0
25-PC-36051 | Riverbend Levee Repair Archaeological Testing | In Progress | Fixed fee | High Desert | Bridget Maddox |  | 405400 | 274617.96 | 274617.96 | 250415.58 | 250415.58 | 0 | 169641.96 | 80773.62 | 67.7% | 67.74% | 235758.04 | 58.15% | 1645.23 | 0 | 2635.1
25-PC-36071 | Task Order 12: Foxglove Transmission Line Archaeological Testing | Final Billing/Invoice | Fixed fee | High Desert | Eileen Poole |  | 245200 | 245200 | 245200 | 202167.4 | 202167.4 | 0 | 191722.88 | 10444.52 | 100% | 94.83% | 53477.12 | 21.81% | 0 | 0 | 12676.84
25-PC-36093 | Pine Hollow Pipeline Cultural Resources Assessment | Lab/Curation | Fixed fee | High Desert | Jody Wang |  | 213300 | 150611.13 | 149533.07 | 157884.66 | 157884.66 | 0 | 111476.29 | 46408.37 | 70.6% | 70.61% | 101823.71 | 47.74% | 39686.33 | 198.17 | 52545.56
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | In Progress | Time and material | High Desert | Kathy Hurley |  | 114200 | 114200 | 114200 | 78124.22 | 78124.22 | 0 | 79562.79 | -1438.57 | 100% | 101.8% | 34637.21 | 30.33% | 66771.49 | 0 | 96727.4
25-PC-36197 | Windmill Flat Rail Siding - Historic Resources Evaluation | On Hold | Fixed fee | High Desert | Eileen Poole |  | 35900 | 28777.44 | 28777.44 | 26935.77 | 26935.77 | 0 | 21592.01 | 5343.76 | 80.2% | 80.16% | 14307.99 | 39.86% | 0 | 0 | 0
25-PC-36251 | Kestrel Butte Environmental Review Support | Lab/Curation | Fixed fee | Island | Joan Mathis |  | 39200 | 39200 | 39200 | 30446.64 | 30446.64 | 0 | 49335.55 | -18888.91 | 100% | 162% | -10135.55 | -25.86% | 16518.48 | 0 | 0
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | In Progress | Time and material | Island | Joan Mathis |  | 28100 | 24522.2 | 24500.73 | 19141.72 | 19141.72 | 0 | 16573.11 | 2568.61 | 87.3% | 86.58% | 11526.89 | 41.02% | 12422.63 | 29.4 | 18262.53
25-PC-36313 | Task Order 27: Coyote Springs Solar Historic Resources Evaluation | Completed | Time and material | Island | Briana Melton |  | 135100 | 91868 | 91868 | 94691.59 | 94691.59 | 0 | 123099.07 | -28407.48 | 68% | 130% | 12000.93 | 8.88% | 0 | 0 | 0
25-PC-36332 | Goldfinch Data Recovery | In Progress | Fixed fee | Island | Briana Melton |  | 871000 | 472953 | 455814.95 | 618958.05 | 566005.77 | 52952.28 | 336119.33 | 282838.72 | 54.3% | 54.3% | 534880.67 | 61.41% | 94122.02 | 7795.07 | 115253.95
25-PC-36336 | Sea Oat Canal Lining Data Recovery | In Progress | Fixed fee | Island | Briana Melton |  | 36400 | 33364.24 | 29544.7 | 25854.92 | 25854.92 | 0 | 23699.14 | 2155.78 | 91.7% | 91.66% | 12700.86 | 34.89% | 18350.91 | 3531.34 | 22013.54
25-PC-36352 | Phase I: Plover Cove Substation Paleontological Monitoring | In Progress | Fixed fee | Island | Joan Mathis |  | 3262900 | 451585.36 | 413628.97 | 2263196.88 | 1903101.18 | 360095.7 | 313300.73 | 1949896.15 | 13.8% | 13.84% | 2949599.27 | 90.4% | 178151.41 | 19410.17 | 218833.84
25-PC-36366 | Lone Pine Solar Data Recovery | In Progress | Fixed fee | Island | Briana Melton |  | 119500 | 45517.55 | 41825.58 | 101598.9 | 101598.9 | 0 | 38701.28 | 62897.62 | 38.1% | 38.09% | 80798.72 | 67.61% | 29789.72 | 2435.28 | 31345.43
25-PC-36464 | Larkspur Highway Widening Cultural Resources Assessment | In Progress | Time and material | Island | Joan Mathis |  | 102300 | 76761.1 | 76761.1 | 72751.63 | 53089.29 | 19662.34 | 60185.29 | 12566.34 | 75% | 82.73% | 42114.71 | 41.17% | 4574.12 | 0 | 9550
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | In Progress | Fixed fee | Island | Becky Velazquez |  | 33100 | 33100 | 33100 | 25870.96 | 25870.96 | 0 | 34277.75 | -8406.79 | 100% | 132.5% | -1177.75 | -3.56% | 17816.25 | 0 | 12038.47
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | In Progress | Fixed fee | Island | Joan Mathis |  | 88300 | 68397.18 | 67497.4 | 54269.18 | 54269.18 | 0 | 42036.07 | 12233.11 | 77.5% | 77.46% | 46263.93 | 52.39% | 18606.93 | 282.12 | 29378.29
25-PC-36532 | Sparrow Hill Cell Tower - Architectural History Survey | On Hold | Fixed fee | Island | Joan Mathis |  | 67300 | 31980.96 | 31980.96 | 46773.5 | 46773.5 | 0 | 22227.54 | 24545.96 | 47.5% | 47.52% | 45072.46 | 66.97% | 0 | 0 | 0
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Becky Velazquez | 08/07/2026 | 116000 | 85573.2 | 85573.2 | 66050.4 | 66050.4 | 0 | 48723.63 | 17326.77 | 73.8% | 73.77% | 67276.37 | 58% | 0 | 0 | 0
25-PC-36637 | Lantern Bay Fiber Route Environmental Review Support | Final Billing/Invoice | Fixed fee | Lakeshore | Terrence Gillespie |  | 44400 | 44400 | 44400 | 36003.96 | 36003.96 | 0 | 29922.84 | 6081.12 | 100% | 83.11% | 14477.16 | 32.61% | 0 | 0 | 7499.16
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | In Progress | Time and material | Lakeshore | Lucas Benson |  | 181300 | 181300 | 174825.53 | 117609.31 | 117609.31 | 0 | 164790.18 | -47180.87 | 100% | 140.1% | 16509.82 | 9.11% | 120831.98 | 2885.36 | 116265.63
25-PC-36645 | Falcon Mesa Archaeological Testing | In Progress | Fixed fee | Lakeshore | Jeanette Riddle |  | 25400 | 25400 | 24158.24 | 20302.22 | 20302.22 | 0 | 38922.61 | -18620.39 | 100% | 191.7% | -13522.61 | -53.24% | 36410.28 | 446.02 | 21016.26
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | In Progress | Time and material | Lakeshore | Lucas Benson |  | 137400 | 108023.85 | 108023.85 | 99958.5 | 99958.5 | 0 | 83440.54 | 16517.96 | 78.6% | 83.48% | 53959.46 | 39.27% | 23260.61 | 0 | 40835.25
25-PC-36657 | Stone Mill Park Improvements Phase II Testing | Final Reporting/Review | Time and material | Lakeshore | Jeanette Riddle |  | 255700 | 128243.4 | 121473 | 186833.25 | 150017.49 | 36815.76 | 88980.55 | 97852.7 | 50.2% | 47.63% | 166719.45 | 65.2% | 47630.6 | 3946.05 | 74935.6
25-PC-36697 | Phase III: Juniper Wash Solar Built Environment Survey | Completed | Fixed fee | Lakeshore | Lucas Benson |  | 197400 | 197400 | 197400 | 133797.72 | 133797.72 | 0 | 127892.21 | 5905.51 | 100% | 95.59% | 69507.79 | 35.21% | 0 | 0 | 8705.34
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Final Reporting/Review | Fixed fee | Lakeshore | Jeanette Riddle |  | 74000 | 74000 | 66065.35 | 56358.4 | 56358.4 | 0 | 66079.16 | -9720.76 | 100% | 117.3% | 7920.84 | 10.7% | 53318.61 | 6922.06 | 49311.75
25-PC-36799 | Meadowlark Substation Phase I Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 09/18/2026 | 32900 | 32900 | 30883.36 | 26389.09 | 26389.09 | 0 | 33048.52 | -6659.43 | 100% | 125.2% | -148.52 | -0.45% | 23540.32 | 491.52 | 19029.49
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 09/04/2026 | 24200 | 24200 | 22550.8 | 16235.78 | 16235.78 | 0 | 26420.57 | -10184.79 | 100% | 162.7% | -2220.57 | -9.18% | 23824.58 | 238.55 | 18681.22
25-PC-36832 | Stone Mill Phase I Survey | In Progress | Fixed fee | Hill Country | Theresa Fernandez |  | 78400 | 44029.44 | 44029.44 | 52449.6 | 52449.6 | 0 | 29456.38 | 22993.22 | 56.2% | 56.16% | 48943.62 | 62.43% | 0 | 0 | 0
25-PC-36838 | Phase II: Granite Pass Highway Widening Environmental Review Support | Final Reporting/Review | Time and material | Hill Country | Samuel Wilkerson | 07/31/2026 | 216400 | 216400 | 203236.1 | 160499.18 | 119267.1 | 41232.08 | 158776.88 | 1722.3 | 100% | 98.93% | 57623.12 | 26.63% | 147255.87 | 10941.67 | 188953.7
25-PC-36876 | Kestrel Butte Wastewater Plant - GIS Mapping | Completed | Fixed fee | Hill Country | Samuel Wilkerson |  | 337000 | 337000 | 337000 | 240685.4 | 240685.4 | 0 | 312891.02 | -72205.62 | 100% | 130% | 24108.98 | 7.15% | 0 | 0 | 0
25-PC-36896 | Slate Ridge Pipeline Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Hill Country | Danielle Villanueva |  | 184200 | 184200 | 184200 | 117335.4 | 117335.4 | 0 | 139790.5 | -22455.1 | 100% | 119.1% | 44409.5 | 24.11% | 0 | 0 | 0
25-PC-36909 | Aspen Ridge Water Main Section 106 Consultation | Final Billing/Invoice | Fixed fee | Hill Country | Danielle Villanueva |  | 41900 | 41900 | 41900 | 30260.18 | 30260.18 | 0 | 31926.6 | -1666.42 | 100% | 105.5% | 9973.4 | 23.8% | 0 | 0 | 0
25-PC-36971 | North Fork Historic Resources Evaluation | Completed | Fixed fee | Hill Country | Suzanne Mcmillan |  | 85100 | 85100 | 85100 | 64888.75 | 64888.75 | 0 | 84355.38 | -19466.62 | 100% | 130% | 744.62 | 0.88% | 0 | 0 | 0
25-PC-36988 | Cedar Hollow Maritime Remote Sensing Survey | Final Billing/Invoice | Time and material | Hill Country | Gail Meza |  | 246000 | 51414 | 51414 | 173331.6 | 173331.6 | 0 | 162799.16 | 10532.44 | 20.9% | 93.92% | 83200.84 | 33.82% | 0 | 0 | 0
25-PC-36993 | Sandpiper Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | Hill Country | Danielle Villanueva |  | 702000 | 702000 | 702000 | 446191.2 | 446191.2 | 0 | 385770.37 | 60420.83 | 100% | 86.46% | 316229.63 | 45.05% | 0 | 0 | 95050.8
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | In Progress | Time and material | Hill Country | Glen Delacruz |  | 75400 | 75400 | 71354.11 | 50299.34 | 50299.34 | 0 | 90901.92 | -40602.58 | 100% | 180.7% | -15501.92 | -20.56% | 89564.25 | 930.44 | 69846.11
25-PC-37188 | On-Call: Lone Pine Airport Apron Cultural Resources Assessment | In Progress | Time and material | Hill Country | Suzanne Mcmillan |  | 131600 | 103670.5 | 103670.5 | 95554.76 | 95554.76 | 0 | 53871.13 | 41683.63 | 78.8% | 56.38% | 77728.87 | 59.06% | 8978.25 | 0 | 14182.5
25-PC-37359 | Bramble Creek Water Main Curation | Completed | Fixed fee | Hill Country | Danielle Villanueva |  | 228400 | 228400 | 228400 | 164950.48 | 164950.48 | 0 | 143914.59 | 21035.89 | 100% | 87.25% | 84485.41 | 36.99% | 0 | 0 | 29121
25-PC-37371 | Phase II: Ember Valley Water Main Class III Survey | In Progress | Fixed fee | Piedmont | Maria Parrish |  | 292700 | 126329.32 | 120692.53 | 199428.52 | 154432.08 | 44996.44 | 86077.44 | 113351.08 | 43.2% | 43.16% | 206622.56 | 70.59% | 77209.2 | 4210.42 | 107667.38
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | In Progress | Fixed fee | Piedmont | Maria Parrish |  | 59200 | 54913.92 | 54913.92 | 50698.88 | 50698.88 | 0 | 47030.53 | 3668.35 | 92.8% | 92.76% | 12169.47 | 20.56% | 23995.14 | 0 | 28013.44
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Cost Tracking on Closed Project | Time and material | Piedmont | Megan Pineda | 07/31/2026 | 83200 | 22297.6 | 22297.6 | 60186.88 | 60186.88 | 0 | 78242.94 | -18056.06 | 26.8% | 130% | 4957.06 | 5.96% | 0 | 0 | 0
25-PC-37487 | Sparrow Hill Airport Apron Environmental Review Support | Final Billing/Invoice | Fixed fee | Piedmont | Annette Vaughan |  | 43400 | 43400 | 43400 | 34525.12 | 25324.73 | 9200.39 | 25603.88 | 8921.24 | 100% | 74.16% | 17796.12 | 41% | 0 | 0 | 11214.56
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | In Progress | Time and material | Piedmont | Jody Chung | 08/28/2026 | 458200 | 311576 | 311576 | 301449.78 | 301449.78 | 0 | 240796.49 | 60653.29 | 68% | 79.88% | 217403.51 | 47.45% | 0 | 0 | 0
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Lab/Curation | Fixed fee | Piedmont | Jody Chung | 09/11/2026 | 21500 | 21500 | 20397.5 | 15617.6 | 15617.6 | 0 | 19499.41 | -3881.81 | 100% | 124.9% | 2000.59 | 9.31% | 18207.42 | 292.18 | 18619.45
25-PC-37544 | Sparrow Hill Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 09/04/2026 | 1009600 | 789709.12 | 789709.12 | 644730.56 | 644730.56 | 0 | 504318.97 | 140411.59 | 78.2% | 78.22% | 505281.03 | 50.05% | 0 | 0 | 0
25-PC-37612 | Elk Meadow Solar Historic Resources Evaluation | On Hold | Time and material | Piedmont | Maria Parrish |  | 134400 | 87628.8 | 87628.8 | 94725.12 | 94725.12 | 0 | 69378.25 | 25346.87 | 65.2% | 73.24% | 65021.75 | 48.38% | 0 | 0 | 0
25-PC-37630 | Goldfinch Solar Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Piedmont | Jody Chung |  | 528200 | 528200 | 528200 | 365998.97 | 324693.9 | 41305.07 | 475798.66 | -109799.69 | 100% | 130% | 52401.34 | 9.92% | 0 | 0 | 0
25-PC-37675 | Copper Flats Park Improvements - Phase I Survey | Final Billing/Invoice | Fixed fee | Piedmont | Megan Pineda |  | 129900 | 129900 | 129900 | 96138.99 | 96138.99 | 0 | 76435.27 | 19703.72 | 100% | 79.5% | 53464.73 | 41.16% | 0 | 0 | 26629.5
25-PC-37732 | Hawk Point Housing Development Class III Survey | In Progress | Fixed fee | Piedmont | Megan Pineda | 09/11/2026 | 72900 | 64100.97 | 59413.97 | 45824.94 | 45824.94 | 0 | 40294.47 | 5530.47 | 87.9% | 87.93% | 32605.53 | 44.73% | 33699.98 | 1453.4 | 48923.66
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Final Reporting/Review | Time and material | Piedmont | Maria Parrish |  | 72200 | 69466.7 | 69466.7 | 44893.96 | 44893.96 | 0 | 57390.52 | -12496.56 | 96.2% | 127.8% | 14809.48 | 20.51% | 15434.61 | 0 | 23908.5
25-PC-37841 | Coyote Springs Data Recovery | On Hold | Fixed fee | Piedmont | Annette Vaughan |  | 243900 | 59804.28 | 59804.28 | 144430.51 | 115129.95 | 29300.56 | 35409.46 | 109021.05 | 24.5% | 24.52% | 208490.54 | 85.48% | 0 | 0 | 0
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Megan Pineda |  | 7900 | 7900 | 7900 | 6020.59 | 6020.59 | 0 | 6629.3 | -608.71 | 100% | 110.1% | 1270.7 | 16.08% | 66.53 | 0 | 0
25-PC-37903 | Sandpiper Mine Expansion Curation | Final Billing/Invoice | Fixed fee | Piedmont | Jody Chung |  | 195600 | 195600 | 195600 | 128411.4 | 128411.4 | 0 | 166934.82 | -38523.42 | 100% | 130% | 28665.18 | 14.65% | 0 | 0 | 0
25-PC-37920 | Heron Marsh Mine Expansion Class III Survey | In Progress | Time and material | Piedmont | Maria Parrish |  | 138600 | 69844.2 | 64957.08 | 92806.56 | 92806.56 | 0 | 44711.28 | 48095.28 | 50.4% | 48.18% | 93888.72 | 67.74% | 29701.03 | 3017.52 | 43889.88
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 148100 | 109890.2 | 107447.04 | 106809.72 | 106809.72 | 0 | 79254.52 | 27555.2 | 74.2% | 74.2% | 68845.48 | 46.49% | 26843 | 2196.34 | 34774.37
25-PC-37979 | Pine Hollow Wind Farm - Built Environment Survey | Final Billing/Invoice | Fixed fee | Prairie | Sherry Lloyd |  | 230300 | 230300 | 230300 | 172720.13 | 151719.04 | 21001.09 | 202559.1 | -29838.97 | 100% | 117.3% | 27740.9 | 12.05% | 0 | 0 | 0
25-PC-37994 | Blue Heron Harbor Dredging - Curation | On Hold | Time and material | Prairie | Sherry Lloyd |  | 326300 | 80269.8 | 80269.8 | 217772.62 | 217772.62 | 0 | 62933.16 | 154839.46 | 24.6% | 28.9% | 263366.84 | 80.71% | 0 | 0 | 0
25-PC-38006 | Timber Gap Wastewater Plant Archaeological Testing | In Progress | Time and material | Prairie | Sherry Lloyd |  | 112000 | 46616.5 | 46616.5 | 75667.2 | 75667.2 | 0 | 36469.16 | 39198.04 | 41.6% | 48.2% | 75530.84 | 67.44% | 12970.71 | 0 | 17496.5
25-PC-38036 | Elk Meadow Mixed-Use Development - Maritime Remote Sensing Survey | Completed | Fixed fee | Prairie | Sherry Lloyd |  | 27300 | 27300 | 27300 | 23352.42 | 23352.42 | 0 | 30358.15 | -7005.73 | 100% | 130% | -3058.15 | -11.2% | 0 | 0 | 0
25-PC-38042 | Oak Terrace School Campus GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 07/31/2026 | 24300 | 20144.7 | 20144.7 | 19082.79 | 19082.79 | 0 | 15820.03 | 3262.76 | 82.9% | 82.9% | 8479.97 | 34.9% | 944.65 | 0 | 1202.85
25-PC-38070 | Phase III: Willow Springs Wastewater Plant Historic Resources Evaluation | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 132800 | 82601.6 | 82601.6 | 116864 | 116864 | 0 | 72689.82 | 44174.18 | 62.2% | 62.2% | 60110.18 | 45.26% | 0 | 0 | 0
25-PC-38107 | Task Order 13: Pebble Beach Road Substation Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 234600 | 77957.58 | 71933.85 | 208913.08 | 154792 | 54121.08 | 69422.07 | 139491.01 | 33.2% | 33.23% | 165177.93 | 70.41% | 50084.65 | 816.53 | 50209.89
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 25300 | 20781.42 | 19246.71 | 16961.12 | 16961.12 | 0 | 13931.44 | 3029.68 | 82.1% | 82.14% | 11368.56 | 44.94% | 12294.68 | 13.78 | 16805.26
25-PC-38196 | Sea Oat Cell Tower Built Environment Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 1160700 | 688295.1 | 688295.1 | 717428.67 | 717428.67 | 0 | 425399.95 | 292028.72 | 59.3% | 59.3% | 735300.05 | 63.35% | 24794.03 | 0 | 40160.22
25-PC-38282 | Task Order 16: Fern Valley Reservoir Architectural History Survey | In Progress | Time and material | Prairie | Sherry Lloyd |  | 1334100 | 672386.4 | 672386.4 | 876348.58 | 703000.66 | 173347.92 | 522008.11 | 354340.47 | 50.4% | 59.57% | 812091.89 | 60.87% | 0 | 0 | 0
25-PC-38296 | Ember Valley Pipeline - GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 173000 | 83922.3 | 73131.65 | 111169.8 | 111169.8 | 0 | 53923.32 | 57246.48 | 48.5% | 48.51% | 119076.68 | 68.83% | 36615.1 | 6045.97 | 46195.55
25-PC-38332 | Redbud GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 899800 | 706522.96 | 706522.96 | 754394.62 | 682213.35 | 72181.27 | 592323.19 | 162071.43 | 78.5% | 78.52% | 307476.81 | 34.17% | 11762.82 | 0 | 14036.88
25-PC-38333 | Pine Hollow Cell Tower Phase II Testing | In Progress | Fixed fee | Prairie | Sherry Lloyd | 09/04/2026 | 78300 | 56861.46 | 56861.46 | 51450.4 | 46958.73 | 4491.67 | 37360.87 | 14089.53 | 72.6% | 72.62% | 40939.13 | 52.28% | 763.9 | 0 | 1166.67
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd | 09/11/2026 | 136400 | 99080.96 | 99080.96 | 86736.76 | 86736.76 | 0 | 63001.3 | 23735.46 | 72.6% | 72.64% | 73398.7 | 53.81% | 494.27 | 0 | 777.48
25-PC-38461 | Rushgrass Draw Substation Phase II Testing | Final Billing/Invoice | Fixed fee | Red Rock | Lydia Cisneros |  | 187400 | 187400 | 187400 | 143548.4 | 143548.4 | 0 | 140284.68 | 3263.72 | 100% | 97.73% | 47115.32 | 25.14% | 0 | 0 | 4253.98
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | In Progress | Time and material | Red Rock | Jeanette Chung |  | 496400 | 481730.55 | 460087.32 | 357705.84 | 357705.84 | 0 | 311579.9 | 46125.94 | 97% | 87.11% | 184820.1 | 37.23% | 216912.68 | 12085.62 | 352368.52
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 07/31/2026 | 176400 | 154297.08 | 154297.08 | 137697.84 | 137697.84 | 0 | 120438.25 | 17259.59 | 87.5% | 87.47% | 55961.75 | 31.72% | 77094.98 | 0 | 98766.36
25-PC-38596 | Tansy Flat Pipeline Data Recovery | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 178000 | 91848 | 91848 | 148416.4 | 148416.4 | 0 | 76585.73 | 71830.67 | 51.6% | 51.6% | 101414.27 | 56.97% | 0 | 0 | 0
25-PC-38606 | Silver Lake School Campus - Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung |  | 34800 | 20358 | 20358 | 26816.2 | 23301.12 | 3515.08 | 15688.36 | 11127.84 | 58.5% | 58.5% | 19111.64 | 54.92% | 0 | 0 | 0
25-PC-38659 | On-Call: Elk Meadow School Campus Architectural History Survey | Completed | Time and material | Red Rock | Bruce Suarez |  | 3059900 | 927149.7 | 927149.7 | 2017698.06 | 2017698.06 | 0 | 1793049.08 | 224648.98 | 30.3% | 88.87% | 1266850.92 | 41.4% | 0 | 0 | 0
25-PC-38701 | Slate Ridge Curation | In Progress | Time and material | Red Rock | Javier Newman |  | 156400 | 109600.75 | 102197.06 | 98735.32 | 98735.32 | 0 | 71024.19 | 27711.13 | 70.1% | 71.93% | 85375.81 | 54.59% | 61608.18 | 1727.65 | 87339.06
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | In Progress | Fixed fee | Red Rock | Javier Newman | 09/04/2026 | 63900 | 63900 | 60446.65 | 41637.24 | 41637.24 | 0 | 60770.39 | -19133.15 | 100% | 145.9% | 3129.61 | 4.9% | 49954.22 | 753.17 | 43845.43
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez |  | 10400 | 10400 | 9781.64 | 5866.64 | 5866.64 | 0 | 18017.52 | -12150.88 | 100% | 307.1% | -7617.52 | -73.25% | 16729.15 | 416.94 | 7497.8
25-PC-38879 | Kestrel Butte Built Environment Survey | In Progress | Fixed fee | Red Rock | Marisa Odom |  | 119700 | 88482.24 | 88482.24 | 70323.75 | 70323.75 | 0 | 51984.23 | 18339.52 | 73.9% | 73.92% | 67715.77 | 56.57% | 7485.87 | 0 | 12736.08
25-PC-38970 | Ember Valley Park Improvements Curation | Final Billing/Invoice | Time and material | Red Rock | Jeanette Chung |  | 160100 | 31539.7 | 31539.7 | 117257.24 | 117257.24 | 0 | 130219.78 | -12962.54 | 19.7% | 111.1% | 29880.22 | 18.66% | 0 | 0 | 0
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | In Progress | Time and material | Red Rock | Tina Aguirre |  | 244000 | 201680 | 201680 | 174704 | 174704 | 0 | 157468.07 | 17235.93 | 82.7% | 90.13% | 86531.93 | 35.46% | 71187.66 | 0 | 100664
25-PC-39055 | Dove Canyon Transmission Line - Cultural Resources Assessment | Final Billing/Invoice | Time and material | Red Rock | Jeanette Chung |  | 128700 | 79794 | 79794 | 90984.64 | 84460.6 | 6524.04 | 109223.65 | -18239.01 | 62% | 120% | 19476.35 | 15.13% | 0 | 0 | 0
25-PC-39085 | Slate Ridge Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 120700 | 119806.82 | 119806.82 | 69209.38 | 69209.38 | 0 | 68696.85 | 512.53 | 99.3% | 99.26% | 52003.15 | 43.08% | 41227.87 | 0 | 71900.99
25-PC-39093 | Goldfinch Canal Lining Phase I Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre |  | 100100 | 49219.17 | 45898.43 | 73673.6 | 73673.6 | 0 | 36221.91 | 37451.69 | 49.2% | 49.17% | 63878.09 | 63.81% | 20062.27 | 1078.81 | 23946.5
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Shelia Horne | 09/11/2026 | 90300 | 67986.87 | 62928.94 | 58198.35 | 58198.35 | 0 | 43819.98 | 14378.37 | 75.3% | 75.29% | 46480.02 | 51.47% | 33141.24 | 2955.24 | 46358.89
25-PC-39187 | Windmill Flat Trail - Architectural History Survey | Lab/Curation | Fixed fee | Red Rock | Javier Newman |  | 28100 | 13811.15 | 13811.15 | 19470.49 | 19470.49 | 0 | 9569.28 | 9901.21 | 49.1% | 49.15% | 18530.72 | 65.95% | 0 | 0 | 0
25-PC-39222 | Phase I: Badger Hollow Trail GIS Mapping | Completed | Fixed fee | Red Rock | Lydia Cisneros |  | 27000 | 27000 | 27000 | 21648.6 | 21648.6 | 0 | 19644.61 | 2003.99 | 100% | 90.74% | 7355.39 | 27.24% | 0 | 0 | 2500.2
25-PC-39318 | Lone Pine Fiber Route - Class III Survey | In Progress | Fixed fee | Red Rock | Marisa Odom |  | 104300 | 71143.03 | 70186.4 | 69818.42 | 69818.42 | 0 | 47626.24 | 22192.18 | 68.2% | 68.21% | 56673.76 | 54.34% | 32674.77 | 0 | 47855.77
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Final Reporting/Review | Time and material | Red Rock | Tina Aguirre |  | 55900 | 55900 | 54034.56 | 39633.1 | 39633.1 | 0 | 38428.92 | 1204.18 | 100% | 96.96% | 17471.08 | 31.25% | 34734.04 | 1046.95 | 49897.96
25-PC-39398 | Silver Lake Housing Development - Data Recovery | Final Reporting/Review | Fixed fee | Red Rock | Marisa Odom |  | 103300 | 66783.45 | 66783.45 | 81096.61 | 66453.3 | 14643.31 | 52431.07 | 28665.54 | 64.6% | 64.65% | 50868.93 | 49.24% | 0 | 0 | 0
25-PC-39422 | Willow Springs Historic Resources Evaluation | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 56900 | 14731.41 | 14948.37 | 45036.35 | 45036.35 | 0 | 11658.25 | 33378.1 | 25.9% | 25.89% | 45241.75 | 79.51% | 3629.28 | 0 | 4803.1
25-PC-39424 | Tansy Flat Cultural Resources Assessment | In Progress | Fixed fee | Red Rock | Shelia Horne | 09/04/2026 | 19700 | 19700 | 17614.13 | 13882.59 | 13882.59 | 0 | 16267.84 | -2385.25 | 100% | 117.2% | 3432.16 | 17.42% | 11942.2 | 1957.79 | 11475.61
25-PC-39458 | Larkspur Park Improvements Paleontological Monitoring | In Progress | Time and material | Red Rock | Bruce Suarez |  | 345000 | 230912.25 | 222777.3 | 242983.5 | 242983.5 | 0 | 143586.3 | 99397.2 | 66.9% | 59.09% | 201413.7 | 58.38% | 82053.81 | 4749.54 | 120657.3
25-PC-39489 | Phase II: Fern Valley Transmission Line Paleontological Monitoring | Completed | Fixed fee | Red Rock | Marisa Odom |  | 460000 | 460000 | 460000 | 342148 | 342148 | 0 | 315421.89 | 26726.11 | 100% | 92.19% | 144578.11 | 31.43% | 0 | 0 | 35926
25-PC-39554 | Thistle Down Archaeological Testing | In Progress | Fixed fee | Red Rock | Tina Aguirre |  | 86700 | 75628.41 | 63747.46 | 63594.45 | 63594.45 | 0 | 55476.01 | 8118.44 | 87.2% | 87.23% | 31223.99 | 36.01% | 46428.58 | 9481.57 | 51410.05
25-PC-39569 | Badger Hollow Park Improvements GIS Mapping | Completed | Fixed fee | Red Rock | Bruce Suarez |  | 304300 | 304300 | 304300 | 191648.14 | 191648.14 | 0 | 168958.83 | 22689.31 | 100% | 88.16% | 135341.17 | 44.48% | 0 | 0 | 36029.12
25-PC-39661 | Windmill Flat Cultural Resources Monitoring | Completed | Time and material | Red Rock | Bruce Suarez |  | 1468900 | 998852 | 998852 | 1021032.39 | 1021032.39 | 0 | 915026.27 | 106006.12 | 68% | 89.62% | 553873.73 | 37.71% | 0 | 0 | 0
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | In Progress | Time and material | Red Rock | Javier Newman | 09/04/2026 | 51000 | 51000 | 51000 | 36551.7 | 36551.7 | 0 | 75197.04 | -38645.34 | 100% | 205.7% | -24197.04 | -47.45% | 68081.61 | 0 | 41463
25-PC-39808 | On-Call: Pine Hollow Rail Siding Architectural History Survey | In Progress | Fixed fee | Red Rock | Marisa Odom |  | 140600 | 77597.14 | 77597.14 | 88846.16 | 68571.9 | 20274.26 | 49031.18 | 39814.98 | 55.2% | 55.19% | 91568.82 | 65.13% | 22795.28 | 0 | 36077.96
25-PC-39873 | On-Call: Eagle Bend Battery Storage Phase II Testing | In Progress | Fixed fee | Red Rock | Marisa Odom |  | 93300 | 44364.15 | 41424.71 | 70478.82 | 70478.82 | 0 | 33515.14 | 36963.68 | 47.6% | 47.55% | 59784.86 | 64.08% | 30180.63 | 721.99 | 37011.62
25-PC-39885 | Bramble Creek Phase I Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre |  | 85600 | 55357.52 | 55221.19 | 54047.84 | 54047.84 | 0 | 34953.01 | 19094.83 | 64.7% | 64.67% | 50646.99 | 59.17% | 16644.4 | 115.34 | 26228.47
25-PC-39896 | Task Order 8: Raven Rock Highway Widening Archaeological Testing | In Progress | Fixed fee | Red Rock | Lydia Cisneros |  | 730900 | 541743.08 | 541743.08 | 540257.83 | 458118.4 | 82139.43 | 400441.47 | 139816.36 | 74.1% | 74.12% | 330458.53 | 45.21% | 2494.03 | 0 | 3362.14
25-PC-39951 | Falcon Mesa Reservoir - Phase II Testing | Cost Tracking on Closed Project | Fixed fee | Red Rock | Javier Newman |  | 87200 | 69358.88 | 69358.88 | 65277.92 | 65277.92 | 0 | 51921.91 | 13356.01 | 79.5% | 79.54% | 35278.09 | 40.46% | 0 | 0 | 0
25-PC-40020 | Wildrye Curation | On Hold | Fixed fee | Red Rock | Marisa Odom |  | 186200 | 56344.12 | 56344.12 | 128340.42 | 94380 | 33960.42 | 38836.44 | 89503.98 | 30.3% | 30.26% | 147363.56 | 79.14% | 0 | 0 | 0
25-PC-40099 | On-Call: Sparrow Hill Pipeline Phase II Testing | Completed | Time and material | Sierra | Benjamin Mathis |  | 665100 | 135680.4 | 135680.4 | 460201.14 | 389294.01 | 70907.13 | 598261.48 | -138060.34 | 20.4% | 130% | 66838.52 | 10.05% | 0 | 0 | 0
25-PC-40170 | Plover Cove Wastewater Plant Cultural Resources Assessment | Final Billing/Invoice | Time and material | Sierra South | Angelica Poole |  | 260400 | 177072 | 177072 | 190690.92 | 190690.92 | 0 | 133483.64 | 57207.28 | 68% | 70% | 126916.36 | 48.74% | 0 | 0 | 0
25-PC-40205 | Eagle Bend Cell Tower Paleontological Monitoring | Completed | Fixed fee | Sierra | Donna Herring |  | 88100 | 88100 | 88100 | 59027 | 59027 | 0 | 55179.61 | 3847.39 | 100% | 93.48% | 32920.39 | 37.37% | 0 | 0 | 5744.12
25-PC-40231 | Goldfinch Pipeline - Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring |  | 88300 | 65426.7 | 60462.94 | 59478.88 | 59478.88 | 0 | 40234.79 | 19244.09 | 74.1% | 67.65% | 48065.21 | 54.43% | 35325.4 | 3142.94 | 51721.24
25-PC-40248 | Stone Mill Cultural Resources Monitoring | Final Billing/Invoice | Time and material | Sierra North | Louis Huff |  | 164500 | 10692.5 | 10692.5 | 111854.21 | 86668.53 | 25185.68 | 117848.67 | -5994.46 | 6.5% | 105.4% | 46651.33 | 28.36% | 0 | 0 | 0
25-PC-40383 | North Fork Archaeological Testing | In Progress | Fixed fee | Sierra | Donna Herring |  | 193200 | 161148.12 | 161148.12 | 144185.16 | 144185.16 | 0 | 120262.61 | 23922.55 | 83.4% | 83.41% | 72937.39 | 37.75% | 25332.54 | 0 | 33945.24
25-PC-40465 | Task Order 32: Copper Flats Solar Historic Resources Evaluation | In Progress | Fixed fee | Sierra | Benjamin Mathis |  | 127600 | 80860.12 | 77042.86 | 94627.43 | 86041.09 | 8586.34 | 59968.41 | 34659.02 | 63.4% | 63.37% | 67631.59 | 53% | 40734.16 | 2491.9 | 51101.78
25-PC-40482 | Task Order 33: Tamarack Cell Tower Cultural Resources Assessment | In Progress | Fixed fee | Sierra South | Louis Huff |  | 73200 | 32705.76 | 32090.81 | 60199.68 | 60199.68 | 0 | 26897 | 33302.68 | 44.7% | 44.68% | 46303 | 63.26% | 18457.68 | 348.83 | 21828.17
25-PC-40501 | Aspen Ridge Archaeological Testing | Completed | Fixed fee | Sierra South | Benjamin Mathis |  | 1246400 | 1246400 | 1246400 | 817638.4 | 817638.4 | 0 | 784481.65 | 33156.75 | 100% | 95.94% | 461918.35 | 37.06% | 0 | 0 | 50603.84
25-PC-40503 | Copper Flats Phase I Survey | Lab/Curation | Time and material | Sierra | Benjamin Mathis |  | 43400 | 43400 | 43400 | 30119.6 | 30119.6 | 0 | 42364.23 | -12244.63 | 100% | 140.7% | 1035.77 | 2.39% | 30894.54 | 0 | 25953.2
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring |  | 71000 | 71000 | 67104.25 | 49579.3 | 49579.3 | 0 | 76399.6 | -26820.3 | 100% | 154.1% | -5399.6 | -7.61% | 60072.59 | 2541.24 | 49141.25
25-PC-40541 | Eagle Bend Airport Apron - Archaeological Testing | In Progress | Fixed fee | Sierra | Louis Huff |  | 25000 | 16595 | 16595 | 16850 | 16850 | 0 | 11185.54 | 5664.46 | 66.4% | 66.38% | 13814.46 | 55.26% | 2002.39 | 0 | 2970
25-PC-40572 | Maple Fork Cell Tower Environmental Review Support | In Progress | Fixed fee | Sierra | Benjamin Mathis |  | 88300 | 34887.33 | 34769.84 | 67293.43 | 67293.43 | 0 | 26589.42 | 40704.01 | 39.5% | 39.51% | 61710.58 | 69.89% | 10048.41 | 0 | 13065.7
25-PC-40595 | Willow Springs Levee Repair - Built Environment Survey | Final Reporting/Review | Fixed fee | Sierra South | Angelica Poole |  | 1568300 | 611950.66 | 594232.15 | 1302159.49 | 1302159.49 | 0 | 508068.66 | 794090.83 | 39% | 39.02% | 1060231.34 | 67.6% | 126287.85 | 8850.24 | 134406.59
25-PC-40677 | Quail Run Paleontological Monitoring | Transferred Entity | Time and material | Sierra South | Louis Huff |  | 225000 | 192903.25 | 192903.25 | 157612.5 | 157612.5 | 0 | 153698.04 | 3914.46 | 85.7% | 97.52% | 71301.96 | 31.69% | 32495.74 | 0 | 45528.25
25-PC-40680 | On-Call: Eagle Bend Battery Storage Cultural Resources Assessment | Lab/Curation | Time and material | Sierra | Donna Herring |  | 10100 | 8386.75 | 8386.75 | 6706.4 | 6706.4 | 0 | 5628.16 | 1078.24 | 83% | 83.92% | 4471.84 | 44.28% | 1122.37 | 0 | 1518.75
25-PC-40708 | Lantern Bay Built Environment Survey | Final Billing/Invoice | Fixed fee | Coastal Bend | Duane Ballard |  | 50900 | 50900 | 50900 | 31379.85 | 31379.85 | 0 | 25719.64 | 5660.21 | 100% | 81.96% | 25180.36 | 49.47% | 0 | 0 | 9182.36
25-PC-40722 | Goldfinch Canal Lining - Archaeological Testing | In Progress | Time and material | Coastal Bend | Duane Ballard |  | 166600 | 128119.75 | 128119.75 | 119491.23 | 103318.2 | 16173.03 | 80423 | 39068.23 | 76.9% | 67.3% | 86177 | 51.73% | 7984.34 | 0 | 14831.75
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 08/28/2026 | 50100 | 50100 | 47994.45 | 34844.55 | 34844.55 | 0 | 37556.22 | -2711.67 | 100% | 107.8% | 12543.78 | 25.04% | 27106.96 | 1069.17 | 32969.46
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi |  | 46800 | 46800 | 46800 | 34243.56 | 34243.56 | 0 | 37494.89 | -3251.33 | 100% | 109.5% | 9305.11 | 19.88% | 35310.05 | 0 | 43814.16
25-PC-40880 | Pebble Beach Road Bridge Replacement Cultural Resources Assessment | In Progress | Time and material | Coastal Bend | Diane Daniels |  | 45800 | 28954.35 | 26615.83 | 30347.08 | 30347.08 | 0 | 18281.09 | 12065.99 | 63.2% | 60.24% | 27518.91 | 60.08% | 14576.05 | 201.63 | 19654.23
25-PC-40925 | Harbor View Airport Apron - Data Recovery | Final Reporting/Review | Time and material | Coastal Bend | Alexis Nixon |  | 35000 | 23800 | 23800 | 23562 | 23562 | 0 | 20240.75 | 3321.25 | 68% | 85.9% | 14759.25 | 42.17% | 0 | 0 | 0
25-PC-40944 | Maple Fork Archaeological Testing | Final Billing/Invoice | Fixed fee | Coastal Bend | Steve Rubio |  | 101400 | 101400 | 101400 | 73160.1 | 73160.1 | 0 | 95108.13 | -21948.03 | 100% | 130% | 6291.87 | 6.2% | 0 | 0 | 0
25-PC-41075 | Phase I: Cedar Hollow Airport Apron Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Duane Ballard |  | 82100 | 46534.28 | 45582.42 | 61304.07 | 61304.07 | 0 | 34747.46 | 26556.61 | 56.7% | 56.68% | 47352.54 | 57.68% | 22889.57 | 650.65 | 29704.28
25-PC-41083 | On-Call: Hackberry Bend Rail Siding Class III Survey | On Hold | Time and material | Coastal Bend | Diane Daniels |  | 193500 | 36958.5 | 36958.5 | 140887.35 | 140887.35 | 0 | 26486.33 | 114401.02 | 19.1% | 18.8% | 167013.67 | 86.31% | 0 | 0 | 0
25-PC-41097 | On-Call: Falcon Mesa Wastewater Plant Phase II Testing | Final Reporting/Review | Time and material | Coastal Bend | Duane Ballard |  | 197800 | 157477.05 | 151428.7 | 128154.62 | 128154.62 | 0 | 105966.35 | 22188.27 | 79.6% | 82.69% | 91833.65 | 46.43% | 71536.55 | 2559.99 | 102769.9
25-PC-41187 | Hackberry Bend Trail GIS Mapping | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 09/11/2026 | 98900 | 75510.15 | 72782.09 | 55621.36 | 55621.36 | 0 | 42469.63 | 13151.73 | 76.3% | 76.35% | 56430.37 | 57.06% | 24409.8 | 144.1 | 40669.26
25-PC-41252 | Oak Terrace Wastewater Plant Curation | Final Reporting/Review | Fixed fee | Coastal Bend | Steve Rubio | 08/28/2026 | 33000 | 30736.2 | 30524.42 | 25325 | 22089.27 | 3235.73 | 23587.72 | 1737.28 | 93.1% | 93.14% | 9412.28 | 28.52% | 22598.02 | 196.27 | 29234.12
25-PC-41265 | Larkspur Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels |  | 89800 | 85318.98 | 85318.98 | 71911.84 | 71911.84 | 0 | 68323.14 | 3588.7 | 95% | 95.01% | 21476.86 | 23.92% | 0 | 0 | 0
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | In Progress | Fixed fee | Coastal Bend | Diane Daniels |  | 167900 | 133782.72 | 130782.09 | 131616.81 | 131616.81 | 0 | 104866.5 | 26750.31 | 79.7% | 79.68% | 63033.5 | 37.54% | 75882.29 | 3006.32 | 93810.51
25-PC-41372 | Thistle Down Pipeline Curation | Final Billing/Invoice | Fixed fee | Coastal Bend | Duane Ballard |  | 86100 | 86100 | 86100 | 63016.59 | 63016.59 | 0 | 53963.72 | 9052.87 | 100% | 85.63% | 32136.28 | 37.32% | 0 | 0 | 12372.57
25-PC-41383 | Harbor View Reservoir - Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Steve Rubio |  | 342200 | 263870.42 | 263870.42 | 223902.7 | 185978.46 | 37924.24 | 172645.04 | 51257.66 | 77.1% | 77.11% | 169554.96 | 49.55% | 4138.16 | 0 | 6330.7
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 08/14/2026 | 179800 | 179800 | 170811.36 | 119171.44 | 119171.44 | 0 | 171055.95 | -51884.51 | 100% | 143.5% | 8744.05 | 4.86% | 144190.2 | 3134.97 | 130284.44
25-PC-41476 | North Fork Mixed-Use Development Archaeological Testing | Completed | Time and material | Coastal Bend | Alexis Nixon |  | 211900 | 79674.4 | 79674.4 | 146804.32 | 146804.32 | 0 | 190845.62 | -44041.3 | 37.6% | 130% | 21054.38 | 9.94% | 0 | 0 | 0
25-PC-41479 | Hawk Point Trail Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels |  | 633600 | 203892.48 | 200991.35 | 405123.84 | 405123.84 | 0 | 130355.73 | 274768.11 | 32.2% | 32.18% | 503244.27 | 79.43% | 40409.79 | 2398.41 | 60332.15
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Jared Choi |  | 130200 | 121022.45 | 121022.45 | 94156.73 | 81265.42 | 12891.31 | 105548.13 | -11391.4 | 93% | 112.1% | 24651.87 | 18.93% | 38537.73 | 0 | 53839.25
25-PC-41514 | Lantern Bay Levee Repair Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 07/31/2026 | 48700 | 38575.27 | 38543.24 | 31123.36 | 29237.6 | 1885.76 | 24653.59 | 6469.77 | 79.2% | 79.21% | 24046.41 | 49.38% | 11519.46 | 0 | 17991.84
25-PC-41600 | Twin Buttes Cultural Resources Monitoring | Final Billing/Invoice | Fixed fee | Coastal Bend | Diane Daniels |  | 647300 | 647300 | 647300 | 488406.31 | 439366.44 | 49039.87 | 486062.64 | 2343.67 | 100% | 99.52% | 161237.36 | 24.91% | 0 | 0 | 3107.04
25-PC-41603 | Task Order 22: Wren Hollow Cell Tower Paleontological Monitoring | Final Billing/Invoice | Time and material | Coastal Bend | Alexis Nixon |  | 73800 | 1992.6 | 1992.6 | 50808.19 | 45601.1 | 5207.09 | 66050.65 | -15242.46 | 2.7% | 130% | 7749.35 | 10.5% | 0 | 0 | 0
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | In Progress | Time and material | Coastal Bend | Jared Choi | 09/04/2026 | 412300 | 300806.95 | 290386.6 | 281889.51 | 281889.51 | 0 | 224531.7 | 57357.81 | 73% | 79.65% | 187768.3 | 45.54% | 78072.73 | 3770.08 | 105263.9
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | In Progress | Time and material | Built Environment | Jenny Wilkinson |  | 152100 | 112187.4 | 112187.4 | 108599.4 | 108599.4 | 0 | 90984.66 | 17614.74 | 73.8% | 83.78% | 61115.34 | 40.18% | 8665.97 | 0 | 12714
25-PC-41764 | Stone Mill Environmental Review Support | In Progress | Time and material | Built Environment | Jenny Wilkinson |  | 20700 | 16684.25 | 16684.25 | 15642.78 | 13328.34 | 2314.44 | 14549.83 | 1092.95 | 80.6% | 93.01% | 6150.17 | 29.71% | 1509.08 | 0 | 2608.25
25-PC-41834 | Pebble Beach Road Data Recovery | In Progress | Fixed fee | Built Environment | Rickey Salas |  | 170100 | 63736.47 | 58480.85 | 145401.48 | 145401.48 | 0 | 54475.63 | 90925.85 | 37.5% | 37.47% | 115624.37 | 67.97% | 15063.28 | 2377.96 | 12366.74
25-PC-41843 | Wren Hollow Rail Siding - Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Jesse Maynard |  | 54000 | 36720 | 36720 | 35988.02 | 26607.55 | 9380.47 | 23655.15 | 12332.87 | 68% | 65.73% | 30344.85 | 56.19% | 0 | 0 | 0
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | In Progress | Time and material | Built Environment | Rickey Salas | 08/14/2026 | 39700 | 39700 | 38010.35 | 25920.13 | 25920.13 | 0 | 29882.88 | -3962.75 | 100% | 115.3% | 9817.12 | 24.73% | 22160.01 | 2193.72 | 30149.75
25-PC-41931 | Sandpiper Pipeline Curation | Final Billing/Invoice | Fixed fee | Built Environment | Jesse Maynard |  | 56200 | 56200 | 56200 | 36698.6 | 36698.6 | 0 | 36424.62 | 273.98 | 100% | 99.25% | 19775.38 | 35.19% | 0 | 0 | 421.5
25-PC-41967 | On-Call: Redbud Pipeline Section 106 Consultation | On Hold | Fixed fee | Built Environment | Rickey Salas |  | 37300 | 10499.95 | 10499.95 | 28348 | 28348 | 0 | 7978.96 | 20369.04 | 28.1% | 28.15% | 29321.04 | 78.61% | 0 | 0 | 0
25-PC-42076 | Bramble Creek Highway Widening Curation | In Progress | Time and material | Built Environment | Jesse Maynard |  | 319600 | 155773.55 | 147831.26 | 227746.96 | 227746.96 | 0 | 98992.02 | 128754.94 | 48.7% | 43.47% | 220607.98 | 69.03% | 95171.42 | 5082.47 | 142078.46
25-PC-42078 | Sea Oat Paleontological Monitoring | Completed | Fixed fee | Built Environment | Jenny Wilkinson |  | 433900 | 433900 | 433900 | 316573.44 | 316573.44 | 0 | 263762.67 | 52810.77 | 100% | 83.32% | 170137.33 | 39.21% | 0 | 0 | 72374.52
25-PC-42084 | Foxglove Built Environment Survey | In Progress | Time and material | Built Environment | Kathleen Cabrera |  | 1294200 | 344257.2 | 344257.2 | 847312.74 | 847312.74 | 0 | 296024.06 | 551288.68 | 26.6% | 34.94% | 998175.94 | 77.13% | 0 | 0 | 0
25-PC-42097 | Tansy Flat Solar Data Recovery | In Progress | Fixed fee | Built Environment | Jenny Wilkinson |  | 179700 | 84315.24 | 72979.58 | 138548.7 | 138548.7 | 0 | 65000.81 | 73547.89 | 46.9% | 46.92% | 114699.19 | 63.83% | 53852.32 | 8726.72 | 58513.73
25-PC-42115 | Hawk Point Reservoir Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Built Environment | Jesse Maynard |  | 110400 | 70534.56 | 70534.56 | 90660.48 | 90660.48 | 0 | 57919.11 | 32741.37 | 63.9% | 63.89% | 52480.89 | 47.54% | 13816.6 | 0 | 16824.96
25-PC-42136 | Phase III: Granite Pass Mixed-Use Development Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 08/21/2026 | 31700 | 23670.39 | 20580.8 | 23936.32 | 17555.9 | 6380.42 | 17873.56 | 6062.76 | 74.7% | 74.67% | 13826.44 | 43.62% | 12940.25 | 159.47 | 14047.43
25-PC-42163 | Foxglove Historic Resources Evaluation | Final Reporting/Review | Time and material | Built Environment | Rickey Salas |  | 50700 | 38724.35 | 38724.35 | 34430.37 | 34430.37 | 0 | 27262.05 | 7168.32 | 76.4% | 79.18% | 23437.95 | 46.23% | 4562.9 | 0 | 7138.25
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Cost Tracking on Closed Project | Time and material | Built Environment | Kathleen Cabrera | 09/11/2026 | 17900 | 161.1 | 161.1 | 12066.39 | 12066.39 | 0 | 14332.43 | -2266.04 | 0.9% | 118.8% | 3567.57 | 19.93% | 0 | 0 | 0
25-PC-42253 | On-Call: Plover Cove Substation Phase I Survey | In Progress | Time and material | Paleontology | Charlene Sparks |  | 67000 | 47935 | 47935 | 45781.1 | 45781.1 | 0 | 27198.17 | 18582.93 | 71.5% | 59.41% | 39801.83 | 59.41% | 1522.61 | 0 | 2375
25-PC-42282 | Dove Canyon Levee Repair - Phase I Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks |  | 33000 | 20116.8 | 20116.8 | 19255.5 | 19255.5 | 0 | 11737.58 | 7517.92 | 61% | 60.96% | 21262.42 | 64.43% | 7065.98 | 0 | 12111
25-PC-42303 | Copper Flats Cell Tower Environmental Review Support | Completed | Time and material | Paleontology | Travis Delgado |  | 147500 | 46610 | 46610 | 99769 | 99769 | 0 | 129699.7 | -29930.7 | 31.6% | 130% | 17800.3 | 12.07% | 0 | 0 | 0
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 08/14/2026 | 41200 | 32304.92 | 29924.09 | 29239.64 | 29239.64 | 0 | 22925.4 | 6314.24 | 78.4% | 78.41% | 18274.6 | 44.36% | 18708.49 | 1752.25 | 23983.05
25-PC-42323 | Millbrook Cultural Resources Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 79800 | 46355.82 | 46355.82 | 58357.74 | 58357.74 | 0 | 33900.56 | 24457.18 | 58.1% | 58.09% | 45899.44 | 57.52% | 16423.72 | 0 | 22455.72
25-PC-42343 | Phase III: Coyote Springs Pipeline Phase II Testing | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 6100 | 4126.04 | 4126.04 | 4038.38 | 3787.65 | 250.73 | 2731.5 | 1306.88 | 67.6% | 67.64% | 3368.5 | 55.22% | 0 | 0 | 0
25-PC-42364 | Sparrow Hill Fiber Route - Phase I Survey | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 594900 | 375917.31 | 375917.31 | 426353.2 | 400715.25 | 25637.95 | 269416.69 | 156936.51 | 63.2% | 63.19% | 325483.31 | 54.71% | 2853.1 | 0 | 3985.83
25-PC-42399 | Task Order 7: Aspen Ridge Housing Development Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks |  | 683800 | 385594.82 | 364616.3 | 509225.86 | 509225.86 | 0 | 287162.01 | 222063.85 | 56.4% | 56.39% | 396637.99 | 58% | 162546.58 | 9885.01 | 197290.44
25-PC-42528 | Slate Ridge Park Improvements - Phase I Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks |  | 132000 | 37144.8 | 36898.14 | 93601.2 | 93601.2 | 0 | 26336.22 | 67264.98 | 28.1% | 28.14% | 105663.78 | 80.05% | 7330.55 | 240.3 | 10102.14
25-PC-42569 | Larkspur Phase I Survey | Final Billing/Invoice | Fixed fee | Paleontology | Charlene Sparks |  | 105700 | 105700 | 105700 | 81219.88 | 81219.88 | 0 | 68472.33 | 12747.55 | 100% | 84.3% | 37227.67 | 35.22% | 0 | 0 | 16594.9
25-PC-42601 | Lantern Bay Park Improvements - Cultural Resources Monitoring | Transferred Entity | Time and material | Paleontology | Charlene Sparks |  | 302100 | 108000.1 | 100989.07 | 213521.46 | 177364.48 | 36156.98 | 62873.17 | 150648.29 | 35.7% | 29.45% | 239226.83 | 79.19% | 37216.16 | 2647.98 | 53861.47
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | In Progress | Time and material | Maritime | Kyle Maynard | 09/18/2026 | 130300 | 128601.35 | 128601.35 | 95796.56 | 95796.56 | 0 | 79985.69 | 15810.87 | 98.7% | 83.5% | 50314.31 | 38.61% | 33764.75 | 0 | 56675.75
25-PC-42747 | Yarrow Point Transmission Line - Historic Resources Evaluation | On Hold | Fixed fee | Maritime | Rita Ayala |  | 128900 | 70031.37 | 70031.37 | 87896.91 | 87896.91 | 0 | 47757.12 | 40139.79 | 54.3% | 54.33% | 81142.88 | 62.95% | 0 | 0 | 0
25-PC-43037 | Cedar Hollow Section 106 Consultation | Completed | Fixed fee | Maritime | Rita Ayala |  | 250200 | 250200 | 250200 | 196231.86 | 196231.86 | 0 | 238460.35 | -42228.49 | 100% | 121.5% | 11739.65 | 4.69% | 0 | 0 | 0
25-PC-43061 | Plover Cove Built Environment Survey | Final Billing/Invoice | Fixed fee | Geospatial | Priscilla Pennington |  | 106500 | 106500 | 106500 | 81184.95 | 81184.95 | 0 | 77334.09 | 3850.86 | 100% | 95.26% | 29165.91 | 27.39% | 0 | 0 | 5048.1
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Transferred Entity | Time and material | Geospatial | Sylvia Callahan | 08/07/2026 | 62000 | 54684.75 | 54684.75 | 44404.4 | 44404.4 | 0 | 44584.79 | -180.39 | 88.2% | 100.4% | 17415.21 | 28.09% | 9162.77 | 0 | 12648.75
25-PC-43075 | Coyote Springs Reservoir Cultural Resources Assessment | On Hold | Time and material | Geospatial | Sylvia Callahan |  | 381100 | 124619.7 | 124619.7 | 238416.16 | 238416.16 | 0 | 83479.16 | 154937 | 32.7% | 35.01% | 297620.84 | 78.1% | 0 | 0 | 0
25-PC-43106 | Kestrel Butte Wastewater Plant - Maritime Remote Sensing Survey | Final Billing/Invoice | Time and material | Geospatial | Priscilla Pennington |  | 63000 | 42840 | 42840 | 41082.3 | 41082.3 | 0 | 36605.84 | 4476.46 | 68% | 89.1% | 26394.16 | 41.9% | 0 | 0 | 0
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | In Progress | Fixed fee | Meridian Central | Seth Zavala | 08/28/2026 | 128400 | 128400 | 128209.36 | 106315.2 | 106315.2 | 0 | 195734.3 | -89419.1 | 100% | 184.1% | -67334.3 | -52.44% | 133157.24 | 48.08 | 52633.12
25-PC-43244 | Windmill Flat Environmental Review Support | Final Billing/Invoice | Fixed fee | Meridian Central | Clinton Solis |  | 794900 | 794900 | 794900 | 585516.71 | 437871.9 | 147644.81 | 519424.85 | 66091.86 | 100% | 88.71% | 275475.15 | 34.66% | 0 | 0 | 89744.21
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | In Progress | Time and material | Meridian Central | Seth Zavala | 09/04/2026 | 15700 | 15700 | 11349.21 | 10903.65 | 10903.65 | 0 | 71168.37 | -60264.72 | 100% | 652.7% | -55468.37 | -353.3% | 68756.17 | 0 | 8020.81
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Clinton Solis | 09/04/2026 | 715500 | 650818.8 | 650818.8 | 625275.45 | 625275.45 | 0 | 568777.84 | 56497.61 | 91% | 90.96% | 146722.16 | 20.51% | 0 | 0 | 0
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Seth Zavala |  | 551800 | 551800 | 551800 | 378424.44 | 378424.44 | 0 | 405626.36 | -27201.92 | 100% | 107.2% | 146173.64 | 26.49% | 0 | 0 | 0
25-PC-43455 | Kestrel Butte Maritime Remote Sensing Survey | On Hold | Fixed fee | Meridian Central | Seth Zavala |  | 116100 | 11563.56 | 11563.56 | 84903.93 | 84903.93 | 0 | 8459.31 | 76444.62 | 10% | 9.96% | 107640.69 | 92.71% | 0 | 0 | 0
25-PC-43511 | Wildrye Solar Phase II Testing | Completed | Time and material | Meridian Central | Mathew Shea |  | 1026200 | 607510.4 | 607510.4 | 701711.56 | 512707.7 | 189003.86 | 912225.03 | -210513.47 | 59.2% | 130% | 113974.97 | 11.11% | 0 | 0 | 0
25-PC-43566 | Copper Flats Solar - Phase II Testing | In Progress | Fixed fee | Meridian Central | Mathew Shea |  | 114200 | 114200 | 114200 | 73887.4 | 73887.4 | 0 | 131458.02 | -57570.62 | 100% | 177.9% | -17258.02 | -15.11% | 90986.05 | 0 | 51641.24
25-PC-43590 | Task Order 37: Elk Meadow Harbor Dredging Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Meridian Central | Mathew Shea |  | 24800 | 16978.08 | 16978.08 | 16619.52 | 14642.64 | 1976.88 | 11377.59 | 5241.93 | 68.5% | 68.46% | 13422.41 | 54.12% | 0 | 0 | 0
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | In Progress | Fixed fee | Meridian Southwest | Alan Gay |  | 52800 | 52800 | 52800 | 37979.04 | 37979.04 | 0 | 37986.88 | -7.84 | 100% | 100% | 14813.12 | 28.06% | 20052.34 | 0 | 27867.84
25-PC-43639 | Windmill Flat Battery Storage Curation | Final Reporting/Review | Fixed fee | Meridian Southwest | Harold Chaney |  | 137000 | 137000 | 133193.26 | 91502.3 | 91502.3 | 0 | 100918.9 | -9416.6 | 100% | 110.3% | 36081.1 | 26.34% | 71700.36 | 1941.02 | 89449.16
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Lab/Curation | Fixed fee | Meridian Southwest | Reginald Kerr |  | 92800 | 92800 | 80044.54 | 78211.84 | 78211.84 | 0 | 103245.03 | -25033.19 | 100% | 132% | -10445.03 | -11.26% | 92711.21 | 6019.46 | 67544.38
25-PC-43752 | Bramble Creek Rail Siding - Environmental Review Support | Final Billing/Invoice | Time and material | Meridian Southwest | Reginald Kerr |  | 49900 | 4391.2 | 4391.2 | 36001.87 | 27260.16 | 8741.71 | 46802.43 | -10800.56 | 8.8% | 130% | 3097.57 | 6.21% | 0 | 0 | 0
25-PC-43771 | Granite Pass Reservoir - Built Environment Survey | Lab/Curation | Time and material | Meridian Southwest | Lynn Tran |  | 31500 | 15790.5 | 15172.4 | 20147.4 | 20147.4 | 0 | 11344.38 | 8803.02 | 50.1% | 56.31% | 20155.62 | 63.99% | 6204.68 | 804.82 | 8588.9
25-PC-43844 | Slate Ridge Battery Storage Class III Survey | In Progress | Fixed fee | Meridian Southwest | Alan Gay |  | 50700 | 47891.22 | 43959.81 | 33907.9 | 26087.6 | 7820.3 | 32031.03 | 1876.87 | 94.5% | 94.46% | 18668.97 | 36.82% | 25781.02 | 3597.36 | 34615.8
25-PC-43853 | Heron Marsh Battery Storage - Phase II Testing | Final Reporting/Review | Time and material | Meridian Southwest | Alan Gay |  | 162800 | 159982.25 | 146251.97 | 115799.64 | 115799.64 | 0 | 99239.21 | 16560.43 | 98.3% | 85.7% | 63560.79 | 39.04% | 84651.08 | 5203.63 | 118575.97
25-PC-43859 | On-Call: Juniper Wash Solar Architectural History Survey | Completed | Fixed fee | Meridian Southwest | Alan Gay |  | 1802800 | 1802800 | 1802800 | 1378420.88 | 1378420.88 | 0 | 1051248.86 | 327172.02 | 100% | 76.26% | 751551.14 | 41.69% | 0 | 0 | 427984.72
25-PC-43863 | Yarrow Point Cultural Resources Assessment | In Progress | Fixed fee | Meridian Southwest | Reginald Kerr |  | 545200 | 101298.16 | 95002.43 | 450335.2 | 450335.2 | 0 | 83664.45 | 366670.75 | 18.6% | 18.58% | 461535.55 | 84.65% | 49445.09 | 3807.92 | 53567.23
25-PC-43932 | Blue Heron Built Environment Survey | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins |  | 0 | 0 | 0 | 24656.25 | 18135 | 6521.25 | 14873.81 | 9782.44 | 0% | 60.32% | -14873.81 | 0% | 6396.46 | 0 | 0
25-PC-43944 | Elk Meadow Data Recovery | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 74800 | 26741 | 26741 | 60460.84 | 60460.84 | 0 | 21611.75 | 38849.09 | 35.7% | 35.75% | 53188.25 | 71.11% | 9141.24 | 0 | 11309.76
25-PC-43966 | Silver Lake Rail Siding - Cultural Resources Monitoring | Transferred Entity | Fixed fee | NH Gulf (USD) | Tonya Spence |  | 0 | 0 | 0 | 34547.14 | 30211.65 | 4335.49 | 25260.3 | 9286.84 | 0% | 73.12% | -25260.3 | 0% | 22170.79 | 0 | 0
25-PC-43993 | Timber Gap GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Javier Rangel | 09/04/2026 | 0 | 0 | 0 | 19669.5 | 19669.5 | 0 | 14401.75 | 5267.75 | 0% | 73.22% | -14401.75 | 0% | 13781.31 | 0 | 0
25-PC-44046 | Kestrel Butte Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu |  | 0 | 0 | 0 | 220526.55 | 220526.55 | 0 | 276639.9 | -56113.35 | 0% | 125.4% | -276639.9 | 0% | 31870.48 | 0 | 0
25-PC-44186 | Falcon Mesa Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu |  | 0 | 0 | 0 | 338148.9 | 338148.9 | 0 | 215370.94 | 122777.96 | 0% | 63.69% | -215370.94 | 0% | 26400.15 | 0 | 0
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins |  | 0 | 0 | 0 | 17934.14 | 13115.76 | 4818.38 | 31152.52 | -13218.38 | 0% | 173.7% | -31152.52 | 0% | 29833.49 | 0 | 0
25-PC-44241 | On-Call: Timber Gap Reservoir Paleontological Monitoring | Final Billing/Invoice | Time and material | NH Gulf (USD) | Justin Mejia |  | 348700 | 164586.4 | 164586.4 | 228712.33 | 228712.33 | 0 | 297326.03 | -68613.7 | 47.2% | 130% | 51373.97 | 14.73% | 0 | 0 | 0
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu |  | 97000 | 97000 | 91499.34 | 71004 | 71004 | 0 | 79042.17 | -8038.17 | 100% | 111.3% | 17957.83 | 18.51% | 59812.94 | 4142.43 | 65231.74
26-PC-30013 | Windmill Flat Mine Expansion - Architectural History Survey | Final Reporting/Review | Time and material | Big Sky | Bob Frye |  | 62300 | 13942 | 8607.19 | 43902.81 | 43902.81 | 0 | 9546.49 | 34356.32 | 22.4% | 21.74% | 52753.51 | 84.68% | 9546.49 | 2214.93 | 8607.19
26-PC-30057 | Sparrow Hill Environmental Review Support | In Progress | Time and material | Big Sky | Brendan Melton |  | 197500 | 104876.75 | 81807.77 | 144017 | 144017 | 0 | 68917.84 | 75099.16 | 53.1% | 47.85% | 128582.16 | 65.1% | 68917.84 | 11102.95 | 81807.77
26-PC-30065 | Granite Pass Water Main - Cultural Resources Assessment | In Progress | Fixed fee | Big Sky | Javier Estrada |  | 132100 | 26367.16 | 20607.73 | 104411.84 | 104411.84 | 0 | 20838.3 | 83573.54 | 20% | 19.96% | 111261.7 | 84.23% | 20838.3 | 2674.43 | 20607.73
26-PC-30094 | Sumac Ridge Wastewater Plant Paleontological Monitoring | In Progress | Fixed fee | Big Sky | Carl Barajas |  | 98400 | 3906.48 | 1293.62 | 82193.52 | 82193.52 | 0 | 3266.46 | 78927.06 | 4% | 3.97% | 95133.54 | 96.68% | 3266.46 | 1173.76 | 1293.62
26-PC-30115 | Quail Run Housing Development - Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Big Sky | Bob Frye |  | 18600 | 18600 | 18600 | 16368 | 16368 | 0 | 16558.04 | -190.04 | 100% | 101.2% | 2041.96 | 10.98% | 0 | 0 | 0
26-PC-30123 | Eagle Bend Park Improvements - Class III Survey | In Progress | Fixed fee | Big Sky | Bob Frye |  | 277200 | 59237.64 | 45677.97 | 210477.96 | 210477.96 | 0 | 44970.8 | 165507.16 | 21.4% | 21.37% | 232229.2 | 83.78% | 44970.8 | 9704.42 | 45677.97
26-PC-30139 | Quail Run Canal Lining Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada |  | 239600 | 19168 | 19168 | 198628.4 | 198628.4 | 0 | 15884.69 | 182743.71 | 8% | 8% | 223715.31 | 93.37% | 15884.69 | 0 | 19168
26-PC-30180 | Willow Springs Architectural History Survey | Lab/Curation | Fixed fee | Big Sky | Carl Barajas |  | 115700 | 30024.15 | 24550.75 | 79798.29 | 79798.29 | 0 | 20705.53 | 59092.76 | 26% | 25.95% | 94994.47 | 82.1% | 20705.53 | 4831.72 | 24550.75
26-PC-30185 | Task Order 40: Cedar Hollow Cell Tower Curation | Final Reporting/Review | Fixed fee | Big Sky | Javier Estrada |  | 53400 | 3102.54 | 0 | 42447.66 | 42447.66 | 0 | 2466.42 | 39981.24 | 5.8% | 5.81% | 50933.58 | 95.38% | 2466.42 | 2466.42 | 0
26-PC-30203 | Millbrook Pipeline Data Recovery | In Progress | Fixed fee | Big Sky | Carl Barajas |  | 134800 | 8721.56 | 7426.17 | 102421.04 | 102421.04 | 0 | 6626.59 | 95794.45 | 6.5% | 6.47% | 128173.41 | 95.08% | 6626.59 | 1119.03 | 7426.17
26-PC-30211 | Copper Flats Paleontological Monitoring | Lab/Curation | Fixed fee | Big Sky | Javier Estrada |  | 736100 | 0 | 0 | 498404.34 | 394730.97 | 103673.37 | 0 | 498404.34 | 0% | 0% | 736100 | 100% | 0 | 0 | 0
26-PC-30273 | Task Order 40: Copper Flats Trail Class III Survey | Lab/Curation | Fixed fee | Big Sky | Bob Frye |  | 77200 | 6901.68 | 6811.24 | 53522.76 | 53522.76 | 0 | 4782.94 | 48739.82 | 8.9% | 8.94% | 72417.06 | 93.8% | 4782.94 | 0 | 6811.24
26-PC-30287 | Task Order 40: Maple Fork Solar Historic Resources Evaluation | In Progress | Fixed fee | Big Sky | Javier Estrada |  | 10100 | 5081.31 | 5081.31 | 6193.32 | 6193.32 | 0 | 3115.89 | 3077.43 | 50.3% | 50.31% | 6984.11 | 69.15% | 3115.89 | 0 | 5081.31
26-PC-30329 | Hackberry Bend Rail Siding Built Environment Survey | In Progress | Fixed fee | Big Sky | Javier Estrada |  | 483600 | 122060.64 | 103417.88 | 313904.76 | 313904.76 | 0 | 79237.08 | 234667.68 | 25.2% | 25.24% | 404362.92 | 83.62% | 79237.08 | 11761.54 | 103417.88
26-PC-30338 | On-Call: Saltgrass Mixed-Use Development Phase II Testing | Lab/Curation | Fixed fee | Big Sky | Brendan Melton |  | 268300 | 1529.31 | 1529.31 | 189811.91 | 146074.38 | 43737.53 | 1089.39 | 188722.52 | 0.6% | 0.57% | 267210.61 | 99.59% | 1089.39 | 0 | 1529.31
26-PC-30349 | Phase I: Copper Flats Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Big Sky | Brendan Melton |  | 184200 | 30853.5 | 24917.81 | 105343.98 | 105343.98 | 0 | 17644.68 | 87699.3 | 16.8% | 16.75% | 166555.32 | 90.42% | 17644.68 | 2929.88 | 24917.81
26-PC-30351 | Wildrye Architectural History Survey | In Progress | Fixed fee | Big Sky | Bob Frye |  | 393800 | 132710.6 | 114207.61 | 262900.88 | 262900.88 | 0 | 88597.25 | 174303.63 | 33.7% | 33.7% | 305202.75 | 77.5% | 88597.25 | 11453.13 | 114207.61
26-PC-30396 | Tamarack Historic Resources Evaluation | In Progress | Fixed fee | Big Sky | Brendan Melton |  | 31300 | 0 | 0 | 23853.73 | 23853.73 | 0 | 0 | 23853.73 | 0% | 0% | 31300 | 100% | 0 | 0 | 0
26-PC-30402 | On-Call: Cedar Hollow Highway Widening Paleontological Monitoring | Transferred Entity | Time and material | Big Sky | Carl Barajas |  | 151000 | 0 | 0 | 118603.52 | 90316.94 | 28286.58 | 0 | 118603.52 | 0% | 0% | 151000 | 100% | 0 | 0 | 0
26-PC-30425 | Tamarack Water Main - Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Big Sky | Bob Frye |  | 58100 | 58100 | 58100 | 42076.02 | 42076.02 | 0 | 39854.91 | 2221.11 | 100% | 94.72% | 18245.09 | 31.4% | 0 | 0 | 3067.68
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Big Sky | Javier Estrada | 08/07/2026 | 93100 | 0 | 0 | 63801.43 | 63801.43 | 0 | 65021.47 | -1220.04 | 0% | 101.9% | 28078.53 | 30.16% | 0 | 0 | 0
26-PC-30457 | Wren Hollow Transmission Line - Data Recovery | Final Reporting/Review | Fixed fee | Big Sky | Bob Frye |  | 719800 | 120350.56 | 120350.56 | 547191.96 | 547191.96 | 0 | 91469.2 | 455722.76 | 16.7% | 16.72% | 628330.8 | 87.29% | 91469.2 | 0 | 120350.56
26-PC-30480 | Tansy Flat Canal Lining Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | Big Sky | Javier Estrada |  | 194300 | 194300 | 194300 | 143375.92 | 117312.25 | 26063.67 | 181546.67 | -38170.75 | 100% | 126.6% | 12753.33 | 6.56% | 0 | 0 | 0
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | In Progress | Fixed fee | Big Sky | Brendan Melton | 08/14/2026 | 19900 | 19900 | 19400.11 | 14258.19 | 12707.2 | 1550.99 | 18074.33 | -3816.14 | 100% | 126.8% | 1825.67 | 9.17% | 18074.33 | 218.82 | 19400.11
26-PC-30528 | Plover Cove School Campus Architectural History Survey | In Progress | Fixed fee | Big Sky | Javier Estrada |  | 112900 | 77009.09 | 71440.49 | 74017.24 | 74017.24 | 0 | 50490.81 | 23526.43 | 68.2% | 68.21% | 62409.19 | 55.28% | 50490.81 | 3582.61 | 71440.49
26-PC-30554 | Thistle Down Airport Apron Curation | In Progress | Fixed fee | Big Sky | Bob Frye |  | 139800 | 16678.14 | 9641.87 | 79741.92 | 79741.92 | 0 | 9511.95 | 70229.97 | 11.9% | 11.93% | 130288.05 | 93.2% | 9511.95 | 4400.83 | 9641.87
26-PC-30577 | Task Order 15: Wildrye Bridge Replacement Phase I Survey | On Hold | Fixed fee | Big Sky | Javier Estrada |  | 46800 | 0 | 0 | 36479.31 | 29213.73 | 7265.58 | 0 | 36479.31 | 0% | 0% | 46800 | 100% | 0 | 0 | 0
26-PC-30588 | Bramble Creek Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Bluegrass | Alice Galloway |  | 97000 | 11795.2 | 8704.54 | 75388.4 | 75388.4 | 0 | 9168.73 | 66219.67 | 12.2% | 12.16% | 87831.27 | 90.55% | 9168.73 | 1315.46 | 8704.54
26-PC-30589 | Aspen Ridge Trail Cultural Resources Assessment | Completed | Fixed fee | Bluegrass | Kiara Gillespie |  | 143200 | 143200 | 143200 | 108502.64 | 108502.64 | 0 | 141053.43 | -32550.79 | 100% | 130% | 2146.57 | 1.5% | 0 | 0 | 0
26-PC-30602 | On-Call: Hawk Point Solar Cultural Resources Assessment | In Progress | Time and material | Bluegrass | Kiara Gillespie |  | 211900 | 55300 | 46785.39 | 152752.98 | 141361.45 | 11391.53 | 35317.52 | 117435.46 | 26.1% | 23.12% | 176582.48 | 83.33% | 35317.52 | 5040.65 | 46785.39
26-PC-30634 | Task Order 7: Blue Heron Canal Lining Historic Resources Evaluation | Completed | Time and material | Bluegrass | Kiara Gillespie |  | 21200 | 0 | 0 | 13865.34 | 11167.32 | 2698.02 | 18024.94 | -4159.6 | 0% | 130% | 3175.06 | 14.98% | 0 | 0 | 0
26-PC-30754 | On-Call: Kestrel Butte Highway Widening Archaeological Testing | Final Reporting/Review | Fixed fee | Bluegrass | Alice Galloway |  | 153300 | 12585.93 | 3576.72 | 106834.77 | 106834.77 | 0 | 8772.63 | 98062.14 | 8.2% | 8.21% | 144527.37 | 94.28% | 8772.63 | 8424.08 | 3576.72
26-PC-30781 | Cedar Hollow Trail - Architectural History Survey | Final Billing/Invoice | Fixed fee | Bluegrass | Kiara Gillespie |  | 113700 | 113700 | 113700 | 71210.31 | 71210.31 | 0 | 82296.91 | -11086.6 | 100% | 115.6% | 31403.09 | 27.62% | 0 | 0 | 0
26-PC-30815 | Juniper Wash Water Main Archaeological Testing | In Progress | Fixed fee | Bluegrass | Kiara Gillespie |  | 236000 | 41040.4 | 26899.17 | 177731.6 | 177731.6 | 0 | 30899.89 | 146831.71 | 17.4% | 17.39% | 205100.11 | 86.91% | 30899.89 | 4399.84 | 26899.17
26-PC-30871 | Sea Oat Substation - Section 106 Consultation | Final Billing/Invoice | Time and material | Bluegrass | Alice Galloway |  | 205700 | 0 | 0 | 139834.86 | 139834.86 | 0 | 129872.01 | 9962.85 | 0% | 92.88% | 75827.99 | 36.86% | 0 | 0 | 0
26-PC-30896 | Phase III: Timber Gap Pipeline Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Bluegrass | Kiara Gillespie |  | 158100 | 158100 | 158100 | 109547.49 | 109547.49 | 0 | 104692.72 | 4854.77 | 100% | 95.57% | 53407.28 | 33.78% | 0 | 0 | 7003.83
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 09/18/2026 | 209800 | 0 | 0 | 135467.86 | 135467.86 | 0 | 134699.95 | 767.91 | 0% | 99.43% | 75100.05 | 35.8% | 0 | 0 | 0
26-PC-30945 | Wildrye Reservoir Architectural History Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie |  | 179500 | 83772.65 | 69601.09 | 120265 | 120265 | 0 | 56121.76 | 64143.24 | 46.7% | 46.67% | 123378.24 | 68.73% | 56121.76 | 6979.32 | 69601.09
26-PC-30967 | Timber Gap Pipeline - Built Environment Survey | Final Reporting/Review | Time and material | Bluegrass | Alice Galloway |  | 173400 | 145618.75 | 132862.73 | 108877.86 | 108877.86 | 0 | 91606.15 | 17271.71 | 84% | 84.14% | 81793.85 | 47.17% | 91606.15 | 3708.24 | 132862.73
26-PC-30985 | On-Call: Maple Fork Wastewater Plant Built Environment Survey | Final Billing/Invoice | Fixed fee | Bluegrass | Kiara Gillespie |  | 46500 | 46500 | 46500 | 30100.87 | 25425.4 | 4675.47 | 38312.83 | -8211.96 | 100% | 127.3% | 8187.17 | 17.61% | 0 | 0 | 0
26-PC-31002 | North Fork Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway |  | 211500 | 29144.7 | 13311.23 | 164758.5 | 164758.5 | 0 | 22695.69 | 142062.81 | 13.8% | 13.78% | 188804.31 | 89.27% | 22695.69 | 9737.43 | 13311.23
26-PC-31037 | Cedar Hollow Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway |  | 168500 | 63086.4 | 52530.72 | 131345.75 | 131345.75 | 0 | 49181.51 | 82164.24 | 37.4% | 37.44% | 119318.49 | 70.81% | 49181.51 | 6315.37 | 52530.72
26-PC-31064 | Quail Run Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Gene Nixon |  | 74500 | 74500 | 74500 | 60394.3 | 53043.19 | 7351.11 | 76340.83 | -15946.53 | 100% | 126.4% | -1840.83 | -2.47% | 0 | 0 | 0
26-PC-31084 | Bramble Creek Park Improvements Section 106 Consultation | Final Billing/Invoice | Fixed fee | Cascade | Gene Nixon |  | 28300 | 28300 | 28300 | 14716 | 14716 | 0 | 12592.07 | 2123.93 | 100% | 85.57% | 15707.93 | 55.51% | 0 | 0 | 4083.69
26-PC-31098 | Millbrook School Campus - Environmental Review Support | On Hold | Time and material | Cascade | Cassidy Gay |  | 414100 | 0 | 0 | 297365.21 | 297365.21 | 0 | 0 | 297365.21 | 0% | 0% | 414100 | 100% | 0 | 0 | 0
26-PC-31155 | Slate Ridge Cell Tower - Phase II Testing | Final Billing/Invoice | Fixed fee | Cascade | Jean Cooke |  | 56600 | 56600 | 56600 | 35980.62 | 35980.62 | 0 | 40333.19 | -4352.57 | 100% | 112.1% | 16266.81 | 28.74% | 0 | 0 | 0
26-PC-31174 | Task Order 33: Tamarack Housing Development Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 08/28/2026 | 4400 | 0 | 0 | 2984.25 | 2426.55 | 557.7 | 2714.71 | 269.54 | 0% | 90.97% | 1685.29 | 38.3% | 0 | 0 | 0
26-PC-31182 | Elk Meadow School Campus Curation | In Progress | Fixed fee | Cascade | Jeff Spence |  | 73400 | 8925.44 | 5265.51 | 57596.98 | 57596.98 | 0 | 7004.67 | 50592.31 | 12.2% | 12.16% | 66395.33 | 90.46% | 7004.67 | 2038.32 | 5265.51
26-PC-31186 | Task Order 14: Meadowlark Cell Tower Archaeological Testing | Completed | Time and material | Cascade | Cassidy Gay |  | 43100 | 0 | 0 | 31458.69 | 31458.69 | 0 | 26223.26 | 5235.43 | 0% | 83.36% | 16876.74 | 39.16% | 0 | 0 | 0
26-PC-31209 | Redbud Canal Lining - Built Environment Survey | Final Billing/Invoice | Fixed fee | Cascade | Donald Lutz |  | 960700 | 960700 | 960700 | 765293.62 | 765293.62 | 0 | 893005.2 | -127711.58 | 100% | 116.7% | 67694.8 | 7.05% | 0 | 0 | 0
26-PC-31216 | On-Call: Saltgrass Fiber Route Environmental Review Support | In Progress | Time and material | Cascade | Preston Duarte |  | 172400 | 25313.25 | 6773.41 | 111025.6 | 111025.6 | 0 | 16381.13 | 94644.47 | 14.7% | 14.75% | 156018.87 | 90.5% | 16381.13 | 7730.62 | 6773.41
26-PC-31238 | Task Order 27: Wren Hollow Bridge Replacement Built Environment Survey | In Progress | Time and material | Cascade | Preston Duarte |  | 832700 | 154708.25 | 129716.05 | 533060.12 | 386912.7 | 146147.42 | 91086.67 | 441973.45 | 18.6% | 17.09% | 741613.33 | 89.06% | 91086.67 | 17784.12 | 129716.05
26-PC-31276 | Phase II: Sea Oat Solar Phase I Survey | Final Billing/Invoice | Time and material | Cascade | Jean Cooke |  | 132400 | 0 | 0 | 98558.56 | 98558.56 | 0 | 102977.3 | -4418.74 | 0% | 104.5% | 29422.7 | 22.22% | 0 | 0 | 0
26-PC-31316 | Sparrow Hill Trail Architectural History Survey | Final Reporting/Review | Fixed fee | Cascade | Cassidy Gay |  | 148200 | 38117.04 | 29984.37 | 109860.66 | 109860.66 | 0 | 28261.6 | 81599.06 | 25.7% | 25.72% | 119938.4 | 80.93% | 28261.6 | 4569.5 | 29984.37
26-PC-31421 | Task Order 30: Sage Flat Levee Repair Environmental Review Support | Completed | Fixed fee | Cascade | Cassidy Gay |  | 740400 | 740400 | 740400 | 532717.8 | 532717.8 | 0 | 692533.14 | -159815.34 | 100% | 130% | 47866.86 | 6.46% | 0 | 0 | 0
26-PC-31448 | Foxglove Class III Survey | In Progress | Fixed fee | Cascade | Gene Nixon |  | 25800 | 7216.26 | 6639.74 | 20065.31 | 16136.4 | 3928.91 | 5612.5 | 14452.81 | 28% | 27.97% | 20187.5 | 78.25% | 5612.5 | 757.32 | 6639.74
26-PC-31473 | Plover Cove Mixed-Use Development - Curation | In Progress | Fixed fee | Cascade | Cassidy Gay |  | 180800 | 11119.2 | 2976.07 | 112403.36 | 112403.36 | 0 | 6908.42 | 105494.94 | 6.2% | 6.15% | 173891.58 | 96.18% | 6908.42 | 6578.55 | 2976.07
26-PC-31484 | Maple Fork Wastewater Plant Data Recovery | In Progress | Fixed fee | Cascade | Jean Cooke |  | 31800 | 8223.48 | 7336.57 | 23427.06 | 23427.06 | 0 | 6057.36 | 17369.7 | 25.9% | 25.86% | 25742.64 | 80.95% | 6057.36 | 578.91 | 7336.57
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | In Progress | Fixed fee | Cascade | Donald Lutz |  | 44400 | 31128.84 | 30936.04 | 34032.6 | 34032.6 | 0 | 23861.11 | 10171.49 | 70.1% | 70.11% | 20538.89 | 46.26% | 23861.11 | 175.3 | 30936.04
26-PC-31537 | Raven Rock Park Improvements - Maritime Remote Sensing Survey | In Progress | Fixed fee | Cascade | Preston Duarte |  | 87300 | 4522.14 | 3456.58 | 54449.01 | 54449.01 | 0 | 2823.15 | 51625.86 | 5.2% | 5.18% | 84476.85 | 96.77% | 2823.15 | 1166.9 | 3456.58
26-PC-31568 | Sea Oat Housing Development - Section 106 Consultation | In Progress | Fixed fee | Cascade | Donald Lutz |  | 229100 | 38374.25 | 31669.56 | 148678.02 | 119301 | 29377.02 | 24897.44 | 123780.58 | 16.8% | 16.75% | 204202.56 | 89.13% | 24897.44 | 5924.46 | 31669.56
26-PC-31638 | Kestrel Butte Highway Widening - Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Gene Nixon |  | 170300 | 21611.07 | 13959.16 | 108060.44 | 100421.9 | 7638.54 | 13711.23 | 94349.21 | 12.7% | 12.69% | 156588.77 | 91.95% | 13711.23 | 3415.67 | 13959.16
26-PC-31648 | Rushgrass Draw Solar Data Recovery | In Progress | Fixed fee | Cascade | Jeff Spence |  | 388400 | 167672.28 | 138803.11 | 288425.84 | 288425.84 | 0 | 124527.73 | 163898.11 | 43.2% | 43.17% | 263872.27 | 67.94% | 124527.73 | 14400.56 | 138803.11
26-PC-31678 | Heron Marsh Wind Farm Phase I Survey | In Progress | Fixed fee | Cascade | Preston Duarte |  | 892800 | 297302.4 | 267319.35 | 641923.2 | 641923.2 | 0 | 213779.38 | 428143.82 | 33.3% | 33.3% | 679020.62 | 76.06% | 213779.38 | 24382.91 | 267319.35
26-PC-31692 | Phase III: Meadowlark Reservoir Paleontological Monitoring | In Progress | Fixed fee | Cascade | Preston Duarte |  | 615300 | 36733.41 | 14836.74 | 423803.64 | 362956.1 | 60847.54 | 25309.14 | 398494.5 | 6% | 5.97% | 589990.86 | 95.89% | 25309.14 | 11601.45 | 14836.74
26-PC-31700 | On-Call: Granite Pass Bridge Replacement Environmental Review Support | Completed | Time and material | Cascade | Gene Nixon |  | 49200 | 0 | 0 | 33923.4 | 33923.4 | 0 | 33810.01 | 113.39 | 0% | 99.67% | 15389.99 | 31.28% | 0 | 0 | 0
26-PC-31716 | Saltgrass Wind Farm Data Recovery | In Progress | Fixed fee | Cascade | Donald Lutz |  | 13300 | 3517.85 | 2027.4 | 9413.74 | 9413.74 | 0 | 2489.99 | 6923.75 | 26.5% | 26.45% | 10810.01 | 81.28% | 2489.99 | 540.16 | 2027.4
26-PC-31728 | On-Call: Slate Ridge Housing Development Data Recovery | In Progress | Fixed fee | Cascade | Jeff Spence |  | 38500 | 1963.5 | 332.4 | 31042.55 | 31042.55 | 0 | 1583.43 | 29459.12 | 5.1% | 5.1% | 36916.57 | 95.89% | 1583.43 | 581.98 | 332.4
26-PC-31802 | Bramble Creek Environmental Review Support | Lab/Curation | Fixed fee | Cascade | Jean Cooke |  | 53700 | 30651.96 | 28674.1 | 41655.09 | 41655.09 | 0 | 23774.89 | 17880.2 | 57.1% | 57.08% | 29925.11 | 55.73% | 23774.89 | 2249.93 | 28674.1
26-PC-31823 | Slate Ridge Phase II Testing | Final Reporting/Review | Fixed fee | Cascade | Jeff Spence |  | 173900 | 16068.36 | 5114.84 | 122721.23 | 122721.23 | 0 | 11344.92 | 111376.31 | 9.2% | 9.24% | 162555.08 | 93.48% | 11344.92 | 10378.12 | 5114.84
26-PC-31830 | Ember Valley Archaeological Testing | Transferred Entity | Fixed fee | Cascade | Cassidy Gay |  | 86700 | 40211.46 | 31491.18 | 59425.39 | 54460.35 | 4965.04 | 27563.45 | 31861.94 | 46.4% | 46.38% | 59136.55 | 68.21% | 27563.45 | 5226.34 | 31491.18
26-PC-31872 | Sumac Ridge Water Main Archaeological Testing | Lab/Curation | Fixed fee | Cascade | Donald Lutz |  | 63800 | 33546.04 | 30533.41 | 45642.52 | 45642.52 | 0 | 24000.95 | 21641.57 | 52.6% | 52.58% | 39799.05 | 62.38% | 24000.95 | 1381.22 | 30533.41
26-PC-31881 | Fern Valley Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke |  | 125300 | 0 | 0 | 94955.6 | 80579.84 | 14375.76 | 0 | 94955.6 | 0% | 0% | 125300 | 100% | 0 | 0 | 0
26-PC-32047 | On-Call: Sumac Ridge Mine Expansion Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox |  | 73200 | 51181.44 | 43002 | 51825.6 | 51825.6 | 0 | 36238.56 | 15587.04 | 69.9% | 69.92% | 36961.44 | 50.49% | 36238.56 | 4159.88 | 43002
26-PC-32069 | Task Order 25: Heron Marsh Wind Farm Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Chesapeake | Sandy Kerr |  | 844700 | 65802.13 | 59477.56 | 646026.56 | 646026.56 | 0 | 50316.32 | 595710.24 | 7.8% | 7.79% | 794383.68 | 94.04% | 50316.32 | 4590.71 | 59477.56
26-PC-32076 | Lone Pine Environmental Review Support | Completed | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 165800 | 165800 | 165800 | 125610.08 | 125610.08 | 0 | 111698.97 | 13911.11 | 100% | 88.93% | 54101.03 | 32.63% | 0 | 0 | 18354.06
26-PC-32094 | Maple Fork Trail - Phase II Testing | In Progress | Time and material | Chesapeake | Bryan Mann |  | 19000 | 8805.75 | 8805.75 | 11274.6 | 11274.6 | 0 | 5989.44 | 5285.16 | 46.3% | 53.12% | 13010.56 | 68.48% | 5989.44 | 0 | 8805.75
26-PC-32165 | Juniper Wash Park Improvements - Data Recovery | In Progress | Time and material | Chesapeake | Jason Oconnor |  | 501000 | 13806 | 3832.67 | 394086.6 | 394086.6 | 0 | 10370.06 | 383716.54 | 2.8% | 2.63% | 490629.94 | 97.93% | 10370.06 | 3793.74 | 3832.67
26-PC-32188 | Creosote Draw Reservoir Curation | In Progress | Fixed fee | Chesapeake | Ian Maddox |  | 91500 | 0 | 0 | 74856.15 | 74856.15 | 0 | 0 | 74856.15 | 0% | 0% | 91500 | 100% | 0 | 0 | 0
26-PC-32227 | Foxglove Harbor Dredging Paleontological Monitoring | Completed | Time and material | Chesapeake | Sandy Kerr |  | 32900 | 0 | 0 | 22437.8 | 22437.8 | 0 | 23290.1 | -852.3 | 0% | 103.8% | 9609.9 | 29.21% | 0 | 0 | 0
26-PC-32288 | Quail Run Solar - Architectural History Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox |  | 400500 | 4365.45 | 2126.22 | 287318.7 | 287318.7 | 0 | 3140.21 | 284178.49 | 1.1% | 1.09% | 397359.79 | 99.22% | 3140.21 | 3140.21 | 2126.22
26-PC-32303 | Lone Pine Housing Development - Archaeological Testing | In Progress | Time and material | Chesapeake | Ian Maddox |  | 18700 | 816 | 277.36 | 13411.64 | 13411.64 | 0 | 852.48 | 12559.16 | 4.4% | 6.36% | 17847.52 | 95.44% | 852.48 | 852.48 | 277.36
26-PC-32322 | Foxglove Fiber Route - Curation | In Progress | Fixed fee | Chesapeake | Sandy Kerr |  | 317500 | 39751 | 37103.87 | 244665.5 | 244665.5 | 0 | 30629.91 | 214035.59 | 12.5% | 12.52% | 286870.09 | 90.35% | 30629.91 | 0 | 37103.87
26-PC-32369 | Twin Buttes Water Main - Phase I Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox |  | 730600 | 71233.5 | 65269.21 | 470798.64 | 470798.64 | 0 | 45896.51 | 424902.13 | 9.8% | 9.75% | 684703.49 | 93.72% | 45896.51 | 2957.36 | 65269.21
26-PC-32382 | Sea Oat Airport Apron Data Recovery | Final Billing/Invoice | Fixed fee | Chesapeake | Ian Maddox |  | 180500 | 180500 | 180500 | 138172.75 | 138172.75 | 0 | 160382.34 | -22209.59 | 100% | 116.1% | 20117.66 | 11.15% | 0 | 0 | 0
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann |  | 13700 | 13700 | 13641.82 | 9522.87 | 9522.87 | 0 | 31103.81 | -21580.94 | 100% | 326.6% | -17403.81 | -127% | 31103.81 | 50.01 | 13641.82
26-PC-32396 | On-Call: Copper Flats Mixed-Use Development Curation | Final Reporting/Review | Time and material | Chesapeake | Sandy Kerr |  | 205600 | 5224.75 | 2772.21 | 152123.45 | 136826.23 | 15297.22 | 3555.36 | 148568.09 | 2.5% | 2.34% | 202044.64 | 98.27% | 3555.36 | 1854 | 2772.21
26-PC-32420 | Phase I: Copper Flats Water Main Architectural History Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 324200 | 13843.34 | 4463.06 | 246926.01 | 225112.5 | 21813.51 | 10551.41 | 236374.6 | 4.3% | 4.27% | 313648.59 | 96.75% | 10551.41 | 9064.48 | 4463.06
26-PC-32442 | Sumac Ridge Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Chesapeake | Sandy Kerr |  | 53400 | 17088 | 14860.55 | 33316.26 | 33316.26 | 0 | 10661.31 | 22654.95 | 32% | 32% | 42738.69 | 80.03% | 10661.31 | 656.79 | 14860.55
26-PC-32453 | Quail Run Housing Development Phase II Testing | In Progress | Time and material | Chesapeake | Ian Maddox |  | 103800 | 6785.75 | 1853.51 | 74927.88 | 58312.8 | 16615.08 | 4515.47 | 70412.41 | 6.5% | 6.03% | 99284.53 | 95.65% | 4515.47 | 3076.9 | 1853.51
26-PC-32540 | Task Order 36: Granite Pass Mixed-Use Development Phase II Testing | Lab/Curation | Time and material | Chesapeake | Bryan Mann |  | 846100 | 79570 | 49253.92 | 625775.56 | 625775.56 | 0 | 55637.33 | 570138.23 | 9.4% | 8.89% | 790462.67 | 93.42% | 55637.33 | 16358.9 | 49253.92
26-PC-32556 | Maple Fork Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Sandy Kerr |  | 45700 | 15771.07 | 13650.9 | 32259.63 | 32259.63 | 0 | 11132.77 | 21126.86 | 34.5% | 34.51% | 34567.23 | 75.64% | 11132.77 | 1223.53 | 13650.9
26-PC-32563 | On-Call: Creosote Draw Substation Phase I Survey | Transferred Entity | Fixed fee | Chesapeake | Bryan Mann |  | 534900 | 133136.61 | 127694.45 | 344315.13 | 344315.13 | 0 | 85685.88 | 258629.25 | 24.9% | 24.89% | 449214.12 | 83.98% | 85685.88 | 3262.44 | 127694.45
26-PC-32569 | Hawk Point Data Recovery | Completed | Fixed fee | Chesapeake | Bryan Mann |  | 191800 | 191800 | 191800 | 155949 | 122498.04 | 33450.96 | 151388.06 | 4560.94 | 100% | 97.08% | 40411.94 | 21.07% | 0 | 0 | 5600.56
26-PC-32594 | On-Call: Tamarack Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Jason Oconnor |  | 94400 | 51193.12 | 38376.64 | 71536.32 | 71536.32 | 0 | 38790.59 | 32745.73 | 54.2% | 54.23% | 55609.41 | 58.91% | 38790.59 | 9472.29 | 38376.64
26-PC-32614 | Fern Valley Architectural History Survey | In Progress | Time and material | Chesapeake | Ian Maddox |  | 29700 | 0 | 0 | 20748.42 | 20748.42 | 0 | 0 | 20748.42 | 0% | 0% | 29700 | 100% | 0 | 0 | 0
26-PC-32646 | Goldfinch Historic Resources Evaluation | In Progress | Time and material | Chesapeake | Ian Maddox |  | 48600 | 24344.25 | 19074.93 | 33922.8 | 33922.8 | 0 | 15954.4 | 17968.4 | 50.1% | 47.03% | 32645.6 | 67.17% | 15954.4 | 3734.83 | 19074.93
26-PC-32668 | Millbrook Trail - Data Recovery | Final Billing/Invoice | Time and material | Chesapeake | Alexandria Wilkinson |  | 300600 | 0 | 0 | 206151.48 | 206151.48 | 0 | 209897.1 | -3745.62 | 0% | 101.8% | 90702.9 | 30.17% | 0 | 0 | 0
26-PC-32707 | On-Call: Creosote Draw Transmission Line Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Sandy Kerr |  | 327400 | 152306.48 | 137397.62 | 229376.44 | 229376.44 | 0 | 106701.23 | 122675.21 | 46.5% | 46.52% | 220698.77 | 67.41% | 106701.23 | 10438.6 | 137397.62
26-PC-32711 | Creosote Draw Phase I Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor |  | 62100 | 12997.53 | 10647.65 | 44997.66 | 44997.66 | 0 | 9419.95 | 35577.71 | 20.9% | 20.93% | 52680.05 | 84.83% | 9419.95 | 1719.7 | 10647.65
26-PC-32725 | Willow Springs Wind Farm - GIS Mapping | Final Reporting/Review | Fixed fee | Chesapeake | Bryan Mann |  | 26300 | 16079.82 | 12170.12 | 18699.3 | 18699.3 | 0 | 11432.01 | 7267.29 | 61.1% | 61.14% | 14867.99 | 56.53% | 11432.01 | 1538.24 | 12170.12
26-PC-32727 | North Fork Mine Expansion - Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Chesapeake | Alexandria Wilkinson |  | 70100 | 57594.16 | 57594.16 | 47310.49 | 47310.49 | 0 | 38868.52 | 8441.97 | 82.2% | 82.16% | 31231.48 | 44.55% | 0 | 0 | 0
26-PC-32731 | Wildrye Fiber Route Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Chesapeake | Bryan Mann |  | 26000 | 26000 | 26000 | 20311.2 | 20311.2 | 0 | 15521.91 | 4789.29 | 100% | 76.42% | 10478.09 | 40.3% | 0 | 0 | 6130.8
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Cost Tracking on Closed Project | Time and material | Chesapeake | Sandy Kerr |  | 137100 | 0 | 0 | 100617.66 | 93287.5 | 7330.16 | 122245.29 | -21627.63 | 0% | 121.5% | 14854.71 | 10.83% | 0 | 0 | 0
26-PC-32745 | Task Order 37: Hawk Point Park Improvements Phase II Testing | In Progress | Fixed fee | Chesapeake | Ian Maddox |  | 135300 | 56149.5 | 34745.99 | 89758.02 | 89758.02 | 0 | 37247.73 | 52510.29 | 41.5% | 41.5% | 98052.27 | 72.47% | 37247.73 | 14650.49 | 34745.99
26-PC-32773 | Oak Terrace Paleontological Monitoring | In Progress | Fixed fee | Front Range | Mindy Galvan |  | 48100 | 21236.15 | 16486.92 | 32496.36 | 32496.36 | 0 | 14347.77 | 18148.59 | 44.2% | 44.15% | 33752.23 | 70.17% | 14347.77 | 1882.68 | 16486.92
26-PC-32803 | Copper Flats Housing Development Archaeological Testing | Final Billing/Invoice | Time and material | Front Range | Kimberly Daugherty |  | 198300 | 0 | 0 | 132700 | 111823 | 20877 | 163858.96 | -31158.96 | 0% | 123.5% | 34441.04 | 17.37% | 0 | 0 | 0
26-PC-32852 | Task Order 39: Foxglove Highway Widening Data Recovery | In Progress | Time and material | Front Range | Joanna Herrera |  | 148800 | 31449.25 | 18923.38 | 95395.68 | 95395.68 | 0 | 18228.56 | 77167.12 | 21.1% | 19.11% | 130571.44 | 87.75% | 18228.56 | 3216.45 | 18923.38
26-PC-32946 | Phase I: Plover Cove Levee Repair GIS Mapping | On Hold | Time and material | Front Range | Jeremy Tran |  | 151600 | 0 | 0 | 96190.2 | 96190.2 | 0 | 0 | 96190.2 | 0% | 0% | 151600 | 100% | 0 | 0 | 0
26-PC-32973 | Sage Flat GIS Mapping | On Hold | Time and material | Front Range | Mindy Galvan |  | 203200 | 0 | 0 | 132028.51 | 111088.4 | 20940.11 | 0 | 132028.51 | 0% | 0% | 203200 | 100% | 0 | 0 | 0
26-PC-32985 | Pine Hollow Built Environment Survey | In Progress | Fixed fee | Front Range | Jeremy Tran |  | 106500 | 64783.95 | 55174.32 | 89214.38 | 75741.38 | 13473 | 54267.06 | 34947.32 | 60.8% | 60.83% | 52232.94 | 49.05% | 54267.06 | 7499.58 | 55174.32
26-PC-33011 | Kestrel Butte Wastewater Plant Curation | Completed | Fixed fee | Front Range | Devon Pitts |  | 590600 | 590600 | 590600 | 477965.46 | 397509.56 | 80455.9 | 549114.61 | -71149.15 | 100% | 114.9% | 41485.39 | 7.02% | 0 | 0 | 0
26-PC-33017 | Redbud Battery Storage - Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Mindy Galvan |  | 588600 | 188116.56 | 188116.56 | 441413.1 | 336449.96 | 104963.14 | 141067.52 | 300345.58 | 32% | 31.96% | 447532.48 | 76.03% | 141067.52 | 0 | 188116.56
26-PC-33033 | Task Order 10: Pebble Beach Road Highway Widening Environmental Review Support | On Hold | Fixed fee | Front Range | Joanna Herrera |  | 121200 | 0 | 0 | 102111 | 102111 | 0 | 0 | 102111 | 0% | 0% | 121200 | 100% | 0 | 0 | 0
26-PC-33099 | Eagle Bend Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Joanna Herrera |  | 164900 | 29055.38 | 16045.73 | 122091.96 | 122091.96 | 0 | 21510.66 | 100581.3 | 17.6% | 17.62% | 143389.34 | 86.96% | 21510.66 | 8471.98 | 16045.73
26-PC-33127 | Fern Valley Phase I Survey | In Progress | Time and material | Front Range | Kimberly Daugherty |  | 179500 | 46153.5 | 39555.28 | 119968.02 | 92441.25 | 27526.77 | 30425.42 | 89542.6 | 25.7% | 25.36% | 149074.58 | 83.05% | 30425.42 | 3645.87 | 39555.28
26-PC-33162 | Phase III: Yarrow Point Airport Apron GIS Mapping | In Progress | Time and material | Front Range | Dean Velazquez |  | 81900 | 9863.25 | 8708.14 | 55036.8 | 55036.8 | 0 | 6614.56 | 48422.24 | 12% | 12.02% | 75285.44 | 91.92% | 6614.56 | 0 | 8708.14
26-PC-33217 | Larkspur Phase II Testing | Final Billing/Invoice | Fixed fee | Front Range | Devon Pitts |  | 28700 | 28700 | 28700 | 20572.16 | 20572.16 | 0 | 23901.25 | -3329.09 | 100% | 116.2% | 4798.75 | 16.72% | 0 | 0 | 0
26-PC-33223 | Meadowlark Levee Repair - Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Front Range | Jeremy Tran |  | 51600 | 51600 | 51600 | 37858.92 | 37858.92 | 0 | 49216.6 | -11357.68 | 100% | 130% | 2383.4 | 4.62% | 0 | 0 | 0
26-PC-33255 | Task Order 13: Pine Hollow Substation Maritime Remote Sensing Survey | Final Billing/Invoice | Time and material | Front Range | Devon Pitts |  | 70300 | 0 | 0 | 51804.07 | 51804.07 | 0 | 66810.42 | -15006.35 | 0% | 129% | 3489.58 | 4.96% | 0 | 0 | 0
26-PC-33257 | Badger Hollow Levee Repair - Curation | Completed | Time and material | Front Range | Joanna Herrera |  | 60000 | 0 | 0 | 42360 | 42360 | 0 | 42545.9 | -185.9 | 0% | 100.4% | 17454.1 | 29.09% | 0 | 0 | 0
26-PC-33276 | Quail Run Housing Development Archaeological Testing | In Progress | Time and material | Front Range | Jeremy Tran |  | 64200 | 15702.5 | 15096.5 | 42609.54 | 42609.54 | 0 | 10124.5 | 32485.04 | 24.5% | 23.76% | 54075.5 | 84.23% | 10124.5 | 105.69 | 15096.5
26-PC-33413 | Hawk Point Bridge Replacement Cultural Resources Monitoring | Final Billing/Invoice | Time and material | Front Range | Jeremy Tran |  | 484800 | 0 | 0 | 325106.88 | 325106.88 | 0 | 420732.7 | -95625.82 | 0% | 129.4% | 64067.3 | 13.22% | 0 | 0 | 0
26-PC-33485 | Sea Oat Harbor Dredging GIS Mapping | In Progress | Time and material | Front Range | Dean Velazquez |  | 563800 | 45105.5 | 22501.56 | 406950.84 | 406950.84 | 0 | 29789.86 | 377160.98 | 8% | 7.32% | 534010.14 | 94.72% | 29789.86 | 13346.85 | 22501.56
26-PC-33505 | Stone Mill Park Improvements - Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Mindy Galvan |  | 105100 | 1492.42 | 398.58 | 81200.26 | 81200.26 | 0 | 1152.87 | 80047.39 | 1.4% | 1.42% | 103947.13 | 98.9% | 1152.87 | 1152.87 | 398.58
26-PC-33533 | Harbor View Wastewater Plant Phase I Survey | Final Billing/Invoice | Fixed fee | Front Range | Jeremy Tran |  | 37700 | 37700 | 37700 | 27626.56 | 27626.56 | 0 | 35914.53 | -8287.97 | 100% | 130% | 1785.47 | 4.74% | 0 | 0 | 0
26-PC-33563 | Foxglove Phase I Survey | In Progress | Fixed fee | Front Range | Devon Pitts |  | 61100 | 0 | 0 | 42098.14 | 35698.3 | 6399.84 | 0 | 42098.14 | 0% | 0% | 61100 | 100% | 0 | 0 | 0
26-PC-33588 | Fern Valley Trail - Cultural Resources Assessment | Lab/Curation | Time and material | Front Range | Joanna Herrera |  | 207400 | 38333.25 | 35440.47 | 141868.32 | 122263.6 | 19604.72 | 25436.79 | 116431.53 | 18.5% | 17.93% | 181963.21 | 87.74% | 25436.79 | 1849.84 | 35440.47
26-PC-33624 | Stone Mill Airport Apron - Phase II Testing | Final Billing/Invoice | Fixed fee | Front Range | Devon Pitts |  | 54500 | 54500 | 54500 | 38509.7 | 38509.7 | 0 | 50062.61 | -11552.91 | 100% | 130% | 4437.39 | 8.14% | 0 | 0 | 0
26-PC-33660 | Task Order 33: Fern Valley Water Main Section 106 Consultation | In Progress | Fixed fee | Front Range | Dean Velazquez |  | 108400 | 24216.56 | 7479.68 | 94229.41 | 77792 | 16437.41 | 21052.74 | 73176.67 | 22.3% | 22.34% | 87347.26 | 80.58% | 21052.74 | 8059.99 | 7479.68
26-PC-33684 | On-Call: Juniper Wash Airport Apron Paleontological Monitoring | Final Reporting/Review | Time and material | Front Range | Kimberly Daugherty |  | 24000 | 4253.75 | 1910.97 | 17450.4 | 17450.4 | 0 | 2500.59 | 14949.81 | 17.7% | 14.33% | 21499.41 | 89.58% | 2500.59 | 1134.41 | 1910.97
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Final Reporting/Review | Fixed fee | Great Lakes | Karl Valenzuela | 09/18/2026 | 21700 | 21700 | 11375.68 | 18501.42 | 18501.42 | 0 | 21928.62 | -3427.2 | 100% | 118.5% | -228.62 | -1.05% | 21928.62 | 4870.23 | 11375.68
26-PC-33705 | Twin Buttes Phase I Survey | In Progress | Fixed fee | Great Lakes | Karl Valenzuela |  | 211200 | 101629.44 | 84698.25 | 166784.64 | 166784.64 | 0 | 80257.44 | 86527.2 | 48.1% | 48.12% | 130942.56 | 62% | 80257.44 | 10450.03 | 84698.25
26-PC-33719 | Saltgrass GIS Mapping | In Progress | Fixed fee | Great Lakes | Gina Beltran |  | 394200 | 11274.12 | 4081.27 | 310235.4 | 310235.4 | 0 | 8878.32 | 301357.08 | 2.9% | 2.86% | 385321.68 | 97.75% | 8878.32 | 3843.11 | 4081.27
26-PC-33727 | Task Order 25: Badger Hollow Canal Lining Architectural History Survey | Final Billing/Invoice | Fixed fee | Great Lakes | Angelica Cervantes |  | 185200 | 185200 | 185200 | 146011.68 | 146011.68 | 0 | 135472.77 | 10538.91 | 100% | 92.78% | 49727.23 | 26.85% | 0 | 0 | 13371.44
26-PC-33743 | Raven Rock Canal Lining Architectural History Survey | In Progress | Fixed fee | Great Lakes | Brendan Padilla |  | 111800 | 61277.58 | 58305.85 | 75766.86 | 75766.86 | 0 | 41526.74 | 34240.12 | 54.8% | 54.81% | 70273.26 | 62.86% | 41526.74 | 3394.7 | 58305.85
26-PC-33773 | Aspen Ridge Maritime Remote Sensing Survey | On Hold | Fixed fee | Great Lakes | Geoffrey Fernandez |  | 41200 | 0 | 0 | 25469.84 | 25469.84 | 0 | 0 | 25469.84 | 0% | 0% | 41200 | 100% | 0 | 0 | 0
26-PC-33834 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Great Lakes | Leonard Mejia |  | 204800 | 48885.76 | 40950.62 | 158052.15 | 136321.79 | 21730.36 | 37725.67 | 120326.48 | 23.9% | 23.87% | 167074.33 | 81.58% | 37725.67 | 5630.3 | 40950.62
26-PC-33896 | Maple Fork Trail Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert |  | 69800 | 21798.54 | 14218.1 | 48734.36 | 48734.36 | 0 | 15222.15 | 33512.21 | 31.2% | 31.23% | 54577.85 | 78.19% | 15222.15 | 1702.37 | 14218.1
26-PC-33903 | Task Order 3: Silver Lake Solar Cultural Resources Monitoring | Final Billing/Invoice | Fixed fee | Great Lakes | Reginald Koch |  | 1201100 | 1201100 | 1201100 | 916078.97 | 916078.97 | 0 | 1002792.56 | -86713.59 | 100% | 109.5% | 198307.44 | 16.51% | 0 | 0 | 0
26-PC-33913 | Windmill Flat Section 106 Consultation | Final Reporting/Review | Time and material | Great Lakes | Angelica Cervantes |  | 31100 | 1702.75 | 828.06 | 20015.96 | 20015.96 | 0 | 1134.5 | 18881.46 | 5.5% | 5.67% | 29965.5 | 96.35% | 1134.5 | 0 | 828.06
26-PC-33950 | Raven Rock Built Environment Survey | Final Billing/Invoice | Fixed fee | Great Lakes | Robin Mercado |  | 483700 | 483700 | 483700 | 372594.11 | 372594.11 | 0 | 306150.14 | 66443.97 | 100% | 82.17% | 177549.86 | 36.71% | 0 | 0 | 86243.71
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 09/18/2026 | 76400 | 76400 | 70250.02 | 53087.85 | 46646.64 | 6441.21 | 80951.18 | -27863.33 | 100% | 152.5% | -4551.18 | -5.96% | 80951.18 | 5802.63 | 70250.02
26-PC-34114 | Granite Pass Canal Lining - Section 106 Consultation | In Progress | Time and material | Great Lakes | Brendan Padilla |  | 216500 | 17201 | 12093.51 | 145812.75 | 145812.75 | 0 | 9715.07 | 136097.68 | 7.9% | 6.66% | 206784.93 | 95.51% | 9715.07 | 2189.86 | 12093.51
26-PC-34198 | Tansy Flat Pipeline - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Brendan Padilla |  | 65600 | 16223.25 | 16223.25 | 47297.6 | 47297.6 | 0 | 9004.51 | 38293.09 | 24.7% | 19.04% | 56595.49 | 86.27% | 9004.51 | 0 | 16223.25
26-PC-34247 | Harbor View Trail Phase I Survey | Final Billing/Invoice | Fixed fee | Great Lakes | Robin Mercado |  | 106200 | 106200 | 106200 | 73362.96 | 73362.96 | 0 | 95371.85 | -22008.89 | 100% | 130% | 10828.15 | 10.2% | 0 | 0 | 0
26-PC-34297 | Badger Hollow Historic Resources Evaluation | In Progress | Fixed fee | Great Lakes | Reginald Koch |  | 41700 | 3494.46 | 3494.46 | 29306.76 | 29306.76 | 0 | 2455.17 | 26851.59 | 8.4% | 8.38% | 39244.83 | 94.11% | 2455.17 | 0 | 3494.46
26-PC-34336 | Pine Hollow Solar Architectural History Survey | In Progress | Fixed fee | Great Lakes | Robin Mercado |  | 56500 | 17159.05 | 16619.72 | 40414.45 | 40414.45 | 0 | 12273.01 | 28141.44 | 30.4% | 30.37% | 44226.99 | 78.28% | 12273.01 | 488.19 | 16619.72
26-PC-34394 | Ember Valley Battery Storage Maritime Remote Sensing Survey | In Progress | Time and material | Great Lakes | Angelica Cervantes |  | 134200 | 0 | 0 | 94370.11 | 80628.03 | 13742.08 | 0 | 94370.11 | 0% | 0% | 134200 | 100% | 0 | 0 | 0
26-PC-34400 | Wren Hollow Curation | In Progress | Fixed fee | Great Lakes | Leonard Mejia |  | 34200 | 2072.52 | 1844.21 | 23833.56 | 20735.65 | 3097.91 | 1444.35 | 22389.21 | 6.1% | 6.06% | 32755.65 | 95.78% | 1444.35 | 0 | 1844.21
26-PC-34432 | Stone Mill Bridge Replacement - GIS Mapping | Final Reporting/Review | Fixed fee | Great Lakes | Reginald Koch |  | 117900 | 10245.51 | 6103.62 | 80620.02 | 80620.02 | 0 | 7006.23 | 73613.79 | 8.7% | 8.69% | 110893.77 | 94.06% | 7006.23 | 1945.36 | 6103.62
26-PC-34472 | Eagle Bend Canal Lining Phase II Testing | Completed | Time and material | Great Lakes | Gina Beltran |  | 25400 | 0 | 0 | 16500.99 | 13601.12 | 2899.87 | 14935.8 | 1565.19 | 0% | 90.51% | 10464.2 | 41.2% | 0 | 0 | 0
26-PC-34477 | Willow Springs Pipeline - Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Geoffrey Fernandez |  | 212500 | 23481.25 | 15454.44 | 157143.75 | 157143.75 | 0 | 17368.48 | 139775.27 | 11.1% | 11.05% | 195131.52 | 91.83% | 17368.48 | 6091.28 | 15454.44
26-PC-34487 | Quail Run Airport Apron - Phase I Survey | In Progress | Time and material | Great Lakes | Jeff Pugh |  | 488600 | 212913.75 | 171542.56 | 348176.36 | 348176.36 | 0 | 135902.87 | 212273.49 | 43.6% | 39.03% | 352697.13 | 72.19% | 135902.87 | 20883.44 | 171542.56
26-PC-34552 | Blue Heron Mine Expansion Phase I Survey | Lab/Curation | Fixed fee | Great Lakes | Geoffrey Fernandez |  | 245500 | 4639.95 | 2962.54 | 205115.25 | 205115.25 | 0 | 3881.67 | 201233.58 | 1.9% | 1.89% | 241618.33 | 98.42% | 3881.67 | 269.17 | 2962.54
26-PC-34574 | Elk Meadow Pipeline Paleontological Monitoring | Completed | Time and material | Great Lakes | Brendan Padilla |  | 1357400 | 0 | 0 | 944343.18 | 944343.18 | 0 | 1020057.26 | -75714.08 | 0% | 108% | 337342.74 | 24.85% | 0 | 0 | 0
26-PC-34602 | Phase III: Sandpiper Park Improvements Historic Resources Evaluation | In Progress | Fixed fee | Great Lakes | Brendan Padilla |  | 36800 | 32321.44 | 28986.41 | 26501.12 | 21328.5 | 5172.62 | 23274.94 | 3226.18 | 87.8% | 87.83% | 13525.06 | 36.75% | 23274.94 | 1743.47 | 28986.41
26-PC-34611 | Wren Hollow Pipeline Environmental Review Support | In Progress | Time and material | Great Lakes | Robin Mercado |  | 365800 | 0 | 0 | 264180.76 | 264180.76 | 0 | 0 | 264180.76 | 0% | 0% | 365800 | 100% | 0 | 0 | 0
26-PC-34628 | Meadowlark Canal Lining Class III Survey | Final Billing/Invoice | Fixed fee | Great Lakes | Leonard Mejia |  | 121500 | 121500 | 121500 | 80104.95 | 80104.95 | 0 | 75141.77 | 4963.18 | 100% | 93.8% | 46358.23 | 38.15% | 0 | 0 | 7533
26-PC-34631 | Tamarack Battery Storage - Phase I Survey | Completed | Fixed fee | Great Lakes | Brendan Padilla |  | 438600 | 438600 | 438600 | 344257.14 | 344257.14 | 0 | 339100.9 | 5156.24 | 100% | 98.5% | 99499.1 | 22.69% | 0 | 0 | 6579
26-PC-34701 | North Fork Paleontological Monitoring | Final Billing/Invoice | Time and material | Great Lakes | Kathleen Galvan |  | 248300 | 0 | 0 | 162629.9 | 138920.73 | 23709.17 | 211418.87 | -48788.97 | 0% | 130% | 36881.13 | 14.85% | 0 | 0 | 0
26-PC-34711 | Hackberry Bend Section 106 Consultation | Completed | Fixed fee | Great Lakes | Karl Valenzuela |  | 34000 | 34000 | 34000 | 25561.2 | 25561.2 | 0 | 21829.21 | 3731.99 | 100% | 85.4% | 12170.79 | 35.8% | 0 | 0 | 4964
26-PC-34725 | Redbud Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Kathleen Galvan |  | 107600 | 12083.48 | 8872.18 | 89211.16 | 89211.16 | 0 | 10016.64 | 79194.52 | 11.2% | 11.23% | 97583.36 | 90.69% | 10016.64 | 0 | 8872.18
26-PC-34757 | Kestrel Butte Data Recovery | In Progress | Time and material | Great Lakes | Angelica Cervantes | 08/28/2026 | 43800 | 43800 | 29653.46 | 30230.76 | 30230.76 | 0 | 49508.25 | -19277.49 | 100% | 163.8% | -5708.25 | -13.03% | 49508.25 | 8857.9 | 29653.46
26-PC-34794 | On-Call: Kestrel Butte Reservoir Class III Survey | Completed | Fixed fee | Gulf Coast East | Courtney Daugherty |  | 40000 | 40000 | 40000 | 25252 | 25252 | 0 | 32827.6 | -7575.6 | 100% | 130% | 7172.4 | 17.93% | 0 | 0 | 0
26-PC-34906 | Cedar Hollow Harbor Dredging - Curation | In Progress | Fixed fee | Gulf Coast | Sean Jennings |  | 81100 | 41961.14 | 34013.4 | 60821.43 | 44369.15 | 16452.28 | 31471.96 | 29349.47 | 51.7% | 51.74% | 49628.04 | 61.19% | 31471.96 | 5622.73 | 34013.4
26-PC-34965 | On-Call: Pebble Beach Road Fiber Route Section 106 Consultation | Final Reporting/Review | Fixed fee | Gulf Coast East | Wyatt Erickson |  | 131600 | 0 | 0 | 95225.76 | 95225.76 | 0 | 0 | 95225.76 | 0% | 0% | 131600 | 100% | 0 | 0 | 0
26-PC-34982 | Sandpiper Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 09/11/2026 | 10600 | 10600 | 7692.83 | 7895.94 | 7895.94 | 0 | 18818.09 | -10922.15 | 100% | 238.3% | -8218.09 | -77.53% | 18818.09 | 81.07 | 7692.83
26-PC-35012 | Task Order 40: Granite Pass Harbor Dredging Archaeological Testing | Final Billing/Invoice | Time and material | Gulf Coast East | Wyatt Erickson |  | 179700 | 0 | 0 | 130282.5 | 130282.5 | 0 | 155527.73 | -25245.23 | 0% | 119.4% | 24172.27 | 13.45% | 0 | 0 | 0
26-PC-35056 | Yarrow Point Cell Tower - Section 106 Consultation | Lab/Curation | Fixed fee | Gulf Coast West | Sean Jennings |  | 92800 | 46381.44 | 43606.66 | 78555.2 | 78555.2 | 0 | 39261.22 | 39293.98 | 50% | 49.98% | 53538.78 | 57.69% | 39261.22 | 1043.48 | 43606.66
26-PC-35062 | Phase I: Falcon Mesa Park Improvements Data Recovery | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson |  | 267300 | 30659.31 | 4507.74 | 207542.06 | 185979.15 | 21562.91 | 23807.74 | 183734.32 | 11.5% | 11.47% | 243492.26 | 91.09% | 23807.74 | 15072.56 | 4507.74
26-PC-35063 | Meadowlark School Campus - Phase I Survey | Final Reporting/Review | Fixed fee | Gulf Coast East | Bernard Erickson |  | 112100 | 59166.38 | 53777.48 | 70129.76 | 70129.76 | 0 | 37016.5 | 33113.26 | 52.8% | 52.78% | 75083.5 | 66.98% | 37016.5 | 1452.2 | 53777.48
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty |  | 29600 | 29600 | 22003.12 | 19287.36 | 19287.36 | 0 | 56287.28 | -36999.92 | 100% | 291.8% | -26687.28 | -90.16% | 56287.28 | 2131.6 | 22003.12
26-PC-35111 | Fern Valley GIS Mapping | Final Billing/Invoice | Fixed fee | Gulf Coast West | Bernard Erickson |  | 114800 | 114800 | 114800 | 81129.16 | 81129.16 | 0 | 73694.31 | 7434.85 | 100% | 90.84% | 41105.69 | 35.81% | 0 | 0 | 10515.68
26-PC-35158 | Sparrow Hill Trail Phase I Survey | In Progress | Fixed fee | Gulf Coast | Bernard Erickson |  | 41600 | 12629.76 | 5669.01 | 27755.93 | 24147.48 | 3608.45 | 8426.77 | 19329.16 | 30.4% | 30.36% | 33173.23 | 79.74% | 8426.77 | 8426.77 | 5669.01
26-PC-35193 | Heron Marsh Reservoir - Phase II Testing | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 08/07/2026 | 102600 | 82510.92 | 71608.18 | 74022.89 | 54115.25 | 19907.64 | 59527.5 | 14495.39 | 80.4% | 80.42% | 43072.5 | 41.98% | 59527.5 | 6645.64 | 71608.18
26-PC-35201 | Plover Cove Transmission Line Data Recovery | Lab/Curation | Fixed fee | Gulf Coast | Sean Jennings |  | 51600 | 1558.32 | 145.25 | 40057.08 | 40057.08 | 0 | 1211.47 | 38845.61 | 3% | 3.02% | 50388.53 | 97.65% | 1211.47 | 1211.47 | 145.25
26-PC-35220 | Badger Hollow Highway Widening GIS Mapping | In Progress | Time and material | Gulf Coast West | Bernard Erickson |  | 109500 | 4400.75 | 1288.42 | 69598.2 | 69598.2 | 0 | 3074.48 | 66523.72 | 4% | 4.42% | 106425.52 | 97.19% | 3074.48 | 3074.48 | 1288.42
26-PC-35245 | Stone Mill Cell Tower - Curation | Completed | Time and material | Gulf Coast East | Wyatt Erickson |  | 240900 | 0 | 0 | 162438.87 | 162438.87 | 0 | 157928.04 | 4510.83 | 0% | 97.22% | 82971.96 | 34.44% | 0 | 0 | 0
26-PC-35248 | Granite Pass Levee Repair - Curation | Final Billing/Invoice | Fixed fee | Gulf Coast East | Bernard Erickson |  | 107400 | 107400 | 107400 | 75437.76 | 75437.76 | 0 | 65927.7 | 9510.06 | 100% | 87.39% | 41472.3 | 38.61% | 0 | 0 | 13543.14
26-PC-35302 | Task Order 37: Hackberry Bend Battery Storage Cultural Resources Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson |  | 82400 | 32292.56 | 21108.58 | 69199.52 | 69199.52 | 0 | 27118.13 | 42081.39 | 39.2% | 39.19% | 55281.87 | 67.09% | 27118.13 | 3249.28 | 21108.58
26-PC-35318 | Copper Flats Curation | In Progress | Fixed fee | Gulf Coast West | Wyatt Erickson |  | 153900 | 37289.97 | 27419.19 | 103851.72 | 103851.72 | 0 | 25162.21 | 78689.51 | 24.2% | 24.23% | 128737.79 | 83.65% | 25162.21 | 4192.7 | 27419.19
26-PC-35381 | Badger Hollow Mine Expansion Archaeological Testing | In Progress | Fixed fee | High Desert | Bridget Maddox |  | 77800 | 56210.5 | 45584.74 | 51064.93 | 45374 | 5690.93 | 36896.81 | 14168.12 | 72.3% | 72.25% | 40903.19 | 52.57% | 36896.81 | 3137.38 | 45584.74
26-PC-35401 | Raven Rock Phase II Testing | In Progress | Time and material | High Desert | Bridget Maddox |  | 312900 | 35485.5 | 8384.38 | 205376.26 | 152268.46 | 53107.8 | 21093.83 | 184282.43 | 11.3% | 10.27% | 291806.17 | 93.26% | 21093.83 | 15253.95 | 8384.38
26-PC-35449 | Saltgrass Cultural Resources Monitoring | In Progress | Time and material | High Desert | Bridget Maddox |  | 145800 | 31446 | 7978.96 | 103226.4 | 103226.4 | 0 | 22115.43 | 81110.97 | 21.6% | 21.42% | 123684.57 | 84.83% | 22115.43 | 9642.45 | 7978.96
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 09/04/2026 | 68900 | 59529.6 | 49947.75 | 53679.99 | 53679.99 | 0 | 46380.29 | 7299.7 | 86.4% | 86.4% | 22519.71 | 32.68% | 46380.29 | 4099.34 | 49947.75
26-PC-35583 | On-Call: Eagle Bend Highway Widening Phase II Testing | In Progress | Time and material | High Desert | Jody Wang |  | 39700 | 2479.5 | 721.99 | 28536.36 | 28536.36 | 0 | 1470.29 | 27066.07 | 6.2% | 5.15% | 38229.71 | 96.3% | 1470.29 | 1470.29 | 721.99
26-PC-35588 | Fern Valley Wind Farm - Class III Survey | Completed | Fixed fee | High Desert | Eileen Poole |  | 148800 | 148800 | 148800 | 130289.28 | 130289.28 | 0 | 169376.06 | -39086.78 | 100% | 130% | -20576.06 | -13.83% | 0 | 0 | 0
26-PC-35596 | Millbrook Solar GIS Mapping | Lab/Curation | Fixed fee | High Desert | Eileen Poole |  | 197200 | 42141.64 | 27554.12 | 149142.36 | 149142.36 | 0 | 31870.85 | 117271.51 | 21.4% | 21.37% | 165329.15 | 83.84% | 31870.85 | 6669.87 | 27554.12
26-PC-35598 | Task Order 3: Raven Rock Rail Siding Built Environment Survey | Final Billing/Invoice | Time and material | High Desert | Eileen Poole |  | 22100 | 0 | 0 | 15626.91 | 15626.91 | 0 | 20314.98 | -4688.07 | 0% | 130% | 1785.02 | 8.08% | 0 | 0 | 0
26-PC-35635 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | High Desert | Eileen Poole |  | 223600 | 64486.24 | 42964.82 | 138900.32 | 138900.32 | 0 | 40059.7 | 98840.62 | 28.8% | 28.84% | 183540.3 | 82.08% | 40059.7 | 8212.63 | 42964.82
26-PC-35650 | Aspen Ridge Harbor Dredging - Maritime Remote Sensing Survey | In Progress | Time and material | High Desert | Jody Wang |  | 155300 | 0 | 0 | 100626.66 | 93441.15 | 7185.51 | 0 | 100626.66 | 0% | 0% | 155300 | 100% | 0 | 0 | 0
26-PC-35698 | Silver Lake Class III Survey | Completed | Time and material | High Desert | Bridget Maddox |  | 274000 | 0 | 0 | 188320.48 | 149951.76 | 38368.72 | 244816.62 | -56496.14 | 0% | 130% | 29183.38 | 10.65% | 0 | 0 | 0
26-PC-35730 | Larkspur Solar Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole |  | 74800 | 3179 | 1495.98 | 50078.6 | 50078.6 | 0 | 2126.96 | 47951.64 | 4.3% | 4.25% | 72673.04 | 97.16% | 2126.96 | 2126.96 | 1495.98
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | High Desert | Jody Wang |  | 26300 | 26300 | 26300 | 19575.09 | 19575.09 | 0 | 22787.95 | -3212.86 | 100% | 116.4% | 3512.05 | 13.35% | 0 | 0 | 0
26-PC-35789 | Cedar Hollow Environmental Review Support | In Progress | Time and material | High Desert | Eileen Poole |  | 3800 | 159.5 | 27.38 | 2575.26 | 2575.26 | 0 | 95.95 | 2479.31 | 4.2% | 3.73% | 3704.05 | 97.48% | 95.95 | 95.95 | 27.38
26-PC-35803 | Tamarack Airport Apron GIS Mapping | In Progress | Time and material | High Desert | Jody Wang |  | 82900 | 217.5 | 87.2 | 52144.1 | 52144.1 | 0 | 123.8 | 52020.3 | 0.3% | 0.24% | 82776.2 | 99.85% | 123.8 | 123.8 | 87.2
26-PC-35811 | Phase III: Wildrye Solar Architectural History Survey | In Progress | Time and material | High Desert | Eileen Poole |  | 19500 | 0 | 0 | 12897.3 | 12897.3 | 0 | 0 | 12897.3 | 0% | 0% | 19500 | 100% | 0 | 0 | 0
26-PC-35828 | Aspen Ridge Park Improvements - Class III Survey | In Progress | Time and material | High Desert | Jody Wang |  | 48300 | 27612.25 | 23270.14 | 31733.1 | 31733.1 | 0 | 19018.68 | 12714.42 | 57.2% | 59.93% | 29281.32 | 60.62% | 19018.68 | 1930.54 | 23270.14
26-PC-35920 | Phase I: Creosote Draw Park Improvements Historic Resources Evaluation | In Progress | Time and material | High Desert | Eileen Poole |  | 61600 | 0 | 0 | 42591.82 | 34150 | 8441.82 | 0 | 42591.82 | 0% | 0% | 61600 | 100% | 0 | 0 | 0
26-PC-35937 | Pebble Beach Road Built Environment Survey | Transferred Entity | Fixed fee | High Desert | Kathy Hurley |  | 73700 | 7274.19 | 1654.38 | 51155.17 | 51155.17 | 0 | 5050.91 | 46104.26 | 9.9% | 9.87% | 68649.09 | 93.15% | 5050.91 | 2386.93 | 1654.38
26-PC-35984 | Timber Gap Bridge Replacement Archaeological Testing | Final Reporting/Review | Time and material | High Desert | Bridget Maddox |  | 75200 | 13619.25 | 7059.33 | 47215.34 | 40029.6 | 7185.74 | 10159.66 | 37055.68 | 18.1% | 21.52% | 65040.34 | 86.49% | 10159.66 | 3062.42 | 7059.33
26-PC-36056 | Rushgrass Draw Historic Resources Evaluation | Completed | Fixed fee | High Desert | Bridget Maddox |  | 559500 | 559500 | 559500 | 461307.75 | 461307.75 | 0 | 474417.43 | -13109.68 | 100% | 102.8% | 85082.57 | 15.21% | 0 | 0 | 0
26-PC-36110 | Blue Heron Canal Lining - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox |  | 776100 | 55413.54 | 49922.17 | 567018.66 | 567018.66 | 0 | 40481.07 | 526537.59 | 7.1% | 7.14% | 735618.93 | 94.78% | 40481.07 | 3330.99 | 49922.17
26-PC-36112 | Task Order 31: Twin Buttes Housing Development Built Environment Survey | Final Billing/Invoice | Fixed fee | High Desert | Kathy Hurley |  | 39800 | 39800 | 39800 | 29581.08 | 24488.82 | 5092.26 | 38455.4 | -8874.32 | 100% | 130% | 1344.6 | 3.38% | 0 | 0 | 0
26-PC-36208 | Foxglove Fiber Route GIS Mapping | Final Billing/Invoice | Time and material | High Desert | Jody Wang |  | 36600 | 0 | 0 | 24946.56 | 24946.56 | 0 | 26109.81 | -1163.25 | 0% | 104.7% | 10490.19 | 28.66% | 0 | 0 | 0
26-PC-36247 | Harbor View Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Maurice Dodson |  | 44300 | 522.74 | 202 | 33455.36 | 33455.36 | 0 | 394.65 | 33060.71 | 1.2% | 1.18% | 43905.35 | 99.11% | 394.65 | 197.32 | 202
26-PC-36281 | Saltgrass Mixed-Use Development Architectural History Survey | In Progress | Time and material | Island | Becky Velazquez |  | 25900 | 202.5 | 109.61 | 16954.14 | 16954.14 | 0 | 138.86 | 16815.28 | 0.8% | 0.82% | 25761.14 | 99.46% | 138.86 | 138.86 | 109.61
26-PC-36361 | Dove Canyon Maritime Remote Sensing Survey | Final Billing/Invoice | Fixed fee | Island | Maurice Dodson |  | 343400 | 343400 | 343400 | 282103.1 | 282103.1 | 0 | 295342.63 | -13239.53 | 100% | 104.7% | 48057.37 | 13.99% | 0 | 0 | 0
26-PC-36394 | Meadowlark Cultural Resources Monitoring | In Progress | Fixed fee | Island | Briana Melton |  | 61900 | 3237.37 | 1344.78 | 39879.42 | 32483.92 | 7395.5 | 2084.51 | 37794.91 | 5.2% | 5.23% | 59815.49 | 96.63% | 2084.51 | 1280.35 | 1344.78
26-PC-36396 | Task Order 9: Twin Buttes Solar Architectural History Survey | In Progress | Fixed fee | Island | Briana Melton |  | 77700 | 9759.12 | 7129.67 | 47283.31 | 43484.4 | 3798.91 | 5937.18 | 41346.13 | 12.6% | 12.56% | 71762.82 | 92.36% | 5937.18 | 1316.11 | 7129.67
26-PC-36416 | Task Order 2: Thistle Down Wind Farm Archaeological Testing | Lab/Curation | Fixed fee | Island | Maurice Dodson |  | 589600 | 270626.4 | 239675.91 | 462173.13 | 351925 | 110248.13 | 212155.53 | 250017.6 | 45.9% | 45.9% | 377444.47 | 64.02% | 212155.53 | 25254.53 | 239675.91
26-PC-36477 | Elk Meadow Pipeline - Environmental Review Support | Final Billing/Invoice | Fixed fee | Island | Briana Melton |  | 70100 | 70100 | 70100 | 51383.3 | 51383.3 | 0 | 66798.29 | -15414.99 | 100% | 130% | 3301.71 | 4.71% | 0 | 0 | 0
26-PC-36537 | Yarrow Point Park Improvements Built Environment Survey | In Progress | Fixed fee | Island | Becky Velazquez |  | 125300 | 39544.68 | 36421.55 | 86482.06 | 86482.06 | 0 | 27291.85 | 59190.21 | 31.6% | 31.56% | 98008.15 | 78.22% | 27291.85 | 2161.89 | 36421.55
26-PC-36548 | Phase II: Granite Pass Levee Repair Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Island | Becky Velazquez |  | 59700 | 59700 | 59700 | 35999.1 | 35999.1 | 0 | 41117.1 | -5118 | 100% | 114.2% | 18582.9 | 31.13% | 0 | 0 | 0
26-PC-36555 | Coyote Springs Pipeline Class III Survey | On Hold | Time and material | Island | Joan Mathis |  | 206100 | 0 | 0 | 139514.38 | 110535.32 | 28979.06 | 0 | 139514.38 | 0% | 0% | 206100 | 100% | 0 | 0 | 0
26-PC-36581 | Harbor View Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Briana Melton |  | 127600 | 48755.96 | 43545.62 | 76674.84 | 76674.84 | 0 | 29299.63 | 47375.21 | 38.2% | 38.21% | 98300.37 | 77.04% | 29299.63 | 4223.89 | 43545.62
26-PC-36595 | Blue Heron School Campus - Cultural Resources Monitoring | Completed | Time and material | Lakeshore | Lucas Benson |  | 35700 | 0 | 0 | 26328.75 | 26328.75 | 0 | 31762.49 | -5433.74 | 0% | 120.6% | 3937.51 | 11.03% | 0 | 0 | 0
26-PC-36602 | Sea Oat Airport Apron Cultural Resources Monitoring | In Progress | Fixed fee | Lakeshore | Terrence Gillespie |  | 396600 | 57269.04 | 42958.07 | 288646.28 | 223565.16 | 65081.12 | 41680.56 | 246965.72 | 14.4% | 14.44% | 354919.44 | 89.49% | 41680.56 | 5148.88 | 42958.07
26-PC-36616 | Lone Pine Harbor Dredging - Section 106 Consultation | Final Billing/Invoice | Fixed fee | Lakeshore | Terrence Gillespie |  | 79100 | 79100 | 79100 | 51885.54 | 39912.41 | 11973.13 | 38340.61 | 13544.93 | 100% | 73.89% | 40759.39 | 51.53% | 0 | 0 | 20653.01
26-PC-36726 | Willow Springs Cultural Resources Assessment | In Progress | Fixed fee | Lakeshore | Lucas Benson |  | 153200 | 16668.16 | 0 | 110288.68 | 110288.68 | 0 | 12003.91 | 98284.77 | 10.9% | 10.88% | 141196.09 | 92.16% | 12003.91 | 8587.6 | 0
26-PC-36749 | Windmill Flat Water Main - Cultural Resources Assessment | In Progress | Fixed fee | Lakeshore | Lucas Benson |  | 199000 | 95321 | 85531.32 | 173567.8 | 173567.8 | 0 | 83133.93 | 90433.87 | 47.9% | 47.9% | 115866.07 | 58.22% | 83133.93 | 6429.44 | 85531.32
26-PC-36750 | Task Order 15: North Fork Canal Lining Data Recovery | In Progress | Time and material | Lakeshore | Terrence Gillespie |  | 121800 | 24027.5 | 11545.83 | 80948.28 | 80948.28 | 0 | 13368.46 | 67579.82 | 19.7% | 16.51% | 108431.54 | 89.02% | 13368.46 | 3011.15 | 11545.83
26-PC-36775 | Falcon Mesa Cultural Resources Monitoring | Transferred Entity | Fixed fee | Hill Country | Gail Meza |  | 90800 | 190.68 | 37.35 | 77565.54 | 58243.86 | 19321.68 | 160.5 | 77405.04 | 0.2% | 0.21% | 90639.5 | 99.82% | 160.5 | 160.5 | 37.35
26-PC-36802 | Thistle Down Canal Lining - Cultural Resources Assessment | Final Reporting/Review | Time and material | Hill Country | Gail Meza |  | 71600 | 0 | 0 | 52303.8 | 52303.8 | 0 | 0 | 52303.8 | 0% | 0% | 71600 | 100% | 0 | 0 | 0
26-PC-36828 | Phase III: Rushgrass Draw Canal Lining GIS Mapping | In Progress | Time and material | Hill Country | Gail Meza |  | 28100 | 1368.5 | 1198.92 | 19006.84 | 19006.84 | 0 | 844.43 | 18162.41 | 4.9% | 4.44% | 27255.57 | 96.99% | 844.43 | 0 | 1198.92
26-PC-36861 | North Fork Park Improvements - Cultural Resources Assessment | In Progress | Fixed fee | Hill Country | Samuel Wilkerson |  | 463900 | 11411.94 | 8632.46 | 337255.3 | 337255.3 | 0 | 8285.6 | 328969.7 | 2.5% | 2.46% | 455614.4 | 98.21% | 8285.6 | 2148.12 | 8632.46
26-PC-36944 | Copper Flats Levee Repair - Data Recovery | Final Reporting/Review | Fixed fee | Hill Country | Marcus Shea |  | 102000 | 18278.4 | 15058.85 | 68921.4 | 68921.4 | 0 | 12352.09 | 56569.31 | 17.9% | 17.92% | 89647.91 | 87.89% | 12352.09 | 1658.58 | 15058.85
26-PC-36945 | Hawk Point Fiber Route - Maritime Remote Sensing Survey | In Progress | Fixed fee | Hill Country | Gail Meza |  | 496500 | 211211.1 | 185861.75 | 329824.95 | 329824.95 | 0 | 140294.42 | 189530.53 | 42.5% | 42.54% | 356205.58 | 71.74% | 140294.42 | 11823.3 | 185861.75
26-PC-36949 | On-Call: Sandpiper Transmission Line Cultural Resources Monitoring | Completed | Time and material | Hill Country | Glen Delacruz |  | 100300 | 0 | 0 | 70075.49 | 54904 | 15171.49 | 80869.16 | -10793.67 | 0% | 115.4% | 19430.84 | 19.37% | 0 | 0 | 0
26-PC-37015 | Phase III: Hawk Point Substation Phase II Testing | On Hold | Fixed fee | Hill Country | Suzanne Mcmillan |  | 40400 | 0 | 0 | 28833.48 | 28833.48 | 0 | 0 | 28833.48 | 0% | 0% | 40400 | 100% | 0 | 0 | 0
26-PC-37016 | Aspen Ridge Built Environment Survey | Final Billing/Invoice | Time and material | Hill Country | Suzanne Mcmillan |  | 26000 | 0 | 0 | 19416.8 | 19416.8 | 0 | 13591.76 | 5825.04 | 0% | 70% | 12408.24 | 47.72% | 0 | 0 | 0
26-PC-37024 | Hackberry Bend Mine Expansion - Maritime Remote Sensing Survey | In Progress | Fixed fee | Hill Country | Danielle Villanueva |  | 78900 | 12979.05 | 10889.26 | 63394.72 | 59087.34 | 4307.38 | 10425.9 | 52968.82 | 16.5% | 16.45% | 68474.1 | 86.79% | 10425.9 | 117.12 | 10889.26
26-PC-37032 | Raven Rock Section 106 Consultation | Final Billing/Invoice | Fixed fee | Hill Country | Gail Meza |  | 155000 | 155000 | 155000 | 112060.12 | 88719.36 | 23340.76 | 145678.16 | -33618.04 | 100% | 130% | 9321.84 | 6.01% | 0 | 0 | 0
26-PC-37051 | On-Call: Sandpiper Rail Siding Section 106 Consultation | Lab/Curation | Fixed fee | Hill Country | Theresa Fernandez |  | 365900 | 10903.82 | 7006.96 | 243543.04 | 243543.04 | 0 | 7245.79 | 236297.25 | 3% | 2.98% | 358654.21 | 98.02% | 7245.79 | 3742.33 | 7006.96
26-PC-37068 | Copper Flats Highway Widening - Data Recovery | On Hold | Time and material | Hill Country | Marcus Shea |  | 419100 | 0 | 0 | 298944.03 | 298944.03 | 0 | 0 | 298944.03 | 0% | 0% | 419100 | 100% | 0 | 0 | 0
26-PC-37073 | Kestrel Butte Pipeline Curation | In Progress | Fixed fee | Hill Country | Marcus Shea |  | 441700 | 11219.18 | 512.97 | 346822.84 | 346822.84 | 0 | 8825.19 | 337997.65 | 2.5% | 2.54% | 432874.81 | 98% | 8825.19 | 8825.19 | 512.97
26-PC-37089 | Rushgrass Draw GIS Mapping | In Progress | Time and material | Hill Country | Gail Meza |  | 28900 | 1656.25 | 1656.25 | 19054.14 | 14854.2 | 4199.94 | 1063.17 | 17990.97 | 5.7% | 5.58% | 27836.83 | 96.32% | 1063.17 | 0 | 1656.25
26-PC-37136 | Yarrow Point Housing Development - Section 106 Consultation | In Progress | Fixed fee | Hill Country | Marcus Shea |  | 153700 | 54271.47 | 51231.02 | 109797.26 | 86150.47 | 23646.79 | 38767.55 | 71029.71 | 35.3% | 35.31% | 114932.45 | 74.78% | 38767.55 | 984.53 | 51231.02
26-PC-37137 | Sea Oat Archaeological Testing | Final Billing/Invoice | Fixed fee | Hill Country | Gail Meza |  | 105600 | 105600 | 105600 | 78492.48 | 78492.48 | 0 | 64062.46 | 14430.02 | 100% | 81.62% | 41537.54 | 39.33% | 0 | 0 | 19409.28
26-PC-37138 | Granite Pass Canal Lining - Environmental Review Support | Final Reporting/Review | Time and material | Hill Country | Gail Meza |  | 315800 | 49327.5 | 44944.82 | 223705.16 | 164829.33 | 58875.83 | 33971.44 | 189733.72 | 15.6% | 15.19% | 281828.56 | 89.24% | 33971.44 | 3325.4 | 44944.82
26-PC-37139 | Goldfinch Reservoir Environmental Review Support | In Progress | Time and material | Hill Country | Theresa Fernandez |  | 1070500 | 113864.25 | 91019.47 | 734587.52 | 579542.04 | 155045.48 | 66797.88 | 667789.64 | 10.6% | 9.09% | 1003702.12 | 93.76% | 66797.88 | 13500.24 | 91019.47
26-PC-37160 | Twin Buttes Environmental Review Support | Completed | Time and material | Hill Country | Samuel Wilkerson |  | 733800 | 0 | 0 | 451360.38 | 451360.38 | 0 | 496365.43 | -45005.05 | 0% | 110% | 237434.57 | 32.36% | 0 | 0 | 0
26-PC-37166 | Stone Mill Airport Apron - Section 106 Consultation | Completed | Time and material | Hill Country | Marcus Shea |  | 252900 | 0 | 0 | 181708.65 | 181708.65 | 0 | 201511.59 | -19802.94 | 0% | 110.9% | 51388.41 | 20.32% | 0 | 0 | 0
26-PC-37196 | Sea Oat Built Environment Survey | In Progress | Fixed fee | Hill Country | Suzanne Mcmillan |  | 26900 | 0 | 0 | 22881.14 | 22881.14 | 0 | 0 | 22881.14 | 0% | 0% | 26900 | 100% | 0 | 0 | 0
26-PC-37204 | On-Call: Saltgrass Housing Development Built Environment Survey | In Progress | Time and material | Hill Country | Gail Meza |  | 201900 | 73828.25 | 69269.36 | 145630.47 | 145630.47 | 0 | 45387.98 | 100242.49 | 36.6% | 31.17% | 156512.02 | 77.52% | 45387.98 | 0 | 69269.36
26-PC-37224 | On-Call: Ember Valley Trail Class III Survey | Final Billing/Invoice | Time and material | Hill Country | Glen Delacruz |  | 168700 | 0 | 0 | 129802.56 | 117616.11 | 12186.45 | 117866.55 | 11936.01 | 0% | 90.8% | 50833.45 | 30.13% | 0 | 0 | 0
26-PC-37271 | Maple Fork Wind Farm Built Environment Survey | In Progress | Time and material | Hill Country | Gail Meza |  | 879900 | 258254.5 | 204281.16 | 587259.92 | 482467.22 | 104792.7 | 171065.39 | 416194.53 | 29.4% | 29.13% | 708834.61 | 80.56% | 171065.39 | 27099.92 | 204281.16
26-PC-37282 | Windmill Flat Harbor Dredging GIS Mapping | In Progress | Fixed fee | Hill Country | Suzanne Mcmillan |  | 48800 | 761.28 | 644.79 | 41616.64 | 41616.64 | 0 | 649.35 | 40967.29 | 1.6% | 1.56% | 48150.65 | 98.67% | 649.35 | 160.11 | 644.79
26-PC-37311 | North Fork School Campus - Paleontological Monitoring | On Hold | Time and material | Hill Country | Marcus Shea |  | 49100 | 0 | 0 | 34527.12 | 34527.12 | 0 | 0 | 34527.12 | 0% | 0% | 49100 | 100% | 0 | 0 | 0
26-PC-37317 | Hackberry Bend Environmental Review Support | In Progress | Time and material | Hill Country | Danielle Villanueva |  | 348700 | 11592.75 | 10796.07 | 224737.15 | 224737.15 | 0 | 7817.14 | 216920.01 | 3.3% | 3.48% | 340882.86 | 97.76% | 7817.14 | 379.34 | 10796.07
26-PC-37322 | Maple Fork Canal Lining Built Environment Survey | In Progress | Time and material | Hill Country | Danielle Villanueva |  | 30900 | 5098.25 | 1737.78 | 21095.43 | 21095.43 | 0 | 2933.98 | 18161.45 | 16.5% | 13.91% | 27966.02 | 90.5% | 2933.98 | 2300.89 | 1737.78
26-PC-37329 | Stone Mill Battery Storage Built Environment Survey | Final Reporting/Review | Fixed fee | Hill Country | Glen Delacruz |  | 32600 | 20707.52 | 14930.69 | 25463.86 | 25463.86 | 0 | 16175.73 | 9288.13 | 63.5% | 63.52% | 16424.27 | 50.38% | 16175.73 | 6002.1 | 14930.69
26-PC-37367 | Millbrook Trail - Cultural Resources Assessment | Completed | Time and material | Hill Country | Theresa Fernandez |  | 196400 | 0 | 0 | 130802.4 | 130802.4 | 0 | 117597.88 | 13204.52 | 0% | 89.9% | 78802.12 | 40.12% | 0 | 0 | 0
26-PC-37368 | Cedar Hollow Mine Expansion - Section 106 Consultation | In Progress | Fixed fee | Piedmont | Maria Parrish |  | 201100 | 9069.61 | 2512.18 | 123555.84 | 123555.84 | 0 | 5568.91 | 117986.93 | 4.5% | 4.51% | 195531.09 | 97.23% | 5568.91 | 5568.91 | 2512.18
26-PC-37428 | Ember Valley Section 106 Consultation | In Progress | Fixed fee | Piedmont | Megan Pineda |  | 57900 | 16895.22 | 2174.77 | 44206.65 | 44206.65 | 0 | 12898.79 | 31307.86 | 29.2% | 29.18% | 45001.21 | 77.72% | 12898.79 | 7719.73 | 2174.77
26-PC-37441 | Juniper Wash Transmission Line Built Environment Survey | Final Billing/Invoice | Time and material | Piedmont | Megan Pineda |  | 91500 | 0 | 0 | 66758.4 | 66758.4 | 0 | 47155.66 | 19602.74 | 0% | 70.64% | 44344.34 | 48.46% | 0 | 0 | 0
26-PC-37477 | Dove Canyon Data Recovery | On Hold | Fixed fee | Piedmont | Annette Vaughan |  | 41100 | 0 | 0 | 28424.76 | 28424.76 | 0 | 0 | 28424.76 | 0% | 0% | 41100 | 100% | 0 | 0 | 0
26-PC-37511 | Badger Hollow Paleontological Monitoring | Final Billing/Invoice | Time and material | Piedmont | Jody Chung |  | 202900 | 0 | 0 | 142943.05 | 142943.05 | 0 | 174521.6 | -31578.55 | 0% | 122.1% | 28378.4 | 13.99% | 0 | 0 | 0
26-PC-37513 | Harbor View Housing Development Paleontological Monitoring | Final Reporting/Review | Fixed fee | Piedmont | Jody Chung |  | 34700 | 0 | 0 | 23634.17 | 23634.17 | 0 | 0 | 23634.17 | 0% | 0% | 34700 | 100% | 0 | 0 | 0
26-PC-37520 | Elk Meadow Wastewater Plant Maritime Remote Sensing Survey | Completed | Fixed fee | Piedmont | Jody Chung |  | 59200 | 59200 | 59200 | 43476.48 | 43476.48 | 0 | 51249.96 | -7773.48 | 100% | 117.9% | 7950.04 | 13.43% | 0 | 0 | 0
26-PC-37543 | Pebble Beach Road Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Maria Parrish |  | 330200 | 149382.48 | 133334.89 | 218394.28 | 218394.28 | 0 | 98791.1 | 119603.18 | 45.2% | 45.24% | 231408.9 | 70.08% | 98791.1 | 6807.79 | 133334.89
26-PC-37559 | Badger Hollow Paleontological Monitoring | In Progress | Time and material | Piedmont | Jody Chung |  | 44300 | 44300 | 33494.39 | 28024.18 | 28024.18 | 0 | 45539.17 | -17514.99 | 100% | 162.5% | -1239.17 | -2.8% | 45539.17 | 5430.02 | 33494.39
26-PC-37671 | Harbor View Mixed-Use Development Architectural History Survey | In Progress | Time and material | Piedmont | Annette Vaughan |  | 145900 | 9234.5 | 9234.5 | 92486.01 | 92486.01 | 0 | 6017.12 | 86468.89 | 6.3% | 6.51% | 139882.88 | 95.88% | 6017.12 | 0 | 9234.5
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Piedmont | Jody Chung | 07/31/2026 | 40300 | 31772.52 | 24174.36 | 32312.54 | 32312.54 | 0 | 25475.14 | 6837.4 | 78.8% | 78.84% | 14824.86 | 36.79% | 25475.14 | 2312.57 | 24174.36
26-PC-37709 | Sage Flat Phase I Survey | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 09/11/2026 | 31500 | 31500 | 16533.22 | 21725.55 | 21725.55 | 0 | 30289.1 | -8563.55 | 100% | 139.4% | 1210.9 | 3.84% | 30289.1 | 5614.65 | 16533.22
26-PC-37788 | Sumac Ridge Cultural Resources Assessment | In Progress | Fixed fee | Piedmont | Jody Chung |  | 1112800 | 22812.4 | 20528.14 | 826476.56 | 826476.56 | 0 | 16908.48 | 809568.08 | 2.1% | 2.05% | 1095891.52 | 98.48% | 16908.48 | 1700.45 | 20528.14
26-PC-37801 | Slate Ridge Section 106 Consultation | Completed | Time and material | Piedmont | Megan Pineda |  | 72500 | 0 | 0 | 48408.25 | 48408.25 | 0 | 54438.34 | -6030.09 | 0% | 112.5% | 18061.66 | 24.91% | 0 | 0 | 0
26-PC-37860 | Slate Ridge Phase II Testing | Final Billing/Invoice | Fixed fee | Piedmont | Annette Vaughan |  | 27600 | 27600 | 27600 | 19836.12 | 19836.12 | 0 | 22675.01 | -2838.89 | 100% | 114.3% | 4924.99 | 17.84% | 0 | 0 | 0
26-PC-37924 | Raven Rock Architectural History Survey | Completed | Time and material | Piedmont | Jody Chung |  | 33600 | 0 | 0 | 23886.24 | 23886.24 | 0 | 31052.11 | -7165.87 | 0% | 130% | 2547.89 | 7.58% | 0 | 0 | 0
26-PC-37965 | Redbud Cultural Resources Assessment | In Progress | Time and material | Piedmont | Annette Vaughan |  | 55400 | 50946.25 | 31520.73 | 34625 | 34625 | 0 | 31687.21 | 2937.79 | 92% | 91.52% | 23712.79 | 42.8% | 31687.21 | 9045.32 | 31520.73
26-PC-38019 | Phase II: Timber Gap Airport Apron Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | Prairie | Sherry Lloyd |  | 13700 | 13700 | 13700 | 9151.6 | 9151.6 | 0 | 10657.91 | -1506.31 | 100% | 116.5% | 3042.09 | 22.21% | 0 | 0 | 0
26-PC-38025 | Granite Pass Section 106 Consultation | In Progress | Time and material | Prairie | Sherry Lloyd |  | 92200 | 12549.75 | 10628.35 | 64982.56 | 64982.56 | 0 | 8252.26 | 56730.3 | 13.6% | 12.7% | 83947.74 | 91.05% | 8252.26 | 483.45 | 10628.35
26-PC-38124 | Lantern Bay Architectural History Survey | Final Billing/Invoice | Fixed fee | Prairie | Sherry Lloyd |  | 48700 | 48700 | 48700 | 38380.47 | 38380.47 | 0 | 44857.7 | -6477.23 | 100% | 116.9% | 3842.3 | 7.89% | 0 | 0 | 0
26-PC-38153 | Harbor View Reservoir Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 109100 | 61521.49 | 54072.6 | 89766.43 | 69277.74 | 20488.69 | 50619.25 | 39147.18 | 56.4% | 56.39% | 58480.75 | 53.6% | 50619.25 | 5009.93 | 54072.6
26-PC-38215 | Phase I: Juniper Wash Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 42800 | 14868.72 | 8160.18 | 37664 | 37664 | 0 | 13083.31 | 24580.69 | 34.7% | 34.74% | 29716.69 | 69.43% | 13083.31 | 2566.8 | 8160.18
26-PC-38264 | On-Call: Coyote Springs Battery Storage Phase II Testing | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd |  | 25500 | 11801.4 | 4418.43 | 17926.43 | 15639.32 | 2287.11 | 8296.03 | 9630.4 | 46.3% | 46.28% | 17203.97 | 67.47% | 8296.03 | 2277.52 | 4418.43
26-PC-38304 | Yarrow Point Cultural Resources Assessment | In Progress | Time and material | Prairie | Sherry Lloyd |  | 177100 | 0 | 0 | 125191.99 | 125191.99 | 0 | 0 | 125191.99 | 0% | 0% | 177100 | 100% | 0 | 0 | 0
26-PC-38315 | Task Order 21: Larkspur Bridge Replacement Paleontological Monitoring | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd |  | 735000 | 41601 | 41601 | 578298 | 578298 | 0 | 32709.7 | 545588.3 | 5.7% | 5.66% | 702290.3 | 95.55% | 32709.7 | 0 | 41601
26-PC-38367 | Stone Mill Architectural History Survey | In Progress | Time and material | Prairie | Sherry Lloyd |  | 416500 | 110801 | 73148.86 | 276097.85 | 276097.85 | 0 | 80601.22 | 195496.63 | 26.6% | 29.19% | 335898.78 | 80.65% | 80601.22 | 24831.63 | 73148.86
26-PC-38379 | Sandpiper Levee Repair Historic Resources Evaluation | On Hold | Time and material | Prairie | Sherry Lloyd |  | 230500 | 0 | 0 | 167898.45 | 138229.08 | 29669.37 | 0 | 167898.45 | 0% | 0% | 230500 | 100% | 0 | 0 | 0
26-PC-38387 | Granite Pass Section 106 Consultation | In Progress | Time and material | Prairie | Sherry Lloyd |  | 182500 | 92777.25 | 89223.77 | 120358.75 | 120358.75 | 0 | 52528.86 | 67829.89 | 50.8% | 43.64% | 129971.14 | 71.22% | 52528.86 | 0 | 89223.77
26-PC-38390 | Redbud Curation | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd |  | 85100 | 2101.97 | 436.07 | 53630.02 | 53630.02 | 0 | 1324.1 | 52305.92 | 2.5% | 2.47% | 83775.9 | 98.44% | 1324.1 | 1324.1 | 436.07
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | In Progress | Time and material | Prairie | Sherry Lloyd |  | 48300 | 38345.25 | 38154.33 | 32887.47 | 32887.47 | 0 | 24978.26 | 7909.21 | 79.4% | 75.95% | 23321.74 | 48.29% | 24978.26 | 0 | 38154.33
26-PC-38431 | Silver Lake Levee Repair - Archaeological Testing | Final Billing/Invoice | Fixed fee | Prairie | Sherry Lloyd |  | 254800 | 254800 | 254800 | 143528.84 | 143528.84 | 0 | 186587.49 | -43058.65 | 100% | 130% | 68212.51 | 26.77% | 0 | 0 | 0
26-PC-38438 | Slate Ridge Fiber Route Phase I Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd |  | 41000 | 0 | 0 | 32762.53 | 25331.09 | 7431.44 | 0 | 32762.53 | 0% | 0% | 41000 | 100% | 0 | 0 | 0
26-PC-38459 | Task Order 21: Sea Oat Highway Widening Cultural Resources Assessment | Completed | Fixed fee | Red Rock | Javier Newman |  | 96700 | 96700 | 96700 | 76702.44 | 76702.44 | 0 | 59483.59 | 17218.85 | 100% | 77.55% | 37216.41 | 38.49% | 0 | 0 | 21709.15
26-PC-38532 | Tansy Flat Wind Farm - Paleontological Monitoring | On Hold | Fixed fee | Red Rock | Marisa Odom |  | 46400 | 0 | 0 | 33663.2 | 33663.2 | 0 | 0 | 33663.2 | 0% | 0% | 46400 | 100% | 0 | 0 | 0
26-PC-38546 | Sparrow Hill Reservoir Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | Red Rock | Jeanette Chung |  | 103300 | 103300 | 103300 | 55430.78 | 55430.78 | 0 | 59395.16 | -3964.38 | 100% | 107.1% | 43904.84 | 42.5% | 0 | 0 | 0
26-PC-38550 | On-Call: Sage Flat School Campus Class III Survey | Completed | Fixed fee | Red Rock | Jeanette Chung |  | 385200 | 385200 | 385200 | 289636.74 | 249209.9 | 40426.84 | 262282.42 | 27354.32 | 100% | 90.56% | 122917.58 | 31.91% | 0 | 0 | 36362.88
26-PC-38571 | Stone Mill Transmission Line GIS Mapping | Completed | Fixed fee | Red Rock | Jeanette Chung |  | 593600 | 593600 | 593600 | 431665.92 | 431665.92 | 0 | 350808.39 | 80857.53 | 100% | 81.27% | 242791.61 | 40.9% | 0 | 0 | 111181.28
26-PC-38573 | Cedar Hollow School Campus - Class III Survey | In Progress | Fixed fee | Red Rock | Marisa Odom |  | 100100 | 1111.11 | 405.7 | 74784.71 | 74784.71 | 0 | 833.24 | 73951.47 | 1.1% | 1.11% | 99266.76 | 99.17% | 833.24 | 833.24 | 405.7
26-PC-38624 | Juniper Wash Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Red Rock | Bruce Suarez | 07/31/2026 | 77900 | 77900 | 77900 | 56578.77 | 56578.77 | 0 | 73552.4 | -16973.63 | 100% | 130% | 4347.6 | 5.58% | 0 | 0 | 0
26-PC-38647 | Meadowlark Cultural Resources Assessment | In Progress | Time and material | Red Rock | Bruce Suarez |  | 793800 | 281862.75 | 232307.63 | 517795.74 | 517795.74 | 0 | 177498.27 | 340297.47 | 35.5% | 34.28% | 616301.73 | 77.64% | 177498.27 | 23370.8 | 232307.63
26-PC-38675 | On-Call: Lone Pine School Campus Data Recovery | Final Reporting/Review | Fixed fee | Red Rock | Jeanette Chung |  | 289700 | 84476.52 | 82918.83 | 228167.72 | 228167.72 | 0 | 66526.14 | 161641.58 | 29.2% | 29.16% | 223173.86 | 77.04% | 66526.14 | 0 | 82918.83
26-PC-38691 | Elk Meadow Phase I Survey | On Hold | Time and material | Red Rock | Tina Aguirre |  | 1927200 | 0 | 0 | 1370431.92 | 1370431.92 | 0 | 0 | 1370431.92 | 0% | 0% | 1927200 | 100% | 0 | 0 | 0
26-PC-38709 | Timber Gap Airport Apron Phase I Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 14100 | 6839.91 | 6778.98 | 11415.36 | 11415.36 | 0 | 5537.78 | 5877.58 | 48.5% | 48.51% | 8562.22 | 60.72% | 5537.78 | 43.97 | 6778.98
26-PC-38719 | Willow Springs Housing Development - Environmental Review Support | In Progress | Fixed fee | Red Rock | Javier Newman |  | 298600 | 1552.72 | 1508.75 | 193522.66 | 193522.66 | 0 | 1014.83 | 192507.83 | 0.5% | 0.52% | 297585.17 | 99.66% | 1014.83 | 0 | 1508.75
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre |  | 97700 | 97700 | 80334.37 | 60828.02 | 60828.02 | 0 | 76641.91 | -15813.89 | 100% | 126% | 21058.09 | 21.55% | 76641.91 | 11017.8 | 80334.37
26-PC-38769 | On-Call: Elk Meadow Wastewater Plant Paleontological Monitoring | Final Billing/Invoice | Time and material | Red Rock | Marisa Odom |  | 40500 | 0 | 0 | 25733.7 | 25733.7 | 0 | 21634.41 | 4099.29 | 0% | 84.07% | 18865.59 | 46.58% | 0 | 0 | 0
26-PC-38844 | Juniper Wash Cell Tower Phase II Testing | Final Billing/Invoice | Fixed fee | Red Rock | Jeanette Chung |  | 319700 | 319700 | 319700 | 236322.24 | 236322.24 | 0 | 307218.91 | -70896.67 | 100% | 130% | 12481.09 | 3.9% | 0 | 0 | 0
26-PC-38856 | Task Order 6: Maple Fork Trail Section 106 Consultation | Completed | Fixed fee | Red Rock | Tina Aguirre |  | 137600 | 137600 | 137600 | 94200.96 | 94200.96 | 0 | 122461.25 | -28260.29 | 100% | 130% | 15138.75 | 11% | 0 | 0 | 0
26-PC-38880 | Wildrye Trail - Archaeological Testing | Completed | Fixed fee | Red Rock | Lydia Cisneros |  | 141200 | 141200 | 141200 | 118636.24 | 118636.24 | 0 | 92164.2 | 26472.04 | 100% | 77.69% | 49035.8 | 34.73% | 0 | 0 | 31501.72
26-PC-38898 | Redbud Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 150100 | 36234.14 | 19826.4 | 87478.28 | 87478.28 | 0 | 21117.75 | 66360.53 | 24.1% | 24.14% | 128982.25 | 85.93% | 21117.75 | 7354.46 | 19826.4
26-PC-38916 | Sparrow Hill Cultural Resources Assessment | Final Billing/Invoice | Fixed fee | Red Rock | Tina Aguirre |  | 54500 | 54500 | 54500 | 42150.3 | 42150.3 | 0 | 54795.39 | -12645.09 | 100% | 130% | -295.39 | -0.54% | 0 | 0 | 0
26-PC-38924 | Wildrye Harbor Dredging - Architectural History Survey | In Progress | Time and material | Red Rock | Shelia Horne |  | 117200 | 64940 | 57207.78 | 83798 | 83798 | 0 | 43360.21 | 40437.79 | 55.4% | 51.74% | 73839.79 | 63% | 43360.21 | 2829.64 | 57207.78
26-PC-38943 | Task Order 34: Fern Valley Wastewater Plant Archaeological Testing | In Progress | Fixed fee | Red Rock | Marisa Odom | 08/28/2026 | 129100 | 110303.04 | 95459.09 | 80272.12 | 59881.52 | 20390.6 | 68583.92 | 11688.2 | 85.4% | 85.44% | 60516.08 | 46.88% | 68583.92 | 10590.67 | 95459.09
26-PC-38966 | Task Order 12: Bramble Creek Battery Storage Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 269400 | 11988.3 | 7999.35 | 193052.04 | 193052.04 | 0 | 8599.9 | 184452.14 | 4.4% | 4.45% | 260800.1 | 96.81% | 8599.9 | 3663.24 | 7999.35
26-PC-38993 | Willow Springs Airport Apron - Section 106 Consultation | In Progress | Time and material | Red Rock | Lydia Cisneros |  | 201400 | 57707.5 | 50428.33 | 131514.2 | 131514.2 | 0 | 37610.38 | 93903.82 | 28.7% | 28.6% | 163789.62 | 81.33% | 37610.38 | 4901.7 | 50428.33
26-PC-39024 | On-Call: Goldfinch Water Main Phase I Survey | In Progress | Time and material | Red Rock | Marisa Odom |  | 211800 | 7879 | 1334.82 | 149416.47 | 113681.55 | 35734.92 | 5901.64 | 143514.83 | 3.7% | 3.95% | 205898.36 | 97.21% | 5901.64 | 5901.64 | 1334.82
26-PC-39043 | Twin Buttes Reservoir - Archaeological Testing | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 123200 | 19736.64 | 14790.45 | 96884.48 | 96884.48 | 0 | 15516.2 | 81368.28 | 16% | 16.02% | 107683.8 | 87.41% | 15516.2 | 3725.13 | 14790.45
26-PC-39051 | Quail Run Fiber Route - Section 106 Consultation | Final Billing/Invoice | Fixed fee | Red Rock | Lydia Cisneros |  | 510900 | 510900 | 510900 | 377963.82 | 377963.82 | 0 | 284190.67 | 93773.15 | 100% | 75.19% | 226709.33 | 44.37% | 0 | 0 | 126754.29
26-PC-39143 | Meadowlark Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez |  | 500400 | 5404.32 | 3639.56 | 366543 | 366543 | 0 | 3965.11 | 362577.89 | 1.1% | 1.08% | 496434.89 | 99.21% | 3965.11 | 610.19 | 3639.56
26-PC-39165 | Pebble Beach Road Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre |  | 94300 | 87472.68 | 76455.85 | 63218.72 | 63218.72 | 0 | 58643.27 | 4575.45 | 92.8% | 92.76% | 35656.73 | 37.81% | 58643.27 | 5448.68 | 76455.85
26-PC-39230 | Maple Fork Cultural Resources Assessment | In Progress | Time and material | Red Rock | Bruce Suarez |  | 575400 | 64571.5 | 42537.62 | 432643.26 | 432643.26 | 0 | 40379.79 | 392263.47 | 11.2% | 9.33% | 535020.21 | 92.98% | 40379.79 | 13676.44 | 42537.62
26-PC-39232 | Plover Cove Canal Lining Archaeological Testing | Final Billing/Invoice | Fixed fee | Red Rock | Tina Aguirre |  | 11000 | 11000 | 11000 | 8129 | 8129 | 0 | 10389.8 | -2260.8 | 100% | 127.8% | 610.2 | 5.55% | 0 | 0 | 0
26-PC-39249 | On-Call: Millbrook Levee Repair Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre |  | 126200 | 0 | 0 | 95785.8 | 95785.8 | 0 | 0 | 95785.8 | 0% | 0% | 126200 | 100% | 0 | 0 | 0
26-PC-39264 | Hackberry Bend Housing Development - Architectural History Survey | Final Billing/Invoice | Fixed fee | Red Rock | Bruce Suarez |  | 37100 | 37100 | 37100 | 30010.19 | 30010.19 | 0 | 29858.41 | 151.78 | 100% | 99.49% | 7241.59 | 19.52% | 0 | 0 | 189.21
26-PC-39277 | Larkspur Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez |  | 520900 | 208.36 | 42.86 | 341710.4 | 341710.4 | 0 | 124.3 | 341586.1 | 0% | 0.04% | 520775.7 | 99.98% | 124.3 | 124.3 | 42.86
26-PC-39303 | Maple Fork Wind Farm Historic Resources Evaluation | Transferred Entity | Fixed fee | Red Rock | Javier Newman |  | 41200 | 9488.36 | 5457.06 | 35687.44 | 35687.44 | 0 | 8218.46 | 27468.98 | 23% | 23.03% | 32981.54 | 80.05% | 8218.46 | 1303.16 | 5457.06
26-PC-39335 | Windmill Flat Phase II Testing | Completed | Time and material | Red Rock | Javier Newman |  | 78700 | 0 | 0 | 52791.96 | 52791.96 | 0 | 47697.57 | 5094.39 | 0% | 90.35% | 31002.43 | 39.39% | 0 | 0 | 0
26-PC-39372 | Tamarack Environmental Review Support | Lab/Curation | Time and material | Red Rock | Shelia Horne |  | 12300 | 25.25 | 6.19 | 7953.18 | 7953.18 | 0 | 14.5 | 7938.68 | 0.2% | 0.18% | 12285.5 | 99.88% | 14.5 | 14.5 | 6.19
26-PC-39390 | Juniper Wash Fiber Route Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Javier Newman |  | 59600 | 8504.92 | 7212.74 | 37810.24 | 37810.24 | 0 | 5396.14 | 32414.1 | 14.3% | 14.27% | 54203.86 | 90.95% | 5396.14 | 569.06 | 7212.74
26-PC-39408 | Meadowlark Class III Survey | Final Billing/Invoice | Fixed fee | Red Rock | Javier Newman |  | 103000 | 103000 | 103000 | 73854.05 | 54323.89 | 19530.16 | 71114.94 | 2739.11 | 100% | 96.29% | 31885.06 | 30.96% | 0 | 0 | 3821.3
26-PC-39446 | On-Call: Tamarack Bridge Replacement Architectural History Survey | Transferred Entity | Fixed fee | Red Rock | Jeanette Chung |  | 131200 | 36696.64 | 14737.81 | 102152.32 | 102152.32 | 0 | 28568.41 | 73583.91 | 28% | 27.97% | 102631.59 | 78.23% | 28568.41 | 7337.42 | 14737.81
26-PC-39534 | Aspen Ridge Park Improvements Maritime Remote Sensing Survey | On Hold | Fixed fee | Red Rock | Marisa Odom |  | 551900 | 0 | 0 | 348248.9 | 348248.9 | 0 | 0 | 348248.9 | 0% | 0% | 551900 | 100% | 0 | 0 | 0
26-PC-39537 | Badger Hollow Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Tina Aguirre |  | 82700 | 6888.91 | 4164.55 | 63951.91 | 63951.91 | 0 | 5327.47 | 58624.44 | 8.3% | 8.33% | 77372.53 | 93.56% | 5327.47 | 1055.38 | 4164.55
26-PC-39565 | On-Call: Aspen Ridge Battery Storage Maritime Remote Sensing Survey | In Progress | Time and material | Red Rock | Lydia Cisneros |  | 97600 | 32668 | 27241.61 | 60541.28 | 60541.28 | 0 | 19109.38 | 41431.9 | 33.5% | 31.56% | 78490.62 | 80.42% | 19109.38 | 3359.44 | 27241.61
26-PC-39587 | Ember Valley Curation | Cost Tracking on Closed Project | Time and material | Red Rock | Javier Newman | 09/11/2026 | 288900 | 0 | 0 | 211965.93 | 211965.93 | 0 | 213449.22 | -1483.29 | 0% | 100.7% | 75450.78 | 26.12% | 0 | 0 | 0
26-PC-39595 | Plover Cove Archaeological Testing | Completed | Fixed fee | Red Rock | Javier Newman |  | 66700 | 66700 | 66700 | 48564.27 | 48564.27 | 0 | 44495.7 | 4068.57 | 100% | 91.62% | 22204.3 | 33.29% | 0 | 0 | 5589.46
26-PC-39619 | Hackberry Bend Transmission Line - Paleontological Monitoring | In Progress | Fixed fee | Red Rock | Lydia Cisneros |  | 79000 | 2630.7 | 609.56 | 54115 | 54115 | 0 | 1801.57 | 52313.43 | 3.3% | 3.33% | 77198.43 | 97.72% | 1801.57 | 1801.57 | 609.56
26-PC-39638 | On-Call: North Fork Transmission Line Historic Resources Evaluation | In Progress | Time and material | Red Rock | Shelia Horne |  | 131700 | 34411.5 | 20382.48 | 85748.9 | 62865.33 | 22883.57 | 23512.46 | 62236.44 | 26.1% | 27.42% | 108187.54 | 82.15% | 23512.46 | 7766.86 | 20382.48
26-PC-39644 | Ember Valley Reservoir - Section 106 Consultation | Completed | Time and material | Red Rock | Lydia Cisneros |  | 100300 | 0 | 0 | 69527.96 | 69527.96 | 0 | 65771.97 | 3755.99 | 0% | 94.6% | 34528.03 | 34.42% | 0 | 0 | 0
26-PC-39671 | Phase I: Pebble Beach Road Solar Class III Survey | Completed | Fixed fee | Red Rock | Tina Aguirre |  | 62500 | 62500 | 62500 | 46625 | 46625 | 0 | 60612.5 | -13987.5 | 100% | 130% | 1887.5 | 3.02% | 0 | 0 | 0
26-PC-39699 | Thistle Down Reservoir - Data Recovery | In Progress | Fixed fee | Red Rock | Jeanette Chung |  | 88200 | 9931.32 | 5211.57 | 62269.2 | 62269.2 | 0 | 7012.08 | 55257.12 | 11.3% | 11.26% | 81187.92 | 92.05% | 7012.08 | 2432.39 | 5211.57
26-PC-39711 | Sandpiper Canal Lining Phase II Testing | Completed | Fixed fee | Red Rock | Tina Aguirre |  | 69600 | 69600 | 69600 | 59125.2 | 59125.2 | 0 | 67147.15 | -8021.95 | 100% | 113.6% | 2452.85 | 3.52% | 0 | 0 | 0
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Cost Tracking on Closed Project | Fixed fee | Red Rock | Tina Aguirre | 07/31/2026 | 115900 | 115900 | 115900 | 86530.94 | 86530.94 | 0 | 99694.97 | -13164.03 | 100% | 115.2% | 16205.03 | 13.98% | 0 | 0 | 0
26-PC-39730 | Coyote Springs Water Main - Phase I Survey | Completed | Fixed fee | Red Rock | Javier Newman |  | 25600 | 25600 | 25600 | 18618.88 | 18618.88 | 0 | 17603.57 | 1015.31 | 100% | 94.55% | 7996.43 | 31.24% | 0 | 0 | 1395.2
26-PC-39744 | Phase III: Sumac Ridge Wastewater Plant Archaeological Testing | In Progress | Time and material | Red Rock | Bruce Suarez |  | 351100 | 25000.75 | 16051.84 | 225441.31 | 225441.31 | 0 | 14063.62 | 211377.69 | 7.1% | 6.24% | 337036.38 | 95.99% | 14063.62 | 4153.1 | 16051.84
26-PC-39778 | Thistle Down Battery Storage - Architectural History Survey | In Progress | Time and material | Red Rock | Marisa Odom |  | 35700 | 2505.25 | 2429.52 | 26613.7 | 20089.92 | 6523.78 | 1536.44 | 25077.26 | 7% | 5.77% | 34163.56 | 95.7% | 1536.44 | 44.42 | 2429.52
26-PC-39780 | Phase I: Rushgrass Draw Mine Expansion Maritime Remote Sensing Survey | In Progress | Time and material | Red Rock | Shelia Horne |  | 113500 | 9446.75 | 4440.96 | 76714.65 | 76714.65 | 0 | 5533.85 | 71180.8 | 8.3% | 7.21% | 107966.15 | 95.12% | 5533.85 | 2640.03 | 4440.96
26-PC-39880 | Larkspur Section 106 Consultation | In Progress | Time and material | Red Rock | Jeanette Chung |  | 100200 | 37315.75 | 16949.07 | 73772.32 | 69374.59 | 4397.73 | 27101.22 | 46671.1 | 37.2% | 36.74% | 73098.78 | 72.95% | 27101.22 | 7958.92 | 16949.07
26-PC-39913 | On-Call: Bramble Creek Rail Siding Cultural Resources Assessment | On Hold | Fixed fee | Red Rock | Javier Newman |  | 119400 | 0 | 0 | 78314.46 | 78314.46 | 0 | 0 | 78314.46 | 0% | 0% | 119400 | 100% | 0 | 0 | 0
26-PC-39971 | Pebble Beach Road Environmental Review Support | Final Reporting/Review | Time and material | Red Rock | Marisa Odom |  | 114600 | 102477.5 | 83845.05 | 79406.34 | 79406.34 | 0 | 65080 | 14326.34 | 89.4% | 81.96% | 49520 | 43.21% | 65080 | 9848.52 | 83845.05
26-PC-39990 | Falcon Mesa Solar - Phase I Survey | In Progress | Time and material | Red Rock | Tina Aguirre |  | 15600 | 710.5 | 363.28 | 10693.8 | 10693.8 | 0 | 417.69 | 10276.11 | 4.6% | 3.91% | 15182.31 | 97.32% | 417.69 | 177.35 | 363.28
26-PC-40009 | Oak Terrace Harbor Dredging Curation | In Progress | Fixed fee | Red Rock | Shelia Horne |  | 63600 | 23188.56 | 20141.14 | 43349.76 | 43349.76 | 0 | 15804.89 | 27544.87 | 36.5% | 36.46% | 47795.11 | 75.15% | 15804.89 | 1002.77 | 20141.14
26-PC-40038 | Badger Hollow Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Red Rock | Lydia Cisneros |  | 348700 | 348700 | 348700 | 275403.26 | 275403.26 | 0 | 257330.22 | 18073.04 | 100% | 93.44% | 91369.78 | 26.2% | 0 | 0 | 22874.72
26-PC-40055 | Twin Buttes Pipeline Architectural History Survey | In Progress | Time and material | Red Rock | Shelia Horne |  | 22000 | 8813.5 | 2605.35 | 14259.29 | 12788.18 | 1471.11 | 4910.87 | 9348.42 | 40.1% | 34.44% | 17089.13 | 77.68% | 4910.87 | 4910.87 | 2605.35
26-PC-40092 | Eagle Bend Environmental Review Support | In Progress | Fixed fee | Sierra South | Angelica Poole |  | 3672000 | 15422.4 | 7215.21 | 2369908.8 | 2369908.8 | 0 | 9935.54 | 2359973.26 | 0.4% | 0.42% | 3662064.46 | 99.73% | 9935.54 | 4050.06 | 7215.21
26-PC-40108 | Hackberry Bend Trail - Phase II Testing | Final Billing/Invoice | Fixed fee | Sierra South | Benjamin Mathis |  | 138800 | 138800 | 138800 | 89484.36 | 89484.36 | 0 | 90632.27 | -1147.91 | 100% | 101.3% | 48167.73 | 34.7% | 0 | 0 | 0
26-PC-40128 | Goldfinch Maritime Remote Sensing Survey | Final Billing/Invoice | Fixed fee | Sierra South | Donna Herring |  | 67100 | 67100 | 67100 | 49016.55 | 49016.55 | 0 | 50052.19 | -1035.64 | 100% | 102.1% | 17047.81 | 25.41% | 0 | 0 | 0
26-PC-40176 | On-Call: Twin Buttes Harbor Dredging Phase I Survey | Final Reporting/Review | Time and material | Sierra South | Louis Huff |  | 143600 | 39852 | 33027.78 | 93138.96 | 93138.96 | 0 | 23412.97 | 69725.99 | 27.8% | 25.14% | 120187.03 | 83.7% | 23412.97 | 3286.4 | 33027.78
26-PC-40190 | Pebble Beach Road Trail - Section 106 Consultation | On Hold | Fixed fee | Sierra | Benjamin Mathis |  | 113900 | 0 | 0 | 91485.25 | 84716.58 | 6768.67 | 0 | 91485.25 | 0% | 0% | 113900 | 100% | 0 | 0 | 0
26-PC-40229 | Pine Hollow School Campus - Data Recovery | Final Billing/Invoice | Time and material | Sierra South | Angelica Poole |  | 370800 | 0 | 0 | 229525.2 | 229525.2 | 0 | 298382.76 | -68857.56 | 0% | 130% | 72417.24 | 19.53% | 0 | 0 | 0
26-PC-40289 | Windmill Flat Park Improvements Environmental Review Support | Final Billing/Invoice | Fixed fee | Sierra North | Angelica Poole |  | 135800 | 135800 | 135800 | 109481.96 | 109481.96 | 0 | 102903.26 | 6578.7 | 100% | 93.99% | 32896.74 | 24.22% | 0 | 0 | 8161.58
26-PC-40296 | Twin Buttes Class III Survey | In Progress | Fixed fee | Sierra South | Donna Herring |  | 6400 | 1088.64 | 1006.05 | 4648.32 | 4648.32 | 0 | 790.8 | 3857.52 | 17% | 17.01% | 5609.2 | 87.64% | 790.8 | 0 | 1006.05
26-PC-40304 | Willow Springs Fiber Route Archaeological Testing | In Progress | Fixed fee | Sierra | Donna Herring |  | 132900 | 18100.98 | 15168.63 | 101283.22 | 73563.57 | 27719.65 | 13790.75 | 87492.47 | 13.6% | 13.62% | 119109.25 | 89.62% | 13790.75 | 1776.05 | 15168.63
26-PC-40329 | Yarrow Point Maritime Remote Sensing Survey | Final Billing/Invoice | Fixed fee | Sierra North | Donna Herring |  | 416100 | 416100 | 416100 | 281325.21 | 281325.21 | 0 | 365722.77 | -84397.56 | 100% | 130% | 50377.23 | 12.11% | 0 | 0 | 0
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 08/28/2026 | 96900 | 96900 | 90582.43 | 68401.71 | 68401.71 | 0 | 75128.43 | -6726.72 | 100% | 109.8% | 21771.57 | 22.47% | 75128.43 | 2492.02 | 90582.43
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Final Reporting/Review | Fixed fee | Sierra | Louis Huff |  | 19200 | 19200 | 16759.26 | 14098.56 | 14098.56 | 0 | 18399.82 | -4301.26 | 100% | 130.5% | 800.18 | 4.17% | 18399.82 | 1512.08 | 16759.26
26-PC-40361 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Donna Herring | 09/11/2026 | 156300 | 117897.09 | 95830.05 | 102829.77 | 102829.77 | 0 | 77565.49 | 25264.28 | 75.4% | 75.43% | 78734.51 | 50.37% | 77565.49 | 9902.6 | 95830.05
26-PC-40384 | Maple Fork Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Sierra North | Donna Herring |  | 102900 | 49138.25 | 47047.68 | 62220.33 | 48730.76 | 13489.57 | 30693.53 | 31526.8 | 47.8% | 49.33% | 72206.47 | 70.17% | 30693.53 | 1757.57 | 47047.68
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Final Reporting/Review | Fixed fee | Sierra South | Donna Herring |  | 5900 | 5900 | 5708.22 | 4379.73 | 3449.54 | 930.19 | 8489.9 | -4110.17 | 100% | 193.8% | -2589.9 | -43.9% | 8489.9 | 136.59 | 5708.22
26-PC-40443 | Pine Hollow Wastewater Plant - Built Environment Survey | In Progress | Fixed fee | Sierra North | Donna Herring |  | 424500 | 65288.1 | 27486.99 | 299781.9 | 299781.9 | 0 | 46117.81 | 253664.09 | 15.4% | 15.38% | 378382.19 | 89.14% | 46117.81 | 21994.75 | 27486.99
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | In Progress | Fixed fee | Sierra North | Donna Herring | 09/04/2026 | 7500 | 7500 | 7376.17 | 5493 | 5493 | 0 | 8125.76 | -2632.76 | 100% | 147.9% | -625.76 | -8.34% | 8125.76 | 0 | 7376.17
26-PC-40590 | Wildrye Highway Widening - Environmental Review Support | Final Reporting/Review | Fixed fee | Sierra North | Angelica Poole |  | 1002000 | 153406.2 | 121067.73 | 809716.2 | 809716.2 | 0 | 123942.06 | 685774.14 | 15.3% | 15.31% | 878057.94 | 87.63% | 123942.06 | 25280.61 | 121067.73
26-PC-40605 | Willow Springs Mixed-Use Development Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Sierra | Louis Huff | 08/14/2026 | 138400 | 0 | 0 | 95191.52 | 95191.52 | 0 | 81646.35 | 13545.17 | 0% | 85.77% | 56753.65 | 41.01% | 0 | 0 | 0
26-PC-40607 | Task Order 35: Cedar Hollow Housing Development Archaeological Testing | On Hold | Fixed fee | Sierra | Benjamin Mathis |  | 75100 | 0 | 0 | 47821.37 | 36024 | 11797.37 | 0 | 47821.37 | 0% | 0% | 75100 | 100% | 0 | 0 | 0
26-PC-40640 | Cedar Hollow Mine Expansion Cultural Resources Monitoring | Final Billing/Invoice | Time and material | Sierra | Angelica Poole |  | 12900 | 0 | 0 | 9127.87 | 7793.5 | 1334.37 | 8897.34 | 230.53 | 0% | 97.47% | 4002.66 | 31.03% | 0 | 0 | 0
26-PC-40690 | Pine Hollow Wastewater Plant - Paleontological Monitoring | In Progress | Time and material | Coastal Bend | Duane Ballard |  | 252500 | 101574 | 100069.43 | 171094 | 171094 | 0 | 65638.21 | 105455.79 | 40.2% | 38.36% | 186861.79 | 74% | 65638.21 | 0 | 100069.43
26-PC-40716 | Elk Meadow Architectural History Survey | Final Billing/Invoice | Time and material | Coastal Bend | Alexis Nixon |  | 6700 | 0 | 0 | 4710.77 | 4710.77 | 0 | 5030.17 | -319.4 | 0% | 106.8% | 1669.83 | 24.92% | 0 | 0 | 0
26-PC-40729 | On-Call: Dove Canyon Cell Tower Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Alexis Nixon |  | 92500 | 7797.75 | 4889.9 | 58081.13 | 53482.09 | 4599.04 | 4896.28 | 53184.85 | 8.4% | 8.43% | 87603.72 | 94.71% | 4896.28 | 2904.4 | 4889.9
26-PC-40750 | On-Call: Willow Springs Highway Widening Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Steve Rubio |  | 494600 | 24206.25 | 9568.26 | 310521.94 | 245535.75 | 64986.19 | 17521.7 | 293000.24 | 4.9% | 5.64% | 477078.3 | 96.46% | 17521.7 | 6916.46 | 9568.26
26-PC-40760 | Foxglove Canal Lining - Archaeological Testing | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi |  | 77500 | 22064.25 | 19509.79 | 63893.46 | 46765.44 | 17128.02 | 18190.84 | 45702.62 | 28.5% | 28.47% | 59309.16 | 76.53% | 18190.84 | 1742.18 | 19509.79
26-PC-40805 | Willow Springs Battery Storage - Section 106 Consultation | Completed | Time and material | Coastal Bend | Jared Choi |  | 15100 | 0 | 0 | 11494.12 | 11494.12 | 0 | 13051.04 | -1556.92 | 0% | 113.5% | 2048.96 | 13.57% | 0 | 0 | 0
26-PC-40860 | Fern Valley Solar Data Recovery | In Progress | Fixed fee | Coastal Bend | Steve Rubio |  | 181300 | 41481.44 | 31148.81 | 145148.78 | 145148.78 | 0 | 33204.32 | 111944.46 | 22.9% | 22.88% | 148095.68 | 81.69% | 33204.32 | 4617.34 | 31148.81
26-PC-40902 | Badger Hollow Solar Environmental Review Support | Final Billing/Invoice | Fixed fee | Coastal Bend | Jared Choi |  | 86700 | 86700 | 86700 | 65666.58 | 65666.58 | 0 | 63897.65 | 1768.93 | 100% | 97.31% | 22802.35 | 26.3% | 0 | 0 | 2332.23
26-PC-40966 | Harbor View Trail - GIS Mapping | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard |  | 225100 | 53236.15 | 41568.68 | 146315 | 146315 | 0 | 34610.68 | 111704.32 | 23.6% | 23.65% | 190489.32 | 84.62% | 34610.68 | 6066.51 | 41568.68
26-PC-40983 | Falcon Mesa Data Recovery | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 07/31/2026 | 7200 | 5618.88 | 4989.63 | 6217.91 | 4906.72 | 1311.19 | 4852.67 | 1365.24 | 78% | 78.04% | 2347.33 | 32.6% | 4852.67 | 335.62 | 4989.63
26-PC-41005 | Juniper Wash Architectural History Survey | In Progress | Time and material | Coastal Bend | Duane Ballard |  | 60000 | 4026 | 2895.23 | 38934 | 38934 | 0 | 2404.38 | 36529.62 | 6.7% | 6.18% | 57595.62 | 95.99% | 2404.38 | 227.78 | 2895.23
26-PC-41046 | Wren Hollow Airport Apron - Data Recovery | Final Billing/Invoice | Fixed fee | Coastal Bend | Duane Ballard |  | 60200 | 60200 | 60200 | 47644.16 | 35250.42 | 12393.74 | 58991.23 | -11347.07 | 100% | 123.8% | 1208.77 | 2.01% | 0 | 0 | 0
26-PC-41048 | Task Order 33: Granite Pass Battery Storage Phase I Survey | In Progress | Time and material | Coastal Bend | Jared Choi |  | 458200 | 126518.5 | 82360.74 | 315149.96 | 315149.96 | 0 | 88143.15 | 227006.81 | 27.6% | 27.97% | 370056.85 | 80.76% | 88143.15 | 24066.69 | 82360.74
26-PC-41130 | Harbor View Highway Widening Data Recovery | Cost Tracking on Closed Project | Time and material | Coastal Bend | Steve Rubio |  | 290300 | 0 | 0 | 219699.04 | 219699.04 | 0 | 201136.18 | 18562.86 | 0% | 91.55% | 89163.82 | 30.71% | 0 | 0 | 0
26-PC-41176 | Wildrye Park Improvements - Environmental Review Support | Final Reporting/Review | Fixed fee | Coastal Bend | Steve Rubio |  | 109400 | 40401.42 | 34591.32 | 81568.64 | 81568.64 | 0 | 30126.95 | 51441.69 | 36.9% | 36.93% | 79273.05 | 72.46% | 30126.95 | 2670.68 | 34591.32
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 07/31/2026 | 41400 | 41400 | 41400 | 27278.33 | 19877.52 | 7400.81 | 30232.83 | -2954.5 | 100% | 110.8% | 11167.17 | 26.97% | 30232.83 | 0 | 41400
26-PC-41222 | Sage Flat Transmission Line - Cultural Resources Assessment | In Progress | Time and material | Coastal Bend | Alexis Nixon |  | 26000 | 5460 | 3035.93 | 18522.4 | 18522.4 | 0 | 3158.62 | 15363.78 | 21% | 17.05% | 22841.38 | 87.85% | 3158.62 | 377.4 | 3035.93
26-PC-41229 | Windmill Flat Phase I Survey | On Hold | Fixed fee | Coastal Bend | Jared Choi |  | 214000 | 0 | 0 | 143615.4 | 143615.4 | 0 | 0 | 143615.4 | 0% | 0% | 214000 | 100% | 0 | 0 | 0
26-PC-41230 | Phase I: Slate Ridge Battery Storage Phase I Survey | In Progress | Fixed fee | Coastal Bend | Alexis Nixon |  | 46400 | 16425.6 | 9235.19 | 35769.76 | 35769.76 | 0 | 12661.46 | 23108.3 | 35.4% | 35.4% | 33738.54 | 72.71% | 12661.46 | 3130.48 | 9235.19
26-PC-41302 | Thistle Down Pipeline Architectural History Survey | Completed | Time and material | Coastal Bend | Duane Ballard |  | 20300 | 0 | 0 | 13056.96 | 13056.96 | 0 | 13598.19 | -541.23 | 0% | 104.2% | 6701.81 | 33.01% | 0 | 0 | 0
26-PC-41334 | Fern Valley Housing Development - Data Recovery | In Progress | Fixed fee | Coastal Bend | Duane Ballard |  | 154000 | 105967.4 | 97190.14 | 99198.32 | 88810.04 | 10388.28 | 68260.63 | 30937.69 | 68.8% | 68.81% | 85739.37 | 55.67% | 68260.63 | 4704.38 | 97190.14
26-PC-41386 | Task Order 11: Slate Ridge Harbor Dredging Class III Survey | In Progress | Fixed fee | Coastal Bend | Alexis Nixon |  | 302700 | 11260.44 | 5037.07 | 209680.29 | 209680.29 | 0 | 7795.4 | 201884.89 | 3.7% | 3.72% | 294904.6 | 97.42% | 7795.4 | 7795.4 | 5037.07
26-PC-41394 | Maple Fork Bridge Replacement - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Duane Ballard | 08/14/2026 | 15700 | 14005.97 | 14005.97 | 11219.22 | 11219.22 | 0 | 10008.86 | 1210.36 | 89.2% | 89.21% | 5691.14 | 36.25% | 0 | 0 | 0
26-PC-41406 | Task Order 27: Dove Canyon Battery Storage Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Alexis Nixon |  | 381600 | 155540.16 | 139465.09 | 257192.06 | 187803.42 | 69388.64 | 104836.49 | 152355.57 | 40.8% | 40.76% | 276763.51 | 72.53% | 104836.49 | 12162.85 | 139465.09
26-PC-41425 | Pebble Beach Road GIS Mapping | Transferred Entity | Time and material | Coastal Bend | Steve Rubio |  | 268700 | 99208 | 55597.03 | 183253.4 | 183253.4 | 0 | 63737.62 | 119515.78 | 36.9% | 34.78% | 204962.38 | 76.28% | 63737.62 | 24109.14 | 55597.03
26-PC-41446 | Stone Mill Levee Repair Archaeological Testing | In Progress | Time and material | Coastal Bend | Jared Choi |  | 263000 | 0 | 0 | 172291.3 | 172291.3 | 0 | 0 | 172291.3 | 0% | 0% | 263000 | 100% | 0 | 0 | 0
26-PC-41453 | Pebble Beach Road Cell Tower Environmental Review Support | On Hold | Fixed fee | Coastal Bend | Alexis Nixon |  | 28100 | 0 | 0 | 22286.11 | 22286.11 | 0 | 0 | 22286.11 | 0% | 0% | 28100 | 100% | 0 | 0 | 0
26-PC-41466 | Millbrook Cultural Resources Assessment | Lab/Curation | Time and material | Coastal Bend | Alexis Nixon |  | 857800 | 255216.5 | 255216.5 | 634085.76 | 634085.76 | 0 | 178651.18 | 455434.58 | 29.8% | 28.17% | 679148.82 | 79.17% | 178651.18 | 0 | 255216.5
26-PC-41575 | Juniper Wash Highway Widening - Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Diane Daniels |  | 131400 | 13613.04 | 5545.27 | 100941.48 | 100941.48 | 0 | 10453.11 | 90488.37 | 10.4% | 10.36% | 120946.89 | 92.04% | 10453.11 | 4519.57 | 5545.27
26-PC-41578 | Task Order 2: Pebble Beach Road Transmission Line Paleontological Monitoring | On Hold | Time and material | Coastal Bend | Diane Daniels |  | 340900 | 0 | 0 | 240285.42 | 188299.68 | 51985.74 | 0 | 240285.42 | 0% | 0% | 340900 | 100% | 0 | 0 | 0
26-PC-41623 | Eagle Bend Bridge Replacement - GIS Mapping | On Hold | Time and material | Coastal Bend | Duane Ballard |  | 113100 | 0 | 0 | 79124.76 | 79124.76 | 0 | 0 | 79124.76 | 0% | 0% | 113100 | 100% | 0 | 0 | 0
26-PC-41644 | Granite Pass Built Environment Survey | Transferred Entity | Fixed fee | Coastal Bend | Alexis Nixon |  | 330600 | 66384.48 | 36012.37 | 258297.78 | 258297.78 | 0 | 51878.28 | 206419.5 | 20.1% | 20.08% | 278721.72 | 84.31% | 51878.28 | 17443.75 | 36012.37
26-PC-41661 | Ember Valley Levee Repair Data Recovery | In Progress | Fixed fee | Coastal Bend | Diane Daniels |  | 4800 | 4800 | 1827.9 | 4028.16 | 4028.16 | 0 | 4393.64 | -365.48 | 100% | 109.1% | 406.36 | 8.47% | 4393.64 | 794.31 | 1827.9
26-PC-41663 | On-Call: Plover Cove Highway Widening Cultural Resources Assessment | On Hold | Time and material | Coastal Bend | Duane Ballard |  | 510700 | 0 | 0 | 337572.7 | 337572.7 | 0 | 0 | 337572.7 | 0% | 0% | 510700 | 100% | 0 | 0 | 0
26-PC-41667 | Kestrel Butte Transmission Line - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Duane Ballard | 09/04/2026 | 131800 | 127576.25 | 93060.18 | 98659.54 | 84109.2 | 14550.34 | 81942.27 | 16717.27 | 96.8% | 83.06% | 49857.73 | 37.83% | 81942.27 | 16293.97 | 93060.18
26-PC-41671 | Phase I: Slate Ridge Solar Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Coastal Bend | Diane Daniels |  | 256200 | 256200 | 256200 | 182542.5 | 182542.5 | 0 | 237305.25 | -54762.75 | 100% | 130% | 18894.75 | 7.37% | 0 | 0 | 0
26-PC-41683 | On-Call: Slate Ridge Levee Repair Built Environment Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard |  | 250100 | 6877.75 | 1667.12 | 169042.59 | 169042.59 | 0 | 4642.33 | 164400.26 | 2.8% | 2.75% | 245457.67 | 98.14% | 4642.33 | 3887.06 | 1667.12
26-PC-41707 | Quail Run Solar Environmental Review Support | Final Reporting/Review | Fixed fee | Built Environment | Jenny Wilkinson |  | 27000 | 6966 | 3982.77 | 20358 | 20358 | 0 | 5252.61 | 15105.39 | 25.8% | 25.8% | 21747.39 | 80.55% | 5252.61 | 177.5 | 3982.77
26-PC-41721 | Thistle Down Curation | In Progress | Time and material | Built Environment | Melody Holloway |  | 67700 | 36183 | 31888.77 | 46692.69 | 46692.69 | 0 | 23748.7 | 22943.99 | 53.4% | 50.86% | 43951.3 | 64.92% | 23748.7 | 3661.94 | 31888.77
26-PC-41739 | Slate Ridge Historic Resources Evaluation | In Progress | Fixed fee | Built Environment | Melody Holloway |  | 240100 | 27731.55 | 23121.15 | 163268 | 163268 | 0 | 18858.88 | 144409.12 | 11.6% | 11.55% | 221241.12 | 92.15% | 18858.88 | 4693.9 | 23121.15
26-PC-41750 | Task Order 6: Copper Flats Wind Farm Maritime Remote Sensing Survey | On Hold | Fixed fee | Built Environment | Kathleen Cabrera |  | 825200 | 0 | 0 | 659196.16 | 612223.44 | 46972.72 | 0 | 659196.16 | 0% | 0% | 825200 | 100% | 0 | 0 | 0
26-PC-41776 | Sandpiper Battery Storage GIS Mapping | Lab/Curation | Time and material | Built Environment | Jenny Wilkinson |  | 457800 | 40229.25 | 36984.05 | 310067.94 | 310067.94 | 0 | 25479.07 | 284588.87 | 8.8% | 8.22% | 432320.93 | 94.43% | 25479.07 | 2479.72 | 36984.05
26-PC-41803 | Copper Flats Section 106 Consultation | Lab/Curation | Fixed fee | Built Environment | Jenny Wilkinson |  | 554800 | 67130.8 | 55086.8 | 392021.68 | 392021.68 | 0 | 47452.96 | 344568.72 | 12.1% | 12.1% | 507347.04 | 91.45% | 47452.96 | 7432.26 | 55086.8
26-PC-41821 | Blue Heron School Campus Curation | In Progress | Time and material | Built Environment | Jenny Wilkinson |  | 152400 | 38727 | 35011.46 | 98770.44 | 98770.44 | 0 | 25864.78 | 72905.66 | 25.4% | 26.19% | 126535.22 | 83.03% | 25864.78 | 1799.77 | 35011.46
26-PC-41863 | Silver Lake Canal Lining Cultural Resources Assessment | In Progress | Fixed fee | Built Environment | Jenny Wilkinson |  | 322500 | 9255.75 | 8208.44 | 224460 | 224460 | 0 | 6449.34 | 218010.66 | 2.9% | 2.87% | 316050.66 | 98% | 6449.34 | 489.05 | 8208.44
26-PC-41865 | Phase II: Copper Flats Reservoir Class III Survey | In Progress | Time and material | Built Environment | Jenny Wilkinson |  | 67100 | 0 | 0 | 48325.42 | 48325.42 | 0 | 0 | 48325.42 | 0% | 0% | 67100 | 100% | 0 | 0 | 0
26-PC-41884 | Foxglove Trail - Curation | In Progress | Time and material | Built Environment | Melody Holloway |  | 1099300 | 100170 | 75305.17 | 743556.08 | 550430.95 | 193125.13 | 69536.27 | 674019.81 | 9.1% | 9.35% | 1029763.73 | 93.67% | 69536.27 | 11428.25 | 75305.17
26-PC-41918 | Plover Cove Data Recovery | In Progress | Fixed fee | Built Environment | Melody Holloway |  | 121100 | 9058.28 | 7963.02 | 81064.34 | 81064.34 | 0 | 6059.97 | 75004.37 | 7.5% | 7.48% | 115040.03 | 95% | 6059.97 | 1056.2 | 7963.02
26-PC-41947 | Juniper Wash Trail - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Built Environment | Rickey Salas |  | 64400 | 37178.12 | 30400.25 | 52073.84 | 52073.84 | 0 | 30061.9 | 22011.94 | 57.7% | 57.73% | 34338.1 | 53.32% | 30061.9 | 4202.44 | 30400.25
26-PC-41954 | Creosote Draw Class III Survey | Completed | Fixed fee | Built Environment | Kathleen Cabrera |  | 98400 | 98400 | 98400 | 77440.8 | 77440.8 | 0 | 89638.03 | -12197.23 | 100% | 115.8% | 8761.97 | 8.9% | 0 | 0 | 0
26-PC-41961 | Eagle Bend Data Recovery | In Progress | Fixed fee | Built Environment | Melody Holloway |  | 463200 | 104822.16 | 104822.16 | 369077.76 | 369077.76 | 0 | 83505.48 | 285572.28 | 22.6% | 22.63% | 379694.52 | 81.97% | 83505.48 | 0 | 104822.16
26-PC-41970 | North Fork School Campus - Cultural Resources Monitoring | Final Reporting/Review | Time and material | Built Environment | Melody Holloway |  | 292200 | 93249.75 | 93249.75 | 212405.41 | 172247.04 | 40158.37 | 60262.35 | 152143.06 | 31.9% | 28.37% | 231937.65 | 79.38% | 60262.35 | 0 | 93249.75
26-PC-41987 | Wildrye Cultural Resources Monitoring | Completed | Fixed fee | Built Environment | Rickey Salas |  | 88100 | 88100 | 88100 | 66383.35 | 66383.35 | 0 | 49349.09 | 17034.26 | 100% | 74.34% | 38750.91 | 43.99% | 0 | 0 | 22606.46
26-PC-42007 | On-Call: Wren Hollow Mixed-Use Development Architectural History Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard |  | 341700 | 37587 | 31519.6 | 215752.53 | 179922 | 35830.53 | 23729.27 | 192023.26 | 11% | 11% | 317970.73 | 93.06% | 23729.27 | 4022.88 | 31519.6
26-PC-42008 | Millbrook GIS Mapping | In Progress | Time and material | Built Environment | Kathleen Cabrera |  | 79400 | 0 | 0 | 54793.94 | 54793.94 | 0 | 0 | 54793.94 | 0% | 0% | 79400 | 100% | 0 | 0 | 0
26-PC-42023 | North Fork Historic Resources Evaluation | Transferred Entity | Fixed fee | Built Environment | Jenny Wilkinson |  | 157000 | 16673.4 | 14885.86 | 111815.4 | 111815.4 | 0 | 11876.63 | 99938.77 | 10.6% | 10.62% | 145123.37 | 92.44% | 11876.63 | 949.73 | 14885.86
26-PC-42040 | Millbrook Phase II Testing | In Progress | Time and material | Built Environment | Jenny Wilkinson |  | 129700 | 14359.5 | 9132.09 | 89350.33 | 89350.33 | 0 | 9591.8 | 79758.53 | 11.1% | 10.74% | 120108.2 | 92.6% | 9591.8 | 2359.06 | 9132.09
26-PC-42099 | Fern Valley Substation Cultural Resources Monitoring | In Progress | Time and material | Built Environment | Jesse Maynard |  | 661800 | 124275.5 | 110235.78 | 445656.12 | 445656.12 | 0 | 74965.47 | 370690.65 | 18.8% | 16.82% | 586834.53 | 88.67% | 74965.47 | 6230.64 | 110235.78
26-PC-42105 | Creosote Draw Archaeological Testing | Completed | Time and material | Built Environment | Jesse Maynard |  | 671900 | 0 | 0 | 486652.56 | 434399.3 | 52253.26 | 589825.21 | -103172.65 | 0% | 121.2% | 82074.79 | 12.22% | 0 | 0 | 0
26-PC-42108 | Sumac Ridge Mixed-Use Development Curation | In Progress | Fixed fee | Built Environment | Kathleen Cabrera |  | 1000600 | 57834.68 | 51120.33 | 761256.48 | 761256.48 | 0 | 43963.83 | 717292.65 | 5.8% | 5.78% | 956636.17 | 95.61% | 43963.83 | 5545.06 | 51120.33
26-PC-42222 | On-Call: Stone Mill Fiber Route Cultural Resources Monitoring | On Hold | Time and material | Built Environment | Rickey Salas |  | 30000 | 0 | 0 | 21213 | 21213 | 0 | 0 | 21213 | 0% | 0% | 30000 | 100% | 0 | 0 | 0
26-PC-42293 | Eagle Bend Water Main Phase II Testing | In Progress | Fixed fee | Paleontology | Charlene Sparks |  | 100800 | 24685.92 | 22746.35 | 88704 | 88704 | 0 | 21724.75 | 66979.25 | 24.5% | 24.49% | 79075.25 | 78.45% | 21724.75 | 293.01 | 22746.35
26-PC-42406 | Saltgrass Cell Tower - Section 106 Consultation | Final Billing/Invoice | Time and material | Paleontology | Charlene Sparks |  | 92600 | 0 | 0 | 64853.52 | 50728.25 | 14125.27 | 55386.04 | 9467.48 | 0% | 85.4% | 37213.96 | 40.19% | 0 | 0 | 0
26-PC-42427 | Phase II: Stone Mill Mine Expansion Section 106 Consultation | In Progress | Time and material | Paleontology | Travis Delgado |  | 926100 | 199575 | 182757.68 | 644195.16 | 644195.16 | 0 | 140019.29 | 504175.87 | 21.6% | 21.74% | 786080.71 | 84.88% | 140019.29 | 9535.4 | 182757.68
26-PC-42428 | Phase II: Yarrow Point Levee Repair Architectural History Survey | Final Reporting/Review | Fixed fee | Paleontology | Charlene Sparks |  | 921200 | 23214.24 | 7402.27 | 680214.08 | 680214.08 | 0 | 17174.43 | 663039.65 | 2.5% | 2.52% | 904025.57 | 98.14% | 17174.43 | 12209.67 | 7402.27
26-PC-42472 | Kestrel Butte Cultural Resources Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 129200 | 4405.72 | 1825.8 | 94328.92 | 94328.92 | 0 | 3220.98 | 91107.94 | 3.4% | 3.41% | 125979.02 | 97.51% | 3220.98 | 3220.98 | 1825.8
26-PC-42492 | Tamarack Class III Survey | In Progress | Time and material | Paleontology | Charlene Sparks |  | 60100 | 15520.75 | 14528.76 | 39629.94 | 39629.94 | 0 | 9610.68 | 30019.26 | 25.8% | 24.25% | 50489.32 | 84.01% | 9610.68 | 150.3 | 14528.76
26-PC-42510 | Lantern Bay Data Recovery | In Progress | Time and material | Paleontology | Charlene Sparks |  | 1304200 | 147490.25 | 138984.13 | 949196.76 | 949196.76 | 0 | 96292.2 | 852904.56 | 11.3% | 10.14% | 1207907.8 | 92.62% | 96292.2 | 1126.88 | 138984.13
26-PC-42554 | Task Order 36: Larkspur Pipeline Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks |  | 138900 | 9750.78 | 3241.35 | 102674.88 | 102674.88 | 0 | 7211.42 | 95463.46 | 7% | 7.02% | 131688.58 | 94.81% | 7211.42 | 2857.69 | 3241.35
26-PC-42585 | On-Call: Eagle Bend Reservoir Class III Survey | Completed | Fixed fee | Paleontology | Charlene Sparks |  | 29400 | 29400 | 29400 | 20518.26 | 20518.26 | 0 | 14763.84 | 5754.42 | 100% | 71.95% | 14636.16 | 49.78% | 0 | 0 | 8246.7
26-PC-42598 | Badger Hollow Phase II Testing | In Progress | Time and material | Paleontology | Travis Delgado |  | 99400 | 52925.75 | 46544.43 | 74509.83 | 55811.54 | 18698.29 | 31770.68 | 42739.15 | 53.2% | 42.64% | 67629.32 | 68.04% | 31770.68 | 3095.98 | 46544.43
26-PC-42616 | Goldfinch Section 106 Consultation | Final Billing/Invoice | Fixed fee | Paleontology | Charlene Sparks |  | 14600 | 14600 | 14600 | 11993.9 | 11993.9 | 0 | 8413.18 | 3580.72 | 100% | 70.15% | 6186.82 | 42.38% | 0 | 0 | 4358.1
26-PC-42648 | Plover Cove Highway Widening - Architectural History Survey | Final Billing/Invoice | Fixed fee | Paleontology | Charlene Sparks |  | 330300 | 330300 | 330300 | 209145.96 | 209145.96 | 0 | 157531.9 | 51614.06 | 100% | 75.32% | 172768.1 | 52.31% | 0 | 0 | 81518.04
26-PC-42664 | Foxglove Cell Tower GIS Mapping | In Progress | Fixed fee | Paleontology | Travis Delgado |  | 50700 | 3199.17 | 1164.27 | 32903.41 | 29535.99 | 3367.42 | 2075.33 | 30828.08 | 6.3% | 6.31% | 48624.67 | 95.91% | 2075.33 | 1536.52 | 1164.27
26-PC-42679 | Aspen Ridge Phase I Survey | Final Reporting/Review | Fixed fee | Maritime | Kyle Maynard |  | 214600 | 103072.38 | 88132.28 | 144103.9 | 144103.9 | 0 | 69217.42 | 74886.48 | 48% | 48.03% | 145382.58 | 67.75% | 69217.42 | 11674.33 | 88132.28
26-PC-42692 | Quail Run Curation | In Progress | Fixed fee | Maritime | Rita Ayala |  | 300500 | 39666 | 29809.72 | 203889.25 | 203889.25 | 0 | 26905.99 | 176983.26 | 13.2% | 13.2% | 273594.01 | 91.05% | 26905.99 | 5908.29 | 29809.72
26-PC-42734 | On-Call: Lantern Bay Reservoir Architectural History Survey | In Progress | Time and material | Maritime | Rita Ayala |  | 77500 | 41132.25 | 38532.58 | 51615 | 51615 | 0 | 25950.9 | 25664.1 | 53.1% | 50.28% | 51549.1 | 66.51% | 25950.9 | 1928.67 | 38532.58
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | In Progress | Fixed fee | Maritime | Kyle Maynard | 08/28/2026 | 347000 | 252477.2 | 226595.93 | 256363.6 | 256363.6 | 0 | 186528.08 | 69835.52 | 72.8% | 72.76% | 160471.92 | 46.25% | 186528.08 | 10594.73 | 226595.93
26-PC-42759 | Cedar Hollow Pipeline - Section 106 Consultation | Completed | Time and material | Maritime | Kyle Maynard |  | 740600 | 0 | 0 | 515013.24 | 515013.24 | 0 | 489411.31 | 25601.93 | 0% | 95.03% | 251188.69 | 33.92% | 0 | 0 | 0
26-PC-42788 | Riverbend Bridge Replacement Data Recovery | Final Billing/Invoice | Fixed fee | Maritime | Kyle Maynard |  | 1595900 | 1595900 | 1595900 | 1047867.94 | 1047867.94 | 0 | 1257235.02 | -209367.08 | 100% | 120% | 338664.98 | 21.22% | 0 | 0 | 0
26-PC-42811 | On-Call: Yarrow Point Bridge Replacement Archaeological Testing | Completed | Time and material | Maritime | Kyle Maynard |  | 8000 | 0 | 0 | 5034.4 | 5034.4 | 0 | 6127.58 | -1093.18 | 0% | 121.7% | 1872.42 | 23.41% | 0 | 0 | 0
26-PC-42832 | Task Order 39: Saltgrass Levee Repair Class III Survey | Final Reporting/Review | Time and material | Maritime | Rita Ayala |  | 343600 | 38736.25 | 32806.18 | 243097 | 243097 | 0 | 23563.54 | 219533.46 | 11.3% | 9.69% | 320036.46 | 93.14% | 23563.54 | 4126.21 | 32806.18
26-PC-42838 | Phase III: Oak Terrace Pipeline Phase II Testing | In Progress | Fixed fee | Maritime | Rita Ayala |  | 47400 | 19865.34 | 19865.34 | 31824.36 | 31824.36 | 0 | 13337.82 | 18486.54 | 41.9% | 41.91% | 34062.18 | 71.86% | 13337.82 | 0 | 19865.34
26-PC-42859 | On-Call: Redbud Canal Lining Phase II Testing | On Hold | Fixed fee | Maritime | Rita Ayala |  | 34400 | 0 | 0 | 26797.6 | 26797.6 | 0 | 0 | 26797.6 | 0% | 0% | 34400 | 100% | 0 | 0 | 0
26-PC-42880 | Phase I: Quail Run Harbor Dredging Curation | In Progress | Fixed fee | Maritime | Rita Ayala |  | 107200 | 12145.76 | 7389.46 | 87904 | 87904 | 0 | 9955.87 | 77948.13 | 11.3% | 11.33% | 97244.13 | 90.71% | 9955.87 | 1861.31 | 7389.46
26-PC-42898 | Sumac Ridge Architectural History Survey | Final Billing/Invoice | Fixed fee | Maritime | Kyle Maynard |  | 388100 | 388100 | 388100 | 247453.77 | 184120.5 | 63333.27 | 216501.93 | 30951.84 | 100% | 87.49% | 171598.07 | 44.21% | 0 | 0 | 48551.31
26-PC-42926 | Juniper Wash Transmission Line - Class III Survey | In Progress | Fixed fee | Maritime | Rita Ayala |  | 87800 | 4644.62 | 1775.48 | 68132.8 | 68132.8 | 0 | 3601.54 | 64531.26 | 5.3% | 5.29% | 84198.46 | 95.9% | 3601.54 | 2298.71 | 1775.48
26-PC-42940 | North Fork Water Main GIS Mapping | Completed | Time and material | Maritime | Kyle Maynard |  | 17600 | 0 | 0 | 11908.16 | 11908.16 | 0 | 15335.83 | -3427.67 | 0% | 128.8% | 2264.17 | 12.86% | 0 | 0 | 0
26-PC-42951 | Quail Run Solar - Paleontological Monitoring | Final Billing/Invoice | Fixed fee | Maritime | Kyle Maynard |  | 209300 | 209300 | 209300 | 146631.97 | 113788.8 | 32843.17 | 157199.34 | -10567.37 | 100% | 107.2% | 52100.66 | 24.89% | 0 | 0 | 0
26-PC-42962 | Lone Pine Curation | In Progress | Time and material | Maritime | Rita Ayala |  | 1041700 | 12393.75 | 4165.92 | 704293.37 | 704293.37 | 0 | 7965.32 | 696328.05 | 1.2% | 1.13% | 1033734.68 | 99.24% | 7965.32 | 4537.58 | 4165.92
26-PC-42989 | North Fork Cultural Resources Monitoring | In Progress | Time and material | Maritime | Rita Ayala |  | 24000 | 1482 | 1076.33 | 15241.71 | 11972.82 | 3268.89 | 928.45 | 14313.26 | 6.2% | 6.09% | 23071.55 | 96.13% | 928.45 | 232.11 | 1076.33
26-PC-43000 | Pebble Beach Road Park Improvements Curation | Final Billing/Invoice | Fixed fee | Maritime | Rita Ayala |  | 150700 | 150700 | 150700 | 99296.23 | 99296.23 | 0 | 101028.81 | -1732.58 | 100% | 101.7% | 49671.19 | 32.96% | 0 | 0 | 0
26-PC-43026 | Fern Valley Phase I Survey | On Hold | Fixed fee | Maritime | Rita Ayala |  | 66700 | 0 | 0 | 42521.25 | 42521.25 | 0 | 0 | 42521.25 | 0% | 0% | 66700 | 100% | 0 | 0 | 0
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Final Reporting/Review | Time and material | Geospatial | Sylvia Callahan |  | 107600 | 107600 | 99262.67 | 77827.43 | 68885.46 | 8941.97 | 89098.75 | -11271.32 | 100% | 114.5% | 18501.25 | 17.19% | 89098.75 | 7087.44 | 99262.67
26-PC-43059 | Kestrel Butte Battery Storage - Phase II Testing | Final Billing/Invoice | Fixed fee | Geospatial | Sylvia Callahan |  | 44100 | 44100 | 44100 | 27527.22 | 27527.22 | 0 | 34304.67 | -6777.45 | 100% | 124.6% | 9795.33 | 22.21% | 0 | 0 | 0
26-PC-43086 | On-Call: Silver Lake Transmission Line Archaeological Testing | In Progress | Time and material | Geospatial | Sylvia Callahan |  | 2118800 | 0 | 0 | 1431461.28 | 1431461.28 | 0 | 0 | 1431461.28 | 0% | 0% | 2118800 | 100% | 0 | 0 | 0
26-PC-43132 | Phase III: Ember Valley Highway Widening Phase II Testing | Lab/Curation | Fixed fee | Geospatial | Priscilla Pennington |  | 140700 | 47036.01 | 43252.63 | 112756.98 | 112756.98 | 0 | 37690.1 | 75066.88 | 33.4% | 33.43% | 103009.9 | 73.21% | 37690.1 | 161.91 | 43252.63
26-PC-43136 | Phase III: Harbor View Highway Widening Section 106 Consultation | In Progress | Time and material | Geospatial | Priscilla Pennington |  | 3831800 | 168416.5 | 138596.66 | 2564623.74 | 2564623.74 | 0 | 120256.61 | 2444367.13 | 4.4% | 4.69% | 3711543.39 | 96.86% | 120256.61 | 18792.49 | 138596.66
26-PC-43168 | Task Order 35: Aspen Ridge Transmission Line Architectural History Survey | Final Reporting/Review | Fixed fee | Geospatial | Sylvia Callahan |  | 281200 | 84050.68 | 79022.62 | 164749.65 | 145548.52 | 19201.13 | 49236.49 | 115513.16 | 29.9% | 29.89% | 231963.51 | 82.49% | 49236.49 | 4429.8 | 79022.62
26-PC-43191 | Sandpiper Harbor Dredging - Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Meridian Central | Seth Zavala |  | 47200 | 47200 | 47200 | 37639.5 | 27988.2 | 9651.3 | 39248.37 | -1608.87 | 100% | 104.3% | 7951.63 | 16.85% | 0 | 0 | 0
26-PC-43199 | Thistle Down Airport Apron Phase I Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Mathew Shea | 08/14/2026 | 42200 | 38937.94 | 38937.94 | 26341.24 | 26341.24 | 0 | 24305.56 | 2035.68 | 92.3% | 92.27% | 17894.44 | 42.4% | 0 | 0 | 0
26-PC-43222 | Blue Heron Highway Widening Phase II Testing | On Hold | Time and material | Meridian Central | Raymond Hensley |  | 15100 | 0 | 0 | 9664 | 9664 | 0 | 0 | 9664 | 0% | 0% | 15100 | 100% | 0 | 0 | 0
26-PC-43266 | Silver Lake Curation | In Progress | Fixed fee | Meridian Central | Mathew Shea |  | 21300 | 464.34 | 217.28 | 13227.3 | 13227.3 | 0 | 288.09 | 12939.21 | 2.2% | 2.18% | 21011.91 | 98.65% | 288.09 | 288.09 | 217.28
26-PC-43307 | Phase III: Aspen Ridge Mine Expansion Maritime Remote Sensing Survey | In Progress | Time and material | Meridian Central | Raymond Hensley |  | 239600 | 71378.75 | 71378.75 | 189451.72 | 189451.72 | 0 | 52539.33 | 136912.39 | 29.8% | 27.73% | 187060.67 | 78.07% | 52539.33 | 0 | 71378.75
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | In Progress | Fixed fee | Meridian Central | Mathew Shea | 09/18/2026 | 41200 | 30945.32 | 29998.17 | 27426.84 | 27426.84 | 0 | 20599.46 | 6827.38 | 75.1% | 75.11% | 20600.54 | 50% | 20599.46 | 1060.35 | 29998.17
26-PC-43338 | Sparrow Hill Bridge Replacement Section 106 Consultation | In Progress | Time and material | Meridian Central | Raymond Hensley |  | 121900 | 0 | 0 | 79125.29 | 79125.29 | 0 | 0 | 79125.29 | 0% | 0% | 121900 | 100% | 0 | 0 | 0
26-PC-43341 | Phase III: Twin Buttes Wastewater Plant Historic Resources Evaluation | Final Billing/Invoice | Fixed fee | Meridian Central | Seth Zavala |  | 87500 | 87500 | 87500 | 70376.25 | 70376.25 | 0 | 55410.62 | 14965.63 | 100% | 78.73% | 32089.38 | 36.67% | 0 | 0 | 18611.25
26-PC-43364 | Goldfinch Class III Survey | Transferred Entity | Fixed fee | Meridian Central | Raymond Hensley | 08/14/2026 | 24900 | 24900 | 23821.32 | 16624.07 | 15142.4 | 1481.67 | 22825.96 | -6201.89 | 100% | 137.3% | 2074.04 | 8.33% | 22825.96 | 181.76 | 23821.32
26-PC-43381 | Lantern Bay Canal Lining Archaeological Testing | In Progress | Fixed fee | Meridian Central | Clinton Solis |  | 309600 | 23684.4 | 7401.4 | 249847.2 | 249847.2 | 0 | 19118.33 | 230728.87 | 7.6% | 7.65% | 290481.67 | 93.82% | 19118.33 | 9199.48 | 7401.4
26-PC-43404 | On-Call: Timber Gap Transmission Line Built Environment Survey | Final Billing/Invoice | Fixed fee | Meridian Central | Raymond Hensley |  | 190700 | 190700 | 190700 | 155973.53 | 155973.53 | 0 | 202765.59 | -46792.06 | 100% | 130% | -12065.59 | -6.33% | 0 | 0 | 0
26-PC-43429 | Stone Mill Highway Widening Curation | Transferred Entity | Fixed fee | Meridian Central | Clinton Solis |  | 202600 | 10514.94 | 5068.52 | 115400.96 | 115400.96 | 0 | 5994.77 | 109406.19 | 5.2% | 5.19% | 196605.23 | 97.04% | 5994.77 | 4296.47 | 5068.52
26-PC-43478 | Tamarack Airport Apron Phase II Testing | In Progress | Time and material | Meridian Central | Clinton Solis |  | 531800 | 167292.25 | 118587.81 | 378109.8 | 378109.8 | 0 | 117552.59 | 260557.21 | 31.5% | 31.09% | 414247.41 | 77.9% | 117552.59 | 34093.51 | 118587.81
26-PC-43493 | Millbrook Pipeline Cultural Resources Monitoring | In Progress | Time and material | Meridian Central | Raymond Hensley |  | 1164300 | 96389 | 74613.99 | 893116.35 | 726254.3 | 166862.05 | 66672.18 | 826444.17 | 8.3% | 7.47% | 1097627.82 | 94.27% | 66672.18 | 17190.42 | 74613.99
26-PC-43519 | On-Call: Meadowlark Pipeline GIS Mapping | Completed | Fixed fee | Meridian Central | Raymond Hensley |  | 28100 | 28100 | 28100 | 19981.91 | 19981.91 | 0 | 20035.99 | -54.08 | 100% | 100.3% | 8064.01 | 28.7% | 0 | 0 | 0
26-PC-43527 | Maple Fork School Campus Phase II Testing | In Progress | Time and material | Meridian Central | Raymond Hensley |  | 333700 | 77471 | 72040.32 | 224680.21 | 224680.21 | 0 | 53521.21 | 171159 | 23.2% | 23.82% | 280178.79 | 83.96% | 53521.21 | 1976.75 | 72040.32
26-PC-43528 | Quail Run Cell Tower GIS Mapping | Final Reporting/Review | Fixed fee | Meridian Central | Mathew Shea | 08/21/2026 | 21800 | 18639 | 5521.71 | 14869.78 | 14869.78 | 0 | 12713.55 | 2156.23 | 85.5% | 85.5% | 9086.45 | 41.68% | 12713.55 | 9675.16 | 5521.71
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | In Progress | Fixed fee | Meridian Central | Clinton Solis |  | 136900 | 131026.99 | 130552.64 | 105043.37 | 105043.37 | 0 | 100533.21 | 4510.16 | 95.7% | 95.71% | 36366.79 | 26.56% | 100533.21 | 0 | 130552.64
26-PC-43563 | Thistle Down Section 106 Consultation | In Progress | Time and material | Meridian Central | Mathew Shea |  | 79800 | 25811.25 | 19196.62 | 52393.25 | 45333 | 7060.25 | 16759.41 | 35633.84 | 32.3% | 31.99% | 63040.59 | 79% | 16759.41 | 3070.14 | 19196.62
26-PC-43575 | On-Call: Fern Valley Substation Data Recovery | Lab/Curation | Fixed fee | Meridian Central | Mathew Shea |  | 113100 | 79645.02 | 74740.94 | 87831.71 | 66733.2 | 21098.51 | 61848.22 | 25983.49 | 70.4% | 70.42% | 51251.78 | 45.32% | 61848.22 | 564.62 | 74740.94
26-PC-43584 | On-Call: Wren Hollow Solar Architectural History Survey | In Progress | Fixed fee | Meridian Central | Mathew Shea |  | 223700 | 0 | 0 | 185536.78 | 185536.78 | 0 | 0 | 185536.78 | 0% | 0% | 223700 | 100% | 0 | 0 | 0
26-PC-43695 | Willow Springs Maritime Remote Sensing Survey | In Progress | Fixed fee | Meridian Southwest | Alan Gay |  | 104700 | 36027.27 | 27395.63 | 73750.68 | 73750.68 | 0 | 25376.37 | 48374.31 | 34.4% | 34.41% | 79323.63 | 75.76% | 25376.37 | 5734.77 | 27395.63
26-PC-43731 | Task Order 32: Dove Canyon Transmission Line Paleontological Monitoring | In Progress | Time and material | Meridian Southwest | Alan Gay |  | 17700 | 0 | 0 | 12905.07 | 12905.07 | 0 | 0 | 12905.07 | 0% | 0% | 17700 | 100% | 0 | 0 | 0
26-PC-43746 | Cedar Hollow Wastewater Plant - Paleontological Monitoring | On Hold | Fixed fee | Meridian Southwest | Alan Gay |  | 94200 | 0 | 0 | 53458.5 | 53458.5 | 0 | 0 | 53458.5 | 0% | 0% | 94200 | 100% | 0 | 0 | 0
26-PC-43762 | Hawk Point Substation Paleontological Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran |  | 17500 | 946.75 | 335.45 | 15400 | 15400 | 0 | 832.67 | 14567.33 | 5.4% | 5.41% | 16667.33 | 95.24% | 832.67 | 203.09 | 335.45
26-PC-43818 | Plover Cove Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Meridian Southwest | Lynn Tran |  | 277600 | 32062.8 | 22111.94 | 226882.48 | 226882.48 | 0 | 26203.95 | 200678.53 | 11.6% | 11.55% | 251396.05 | 90.56% | 26203.95 | 5427.28 | 22111.94
26-PC-43874 | Oak Terrace Cell Tower - Class III Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Justin Mejia |  | 0 | 0 | 0 | 51991.31 | 51991.31 | 0 | 0 | 51991.31 | 0% | 0% | 0 | 0% | 0 | 0 | 0
26-PC-43899 | On-Call: Foxglove Reservoir Cultural Resources Monitoring | In Progress | Time and material | NH Gulf (USD) | Justin Mejia |  | 154600 | 17698 | 9002.14 | 103767.52 | 103767.52 | 0 | 12573.63 | 91193.89 | 11.4% | 12.12% | 142026.37 | 91.87% | 12573.63 | 8729.01 | 9002.14
26-PC-43915 | Task Order 5: Twin Buttes Bridge Replacement Phase I Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Javier Rangel |  | 0 | 0 | 0 | 177936 | 177936 | 0 | 0 | 177936 | 0% | 0% | 0 | 0% | 0 | 0 | 0
26-PC-43927 | On-Call: Millbrook Cell Tower Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins |  | 0 | 0 | 0 | 39334.64 | 35895.35 | 3439.29 | 1978.95 | 37355.69 | 0% | 5.03% | -1978.95 | 0% | 1978.95 | 0 | 0
26-PC-43957 | Meadowlark Rail Siding - GIS Mapping | Completed | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 294000 | 294000 | 294000 | 218030.4 | 218030.4 | 0 | 255258.13 | -37227.73 | 100% | 117.1% | 38741.87 | 13.18% | 0 | 0 | 0
26-PC-43961 | On-Call: Sparrow Hill Fiber Route Architectural History Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 0 | 0 | 0 | 211627.08 | 211627.08 | 0 | 82957.71 | 128669.37 | 0% | 39.2% | -82957.71 | 0% | 82957.71 | 0 | 0
26-PC-43963 | On-Call: Foxglove Trail Data Recovery | In Progress | Fixed fee | NH Gulf (USD) | Javier Rangel |  | 532600 | 133842.38 | 117842.42 | 335058.66 | 335058.66 | 0 | 84187.73 | 250870.93 | 25.1% | 25.13% | 448412.27 | 84.19% | 84187.73 | 7928.03 | 117842.42
26-PC-43979 | Pine Hollow Harbor Dredging - Historic Resources Evaluation | Transferred Entity | Fixed fee | NH Gulf (USD) | Justin Mejia |  | 0 | 0 | 0 | 72742.25 | 72742.25 | 0 | 0 | 72742.25 | 0% | 0% | 0 | 0% | 0 | 0 | 0
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Justin Mejia |  | 0 | 0 | 0 | 146699.52 | 146699.52 | 0 | 127368.63 | 19330.89 | 0% | 86.82% | -127368.63 | 0% | 127368.63 | 0 | 0
26-PC-43991 | Saltgrass Water Main - Archaeological Testing | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence |  | 22500 | 13819.5 | 10534.3 | 13335.87 | 10433.28 | 2902.59 | 8191.4 | 5144.47 | 61.4% | 61.42% | 14308.6 | 63.59% | 8191.4 | 1515.19 | 10534.3
26-PC-44007 | Goldfinch Battery Storage Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Randy Cantu |  | 0 | 0 | 0 | 149799.38 | 149799.38 | 0 | 8751.52 | 141047.86 | 0% | 5.84% | -8751.52 | 0% | 8751.52 | 0 | 0
26-PC-44050 | On-Call: Hawk Point Canal Lining Archaeological Testing | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 0 | 0 | 0 | 477190.72 | 477190.72 | 0 | 19701.7 | 457489.02 | 0% | 4.13% | -19701.7 | 0% | 19701.7 | 0 | 0
26-PC-44072 | Oak Terrace Water Main GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Susan Wilkins |  | 0 | 0 | 0 | 79469.46 | 79469.46 | 0 | 40463.71 | 39005.75 | 0% | 50.92% | -40463.71 | 0% | 40463.71 | 0 | 0
26-PC-44090 | Eagle Bend Phase I Survey | Transferred Entity | Time and material | NH Gulf (USD) | Tonya Spence |  | 0 | 0 | 0 | 4404.16 | 3266.03 | 1138.13 | 565.68 | 3838.48 | 0% | 12.84% | -565.68 | 0% | 565.68 | 0 | 0
26-PC-44129 | Tamarack Airport Apron - Section 106 Consultation | In Progress | Fixed fee | NH Gulf (USD) | Javier Rangel |  | 40400 | 0 | 0 | 30324.24 | 30324.24 | 0 | 0 | 30324.24 | 0% | 0% | 40400 | 100% | 0 | 0 | 0
26-PC-44173 | Timber Gap Harbor Dredging - Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Susan Wilkins |  | 0 | 0 | 0 | 111038.84 | 111038.84 | 0 | 15667.21 | 95371.63 | 0% | 14.11% | -15667.21 | 0% | 15667.21 | 0 | 0
26-PC-44201 | Plover Cove Section 106 Consultation | Transferred Entity | Time and material | NH Gulf (USD) | Javier Rangel |  | 0 | 0 | 0 | 115267.26 | 115267.26 | 0 | 35951.46 | 79315.8 | 0% | 31.19% | -35951.46 | 0% | 35951.46 | 0 | 0
26-PC-44220 | Dove Canyon GIS Mapping | Transferred Entity | Time and material | NH Gulf (USD) | Justin Mejia |  | 0 | 0 | 0 | 47634.63 | 47634.63 | 0 | 4924.66 | 42709.97 | 0% | 10.34% | -4924.66 | 0% | 4924.66 | 0 | 0
26-PC-44256 | On-Call: Twin Buttes Rail Siding Environmental Review Support | Transferred Entity | Fixed fee | NH Gulf (USD) | Susan Wilkins |  | 0 | 0 | 0 | 574867.37 | 574867.37 | 0 | 207822.36 | 367045.01 | 0% | 36.15% | -207822.36 | 0% | 207822.36 | 0 | 0
26-PC-44277 | Phase I: Sea Oat Harbor Dredging Architectural History Survey | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence |  | 49100 | 28482.91 | 25401.55 | 39677.71 | 39677.71 | 0 | 23018.4 | 16659.31 | 58% | 58.01% | 26081.6 | 53.12% | 23018.4 | 952.16 | 25401.55
26-PC-44290 | On-Call: Larkspur Park Improvements GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Justin Mejia |  | 0 | 0 | 0 | 160077.87 | 160077.87 | 0 | 28397.17 | 131680.7 | 0% | 17.74% | -28397.17 | 0% | 28397.17 | 0 | 0
26-PC-44302 | Dove Canyon Cell Tower - Built Environment Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte |  | 0 | 0 | 0 | 67334.3 | 67334.3 | 0 | 26359.43 | 40974.87 | 0% | 39.15% | -26359.43 | 0% | 26359.43 | 0 | 0
Big Sky OVHD | Big Sky Overhead | In Progress |  | Big Sky | Carl Barajas |  | 0 | 0 | 0 | 0 | 0 | 0 | 215901.23 | -215901.23 | 0% | 0% | -215901.23 | 0% | 215901.23 | 19977.15 | 0
Bluegrass OVHD | Bluegrass Overhead | In Progress |  | Bluegrass | Kiara Gillespie |  | 0 | 0 | 0 | 0 | 0 | 0 | 128517.19 | -128517.19 | 0% | 0% | -128517.19 | 0% | 128517.19 | 12243.98 | 0
Built Environment OVHD | Built Environment Overhead | In Progress |  | Built Environment | Kathleen Cabrera |  | 0 | 0 | 0 | 0 | 0 | 0 | 276709.42 | -276709.42 | 0% | 0% | -276709.42 | 0% | 276709.42 | 28286.38 | 0
Cascade OVHD | Cascade Overhead | In Progress |  | Cascade | Jean Cooke |  | 0 | 0 | 0 | 0 | 0 | 0 | 226146.2 | -226146.2 | 0% | 0% | -226146.2 | 0% | 226146.2 | 21453.36 | 0
Chesapeake OVHD | Chesapeake Overhead | In Progress |  | Chesapeake | Bryan Mann |  | 0 | 0 | 0 | 0 | 0 | 0 | 235657.93 | -235657.93 | 0% | 0% | -235657.93 | 0% | 235657.93 | 26831.19 | 0
Coastal Bend OVHD | Coastal Bend Overhead | In Progress |  | Coastal Bend | Duane Ballard |  | 0 | 0 | 0 | 0 | 0 | 0 | 258988.95 | -258988.95 | 0% | 0% | -258988.95 | 0% | 258988.95 | 33271.05 | 0
Corporate OVHD | Corporate Overhead | In Progress |  | Corporate | Regina Spence |  | 0 | 0 | 0 | 0 | 0 | 0 | 1287464.5 | -1287464.5 | 0% | 0% | -1287464.5 | 0% | 1287464.5 | 132289.5 | 0
EVT-2026-01 | Company Meeting 2026 | In Progress | Time and material | Corporate | Regina Spence |  | 0 | 0 | 0 | 0 | 0 | 0 | 73967.94 | -73967.94 | 0% | 0% | -73967.94 | 0% | 73967.94 | 12232.4 | 0
Front Range OVHD | Front Range Overhead | In Progress |  | Front Range | Reginald Vargas |  | 0 | 0 | 0 | 0 | 0 | 0 | 321612.77 | -321612.77 | 0% | 0% | -321612.77 | 0% | 321612.77 | 31891.54 | 0
Geospatial OVHD | Geospatial Overhead | In Progress |  | Geospatial | Priscilla Pennington |  | 0 | 0 | 0 | 0 | 0 | 0 | 101511.63 | -101511.63 | 0% | 0% | -101511.63 | 0% | 101511.63 | 10386.57 | 0
Great Lakes OVHD | Great Lakes Overhead | In Progress |  | Great Lakes | Angelica Cervantes |  | 0 | 0 | 0 | 0 | 0 | 0 | 362926.32 | -362926.32 | 0% | 0% | -362926.32 | 0% | 362926.32 | 47971.94 | 0
Gulf Coast OVHD | Gulf Coast Overhead | In Progress |  | Gulf Coast | Sean Jennings |  | 0 | 0 | 0 | 0 | 0 | 0 | 257124.48 | -257124.48 | 0% | 0% | -257124.48 | 0% | 257124.48 | 33197.63 | 0
High Desert OVHD | High Desert Overhead | In Progress |  | High Desert | Jody Wang |  | 0 | 0 | 0 | 0 | 0 | 0 | 280129.7 | -280129.7 | 0% | 0% | -280129.7 | 0% | 280129.7 | 39272.43 | 0
Hill Country OVHD | Hill Country Overhead | In Progress |  | Hill Country | Glen Delacruz |  | 0 | 0 | 0 | 0 | 0 | 0 | 183770.51 | -183770.51 | 0% | 0% | -183770.51 | 0% | 183770.51 | 25933.7 | 0
International OVHD | International Overhead | In Progress |  | NH Gulf (USD) | Tonya Spence |  | 0 | 0 | 0 | 0 | 0 | 0 | 196731.13 | -196731.13 | 0% | 0% | -196731.13 | 0% | 196731.13 | 0 | 0
Island OVHD | Island Overhead | In Progress |  | Island | Briana Melton |  | 0 | 0 | 0 | 0 | 0 | 0 | 215513.04 | -215513.04 | 0% | 0% | -215513.04 | 0% | 215513.04 | 19455.52 | 0
Lakeshore OVHD | Lakeshore Overhead | In Progress |  | Lakeshore | Jeanette Riddle |  | 0 | 0 | 0 | 0 | 0 | 0 | 124102.57 | -124102.57 | 0% | 0% | -124102.57 | 0% | 124102.57 | 11662.86 | 0
MKTG-2026 | Sales and Marketing | In Progress | Time and material | Sales and Marketing | Darius Erickson |  | 0 | 0 | 0 | 0 | 0 | 0 | 2776489.14 | -2776489.14 | 0% | 0% | -2776489.14 | 0% | 2776489.14 | 252477.21 | 0
Maritime OVHD | Maritime Overhead | In Progress |  | Maritime | Kyle Maynard |  | 0 | 0 | 0 | 0 | 0 | 0 | 168758.34 | -168758.34 | 0% | 0% | -168758.34 | 0% | 168758.34 | 17817.48 | 0
Meridian Central OVHD | Meridian Central Overhead | In Progress |  | Meridian Central | Seth Zavala |  | 0 | 0 | 0 | 0 | 0 | 0 | 147475.08 | -147475.08 | 0% | 0% | -147475.08 | 0% | 147475.08 | 13953.22 | 0
Meridian Southwest OVHD | Meridian Southwest Overhead | In Progress |  | Meridian Southwest | Harold Chaney |  | 0 | 0 | 0 | 0 | 0 | 0 | 208908.11 | -208908.11 | 0% | 0% | -208908.11 | 0% | 208908.11 | 26727.4 | 0
Paleontology OVHD | Paleontology Overhead | In Progress |  | Paleontology | Charlene Sparks |  | 0 | 0 | 0 | 0 | 0 | 0 | 128715.62 | -128715.62 | 0% | 0% | -128715.62 | 0% | 128715.62 | 20390.49 | 0
Piedmont OVHD | Piedmont Overhead | In Progress |  | Piedmont | Megan Pineda |  | 0 | 0 | 0 | 0 | 0 | 0 | 220392.92 | -220392.92 | 0% | 0% | -220392.92 | 0% | 220392.92 | 28975.97 | 0
Prairie OVHD | Prairie Overhead | In Progress |  | Prairie | Sherry Lloyd |  | 0 | 0 | 0 | 0 | 0 | 0 | 154336.5 | -154336.5 | 0% | 0% | -154336.5 | 0% | 154336.5 | 13708.37 | 0
Red Rock OVHD | Red Rock Overhead | In Progress |  | Red Rock | Bruce Suarez |  | 0 | 0 | 0 | 0 | 0 | 0 | 326755.13 | -326755.13 | 0% | 0% | -326755.13 | 0% | 326755.13 | 30497.65 | 0
Sales & Marketing OVHD | Sales & Marketing Overhead | In Progress |  | Sales and Marketing | Darius Erickson |  | 0 | 0 | 0 | 0 | 0 | 0 | 270881.2 | -270881.2 | 0% | 0% | -270881.2 | 0% | 270881.2 | 27426.54 | 0
Sierra OVHD | Sierra Overhead | In Progress |  | Sierra | Louis Huff |  | 0 | 0 | 0 | 0 | 0 | 0 | 291776.41 | -291776.41 | 0% | 0% | -291776.41 | 0% | 291776.41 | 27428.96 | 0
Total All Other Projects | Total All Other Projects | [5 empty] | 263537500 | 134096090.79 | 130605637.66 | 190599116.49 | 182111988.74 | 8487127.75 | 124096013.58 | 66503102.91 | 50.9% | 65.11% | 139441486.42 | 52.91% | 30880409.78 | 2917439.79 | 26314082.05
All Projects | All Projects | [5 empty] | 265599000 | 134096090.79 | 130605637.66 | 190599116.49 | 182111988.74 | 8487127.75 | 124096013.58 | 66503102.91 | 50.5% | 65.11% | 141502986.42 | 53.28% | 30880409.78 | 2917439.79 | 26314082.05