## FP&A & QC Project Report
Northstar Heritage, LLC
FP&A & QC Project Report (In SAR)
As of September 29, 2026
Reporting Book: | ACCRUAL
As of Date: | 09/29/2026
Location: | Northstar Gulf
Project: | All Projects
[7 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Original Budget | Total Budget Adjustment | Total Costs |  | Recognized % |  |  |  | Total Costs | Total Costs | Invoiced Amount
[7 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Inception To Date | REV REC % | Budget Spent % | Gross profit | Margin % | Year To Date | Month Ending | Year To Date
[7 empty] | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 | 09/29/2026 |  |  |  | 09/29/2026 | 09/30/2026 | 09/29/2026
| Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | On-Track As of Date | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Actual | Summary | Summary | Summary | Actual | Actual | Actual
All Projects | All Projects
All Other Projects | All Other Projects
24-PC-43877-Int | Wren Hollow Canal Lining Maritime Remote Sensing Survey | In Progress | Fixed fee | NH Gulf | Vanessa Duarte |  | 799125 | 572972.62 | 572972.62 | 703230 | 703230 | 0 | 0 | 703230 | 71.7% | 0% | 799125 | 100% | 0 | 0 | 0
24-PC-44022-Int | Sea Oat Historic Resources Evaluation | In Progress | Time and material | NH Gulf | Vanessa Duarte |  | 4023375 | 2735895 | 2735895 | 2343836.14 | 2031380.06 | 312456.07 | 0 | 2343836.14 | 68% | 0% | 4023375 | 100% | 0 | 0 | 0
24-PC-44113-Int | Cedar Hollow Airport Apron - Paleontological Monitoring | In Progress | Time and material | NH Gulf | Susan Wilkins |  | 991875 | 991875 | 962884.42 | 728333.81 | 728333.81 | 0 | 12387.11 | 715946.7 | 100% | 1.7% | 979487.89 | 98.75% | 12387.11 | 12387.11 | 437190.67
24-PC-44158-Int | Saltgrass Environmental Review Support | In Progress | Fixed fee | NH Gulf | Vanessa Duarte |  | 87000 | 87000 | 86805.04 | 58437.9 | 58437.9 | 0 | 0 | 58437.9 | 100% | 0% | 87000 | 100% | 0 | 0 | 37797.94
25-PC-43932-Int | Blue Heron Built Environment Survey | In Progress | Time and material | NH Gulf | Susan Wilkins |  | 134625 | 90512.06 | 88538.7 | 92460.94 | 68006.25 | 24454.69 | 0 | 92460.94 | 67.2% | 0% | 134625 | 100% | 0 | 0 | 39804.45
25-PC-43966-Int | Silver Lake Rail Siding - Cultural Resources Monitoring | In Progress | Fixed fee | NH Gulf | Tonya Spence |  | 179250 | 141930.15 | 128406.37 | 129551.77 | 113293.69 | 16258.09 | 7848.44 | 121703.33 | 79.2% | 6.06% | 171401.56 | 95.62% | 7848.44 | 7848.44 | 112381.42
25-PC-43993-Int | Timber Gap GIS Mapping | In Progress | Fixed fee | NH Gulf | Javier Rangel |  | 104625 | 76606.42 | 71844.49 | 73760.62 | 73760.62 | 0 | 0 | 73760.62 | 73.2% | 0% | 104625 | 100% | 0 | 0 | 68548.8
25-PC-44046-Int | Kestrel Butte Section 106 Consultation | In Progress | Fixed fee | NH Gulf | Randy Cantu |  | 1201125 | 1201125 | 1201125 | 826974.56 | 826974.56 | 0 | 0 | 826974.56 | 100% | 0% | 1201125 | 100% | 0 | 0 | 0
25-PC-44140 | Stone Mill Archaeological Testing | In Progress | Fixed fee | NH Gulf | Tonya Spence |  | 562125 | 560663.47 | 490533.94 | 376117.84 | 376117.84 | 0 | 328088.88 | 48028.96 | 99.7% | 87.23% | 234036.12 | 41.63% | 281535.86 | 0 | 420942.86
25-PC-44140-Int | Stone Mill Archaeological Testing | In Progress | Fixed fee | NH Gulf | Tonya Spence |  | 0 | 0 | 0 | 0 | 0 | 0 | 47044.07 | -47044.07 | 0% | 0% | -47044.07 | 0% | 47044.07 | 47044.07 | 0
25-PC-44186-Int | Falcon Mesa Section 106 Consultation | In Progress | Fixed fee | NH Gulf | Randy Cantu |  | 2013750 | 1282557.38 | 1282557.38 | 1268058.38 | 1268058.38 | 0 | 0 | 1268058.38 | 63.7% | 0% | 2013750 | 100% | 0 | 0 | 157273.88
25-PC-44198-Int | Task Order 2: Redbud Highway Widening GIS Mapping | In Progress | Time and material | NH Gulf | Susan Wilkins |  | 116625 | 116625 | 115960.73 | 67253.02 | 49184.1 | 18068.92 | 463.49 | 66789.53 | 100% | 0.69% | 116161.51 | 99.6% | 463.49 | 463.49 | 110012.85
26-PC-43874-Int | Oak Terrace Cell Tower - Class III Survey | In Progress | Fixed fee | NH Gulf | Justin Mejia |  | 270375 | 0 | 0 | 194967.41 | 194967.41 | 0 | 0 | 194967.41 | 0% | 0% | 270375 | 100% | 0 | 0 | 0
26-PC-43915-Int | Task Order 5: Twin Buttes Bridge Replacement Phase I Survey | In Progress | Fixed fee | NH Gulf | Javier Rangel |  | 758250 | 4625.33 | 1168.46 | 667260 | 667260 | 0 | 4074.29 | 663185.71 | 0.6% | 0.61% | 754175.71 | 99.46% | 4074.29 | 4074.29 | 1168.46
26-PC-43927-Int | On-Call: Millbrook Cell Tower Architectural History Survey | In Progress | Time and material | NH Gulf | Susan Wilkins |  | 225000 | 13275.94 | 5298.26 | 147504.9 | 134607.56 | 12897.34 | 1125.9 | 146379 | 5.9% | 0.76% | 223874.1 | 99.5% | 1125.9 | 1125.9 | 5298.26
26-PC-43961-Int | On-Call: Sparrow Hill Fiber Route Architectural History Survey | In Progress | Fixed fee | NH Gulf | Vanessa Duarte |  | 992250 | 445421.03 | 369694.46 | 793601.55 | 793601.55 | 0 | 45153.06 | 748448.49 | 44.9% | 5.69% | 947096.94 | 95.45% | 45153.06 | 45153.06 | 369694.46
26-PC-43979-Int | Pine Hollow Harbor Dredging - Historic Resources Evaluation | In Progress | Fixed fee | NH Gulf | Justin Mejia |  | 369375 | 0 | 0 | 272783.44 | 272783.44 | 0 | 0 | 272783.44 | 0% | 0% | 369375 | 100% | 0 | 0 | 0
26-PC-43986-Int | Sage Flat Airport Apron Architectural History Survey | In Progress | Time and material | NH Gulf | Justin Mejia |  | 828000 | 820392.19 | 732577.5 | 550123.2 | 550123.2 | 0 | 35551.69 | 514571.51 | 99.1% | 6.46% | 792448.31 | 95.71% | 35551.69 | 35551.69 | 732577.5
26-PC-44007-Int | Goldfinch Battery Storage Architectural History Survey | In Progress | Time and material | NH Gulf | Randy Cantu |  | 850875 | 55462.5 | 55462.5 | 561747.68 | 561747.68 | 0 | 0 | 561747.68 | 6.5% | 0% | 850875 | 100% | 0 | 0 | 55462.5
26-PC-44050-Int | On-Call: Hawk Point Canal Lining Archaeological Testing | In Progress | Fixed fee | NH Gulf | Vanessa Duarte |  | 2514000 | 140029.8 | 82400.4 | 1789465.2 | 1789465.2 | 0 | 25753.58 | 1763711.62 | 5.6% | 1.44% | 2488246.42 | 98.98% | 25753.58 | 25753.58 | 82400.4
26-PC-44072-Int | Oak Terrace Water Main GIS Mapping | In Progress | Fixed fee | NH Gulf | Susan Wilkins |  | 398250 | 207926.33 | 181439.63 | 298010.48 | 298010.48 | 0 | 3846.57 | 294163.91 | 52.2% | 1.29% | 394403.43 | 99.03% | 3846.57 | 3846.57 | 181439.63
26-PC-44090-Int | Eagle Bend Phase I Survey | In Progress | Time and material | NH Gulf | Tonya Spence |  | 23625 | 3902.81 | 852.37 | 16515.6 | 12247.61 | 4267.99 | 0 | 16515.6 | 16.5% | 0% | 23625 | 100% | 0 | 0 | 852.37
26-PC-44173-Int | Timber Gap Harbor Dredging - Section 106 Consultation | In Progress | Fixed fee | NH Gulf | Susan Wilkins |  | 602250 | 109489.05 | 82253.74 | 416395.65 | 416395.65 | 0 | 16938.33 | 399457.32 | 18.2% | 4.07% | 585311.67 | 97.19% | 16938.33 | 16938.33 | 82253.74
26-PC-44201-Int | Plover Cove Section 106 Consultation | In Progress | Time and material | NH Gulf | Javier Rangel |  | 620250 | 251981.25 | 226035.56 | 432252.22 | 432252.22 | 0 | 13501.45 | 418750.77 | 40.6% | 3.12% | 606748.55 | 97.82% | 13501.45 | 13501.45 | 226035.56
26-PC-44220-Int | Dove Canyon GIS Mapping | In Progress | Time and material | NH Gulf | Justin Mejia |  | 223875 | 29105.62 | 20346.45 | 178629.86 | 178629.86 | 0 | 0 | 178629.86 | 13% | 0% | 223875 | 100% | 0 | 0 | 20346.45
26-PC-44256-Int | On-Call: Twin Buttes Rail Siding Environmental Review Support | In Progress | Fixed fee | NH Gulf | Susan Wilkins |  | 3040125 | 1205409.56 | 1063502.62 | 2155752.64 | 2155752.64 | 0 | 0 | 2155752.64 | 39.6% | 0% | 3040125 | 100% | 0 | 0 | 1063502.62
26-PC-44256 | On-Call: Twin Buttes Rail Siding Environmental Review Support | In Progress | Fixed fee | NH Gulf | Susan Wilkins |  | 0 | 0 | 0 | 0 | 0 | 0 | 75326.97 | -75326.97 | 0% | 0% | -75326.97 | 0% | 75326.97 | 75326.97 | 0
26-PC-44290-Int | On-Call: Larkspur Park Improvements GIS Mapping | In Progress | Fixed fee | NH Gulf | Justin Mejia |  | 772875 | 163694.92 | 144801.34 | 600292.01 | 600292.01 | 0 | 20648.83 | 579643.18 | 21.2% | 3.44% | 752226.17 | 97.33% | 20648.83 | 20648.83 | 144801.34
26-PC-44302-Int | Dove Canyon Cell Tower - Built Environment Survey | In Progress | Fixed fee | NH Gulf | Vanessa Duarte |  | 338250 | 150385.95 | 107584.76 | 252503.62 | 252503.62 | 0 | 13418.18 | 239085.44 | 44.5% | 5.31% | 324831.82 | 96.03% | 13418.18 | 13418.18 | 107584.76
OVHD |  | In Progress |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 96055.19 | -96055.19 | 0% | 0% | -96055.19 | 0% | 96055.19 | 96055.19 | 0
Total All Other Projects | Total All Other Projects | [5 empty] | 23041125 | 11458864.38 | 10810941.74 | 15995820.44 | 15607417.34 | 388403.1 | 747226.03 | 15248594.41 | 49.7% | 4.67% | 22293898.97 | 96.76% | 700673.01 | 419137.15 | 4457370.92
All Projects | All Projects | [5 empty] | 23041125 | 11458864.38 | 10810941.74 | 15995820.44 | 15607417.34 | 388403.1 | 747226.03 | 15248594.41 | 49.7% | 4.67% | 22293898.97 | 96.76% | 700673.01 | 419137.15 | 4457370.92