## Project Details
Projects with Task Overruns >5%
As of September 26, 2026
Layout check OK ¦ 1,219 projects ¦ 289 over 5%
Project ID | Project Name | Billing Type | Project Status | Location Name | Project Manager Name | Contract Value | Revised Budget | Total Cost ITD | Total Task Overrun | Task Overrun % | > 5% | Cost % Complete | Budgeted Hours | Actual Hours | Task Overrun Hours | Hours Overrun %
23-PC-30060 | Lone Pine Pipeline - Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | Big Sky | Javier Estrada | 397800 | 312273 | 376882.23 | 64609.23 | 20.69% | 1 | 100% | 3891 | 5938.27 | 2047.27 | 52.62%
23-PC-30163 | Timber Gap Phase I Survey | Fixed fee | Completed | Big Sky | Bob Frye | 33300 | 22510.8 | 22797.57 | 286.77 | 1.274% | 0 | 100% | 299 | 428 | 129 | 43.14%
23-PC-30307 | Quail Run Wastewater Plant Cultural Resources Assessment | Fixed fee | Transferred Entity | Big Sky | Javier Estrada | 240100 | 136256.75 | 89412.87 | 0 | 0% | 0 | 65.62% | 1118 | 1504 | 386 | 34.53%
23-PC-30372 | Phase I: Lone Pine Reservoir Architectural History Survey | Time and material | In Progress | Big Sky | Bob Frye | 27100 | 19864.3 | 11402.28 | 0 | 0% | 0 | 57.4% | 357 | 175.18 | 0 | 0%
23-PC-30543 | Phase III: Riverbend Rail Siding Maritime Remote Sensing Survey | Fixed fee | In Progress | Big Sky | Javier Estrada | 320600 | 255628.66 | 180013.95 | 0 | 0% | 0 | 70.42% | 2538 | 2749.93 | 240.79 | 9.487%
23-PC-30644 | Phase II: Millbrook Wastewater Plant Data Recovery | Time and material | In Progress | Bluegrass | Alice Galloway | 108100 | 72102.7 | 46653.03 | 0 | 0% | 0 | 64.7% | 854 | 762.32 | 0 | 0%
23-PC-30667 | North Fork Canal Lining Data Recovery | Time and material | Completed | Bluegrass | Kiara Gillespie | 210500 | 144045.15 | 154304.59 | 10259.44 | 7.122% | 1 | 100% | 2053 | 2749.41 | 696.41 | 33.92%
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | Time and material | In Progress | Bluegrass | Kiara Gillespie | 49800 | 34501.44 | 28656.36 | 0 | 0% | 0 | 83.06% | 399 | 488.25 | 89.25 | 22.37%
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Time and material | Cost Tracking on Closed Project | Bluegrass | Alice Galloway | 86200 | 58650.48 | 61318.15 | 2667.67 | 4.548% | 0 | 100% | 0 | 871.79 | 0 | 0%
23-PC-30933 | Lantern Bay Water Main - Phase I Survey | Time and material | On Hold | Bluegrass | Kiara Gillespie | 703200 | 461299.2 | 382697.29 | 0 | 0% | 0 | 82.96% | 9230 | 6044.67 | 0 | 0%
23-PC-31003 | Windmill Flat Environmental Review Support | Fixed fee | In Progress | Bluegrass | Kiara Gillespie | 19300 | 10568.68 | 8458.51 | 0 | 0% | 0 | 80.03% | 0 | 175.14 | 0 | 0%
23-PC-31042 | Stone Mill Historic Resources Evaluation | Time and material | In Progress | Cascade | Donald Lutz | 299700 | 202896.9 | 147919.88 | 0 | 0% | 0 | 72.9% | 2753 | 2701.72 | 0 | 0%
23-PC-31076 | Wildrye Rail Siding - Archaeological Testing | Time and material | Final Reporting/Review | Cascade | Cassidy Gay | 95100 | 65561.94 | 41531.43 | 0 | 0% | 0 | 63.35% | 720 | 688.12 | 0 | 0%
23-PC-31344 | Timber Gap Battery Storage Archaeological Testing | Fixed fee | In Progress | Cascade | Cassidy Gay | 331600 | 264351.52 | 155057.32 | 0 | 0% | 0 | 58.66% | 0 | 2647.45 | 0 | 0%
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | Time and material | In Progress | Cascade | Donald Lutz | 255700 | 168225.03 | 202903.45 | 34678.42 | 20.61% | 1 | 100% | 3342 | 3139.64 | 85.77 | 2.566%
23-PC-31389 | Juniper Wash Highway Widening Archaeological Testing | Time and material | Final Billing/Invoice | Cascade | Preston Duarte | 30700 | 20958.95 | 27246.63 | 6287.68 | 30% | 1 | 100% | 541 | 482.22 | 5.71 | 1.055%
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | Fixed fee | In Progress | Cascade | Jeff Spence | 108000 | 82404 | 58391.35 | 0 | 0% | 0 | 70.86% | 1308 | 1111.4 | 22.37 | 1.71%
23-PC-31604 | Timber Gap Pipeline - Cultural Resources Assessment | Time and material | Final Billing/Invoice | Cascade | Cassidy Gay | 180800 | 124607.36 | 161989.57 | 37382.21 | 30% | 1 | 100% | 1897 | 2828.48 | 931.48 | 49.1%
23-PC-31765 | Saltgrass Phase I Survey | Fixed fee | Final Reporting/Review | Cascade | Jean Cooke | 32700 | 27114.84 | 15513.28 | 0 | 0% | 0 | 57.21% | 0 | 253.02 | 0 | 0%
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | Fixed fee | In Progress | Cascade | Gene Nixon | 34800 | 28779.6 | 31540.76 | 2761.16 | 9.594% | 1 | 100% | 367 | 464.59 | 97.59 | 26.59%
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | Fixed fee | In Progress | Cascade | Jeff Spence | 460600 | 390957.28 | 295973.9 | 0 | 0% | 0 | 75.7% | 6183 | 4647.8 | 0 | 0%
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | Cascade | Jeff Spence | 175300 | 93481.01 | 112759.17 | 19278.16 | 20.62% | 1 | 100% | 0 | 1811.68 | 0 | 0%
23-PC-31944 | Phase I: Goldfinch Airport Apron Class III Survey | Fixed fee | Final Billing/Invoice | Cascade | Preston Duarte | 76000 | 54636.4 | 67585.21 | 12948.81 | 23.7% | 1 | 100% | 626 | 1089.18 | 463.18 | 73.99%
23-PC-31976 | Foxglove Cell Tower GIS Mapping | Time and material | Completed | Chesapeake | Jason Oconnor | 72100 | 51263.1 | 37578.85 | 0 | 0% | 0 | 73.31% | 698 | 610.57 | 0 | 0%
23-PC-32015 | Copper Flats Harbor Dredging - Class III Survey | Fixed fee | In Progress | Chesapeake | Jason Oconnor | 89300 | 65024.25 | 29508.22 | 0 | 0% | 0 | 45.38% | 852 | 448.09 | 0 | 0%
23-PC-32135 | Sage Flat Levee Repair Architectural History Survey | Fixed fee | Final Billing/Invoice | Chesapeake | Bryan Mann | 171600 | 128744.02 | 90120.81 | 0 | 0% | 0 | 70% | 0 | 1585.82 | 0 | 0%
23-PC-32278 | Coyote Springs Highway Widening Paleontological Monitoring | Time and material | Lab/Curation | Chesapeake | Ian Maddox | 3500 | 2281.3 | 1738.97 | 0 | 0% | 0 | 76.23% | 46 | 24 | 0 | 0%
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | Fixed fee | In Progress | Chesapeake | Sandy Kerr | 149100 | 111109.32 | 99032.78 | 0 | 0% | 0 | 89.13% | 1506 | 2324.85 | 818.85 | 54.37%
23-PC-32443 | Tamarack Battery Storage - Cultural Resources Monitoring | Time and material | In Progress | Chesapeake | Bryan Mann | 152600 | 107415.14 | 63511.76 | 173.12 | 0.1612% | 0 | 58.97% | 1030 | 1074.77 | 79.34 | 7.703%
23-PC-32474 | Slate Ridge Cell Tower - Phase I Survey | Fixed fee | Completed | Chesapeake | Ian Maddox | 52900 | 42882.38 | 44741.34 | 1858.96 | 4.335% | 0 | 100% | 745 | 746.66 | 29.66 | 3.981%
23-PC-32520 | Tamarack Battery Storage GIS Mapping | Time and material | Lab/Curation | Chesapeake | Ian Maddox | 1116300 | 767567.88 | 601405.25 | 0 | 0% | 0 | 78.35% | 8561 | 7720.02 | 59.42 | 0.6941%
23-PC-32635 | Rushgrass Draw Curation | Time and material | Cost Tracking on Closed Project | Chesapeake | Jason Oconnor | 36800 | 24644.96 | 27323.95 | 2678.99 | 10.87% | 1 | 100% | 421 | 362.31 | 8.95 | 2.126%
23-PC-33001 | Heron Marsh Environmental Review Support | Time and material | In Progress | Front Range | Dean Velazquez | 356400 | 221573.88 | 127558.9 | 0 | 0% | 0 | 57.57% | 3325 | 2150.12 | 0 | 0%
23-PC-33043 | Phase II: Copper Flats Fiber Route Data Recovery | Fixed fee | Completed | Front Range | Reginald Vargas | 508800 | 282312.26 | 340194.25 | 57881.99 | 20.5% | 1 | 100% | 4078 | 5189.02 | 1111.02 | 27.24%
23-PC-33070 | Meadowlark Curation | Fixed fee | In Progress | Front Range | Reginald Vargas | 55100 | 34299.75 | 28871.53 | 0 | 0% | 0 | 84.17% | 461 | 487.09 | 32.49 | 7.048%
23-PC-33151 | Sandpiper Class III Survey | Fixed fee | In Progress | Front Range | Kimberly Daugherty | 637100 | 497638.81 | 422546.87 | 0 | 0% | 0 | 84.91% | 6012 | 6445.55 | 433.55 | 7.211%
23-PC-33193 | Falcon Mesa Transmission Line - Environmental Review Support | Fixed fee | On Hold | Front Range | Devon Pitts | 10900 | 8531.43 | 5992.26 | 0 | 0% | 0 | 70.24% | 68 | 97.56 | 29.56 | 43.47%
23-PC-33218 | Plover Cove Class III Survey | Time and material | On Hold | Front Range | Jeremy Tran | 57000 | 36256.05 | 29341.56 | 0 | 0% | 0 | 80.93% | 422 | 401.36 | 0 | 0%
23-PC-33299 | Fern Valley Fiber Route - Curation | Fixed fee | On Hold | Front Range | Reginald Vargas | 71300 | 47214.86 | 37033.01 | 0 | 0% | 0 | 78.44% | 408 | 521.71 | 113.71 | 27.87%
23-PC-33395 | Lone Pine Environmental Review Support | Time and material | Final Billing/Invoice | Front Range | Jeremy Tran | 186900 | 122438.19 | 159169.65 | 36731.46 | 30% | 1 | 100% | 824 | 2697.57 | 1873.57 | 227.4%
23-PC-33428 | Hackberry Bend Archaeological Testing | Fixed fee | Final Billing/Invoice | Front Range | Reginald Vargas | 293900 | 208874.73 | 271537.15 | 62662.42 | 30% | 1 | 100% | 3332 | 4211.55 | 879.55 | 26.4%
23-PC-33471 | Sandpiper Park Improvements - Environmental Review Support | Time and material | Lab/Curation | Front Range | Devon Pitts | 113200 | 80813.48 | 61581.06 | 0 | 0% | 0 | 76.2% | 0 | 907.79 | 0 | 0%
23-PC-33551 | Heron Marsh Airport Apron GIS Mapping | Time and material | Final Reporting/Review | Front Range | Reginald Vargas | 95400 | 62019.54 | 47726 | 0 | 0% | 0 | 76.95% | 0 | 729.53 | 0 | 0%
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | Fixed fee | In Progress | Front Range | Kimberly Daugherty | 21600 | 15245.28 | 16551.79 | 1306.51 | 8.57% | 1 | 100% | 0 | 280.37 | 0 | 0%
23-PC-33605 | Rushgrass Draw Highway Widening - Class III Survey | Fixed fee | Completed | Front Range | Kimberly Daugherty | 309100 | 188427.36 | 187603 | 0 | 0% | 0 | 99.56% | 3432 | 3261.72 | 0 | 0%
23-PC-33695 | On-Call: Windmill Flat Highway Widening Phase I Survey | Fixed fee | On Hold | Great Lakes | Jeff Pugh | 42600 | 34191.4 | 19060.38 | 0 | 0% | 0 | 55.75% | 408 | 243.63 | 0 | 0%
23-PC-33803 | Willow Springs Pipeline Cultural Resources Assessment | Time and material | On Hold | Great Lakes | Brendan Padilla | 66400 | 40244.88 | 20144.95 | 0 | 0% | 0 | 50.06% | 0 | 331.43 | 0 | 0%
23-PC-33858 | Phase II: Cedar Hollow Pipeline Section 106 Consultation | Fixed fee | Final Billing/Invoice | Great Lakes | Jeff Pugh | 68500 | 46737.55 | 44645.58 | 0 | 0% | 0 | 95.52% | 823 | 650.83 | 0 | 0%
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | Time and material | In Progress | Great Lakes | Jeff Pugh | 300600 | 219257.64 | 176674.59 | 0 | 0% | 0 | 80.58% | 0 | 2278.09 | 0 | 0%
23-PC-33998 | Phase II: Granite Pass Reservoir Class III Survey | Time and material | In Progress | Great Lakes | Nathan Lambert | 238800 | 156891.6 | 95556.7 | 0 | 0% | 0 | 60.91% | 0 | 1466.53 | 0 | 0%
23-PC-34054 | Slate Ridge Wastewater Plant - Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | Great Lakes | Angelica Cervantes | 99000 | 67052.7 | 66496.14 | 0 | 0% | 0 | 99.17% | 0 | 844.11 | 0 | 0%
23-PC-34135 | Falcon Mesa Architectural History Survey | Fixed fee | Completed | Great Lakes | Kathleen Galvan | 108800 | 84537.6 | 97602.11 | 13064.51 | 15.45% | 1 | 100% | 0 | 1312.22 | 0 | 0%
23-PC-34171 | Timber Gap Rail Siding - Built Environment Survey | Time and material | In Progress | Great Lakes | Jeff Pugh | 221100 | 154858.44 | 75735.59 | 0 | 0% | 0 | 48.91% | 0 | 1017.51 | 0 | 0%
23-PC-34229 | Creosote Draw Mixed-Use Development Paleontological Monitoring | Time and material | In Progress | Great Lakes | Jeff Pugh | 48800 | 34427.85 | 25157.23 | 0 | 0% | 0 | 73.07% | 330 | 390.22 | 63.39 | 19.21%
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | Time and material | In Progress | Great Lakes | Kathleen Galvan | 373100 | 247626.47 | 184659.6 | 0 | 0% | 0 | 74.57% | 3361 | 2842.64 | 0 | 0%
23-PC-34403 | Plover Cove Built Environment Survey | Time and material | In Progress | Great Lakes | Kathleen Galvan | 46200 | 30187.08 | 23628.2 | 0 | 0% | 0 | 78.27% | 397 | 303.4 | 0 | 0%
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | Fixed fee | In Progress | Great Lakes | Angelica Cervantes | 477000 | 333756.9 | 243019.93 | 0 | 0% | 0 | 72.81% | 2495 | 3421.87 | 926.87 | 37.15%
23-PC-34473 | Aspen Ridge Cell Tower Phase I Survey | Time and material | In Progress | Great Lakes | Leonard Mejia | 52300 | 36353.73 | 23508.92 | 0 | 0% | 0 | 64.67% | 459 | 336.91 | 0 | 0%
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Time and material | Final Reporting/Review | Great Lakes | Geoffrey Fernandez | 70000 | 50246 | 45814.41 | 0 | 0% | 0 | 91.18% | 424 | 642.37 | 218.37 | 51.5%
23-PC-34522 | Foxglove GIS Mapping | Time and material | In Progress | Great Lakes | Brendan Padilla | 192200 | 131503.24 | 75113.75 | 0 | 0% | 0 | 57.12% | 1192 | 1064.53 | 0 | 0%
23-PC-34567 | Foxglove School Campus Phase II Testing | Fixed fee | On Hold | Great Lakes | Brendan Padilla | 17900 | 14103.41 | 7134.41 | 0 | 0% | 0 | 50.59% | 0 | 95.93 | 0 | 0%
23-PC-34745 | Slate Ridge Battery Storage Environmental Review Support | Fixed fee | In Progress | Great Lakes | Robin Mercado | 614200 | 440258.56 | 292800.8 | 0 | 0% | 0 | 66.51% | 3354 | 3980.82 | 626.82 | 18.69%
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | Fixed fee | In Progress | Gulf Coast | Sean Jennings | 46100 | 31721.41 | 22343.25 | 0 | 0% | 0 | 70.44% | 415 | 392.52 | 3.6 | 0.8675%
23-PC-34811 | Task Order 2: Saltgrass Airport Apron Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | Gulf Coast | Courtney Daugherty | 112600 | 80883.68 | 66744.54 | 0 | 0% | 0 | 82.52% | 0 | 1300.45 | 0 | 0%
23-PC-34826 | Task Order 13: Foxglove Canal Lining Cultural Resources Monitoring | Time and material | In Progress | Gulf Coast | Bernard Erickson | 168500 | 109642.95 | 61763.3 | 0 | 0% | 0 | 56.33% | 1384 | 1139.36 | 0 | 0%
23-PC-34891 | Saltgrass GIS Mapping | Fixed fee | Final Billing/Invoice | Gulf Coast | Bernard Erickson | 26600 | 20891.64 | 16379.36 | 0 | 0% | 0 | 78.4% | 237 | 269.54 | 32.54 | 13.73%
23-PC-34902 | Sumac Ridge Built Environment Survey | Time and material | Final Reporting/Review | Gulf Coast | Sean Jennings | 37000 | 26270 | 17779.33 | 0 | 0% | 0 | 67.68% | 550 | 358.24 | 0 | 0%
23-PC-34939 | Maple Fork Maritime Remote Sensing Survey | Time and material | In Progress | Gulf Coast | Bernard Erickson | 145800 | 104172.04 | 74711.94 | 0 | 0% | 0 | 71.72% | 1587 | 1482.45 | 46.56 | 2.934%
23-PC-34947 | Aspen Ridge Cell Tower Architectural History Survey | Fixed fee | In Progress | Gulf Coast | Wyatt Erickson | 285900 | 199615.38 | 134588.76 | 0 | 0% | 0 | 67.42% | 2885 | 2202.8 | 0 | 0%
23-PC-35003 | Creosote Draw Archaeological Testing | Time and material | In Progress | Gulf Coast | Bernard Erickson | 187900 | 127170.72 | 85671.58 | 0 | 0% | 0 | 67.37% | 0 | 1529.94 | 0 | 0%
23-PC-35098 | On-Call: Larkspur Reservoir Environmental Review Support | Fixed fee | Final Billing/Invoice | Gulf Coast | Sean Jennings | 120000 | 100560 | 92975.9 | 0 | 0% | 0 | 92.46% | 1765 | 1675.6 | 8.25 | 0.4674%
23-PC-35126 | Falcon Mesa Rail Siding Built Environment Survey | Time and material | In Progress | Gulf Coast | Wyatt Erickson | 273100 | 197014.34 | 105573.3 | 0 | 0% | 0 | 53.59% | 1974 | 1599.81 | 0 | 0%
23-PC-35176 | Plover Cove Mine Expansion Section 106 Consultation | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 74700 | 53388.09 | 35373.34 | 0 | 0% | 0 | 66.26% | 0 | 565 | 0 | 0%
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | Fixed fee | In Progress | Gulf Coast | Wyatt Erickson | 407900 | 321139.67 | 238828.33 | 0 | 0% | 0 | 74.37% | 4342 | 4982.87 | 794.96 | 18.31%
23-PC-35425 | Yarrow Point Trail - GIS Mapping | Time and material | Lab/Curation | High Desert | Eileen Poole | 24000 | 15998.4 | 13187.18 | 0 | 0% | 0 | 82.43% | 0 | 196.12 | 0 | 0%
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | Time and material | In Progress | High Desert | Jody Wang | 116200 | 87219.72 | 78190.34 | 0 | 0% | 0 | 89.65% | 1824 | 1404.12 | 0 | 0%
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | Fixed fee | In Progress | High Desert | Eileen Poole | 11400 | 8206.86 | 6249.46 | 0 | 0% | 0 | 76.15% | 123 | 125.59 | 9.6 | 7.805%
23-PC-35568 | Phase II: Coyote Springs Wind Farm Environmental Review Support | Fixed fee | In Progress | High Desert | Bridget Maddox | 253600 | 168365.04 | 95853.64 | 0 | 0% | 0 | 56.93% | 2504 | 1699.14 | 0 | 0%
23-PC-35682 | Lantern Bay Class III Survey | Fixed fee | In Progress | High Desert | Eileen Poole | 290400 | 252938.4 | 241578.4 | 0 | 0% | 0 | 95.51% | 0 | 3585.38 | 0 | 0%
23-PC-35715 | Saltgrass Cell Tower Historic Resources Evaluation | Fixed fee | On Hold | High Desert | Jody Wang | 44500 | 33802.2 | 28157.72 | 0 | 0% | 0 | 83.3% | 608 | 465.18 | 0 | 0%
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | Fixed fee | In Progress | High Desert | Kathy Hurley | 114600 | 77893.62 | 71277.07 | 0 | 0% | 0 | 91.51% | 1250 | 1265.51 | 15.51 | 1.241%
23-PC-36108 | Pebble Beach Road Maritime Remote Sensing Survey | Fixed fee | On Hold | High Desert | Jody Wang | 50200 | 40154.98 | 26350.13 | 0 | 0% | 0 | 65.62% | 555 | 468.12 | 0 | 0%
23-PC-36231 | Phase II: Rushgrass Draw Airport Apron GIS Mapping | Time and material | Final Billing/Invoice | Island | Briana Melton | 436500 | 298453.59 | 384508.62 | 86055.03 | 28.83% | 1 | 100% | 3577 | 4852.51 | 1275.51 | 35.66%
23-PC-36385 | On-Call: Cedar Hollow Transmission Line Paleontological Monitoring | Time and material | In Progress | Island | Maurice Dodson | 392900 | 262008.61 | 185677.7 | 0 | 0% | 0 | 70.87% | 2505 | 2771.74 | 266.74 | 10.65%
23-PC-36422 | Hawk Point Phase I Survey | Time and material | In Progress | Island | Joan Mathis | 50700 | 36579.06 | 37409.59 | 830.53 | 2.271% | 0 | 100% | 365 | 523.59 | 158.59 | 43.45%
23-PC-36426 | On-Call: Fern Valley Wastewater Plant Environmental Review Support | Fixed fee | Final Billing/Invoice | Island | Maurice Dodson | 76300 | 52730.93 | 51196.02 | 0 | 0% | 0 | 97.09% | 585 | 575.87 | 92.1 | 15.74%
23-PC-36530 | Lone Pine Architectural History Survey | Time and material | In Progress | Island | Joan Mathis | 141100 | 102823.29 | 97024.26 | 0 | 0% | 0 | 94.36% | 1480 | 1449.38 | 44.46 | 3.004%
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | Fixed fee | In Progress | Lakeshore | Jeanette Riddle | 201000 | 151513.8 | 128322.24 | 0 | 0% | 0 | 84.69% | 1290 | 1729.11 | 439.11 | 34.04%
23-PC-36734 | Raven Rock Curation | Fixed fee | In Progress | Lakeshore | Terrence Gillespie | 38600 | 27753.4 | 26089.14 | 9.9 | 0.03567% | 0 | 93.97% | 337 | 473.52 | 136.52 | 40.51%
23-PC-36776 | On-Call: Twin Buttes Trail Phase I Survey | Time and material | In Progress | Hill Country | Danielle Villanueva | 457300 | 338564.86 | 214892.1 | 0 | 0% | 0 | 63.47% | 4554 | 3122.61 | 0 | 0%
23-PC-37105 | Foxglove Housing Development - Data Recovery | Fixed fee | In Progress | Hill Country | Theresa Fernandez | 110800 | 80165.21 | 60019.33 | 1791.29 | 2.234% | 0 | 72.64% | 583 | 524.96 | 40.63 | 6.969%
23-PC-37245 | Rushgrass Draw Wind Farm Archaeological Testing | Fixed fee | In Progress | Hill Country | Gail Meza | 425700 | 306248.58 | 171495.1 | 0 | 0% | 0 | 56% | 2792 | 2101.79 | 0 | 0%
23-PC-37301 | Coyote Springs Highway Widening Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | Hill Country | Glen Delacruz | 71900 | 50775.78 | 52725.53 | 1949.75 | 3.84% | 0 | 100% | 466 | 637.88 | 171.88 | 36.88%
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | Fixed fee | In Progress | Piedmont | Maria Parrish | 44500 | 35070.45 | 25141.75 | 0 | 0% | 0 | 71.69% | 524 | 367.65 | 0 | 0%
23-PC-37590 | On-Call: Rushgrass Draw Water Main Environmental Review Support | Fixed fee | In Progress | Piedmont | Annette Vaughan | 46500 | 36232.8 | 22148.93 | 0 | 0% | 0 | 61.13% | 387 | 325.63 | 1.26 | 0.3256%
23-PC-37642 | Quail Run Solar Curation | Fixed fee | Final Billing/Invoice | Piedmont | Megan Pineda | 286500 | 185422.8 | 174327.06 | 0 | 0% | 0 | 94.02% | 2263 | 2494.87 | 231.87 | 10.25%
23-PC-37648 | Phase III: Thistle Down Mixed-Use Development Phase I Survey | Time and material | Final Billing/Invoice | Piedmont | Annette Vaughan | 49100 | 32995.2 | 28734.29 | 0 | 0% | 0 | 87.09% | 389 | 525.22 | 136.22 | 35.02%
23-PC-37740 | Sandpiper Trail Archaeological Testing | Fixed fee | Final Billing/Invoice | Piedmont | Megan Pineda | 33900 | 20068.8 | 14048.16 | 0 | 0% | 0 | 70% | 424 | 229.41 | 0 | 0%
23-PC-37763 | Bramble Creek School Campus - Environmental Review Support | Time and material | In Progress | Piedmont | Megan Pineda | 35000 | 25056.5 | 15144.42 | 0 | 0% | 0 | 60.44% | 380 | 197.62 | 0 | 0%
23-PC-38089 | Lone Pine Wastewater Plant - Phase I Survey | Fixed fee | In Progress | Prairie | Sherry Lloyd | 110100 | 84001.75 | 57321.44 | 0 | 0% | 0 | 68.24% | 1984 | 1168.25 | 0 | 0%
23-PC-38159 | Badger Hollow Data Recovery | Time and material | Completed | Prairie | Sherry Lloyd | 8000 | 5319.2 | 6409.99 | 1090.79 | 20.51% | 1 | 100% | 0 | 116.97 | 0 | 0%
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | Time and material | In Progress | Prairie | Sherry Lloyd | 128200 | 90073.32 | 73724.08 | 0 | 0% | 0 | 81.85% | 1080 | 1573.7 | 493.7 | 45.71%
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | Prairie | Sherry Lloyd | 79800 | 53434.08 | 38783.48 | 0 | 0% | 0 | 72.58% | 660 | 627.71 | 31.91 | 4.835%
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | Fixed fee | In Progress | Red Rock | Shelia Horne | 67700 | 44688.77 | 37332.05 | 0 | 0% | 0 | 83.54% | 682 | 698.21 | 90.38 | 13.25%
23-PC-38520 | On-Call: Larkspur Park Improvements Built Environment Survey | Time and material | In Progress | Red Rock | Marisa Odom | 148500 | 97074.45 | 56211.48 | 0 | 0% | 0 | 57.91% | 1080 | 1005.81 | 0 | 0%
23-PC-38666 | Tamarack Paleontological Monitoring | Fixed fee | In Progress | Red Rock | Bruce Suarez | 390300 | 243898.47 | 132781.77 | 0 | 0% | 0 | 54.44% | 3241 | 2548.85 | 0 | 0%
23-PC-38759 | Saltgrass Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | Red Rock | Tina Aguirre | 52400 | 36847.68 | 40372.44 | 3524.76 | 9.566% | 1 | 100% | 626 | 757.87 | 131.87 | 21.07%
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | Fixed fee | In Progress | Red Rock | Tina Aguirre | 109400 | 83089.3 | 66048.24 | 0 | 0% | 0 | 79.49% | 1032 | 997.41 | 0 | 0%
23-PC-39011 | Fern Valley Solar Curation | Time and material | Final Billing/Invoice | Red Rock | Tina Aguirre | 189300 | 142126.44 | 140658.85 | 0 | 0% | 0 | 98.97% | 2303 | 2106.23 | 71.63 | 3.11%
23-PC-39063 | Task Order 21: Badger Hollow Substation Historic Resources Evaluation | Time and material | Lab/Curation | Red Rock | Lydia Cisneros | 24200 | 17235.24 | 12296.83 | 0 | 0% | 0 | 71.35% | 0 | 250.6 | 0 | 0%
23-PC-39111 | On-Call: Sage Flat Housing Development Section 106 Consultation | Time and material | Final Billing/Invoice | Red Rock | Marisa Odom | 414500 | 281113.9 | 292132.6 | 11018.7 | 3.92% | 0 | 100% | 2736 | 5577.92 | 2841.92 | 103.9%
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | Fixed fee | In Progress | Red Rock | Jeanette Chung | 27800 | 18214.56 | 13614.39 | 0 | 0% | 0 | 74.74% | 232 | 236.47 | 7.51 | 3.237%
23-PC-39280 | Eagle Bend Architectural History Survey | Fixed fee | Final Billing/Invoice | Red Rock | Javier Newman | 122700 | 84258.09 | 74439.03 | 0 | 0% | 0 | 88.35% | 1705 | 1173.77 | 0 | 0%
23-PC-39323 | Silver Lake Battery Storage Class III Survey | Fixed fee | In Progress | Red Rock | Tina Aguirre | 550600 | 444994.92 | 341994.21 | 0 | 0% | 0 | 76.85% | 6352 | 5841.13 | 334.16 | 5.261%
23-PC-39502 | Ember Valley Housing Development - Phase II Testing | Time and material | Final Billing/Invoice | Red Rock | Marisa Odom | 352700 | 238918.98 | 310594.67 | 71675.69 | 30% | 1 | 100% | 3268 | 6065.13 | 2797.13 | 85.59%
23-PC-39608 | Tansy Flat Historic Resources Evaluation | Time and material | Completed | Red Rock | Bruce Suarez | 166700 | 118140.29 | 100389.47 | 0 | 0% | 0 | 84.97% | 0 | 1572.34 | 0 | 0%
23-PC-39840 | Kestrel Butte Cell Tower - Curation | Time and material | In Progress | Red Rock | Bruce Suarez | 237700 | 173575 | 88754.16 | 0 | 0% | 0 | 51.13% | 1867 | 1039.6 | 0 | 0%
23-PC-39856 | Phase II: Thistle Down Transmission Line Historic Resources Evaluation | Fixed fee | Final Reporting/Review | Red Rock | Bruce Suarez | 91300 | 72285.79 | 36987.95 | 0 | 0% | 0 | 51.17% | 1044 | 691.46 | 0 | 0%
23-PC-39857 | Copper Flats Highway Widening - Environmental Review Support | Fixed fee | In Progress | Red Rock | Bruce Suarez | 69000 | 58157.02 | 34016 | 0 | 0% | 0 | 58.49% | 0 | 592.68 | 0 | 0%
23-PC-39918 | Elk Meadow Transmission Line - Data Recovery | Time and material | Completed | Red Rock | Javier Newman | 75300 | 51437.43 | 50643.39 | 0 | 0% | 0 | 98.46% | 711 | 813.45 | 109.15 | 15.35%
23-PC-39996 | Plover Cove Trail - Data Recovery | Fixed fee | On Hold | Red Rock | Bruce Suarez | 611900 | 419273.88 | 272035.22 | 0 | 0% | 0 | 64.88% | 6615 | 4530.24 | 0 | 0%
23-PC-40028 | Phase II: Sumac Ridge Mixed-Use Development Section 106 Consultation | Fixed fee | In Progress | Red Rock | Bruce Suarez | 100900 | 70256.67 | 47284.49 | 0 | 0% | 0 | 67.3% | 0 | 842.74 | 0 | 0%
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | Time and material | In Progress | Red Rock | Javier Newman | 119500 | 80196.45 | 70430.4 | 316.41 | 0.3945% | 0 | 87.43% | 1374 | 1454.34 | 99.21 | 7.221%
23-PC-40150 | Juniper Wash Curation | Time and material | In Progress | Sierra | Benjamin Mathis | 114700 | 73316.24 | 47860.78 | 98.28 | 0.134% | 0 | 65.15% | 1388 | 860.18 | 2.5 | 0.1801%
23-PC-40387 | Copper Flats Trail Paleontological Monitoring | Fixed fee | Lab/Curation | Sierra | Louis Huff | 145000 | 97266 | 55173.29 | 0 | 0% | 0 | 56.72% | 1547 | 936.01 | 0 | 0%
23-PC-40402 | Pebble Beach Road Architectural History Survey | Fixed fee | In Progress | Sierra | Louis Huff | 411600 | 302937.6 | 245232.54 | 0 | 0% | 0 | 80.95% | 3909 | 3815.75 | 0 | 0%
23-PC-40406 | Maple Fork Airport Apron Environmental Review Support | Time and material | In Progress | Sierra | Louis Huff | 60100 | 40631.14 | 33352.18 | 0 | 0% | 0 | 82.09% | 0 | 492.88 | 0 | 0%
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | Fixed fee | In Progress | Sierra | Benjamin Mathis | 53900 | 40910.1 | 29233.55 | 0 | 0% | 0 | 71.46% | 522 | 443.15 | 0 | 0%
23-PC-40493 | Phase III: Quail Run Rail Siding Phase I Survey | Fixed fee | In Progress | Sierra | Benjamin Mathis | 84700 | 57130.15 | 36092.25 | 0 | 0% | 0 | 63.18% | 681 | 605.4 | 0 | 0%
23-PC-40519 | Windmill Flat Mixed-Use Development - Class III Survey | Fixed fee | In Progress | Sierra | Donna Herring | 194700 | 157875.18 | 113693.31 | 0 | 0% | 0 | 72.01% | 1257 | 1697.63 | 440.63 | 35.05%
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Fixed fee | Lab/Curation | Sierra | Louis Huff | 76500 | 58746.94 | 63236.56 | 4489.62 | 7.642% | 1 | 100% | 633 | 958.89 | 325.89 | 51.48%
23-PC-40627 | Ember Valley Solar - Phase I Survey | Fixed fee | In Progress | Sierra | Louis Huff | 71300 | 38273.84 | 23707.44 | 0 | 0% | 0 | 61.94% | 0 | 367.92 | 0 | 0%
23-PC-40688 | Sparrow Hill Historic Resources Evaluation | Time and material | On Hold | Coastal Bend | Jared Choi | 70500 | 43731.15 | 29728.69 | 0 | 0% | 0 | 67.98% | 711 | 464.87 | 0 | 0%
23-PC-40963 | Wildrye Archaeological Testing | Fixed fee | On Hold | Coastal Bend | Diane Daniels | 58000 | 34689.8 | 24226.81 | 0 | 0% | 0 | 69.84% | 334 | 451.83 | 117.83 | 35.28%
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | Time and material | In Progress | Coastal Bend | Steve Rubio | 56300 | 42714.81 | 47948.89 | 5234.08 | 12.25% | 1 | 100% | 676 | 756.99 | 97.48 | 14.42%
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | Fixed fee | In Progress | Coastal Bend | Jared Choi | 33100 | 29128 | 21890.46 | 0 | 0% | 0 | 75.15% | 496 | 371.48 | 0 | 0%
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Fixed fee | Cost Tracking on Closed Project | Coastal Bend | Diane Daniels | 349600 | 221087.04 | 229204.35 | 8117.31 | 3.672% | 0 | 100% | 4274 | 3837.51 | 198.94 | 4.655%
23-PC-41314 | Raven Rock Transmission Line - Maritime Remote Sensing Survey | Fixed fee | In Progress | Coastal Bend | Jared Choi | 38800 | 29503.45 | 21412.36 | 0 | 0% | 0 | 72.58% | 0 | 392.97 | 0 | 0%
23-PC-41361 | Juniper Wash Substation - Cultural Resources Assessment | Time and material | Final Billing/Invoice | Coastal Bend | Alexis Nixon | 240700 | 180645.35 | 201492.26 | 20846.91 | 11.54% | 1 | 100% | 2473 | 3497.11 | 1024.11 | 41.41%
23-PC-41378 | Thistle Down Cultural Resources Assessment | Fixed fee | In Progress | Coastal Bend | Duane Ballard | 170800 | 91151.1 | 50973.67 | 0 | 0% | 0 | 55.92% | 0 | 928.04 | 0 | 0%
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | Fixed fee | Transferred Entity | Coastal Bend | Duane Ballard | 132000 | 108108 | 75830.35 | 0 | 0% | 0 | 70.14% | 0 | 1233.61 | 0 | 0%
23-PC-41429 | Meadowlark Housing Development - Phase II Testing | Time and material | In Progress | Coastal Bend | Duane Ballard | 1924200 | 1334625.12 | 884955.35 | 0 | 0% | 0 | 66.31% | 18838 | 13808.23 | 0 | 0%
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Fixed fee | Lab/Curation | Coastal Bend | Alexis Nixon | 755000 | 444695 | 415325.46 | 0 | 0% | 0 | 93.4% | 6838 | 6017.92 | 21.19 | 0.3099%
23-PC-41613 | Tamarack School Campus Archaeological Testing | Fixed fee | In Progress | Coastal Bend | Steve Rubio | 151900 | 105099.61 | 89014.21 | 0 | 0% | 0 | 84.7% | 1394 | 1426.54 | 170.21 | 12.21%
23-PC-41787 | Copper Flats Phase I Survey | Time and material | Completed | Built Environment | Rickey Salas | 48000 | 31929.6 | 27473.21 | 0 | 0% | 0 | 86.04% | 0 | 385.62 | 0 | 0%
23-PC-41802 | Plover Cove Paleontological Monitoring | Fixed fee | In Progress | Built Environment | Melody Holloway | 102400 | 66672.64 | 43658.58 | 0 | 0% | 0 | 65.48% | 1017 | 623.41 | 0 | 0%
23-PC-41827 | Task Order 9: Dove Canyon Bridge Replacement Section 106 Consultation | Fixed fee | In Progress | Built Environment | Rickey Salas | 646100 | 414881.21 | 241290.96 | 0 | 0% | 0 | 58.16% | 4362 | 3813.52 | 66.3 | 1.52%
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | Time and material | In Progress | Built Environment | Jesse Maynard | 18800 | 12705.04 | 12736.47 | 31.43 | 0.2474% | 0 | 100% | 147 | 200.97 | 53.97 | 36.71%
23-PC-41934 | Sea Oat Bridge Replacement - GIS Mapping | Fixed fee | Final Reporting/Review | Built Environment | Rickey Salas | 364700 | 228812.78 | 131064.99 | 0 | 0% | 0 | 57.28% | 3661 | 2028.97 | 0 | 0%
23-PC-42054 | Task Order 25: Meadowlark Water Main Curation | Time and material | Completed | Built Environment | Rickey Salas | 35600 | 24350.4 | 23894.23 | 0 | 0% | 0 | 98.13% | 265 | 368.59 | 103.59 | 39.09%
23-PC-42154 | Task Order 25: Goldfinch School Campus Section 106 Consultation | Time and material | Final Reporting/Review | Built Environment | Rickey Salas | 29200 | 20127.56 | 12454.55 | 0 | 0% | 0 | 61.88% | 191 | 197.54 | 6.54 | 3.424%
23-PC-42199 | Sandpiper Highway Widening GIS Mapping | Fixed fee | Completed | Built Environment | Rickey Salas | 270200 | 196621.63 | 186167.87 | 0 | 0% | 0 | 94.68% | 0 | 2745.64 | 0 | 0%
23-PC-42237 | Foxglove Historic Resources Evaluation | Time and material | In Progress | Paleontology | Charlene Sparks | 82300 | 55519.51 | 30299.65 | 0 | 0% | 0 | 54.57% | 1157 | 571.64 | 0 | 0%
23-PC-42377 | Sumac Ridge Curation | Fixed fee | In Progress | Paleontology | Travis Delgado | 68300 | 47215.79 | 27022.26 | 0 | 0% | 0 | 57.23% | 0 | 443.55 | 0 | 0%
23-PC-42405 | Task Order 23: Silver Lake Levee Repair Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Paleontology | Travis Delgado | 757500 | 494268.75 | 636741.85 | 142473.1 | 28.83% | 1 | 100% | 8170 | 12394.07 | 4224.07 | 51.7%
23-PC-42451 | Phase I: Oak Terrace Cell Tower Data Recovery | Time and material | In Progress | Paleontology | Travis Delgado | 101800 | 72208.06 | 49547.32 | 0 | 0% | 0 | 68.62% | 847 | 840.11 | 15 | 1.771%
23-PC-42496 | Silver Lake Paleontological Monitoring | Fixed fee | Completed | Paleontology | Travis Delgado | 254000 | 143230.6 | 131932.2 | 0 | 0% | 0 | 92.11% | 1807 | 2235.06 | 446.75 | 24.72%
23-PC-42771 | Redbud Housing Development GIS Mapping | Fixed fee | In Progress | Maritime | Kyle Maynard | 25200 | 18799.2 | 14265.92 | 0 | 0% | 0 | 75.89% | 327 | 191.1 | 0 | 0%
23-PC-42907 | Heron Marsh Historic Resources Evaluation | Fixed fee | In Progress | Maritime | Rita Ayala | 1637200 | 977458.87 | 631212.64 | 0 | 0% | 0 | 64.58% | 0 | 9871.41 | 0 | 0%
23-PC-42981 | Hawk Point Architectural History Survey | Fixed fee | In Progress | Maritime | Kyle Maynard | 175800 | 129494.28 | 98123.54 | 0 | 0% | 0 | 75.77% | 0 | 1463.54 | 0 | 0%
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | Time and material | In Progress | Maritime | Rita Ayala | 139700 | 93543.12 | 67047.93 | 0 | 0% | 0 | 71.68% | 1018 | 906.97 | 6.01 | 0.5904%
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | Fixed fee | In Progress | Geospatial | Priscilla Pennington | 73300 | 53362.4 | 48458.95 | 0 | 0% | 0 | 90.81% | 805 | 740.46 | 0 | 0%
23-PC-43209 | Sea Oat Harbor Dredging Curation | Fixed fee | In Progress | Meridian Central | Seth Zavala | 247500 | 178398 | 98806.54 | 0 | 0% | 0 | 55.39% | 1850 | 1467.94 | 0 | 0%
23-PC-43238 | Thistle Down Fiber Route - Data Recovery | Fixed fee | In Progress | Meridian Central | Clinton Solis | 454300 | 287491.13 | 179098.38 | 0 | 0% | 0 | 62.3% | 0 | 2515.59 | 0 | 0%
23-PC-43356 | Granite Pass Wastewater Plant - Phase II Testing | Fixed fee | Final Billing/Invoice | Meridian Central | Seth Zavala | 66500 | 43863.4 | 31972.52 | 0 | 0% | 0 | 72.89% | 457 | 380.63 | 0 | 0%
23-PC-43408 | Wildrye Solar - Built Environment Survey | Time and material | In Progress | Meridian Central | Mathew Shea | 176300 | 121964.34 | 65842.99 | 0 | 0% | 0 | 53.99% | 0 | 758.15 | 0 | 0%
23-PC-43477 | On-Call: Meadowlark Levee Repair Cultural Resources Monitoring | Time and material | Completed | Meridian Central | Mathew Shea | 69800 | 51233.2 | 57791.37 | 6558.17 | 12.8% | 1 | 100% | 0 | 820.58 | 0 | 0%
23-PC-43564 | Willow Springs Levee Repair - Curation | Fixed fee | Final Billing/Invoice | Meridian Central | Mathew Shea | 277000 | 174842.4 | 168435.86 | 0 | 0% | 0 | 96.34% | 0 | 2313.58 | 0 | 0%
23-PC-43612 | Maple Fork Wind Farm Class III Survey | Time and material | In Progress | Meridian Central | Seth Zavala | 201800 | 135120.77 | 73233.08 | 0 | 0% | 0 | 54.2% | 1451 | 1000.59 | 0 | 0%
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | Fixed fee | In Progress | Meridian Southwest | Lynn Tran | 112600 | 77637.7 | 63002.79 | 0 | 0% | 0 | 81.15% | 872 | 1100.93 | 228.93 | 26.25%
23-PC-43788 | Sandpiper Cell Tower - GIS Mapping | Fixed fee | Final Billing/Invoice | Meridian Southwest | Reginald Kerr | 57800 | 39628.4 | 39255.29 | 0 | 0% | 0 | 99.06% | 508 | 589.14 | 81.14 | 15.97%
23-PC-43811 | Phase I: Thistle Down Fiber Route Section 106 Consultation | Fixed fee | On Hold | Meridian Southwest | Alan Gay | 34600 | 28596.9 | 16505.25 | 0 | 0% | 0 | 57.72% | 0 | 243.85 | 0 | 0%
23-PC-43829 | Task Order 34: Ember Valley Wastewater Plant Architectural History Survey | Fixed fee | In Progress | Meridian Southwest | Harold Chaney | 166500 | 125557.65 | 75422.97 | 0 | 0% | 0 | 60.07% | 1154 | 1135.18 | 30.48 | 2.641%
23-PC-44023 | Phase I: Sandpiper Pipeline Archaeological Testing | Time and material | Transferred Entity | NH Gulf (USD) | Randy Cantu | 299200 | 196796.95 | 154364.16 | 0 | 0% | 0 | 78.44% | 1565 | 1884.83 | 319.83 | 20.44%
23-PC-44147 | Phase II: Wren Hollow Harbor Dredging Historic Resources Evaluation | Fixed fee | Transferred Entity | NH Gulf (USD) | Randy Cantu | 138100 | 115907.33 | 138824.03 | 22916.7 | 19.77% | 1 | 100% | 0 | 1952.92 | 0 | 0%
24-PC-30017 | Sparrow Hill Data Recovery | Time and material | Final Billing/Invoice | Big Sky | Carl Barajas | 24800 | 17553.44 | 21304.8 | 3751.36 | 21.37% | 1 | 100% | 0 | 381.49 | 0 | 0%
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | Fixed fee | In Progress | Big Sky | Javier Estrada | 93300 | 59544.06 | 93708.96 | 34164.9 | 57.38% | 1 | 100% | 1332 | 1605.04 | 293.98 | 22.07%
24-PC-30378 | Phase III: Eagle Bend Rail Siding Class III Survey | Fixed fee | Completed | Big Sky | Brendan Melton | 133000 | 107304.4 | 75113.08 | 0 | 0% | 0 | 70% | 1659 | 1134.55 | 0 | 0%
24-PC-30448 | Maple Fork Substation - Data Recovery | Fixed fee | In Progress | Big Sky | Bob Frye | 142600 | 105894.76 | 72554.14 | 0 | 0% | 0 | 68.52% | 2040 | 1235.55 | 0 | 0%
24-PC-30509 | On-Call: Yarrow Point Mine Expansion Cultural Resources Monitoring | Fixed fee | Lab/Curation | Big Sky | Javier Estrada | 682700 | 517281.79 | 316284.4 | 0 | 0% | 0 | 61.14% | 7437 | 4517.57 | 0 | 0%
24-PC-30620 | Task Order 31: Sumac Ridge Trail GIS Mapping | Fixed fee | Lab/Curation | Bluegrass | Kiara Gillespie | 104400 | 78268.68 | 66519.65 | 0 | 0% | 0 | 84.99% | 0 | 1095.84 | 0 | 0%
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | Fixed fee | In Progress | Bluegrass | Kiara Gillespie | 60600 | 45577.26 | 50596.88 | 5019.62 | 11.01% | 1 | 100% | 930 | 1039.2 | 109.2 | 11.74%
24-PC-30751 | Windmill Flat Section 106 Consultation | Fixed fee | In Progress | Bluegrass | Kiara Gillespie | 90800 | 72034.09 | 50229.44 | 0 | 0% | 0 | 69.73% | 1122 | 819.35 | 0 | 0%
24-PC-30843 | North Fork Highway Widening - Built Environment Survey | Time and material | Final Billing/Invoice | Bluegrass | Alice Galloway | 108600 | 82210.2 | 75334.1 | 0 | 0% | 0 | 91.64% | 1541 | 1455.98 | 8.54 | 0.5542%
24-PC-30850 | Tamarack Transmission Line - Data Recovery | Time and material | Final Reporting/Review | Bluegrass | Alice Galloway | 991800 | 689995.26 | 423701.35 | 0 | 0% | 0 | 61.41% | 8332 | 6326.3 | 0 | 0%
24-PC-31134 | Blue Heron Built Environment Survey | Time and material | On Hold | Cascade | Jeff Spence | 59300 | 41670.11 | 27663.45 | 0 | 0% | 0 | 66.39% | 502 | 469.67 | 7.78 | 1.55%
24-PC-31224 | Quail Run Harbor Dredging - Architectural History Survey | Fixed fee | Final Billing/Invoice | Cascade | Preston Duarte | 64800 | 37720.08 | 49036.1 | 11316.02 | 30% | 1 | 100% | 478 | 837.31 | 359.31 | 75.17%
24-PC-31267 | Coyote Springs Built Environment Survey | Fixed fee | On Hold | Cascade | Cassidy Gay | 97500 | 73905 | 46761.91 | 0 | 0% | 0 | 63.27% | 1492 | 943.76 | 0 | 0%
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Time and material | Cost Tracking on Closed Project | Cascade | Preston Duarte | 94000 | 65640.2 | 73270.02 | 7629.82 | 11.62% | 1 | 100% | 1164 | 1351.09 | 187.09 | 16.07%
24-PC-31358 | Dove Canyon Archaeological Testing | Fixed fee | Final Reporting/Review | Cascade | Donald Lutz | 595100 | 484590.9 | 466249.95 | 0 | 0% | 0 | 96.22% | 6789 | 7390.32 | 601.32 | 8.857%
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | Fixed fee | In Progress | Cascade | Jean Cooke | 18200 | 12417.86 | 9098.08 | 0 | 0% | 0 | 73.27% | 138 | 148.77 | 10.77 | 7.804%
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | Time and material | In Progress | Cascade | Gene Nixon | 18300 | 11931.6 | 9112.04 | 0 | 0% | 0 | 76.37% | 174 | 159.04 | 8.53 | 4.902%
24-PC-31503 | North Fork Wind Farm Curation | Time and material | Lab/Curation | Cascade | Preston Duarte | 129900 | 87825.39 | 98773.26 | 10947.87 | 12.47% | 1 | 100% | 1437 | 1539.64 | 102.64 | 7.143%
24-PC-31514 | On-Call: Harbor View Highway Widening Curation | Fixed fee | Final Billing/Invoice | Cascade | Gene Nixon | 111700 | 98296 | 107941.44 | 9645.44 | 9.813% | 1 | 100% | 0 | 1730.53 | 0 | 0%
24-PC-31534 | Willow Springs Wastewater Plant - Architectural History Survey | Fixed fee | Completed | Cascade | Donald Lutz | 156900 | 93967.41 | 113173.46 | 19206.05 | 20.44% | 1 | 100% | 1344 | 1886.76 | 542.76 | 40.38%
24-PC-31663 | Fern Valley Section 106 Consultation | Fixed fee | In Progress | Cascade | Jean Cooke | 52600 | 37714.2 | 31436.99 | 0 | 0% | 0 | 83.36% | 487 | 583.39 | 101.76 | 20.9%
24-PC-31750 | Kestrel Butte Park Improvements - Phase I Survey | Fixed fee | Final Reporting/Review | Cascade | Cassidy Gay | 257200 | 200024.44 | 169133.71 | 4945.12 | 2.472% | 0 | 82.08% | 2056 | 2015.5 | 68.82 | 3.347%
24-PC-31819 | Plover Cove Reservoir - Curation | Time and material | Final Reporting/Review | Cascade | Gene Nixon | 38600 | 26703.48 | 15843.15 | 0 | 0% | 0 | 59.33% | 515 | 224.76 | 0 | 0%
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | Time and material | In Progress | Cascade | Gene Nixon | 15200 | 10676.48 | 7665.22 | 24.57 | 0.2301% | 0 | 71.57% | 234 | 121.12 | 0.5 | 0.2137%
24-PC-31924 | Cedar Hollow Wind Farm - Cultural Resources Assessment | Fixed fee | In Progress | Cascade | Gene Nixon | 186800 | 147262.72 | 97605.67 | 0 | 0% | 0 | 66.28% | 2395 | 1498.57 | 0 | 0%
24-PC-32088 | Elk Meadow Phase I Survey | Time and material | In Progress | Chesapeake | Jason Oconnor | 305100 | 228062.25 | 135703.34 | 0 | 0% | 0 | 59.5% | 5158 | 2065.63 | 0 | 0%
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | In Progress | Chesapeake | Jason Oconnor | 51800 | 36731.38 | 59530.74 | 22799.36 | 62.07% | 1 | 100% | 697 | 983.06 | 286.06 | 41.04%
24-PC-32209 | Saltgrass Wastewater Plant - Phase I Survey | Fixed fee | In Progress | Chesapeake | Ian Maddox | 13000 | 9029.25 | 8880.11 | 549.7 | 6.088% | 1 | 92.26% | 74 | 85.76 | 11.76 | 15.89%
24-PC-32210 | Badger Hollow Transmission Line - Class III Survey | Fixed fee | In Progress | Chesapeake | Alexandria Wilkinson | 114400 | 91211.12 | 63386.97 | 0 | 0% | 0 | 69.49% | 1153 | 823.35 | 0 | 0%
24-PC-32270 | Creosote Draw School Campus Data Recovery | Time and material | Final Billing/Invoice | Chesapeake | Alexandria Wilkinson | 42200 | 29472.48 | 28972.81 | 0 | 0% | 0 | 98.3% | 0 | 468.81 | 0 | 0%
24-PC-32479 | Riverbend Transmission Line Maritime Remote Sensing Survey | Fixed fee | In Progress | Chesapeake | Alexandria Wilkinson | 94000 | 66890.4 | 44542.3 | 42.56 | 0.06363% | 0 | 66.53% | 0 | 925.57 | 1 | 0%
24-PC-32591 | Larkspur Fiber Route - Cultural Resources Assessment | Time and material | Final Billing/Invoice | Chesapeake | Sandy Kerr | 41000 | 27478.2 | 33999.85 | 6521.65 | 23.73% | 1 | 100% | 292 | 484.21 | 192.21 | 65.83%
24-PC-32640 | Badger Hollow Harbor Dredging Architectural History Survey | Time and material | Transferred Entity | Chesapeake | Alexandria Wilkinson | 39000 | 28130.47 | 22328.99 | 0 | 0% | 0 | 79.38% | 581 | 378.85 | 0 | 0%
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | Chesapeake | Alexandria Wilkinson | 84000 | 70198.8 | 85361.66 | 21316.47 | 30.37% | 1 | 91.23% | 938 | 929.1 | 172.04 | 18.34%
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | Fixed fee | In Progress | Chesapeake | Ian Maddox | 51700 | 45206.48 | 39111.36 | 0 | 0% | 0 | 86.52% | 588 | 668.18 | 88.13 | 14.99%
24-PC-32954 | Redbud Substation - Historic Resources Evaluation | Time and material | In Progress | Front Range | Kimberly Daugherty | 331200 | 217532.16 | 114290.35 | 0 | 0% | 0 | 52.54% | 2762 | 1838.59 | 0 | 0%
24-PC-33384 | Phase III: Pine Hollow Rail Siding Maritime Remote Sensing Survey | Time and material | In Progress | Front Range | Dean Velazquez | 288100 | 207230.33 | 139777.64 | 0 | 0% | 0 | 67.45% | 2094 | 2290.13 | 239.64 | 11.44%
24-PC-33394 | Foxglove Park Improvements Cultural Resources Assessment | Time and material | In Progress | Front Range | Joanna Herrera | 298200 | 197617.14 | 102377.3 | 0 | 0% | 0 | 51.81% | 3027 | 1771.79 | 0 | 0%
24-PC-33448 | Ember Valley Solar Architectural History Survey | Fixed fee | In Progress | Front Range | Devon Pitts | 681000 | 419972.7 | 347755.54 | 279.17 | 0.06647% | 0 | 82.74% | 6739 | 7004.33 | 679.44 | 10.08%
24-PC-33531 | North Fork Park Improvements - Curation | Fixed fee | Lab/Curation | Front Range | Dean Velazquez | 31500 | 23760.45 | 18077.06 | 0 | 0% | 0 | 76.08% | 534 | 336.04 | 0 | 0%
24-PC-33575 | On-Call: North Fork Trail Architectural History Survey | Time and material | Final Reporting/Review | Front Range | Devon Pitts | 589600 | 433356 | 309438.41 | 1630.07 | 0.3762% | 0 | 71.03% | 9742 | 6706.64 | 36.75 | 0.3772%
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | Fixed fee | In Progress | Great Lakes | Karl Valenzuela | 64500 | 49568.25 | 45606.08 | 5058.83 | 10.21% | 1 | 81.8% | 431 | 565.3 | 134.3 | 31.16%
24-PC-33927 | Aspen Ridge Solar Class III Survey | Fixed fee | Final Reporting/Review | Great Lakes | Nathan Lambert | 104000 | 77001.6 | 42209.16 | 114.33 | 0.1485% | 0 | 54.67% | 908 | 439 | 1.5 | 0.1652%
24-PC-33981 | Yarrow Point Airport Apron - Phase II Testing | Time and material | Lab/Curation | Great Lakes | Nathan Lambert | 47500 | 29944 | 26339.43 | 19.41 | 0.06482% | 0 | 87.9% | 0 | 281.02 | 0.25 | 0%
24-PC-33985 | Thistle Down Substation Curation | Time and material | In Progress | Great Lakes | Angelica Cervantes | 78300 | 57863.7 | 50630.38 | 0 | 0% | 0 | 87.5% | 797 | 798.02 | 30.29 | 3.801%
24-PC-34015 | Sea Oat Mixed-Use Development Environmental Review Support | Fixed fee | Final Billing/Invoice | Great Lakes | Karl Valenzuela | 16200 | 10449 | 8825.53 | 0 | 0% | 0 | 84.46% | 149 | 116.88 | 0 | 0%
24-PC-34211 | Quail Run Substation - Cultural Resources Monitoring | Time and material | On Hold | Great Lakes | Gina Beltran | 70900 | 50537.52 | 37357.74 | 0 | 0% | 0 | 73.92% | 470 | 474.45 | 25.98 | 5.528%
24-PC-34263 | Cedar Hollow Airport Apron Section 106 Consultation | Fixed fee | In Progress | Great Lakes | Robin Mercado | 199300 | 147800.88 | 94406.95 | 0 | 0% | 0 | 63.87% | 2016 | 1539.84 | 23.28 | 1.155%
24-PC-34274 | Lantern Bay Rail Siding - Environmental Review Support | Fixed fee | Completed | Great Lakes | Angelica Cervantes | 61900 | 48195.34 | 57257.25 | 9061.91 | 18.8% | 1 | 100% | 415 | 862.75 | 447.75 | 107.9%
24-PC-34320 | Sage Flat Canal Lining Curation | Fixed fee | In Progress | Great Lakes | Nathan Lambert | 388400 | 253927.23 | 182728.59 | 0 | 0% | 0 | 71.96% | 2815 | 2656.32 | 152.96 | 5.434%
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | Time and material | In Progress | Great Lakes | Karl Valenzuela | 38700 | 26644.95 | 19241.81 | 0 | 0% | 0 | 72.22% | 0 | 272.21 | 0 | 0%
24-PC-34422 | Silver Lake Historic Resources Evaluation | Fixed fee | Completed | Great Lakes | Angelica Cervantes | 183900 | 106036.74 | 137847.76 | 31811.02 | 30% | 1 | 100% | 0 | 2040.66 | 0 | 0%
24-PC-34458 | Badger Hollow Built Environment Survey | Time and material | Completed | Great Lakes | Leonard Mejia | 78300 | 57511.35 | 65133.46 | 7622.11 | 13.25% | 1 | 100% | 801 | 905.46 | 104.46 | 13.04%
24-PC-34499 | Dove Canyon Trail - GIS Mapping | Time and material | In Progress | Great Lakes | Brendan Padilla | 104200 | 76427.58 | 75193.06 | 0 | 0% | 0 | 98.38% | 568 | 973.04 | 405.04 | 71.31%
24-PC-34593 | Riverbend Park Improvements - Paleontological Monitoring | Fixed fee | In Progress | Great Lakes | Leonard Mejia | 43500 | 33447.15 | 19459.27 | 0 | 0% | 0 | 58.18% | 403 | 261.55 | 0 | 0%
24-PC-34654 | Timber Gap Phase II Testing | Time and material | Final Reporting/Review | Great Lakes | Brendan Padilla | 115400 | 87787.28 | 47046.35 | 1417.07 | 1.614% | 0 | 51.98% | 0 | 1080.22 | 32.25 | 0%
24-PC-34663 | Redbud Airport Apron - GIS Mapping | Time and material | In Progress | Great Lakes | Kathleen Galvan | 505100 | 342760.86 | 286062.16 | 0 | 0% | 0 | 83.46% | 5130 | 3930.87 | 0 | 0%
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | Time and material | In Progress | Gulf Coast | Courtney Daugherty | 176500 | 121414.35 | 122080.25 | 665.9 | 0.5485% | 0 | 100% | 2269 | 2309.8 | 77.89 | 3.433%
24-PC-34919 | Fern Valley Levee Repair Class III Survey | Fixed fee | Completed | Gulf Coast | Sean Jennings | 20000 | 13582 | 12468.14 | 0 | 0% | 0 | 91.8% | 153 | 230.18 | 77.18 | 50.44%
24-PC-34975 | Foxglove Fiber Route GIS Mapping | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 205900 | 181192 | 154132.44 | 0 | 0% | 0 | 85.07% | 2902 | 2493.65 | 0 | 0%
24-PC-35267 | Falcon Mesa Trail - Phase II Testing | Fixed fee | Final Reporting/Review | Gulf Coast | Sean Jennings | 56700 | 42581.7 | 24952.14 | 0 | 0% | 0 | 58.6% | 733 | 450.08 | 0 | 0%
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | Time and material | In Progress | High Desert | Kathy Hurley | 301200 | 217496.52 | 196030.1 | 0 | 0% | 0 | 90.13% | 0 | 3654.75 | 0 | 0%
24-PC-35419 | Yarrow Point Pipeline - Class III Survey | Time and material | Completed | High Desert | Bridget Maddox | 24800 | 16359.63 | 14431.84 | 0 | 0% | 0 | 88.22% | 223 | 245.96 | 33.01 | 14.8%
24-PC-35474 | Larkspur Curation | Fixed fee | In Progress | High Desert | Eileen Poole | 369600 | 278295.85 | 213962.17 | 0 | 0% | 0 | 76.88% | 6675 | 4045.4 | 0 | 0%
24-PC-35559 | Phase III: Fern Valley Battery Storage Curation | Fixed fee | Final Reporting/Review | High Desert | Eileen Poole | 218200 | 144252.02 | 122823.72 | 0 | 0% | 0 | 85.15% | 2249 | 2385.81 | 144.6 | 6.43%
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | Fixed fee | In Progress | High Desert | Eileen Poole | 119200 | 88243.76 | 66735.14 | 0 | 0% | 0 | 75.63% | 0 | 1288.52 | 0 | 0%
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | Time and material | In Progress | High Desert | Kathy Hurley | 69900 | 49013.31 | 53862.59 | 9906.06 | 20.21% | 1 | 89.68% | 1005 | 1225.73 | 315.55 | 31.4%
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | Time and material | In Progress | High Desert | Kathy Hurley | 225100 | 153743.3 | 140872.8 | 5406.29 | 3.516% | 0 | 88.11% | 4322 | 2953.59 | 84.38 | 1.952%
24-PC-35881 | Wren Hollow Transmission Line - Architectural History Survey | Fixed fee | Final Billing/Invoice | High Desert | Bridget Maddox | 154200 | 112673.94 | 89889.66 | 0 | 0% | 0 | 79.78% | 1704 | 1511.44 | 0 | 0%
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | Fixed fee | In Progress | High Desert | Eileen Poole | 12900 | 9094.5 | 7655.43 | 0 | 0% | 0 | 84.18% | 157 | 130.11 | 0 | 0%
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Fixed fee | Cost Tracking on Closed Project | High Desert | Kathy Hurley | 58300 | 39072.66 | 45518.79 | 6446.13 | 16.5% | 1 | 100% | 662 | 744.04 | 107 | 16.16%
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | Time and material | In Progress | High Desert | Kathy Hurley | 5700 | 4244.79 | 3255.04 | 0 | 0% | 0 | 76.68% | 69 | 55.44 | 0 | 0%
24-PC-36184 | Juniper Wash Pipeline Maritime Remote Sensing Survey | Fixed fee | On Hold | High Desert | Eileen Poole | 3500 | 2062.55 | 1372.9 | 0 | 0% | 0 | 66.56% | 21 | 19.7 | 1.57 | 7.476%
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Fixed fee | Cost Tracking on Closed Project | Island | Rodney Mcguire | 56300 | 37721 | 34891.33 | 0 | 0% | 0 | 92.5% | 604 | 463.6 | 0 | 0%
24-PC-36445 | Tamarack Archaeological Testing | Time and material | On Hold | Island | Briana Melton | 63600 | 43330.68 | 44727.96 | 1397.28 | 3.225% | 0 | 100% | 471 | 534.73 | 65.1 | 13.82%
24-PC-36559 | Stone Mill Airport Apron - Class III Survey | Fixed fee | Completed | Island | Becky Velazquez | 11800 | 8903.1 | 6324.69 | 0 | 0% | 0 | 71.04% | 0 | 81.67 | 0 | 0%
24-PC-36620 | Silver Lake Cultural Resources Assessment | Time and material | In Progress | Lakeshore | Terrence Gillespie | 368100 | 252295.74 | 163066.37 | 0 | 0% | 0 | 64.63% | 0 | 2592.84 | 0 | 0%
24-PC-36676 | Task Order 38: Ember Valley Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | Lakeshore | Lucas Benson | 93200 | 62093.62 | 55674.87 | 0 | 0% | 0 | 89.66% | 960 | 727.18 | 0 | 0%
24-PC-36710 | Phase III: Twin Buttes Cell Tower Section 106 Consultation | Fixed fee | On Hold | Lakeshore | Jeanette Riddle | 138500 | 97600.95 | 65764.21 | 0 | 0% | 0 | 67.38% | 1211 | 902.91 | 0 | 0%
24-PC-36932 | Badger Hollow Canal Lining - Section 106 Consultation | Time and material | Final Reporting/Review | Hill Country | Marcus Shea | 12200 | 7733.58 | 6430.16 | 0 | 0% | 0 | 83.15% | 111 | 124.62 | 18.29 | 16.48%
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | Fixed fee | In Progress | Hill Country | Glen Delacruz | 141000 | 113970.3 | 138124.06 | 24153.76 | 21.19% | 1 | 100% | 1209 | 1790.72 | 581.72 | 48.12%
24-PC-37107 | Hawk Point Mixed-Use Development Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | Hill Country | Gail Meza | 259400 | 186117.89 | 126346.85 | 0 | 0% | 0 | 67.89% | 2146 | 1414.79 | 0 | 0%
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | Fixed fee | In Progress | Hill Country | Gail Meza | 1259200 | 853989.44 | 629919.62 | 0 | 0% | 0 | 73.76% | 10052 | 7007.63 | 0 | 0%
24-PC-37167 | Saltgrass Curation | Time and material | Lab/Curation | Hill Country | Marcus Shea | 65600 | 48603.04 | 33605.6 | 0 | 0% | 0 | 69.14% | 0 | 434.21 | 0 | 0%
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | Time and material | In Progress | Hill Country | Samuel Wilkerson | 67000 | 40709.2 | 34240.46 | 215.52 | 0.5294% | 0 | 83.58% | 316 | 431.01 | 115.01 | 36.4%
24-PC-37266 | Granite Pass Cell Tower Phase I Survey | Time and material | In Progress | Hill Country | Marcus Shea | 41400 | 24587.46 | 17096.41 | 0 | 0% | 0 | 69.53% | 612 | 288.37 | 0 | 0%
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | Fixed fee | In Progress | Hill Country | Theresa Fernandez | 298500 | 243904.35 | 174092 | 2462.61 | 1.01% | 0 | 70.37% | 0 | 2237.11 | 33.5 | 0%
24-PC-37372 | Harbor View Harbor Dredging Paleontological Monitoring | Fixed fee | Final Reporting/Review | Piedmont | Maria Parrish | 272100 | 221924.76 | 199459.24 | 2585.3 | 1.165% | 0 | 88.71% | 0 | 3705.88 | 53.25 | 0%
24-PC-37415 | Sage Flat Mine Expansion Maritime Remote Sensing Survey | Fixed fee | In Progress | Piedmont | Megan Pineda | 191000 | 147948.6 | 89853.11 | 0 | 0% | 0 | 60.73% | 0 | 1518.52 | 0 | 0%
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | Time and material | In Progress | Piedmont | Jody Chung | 309400 | 184093 | 149432.06 | 0 | 0% | 0 | 81.17% | 0 | 2476.31 | 0 | 0%
24-PC-37686 | Twin Buttes Mixed-Use Development Paleontological Monitoring | Fixed fee | In Progress | Piedmont | Annette Vaughan | 50600 | 39155.85 | 32027.2 | 0 | 0% | 0 | 81.79% | 490 | 519.5 | 29.5 | 6.02%
24-PC-37823 | Granite Pass Pipeline Cultural Resources Monitoring | Fixed fee | Lab/Curation | Piedmont | Jody Chung | 28900 | 21651.88 | 15787.12 | 0 | 0% | 0 | 72.91% | 341 | 253.23 | 1.24 | 0.3636%
24-PC-37942 | Task Order 39: Meadowlark Mine Expansion Curation | Time and material | Final Reporting/Review | Piedmont | Annette Vaughan | 241400 | 173542.46 | 141494.45 | 411.62 | 0.2372% | 0 | 81.3% | 2422 | 1837.69 | 6.25 | 0.2581%
24-PC-38054 | On-Call: Willow Springs Highway Widening GIS Mapping | Fixed fee | Final Reporting/Review | Prairie | Sherry Lloyd | 60700 | 51516.09 | 35113.87 | 0 | 0% | 0 | 68.16% | 0 | 743.8 | 0 | 0%
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | Fixed fee | In Progress | Prairie | Sherry Lloyd | 132200 | 95580.6 | 87961.2 | 0 | 0% | 0 | 92.03% | 1704 | 1558.32 | 42.57 | 2.498%
24-PC-38374 | On-Call: Riverbend Highway Widening Archaeological Testing | Time and material | In Progress | Prairie | Sherry Lloyd | 481100 | 330082.71 | 229684.73 | 0 | 0% | 0 | 69.58% | 6959 | 4079.75 | 0 | 0%
24-PC-38426 | Elk Meadow Mine Expansion Phase II Testing | Fixed fee | Final Billing/Invoice | Prairie | Sherry Lloyd | 203000 | 167048.7 | 176034.28 | 8985.58 | 5.379% | 1 | 100% | 0 | 3000.92 | 0 | 0%
24-PC-38469 | Falcon Mesa Harbor Dredging - Built Environment Survey | Fixed fee | In Progress | Red Rock | Jeanette Chung | 656700 | 435290.48 | 349739.21 | 470.36 | 0.1081% | 0 | 80.24% | 7103 | 5373.15 | 9.75 | 0.1373%
24-PC-38486 | Kestrel Butte Phase I Survey | Fixed fee | In Progress | Red Rock | Jeanette Chung | 153600 | 105043.81 | 119866.24 | 14822.43 | 14.11% | 1 | 100% | 1729 | 2304.83 | 575.83 | 33.3%
24-PC-38579 | Kestrel Butte Harbor Dredging - Data Recovery | Time and material | Final Billing/Invoice | Red Rock | Javier Newman | 59100 | 39502.44 | 34682.96 | 0 | 0% | 0 | 87.8% | 508 | 631.12 | 123.12 | 24.24%
24-PC-38687 | Lantern Bay GIS Mapping | Time and material | In Progress | Red Rock | Javier Newman | 68600 | 49542.92 | 28559.72 | 0 | 0% | 0 | 57.65% | 832 | 502.08 | 0 | 0%
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | Red Rock | Marisa Odom | 168200 | 130489.56 | 132230.67 | 1741.11 | 1.334% | 0 | 100% | 1711 | 2212.09 | 501.09 | 29.29%
24-PC-38795 | Meadowlark Class III Survey | Time and material | Final Billing/Invoice | Red Rock | Javier Newman | 684500 | 462838.34 | 454739.93 | 0 | 0% | 0 | 98.25% | 8935 | 8030.52 | 245.46 | 2.747%
24-PC-38817 | Phase III: Wildrye Fiber Route Built Environment Survey | Fixed fee | Completed | Red Rock | Bruce Suarez | 1966200 | 1268002.38 | 1321460.02 | 53457.64 | 4.216% | 0 | 100% | 14990 | 22156.26 | 7166.26 | 47.81%
24-PC-38847 | Pine Hollow School Campus - Environmental Review Support | Fixed fee | On Hold | Red Rock | Tina Aguirre | 118600 | 93456.8 | 61462.32 | 0 | 0% | 0 | 65.77% | 1770 | 1128.04 | 0 | 0%
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | Fixed fee | In Progress | Red Rock | Shelia Horne | 100200 | 72685.08 | 103671 | 30985.92 | 42.63% | 1 | 100% | 1304 | 1568.08 | 264.08 | 20.25%
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | Time and material | In Progress | Red Rock | Lydia Cisneros | 126600 | 82581.18 | 59856.61 | 0 | 0% | 0 | 72.48% | 0 | 1155.29 | 0 | 0%
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | Fixed fee | In Progress | Red Rock | Javier Newman | 597800 | 435557.08 | 334422.56 | 2879.71 | 0.6612% | 0 | 76.12% | 5341 | 5471.22 | 130.22 | 2.438%
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Fixed fee | Cost Tracking on Closed Project | Red Rock | Shelia Horne | 11000 | 7227 | 7427.79 | 200.79 | 2.778% | 0 | 100% | 88 | 132.38 | 44.38 | 50.43%
24-PC-39405 | Wren Hollow Harbor Dredging - Section 106 Consultation | Time and material | Final Billing/Invoice | Red Rock | Javier Newman | 159700 | 107248.85 | 82820.14 | 0 | 0% | 0 | 77.22% | 1716 | 1565.6 | 0 | 0%
24-PC-39479 | Granite Pass Solar - Cultural Resources Assessment | Time and material | Final Reporting/Review | Red Rock | Javier Newman | 233000 | 164777.6 | 116733.86 | 0 | 0% | 0 | 70.84% | 3729 | 2054.88 | 0 | 0%
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | Time and material | In Progress | Red Rock | Tina Aguirre | 33000 | 23227.58 | 29633.53 | 6405.95 | 27.58% | 1 | 100% | 0 | 501.58 | 0.25 | 0%
24-PC-39533 | Elk Meadow Architectural History Survey | Fixed fee | In Progress | Red Rock | Jeanette Chung | 67000 | 52641.9 | 49919.2 | 0 | 0% | 0 | 94.83% | 0 | 940.76 | 0 | 0%
24-PC-39694 | Task Order 35: Sandpiper Trail Historic Resources Evaluation | Time and material | In Progress | Red Rock | Tina Aguirre | 136500 | 93075.52 | 77289.3 | 0 | 0% | 0 | 83.04% | 1695 | 1240.48 | 0 | 0%
24-PC-39789 | Meadowlark Airport Apron Archaeological Testing | Fixed fee | On Hold | Red Rock | Marisa Odom | 126000 | 101029.58 | 50075.41 | 0 | 0% | 0 | 49.57% | 0 | 917.9 | 0 | 0%
24-PC-39822 | On-Call: Redbud Wind Farm Class III Survey | Fixed fee | Completed | Red Rock | Lydia Cisneros | 109500 | 87460.32 | 78994.88 | 0 | 0% | 0 | 90.32% | 1225 | 1547.06 | 322.06 | 26.29%
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | Fixed fee | In Progress | Red Rock | Bruce Suarez | 17800 | 14308.95 | 14659.16 | 350.21 | 2.447% | 0 | 100% | 238 | 226.51 | 13.63 | 5.727%
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | Time and material | In Progress | Red Rock | Lydia Cisneros | 414900 | 270722.25 | 215589.54 | 1353.01 | 0.4998% | 0 | 79.14% | 4873 | 4543.37 | 323.31 | 6.635%
24-PC-39940 | Riverbend Levee Repair - Curation | Fixed fee | In Progress | Red Rock | Marisa Odom | 20400 | 16397.52 | 10559.17 | 0 | 0% | 0 | 64.39% | 268 | 168.48 | 0 | 0%
24-PC-40067 | Saltgrass Fiber Route Class III Survey | Time and material | In Progress | Red Rock | Marisa Odom | 218100 | 163684.05 | 137568.33 | 0 | 0% | 0 | 84.05% | 1738 | 2408.8 | 670.8 | 38.6%
24-PC-40078 | Task Order 32: Heron Marsh Highway Widening Paleontological Monitoring | Time and material | Completed | Sierra | Donna Herring | 1820100 | 1155945.51 | 897222.7 | 0 | 0% | 0 | 77.62% | 16689 | 13089.93 | 0 | 0%
24-PC-40091 | Stone Mill Canal Lining Curation | Fixed fee | Completed | Sierra | Angelica Poole | 121900 | 105126.56 | 117486.47 | 12359.91 | 11.76% | 1 | 100% | 1805 | 1676.67 | 0 | 0%
24-PC-40102 | Redbud Class III Survey | Fixed fee | Final Reporting/Review | Sierra | Benjamin Mathis | 453900 | 322187.01 | 359994.6 | 37807.59 | 11.73% | 1 | 100% | 5462 | 7394.61 | 1932.61 | 35.38%
24-PC-40218 | North Fork Bridge Replacement - Built Environment Survey | Time and material | In Progress | Sierra | Angelica Poole | 141000 | 95626.2 | 51169.2 | 0 | 0% | 0 | 53.51% | 1169 | 774.58 | 0 | 0%
24-PC-40271 | Millbrook Rail Siding Phase II Testing | Fixed fee | Final Billing/Invoice | Sierra | Louis Huff | 1146200 | 757124.2 | 922496.97 | 165372.77 | 21.84% | 1 | 100% | 12512 | 15587.07 | 3075.07 | 24.58%
24-PC-40317 | Sumac Ridge Harbor Dredging Curation | Time and material | In Progress | Sierra | Angelica Poole | 225800 | 153318.2 | 86572.73 | 0 | 0% | 0 | 56.47% | 2177 | 1452.23 | 0 | 0%
24-PC-40427 | On-Call: Harbor View Trail Built Environment Survey | Fixed fee | Completed | Sierra | Louis Huff | 121700 | 90556.97 | 103112.89 | 12555.92 | 13.87% | 1 | 100% | 0 | 1375.63 | 0 | 0%
24-PC-40479 | Quail Run Rail Siding - Built Environment Survey | Fixed fee | In Progress | Sierra | Donna Herring | 139600 | 110619.04 | 70556.04 | 0 | 0% | 0 | 63.78% | 935 | 1202.18 | 267.18 | 28.58%
24-PC-40561 | Task Order 39: Aspen Ridge Housing Development GIS Mapping | Fixed fee | In Progress | Sierra | Benjamin Mathis | 2335800 | 1746045.15 | 1245666.04 | 838.52 | 0.04802% | 0 | 71.29% | 28964 | 14974.25 | 16.25 | 0.0561%
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | Fixed fee | In Progress | Sierra | Angelica Poole | 460500 | 381017.7 | 270177.48 | 165.66 | 0.04348% | 0 | 70.87% | 0 | 5627.46 | 3.5 | 0%
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Fixed fee | Cost Tracking on Closed Project | Sierra | Louis Huff | 50300 | 35350.84 | 32471.24 | 0 | 0% | 0 | 91.85% | 408 | 516.47 | 108.47 | 26.59%
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | Sierra | Donna Herring | 22100 | 17918.68 | 33602.1 | 15683.42 | 87.53% | 1 | 100% | 358 | 713.91 | 355.91 | 99.42%
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | Time and material | In Progress | Coastal Bend | Alexis Nixon | 48400 | 37137.32 | 47362.38 | 10225.06 | 27.53% | 1 | 100% | 0 | 876.91 | 12 | 0%
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | Coastal Bend | Duane Ballard | 31800 | 20975.28 | 22323.11 | 1347.83 | 6.426% | 1 | 100% | 253 | 396.48 | 143.48 | 56.71%
24-PC-40836 | Task Order 12: Saltgrass Highway Widening Curation | Fixed fee | On Hold | Coastal Bend | Alexis Nixon | 17000 | 11633.1 | 10174.53 | 0 | 0% | 0 | 87.46% | 171 | 175.61 | 4.61 | 2.696%
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Fixed fee | Lab/Curation | Coastal Bend | Diane Daniels | 579300 | 392475.75 | 413750.74 | 21274.99 | 5.421% | 1 | 100% | 4511 | 6199.18 | 1688.18 | 37.42%
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 8800 | 6914.16 | 7269.9 | 355.74 | 5.145% | 1 | 100% | 0 | 130.85 | 0 | 0%
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | Time and material | In Progress | Coastal Bend | Alexis Nixon | 60600 | 39983.88 | 31771.04 | 0 | 0% | 0 | 79.46% | 534 | 507.1 | 46.86 | 8.775%
24-PC-41066 | Task Order 31: Yarrow Point Wind Farm Curation | Time and material | Final Billing/Invoice | Coastal Bend | Steve Rubio | 30400 | 19493.63 | 17863.22 | 0 | 0% | 0 | 91.64% | 252 | 258.98 | 40.53 | 16.08%
24-PC-41067 | On-Call: Goldfinch Wastewater Plant Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | Coastal Bend | Duane Ballard | 364100 | 243619.31 | 273109.81 | 29490.5 | 12.11% | 1 | 100% | 3387 | 4869.53 | 1482.53 | 43.77%
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Fixed fee | Transferred Entity | Coastal Bend | Alexis Nixon | 18000 | 12312 | 22722.23 | 10410.23 | 84.55% | 1 | 100% | 109 | 245.55 | 136.55 | 125.3%
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | Fixed fee | In Progress | Coastal Bend | Alexis Nixon | 194900 | 131089.74 | 126178.41 | 0 | 0% | 0 | 96.25% | 1042 | 2232.38 | 1190.38 | 114.2%
24-PC-41534 | Badger Hollow Architectural History Survey | Fixed fee | On Hold | Coastal Bend | Duane Ballard | 795200 | 579859.84 | 341062.79 | 0 | 0% | 0 | 58.82% | 0 | 5601.2 | 0 | 0%
24-PC-41555 | Phase III: Pine Hollow Solar Built Environment Survey | Time and material | Final Billing/Invoice | Coastal Bend | Alexis Nixon | 38200 | 27011.22 | 33706.85 | 6695.63 | 24.79% | 1 | 100% | 396 | 577.44 | 181.44 | 45.82%
24-PC-41572 | Task Order 13: Plover Cove Water Main Architectural History Survey | Fixed fee | On Hold | Coastal Bend | Steve Rubio | 126800 | 95391.63 | 67280.28 | 0 | 0% | 0 | 70.53% | 1614 | 1064.34 | 0 | 0%
24-PC-41701 | Cedar Hollow Wastewater Plant - Data Recovery | Fixed fee | On Hold | Built Environment | Kathleen Cabrera | 189100 | 119908.31 | 102542.43 | 0 | 0% | 0 | 85.52% | 1469 | 1472.23 | 82.3 | 5.602%
24-PC-41886 | On-Call: Pebble Beach Road Canal Lining Section 106 Consultation | Time and material | Final Reporting/Review | Built Environment | Melody Holloway | 67500 | 46824.75 | 29307.2 | 173.55 | 0.3706% | 0 | 62.22% | 543 | 383.73 | 2.75 | 0.5064%
24-PC-41904 | Falcon Mesa Battery Storage - Architectural History Survey | Fixed fee | Final Billing/Invoice | Built Environment | Jesse Maynard | 31500 | 21889.35 | 21624.49 | 0 | 0% | 0 | 98.79% | 281 | 319.92 | 38.92 | 13.85%
24-PC-41969 | Windmill Flat Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | Built Environment | Melody Holloway | 216500 | 161335.8 | 107206.67 | 0 | 0% | 0 | 66.45% | 3849 | 2400.42 | 0 | 0%
24-PC-42121 | Oak Terrace Substation Maritime Remote Sensing Survey | Fixed fee | In Progress | Built Environment | Kathleen Cabrera | 267300 | 208453.84 | 187719.43 | 185.92 | 0.08919% | 0 | 89.96% | 2366 | 2639.1 | 287.38 | 12.15%
24-PC-42174 | Thistle Down Section 106 Consultation | Time and material | On Hold | Built Environment | Rickey Salas | 20800 | 14431.04 | 6766.62 | 0 | 0% | 0 | 46.89% | 177 | 102.98 | 0 | 0%
24-PC-42184 | Phase II: Granite Pass Substation Environmental Review Support | Fixed fee | In Progress | Built Environment | Rickey Salas | 25600 | 17986.56 | 7901.19 | 0 | 0% | 0 | 43.93% | 209 | 121.39 | 0 | 0%
24-PC-42267 | Aspen Ridge Bridge Replacement Paleontological Monitoring | Fixed fee | On Hold | Paleontology | Charlene Sparks | 49000 | 32797.59 | 12936.54 | 0 | 0% | 0 | 39.44% | 422 | 203.21 | 0 | 0%
24-PC-42338 | Silver Lake Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | Paleontology | Travis Delgado | 21700 | 14751.66 | 14816.12 | 64.46 | 0.437% | 0 | 100% | 243 | 211.52 | 3.68 | 1.514%
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | Time and material | In Progress | Paleontology | Charlene Sparks | 263500 | 173567.45 | 177335 | 3767.55 | 2.171% | 0 | 100% | 3511 | 3307.62 | 185.94 | 5.296%
24-PC-42495 | Kestrel Butte Battery Storage - Cultural Resources Monitoring | Fixed fee | Lab/Curation | Paleontology | Charlene Sparks | 45900 | 35246.61 | 22172.99 | 0 | 0% | 0 | 62.91% | 440 | 325.58 | 0 | 0%
24-PC-42527 | Heron Marsh Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | Paleontology | Charlene Sparks | 31700 | 20415.55 | 18789.61 | 0 | 0% | 0 | 92.04% | 450 | 278.68 | 0 | 0%
24-PC-42550 | Yarrow Point Paleontological Monitoring | Fixed fee | In Progress | Paleontology | Travis Delgado | 301300 | 216936 | 145304.57 | 223.28 | 0.1029% | 0 | 66.88% | 2420 | 2259.67 | 45.98 | 1.9%
24-PC-42638 | Task Order 21: Plover Cove Transmission Line Maritime Remote Sensing Survey | Fixed fee | On Hold | Paleontology | Charlene Sparks | 417200 | 310521.96 | 167147.98 | 0 | 0% | 0 | 53.83% | 4299 | 3293.98 | 0 | 0%
24-PC-42674 | Foxglove Canal Lining Architectural History Survey | Time and material | Lab/Curation | Maritime | Rita Ayala | 156100 | 111589.34 | 57675.71 | 0 | 0% | 0 | 51.69% | 1241 | 781.68 | 0 | 0%
24-PC-42697 | On-Call: Dove Canyon Airport Apron GIS Mapping | Time and material | Final Billing/Invoice | Maritime | Rita Ayala | 120000 | 85241.3 | 69173.64 | 0 | 0% | 0 | 81.15% | 0 | 1037.67 | 0 | 0%
24-PC-42846 | On-Call: Juniper Wash Airport Apron Historic Resources Evaluation | Fixed fee | Completed | Maritime | Kyle Maynard | 161200 | 115644.05 | 119214.99 | 3570.94 | 3.088% | 0 | 100% | 0 | 1856.74 | 0 | 0%
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | Fixed fee | In Progress | Geospatial | Sylvia Callahan | 639100 | 498050.63 | 351673.07 | 0 | 0% | 0 | 70.61% | 9052 | 4656.57 | 0 | 0%
24-PC-43116 | On-Call: Larkspur Airport Apron Phase II Testing | Fixed fee | Final Reporting/Review | Geospatial | Sylvia Callahan | 424400 | 314395.52 | 212843.45 | 417.69 | 0.1329% | 0 | 67.57% | 0 | 3480.06 | 6.5 | 0%
24-PC-43150 | Rushgrass Draw Architectural History Survey | Fixed fee | In Progress | Geospatial | Sylvia Callahan | 301500 | 222689.15 | 180855.18 | 379.33 | 0.1703% | 0 | 81.04% | 4305 | 3500.23 | 276.29 | 6.418%
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | Time and material | In Progress | Geospatial | Sylvia Callahan | 19700 | 14170.21 | 18919.28 | 4749.07 | 33.51% | 1 | 100% | 0 | 295.53 | 0 | 0%
24-PC-43251 | Phase III: Maple Fork Fiber Route Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | Meridian Central | Seth Zavala | 163100 | 112751.03 | 96362.11 | 0 | 0% | 0 | 85.46% | 1566 | 1418.51 | 0 | 0%
24-PC-43406 | Pine Hollow Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | Meridian Central | Seth Zavala | 38700 | 27987.84 | 24661.43 | 0 | 0% | 0 | 88.11% | 613 | 349.28 | 0 | 0%
24-PC-43670 | Granite Pass Archaeological Testing | Fixed fee | Final Reporting/Review | Meridian Southwest | Lynn Tran | 220400 | 168565.52 | 118945.86 | 0 | 0% | 0 | 70.56% | 0 | 1701.79 | 0 | 0%
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | Time and material | In Progress | Meridian Southwest | Lynn Tran | 1003600 | 771166.24 | 614867.84 | 0 | 0% | 0 | 79.73% | 9084 | 9339.27 | 451.06 | 4.965%
24-PC-43719 | On-Call: Juniper Wash Wastewater Plant Historic Resources Evaluation | Time and material | Final Reporting/Review | Meridian Southwest | Harold Chaney | 382100 | 239599.17 | 170624.75 | 0 | 0% | 0 | 71.21% | 3822 | 2427.81 | 0 | 0%
24-PC-43782 | Stone Mill Cultural Resources Assessment | Time and material | Completed | Meridian Southwest | Harold Chaney | 571500 | 411773.03 | 443050.33 | 31277.3 | 7.596% | 1 | 100% | 4581 | 6353.8 | 1772.8 | 38.7%
24-PC-43786 | Task Order 3: Wren Hollow Canal Lining Architectural History Survey | Fixed fee | Lab/Curation | Meridian Southwest | Alan Gay | 220400 | 123791.36 | 80906.2 | 0 | 0% | 0 | 65.36% | 0 | 1214.83 | 0 | 0%
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | NH Gulf (USD) | Vanessa Duarte | 213100 | 187528 | 134454.77 | 0 | 0% | 0 | 71.7% | 2321 | 1830.38 | 0 | 0%
24-PC-44022 | Sea Oat Historic Resources Evaluation | Time and material | Transferred Entity | NH Gulf (USD) | Vanessa Duarte | 1072900 | 625022.97 | 345106.15 | 0 | 0% | 0 | 55.21% | 6255 | 4992.21 | 0 | 0%
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Time and material | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 264500 | 194222.35 | 246339.61 | 52117.26 | 26.83% | 1 | 100% | 1593 | 2883.21 | 1290.21 | 80.99%
24-PC-44158 | Saltgrass Environmental Review Support | Fixed fee | Transferred Entity | NH Gulf (USD) | Vanessa Duarte | 23200 | 15583.44 | 16044.04 | 460.6 | 2.956% | 0 | 100% | 132 | 166.86 | 34.86 | 26.41%
25-PC-30034 | On-Call: Wren Hollow Wastewater Plant GIS Mapping | Fixed fee | Final Reporting/Review | Big Sky | Bob Frye | 101900 | 74162.82 | 50829.46 | 527.36 | 0.7111% | 0 | 67.83% | 1347 | 1122.1 | 64.07 | 4.756%
25-PC-30077 | Phase II: Tamarack Housing Development Phase I Survey | Time and material | In Progress | Big Sky | Carl Barajas | 103400 | 71293.1 | 65644.01 | 425.56 | 0.5969% | 0 | 91.48% | 718 | 1208.47 | 490.47 | 68.31%
25-PC-30140 | Windmill Flat Cell Tower - GIS Mapping | Time and material | In Progress | Big Sky | Carl Barajas | 257200 | 165353.88 | 95517.33 | 0 | 0% | 0 | 57.77% | 2437 | 1156.74 | 0 | 0%
25-PC-30204 | Maple Fork Phase I Survey | Time and material | Final Billing/Invoice | Big Sky | Brendan Melton | 179400 | 124220.26 | 96161.49 | 0 | 0% | 0 | 77.41% | 0 | 1779.51 | 0 | 0%
25-PC-30254 | Task Order 16: Coyote Springs Reservoir Class III Survey | Time and material | Final Reporting/Review | Big Sky | Brendan Melton | 77100 | 49529.04 | 35308.94 | 0 | 0% | 0 | 71.29% | 569 | 460.46 | 8.35 | 1.467%
25-PC-30345 | Wildrye Phase II Testing | Fixed fee | In Progress | Big Sky | Brendan Melton | 160400 | 92631 | 75656.14 | 893.24 | 0.9643% | 0 | 80.71% | 1097 | 1206.72 | 109.72 | 10%
25-PC-30348 | Phase II: Pine Hollow Wind Farm Environmental Review Support | Fixed fee | In Progress | Big Sky | Carl Barajas | 20800 | 15194.4 | 9749.45 | 0 | 0% | 0 | 64.16% | 256 | 163.2 | 0 | 0%
25-PC-30418 | Dove Canyon Wind Farm Class III Survey | Fixed fee | Final Reporting/Review | Big Sky | Brendan Melton | 344800 | 233309.47 | 168637.51 | 230.46 | 0.09878% | 0 | 72.18% | 3956 | 3419.43 | 21.91 | 0.5538%
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | Fixed fee | In Progress | Bluegrass | Alice Galloway | 19700 | 13027.61 | 13683.53 | 1285.73 | 9.869% | 1 | 95.17% | 149 | 210.87 | 61.87 | 41.52%
25-PC-30694 | Rushgrass Draw Class III Survey | Fixed fee | Completed | Bluegrass | Kiara Gillespie | 358200 | 267073.92 | 347196.1 | 80122.18 | 30% | 1 | 100% | 3515 | 6352.59 | 2837.59 | 80.73%
25-PC-30717 | Phase II: Riverbend Cell Tower Built Environment Survey | Fixed fee | In Progress | Bluegrass | Alice Galloway | 324100 | 205678.64 | 174373.11 | 21518.8 | 10.46% | 1 | 74.32% | 2658 | 3037.47 | 478.87 | 18.02%
25-PC-30725 | Slate Ridge Paleontological Monitoring | Time and material | Completed | Bluegrass | Kiara Gillespie | 7400 | 4916.56 | 6391.53 | 1474.97 | 30% | 1 | 100% | 53 | 103.28 | 50.28 | 94.87%
25-PC-30739 | Saltgrass Solar Class III Survey | Fixed fee | Final Reporting/Review | Bluegrass | Alice Galloway | 244200 | 214896 | 109432.26 | 958.39 | 0.446% | 0 | 50.48% | 0 | 2108.16 | 22.25 | 0%
25-PC-30772 | Sea Oat Cultural Resources Assessment | Fixed fee | In Progress | Bluegrass | Alice Galloway | 63300 | 43065.84 | 56416.91 | 13351.07 | 31% | 1 | 100% | 517 | 961.56 | 444.56 | 85.99%
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | Fixed fee | In Progress | Bluegrass | Alice Galloway | 131000 | 85464.4 | 90183.9 | 4719.5 | 5.522% | 1 | 100% | 713 | 1206.71 | 493.71 | 69.24%
25-PC-30824 | Task Order 2: Lantern Bay Fiber Route Environmental Review Support | Fixed fee | In Progress | Bluegrass | Alice Galloway | 206400 | 145641.07 | 100541.75 | 0 | 0% | 0 | 69.03% | 3572 | 1798.09 | 0 | 0%
25-PC-30928 | Tansy Flat Bridge Replacement Cultural Resources Monitoring | Fixed fee | On Hold | Bluegrass | Kiara Gillespie | 71900 | 53817.15 | 43233.51 | 0 | 0% | 0 | 80.33% | 1114 | 700.77 | 1.84 | 0.1652%
25-PC-31024 | Rushgrass Draw Environmental Review Support | Fixed fee | On Hold | Bluegrass | Alice Galloway | 770600 | 514826.47 | 11092.84 | 0 | 0% | 0 | 2.155% | 5690 | 194.26 | 0 | 0%
25-PC-31109 | Riverbend GIS Mapping | Time and material | In Progress | Cascade | Cassidy Gay | 174700 | 109484.49 | 162892.26 | 53407.77 | 48.78% | 1 | 100% | 785 | 1609.59 | 824.59 | 105%
25-PC-31114 | Granite Pass Built Environment Survey | Time and material | In Progress | Cascade | Jean Cooke | 229400 | 157964.84 | 127618.8 | 415.64 | 0.2631% | 0 | 80.53% | 2257 | 2354.44 | 97.44 | 4.317%
25-PC-31144 | Heron Marsh Bridge Replacement Section 106 Consultation | Time and material | Completed | Cascade | Jeff Spence | 78700 | 54208.56 | 48724.57 | 0 | 0% | 0 | 89.88% | 466 | 694.99 | 228.99 | 49.14%
25-PC-31180 | Blue Heron Environmental Review Support | Fixed fee | In Progress | Cascade | Preston Duarte | 80000 | 60701.89 | 64096.36 | 3394.47 | 5.592% | 1 | 100% | 0 | 637.43 | 4 | 0%
25-PC-31242 | Sage Flat Fiber Route - Class III Survey | Fixed fee | In Progress | Cascade | Gene Nixon | 398600 | 273446.93 | 98245.95 | 354.78 | 0.1297% | 0 | 35.8% | 4289 | 2026.65 | 9 | 0.2098%
25-PC-31263 | Dove Canyon Water Main Phase I Survey | Time and material | Lab/Curation | Cascade | Cassidy Gay | 203400 | 139410.36 | 122334.29 | 8126.42 | 5.829% | 1 | 81.92% | 2275 | 2339.96 | 212.41 | 9.337%
25-PC-31275 | Sage Flat Highway Widening Environmental Review Support | Time and material | Final Billing/Invoice | Cascade | Gene Nixon | 24900 | 18435.96 | 23832.99 | 5397.03 | 29.27% | 1 | 100% | 313 | 423.36 | 110.36 | 35.26%
25-PC-31298 | On-Call: Lone Pine Water Main Class III Survey | Fixed fee | In Progress | Cascade | Cassidy Gay | 48100 | 35361.72 | 30507.92 | 395.84 | 1.119% | 0 | 85.15% | 420 | 512.79 | 98.4 | 23.43%
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Fixed fee | Lab/Curation | Cascade | Donald Lutz | 23500 | 17263.1 | 22123.1 | 4860 | 28.15% | 1 | 100% | 289 | 354.9 | 65.9 | 22.8%
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | Fixed fee | In Progress | Cascade | Cassidy Gay | 52000 | 38781.6 | 51500.29 | 12718.69 | 32.8% | 1 | 100% | 707 | 781.84 | 74.84 | 10.59%
25-PC-31420 | Cedar Hollow Wind Farm Archaeological Testing | Fixed fee | Final Reporting/Review | Cascade | Jeff Spence | 102200 | 68753.09 | 37206.7 | 1822.71 | 2.651% | 0 | 51.47% | 1116 | 754.28 | 51.66 | 4.629%
25-PC-31555 | Wren Hollow Architectural History Survey | Fixed fee | In Progress | Cascade | Gene Nixon | 69300 | 53097.66 | 50888.1 | 3573.2 | 6.729% | 1 | 89.11% | 641 | 753.67 | 122.05 | 19.04%
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | Fixed fee | In Progress | Cascade | Jean Cooke | 16800 | 11810.4 | 15531.6 | 3905.62 | 33.07% | 1 | 98.44% | 139 | 246.26 | 107.26 | 77.17%
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Time and material | Final Reporting/Review | Cascade | Jeff Spence | 30300 | 22049.31 | 34568.29 | 12518.98 | 56.78% | 1 | 100% | 0 | 554.57 | 1.5 | 0%
25-PC-31775 | Task Order 26: Pine Hollow Bridge Replacement Cultural Resources Monitoring | Time and material | In Progress | Cascade | Cassidy Gay | 163200 | 98279.04 | 45032.99 | 51.51 | 0.05241% | 0 | 45.77% | 0 | 1007.08 | 1.25 | 0%
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | Fixed fee | In Progress | Cascade | Preston Duarte | 216800 | 171337.04 | 185663.63 | 36998.58 | 21.59% | 1 | 86.77% | 2601 | 3190.73 | 884.8 | 34.02%
25-PC-31821 | Millbrook Environmental Review Support | Fixed fee | Final Reporting/Review | Cascade | Preston Duarte | 211400 | 183932.36 | 149340.49 | 2037.93 | 1.108% | 0 | 80.09% | 2512 | 2707.94 | 215.52 | 8.58%
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Time and material | Cost Tracking on Closed Project | Cascade | Donald Lutz | 40900 | 28728.16 | 33002.57 | 4274.41 | 14.88% | 1 | 100% | 0 | 645.62 | 0 | 0%
25-PC-31905 | Raven Rock Mixed-Use Development Phase II Testing | Time and material | Final Reporting/Review | Cascade | Cassidy Gay | 331600 | 228107.64 | 134532.56 | 1470.66 | 0.6447% | 0 | 58.33% | 3676 | 2582.79 | 34.25 | 0.9317%
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Time and material | Final Reporting/Review | Chesapeake | Jason Oconnor | 35200 | 24481.6 | 39794.35 | 15312.75 | 62.55% | 1 | 100% | 522 | 827.09 | 323.25 | 61.93%
25-PC-31983 | Task Order 29: Juniper Wash Housing Development Cultural Resources Assessment | Time and material | Final Billing/Invoice | Chesapeake | Ian Maddox | 271500 | 186004.65 | 189698.17 | 3693.52 | 1.986% | 0 | 100% | 2553 | 3228.94 | 767.42 | 30.06%
25-PC-32000 | Twin Buttes Built Environment Survey | Fixed fee | On Hold | Chesapeake | Ian Maddox | 61200 | 50312.52 | 19654.73 | 0 | 0% | 0 | 39.07% | 0 | 271.35 | 0 | 0%
25-PC-32021 | Oak Terrace Cultural Resources Monitoring | Time and material | In Progress | Chesapeake | Alexandria Wilkinson | 148200 | 111253.74 | 57713.28 | 442.17 | 0.3974% | 0 | 51.48% | 1469 | 1158.76 | 9 | 0.6127%
25-PC-32024 | Pine Hollow Historic Resources Evaluation | Time and material | In Progress | Chesapeake | Ian Maddox | 79500 | 57637.5 | 41962.53 | 682.45 | 1.184% | 0 | 71.62% | 565 | 584.52 | 30.96 | 5.48%
25-PC-32112 | Foxglove School Campus Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Chesapeake | Jason Oconnor | 37600 | 26165.84 | 25192.3 | 0 | 0% | 0 | 96.28% | 553 | 429.98 | 0 | 0%
25-PC-32144 | Ember Valley Archaeological Testing | Fixed fee | Completed | Chesapeake | Alexandria Wilkinson | 12100 | 9169.38 | 11920.19 | 2750.81 | 30% | 1 | 100% | 0 | 187.45 | 0 | 0%
25-PC-32241 | Sumac Ridge Canal Lining Cultural Resources Monitoring | Time and material | Final Reporting/Review | Chesapeake | Bryan Mann | 331500 | 231983.7 | 169942.78 | 1467.23 | 0.6325% | 0 | 72.62% | 2426 | 2131.38 | 48.88 | 2.015%
25-PC-32264 | Tansy Flat Wastewater Plant Phase I Survey | Time and material | Final Reporting/Review | Chesapeake | Sandy Kerr | 736000 | 420550.4 | 341293.64 | 0 | 0% | 0 | 81.15% | 5939 | 5495.6 | 25.87 | 0.4356%
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | Time and material | In Progress | Chesapeake | Ian Maddox | 201300 | 150874.35 | 161800.48 | 34249.05 | 22.7% | 1 | 84.54% | 1642 | 2391.69 | 807.71 | 49.19%
25-PC-32346 | Phase II: Aspen Ridge Mixed-Use Development Historic Resources Evaluation | Time and material | Final Billing/Invoice | Chesapeake | Jason Oconnor | 40200 | 29157.06 | 26522.7 | 0 | 0% | 0 | 90.96% | 288 | 425.12 | 137.12 | 47.61%
25-PC-32402 | Hawk Point Highway Widening - Cultural Resources Monitoring | Fixed fee | Lab/Curation | Chesapeake | Sandy Kerr | 401300 | 353144 | 208637.1 | 249.58 | 0.07067% | 0 | 59.01% | 5485 | 4168.63 | 6 | 0.1094%
25-PC-32447 | Pebble Beach Road Archaeological Testing | Fixed fee | In Progress | Chesapeake | Alexandria Wilkinson | 88200 | 61772.24 | 76703.24 | 14931 | 24.17% | 1 | 100% | 840 | 1426.19 | 586.19 | 69.78%
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | Time and material | In Progress | Chesapeake | Sandy Kerr | 118800 | 85013.28 | 117591.54 | 42571.42 | 50.08% | 1 | 88.25% | 651 | 1298.42 | 647.42 | 99.45%
25-PC-32500 | On-Call: Dove Canyon Cell Tower Environmental Review Support | Time and material | Final Billing/Invoice | Chesapeake | Bryan Mann | 95700 | 67273.36 | 69534.49 | 2261.13 | 3.361% | 0 | 100% | 813 | 1085.78 | 272.78 | 33.55%
25-PC-32630 | Wildrye Archaeological Testing | Fixed fee | On Hold | Chesapeake | Sandy Kerr | 865400 | 644117.22 | 341055.04 | 0 | 0% | 0 | 52.95% | 9408 | 5316.19 | 0 | 0%
25-PC-32750 | Elk Meadow Fiber Route Paleontological Monitoring | Fixed fee | In Progress | Chesapeake | Bryan Mann | 35500 | 25187.75 | 19250.93 | 219.78 | 0.8726% | 0 | 75.56% | 440 | 311.26 | 1.75 | 0.3977%
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | Time and material | In Progress | Front Range | Jeremy Tran | 86500 | 62245.4 | 49276.48 | 985 | 1.582% | 0 | 77.58% | 1283 | 939.99 | 18.75 | 1.461%
25-PC-32795 | North Fork Water Main Architectural History Survey | Time and material | In Progress | Front Range | Reginald Vargas | 16900 | 11650.86 | 12884.7 | 1256.23 | 10.78% | 1 | 99.81% | 138 | 176.77 | 39.18 | 28.39%
25-PC-32819 | Eagle Bend Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | Front Range | Joanna Herrera | 49800 | 32021.4 | 30314.49 | 0 | 0% | 0 | 94.67% | 325 | 530.7 | 205.7 | 63.29%
25-PC-32838 | Aspen Ridge Canal Lining - Curation | Fixed fee | In Progress | Front Range | Jeremy Tran | 42600 | 33543.24 | 30870.44 | 1636.33 | 4.878% | 0 | 87.15% | 0 | 238.67 | 9.5 | 0%
25-PC-32861 | Yarrow Point Architectural History Survey | Fixed fee | In Progress | Front Range | Dean Velazquez | 59200 | 41555.52 | 49895.36 | 8339.84 | 20.07% | 1 | 100% | 0 | 513.57 | 4.5 | 0%
25-PC-32867 | Larkspur Levee Repair Maritime Remote Sensing Survey | Fixed fee | In Progress | Front Range | Devon Pitts | 144100 | 82727.81 | 50486.75 | 3646.78 | 4.408% | 0 | 56.62% | 1042 | 785.3 | 107.15 | 10.28%
25-PC-32885 | Maple Fork Reservoir Historic Resources Evaluation | Fixed fee | In Progress | Front Range | Kimberly Daugherty | 1706300 | 1213962.27 | 298115.18 | 2416.88 | 0.1991% | 0 | 24.36% | 17831 | 4288.49 | 31.25 | 0.1753%
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | Fixed fee | In Progress | Front Range | Jeremy Tran | 59600 | 51399.04 | 74823.59 | 23424.55 | 45.57% | 1 | 100% | 797 | 947.72 | 150.72 | 18.91%
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Time and material | Lab/Curation | Front Range | Jeremy Tran | 13300 | 8727.43 | 16463.41 | 7735.98 | 88.64% | 1 | 100% | 68 | 217.8 | 149.8 | 220.3%
25-PC-32926 | Tamarack Pipeline - Cultural Resources Monitoring | Time and material | In Progress | Front Range | Jeremy Tran | 328400 | 212343.44 | 61274.18 | 0 | 0% | 0 | 28.86% | 2847 | 792.34 | 0 | 0%
25-PC-32952 | Eagle Bend Wastewater Plant - Data Recovery | Fixed fee | In Progress | Front Range | Kimberly Daugherty | 299000 | 202368.34 | 101282.84 | 938.39 | 0.4637% | 0 | 49.59% | 0 | 1463.69 | 16.75 | 0%
25-PC-33065 | Wren Hollow GIS Mapping | Fixed fee | In Progress | Front Range | Dean Velazquez | 50400 | 40748.4 | 36866.22 | 0 | 0% | 0 | 90.47% | 423 | 489.27 | 68.56 | 16.21%
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | Fixed fee | In Progress | Front Range | Reginald Vargas | 767800 | 553046.34 | 434972.87 | 0 | 0% | 0 | 78.65% | 10971 | 10950.96 | 62.05 | 0.5656%
25-PC-33105 | Redbud Data Recovery | Fixed fee | In Progress | Front Range | Kimberly Daugherty | 3500 | 2324 | 9006.2 | 6682.2 | 287.5% | 1 | 100% | 23 | 128.24 | 105.24 | 457.6%
25-PC-33136 | North Fork Historic Resources Evaluation | Time and material | In Progress | Front Range | Dean Velazquez | 33200 | 22378.06 | 12542.52 | 615.86 | 2.752% | 0 | 53.3% | 426 | 216.97 | 13.25 | 3.11%
25-PC-33183 | Saltgrass Architectural History Survey | Fixed fee | In Progress | Front Range | Dean Velazquez | 104500 | 79399.1 | 76745.42 | 13594.59 | 17.12% | 1 | 79.54% | 1464 | 1243.87 | 193.51 | 13.22%
25-PC-33206 | Larkspur Water Main - Phase II Testing | Fixed fee | In Progress | Front Range | Mindy Galvan | 48800 | 39449.92 | 22196.75 | 748.05 | 1.896% | 0 | 54.37% | 478 | 321.99 | 9.25 | 1.935%
25-PC-33238 | Phase I: Foxglove Battery Storage Section 106 Consultation | Time and material | Final Billing/Invoice | Front Range | Reginald Vargas | 949900 | 642400.18 | 669394.35 | 26994.17 | 4.202% | 0 | 100% | 9427 | 8871.31 | 0 | 0%
25-PC-33294 | Fern Valley Substation - Built Environment Survey | Fixed fee | In Progress | Front Range | Joanna Herrera | 137200 | 91032.2 | 55566.27 | 757.29 | 0.8319% | 0 | 60.21% | 984 | 967.31 | 140.68 | 14.3%
25-PC-33321 | Hawk Point Section 106 Consultation | Fixed fee | Final Billing/Invoice | Front Range | Devon Pitts | 87200 | 61258 | 52967.28 | 0 | 0% | 0 | 86.47% | 782 | 830.68 | 48.68 | 6.225%
25-PC-33332 | Willow Springs Cultural Resources Assessment | Fixed fee | In Progress | Front Range | Dean Velazquez | 91000 | 69587.7 | 44141.81 | 449.31 | 0.6457% | 0 | 62.79% | 837 | 852.25 | 83.61 | 9.989%
25-PC-33348 | Dove Canyon Cell Tower Phase II Testing | Fixed fee | In Progress | Front Range | Mindy Galvan | 161700 | 117749.94 | 65815.88 | 192.66 | 0.1636% | 0 | 55.73% | 1194 | 840.41 | 3 | 0.2513%
25-PC-33367 | Slate Ridge Rail Siding Archaeological Testing | Time and material | Lab/Curation | Front Range | Dean Velazquez | 150800 | 100689.16 | 32787.21 | 371.02 | 0.3685% | 0 | 32.19% | 3249 | 663.64 | 9.25 | 0.2847%
25-PC-33412 | Tansy Flat Bridge Replacement - GIS Mapping | Time and material | Final Billing/Invoice | Front Range | Mindy Galvan | 1336200 | 914495.28 | 868502.17 | 0 | 0% | 0 | 94.97% | 14331 | 11301.05 | 200.73 | 1.401%
25-PC-33414 | On-Call: Falcon Mesa Substation Historic Resources Evaluation | Fixed fee | Completed | Front Range | Jeremy Tran | 81800 | 64082.12 | 71490.79 | 7408.67 | 11.56% | 1 | 100% | 657 | 1041.03 | 384.03 | 58.45%
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | Fixed fee | In Progress | Front Range | Devon Pitts | 41600 | 29136.64 | 22697.51 | 198.9 | 0.6826% | 0 | 77.22% | 333 | 481.56 | 148.56 | 44.61%
25-PC-33522 | Yarrow Point Architectural History Survey | Time and material | Final Reporting/Review | Front Range | Jeremy Tran | 61800 | 42270.22 | 34825.44 | 3450.71 | 8.163% | 1 | 74.22% | 0 | 482.68 | 13 | 0%
25-PC-33528 | Bramble Creek Wastewater Plant - Environmental Review Support | Time and material | Final Billing/Invoice | Front Range | Joanna Herrera | 138500 | 104844.5 | 84801.75 | 0 | 0% | 0 | 80.88% | 1366 | 1158.81 | 28.43 | 2.081%
25-PC-33535 | Sage Flat Data Recovery | Fixed fee | On Hold | Front Range | Joanna Herrera | 120500 | 91326.95 | 59752.78 | 0 | 0% | 0 | 65.43% | 1783 | 988.66 | 0 | 0%
25-PC-33561 | Task Order 22: Badger Hollow Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | Front Range | Mindy Galvan | 132200 | 85348.32 | 79206.42 | 0 | 0% | 0 | 92.8% | 0 | 1299.86 | 0 | 0%
25-PC-33640 | Tamarack Canal Lining - Cultural Resources Assessment | Fixed fee | In Progress | Front Range | Dean Velazquez | 1444500 | 1192145.85 | 356520.28 | 2237.53 | 0.1877% | 0 | 29.72% | 0 | 4530.4 | 41 | 0%
25-PC-33680 | Quail Run School Campus Cultural Resources Monitoring | Fixed fee | In Progress | Front Range | Kimberly Daugherty | 106800 | 80014.56 | 31893.67 | 78.64 | 0.09828% | 0 | 39.76% | 1057 | 475.79 | 2 | 0.1892%
25-PC-33744 | Blue Heron Canal Lining - Curation | Fixed fee | In Progress | Great Lakes | Nathan Lambert | 87100 | 60133.84 | 44412.55 | 228.43 | 0.3799% | 0 | 73.48% | 1311 | 848.23 | 0 | 0%
25-PC-33750 | Kestrel Butte Archaeological Testing | Fixed fee | Transferred Entity | Great Lakes | Kathleen Galvan | 69600 | 51302.16 | 60286.74 | 14432.08 | 28.13% | 1 | 89.38% | 0 | 1210.73 | 6.5 | 0%
25-PC-33795 | Phase I: Sage Flat Park Improvements Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | Great Lakes | Jeff Pugh | 174500 | 106392.65 | 103920.48 | 0 | 0% | 0 | 97.68% | 1406 | 1248.83 | 36.69 | 2.61%
25-PC-33798 | On-Call: Harbor View Wind Farm Historic Resources Evaluation | Fixed fee | Final Reporting/Review | Great Lakes | Brendan Padilla | 155300 | 128215.68 | 68449.66 | 1440.22 | 1.123% | 0 | 52.26% | 1954 | 1169.99 | 46.76 | 2.393%
25-PC-33827 | Millbrook Transmission Line - Built Environment Survey | Fixed fee | On Hold | Great Lakes | Nathan Lambert | 132500 | 103820.06 | 14173.73 | 0 | 0% | 0 | 13.65% | 1660 | 196.11 | 0 | 0%
25-PC-33841 | Juniper Wash Built Environment Survey | Fixed fee | In Progress | Great Lakes | Kathleen Galvan | 586500 | 416356.35 | 259867.95 | 439.4 | 0.1055% | 0 | 62.31% | 6037 | 6008.86 | 10 | 0.1656%
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Fixed fee | Final Reporting/Review | Great Lakes | Geoffrey Fernandez | 15200 | 11021.49 | 11383.27 | 500.58 | 4.542% | 0 | 98.74% | 163 | 182.5 | 26.98 | 16.55%
25-PC-33855 | Creosote Draw Rail Siding - Paleontological Monitoring | Time and material | Final Reporting/Review | Great Lakes | Karl Valenzuela | 34000 | 23930.44 | 13640.3 | 0 | 0% | 0 | 57% | 451 | 243.48 | 1.09 | 0.2417%
25-PC-33915 | Sage Flat Archaeological Testing | Fixed fee | In Progress | Great Lakes | Angelica Cervantes | 272400 | 198225.48 | 133333.04 | 700.59 | 0.3534% | 0 | 66.91% | 0 | 1659.65 | 11 | 0%
25-PC-33919 | Task Order 18: Coyote Springs Water Main Curation | Fixed fee | Completed | Great Lakes | Kathleen Galvan | 45500 | 26949.65 | 30677.44 | 3727.79 | 13.83% | 1 | 100% | 216 | 408.36 | 192.36 | 89.06%
25-PC-33922 | Slate Ridge Data Recovery | Fixed fee | In Progress | Great Lakes | Nathan Lambert | 22100 | 16113.11 | 33890.1 | 20217.5 | 125.5% | 1 | 84.85% | 227 | 424.16 | 247 | 108.8%
25-PC-33969 | Sumac Ridge Archaeological Testing | Fixed fee | In Progress | Great Lakes | Leonard Mejia | 13200 | 10134.96 | 5999.72 | 0 | 0% | 0 | 59.2% | 156 | 102.4 | 0 | 0%
25-PC-34036 | Kestrel Butte Battery Storage - Phase I Survey | Time and material | Lab/Curation | Great Lakes | Gina Beltran | 62300 | 41495.74 | 38677.3 | 3705.1 | 8.929% | 1 | 84.28% | 434 | 529.97 | 144.69 | 33.34%
25-PC-34077 | Sage Flat Levee Repair Class III Survey | Fixed fee | In Progress | Great Lakes | Leonard Mejia | 580500 | 459697.95 | 229510.92 | 3014.41 | 0.6557% | 0 | 49.27% | 4668 | 2587 | 36.75 | 0.7873%
25-PC-34088 | Timber Gap Harbor Dredging Cultural Resources Monitoring | Time and material | In Progress | Great Lakes | Leonard Mejia | 47300 | 29041.82 | 17359.62 | 0 | 0% | 0 | 59.77% | 211 | 222.87 | 12.95 | 6.137%
25-PC-34090 | Thistle Down Data Recovery | Time and material | In Progress | Great Lakes | Geoffrey Fernandez | 66200 | 46862.98 | 24068 | 35.61 | 0.07599% | 0 | 51.28% | 744 | 412.51 | 0.75 | 0.1008%
25-PC-34144 | On-Call: Dove Canyon School Campus Phase II Testing | Fixed fee | Final Billing/Invoice | Great Lakes | Karl Valenzuela | 23400 | 16230.24 | 19243.13 | 3012.89 | 18.56% | 1 | 100% | 0 | 291.52 | 0 | 0%
25-PC-34151 | Bramble Creek Fiber Route Cultural Resources Monitoring | Time and material | In Progress | Great Lakes | Angelica Cervantes | 505100 | 334224.67 | 126809.69 | 1192.28 | 0.3567% | 0 | 37.58% | 0 | 1523.39 | 15.25 | 0%
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | Time and material | In Progress | Great Lakes | Geoffrey Fernandez | 53000 | 36718.4 | 42629.29 | 5988.93 | 16.31% | 1 | 99.79% | 294 | 522.98 | 228.98 | 77.88%
25-PC-34374 | Tansy Flat Reservoir Cultural Resources Assessment | Time and material | In Progress | Great Lakes | Gina Beltran | 14100 | 9871.41 | 3661.74 | 0 | 0% | 0 | 37.09% | 102 | 49.71 | 0 | 0%
25-PC-34382 | Meadowlark Paleontological Monitoring | Time and material | Completed | Great Lakes | Gina Beltran | 34600 | 26125.87 | 33963.63 | 7837.76 | 30% | 1 | 100% | 250 | 486.13 | 236.13 | 94.45%
25-PC-34451 | North Fork Curation | Time and material | In Progress | Great Lakes | Robin Mercado | 46400 | 32526.4 | 41685.39 | 10012.93 | 30.78% | 1 | 97.37% | 310 | 515.81 | 205.81 | 66.39%
25-PC-34537 | Raven Rock Harbor Dredging - Paleontological Monitoring | Fixed fee | On Hold | Great Lakes | Jeff Pugh | 78900 | 63481.3 | 27987.47 | 0 | 0% | 0 | 44.09% | 682 | 403.88 | 0 | 0%
25-PC-34652 | Coyote Springs Section 106 Consultation | Fixed fee | In Progress | Great Lakes | Gina Beltran | 210700 | 180928.09 | 151256.78 | 26592.7 | 14.7% | 1 | 68.9% | 1733 | 2194.06 | 666.54 | 38.46%
25-PC-34681 | Hawk Point Pipeline Section 106 Consultation | Fixed fee | In Progress | Great Lakes | Brendan Padilla | 715200 | 430908 | 159498.08 | 2674.89 | 0.6208% | 0 | 36.39% | 5498 | 2152.34 | 43.5 | 0.7912%
25-PC-34732 | Thistle Down Trail Architectural History Survey | Fixed fee | In Progress | Great Lakes | Geoffrey Fernandez | 101800 | 76441.62 | 46880.67 | 0 | 0% | 0 | 61.33% | 554 | 685.21 | 131.21 | 23.68%
25-PC-34768 | On-Call: Oak Terrace Wastewater Plant Section 106 Consultation | Time and material | Final Billing/Invoice | Great Lakes | Angelica Cervantes | 119400 | 88654.5 | 114603.2 | 25948.7 | 29.27% | 1 | 100% | 0 | 1542.53 | 0 | 0%
25-PC-34772 | Windmill Flat Paleontological Monitoring | Time and material | Final Reporting/Review | Great Lakes | Brendan Padilla | 186900 | 126437.85 | 11925.12 | 0 | 0% | 0 | 9.432% | 1386 | 228.91 | 0 | 0%
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | Time and material | In Progress | Great Lakes | Gina Beltran | 82200 | 51638.04 | 83204.29 | 31566.25 | 61.13% | 1 | 100% | 662 | 1259.01 | 597.01 | 90.18%
25-PC-34843 | Elk Meadow Highway Widening Data Recovery | Fixed fee | Final Billing/Invoice | Gulf Coast | Bernard Erickson | 188000 | 136544.4 | 132593.97 | 0 | 0% | 0 | 97.11% | 1753 | 2502.84 | 749.84 | 42.77%
25-PC-34850 | Thistle Down Section 106 Consultation | Time and material | In Progress | Gulf Coast | Wyatt Erickson | 201300 | 117035.82 | 94500.26 | 18353.14 | 15.68% | 1 | 65.06% | 1638 | 1329.5 | 298.37 | 18.22%
25-PC-34871 | Willow Springs GIS Mapping | Fixed fee | Lab/Curation | Gulf Coast | Sean Jennings | 338100 | 260979.39 | 150361.81 | 1770.83 | 0.6785% | 0 | 56.94% | 3386 | 2115.35 | 27 | 0.7974%
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | Fixed fee | In Progress | Gulf Coast | Wyatt Erickson | 224400 | 165046.2 | 116067.93 | 0 | 0% | 0 | 70.32% | 2686 | 2208.37 | 0 | 0%
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | Time and material | In Progress | Gulf Coast | Bernard Erickson | 71400 | 48880.44 | 56947.79 | 10091.75 | 20.65% | 1 | 95.86% | 799 | 1070.96 | 271.96 | 34.04%
25-PC-35084 | On-Call: Fern Valley Wastewater Plant Class III Survey | Fixed fee | Final Reporting/Review | Gulf Coast | Bernard Erickson | 204900 | 133588.01 | 92924.35 | 4460.15 | 3.339% | 0 | 66.22% | 2566 | 2020.33 | 327.22 | 12.75%
25-PC-35131 | Tamarack Phase II Testing | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 311900 | 227562.24 | 95549.55 | 0 | 0% | 0 | 41.99% | 6216 | 1950.68 | 0 | 0%
25-PC-35138 | Foxglove Mixed-Use Development - Data Recovery | Time and material | In Progress | Gulf Coast | Sean Jennings | 815000 | 517757.75 | 425247 | 6862.1 | 1.325% | 0 | 80.81% | 8374 | 6479.96 | 82.75 | 0.9882%
25-PC-35168 | Quail Run Park Improvements - GIS Mapping | Time and material | Completed | Gulf Coast | Bernard Erickson | 330300 | 212151.69 | 204097.59 | 0 | 0% | 0 | 96.2% | 4369 | 3761.44 | 0 | 0%
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | Time and material | In Progress | Gulf Coast | Wyatt Erickson | 33200 | 23495.64 | 28098.75 | 5961.35 | 25.37% | 1 | 94.22% | 273 | 532.8 | 259.8 | 95.16%
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | Time and material | In Progress | Gulf Coast | Bernard Erickson | 49900 | 35982.89 | 42125.74 | 8893.31 | 24.72% | 1 | 92.36% | 665 | 934.84 | 301.45 | 45.33%
25-PC-35295 | Copper Flats Architectural History Survey | Time and material | In Progress | Gulf Coast | Bernard Erickson | 80400 | 54551.4 | 39686.68 | 0 | 0% | 0 | 72.75% | 973 | 559.52 | 0 | 0%
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 19400 | 13919.5 | 36287.63 | 22368.13 | 160.7% | 1 | 100% | 148 | 687.23 | 539.23 | 364.3%
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | Fixed fee | In Progress | Gulf Coast | Courtney Daugherty | 25100 | 20032.31 | 27206.95 | 7174.64 | 35.82% | 1 | 100% | 321 | 594.8 | 273.8 | 85.3%
25-PC-35431 | Task Order 26: Wildrye Mine Expansion Environmental Review Support | Fixed fee | On Hold | High Desert | Eileen Poole | 304700 | 252565.83 | 6736.99 | 0 | 0% | 0 | 2.667% | 4186 | 136.04 | 0 | 0%
25-PC-35442 | Pebble Beach Road Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | High Desert | Eileen Poole | 86600 | 65071.24 | 72181.81 | 7110.57 | 10.93% | 1 | 100% | 942 | 1052.7 | 161.42 | 17.14%
25-PC-35470 | Lantern Bay Reservoir Data Recovery | Time and material | Final Billing/Invoice | High Desert | Jody Wang | 484000 | 325683.6 | 348164.43 | 22480.83 | 6.903% | 1 | 100% | 4235 | 5681.02 | 1446.02 | 34.14%
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | Time and material | In Progress | High Desert | Kathy Hurley | 136900 | 90994.45 | 119032.94 | 31552.73 | 34.68% | 1 | 96.14% | 1344 | 1611.58 | 431 | 32.07%
25-PC-35496 | Silver Lake Airport Apron Class III Survey | Time and material | In Progress | High Desert | Kathy Hurley | 15200 | 10132.32 | 10426.7 | 3630.62 | 35.83% | 1 | 67.07% | 155 | 116.78 | 22.53 | 14.54%
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | Fixed fee | In Progress | High Desert | Bridget Maddox | 98800 | 78447.2 | 61430.39 | 11305.93 | 14.41% | 1 | 63.9% | 707 | 710.44 | 176.98 | 25.03%
25-PC-35553 | Rushgrass Draw Rail Siding - Data Recovery | Time and material | In Progress | High Desert | Eileen Poole | 589900 | 444589.27 | 314340.18 | 11146.45 | 2.507% | 0 | 68.2% | 8862 | 5044.26 | 248.7 | 2.806%
25-PC-35620 | Task Order 24: Hackberry Bend Solar Class III Survey | Time and material | Completed | High Desert | Jody Wang | 2007200 | 1423506.24 | 1286006.12 | 0 | 0% | 0 | 90.34% | 0 | 20551.52 | 0 | 0%
25-PC-35740 | Oak Terrace Transmission Line - Historic Resources Evaluation | Fixed fee | In Progress | High Desert | Kathy Hurley | 28600 | 15121.1 | 303.1 | 0 | 0% | 0 | 2.004% | 206 | 5.11 | 0 | 0%
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | Fixed fee | In Progress | High Desert | Kathy Hurley | 204800 | 136396.8 | 140077.69 | 3680.89 | 2.699% | 0 | 100% | 2527 | 3009.42 | 482.42 | 19.09%
25-PC-35779 | Task Order 9: Juniper Wash Wastewater Plant Built Environment Survey | Fixed fee | In Progress | High Desert | Bridget Maddox | 124800 | 84973.75 | 70526.1 | 12017.26 | 14.14% | 1 | 68.86% | 746 | 1061.75 | 364.74 | 48.89%
25-PC-35850 | Pebble Beach Road Environmental Review Support | Time and material | Cost Tracking on Closed Project | High Desert | Bridget Maddox | 53400 | 37978.08 | 32074.27 | 0 | 0% | 0 | 84.45% | 355 | 584.04 | 229.04 | 64.52%
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | Fixed fee | In Progress | High Desert | Jody Wang | 83700 | 61050.78 | 55992.15 | 176.71 | 0.2894% | 0 | 91.42% | 872 | 1172.23 | 300.23 | 34.43%
25-PC-35958 | Task Order 20: Pebble Beach Road Levee Repair Class III Survey | Fixed fee | Final Billing/Invoice | High Desert | Jody Wang | 67300 | 54896.61 | 61901.7 | 7005.09 | 12.76% | 1 | 100% | 806 | 1102.39 | 296.39 | 36.77%
25-PC-35963 | Quail Run Substation - Section 106 Consultation | Time and material | In Progress | High Desert | Kathy Hurley | 320000 | 216192 | 202041.59 | 25320.74 | 11.71% | 1 | 81.74% | 2310 | 3644.92 | 1334.92 | 57.79%
25-PC-35970 | Eagle Bend Wind Farm Phase II Testing | Fixed fee | In Progress | High Desert | Bridget Maddox | 53200 | 38886.26 | 11957.7 | 115 | 0.2957% | 0 | 30.45% | 0 | 247.43 | 2.75 | 0%
25-PC-36007 | Larkspur Rail Siding Phase II Testing | Fixed fee | On Hold | High Desert | Eileen Poole | 21700 | 16244.62 | 159.18 | 0 | 0% | 0 | 0.9799% | 248 | 2.45 | 0 | 0%
25-PC-36030 | Stone Mill Solar Cultural Resources Monitoring | Time and material | Completed | High Desert | Bridget Maddox | 89200 | 57064.52 | 60255.01 | 3190.49 | 5.591% | 1 | 100% | 963 | 1014.76 | 51.76 | 5.375%
25-PC-36051 | Riverbend Levee Repair Archaeological Testing | Fixed fee | In Progress | High Desert | Bridget Maddox | 405400 | 250415.58 | 169641.96 | 0 | 0% | 0 | 67.74% | 3587 | 2787.64 | 0 | 0%
25-PC-36071 | Task Order 12: Foxglove Transmission Line Archaeological Testing | Fixed fee | Final Billing/Invoice | High Desert | Eileen Poole | 245200 | 202167.4 | 191722.88 | 0 | 0% | 0 | 94.83% | 2754 | 3000.78 | 246.78 | 8.961%
25-PC-36093 | Pine Hollow Pipeline Cultural Resources Assessment | Fixed fee | Lab/Curation | High Desert | Jody Wang | 213300 | 157884.66 | 111476.29 | 703.27 | 0.4454% | 0 | 70.16% | 2595 | 2445.66 | 18 | 0.6936%
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | Time and material | In Progress | High Desert | Kathy Hurley | 114200 | 78124.22 | 79562.78 | 15841.49 | 20.28% | 1 | 81.56% | 1254 | 1039.37 | 101.8 | 8.118%
25-PC-36197 | Windmill Flat Rail Siding - Historic Resources Evaluation | Fixed fee | On Hold | High Desert | Eileen Poole | 35900 | 26935.77 | 21592.01 | 0 | 0% | 0 | 80.16% | 0 | 406.71 | 0 | 0%
25-PC-36251 | Kestrel Butte Environmental Review Support | Fixed fee | Lab/Curation | Island | Joan Mathis | 39200 | 30446.64 | 49335.55 | 18888.91 | 62.04% | 1 | 100% | 277 | 521.62 | 244.62 | 88.31%
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | Time and material | In Progress | Island | Joan Mathis | 28100 | 19141.72 | 16573.11 | 247.45 | 1.293% | 0 | 85.29% | 0 | 247.63 | 5.5 | 0%
25-PC-36313 | Task Order 27: Coyote Springs Solar Historic Resources Evaluation | Time and material | Completed | Island | Briana Melton | 135100 | 94691.59 | 123099.07 | 28407.48 | 30% | 1 | 100% | 932 | 1560.66 | 628.66 | 67.45%
25-PC-36332 | Goldfinch Data Recovery | Fixed fee | In Progress | Island | Briana Melton | 871000 | 618958.05 | 336119.33 | 1497.11 | 0.2419% | 0 | 54.06% | 11625 | 5793.5 | 31.5 | 0.271%
25-PC-36336 | Sea Oat Canal Lining Data Recovery | Fixed fee | In Progress | Island | Briana Melton | 36400 | 25854.92 | 23699.14 | 1689.57 | 6.535% | 1 | 85.13% | 278 | 326.76 | 48.76 | 17.54%
25-PC-36352 | Phase I: Plover Cove Substation Paleontological Monitoring | Fixed fee | In Progress | Island | Joan Mathis | 3262900 | 2263196.88 | 313300.73 | 1935.75 | 0.08553% | 0 | 13.76% | 15961 | 3798.61 | 31.5 | 0.1974%
25-PC-36366 | Lone Pine Solar Data Recovery | Fixed fee | In Progress | Island | Briana Melton | 119500 | 101598.9 | 38701.27 | 156.71 | 0.1542% | 0 | 37.94% | 0 | 550.82 | 3.25 | 0%
25-PC-36464 | Larkspur Highway Widening Cultural Resources Assessment | Time and material | In Progress | Island | Joan Mathis | 102300 | 72751.63 | 60185.29 | -605.25 | -0.8319% | 0 | 83.56% | 0 | 864.91 | -5 | 0%
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | Fixed fee | In Progress | Island | Becky Velazquez | 33100 | 25870.96 | 34277.75 | 8406.79 | 32.5% | 1 | 100% | 241 | 431.15 | 190.15 | 78.9%
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | Fixed fee | In Progress | Island | Joan Mathis | 88300 | 54269.18 | 42036.07 | 546.42 | 1.007% | 0 | 76.45% | 568 | 666.6 | 98.6 | 17.36%
25-PC-36532 | Sparrow Hill Cell Tower - Architectural History Survey | Fixed fee | On Hold | Island | Joan Mathis | 67300 | 46773.5 | 22227.54 | 0 | 0% | 0 | 47.52% | 519 | 302.58 | 0 | 0%
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | Island | Becky Velazquez | 116000 | 66050.4 | 48723.63 | 0 | 0% | 0 | 73.77% | 559 | 531.73 | 0 | 0%
25-PC-36637 | Lantern Bay Fiber Route Environmental Review Support | Fixed fee | Final Billing/Invoice | Lakeshore | Terrence Gillespie | 44400 | 36003.96 | 29922.84 | 0 | 0% | 0 | 83.11% | 324 | 417.12 | 93.12 | 28.74%
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | Time and material | In Progress | Lakeshore | Lucas Benson | 181300 | 117609.31 | 164790.18 | 47180.87 | 40.12% | 1 | 100% | 1691 | 2350.83 | 659.83 | 39.02%
25-PC-36645 | Falcon Mesa Archaeological Testing | Fixed fee | In Progress | Lakeshore | Jeanette Riddle | 25400 | 20302.22 | 38922.6 | 18620.38 | 91.72% | 1 | 100% | 525 | 626.6 | 111.21 | 21.18%
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | Time and material | In Progress | Lakeshore | Lucas Benson | 137400 | 99958.5 | 83440.54 | 538.19 | 0.5384% | 0 | 82.94% | 1489 | 1046.6 | 6.75 | 0.4533%
25-PC-36657 | Stone Mill Park Improvements Phase II Testing | Time and material | Final Reporting/Review | Lakeshore | Jeanette Riddle | 255700 | 186833.25 | 88980.55 | 549.98 | 0.2944% | 0 | 47.33% | 1796 | 1064.16 | 9.5 | 0.529%
25-PC-36697 | Phase III: Juniper Wash Solar Built Environment Survey | Fixed fee | Completed | Lakeshore | Lucas Benson | 197400 | 133797.72 | 127892.21 | 0 | 0% | 0 | 95.59% | 2124 | 1497.57 | 0 | 0%
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Fixed fee | Final Reporting/Review | Lakeshore | Jeanette Riddle | 74000 | 56358.4 | 66079.15 | 9720.75 | 17.25% | 1 | 100% | 393 | 835.85 | 442.85 | 112.7%
25-PC-36799 | Meadowlark Substation Phase I Survey | Fixed fee | Final Reporting/Review | Hill Country | Gail Meza | 32900 | 26389.09 | 33048.52 | 6659.43 | 25.24% | 1 | 100% | 161 | 487.82 | 326.82 | 203%
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | Fixed fee | In Progress | Hill Country | Samuel Wilkerson | 24200 | 16235.78 | 26420.57 | 10184.79 | 62.73% | 1 | 100% | 182 | 302.83 | 120.83 | 66.39%
25-PC-36832 | Stone Mill Phase I Survey | Fixed fee | In Progress | Hill Country | Theresa Fernandez | 78400 | 52449.6 | 29456.38 | 0 | 0% | 0 | 56.16% | 565 | 332.57 | 0 | 0%
25-PC-36838 | Phase II: Granite Pass Highway Widening Environmental Review Support | Time and material | Final Reporting/Review | Hill Country | Samuel Wilkerson | 216400 | 160499.18 | 158776.87 | 18565.68 | 11.57% | 1 | 87.36% | 1740 | 1833.31 | 388.85 | 22.35%
25-PC-36876 | Kestrel Butte Wastewater Plant - GIS Mapping | Fixed fee | Completed | Hill Country | Samuel Wilkerson | 337000 | 240685.4 | 312891.02 | 72205.62 | 30% | 1 | 100% | 0 | 3645.71 | 0 | 0%
25-PC-36896 | Slate Ridge Pipeline Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Hill Country | Danielle Villanueva | 184200 | 117335.4 | 139790.5 | 22455.1 | 19.14% | 1 | 100% | 761 | 1519.71 | 758.71 | 99.7%
25-PC-36909 | Aspen Ridge Water Main Section 106 Consultation | Fixed fee | Final Billing/Invoice | Hill Country | Danielle Villanueva | 41900 | 30260.18 | 31926.6 | 1666.42 | 5.507% | 1 | 100% | 381 | 438.98 | 60.12 | 15.78%
25-PC-36971 | North Fork Historic Resources Evaluation | Fixed fee | Completed | Hill Country | Suzanne Mcmillan | 85100 | 64888.75 | 84355.38 | 19466.63 | 30% | 1 | 100% | 715 | 1046.08 | 331.08 | 46.3%
25-PC-36988 | Cedar Hollow Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | Hill Country | Gail Meza | 246000 | 173331.6 | 162799.16 | 0 | 0% | 0 | 93.92% | 1370 | 2096.53 | 726.53 | 53.03%
25-PC-36993 | Sandpiper Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | Hill Country | Danielle Villanueva | 702000 | 446191.2 | 385770.37 | 0 | 0% | 0 | 86.46% | 6519 | 4925.38 | 0 | 0%
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | Time and material | In Progress | Hill Country | Glen Delacruz | 75400 | 50299.34 | 90901.92 | 40602.58 | 80.72% | 1 | 100% | 503 | 1020.71 | 517.71 | 102.9%
25-PC-37188 | On-Call: Lone Pine Airport Apron Cultural Resources Assessment | Time and material | In Progress | Hill Country | Suzanne Mcmillan | 131600 | 95554.76 | 53871.13 | 0 | 0% | 0 | 56.38% | 906 | 818.66 | 42.6 | 4.702%
25-PC-37359 | Bramble Creek Water Main Curation | Fixed fee | Completed | Hill Country | Danielle Villanueva | 228400 | 164950.48 | 143914.59 | 0 | 0% | 0 | 87.25% | 2116 | 1928.81 | 0 | 0%
25-PC-37371 | Phase II: Ember Valley Water Main Class III Survey | Fixed fee | In Progress | Piedmont | Maria Parrish | 292700 | 199428.52 | 86077.44 | 1510.29 | 0.7573% | 0 | 42.4% | 1798 | 1243.32 | 26.5 | 1.474%
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | Fixed fee | In Progress | Piedmont | Maria Parrish | 59200 | 50698.88 | 47030.53 | 5506.86 | 10.86% | 1 | 81.9% | 595 | 599.34 | 91.96 | 15.46%
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Time and material | Cost Tracking on Closed Project | Piedmont | Megan Pineda | 83200 | 60186.88 | 78242.94 | 18056.06 | 30% | 1 | 100% | 560 | 1203.6 | 643.6 | 114.9%
25-PC-37487 | Sparrow Hill Airport Apron Environmental Review Support | Fixed fee | Final Billing/Invoice | Piedmont | Annette Vaughan | 43400 | 34525.12 | 25603.88 | 0 | 0% | 0 | 74.16% | 0 | 408.62 | 0 | 0%
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | Time and material | In Progress | Piedmont | Jody Chung | 458200 | 301449.78 | 240796.49 | 0 | 0% | 0 | 79.88% | 5452 | 3527.4 | 0 | 0%
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Fixed fee | Lab/Curation | Piedmont | Jody Chung | 21500 | 15617.6 | 19499.4 | 6375.94 | 40.83% | 1 | 84.03% | 227 | 346 | 125.39 | 55.24%
25-PC-37544 | Sparrow Hill Historic Resources Evaluation | Fixed fee | Final Reporting/Review | Piedmont | Maria Parrish | 1009600 | 644730.56 | 504318.97 | 0 | 0% | 0 | 78.22% | 7236 | 7905.63 | 669.63 | 9.254%
25-PC-37612 | Elk Meadow Solar Historic Resources Evaluation | Time and material | On Hold | Piedmont | Maria Parrish | 134400 | 94725.12 | 69378.25 | 0 | 0% | 0 | 73.24% | 1489 | 1193.62 | 0 | 0%
25-PC-37630 | Goldfinch Solar Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Piedmont | Jody Chung | 528200 | 365998.97 | 475798.66 | 109799.69 | 30% | 1 | 100% | 4239 | 6994.37 | 2755.37 | 65%
25-PC-37675 | Copper Flats Park Improvements - Phase I Survey | Fixed fee | Final Billing/Invoice | Piedmont | Megan Pineda | 129900 | 96138.99 | 76435.27 | 0 | 0% | 0 | 79.5% | 740 | 1204.33 | 464.33 | 62.75%
25-PC-37732 | Hawk Point Housing Development Class III Survey | Fixed fee | In Progress | Piedmont | Megan Pineda | 72900 | 45824.94 | 40294.48 | 6506.92 | 14.2% | 1 | 73.73% | 436 | 491.73 | 97.07 | 22.26%
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Time and material | Final Reporting/Review | Piedmont | Maria Parrish | 72200 | 44893.96 | 57390.52 | 12496.56 | 27.84% | 1 | 100% | 432 | 505.89 | 73.89 | 17.1%
25-PC-37841 | Coyote Springs Data Recovery | Fixed fee | On Hold | Piedmont | Annette Vaughan | 243900 | 144430.51 | 35409.46 | 0 | 0% | 0 | 24.52% | 1293 | 503.38 | 0 | 0%
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | Fixed fee | In Progress | Piedmont | Megan Pineda | 7900 | 6020.59 | 6629.3 | 608.71 | 10.11% | 1 | 100% | 115 | 122.78 | 8.03 | 6.983%
25-PC-37903 | Sandpiper Mine Expansion Curation | Fixed fee | Final Billing/Invoice | Piedmont | Jody Chung | 195600 | 128411.4 | 166934.82 | 38523.42 | 30% | 1 | 100% | 2171 | 2581.33 | 410.33 | 18.9%
25-PC-37920 | Heron Marsh Mine Expansion Class III Survey | Time and material | In Progress | Piedmont | Maria Parrish | 138600 | 92806.56 | 44711.28 | 634.58 | 0.6838% | 0 | 47.49% | 2102 | 943.45 | 15 | 0.7136%
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | Fixed fee | In Progress | Prairie | Sherry Lloyd | 148100 | 106809.72 | 79254.53 | 448.42 | 0.4198% | 0 | 73.78% | 1080 | 986.94 | 29.08 | 2.693%
25-PC-37979 | Pine Hollow Wind Farm - Built Environment Survey | Fixed fee | Final Billing/Invoice | Prairie | Sherry Lloyd | 230300 | 172720.13 | 202559.1 | 29838.97 | 17.28% | 1 | 100% | 1635 | 3651.33 | 2016.33 | 123.3%
25-PC-37994 | Blue Heron Harbor Dredging - Curation | Time and material | On Hold | Prairie | Sherry Lloyd | 326300 | 217772.62 | 62933.16 | 0 | 0% | 0 | 28.9% | 0 | 1164.04 | 0 | 0%
25-PC-38006 | Timber Gap Wastewater Plant Archaeological Testing | Time and material | In Progress | Prairie | Sherry Lloyd | 112000 | 75667.2 | 36469.16 | 537.19 | 0.7099% | 0 | 47.49% | 1505 | 670.61 | 12.25 | 0.814%
25-PC-38036 | Elk Meadow Mixed-Use Development - Maritime Remote Sensing Survey | Fixed fee | Completed | Prairie | Sherry Lloyd | 27300 | 23352.42 | 30358.15 | 7005.73 | 30% | 1 | 100% | 349 | 639.87 | 290.87 | 83.34%
25-PC-38042 | Oak Terrace School Campus GIS Mapping | Fixed fee | In Progress | Prairie | Sherry Lloyd | 24300 | 19082.79 | 15820.03 | 0 | 0% | 0 | 82.9% | 136 | 175.63 | 39.63 | 29.14%
25-PC-38070 | Phase III: Willow Springs Wastewater Plant Historic Resources Evaluation | Fixed fee | In Progress | Prairie | Sherry Lloyd | 132800 | 116864 | 72689.82 | 0 | 0% | 0 | 62.2% | 0 | 1435.62 | 0 | 0%
25-PC-38107 | Task Order 13: Pebble Beach Road Substation Cultural Resources Monitoring | Fixed fee | In Progress | Prairie | Sherry Lloyd | 234600 | 208913.08 | 69422.07 | 858.71 | 0.411% | 0 | 32.82% | 0 | 1468.45 | 21.5 | 0%
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | Fixed fee | In Progress | Prairie | Sherry Lloyd | 25300 | 16961.12 | 13931.44 | 116.7 | 0.688% | 0 | 81.45% | 345 | 275.35 | 2.5 | 0.7246%
25-PC-38196 | Sea Oat Cell Tower Built Environment Survey | Fixed fee | In Progress | Prairie | Sherry Lloyd | 1160700 | 717428.67 | 425399.95 | 130.49 | 0.01819% | 0 | 59.28% | 10395 | 10611.29 | 216.29 | 2.081%
25-PC-38282 | Task Order 16: Fern Valley Reservoir Architectural History Survey | Time and material | In Progress | Prairie | Sherry Lloyd | 1334100 | 876348.58 | 522008.11 | 0 | 0% | 0 | 59.57% | 17329 | 9600.4 | 0 | 0%
25-PC-38296 | Ember Valley Pipeline - GIS Mapping | Fixed fee | In Progress | Prairie | Sherry Lloyd | 173000 | 111169.8 | 53923.32 | 1231.77 | 1.108% | 0 | 47.4% | 1482 | 1040.78 | 127.09 | 8.576%
25-PC-38332 | Redbud GIS Mapping | Fixed fee | In Progress | Prairie | Sherry Lloyd | 899800 | 754394.62 | 592323.18 | 167.65 | 0.02222% | 0 | 78.49% | 13961 | 11610.16 | 186.37 | 1.335%
25-PC-38333 | Pine Hollow Cell Tower Phase II Testing | Fixed fee | In Progress | Prairie | Sherry Lloyd | 78300 | 51450.4 | 37360.87 | 0 | 0% | 0 | 72.62% | 726 | 773 | 47.89 | 6.596%
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | Fixed fee | In Progress | Prairie | Sherry Lloyd | 136400 | 86736.76 | 63001.3 | 0 | 0% | 0 | 72.64% | 1342 | 1037.92 | 0 | 0%
25-PC-38461 | Rushgrass Draw Substation Phase II Testing | Fixed fee | Final Billing/Invoice | Red Rock | Lydia Cisneros | 187400 | 143548.4 | 140284.68 | 0 | 0% | 0 | 97.73% | 0 | 2290.29 | 0 | 0%
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | Time and material | In Progress | Red Rock | Jeanette Chung | 496400 | 357705.84 | 311579.89 | 34685.88 | 9.697% | 1 | 77.41% | 5296 | 5125.85 | 859.54 | 16.23%
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | Fixed fee | In Progress | Red Rock | Lydia Cisneros | 176400 | 137697.84 | 120438.25 | 9489.37 | 6.891% | 1 | 80.57% | 2964 | 2549.6 | 227.54 | 7.677%
25-PC-38596 | Tansy Flat Pipeline Data Recovery | Fixed fee | In Progress | Red Rock | Bruce Suarez | 178000 | 148416.4 | 76585.73 | 0 | 0% | 0 | 51.6% | 0 | 1313.68 | 0 | 0%
25-PC-38606 | Silver Lake School Campus - Maritime Remote Sensing Survey | Fixed fee | In Progress | Red Rock | Jeanette Chung | 34800 | 26816.2 | 15688.36 | 0 | 0% | 0 | 58.5% | 379 | 247.19 | 0 | 0%
25-PC-38659 | On-Call: Elk Meadow School Campus Architectural History Survey | Time and material | Completed | Red Rock | Bruce Suarez | 3059900 | 2017698.06 | 1793049.08 | 0 | 0% | 0 | 88.87% | 0 | 26327.98 | 0 | 0%
25-PC-38701 | Slate Ridge Curation | Time and material | In Progress | Red Rock | Javier Newman | 156400 | 98735.32 | 71024.19 | 900.4 | 0.9119% | 0 | 71.02% | 1417 | 1132.8 | 20.75 | 1.464%
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | Fixed fee | In Progress | Red Rock | Javier Newman | 63900 | 41637.24 | 60770.39 | 19133.15 | 45.95% | 1 | 100% | 740 | 1032.51 | 292.51 | 39.53%
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Fixed fee | Final Reporting/Review | Red Rock | Bruce Suarez | 10400 | 5866.64 | 18017.53 | 12150.89 | 207.1% | 1 | 100% | 62 | 295.49 | 233.49 | 376.6%
25-PC-38879 | Kestrel Butte Built Environment Survey | Fixed fee | In Progress | Red Rock | Marisa Odom | 119700 | 70323.75 | 51984.23 | 0 | 0% | 0 | 73.92% | 712 | 1109.71 | 397.71 | 55.86%
25-PC-38970 | Ember Valley Park Improvements Curation | Time and material | Final Billing/Invoice | Red Rock | Jeanette Chung | 160100 | 117257.24 | 130219.78 | 12962.54 | 11.05% | 1 | 100% | 2288 | 2367.23 | 97.6 | 4.266%
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | Time and material | In Progress | Red Rock | Tina Aguirre | 244000 | 174704 | 157468.06 | 8259.44 | 4.728% | 0 | 85.41% | 1978 | 2684.86 | 706.86 | 35.74%
25-PC-39055 | Dove Canyon Transmission Line - Cultural Resources Assessment | Time and material | Final Billing/Invoice | Red Rock | Jeanette Chung | 128700 | 90984.64 | 109223.65 | 18239.01 | 20.05% | 1 | 100% | 0 | 2039.45 | 0 | 0%
25-PC-39085 | Slate Ridge Environmental Review Support | Fixed fee | In Progress | Red Rock | Bruce Suarez | 120700 | 69209.38 | 68696.84 | 402.51 | 0.5816% | 0 | 98.68% | 1216 | 1150.4 | 8.5 | 0.699%
25-PC-39093 | Goldfinch Canal Lining Phase I Survey | Fixed fee | In Progress | Red Rock | Tina Aguirre | 100100 | 73673.6 | 36221.91 | 782.06 | 1.062% | 0 | 48.1% | 0 | 790.01 | 18.75 | 0%
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | Fixed fee | In Progress | Red Rock | Shelia Horne | 90300 | 58198.35 | 43819.98 | 308.89 | 0.5308% | 0 | 74.76% | 858 | 872.78 | 14.78 | 1.723%
25-PC-39187 | Windmill Flat Trail - Architectural History Survey | Fixed fee | Lab/Curation | Red Rock | Javier Newman | 28100 | 19470.49 | 9569.28 | 0 | 0% | 0 | 49.15% | 150 | 154.03 | 5.46 | 3.64%
25-PC-39222 | Phase I: Badger Hollow Trail GIS Mapping | Fixed fee | Completed | Red Rock | Lydia Cisneros | 27000 | 21648.6 | 19644.61 | 0 | 0% | 0 | 90.74% | 359 | 296.91 | 0 | 0%
25-PC-39318 | Lone Pine Fiber Route - Class III Survey | Fixed fee | In Progress | Red Rock | Marisa Odom | 104300 | 69818.42 | 47626.24 | 145.5 | 0.2084% | 0 | 68.01% | 810 | 740.84 | 3 | 0.3704%
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Time and material | Final Reporting/Review | Red Rock | Tina Aguirre | 55900 | 39633.1 | 38428.92 | 8177.22 | 20.63% | 1 | 76.33% | 529 | 687.65 | 177.65 | 33.58%
25-PC-39398 | Silver Lake Housing Development - Data Recovery | Fixed fee | Final Reporting/Review | Red Rock | Marisa Odom | 103300 | 81096.61 | 52431.07 | 0 | 0% | 0 | 64.65% | 1428 | 885.2 | 0 | 0%
25-PC-39422 | Willow Springs Historic Resources Evaluation | Fixed fee | In Progress | Red Rock | Bruce Suarez | 56900 | 45036.35 | 11658.26 | -154.89 | -0.3439% | 0 | 26.23% | 628 | 205.84 | -3.25 | -0.5175%
25-PC-39424 | Tansy Flat Cultural Resources Assessment | Fixed fee | In Progress | Red Rock | Shelia Horne | 19700 | 13882.59 | 16267.84 | 2385.25 | 17.18% | 1 | 100% | 213 | 233.21 | 20.21 | 9.488%
25-PC-39458 | Larkspur Park Improvements Paleontological Monitoring | Time and material | In Progress | Red Rock | Bruce Suarez | 345000 | 242983.5 | 143586.3 | 1313.44 | 0.5405% | 0 | 58.55% | 4713 | 2033.64 | 16 | 0.3395%
25-PC-39489 | Phase II: Fern Valley Transmission Line Paleontological Monitoring | Fixed fee | Completed | Red Rock | Marisa Odom | 460000 | 342148 | 315421.89 | 0 | 0% | 0 | 92.19% | 0 | 5370.26 | 0 | 0%
25-PC-39554 | Thistle Down Archaeological Testing | Fixed fee | In Progress | Red Rock | Tina Aguirre | 86700 | 63594.45 | 55476.02 | 218.82 | 0.3441% | 0 | 86.89% | 889 | 969.37 | 80.37 | 9.04%
25-PC-39569 | Badger Hollow Park Improvements GIS Mapping | Fixed fee | Completed | Red Rock | Bruce Suarez | 304300 | 191648.14 | 168958.83 | 0 | 0% | 0 | 88.16% | 3054 | 3057.84 | 99.18 | 3.248%
25-PC-39661 | Windmill Flat Cultural Resources Monitoring | Time and material | Completed | Red Rock | Bruce Suarez | 1468900 | 1021032.39 | 915026.27 | 0 | 0% | 0 | 89.62% | 0 | 15175.87 | 0 | 0%
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | Time and material | In Progress | Red Rock | Javier Newman | 51000 | 36551.7 | 75197.04 | 38645.34 | 105.7% | 1 | 100% | 522 | 1061.35 | 539.35 | 103.3%
25-PC-39808 | On-Call: Pine Hollow Rail Siding Architectural History Survey | Fixed fee | In Progress | Red Rock | Marisa Odom | 140600 | 88846.16 | 49031.18 | 1954.3 | 2.2% | 0 | 52.99% | 1463 | 968.63 | 60.28 | 4.12%
25-PC-39873 | On-Call: Eagle Bend Battery Storage Phase II Testing | Fixed fee | In Progress | Red Rock | Marisa Odom | 93300 | 70478.82 | 33515.14 | 1017.05 | 1.443% | 0 | 46.11% | 0 | 474.31 | 15.75 | 0%
25-PC-39885 | Bramble Creek Phase I Survey | Fixed fee | In Progress | Red Rock | Tina Aguirre | 85600 | 54047.84 | 34953 | 238.66 | 0.4416% | 0 | 64.23% | 620 | 425.9 | 8.42 | 1.358%
25-PC-39896 | Task Order 8: Raven Rock Highway Widening Archaeological Testing | Fixed fee | In Progress | Red Rock | Lydia Cisneros | 730900 | 540257.83 | 400441.48 | -2.6 | -0.0004813% | 0 | 74.12% | 6300 | 6706.59 | 507.28 | 8.052%
25-PC-39951 | Falcon Mesa Reservoir - Phase II Testing | Fixed fee | Cost Tracking on Closed Project | Red Rock | Javier Newman | 87200 | 65277.92 | 51921.91 | 0 | 0% | 0 | 79.54% | 1141 | 927.81 | 0 | 0%
25-PC-40020 | Wildrye Curation | Fixed fee | On Hold | Red Rock | Marisa Odom | 186200 | 128340.42 | 38836.44 | 0 | 0% | 0 | 30.26% | 2445 | 592.3 | 0 | 0%
25-PC-40099 | On-Call: Sparrow Hill Pipeline Phase II Testing | Time and material | Completed | Sierra | Benjamin Mathis | 665100 | 460201.14 | 598261.48 | 138060.34 | 30% | 1 | 100% | 7130 | 11047.87 | 3917.87 | 54.95%
25-PC-40170 | Plover Cove Wastewater Plant Cultural Resources Assessment | Time and material | Final Billing/Invoice | Sierra | Angelica Poole | 260400 | 190690.92 | 133483.64 | 0 | 0% | 0 | 70% | 2511 | 2161.11 | 0 | 0%
25-PC-40205 | Eagle Bend Cell Tower Paleontological Monitoring | Fixed fee | Completed | Sierra | Donna Herring | 88100 | 59027 | 55179.61 | 0 | 0% | 0 | 93.48% | 754 | 973.95 | 221.53 | 29.38%
25-PC-40231 | Goldfinch Pipeline - Section 106 Consultation | Time and material | In Progress | Sierra | Donna Herring | 88300 | 59478.88 | 40234.79 | 842.98 | 1.417% | 0 | 66.23% | 1290 | 821.41 | 19.75 | 1.531%
25-PC-40248 | Stone Mill Cultural Resources Monitoring | Time and material | Final Billing/Invoice | Sierra | Louis Huff | 164500 | 111854.21 | 117848.67 | 5994.46 | 5.359% | 1 | 100% | 1505 | 1901.71 | 397.87 | 26.44%
25-PC-40383 | North Fork Archaeological Testing | Fixed fee | In Progress | Sierra | Donna Herring | 193200 | 144185.16 | 120262.6 | 808.96 | 0.5611% | 0 | 82.85% | 1888 | 2170.19 | 282.19 | 14.95%
25-PC-40465 | Task Order 32: Copper Flats Solar Historic Resources Evaluation | Fixed fee | In Progress | Sierra | Benjamin Mathis | 127600 | 94627.43 | 59968.4 | 914.13 | 0.966% | 0 | 62.41% | 2142 | 1182.92 | 20.75 | 0.9687%
25-PC-40482 | Task Order 33: Tamarack Cell Tower Cultural Resources Assessment | Fixed fee | In Progress | Sierra | Louis Huff | 73200 | 60199.68 | 26897 | 1294.31 | 2.15% | 0 | 42.53% | 0 | 407.25 | 7.75 | 0%
25-PC-40501 | Aspen Ridge Archaeological Testing | Fixed fee | Completed | Sierra | Benjamin Mathis | 1246400 | 817638.4 | 784481.65 | 0 | 0% | 0 | 95.94% | 9946 | 14067.8 | 4121.8 | 41.44%
25-PC-40503 | Copper Flats Phase I Survey | Time and material | Lab/Curation | Sierra | Benjamin Mathis | 43400 | 30119.6 | 42364.23 | 12244.63 | 40.65% | 1 | 100% | 0 | 762.42 | 13 | 0%
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | Time and material | In Progress | Sierra | Donna Herring | 71000 | 49579.3 | 76399.6 | 26820.3 | 54.1% | 1 | 100% | 880 | 1244.93 | 364.93 | 41.47%
25-PC-40541 | Eagle Bend Airport Apron - Archaeological Testing | Fixed fee | In Progress | Sierra | Louis Huff | 25000 | 16850 | 11185.54 | 0 | 0% | 0 | 66.38% | 0 | 255.61 | 0 | 0%
25-PC-40572 | Maple Fork Cell Tower Environmental Review Support | Fixed fee | In Progress | Sierra | Benjamin Mathis | 88300 | 67293.43 | 26589.42 | 175.61 | 0.261% | 0 | 39.25% | 1661 | 680.95 | 4.75 | 0.286%
25-PC-40595 | Willow Springs Levee Repair - Built Environment Survey | Fixed fee | Final Reporting/Review | Sierra | Angelica Poole | 1568300 | 1302159.49 | 508068.66 | 1793.94 | 0.1378% | 0 | 38.88% | 11931 | 6809.74 | 30.75 | 0.2577%
25-PC-40677 | Quail Run Paleontological Monitoring | Time and material | Transferred Entity | Sierra | Louis Huff | 225000 | 157612.5 | 153698.05 | 3594.06 | 2.28% | 0 | 95.24% | 1651 | 2285.7 | 634.7 | 38.44%
25-PC-40680 | On-Call: Eagle Bend Battery Storage Cultural Resources Assessment | Time and material | Lab/Curation | Sierra | Donna Herring | 10100 | 6706.4 | 5628.15 | 166.85 | 2.488% | 0 | 81.43% | 102 | 141.17 | 39.67 | 38.89%
25-PC-40708 | Lantern Bay Built Environment Survey | Fixed fee | Final Billing/Invoice | Coastal Bend | Duane Ballard | 50900 | 31379.85 | 25719.64 | 0 | 0% | 0 | 81.96% | 345 | 437.71 | 92.71 | 26.87%
25-PC-40722 | Goldfinch Canal Lining - Archaeological Testing | Time and material | In Progress | Coastal Bend | Duane Ballard | 166600 | 119491.23 | 80423 | 0 | 0% | 0 | 67.3% | 880 | 1121.95 | 241.95 | 27.49%
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Fixed fee | Transferred Entity | Coastal Bend | Duane Ballard | 50100 | 34844.55 | 37556.23 | 4574.86 | 13.13% | 1 | 94.65% | 706 | 787.04 | 104.8 | 14.84%
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Fixed fee | Final Reporting/Review | Coastal Bend | Jared Choi | 46800 | 34243.56 | 37494.89 | 4475.81 | 13.07% | 1 | 96.42% | 340 | 548.62 | 208.62 | 61.36%
25-PC-40880 | Pebble Beach Road Bridge Replacement Cultural Resources Assessment | Time and material | In Progress | Coastal Bend | Diane Daniels | 45800 | 30347.08 | 18281.09 | 282.79 | 0.9319% | 0 | 59.31% | 0 | 370.28 | 6.75 | 0%
25-PC-40925 | Harbor View Airport Apron - Data Recovery | Time and material | Final Reporting/Review | Coastal Bend | Alexis Nixon | 35000 | 23562 | 20240.75 | 0 | 0% | 0 | 85.9% | 376 | 341.2 | 0 | 0%
25-PC-40944 | Maple Fork Archaeological Testing | Fixed fee | Final Billing/Invoice | Coastal Bend | Steve Rubio | 101400 | 73160.1 | 95108.13 | 21948.03 | 30% | 1 | 100% | 0 | 1555.77 | 0 | 0%
25-PC-41075 | Phase I: Cedar Hollow Airport Apron Archaeological Testing | Fixed fee | In Progress | Coastal Bend | Duane Ballard | 82100 | 61304.07 | 34747.46 | 740.58 | 1.208% | 0 | 55.47% | 880 | 714.48 | 18.25 | 2.074%
25-PC-41083 | On-Call: Hackberry Bend Rail Siding Class III Survey | Time and material | On Hold | Coastal Bend | Diane Daniels | 193500 | 140887.35 | 26486.33 | 0 | 0% | 0 | 18.8% | 1762 | 378.82 | 0 | 0%
25-PC-41097 | On-Call: Falcon Mesa Wastewater Plant Phase II Testing | Time and material | Final Reporting/Review | Coastal Bend | Duane Ballard | 197800 | 128154.62 | 105966.34 | 1793.09 | 1.399% | 0 | 81.29% | 1070 | 2098.64 | 1028.64 | 96.13%
25-PC-41187 | Hackberry Bend Trail GIS Mapping | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 98900 | 55621.36 | 42469.62 | 502.25 | 0.903% | 0 | 75.45% | 0 | 883.42 | 10.75 | 0%
25-PC-41252 | Oak Terrace Wastewater Plant Curation | Fixed fee | Final Reporting/Review | Coastal Bend | Steve Rubio | 33000 | 25325 | 23587.71 | 138.12 | 0.5454% | 0 | 92.59% | 349 | 404.64 | 55.64 | 15.94%
25-PC-41265 | Larkspur Class III Survey | Fixed fee | Cost Tracking on Closed Project | Coastal Bend | Diane Daniels | 89800 | 71911.84 | 68323.14 | 0 | 0% | 0 | 95.01% | 1140 | 1306.21 | 177.88 | 15.6%
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 167900 | 131616.81 | 104866.5 | 0 | 0% | 0 | 79.68% | 1459 | 1576.42 | 117.42 | 8.048%
25-PC-41372 | Thistle Down Pipeline Curation | Fixed fee | Final Billing/Invoice | Coastal Bend | Duane Ballard | 86100 | 63016.59 | 53963.72 | 0 | 0% | 0 | 85.63% | 0 | 805.37 | 0 | 0%
25-PC-41383 | Harbor View Reservoir - Cultural Resources Assessment | Fixed fee | In Progress | Coastal Bend | Steve Rubio | 342200 | 223902.7 | 172645.04 | 63.75 | 0.02847% | 0 | 77.08% | 0 | 2905.73 | 1.5 | 0%
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 179800 | 119171.44 | 171055.96 | 56855.81 | 47.71% | 1 | 95.83% | 819 | 1700.79 | 881.79 | 107.7%
25-PC-41476 | North Fork Mixed-Use Development Archaeological Testing | Time and material | Completed | Coastal Bend | Alexis Nixon | 211900 | 146804.32 | 190845.62 | 44041.3 | 30% | 1 | 100% | 1967 | 2768.71 | 801.71 | 40.76%
25-PC-41479 | Hawk Point Trail Maritime Remote Sensing Survey | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 633600 | 405123.84 | 130355.73 | 652.02 | 0.1609% | 0 | 32.02% | 8732 | 2390.82 | 13.75 | 0.1575%
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | Time and material | In Progress | Coastal Bend | Jared Choi | 130200 | 94156.73 | 105548.12 | 11391.39 | 12.1% | 1 | 100% | 2339 | 1755.56 | 33.25 | 1.422%
25-PC-41514 | Lantern Bay Levee Repair Historic Resources Evaluation | Fixed fee | Final Reporting/Review | Coastal Bend | Duane Ballard | 48700 | 31123.36 | 24653.59 | 798.01 | 2.564% | 0 | 76.65% | 556 | 497.47 | 33.36 | 6%
25-PC-41600 | Twin Buttes Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | Coastal Bend | Diane Daniels | 647300 | 488406.31 | 486062.64 | 0 | 0% | 0 | 99.52% | 8132 | 8472.13 | 340.13 | 4.183%
25-PC-41603 | Task Order 22: Wren Hollow Cell Tower Paleontological Monitoring | Time and material | Final Billing/Invoice | Coastal Bend | Alexis Nixon | 73800 | 50808.19 | 66050.65 | 15242.46 | 30% | 1 | 100% | 819 | 1099.04 | 280.04 | 34.19%
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | Time and material | In Progress | Coastal Bend | Jared Choi | 412300 | 281889.51 | 224531.71 | 11857.88 | 4.207% | 0 | 75.45% | 3365 | 4203.88 | 838.88 | 24.93%
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | Time and material | In Progress | Built Environment | Jenny Wilkinson | 152100 | 108599.4 | 90984.66 | 1015.62 | 0.9352% | 0 | 82.84% | 2573 | 1995.86 | 22.5 | 0.8745%
25-PC-41764 | Stone Mill Environmental Review Support | Time and material | In Progress | Built Environment | Jenny Wilkinson | 20700 | 15642.78 | 14549.83 | 0 | 0% | 0 | 93.01% | 286 | 347.8 | 61.8 | 21.61%
25-PC-41834 | Pebble Beach Road Data Recovery | Fixed fee | In Progress | Built Environment | Rickey Salas | 170100 | 145401.48 | 54475.62 | 306.45 | 0.2108% | 0 | 37.25% | 2069 | 1179.07 | 6.75 | 0.3262%
25-PC-41843 | Wren Hollow Rail Siding - Section 106 Consultation | Time and material | Final Reporting/Review | Built Environment | Jesse Maynard | 54000 | 35988.02 | 23655.15 | 0 | 0% | 0 | 65.73% | 0 | 398.96 | 0 | 0%
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | Time and material | In Progress | Built Environment | Rickey Salas | 39700 | 25920.13 | 29882.88 | 6662.71 | 25.7% | 1 | 89.58% | 577 | 531.03 | 77.36 | 13.41%
25-PC-41931 | Sandpiper Pipeline Curation | Fixed fee | Final Billing/Invoice | Built Environment | Jesse Maynard | 56200 | 36698.6 | 36424.62 | 0 | 0% | 0 | 99.25% | 466 | 658.5 | 192.5 | 41.31%
25-PC-41967 | On-Call: Redbud Pipeline Section 106 Consultation | Fixed fee | On Hold | Built Environment | Rickey Salas | 37300 | 28348 | 7978.96 | 0 | 0% | 0 | 28.15% | 470 | 154.67 | 0 | 0%
25-PC-42076 | Bramble Creek Highway Widening Curation | Time and material | In Progress | Built Environment | Jesse Maynard | 319600 | 227746.96 | 98992.03 | 1734.87 | 0.7618% | 0 | 42.7% | 4605 | 1536.49 | 26.5 | 0.5755%
25-PC-42078 | Sea Oat Paleontological Monitoring | Fixed fee | Completed | Built Environment | Jenny Wilkinson | 433900 | 316573.44 | 263762.67 | 0 | 0% | 0 | 83.32% | 0 | 4462.25 | 0 | 0%
25-PC-42084 | Foxglove Built Environment Survey | Time and material | In Progress | Built Environment | Kathleen Cabrera | 1294200 | 847312.74 | 296024.06 | 0 | 0% | 0 | 34.94% | 10280 | 4546.08 | 0 | 0%
25-PC-42097 | Tansy Flat Solar Data Recovery | Fixed fee | In Progress | Built Environment | Jenny Wilkinson | 179700 | 138548.7 | 65000.81 | 764.26 | 0.5516% | 0 | 46.36% | 1033 | 772.23 | 11.5 | 1.113%
25-PC-42115 | Hawk Point Reservoir Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | Built Environment | Jesse Maynard | 110400 | 90660.48 | 57919.12 | 1755.29 | 1.936% | 0 | 61.95% | 1078 | 1136.54 | 58.54 | 5.43%
25-PC-42136 | Phase III: Granite Pass Mixed-Use Development Maritime Remote Sensing Survey | Fixed fee | In Progress | Built Environment | Jesse Maynard | 31700 | 23936.32 | 17873.56 | 0 | 0% | 0 | 74.67% | 224 | 202.87 | 0 | 0%
25-PC-42163 | Foxglove Historic Resources Evaluation | Time and material | Final Reporting/Review | Built Environment | Rickey Salas | 50700 | 34430.37 | 27262.05 | 34.77 | 0.101% | 0 | 79.08% | 507 | 483.28 | 37.92 | 7.479%
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Time and material | Cost Tracking on Closed Project | Built Environment | Kathleen Cabrera | 17900 | 12066.39 | 14332.43 | 2266.04 | 18.78% | 1 | 100% | 0 | 216.11 | 0 | 0%
25-PC-42253 | On-Call: Plover Cove Substation Phase I Survey | Time and material | In Progress | Paleontology | Charlene Sparks | 67000 | 45781.1 | 27198.17 | 0 | 0% | 0 | 59.41% | 826 | 527.41 | 0 | 0%
25-PC-42282 | Dove Canyon Levee Repair - Phase I Survey | Fixed fee | In Progress | Paleontology | Charlene Sparks | 33000 | 19255.5 | 11737.57 | 127.64 | 0.6629% | 0 | 60.29% | 417 | 222.01 | 3 | 0.7194%
25-PC-42303 | Copper Flats Cell Tower Environmental Review Support | Time and material | Completed | Paleontology | Travis Delgado | 147500 | 99769 | 129699.7 | 29930.7 | 30% | 1 | 100% | 916 | 2149.7 | 1233.7 | 134.7%
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | Fixed fee | In Progress | Paleontology | Charlene Sparks | 41200 | 29239.64 | 22925.41 | 826.73 | 2.827% | 0 | 75.58% | 290 | 229.08 | 7.5 | 2.586%
25-PC-42323 | Millbrook Cultural Resources Monitoring | Fixed fee | In Progress | Paleontology | Travis Delgado | 79800 | 58357.74 | 33900.56 | 317.16 | 0.5435% | 0 | 57.55% | 0 | 392.03 | 4 | 0%
25-PC-42343 | Phase III: Coyote Springs Pipeline Phase II Testing | Fixed fee | In Progress | Paleontology | Travis Delgado | 6100 | 4038.38 | 2731.5 | 0 | 0% | 0 | 67.64% | 77 | 43.33 | 0 | 0%
25-PC-42364 | Sparrow Hill Fiber Route - Phase I Survey | Fixed fee | In Progress | Paleontology | Travis Delgado | 594900 | 426353.2 | 269416.68 | 9.4 | 0.002205% | 0 | 63.19% | 7627 | 5519.01 | 0.25 | 0.003278%
25-PC-42399 | Task Order 7: Aspen Ridge Housing Development Class III Survey | Fixed fee | In Progress | Paleontology | Charlene Sparks | 683800 | 509225.86 | 287162.01 | 2743.58 | 0.5388% | 0 | 55.85% | 10389 | 4545.39 | 55.25 | 0.5318%
25-PC-42528 | Slate Ridge Park Improvements - Phase I Survey | Fixed fee | In Progress | Paleontology | Charlene Sparks | 132000 | 93601.2 | 26336.23 | -145.47 | -0.1554% | 0 | 28.29% | 1161 | 484.97 | -3.5 | -0.3015%
25-PC-42569 | Larkspur Phase I Survey | Fixed fee | Final Billing/Invoice | Paleontology | Charlene Sparks | 105700 | 81219.88 | 68472.33 | 0 | 0% | 0 | 84.3% | 1085 | 1096.04 | 55.19 | 5.087%
25-PC-42601 | Lantern Bay Park Improvements - Cultural Resources Monitoring | Time and material | Transferred Entity | Paleontology | Charlene Sparks | 302100 | 213521.46 | 62873.17 | 661.38 | 0.3097% | 0 | 29.14% | 1670 | 609.13 | 6 | 0.3593%
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | Time and material | In Progress | Maritime | Kyle Maynard | 130300 | 95796.56 | 79985.69 | 1322.06 | 1.38% | 0 | 82.12% | 913 | 1284.02 | 371.02 | 40.64%
25-PC-42747 | Yarrow Point Transmission Line - Historic Resources Evaluation | Fixed fee | On Hold | Maritime | Rita Ayala | 128900 | 87896.91 | 47757.12 | 0 | 0% | 0 | 54.33% | 1803 | 656.03 | 0 | 0%
25-PC-43037 | Cedar Hollow Section 106 Consultation | Fixed fee | Completed | Maritime | Rita Ayala | 250200 | 196231.86 | 238460.35 | 42228.49 | 21.52% | 1 | 100% | 1676 | 3400.85 | 1724.85 | 102.9%
25-PC-43061 | Plover Cove Built Environment Survey | Fixed fee | Final Billing/Invoice | Geospatial | Priscilla Pennington | 106500 | 81184.95 | 77334.09 | 0 | 0% | 0 | 95.26% | 1332 | 1231.28 | 0 | 0%
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Time and material | Transferred Entity | Geospatial | Sylvia Callahan | 62000 | 44404.4 | 44584.79 | 3399.63 | 7.656% | 1 | 92.75% | 549 | 591.52 | 50.38 | 9.177%
25-PC-43075 | Coyote Springs Reservoir Cultural Resources Assessment | Time and material | On Hold | Geospatial | Sylvia Callahan | 381100 | 238416.16 | 83479.16 | 0 | 0% | 0 | 35.01% | 2548 | 1217.29 | 0 | 0%
25-PC-43106 | Kestrel Butte Wastewater Plant - Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | Geospatial | Priscilla Pennington | 63000 | 41082.3 | 36605.84 | 0 | 0% | 0 | 89.1% | 677 | 701.86 | 24.86 | 3.672%
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | Fixed fee | In Progress | Meridian Central | Seth Zavala | 128400 | 106315.2 | 195734.3 | 89419.1 | 84.11% | 1 | 100% | 1431 | 2677.08 | 1246.08 | 87.08%
25-PC-43244 | Windmill Flat Environmental Review Support | Fixed fee | Final Billing/Invoice | Meridian Central | Clinton Solis | 794900 | 585516.71 | 519424.85 | 0 | 0% | 0 | 88.71% | 0 | 8594.92 | 0 | 0%
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | Time and material | In Progress | Meridian Central | Seth Zavala | 15700 | 10903.65 | 71168.36 | 60264.71 | 552.7% | 1 | 100% | 146 | 876.39 | 730.39 | 500.3%
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Fixed fee | Cost Tracking on Closed Project | Meridian Central | Clinton Solis | 715500 | 625275.45 | 568777.84 | 0 | 0% | 0 | 90.96% | 7995 | 9051.77 | 1056.77 | 13.22%
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Fixed fee | Cost Tracking on Closed Project | Meridian Central | Seth Zavala | 551800 | 378424.44 | 405626.36 | 27201.92 | 7.188% | 1 | 100% | 4019 | 6540.98 | 2521.98 | 62.75%
25-PC-43455 | Kestrel Butte Maritime Remote Sensing Survey | Fixed fee | On Hold | Meridian Central | Seth Zavala | 116100 | 84903.93 | 8459.31 | 0 | 0% | 0 | 9.963% | 1658 | 129.43 | 0 | 0%
25-PC-43511 | Wildrye Solar Phase II Testing | Time and material | Completed | Meridian Central | Mathew Shea | 1026200 | 701711.56 | 912225.03 | 210513.47 | 30% | 1 | 100% | 8612 | 13057.47 | 4445.47 | 51.62%
25-PC-43566 | Copper Flats Solar - Phase II Testing | Fixed fee | In Progress | Meridian Central | Mathew Shea | 114200 | 73887.4 | 131458.03 | 57570.63 | 77.92% | 1 | 100% | 0 | 1815.96 | 7.5 | 0%
25-PC-43590 | Task Order 37: Elk Meadow Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | Meridian Central | Mathew Shea | 24800 | 16619.52 | 11377.59 | 0 | 0% | 0 | 68.46% | 218 | 171.8 | 0 | 0%
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | Fixed fee | In Progress | Meridian Southwest | Alan Gay | 52800 | 37979.04 | 37986.89 | 1434.44 | 3.777% | 0 | 96.24% | 0 | 655.33 | 1 | 0%
25-PC-43639 | Windmill Flat Battery Storage Curation | Fixed fee | Final Reporting/Review | Meridian Southwest | Harold Chaney | 137000 | 91502.3 | 100918.91 | 19868.87 | 21.71% | 1 | 88.58% | 1167 | 1365.96 | 298.74 | 25.6%
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Fixed fee | Lab/Curation | Meridian Southwest | Reginald Kerr | 92800 | 78211.84 | 103245.03 | 25033.19 | 32.01% | 1 | 100% | 0 | 1415.49 | 31.5 | 0%
25-PC-43752 | Bramble Creek Rail Siding - Environmental Review Support | Time and material | Final Billing/Invoice | Meridian Southwest | Reginald Kerr | 49900 | 36001.87 | 46802.43 | 10800.56 | 30% | 1 | 100% | 0 | 650.91 | 0 | 0%
25-PC-43771 | Granite Pass Reservoir - Built Environment Survey | Time and material | Lab/Curation | Meridian Southwest | Lynn Tran | 31500 | 20147.4 | 11344.38 | 561.48 | 2.787% | 0 | 53.52% | 366 | 254.16 | 12 | 3.279%
25-PC-43844 | Slate Ridge Battery Storage Class III Survey | Fixed fee | In Progress | Meridian Southwest | Alan Gay | 50700 | 33907.9 | 32031.03 | 8688.95 | 25.63% | 1 | 68.84% | 290 | 384.75 | 122.67 | 42.3%
25-PC-43853 | Heron Marsh Battery Storage - Phase II Testing | Time and material | Final Reporting/Review | Meridian Southwest | Alan Gay | 162800 | 115799.64 | 99239.21 | 2960.72 | 2.557% | 0 | 83.14% | 1431 | 1488.31 | 82.03 | 5.732%
25-PC-43859 | On-Call: Juniper Wash Solar Architectural History Survey | Fixed fee | Completed | Meridian Southwest | Alan Gay | 1802800 | 1378420.88 | 1051248.86 | 0 | 0% | 0 | 76.26% | 21344 | 15991.46 | 0 | 0%
25-PC-43863 | Yarrow Point Cultural Resources Assessment | Fixed fee | In Progress | Meridian Southwest | Reginald Kerr | 545200 | 450335.2 | 83664.45 | 447.95 | 0.09947% | 0 | 18.48% | 0 | 954.77 | 8.25 | 0%
25-PC-43932 | Blue Heron Built Environment Survey | Time and material | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 35900 | 24656.25 | 14873.81 | 479.35 | 1.944% | 0 | 58.38% | 374 | 267.11 | 20.6 | 5.508%
25-PC-43944 | Elk Meadow Data Recovery | Fixed fee | In Progress | NH Gulf (USD) | Vanessa Duarte | 74800 | 60460.84 | 21611.75 | 693.95 | 1.148% | 0 | 34.6% | 1142 | 385.14 | 15.75 | 1.379%
25-PC-43966 | Silver Lake Rail Siding - Cultural Resources Monitoring | Fixed fee | Transferred Entity | NH Gulf (USD) | Tonya Spence | 47800 | 34547.14 | 27353.21 | 0 | 0% | 0 | 79.18% | 217 | 251.05 | 34.05 | 15.69%
25-PC-43993 | Timber Gap GIS Mapping | Fixed fee | Transferred Entity | NH Gulf (USD) | Javier Rangel | 27900 | 19669.5 | 14401.75 | 4496.98 | 22.86% | 1 | 50.36% | 136 | 147.9 | 60.36 | 44.38%
25-PC-44046 | Kestrel Butte Section 106 Consultation | Fixed fee | Transferred Entity | NH Gulf (USD) | Randy Cantu | 320300 | 220526.55 | 276639.91 | 56113.36 | 25.45% | 1 | 100% | 0 | 3042.45 | 16.5 | 0%
25-PC-44140 | Stone Mill Archaeological Testing | Fixed fee | In Progress | NH Gulf (USD) | Tonya Spence | 149900 | 100298.09 | 100035.45 | 20679.25 | 20.62% | 1 | 79.12% | 1193 | 1386.25 | 332.25 | 27.85%
25-PC-44186 | Falcon Mesa Section 106 Consultation | Fixed fee | Transferred Entity | NH Gulf (USD) | Randy Cantu | 537000 | 338148.9 | 215370.94 | 693.06 | 0.205% | 0 | 63.49% | 9096 | 4321.48 | 16.25 | 0.1786%
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | Time and material | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 31100 | 17934.14 | 31276.12 | 13601.15 | 75.84% | 1 | 98.55% | 0 | 292.39 | 10.5 | 0%
25-PC-44241 | On-Call: Timber Gap Reservoir Paleontological Monitoring | Time and material | Final Billing/Invoice | NH Gulf (USD) | Justin Mejia | 348700 | 228712.33 | 297326.03 | 68613.7 | 30% | 1 | 100% | 0 | 3551.32 | 0 | 0%
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | Fixed fee | In Progress | NH Gulf (USD) | Randy Cantu | 97000 | 71004 | 79042.17 | 8038.17 | 11.32% | 1 | 100% | 322 | 803.19 | 481.19 | 149.4%
26-PC-30013 | Windmill Flat Mine Expansion - Architectural History Survey | Time and material | Final Reporting/Review | Big Sky | Bob Frye | 62300 | 43902.81 | 9546.49 | 410.1 | 0.9341% | 0 | 20.81% | 685 | 129.75 | 6 | 0.8759%
26-PC-30057 | Sparrow Hill Environmental Review Support | Time and material | In Progress | Big Sky | Brendan Melton | 197500 | 144017 | 68917.84 | 665.35 | 0.462% | 0 | 47.39% | 1736 | 932.25 | 9.25 | 0.5328%
26-PC-30065 | Granite Pass Water Main - Cultural Resources Assessment | Fixed fee | In Progress | Big Sky | Javier Estrada | 132100 | 104411.84 | 20838.3 | 723.1 | 0.6925% | 0 | 19.27% | 879 | 233.75 | 8.75 | 0.9954%
26-PC-30094 | Sumac Ridge Wastewater Plant Paleontological Monitoring | Fixed fee | In Progress | Big Sky | Carl Barajas | 98400 | 82193.52 | 3266.46 | 0 | 0% | 0 | 3.974% | 1481 | 72.25 | 0 | 0%
26-PC-30115 | Quail Run Housing Development - Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Big Sky | Bob Frye | 18600 | 16368 | 16558.04 | 190.04 | 1.161% | 0 | 100% | 256 | 302.12 | 56.79 | 22.18%
26-PC-30123 | Eagle Bend Park Improvements - Class III Survey | Fixed fee | In Progress | Big Sky | Bob Frye | 277200 | 210477.96 | 44970.8 | 1725.33 | 0.8197% | 0 | 20.55% | 2614 | 631.5 | 25.25 | 0.966%
26-PC-30139 | Quail Run Canal Lining Phase I Survey | Fixed fee | In Progress | Big Sky | Javier Estrada | 239600 | 198628.4 | 15884.69 | 537.16 | 0.2704% | 0 | 7.727% | 2195 | 160.5 | 6.5 | 0.2961%
26-PC-30180 | Willow Springs Architectural History Survey | Fixed fee | Lab/Curation | Big Sky | Carl Barajas | 115700 | 79798.29 | 20705.53 | 159.59 | 0.2% | 0 | 25.75% | 1880 | 467.5 | 4.25 | 0.2261%
26-PC-30185 | Task Order 40: Cedar Hollow Cell Tower Curation | Fixed fee | Final Reporting/Review | Big Sky | Javier Estrada | 53400 | 42447.66 | 2466.42 | 0 | 0% | 0 | 5.81% | 711 | 41.25 | 0 | 0%
26-PC-30203 | Millbrook Pipeline Data Recovery | Fixed fee | In Progress | Big Sky | Carl Barajas | 134800 | 102421.04 | 6626.59 | 0 | 0% | 0 | 6.47% | 2925 | 148.75 | 0 | 0%
26-PC-30211 | Copper Flats Paleontological Monitoring | Fixed fee | Lab/Curation | Big Sky | Javier Estrada | 736100 | 498404.34 | 0 | 0 | 0% | 0 | 0% | 10505 | 0 | 0 | 0%
26-PC-30273 | Task Order 40: Copper Flats Trail Class III Survey | Fixed fee | Lab/Curation | Big Sky | Bob Frye | 77200 | 53522.76 | 4782.94 | 309.76 | 0.5787% | 0 | 8.358% | 0 | 115.25 | 8 | 0%
26-PC-30287 | Task Order 40: Maple Fork Solar Historic Resources Evaluation | Fixed fee | In Progress | Big Sky | Javier Estrada | 10100 | 6193.32 | 3115.9 | 59.97 | 0.9683% | 0 | 49.34% | 0 | 71 | 1.5 | 0%
26-PC-30329 | Hackberry Bend Rail Siding Built Environment Survey | Fixed fee | In Progress | Big Sky | Javier Estrada | 483600 | 313904.76 | 79237.07 | 1101.92 | 0.351% | 0 | 24.89% | 5312 | 1562.25 | 25.5 | 0.48%
26-PC-30338 | On-Call: Saltgrass Mixed-Use Development Phase II Testing | Fixed fee | Lab/Curation | Big Sky | Brendan Melton | 268300 | 189811.91 | 1089.39 | 0 | 0% | 0 | 0.5739% | 3414 | 24 | 0 | 0%
26-PC-30349 | Phase I: Copper Flats Rail Siding Cultural Resources Monitoring | Fixed fee | In Progress | Big Sky | Brendan Melton | 184200 | 105343.98 | 17644.68 | -32.21 | -0.03058% | 0 | 16.78% | 2437 | 315 | 1.5 | 0.06155%
26-PC-30351 | Wildrye Architectural History Survey | Fixed fee | In Progress | Big Sky | Bob Frye | 393800 | 262900.88 | 88597.24 | 425.94 | 0.162% | 0 | 33.54% | 4223 | 1332.75 | 6.5 | 0.1539%
26-PC-30396 | Tamarack Historic Resources Evaluation | Fixed fee | In Progress | Big Sky | Brendan Melton | 31300 | 23853.73 | 0 | 0 | 0% | 0 | 0% | 310 | 0 | 0 | 0%
26-PC-30402 | On-Call: Cedar Hollow Highway Widening Paleontological Monitoring | Time and material | Transferred Entity | Big Sky | Carl Barajas | 151000 | 118603.52 | 0 | 0 | 0% | 0 | 0% | 1142 | 0 | 0 | 0%
26-PC-30425 | Tamarack Water Main - Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Big Sky | Bob Frye | 58100 | 42076.02 | 39854.91 | 0 | 0% | 0 | 94.72% | 829 | 681.15 | 1.82 | 0.2195%
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | Big Sky | Javier Estrada | 93100 | 63801.43 | 65021.47 | 1220.04 | 1.912% | 0 | 100% | 659 | 1137.4 | 478.4 | 72.59%
26-PC-30457 | Wren Hollow Transmission Line - Data Recovery | Fixed fee | Final Reporting/Review | Big Sky | Bob Frye | 719800 | 547191.96 | 91469.21 | 1103.34 | 0.2016% | 0 | 16.51% | 6208 | 1138 | 12.75 | 0.2054%
26-PC-30480 | Tansy Flat Canal Lining Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | Big Sky | Javier Estrada | 194300 | 143375.92 | 181546.67 | 38170.75 | 26.62% | 1 | 100% | 1567 | 2831.06 | 1264.06 | 80.67%
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | Fixed fee | In Progress | Big Sky | Brendan Melton | 19900 | 14258.19 | 18074.32 | 4366.82 | 30.63% | 1 | 96.14% | 199 | 339.75 | 143 | 71.86%
26-PC-30528 | Plover Cove School Campus Architectural History Survey | Fixed fee | In Progress | Big Sky | Javier Estrada | 112900 | 74017.24 | 50490.81 | 576.57 | 0.779% | 0 | 67.44% | 0 | 1041.25 | 13.5 | 0%
26-PC-30554 | Thistle Down Airport Apron Curation | Fixed fee | In Progress | Big Sky | Bob Frye | 139800 | 79741.92 | 9511.95 | 0 | 0% | 0 | 11.93% | 0 | 197.75 | 0 | 0%
26-PC-30577 | Task Order 15: Wildrye Bridge Replacement Phase I Survey | Fixed fee | On Hold | Big Sky | Javier Estrada | 46800 | 36479.31 | 0 | 0 | 0% | 0 | 0% | 420 | 0 | 0 | 0%
26-PC-30588 | Bramble Creek Fiber Route - Historic Resources Evaluation | Fixed fee | In Progress | Bluegrass | Alice Galloway | 97000 | 75388.4 | 9168.72 | 0 | 0% | 0 | 12.16% | 1668 | 174.25 | 0 | 0%
26-PC-30589 | Aspen Ridge Trail Cultural Resources Assessment | Fixed fee | Completed | Bluegrass | Kiara Gillespie | 143200 | 108502.64 | 141053.43 | 32550.79 | 30% | 1 | 100% | 0 | 2161.7 | 0 | 0%
26-PC-30602 | On-Call: Hawk Point Solar Cultural Resources Assessment | Time and material | In Progress | Bluegrass | Kiara Gillespie | 211900 | 152752.98 | 35317.52 | 1501.21 | 0.9828% | 0 | 22.14% | 1755 | 515.25 | 21.25 | 1.211%
26-PC-30634 | Task Order 7: Blue Heron Canal Lining Historic Resources Evaluation | Time and material | Completed | Bluegrass | Kiara Gillespie | 21200 | 13865.34 | 18024.94 | 4159.6 | 30% | 1 | 100% | 159 | 294.02 | 135.02 | 84.92%
26-PC-30754 | On-Call: Kestrel Butte Highway Widening Archaeological Testing | Fixed fee | Final Reporting/Review | Bluegrass | Alice Galloway | 153300 | 106834.77 | 8772.63 | 0 | 0% | 0 | 8.211% | 2318 | 174.5 | 0 | 0%
26-PC-30781 | Cedar Hollow Trail - Architectural History Survey | Fixed fee | Final Billing/Invoice | Bluegrass | Kiara Gillespie | 113700 | 71210.31 | 82296.91 | 11086.6 | 15.57% | 1 | 100% | 933 | 1480.33 | 547.33 | 58.66%
26-PC-30815 | Juniper Wash Water Main Archaeological Testing | Fixed fee | In Progress | Bluegrass | Kiara Gillespie | 236000 | 177731.6 | 30899.89 | 0 | 0% | 0 | 17.39% | 1914 | 478 | 0 | 0%
26-PC-30871 | Sea Oat Substation - Section 106 Consultation | Time and material | Final Billing/Invoice | Bluegrass | Alice Galloway | 205700 | 139834.86 | 129872.01 | 0 | 0% | 0 | 92.88% | 2082 | 2104.58 | 115.53 | 5.549%
26-PC-30896 | Phase III: Timber Gap Pipeline Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Bluegrass | Kiara Gillespie | 158100 | 109547.49 | 104692.72 | 0 | 0% | 0 | 95.57% | 0 | 1422.76 | 0 | 0%
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Time and material | Cost Tracking on Closed Project | Bluegrass | Alice Galloway | 209800 | 135467.86 | 134699.95 | 0 | 0% | 0 | 99.43% | 1355 | 2054.23 | 699.23 | 51.6%
26-PC-30945 | Wildrye Reservoir Architectural History Survey | Fixed fee | In Progress | Bluegrass | Kiara Gillespie | 179500 | 120265 | 56121.76 | 4237.18 | 3.523% | 0 | 43.14% | 0 | 1005 | 23.25 | 0%
26-PC-30967 | Timber Gap Pipeline - Built Environment Survey | Time and material | Final Reporting/Review | Bluegrass | Alice Galloway | 173400 | 108877.86 | 91606.15 | 11289.41 | 10.37% | 1 | 73.77% | 1432 | 1654 | 352.5 | 24.62%
26-PC-30985 | On-Call: Maple Fork Wastewater Plant Built Environment Survey | Fixed fee | Final Billing/Invoice | Bluegrass | Kiara Gillespie | 46500 | 30100.87 | 38312.83 | 8211.96 | 27.28% | 1 | 100% | 376 | 643.26 | 267.26 | 71.08%
26-PC-31002 | North Fork Harbor Dredging Data Recovery | Fixed fee | In Progress | Bluegrass | Alice Galloway | 211500 | 164758.5 | 22695.69 | 189.82 | 0.1152% | 0 | 13.66% | 1533 | 288.75 | 1.5 | 0.09785%
26-PC-31037 | Cedar Hollow Cultural Resources Assessment | Fixed fee | In Progress | Bluegrass | Alice Galloway | 168500 | 131345.75 | 49181.51 | 657.66 | 0.5007% | 0 | 36.94% | 1730 | 716.5 | 13.75 | 0.7948%
26-PC-31064 | Quail Run Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | Cascade | Gene Nixon | 74500 | 60394.3 | 76340.83 | 15946.53 | 26.4% | 1 | 100% | 948 | 895.92 | 0 | 0%
26-PC-31084 | Bramble Creek Park Improvements Section 106 Consultation | Fixed fee | Final Billing/Invoice | Cascade | Gene Nixon | 28300 | 14716 | 12592.07 | 0 | 0% | 0 | 85.57% | 144 | 227.73 | 83.73 | 58.15%
26-PC-31098 | Millbrook School Campus - Environmental Review Support | Time and material | On Hold | Cascade | Cassidy Gay | 414100 | 297365.21 | 0 | 0 | 0% | 0 | 0% | 2837 | 0 | 0 | 0%
26-PC-31155 | Slate Ridge Cell Tower - Phase II Testing | Fixed fee | Final Billing/Invoice | Cascade | Jean Cooke | 56600 | 35980.62 | 40333.19 | 4352.57 | 12.1% | 1 | 100% | 449 | 738.4 | 289.4 | 64.45%
26-PC-31174 | Task Order 33: Tamarack Housing Development Data Recovery | Time and material | Cost Tracking on Closed Project | Cascade | Donald Lutz | 4400 | 2984.25 | 2714.71 | 0 | 0% | 0 | 90.97% | 40 | 49.01 | 10.42 | 26.05%
26-PC-31182 | Elk Meadow School Campus Curation | Fixed fee | In Progress | Cascade | Jeff Spence | 73400 | 57596.98 | 7004.68 | 408.02 | 0.7084% | 0 | 11.45% | 1211 | 141.75 | 9.25 | 0.7638%
26-PC-31186 | Task Order 14: Meadowlark Cell Tower Archaeological Testing | Time and material | Completed | Cascade | Cassidy Gay | 43100 | 31458.69 | 26223.26 | 0 | 0% | 0 | 83.36% | 573 | 475.37 | 0 | 0%
26-PC-31209 | Redbud Canal Lining - Built Environment Survey | Fixed fee | Final Billing/Invoice | Cascade | Donald Lutz | 960700 | 765293.62 | 893005.2 | 127711.58 | 16.69% | 1 | 100% | 14279 | 15104.41 | 1916.04 | 13.42%
26-PC-31216 | On-Call: Saltgrass Fiber Route Environmental Review Support | Time and material | In Progress | Cascade | Preston Duarte | 172400 | 111025.6 | 16381.12 | 1439.96 | 1.297% | 0 | 13.46% | 1218 | 235.5 | 23 | 1.888%
26-PC-31238 | Task Order 27: Wren Hollow Bridge Replacement Built Environment Survey | Time and material | In Progress | Cascade | Preston Duarte | 832700 | 533060.12 | 91086.68 | 1027.92 | 0.1928% | 0 | 16.89% | 11177 | 2077.25 | 25.75 | 0.2304%
26-PC-31276 | Phase II: Sea Oat Solar Phase I Survey | Time and material | Final Billing/Invoice | Cascade | Jean Cooke | 132400 | 98558.56 | 102977.3 | 4418.74 | 4.483% | 0 | 100% | 1157 | 1833.36 | 676.36 | 58.46%
26-PC-31316 | Sparrow Hill Trail Architectural History Survey | Fixed fee | Final Reporting/Review | Cascade | Cassidy Gay | 148200 | 109860.66 | 28261.6 | 581.01 | 0.5289% | 0 | 25.2% | 912 | 293 | 5.25 | 0.5757%
26-PC-31421 | Task Order 30: Sage Flat Levee Repair Environmental Review Support | Fixed fee | Completed | Cascade | Cassidy Gay | 740400 | 532717.8 | 692533.14 | 159815.34 | 30% | 1 | 100% | 8491 | 11771.27 | 3280.27 | 38.63%
26-PC-31448 | Foxglove Class III Survey | Fixed fee | In Progress | Cascade | Gene Nixon | 25800 | 20065.31 | 5612.5 | 0 | 0% | 0 | 27.97% | 439 | 77.75 | 0 | 0%
26-PC-31473 | Plover Cove Mixed-Use Development - Curation | Fixed fee | In Progress | Cascade | Cassidy Gay | 180800 | 112403.36 | 6908.42 | 0 | 0% | 0 | 6.146% | 0 | 97.5 | 0 | 0%
26-PC-31484 | Maple Fork Wastewater Plant Data Recovery | Fixed fee | In Progress | Cascade | Jean Cooke | 31800 | 23427.06 | 6057.36 | 55.14 | 0.2354% | 0 | 25.62% | 483 | 107.25 | 1.25 | 0.2588%
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | Fixed fee | In Progress | Cascade | Donald Lutz | 44400 | 34032.6 | 23861.11 | 417.62 | 1.227% | 0 | 68.89% | 394 | 432.5 | 38.5 | 9.772%
26-PC-31537 | Raven Rock Park Improvements - Maritime Remote Sensing Survey | Fixed fee | In Progress | Cascade | Preston Duarte | 87300 | 54449.01 | 2823.14 | 0 | 0% | 0 | 5.185% | 309 | 18.75 | 0 | 0%
26-PC-31568 | Sea Oat Housing Development - Section 106 Consultation | Fixed fee | In Progress | Cascade | Donald Lutz | 229100 | 148678.02 | 24897.45 | 649.28 | 0.4367% | 0 | 16.31% | 3286 | 541.25 | 16.5 | 0.5021%
26-PC-31638 | Kestrel Butte Highway Widening - Cultural Resources Assessment | Fixed fee | In Progress | Cascade | Gene Nixon | 170300 | 108060.44 | 13711.23 | 167.32 | 0.1548% | 0 | 12.53% | 1587 | 273.25 | 3.75 | 0.2363%
26-PC-31648 | Rushgrass Draw Solar Data Recovery | Fixed fee | In Progress | Cascade | Jeff Spence | 388400 | 288425.84 | 124527.73 | 1341.46 | 0.4651% | 0 | 42.71% | 0 | 1891 | 21 | 0%
26-PC-31678 | Heron Marsh Wind Farm Phase I Survey | Fixed fee | In Progress | Cascade | Preston Duarte | 892800 | 641923.2 | 213779.38 | 2665.75 | 0.4153% | 0 | 32.89% | 0 | 3229.5 | 45 | 0%
26-PC-31692 | Phase III: Meadowlark Reservoir Paleontological Monitoring | Fixed fee | In Progress | Cascade | Preston Duarte | 615300 | 423803.64 | 25309.14 | 615.44 | 0.1452% | 0 | 5.827% | 0 | 475.75 | 14 | 0%
26-PC-31700 | On-Call: Granite Pass Bridge Replacement Environmental Review Support | Time and material | Completed | Cascade | Gene Nixon | 49200 | 33923.4 | 33810.01 | 0 | 0% | 0 | 99.67% | 338 | 652.61 | 314.61 | 93.08%
26-PC-31716 | Saltgrass Wind Farm Data Recovery | Fixed fee | In Progress | Cascade | Donald Lutz | 13300 | 9413.74 | 2489.99 | 51.51 | 0.5472% | 0 | 25.9% | 0 | 47.25 | 1.25 | 0%
26-PC-31728 | On-Call: Slate Ridge Housing Development Data Recovery | Fixed fee | In Progress | Cascade | Jeff Spence | 38500 | 31042.55 | 1583.43 | 0 | 0% | 0 | 5.101% | 324 | 26.75 | 0 | 0%
26-PC-31802 | Bramble Creek Environmental Review Support | Fixed fee | Lab/Curation | Cascade | Jean Cooke | 53700 | 41655.09 | 23774.89 | 968.83 | 2.326% | 0 | 54.75% | 535 | 443.5 | 70.25 | 13.13%
26-PC-31823 | Slate Ridge Phase II Testing | Fixed fee | Final Reporting/Review | Cascade | Jeff Spence | 173900 | 122721.23 | 11344.93 | 40.49 | 0.03299% | 0 | 9.211% | 1756 | 179.75 | 1 | 0.05695%
26-PC-31830 | Ember Valley Archaeological Testing | Fixed fee | Transferred Entity | Cascade | Cassidy Gay | 86700 | 59425.39 | 27563.45 | 0 | 0% | 0 | 46.38% | 1094 | 381 | 0 | 0%
26-PC-31872 | Sumac Ridge Water Main Archaeological Testing | Fixed fee | Lab/Curation | Cascade | Donald Lutz | 63800 | 45642.52 | 24000.96 | 2821.27 | 6.181% | 1 | 46.4% | 622 | 433 | 103.75 | 16.68%
26-PC-31881 | Fern Valley Rail Siding Cultural Resources Monitoring | Fixed fee | In Progress | Cascade | Jean Cooke | 125300 | 94955.6 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-32047 | On-Call: Sumac Ridge Mine Expansion Paleontological Monitoring | Fixed fee | In Progress | Chesapeake | Ian Maddox | 73200 | 51825.6 | 36238.56 | 204.96 | 0.3955% | 0 | 69.53% | 883 | 747.25 | 3 | 0.3398%
26-PC-32069 | Task Order 25: Heron Marsh Wind Farm Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | Chesapeake | Sandy Kerr | 844700 | 646026.56 | 50316.32 | 866.6 | 0.1341% | 0 | 7.654% | 0 | 1097.75 | 20 | 0%
26-PC-32076 | Lone Pine Environmental Review Support | Fixed fee | Completed | Chesapeake | Alexandria Wilkinson | 165800 | 125610.08 | 111698.97 | 0 | 0% | 0 | 88.93% | 2545 | 1873.9 | 0 | 0%
26-PC-32094 | Maple Fork Trail - Phase II Testing | Time and material | In Progress | Chesapeake | Bryan Mann | 19000 | 11274.6 | 5989.44 | 0 | 0% | 0 | 53.12% | 65 | 47.25 | 0 | 0%
26-PC-32165 | Juniper Wash Park Improvements - Data Recovery | Time and material | In Progress | Chesapeake | Jason Oconnor | 501000 | 394086.6 | 10370.05 | 0 | 0% | 0 | 2.631% | 6396 | 207.25 | 0 | 0%
26-PC-32188 | Creosote Draw Reservoir Curation | Fixed fee | In Progress | Chesapeake | Ian Maddox | 91500 | 74856.15 | 0 | 0 | 0% | 0 | 0% | 1129 | 0 | 0 | 0%
26-PC-32227 | Foxglove Harbor Dredging Paleontological Monitoring | Time and material | Completed | Chesapeake | Sandy Kerr | 32900 | 22437.8 | 23290.1 | 852.3 | 3.799% | 0 | 100% | 316 | 356.19 | 40.19 | 12.72%
26-PC-32288 | Quail Run Solar - Architectural History Survey | Fixed fee | In Progress | Chesapeake | Ian Maddox | 400500 | 287318.7 | 3140.21 | 0 | 0% | 0 | 1.093% | 3493 | 38 | 0 | 0%
26-PC-32303 | Lone Pine Housing Development - Archaeological Testing | Time and material | In Progress | Chesapeake | Ian Maddox | 18700 | 13411.64 | 852.49 | 210.16 | 1.567% | 0 | 4.789% | 195 | 18.25 | 5.5 | 2.821%
26-PC-32322 | Foxglove Fiber Route - Curation | Fixed fee | In Progress | Chesapeake | Sandy Kerr | 317500 | 244665.5 | 30629.91 | 788.06 | 0.3221% | 0 | 12.2% | 1845 | 298.5 | 6.25 | 0.3388%
26-PC-32369 | Twin Buttes Water Main - Phase I Survey | Fixed fee | In Progress | Chesapeake | Ian Maddox | 730600 | 470798.64 | 45896.51 | 1060.88 | 0.2253% | 0 | 9.523% | 9652 | 1006.25 | 26.25 | 0.272%
26-PC-32382 | Sea Oat Airport Apron Data Recovery | Fixed fee | Final Billing/Invoice | Chesapeake | Ian Maddox | 180500 | 138172.75 | 160382.34 | 22209.59 | 16.07% | 1 | 100% | 1446 | 2461.57 | 1015.57 | 70.23%
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | Time and material | In Progress | Chesapeake | Bryan Mann | 13700 | 9522.87 | 31103.8 | 21580.93 | 226.6% | 1 | 100% | 90 | 311 | 221 | 245.6%
26-PC-32396 | On-Call: Copper Flats Mixed-Use Development Curation | Time and material | Final Reporting/Review | Chesapeake | Sandy Kerr | 205600 | 152123.45 | 3555.35 | 0 | 0% | 0 | 2.337% | 3197 | 68.75 | 0 | 0%
26-PC-32420 | Phase I: Copper Flats Water Main Architectural History Survey | Fixed fee | In Progress | Chesapeake | Alexandria Wilkinson | 324200 | 246926.01 | 10551.41 | 380.64 | 0.1542% | 0 | 4.119% | 0 | 121.5 | 9.75 | 0%
26-PC-32442 | Sumac Ridge Airport Apron Cultural Resources Assessment | Fixed fee | In Progress | Chesapeake | Sandy Kerr | 53400 | 33316.26 | 10661.31 | 170.24 | 0.511% | 0 | 31.49% | 621 | 212.5 | 4 | 0.6441%
26-PC-32453 | Quail Run Housing Development Phase II Testing | Time and material | In Progress | Chesapeake | Ian Maddox | 103800 | 74927.88 | 4515.47 | 0 | 0% | 0 | 6.026% | 1150 | 85.5 | 0 | 0%
26-PC-32540 | Task Order 36: Granite Pass Mixed-Use Development Phase II Testing | Time and material | Lab/Curation | Chesapeake | Bryan Mann | 846100 | 625775.56 | 55637.33 | 1749.34 | 0.2795% | 0 | 8.611% | 5451 | 567 | 21.75 | 0.399%
26-PC-32556 | Maple Fork Cultural Resources Monitoring | Fixed fee | In Progress | Chesapeake | Sandy Kerr | 45700 | 32259.63 | 11132.77 | -198.31 | -0.6147% | 0 | 35.12% | 0 | 224 | -4.75 | 0%
26-PC-32563 | On-Call: Creosote Draw Substation Phase I Survey | Fixed fee | Transferred Entity | Chesapeake | Bryan Mann | 534900 | 344315.13 | 85685.89 | 1802.81 | 0.5236% | 0 | 24.36% | 7530 | 1733.75 | 45.75 | 0.6076%
26-PC-32569 | Hawk Point Data Recovery | Fixed fee | Completed | Chesapeake | Bryan Mann | 191800 | 155949 | 151388.06 | 0 | 0% | 0 | 97.08% | 2174 | 2263.96 | 89.96 | 4.138%
26-PC-32594 | On-Call: Tamarack Rail Siding Cultural Resources Monitoring | Fixed fee | In Progress | Chesapeake | Jason Oconnor | 94400 | 71536.32 | 38790.59 | 608.97 | 0.8513% | 0 | 53.37% | 1184 | 576 | 13.25 | 1.119%
26-PC-32614 | Fern Valley Architectural History Survey | Time and material | In Progress | Chesapeake | Ian Maddox | 29700 | 20748.42 | 0 | 0 | 0% | 0 | 0% | 337 | 0 | 0 | 0%
26-PC-32646 | Goldfinch Historic Resources Evaluation | Time and material | In Progress | Chesapeake | Ian Maddox | 48600 | 33922.8 | 15954.41 | 0 | 0% | 0 | 47.03% | 671 | 332 | 0 | 0%
26-PC-32668 | Millbrook Trail - Data Recovery | Time and material | Final Billing/Invoice | Chesapeake | Alexandria Wilkinson | 300600 | 206151.48 | 209897.1 | 3745.62 | 1.817% | 0 | 100% | 2747 | 3181.49 | 477.7 | 17.39%
26-PC-32707 | On-Call: Creosote Draw Transmission Line Cultural Resources Monitoring | Fixed fee | In Progress | Chesapeake | Sandy Kerr | 327400 | 229376.44 | 106701.23 | 6651.87 | 2.9% | 0 | 43.62% | 0 | 1758.5 | 47.5 | 0%
26-PC-32711 | Creosote Draw Phase I Survey | Fixed fee | In Progress | Chesapeake | Jason Oconnor | 62100 | 44997.66 | 9419.94 | 0 | 0% | 0 | 20.93% | 597 | 144.25 | 0 | 0%
26-PC-32725 | Willow Springs Wind Farm - GIS Mapping | Fixed fee | Final Reporting/Review | Chesapeake | Bryan Mann | 26300 | 18699.3 | 11432 | 204.88 | 1.096% | 0 | 60.04% | 271 | 241.75 | 20 | 7.38%
26-PC-32727 | North Fork Mine Expansion - Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | Chesapeake | Alexandria Wilkinson | 70100 | 47310.49 | 38868.52 | 0 | 0% | 0 | 82.16% | 817 | 671.93 | 0 | 0%
26-PC-32731 | Wildrye Fiber Route Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Chesapeake | Bryan Mann | 26000 | 20311.2 | 15521.91 | 0 | 0% | 0 | 76.42% | 0 | 251.46 | 0 | 0%
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Time and material | Cost Tracking on Closed Project | Chesapeake | Sandy Kerr | 137100 | 100617.66 | 122245.29 | 21627.63 | 21.49% | 1 | 100% | 1063 | 1798.44 | 735.44 | 69.19%
26-PC-32745 | Task Order 37: Hawk Point Park Improvements Phase II Testing | Fixed fee | In Progress | Chesapeake | Ian Maddox | 135300 | 89758.02 | 37247.72 | 0 | 0% | 0 | 41.5% | 0 | 477.75 | 0 | 0%
26-PC-32773 | Oak Terrace Paleontological Monitoring | Fixed fee | In Progress | Front Range | Mindy Galvan | 48100 | 32496.36 | 14347.77 | 0 | 0% | 0 | 44.15% | 0 | 282.5 | 0 | 0%
26-PC-32803 | Copper Flats Housing Development Archaeological Testing | Time and material | Final Billing/Invoice | Front Range | Kimberly Daugherty | 198300 | 132700 | 163858.96 | 31158.96 | 23.48% | 1 | 100% | 1793 | 2712.7 | 919.7 | 51.29%
26-PC-32852 | Task Order 39: Foxglove Highway Widening Data Recovery | Time and material | In Progress | Front Range | Joanna Herrera | 148800 | 95395.68 | 18228.56 | 57.77 | 0.06056% | 0 | 19.05% | 1154 | 297 | 0.75 | 0.06499%
26-PC-32946 | Phase I: Plover Cove Levee Repair GIS Mapping | Time and material | On Hold | Front Range | Jeremy Tran | 151600 | 96190.2 | 0 | 0 | 0% | 0 | 0% | 1376 | 0 | 0 | 0%
26-PC-32973 | Sage Flat GIS Mapping | Time and material | On Hold | Front Range | Mindy Galvan | 203200 | 132028.51 | 0 | 0 | 0% | 0 | 0% | 1423 | 0 | 0 | 0%
26-PC-32985 | Pine Hollow Built Environment Survey | Fixed fee | In Progress | Front Range | Jeremy Tran | 106500 | 89214.38 | 54267.06 | 1122.84 | 1.259% | 0 | 59.57% | 0 | 784.5 | 22.5 | 0%
26-PC-33011 | Kestrel Butte Wastewater Plant Curation | Fixed fee | Completed | Front Range | Devon Pitts | 590600 | 477965.46 | 549114.61 | 71149.15 | 14.89% | 1 | 100% | 0 | 10044.31 | 0 | 0%
26-PC-33017 | Redbud Battery Storage - Maritime Remote Sensing Survey | Fixed fee | In Progress | Front Range | Mindy Galvan | 588600 | 441413.1 | 141067.52 | 3185.68 | 0.7217% | 0 | 31.24% | 0 | 1763.75 | 44 | 0%
26-PC-33033 | Task Order 10: Pebble Beach Road Highway Widening Environmental Review Support | Fixed fee | On Hold | Front Range | Joanna Herrera | 121200 | 102111 | 0 | 0 | 0% | 0 | 0% | 1062 | 0 | 0 | 0%
26-PC-33099 | Eagle Bend Maritime Remote Sensing Survey | Fixed fee | In Progress | Front Range | Joanna Herrera | 164900 | 122091.96 | 21510.67 | 0 | 0% | 0 | 17.62% | 1628 | 262 | 0 | 0%
26-PC-33127 | Fern Valley Phase I Survey | Time and material | In Progress | Front Range | Kimberly Daugherty | 179500 | 119968.02 | 30425.42 | 711.81 | 0.5933% | 0 | 24.77% | 0 | 287 | 6.25 | 0%
26-PC-33162 | Phase III: Yarrow Point Airport Apron GIS Mapping | Time and material | In Progress | Front Range | Dean Velazquez | 81900 | 55036.8 | 6614.55 | 0 | 0% | 0 | 12.02% | 0 | 135.75 | 0 | 0%
26-PC-33217 | Larkspur Phase II Testing | Fixed fee | Final Billing/Invoice | Front Range | Devon Pitts | 28700 | 20572.16 | 23901.25 | 3329.09 | 16.18% | 1 | 100% | 275 | 381.39 | 106.39 | 38.69%
26-PC-33223 | Meadowlark Levee Repair - Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Front Range | Jeremy Tran | 51600 | 37858.92 | 49216.6 | 11357.68 | 30% | 1 | 100% | 467 | 695.75 | 228.75 | 48.98%
26-PC-33255 | Task Order 13: Pine Hollow Substation Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | Front Range | Devon Pitts | 70300 | 51804.07 | 66810.42 | 15006.35 | 28.97% | 1 | 100% | 696 | 1017.65 | 321.65 | 46.21%
26-PC-33257 | Badger Hollow Levee Repair - Curation | Time and material | Completed | Front Range | Joanna Herrera | 60000 | 42360 | 42545.9 | 185.9 | 0.4389% | 0 | 100% | 390 | 632.89 | 242.89 | 62.28%
26-PC-33276 | Quail Run Housing Development Archaeological Testing | Time and material | In Progress | Front Range | Jeremy Tran | 64200 | 42609.54 | 10124.51 | 597.9 | 1.403% | 0 | 22.36% | 778 | 210.25 | 14.25 | 1.832%
26-PC-33413 | Hawk Point Bridge Replacement Cultural Resources Monitoring | Time and material | Final Billing/Invoice | Front Range | Jeremy Tran | 484800 | 325106.88 | 420732.7 | 95625.82 | 29.41% | 1 | 100% | 6333 | 6857.31 | 530.87 | 8.383%
26-PC-33485 | Sea Oat Harbor Dredging GIS Mapping | Time and material | In Progress | Front Range | Dean Velazquez | 563800 | 406950.84 | 29789.86 | 657.93 | 0.1617% | 0 | 7.159% | 3726 | 396.75 | 8.75 | 0.2348%
26-PC-33505 | Stone Mill Park Improvements - Maritime Remote Sensing Survey | Fixed fee | In Progress | Front Range | Mindy Galvan | 105100 | 81200.26 | 1152.88 | 0 | 0% | 0 | 1.42% | 411 | 8.25 | 0 | 0%
26-PC-33533 | Harbor View Wastewater Plant Phase I Survey | Fixed fee | Final Billing/Invoice | Front Range | Jeremy Tran | 37700 | 27626.56 | 35914.53 | 8287.97 | 30% | 1 | 100% | 427 | 569.74 | 142.74 | 33.43%
26-PC-33563 | Foxglove Phase I Survey | Fixed fee | In Progress | Front Range | Devon Pitts | 61100 | 42098.14 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-33588 | Fern Valley Trail - Cultural Resources Assessment | Time and material | Lab/Curation | Front Range | Joanna Herrera | 207400 | 141868.32 | 25436.78 | 980.47 | 0.6911% | 0 | 17.24% | 1883 | 494.5 | 21.25 | 1.129%
26-PC-33624 | Stone Mill Airport Apron - Phase II Testing | Fixed fee | Final Billing/Invoice | Front Range | Devon Pitts | 54500 | 38509.7 | 50062.61 | 11552.91 | 30% | 1 | 100% | 0 | 773.49 | 0 | 0%
26-PC-33660 | Task Order 33: Fern Valley Water Main Section 106 Consultation | Fixed fee | In Progress | Front Range | Dean Velazquez | 108400 | 94229.41 | 21052.73 | 113.22 | 0.1202% | 0 | 22.22% | 1375 | 340.5 | 3 | 0.2182%
26-PC-33684 | On-Call: Juniper Wash Airport Apron Paleontological Monitoring | Time and material | Final Reporting/Review | Front Range | Kimberly Daugherty | 24000 | 17450.4 | 2500.59 | 0 | 0% | 0 | 14.33% | 261 | 51.25 | 0 | 0%
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Fixed fee | Final Reporting/Review | Great Lakes | Karl Valenzuela | 21700 | 18501.42 | 21928.62 | 6367.34 | 34.42% | 1 | 84.11% | 197 | 281.5 | 88 | 44.67%
26-PC-33705 | Twin Buttes Phase I Survey | Fixed fee | In Progress | Great Lakes | Karl Valenzuela | 211200 | 166784.64 | 80257.45 | 1257.27 | 0.7538% | 0 | 47.37% | 0 | 1259.25 | 21.5 | 0%
26-PC-33719 | Saltgrass GIS Mapping | Fixed fee | In Progress | Great Lakes | Gina Beltran | 394200 | 310235.4 | 8878.32 | 0 | 0% | 0 | 2.862% | 8181 | 167.5 | 0 | 0%
26-PC-33727 | Task Order 25: Badger Hollow Canal Lining Architectural History Survey | Fixed fee | Final Billing/Invoice | Great Lakes | Angelica Cervantes | 185200 | 146011.68 | 135472.77 | 0 | 0% | 0 | 92.78% | 1693 | 2147.81 | 454.81 | 26.86%
26-PC-33743 | Raven Rock Canal Lining Architectural History Survey | Fixed fee | In Progress | Great Lakes | Brendan Padilla | 111800 | 75766.86 | 41526.74 | 9554.68 | 12.61% | 1 | 42.2% | 511 | 580 | 194 | 37.96%
26-PC-33773 | Aspen Ridge Maritime Remote Sensing Survey | Fixed fee | On Hold | Great Lakes | Geoffrey Fernandez | 41200 | 25469.84 | 0 | 0 | 0% | 0 | 0% | 345 | 0 | 0 | 0%
26-PC-33834 | On-Call: Silver Lake Canal Lining Curation | Fixed fee | In Progress | Great Lakes | Leonard Mejia | 204800 | 158052.15 | 37725.67 | 373.49 | 0.2363% | 0 | 23.63% | 3346 | 712.75 | 8.5 | 0.254%
26-PC-33896 | Maple Fork Trail Curation | Fixed fee | In Progress | Great Lakes | Nathan Lambert | 69800 | 48734.36 | 15222.15 | 0 | 0% | 0 | 31.23% | 518 | 173.75 | 0 | 0%
26-PC-33903 | Task Order 3: Silver Lake Solar Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | Great Lakes | Reginald Koch | 1201100 | 916078.97 | 1002792.56 | 86713.59 | 9.466% | 1 | 100% | 12240 | 14704.57 | 2464.57 | 20.14%
26-PC-33913 | Windmill Flat Section 106 Consultation | Time and material | Final Reporting/Review | Great Lakes | Angelica Cervantes | 31100 | 20015.96 | 1134.5 | 0 | 0% | 0 | 5.668% | 278 | 12.25 | 0 | 0%
26-PC-33950 | Raven Rock Built Environment Survey | Fixed fee | Final Billing/Invoice | Great Lakes | Robin Mercado | 483700 | 372594.11 | 306150.14 | 0 | 0% | 0 | 82.17% | 3653 | 4149.45 | 502.89 | 13.77%
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | Fixed fee | In Progress | Great Lakes | Nathan Lambert | 76400 | 53087.85 | 80951.18 | 27863.33 | 52.49% | 1 | 100% | 0 | 1018 | 35.5 | 0%
26-PC-34114 | Granite Pass Canal Lining - Section 106 Consultation | Time and material | In Progress | Great Lakes | Brendan Padilla | 216500 | 145812.75 | 9715.07 | 142.13 | 0.09747% | 0 | 6.565% | 3895 | 219.5 | 3.5 | 0.08986%
26-PC-34198 | Tansy Flat Pipeline - Historic Resources Evaluation | Time and material | In Progress | Great Lakes | Brendan Padilla | 65600 | 47297.6 | 9004.52 | 60.99 | 0.1289% | 0 | 18.91% | 583 | 168.5 | 1.25 | 0.2144%
26-PC-34247 | Harbor View Trail Phase I Survey | Fixed fee | Final Billing/Invoice | Great Lakes | Robin Mercado | 106200 | 73362.96 | 95371.85 | 22008.89 | 30% | 1 | 100% | 858 | 1210.69 | 352.69 | 41.11%
26-PC-34297 | Badger Hollow Historic Resources Evaluation | Fixed fee | In Progress | Great Lakes | Reginald Koch | 41700 | 29306.76 | 2455.17 | 0 | 0% | 0 | 8.377% | 611 | 51.75 | 0 | 0%
26-PC-34336 | Pine Hollow Solar Architectural History Survey | Fixed fee | In Progress | Great Lakes | Robin Mercado | 56500 | 40414.45 | 12273.01 | 428.82 | 1.061% | 0 | 29.31% | 772 | 264 | 10.5 | 1.36%
26-PC-34394 | Ember Valley Battery Storage Maritime Remote Sensing Survey | Time and material | In Progress | Great Lakes | Angelica Cervantes | 134200 | 94370.11 | 0 | 0 | 0% | 0 | 0% | 884 | 0 | 0 | 0%
26-PC-34400 | Wren Hollow Curation | Fixed fee | In Progress | Great Lakes | Leonard Mejia | 34200 | 23833.56 | 1444.35 | 0 | 0% | 0 | 6.06% | 158 | 9.75 | 0 | 0%
26-PC-34432 | Stone Mill Bridge Replacement - GIS Mapping | Fixed fee | Final Reporting/Review | Great Lakes | Reginald Koch | 117900 | 80620.02 | 7006.23 | 0 | 0% | 0 | 8.69% | 790 | 102.5 | 0 | 0%
26-PC-34472 | Eagle Bend Canal Lining Phase II Testing | Time and material | Completed | Great Lakes | Gina Beltran | 25400 | 16500.99 | 14935.8 | 0 | 0% | 0 | 90.51% | 284 | 209.3 | 0 | 0%
26-PC-34477 | Willow Springs Pipeline - Cultural Resources Monitoring | Fixed fee | In Progress | Great Lakes | Geoffrey Fernandez | 212500 | 157143.75 | 17368.48 | 347.14 | 0.2209% | 0 | 10.83% | 2598 | 300.75 | 8.5 | 0.3272%
26-PC-34487 | Quail Run Airport Apron - Phase I Survey | Time and material | In Progress | Great Lakes | Jeff Pugh | 488600 | 348176.36 | 135902.87 | 3978.79 | 1.143% | 0 | 37.89% | 7902 | 2249.75 | 67.75 | 0.8574%
26-PC-34552 | Blue Heron Mine Expansion Phase I Survey | Fixed fee | Lab/Curation | Great Lakes | Geoffrey Fernandez | 245500 | 205115.25 | 3881.68 | 256.15 | 0.1249% | 0 | 1.768% | 4357 | 68.5 | 5.25 | 0.1205%
26-PC-34574 | Elk Meadow Pipeline Paleontological Monitoring | Time and material | Completed | Great Lakes | Brendan Padilla | 1357400 | 944343.18 | 1020057.26 | 75714.08 | 8.018% | 1 | 100% | 17017 | 15224.6 | 81.08 | 0.4765%
26-PC-34602 | Phase III: Sandpiper Park Improvements Historic Resources Evaluation | Fixed fee | In Progress | Great Lakes | Brendan Padilla | 36800 | 26501.12 | 23274.94 | 301.19 | 1.137% | 0 | 86.69% | 239 | 366.25 | 127.25 | 53.24%
26-PC-34611 | Wren Hollow Pipeline Environmental Review Support | Time and material | In Progress | Great Lakes | Robin Mercado | 365800 | 264180.76 | 0 | 0 | 0% | 0 | 0% | 4543 | 0 | 0 | 0%
26-PC-34628 | Meadowlark Canal Lining Class III Survey | Fixed fee | Final Billing/Invoice | Great Lakes | Leonard Mejia | 121500 | 80104.95 | 75141.77 | 0 | 0% | 0 | 93.8% | 726 | 1024.4 | 298.4 | 41.1%
26-PC-34631 | Tamarack Battery Storage - Phase I Survey | Fixed fee | Completed | Great Lakes | Brendan Padilla | 438600 | 344257.14 | 339100.9 | 0 | 0% | 0 | 98.5% | 3690 | 4753.55 | 1063.55 | 28.82%
26-PC-34701 | North Fork Paleontological Monitoring | Time and material | Final Billing/Invoice | Great Lakes | Kathleen Galvan | 248300 | 162629.9 | 211418.87 | 48788.97 | 30% | 1 | 100% | 1594 | 2982.55 | 1388.55 | 87.11%
26-PC-34711 | Hackberry Bend Section 106 Consultation | Fixed fee | Completed | Great Lakes | Karl Valenzuela | 34000 | 25561.2 | 21829.21 | 0 | 0% | 0 | 85.4% | 0 | 330.06 | 0 | 0%
26-PC-34725 | Redbud Paleontological Monitoring | Fixed fee | In Progress | Great Lakes | Kathleen Galvan | 107600 | 89211.16 | 10016.63 | 979.69 | 1.098% | 0 | 10.13% | 1060 | 138 | 13.5 | 1.274%
26-PC-34757 | Kestrel Butte Data Recovery | Time and material | In Progress | Great Lakes | Angelica Cervantes | 43800 | 30230.76 | 49508.25 | 22359.89 | 73.96% | 1 | 89.8% | 281 | 597 | 316 | 112.5%
26-PC-34794 | On-Call: Kestrel Butte Reservoir Class III Survey | Fixed fee | Completed | Gulf Coast | Courtney Daugherty | 40000 | 25252 | 32827.6 | 7575.6 | 30% | 1 | 100% | 407 | 524.71 | 117.71 | 28.92%
26-PC-34906 | Cedar Hollow Harbor Dredging - Curation | Fixed fee | In Progress | Gulf Coast | Sean Jennings | 81100 | 60821.43 | 31471.96 | 1023.99 | 1.684% | 0 | 50.06% | 1147 | 609.75 | 21.75 | 1.896%
26-PC-34965 | On-Call: Pebble Beach Road Fiber Route Section 106 Consultation | Fixed fee | Final Reporting/Review | Gulf Coast | Wyatt Erickson | 131600 | 95225.76 | 0 | 0 | 0% | 0 | 0% | 824 | 0 | 0 | 0%
26-PC-34982 | Sandpiper Historic Resources Evaluation | Time and material | In Progress | Gulf Coast | Bernard Erickson | 10600 | 7895.94 | 18818.09 | 10922.15 | 138.3% | 1 | 100% | 110 | 247.25 | 137.25 | 124.8%
26-PC-35012 | Task Order 40: Granite Pass Harbor Dredging Archaeological Testing | Time and material | Final Billing/Invoice | Gulf Coast | Wyatt Erickson | 179700 | 130282.5 | 155527.73 | 25245.23 | 19.38% | 1 | 100% | 0 | 2604.94 | 0 | 0%
26-PC-35056 | Yarrow Point Cell Tower - Section 106 Consultation | Fixed fee | Lab/Curation | Gulf Coast | Sean Jennings | 92800 | 78555.2 | 39261.22 | 5782.96 | 7.362% | 1 | 42.62% | 1032 | 782.5 | 201.75 | 19.55%
26-PC-35062 | Phase I: Falcon Mesa Park Improvements Data Recovery | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 267300 | 207542.06 | 23807.73 | 754.86 | 0.3637% | 0 | 11.11% | 2128 | 341.75 | 12.25 | 0.5757%
26-PC-35063 | Meadowlark School Campus - Phase I Survey | Fixed fee | Final Reporting/Review | Gulf Coast | Bernard Erickson | 112100 | 70129.76 | 37016.49 | 2937.82 | 4.189% | 0 | 48.59% | 0 | 805.5 | 6.25 | 0%
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | Fixed fee | In Progress | Gulf Coast | Courtney Daugherty | 29600 | 19287.36 | 56287.28 | 36999.92 | 191.8% | 1 | 100% | 252 | 737.5 | 485.5 | 192.7%
26-PC-35111 | Fern Valley GIS Mapping | Fixed fee | Final Billing/Invoice | Gulf Coast | Bernard Erickson | 114800 | 81129.16 | 73694.31 | 0 | 0% | 0 | 90.84% | 683 | 1250.58 | 567.58 | 83.1%
26-PC-35158 | Sparrow Hill Trail Phase I Survey | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 41600 | 27755.93 | 8426.77 | 470.69 | 1.696% | 0 | 28.66% | 309 | 89.25 | 6.25 | 2.023%
26-PC-35193 | Heron Marsh Reservoir - Phase II Testing | Fixed fee | In Progress | Gulf Coast | Courtney Daugherty | 102600 | 74022.89 | 59527.5 | 576.26 | 0.7785% | 0 | 79.64% | 1368 | 1076 | 14 | 1.023%
26-PC-35201 | Plover Cove Transmission Line Data Recovery | Fixed fee | Lab/Curation | Gulf Coast | Sean Jennings | 51600 | 40057.08 | 1211.47 | 0 | 0% | 0 | 3.024% | 0 | 29.25 | 0 | 0%
26-PC-35220 | Badger Hollow Highway Widening GIS Mapping | Time and material | In Progress | Gulf Coast | Bernard Erickson | 109500 | 69598.2 | 3074.48 | 163.16 | 0.2344% | 0 | 4.183% | 989 | 54.25 | 4 | 0.4044%
26-PC-35245 | Stone Mill Cell Tower - Curation | Time and material | Completed | Gulf Coast | Wyatt Erickson | 240900 | 162438.87 | 157928.04 | 0 | 0% | 0 | 97.22% | 0 | 2339.24 | 0 | 0%
26-PC-35248 | Granite Pass Levee Repair - Curation | Fixed fee | Final Billing/Invoice | Gulf Coast | Bernard Erickson | 107400 | 75437.76 | 65927.7 | 0 | 0% | 0 | 87.39% | 855 | 1037.73 | 182.73 | 21.37%
26-PC-35302 | Task Order 37: Hackberry Bend Battery Storage Cultural Resources Monitoring | Fixed fee | In Progress | Gulf Coast | Bernard Erickson | 82400 | 69199.52 | 27118.13 | 199.2 | 0.2879% | 0 | 38.9% | 1094 | 504 | 4.25 | 0.3885%
26-PC-35318 | Copper Flats Curation | Fixed fee | In Progress | Gulf Coast | Wyatt Erickson | 153900 | 103851.72 | 25162.21 | 135.63 | 0.1306% | 0 | 24.1% | 1934 | 517.25 | 2.75 | 0.1422%
26-PC-35381 | Badger Hollow Mine Expansion Archaeological Testing | Fixed fee | In Progress | High Desert | Bridget Maddox | 77800 | 51064.93 | 36896.8 | 3620.85 | 7.091% | 1 | 65.16% | 657 | 610.75 | 108.75 | 16.55%
26-PC-35401 | Raven Rock Phase II Testing | Time and material | In Progress | High Desert | Bridget Maddox | 312900 | 205376.26 | 21093.83 | -215.94 | -0.1051% | 0 | 10.38% | 1873 | 311.25 | -0.5 | -0.0267%
26-PC-35449 | Saltgrass Cultural Resources Monitoring | Time and material | In Progress | High Desert | Bridget Maddox | 145800 | 103226.4 | 22115.43 | 113.47 | 0.1099% | 0 | 21.31% | 900 | 255 | 1 | 0.1111%
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | Fixed fee | In Progress | High Desert | Eileen Poole | 68900 | 53679.99 | 46380.28 | 5149.87 | 9.594% | 1 | 76.81% | 746 | 905.75 | 306 | 41.02%
26-PC-35583 | On-Call: Eagle Bend Highway Widening Phase II Testing | Time and material | In Progress | High Desert | Jody Wang | 39700 | 28536.36 | 1470.29 | 0 | 0% | 0 | 5.152% | 491 | 28.5 | 0 | 0%
26-PC-35588 | Fern Valley Wind Farm - Class III Survey | Fixed fee | Completed | High Desert | Eileen Poole | 148800 | 130289.28 | 169376.06 | 39086.78 | 30% | 1 | 100% | 1303 | 3136.31 | 1833.31 | 140.7%
26-PC-35596 | Millbrook Solar GIS Mapping | Fixed fee | Lab/Curation | High Desert | Eileen Poole | 197200 | 149142.36 | 31870.85 | 0 | 0% | 0 | 21.37% | 3595 | 642 | 0 | 0%
26-PC-35598 | Task Order 3: Raven Rock Rail Siding Built Environment Survey | Time and material | Final Billing/Invoice | High Desert | Eileen Poole | 22100 | 15626.91 | 20314.98 | 4688.07 | 30% | 1 | 100% | 287 | 334.31 | 47.31 | 16.48%
26-PC-35635 | Wren Hollow Architectural History Survey | Fixed fee | In Progress | High Desert | Eileen Poole | 223600 | 138900.32 | 40059.7 | 1810.57 | 1.304% | 0 | 27.54% | 0 | 752.25 | 37.75 | 0%
26-PC-35650 | Aspen Ridge Harbor Dredging - Maritime Remote Sensing Survey | Time and material | In Progress | High Desert | Jody Wang | 155300 | 100626.66 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-35698 | Silver Lake Class III Survey | Time and material | Completed | High Desert | Bridget Maddox | 274000 | 188320.48 | 244816.62 | 56496.14 | 30% | 1 | 100% | 2258 | 3985.12 | 1727.12 | 76.49%
26-PC-35730 | Larkspur Solar Class III Survey | Fixed fee | In Progress | High Desert | Eileen Poole | 74800 | 50078.6 | 2126.96 | 0 | 0% | 0 | 4.247% | 852 | 43.75 | 0 | 0%
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Fixed fee | Cost Tracking on Closed Project | High Desert | Jody Wang | 26300 | 19575.09 | 22787.95 | 3212.86 | 16.41% | 1 | 100% | 385 | 432.23 | 51.64 | 13.41%
26-PC-35789 | Cedar Hollow Environmental Review Support | Time and material | In Progress | High Desert | Eileen Poole | 3800 | 2575.26 | 95.95 | 9.39 | 0.3646% | 0 | 3.361% | 73 | 2.25 | 0.25 | 0.3425%
26-PC-35803 | Tamarack Airport Apron GIS Mapping | Time and material | In Progress | High Desert | Jody Wang | 82900 | 52144.1 | 123.8 | 0 | 0% | 0 | 0.2374% | 758 | 2.5 | 0 | 0%
26-PC-35811 | Phase III: Wildrye Solar Architectural History Survey | Time and material | In Progress | High Desert | Eileen Poole | 19500 | 12897.3 | 0 | 0 | 0% | 0 | 0% | 225 | 0 | 0 | 0%
26-PC-35828 | Aspen Ridge Park Improvements - Class III Survey | Time and material | In Progress | High Desert | Jody Wang | 48300 | 31733.1 | 19018.68 | 438.69 | 1.382% | 0 | 58.55% | 308 | 209.25 | 5.25 | 1.705%
26-PC-35920 | Phase I: Creosote Draw Park Improvements Historic Resources Evaluation | Time and material | In Progress | High Desert | Eileen Poole | 61600 | 42591.82 | 0 | 0 | 0% | 0 | 0% | 672 | 0 | 0 | 0%
26-PC-35937 | Pebble Beach Road Built Environment Survey | Fixed fee | Transferred Entity | High Desert | Kathy Hurley | 73700 | 51155.17 | 5050.91 | 0 | 0% | 0 | 9.874% | 1539 | 104.5 | 0 | 0%
26-PC-35984 | Timber Gap Bridge Replacement Archaeological Testing | Time and material | Final Reporting/Review | High Desert | Bridget Maddox | 75200 | 47215.34 | 10159.67 | 606.39 | 1.284% | 0 | 20.23% | 804 | 176.5 | 14.5 | 1.803%
26-PC-36056 | Rushgrass Draw Historic Resources Evaluation | Fixed fee | Completed | High Desert | Bridget Maddox | 559500 | 461307.75 | 474417.43 | 13109.68 | 2.842% | 0 | 100% | 7519 | 7880.12 | 361.12 | 4.803%
26-PC-36110 | Blue Heron Canal Lining - Section 106 Consultation | Fixed fee | In Progress | High Desert | Bridget Maddox | 776100 | 567018.66 | 40481.07 | 667.12 | 0.1177% | 0 | 7.022% | 12606 | 827.5 | 15.5 | 0.123%
26-PC-36112 | Task Order 31: Twin Buttes Housing Development Built Environment Survey | Fixed fee | Final Billing/Invoice | High Desert | Kathy Hurley | 39800 | 29581.08 | 38455.4 | 8874.32 | 30% | 1 | 100% | 466 | 724.18 | 258.18 | 55.4%
26-PC-36208 | Foxglove Fiber Route GIS Mapping | Time and material | Final Billing/Invoice | High Desert | Jody Wang | 36600 | 24946.56 | 26109.81 | 1163.25 | 4.663% | 0 | 100% | 401 | 393.71 | 11.13 | 2.776%
26-PC-36247 | Harbor View Maritime Remote Sensing Survey | Fixed fee | In Progress | Island | Maurice Dodson | 44300 | 33455.36 | 394.65 | 56.24 | 0.1681% | 0 | 1.012% | 418 | 8 | 1.25 | 0.299%
26-PC-36281 | Saltgrass Mixed-Use Development Architectural History Survey | Time and material | In Progress | Island | Becky Velazquez | 25900 | 16954.14 | 138.86 | 0 | 0% | 0 | 0.819% | 0 | 2.5 | 0 | 0%
26-PC-36361 | Dove Canyon Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | Island | Maurice Dodson | 343400 | 282103.1 | 295342.63 | 13239.53 | 4.693% | 0 | 100% | 2581 | 4061.6 | 1480.6 | 57.37%
26-PC-36394 | Meadowlark Cultural Resources Monitoring | Fixed fee | In Progress | Island | Briana Melton | 61900 | 39879.42 | 2084.51 | 0 | 0% | 0 | 5.227% | 610 | 24.75 | 0 | 0%
26-PC-36396 | Task Order 9: Twin Buttes Solar Architectural History Survey | Fixed fee | In Progress | Island | Briana Melton | 77700 | 47283.31 | 5937.18 | 76.74 | 0.1623% | 0 | 12.39% | 467 | 79.75 | 1 | 0.2141%
26-PC-36416 | Task Order 2: Thistle Down Wind Farm Archaeological Testing | Fixed fee | Lab/Curation | Island | Maurice Dodson | 589600 | 462173.13 | 212155.53 | 2001.46 | 0.4331% | 0 | 45.47% | 3666 | 2408.75 | 30 | 0.8183%
26-PC-36477 | Elk Meadow Pipeline - Environmental Review Support | Fixed fee | Final Billing/Invoice | Island | Briana Melton | 70100 | 51383.3 | 66798.29 | 15414.99 | 30% | 1 | 100% | 587 | 1013.97 | 426.97 | 72.74%
26-PC-36537 | Yarrow Point Park Improvements Built Environment Survey | Fixed fee | In Progress | Island | Becky Velazquez | 125300 | 86482.06 | 27291.84 | 515.57 | 0.5962% | 0 | 30.96% | 988 | 448.75 | 26.75 | 2.707%
26-PC-36548 | Phase II: Granite Pass Levee Repair Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Island | Becky Velazquez | 59700 | 35999.1 | 41117.1 | 5118 | 14.22% | 1 | 100% | 395 | 451 | 65.34 | 16.54%
26-PC-36555 | Coyote Springs Pipeline Class III Survey | Time and material | On Hold | Island | Joan Mathis | 206100 | 139514.38 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-36581 | Harbor View Maritime Remote Sensing Survey | Fixed fee | In Progress | Island | Briana Melton | 127600 | 76674.84 | 29299.63 | 506.84 | 0.661% | 0 | 37.55% | 831 | 397.75 | 9.25 | 1.113%
26-PC-36595 | Blue Heron School Campus - Cultural Resources Monitoring | Time and material | Completed | Lakeshore | Lucas Benson | 35700 | 26328.75 | 31762.49 | 5433.74 | 20.64% | 1 | 100% | 207 | 400.63 | 193.63 | 93.54%
26-PC-36602 | Sea Oat Airport Apron Cultural Resources Monitoring | Fixed fee | In Progress | Lakeshore | Terrence Gillespie | 396600 | 288646.28 | 41680.57 | 372.63 | 0.1291% | 0 | 14.31% | 3485 | 499.5 | 4.25 | 0.122%
26-PC-36616 | Lone Pine Harbor Dredging - Section 106 Consultation | Fixed fee | Final Billing/Invoice | Lakeshore | Terrence Gillespie | 79100 | 51885.54 | 38340.61 | 0 | 0% | 0 | 73.89% | 586 | 506.85 | 8.51 | 1.452%
26-PC-36726 | Willow Springs Cultural Resources Assessment | Fixed fee | In Progress | Lakeshore | Lucas Benson | 153200 | 110288.68 | 12003.91 | 79.11 | 0.07173% | 0 | 10.81% | 1117 | 140.75 | 0.75 | 0.06714%
26-PC-36749 | Windmill Flat Water Main - Cultural Resources Assessment | Fixed fee | In Progress | Lakeshore | Lucas Benson | 199000 | 173567.8 | 83133.93 | 1008.6 | 0.5811% | 0 | 47.32% | 2352 | 985.25 | 10.5 | 0.4464%
26-PC-36750 | Task Order 15: North Fork Canal Lining Data Recovery | Time and material | In Progress | Lakeshore | Terrence Gillespie | 121800 | 80948.28 | 13368.46 | 175.91 | 0.2173% | 0 | 16.3% | 1714 | 209.25 | 4.25 | 0.248%
26-PC-36775 | Falcon Mesa Cultural Resources Monitoring | Fixed fee | Transferred Entity | Hill Country | Gail Meza | 90800 | 77565.54 | 160.5 | 18.98 | 0.02447% | 0 | 0.1825% | 1726 | 3.5 | 0.5 | 0.02897%
26-PC-36802 | Thistle Down Canal Lining - Cultural Resources Assessment | Time and material | Final Reporting/Review | Hill Country | Gail Meza | 71600 | 52303.8 | 0 | 0 | 0% | 0 | 0% | 729 | 0 | 0 | 0%
26-PC-36828 | Phase III: Rushgrass Draw Canal Lining GIS Mapping | Time and material | In Progress | Hill Country | Gail Meza | 28100 | 19006.84 | 844.43 | 0 | 0% | 0 | 4.443% | 193 | 11.5 | 0 | 0%
26-PC-36861 | North Fork Park Improvements - Cultural Resources Assessment | Fixed fee | In Progress | Hill Country | Samuel Wilkerson | 463900 | 337255.3 | 8285.61 | 271.5 | 0.0805% | 0 | 2.376% | 0 | 148.5 | 6 | 0%
26-PC-36944 | Copper Flats Levee Repair - Data Recovery | Fixed fee | Final Reporting/Review | Hill Country | Marcus Shea | 102000 | 68921.4 | 12352.09 | 0 | 0% | 0 | 17.92% | 851 | 177.75 | 0 | 0%
26-PC-36945 | Hawk Point Fiber Route - Maritime Remote Sensing Survey | Fixed fee | In Progress | Hill Country | Gail Meza | 496500 | 329824.95 | 140294.43 | 2795.55 | 0.8476% | 0 | 41.69% | 3948 | 1427.5 | 38 | 0.9625%
26-PC-36949 | On-Call: Sandpiper Transmission Line Cultural Resources Monitoring | Time and material | Completed | Hill Country | Glen Delacruz | 100300 | 70075.49 | 80869.16 | 10793.67 | 15.4% | 1 | 100% | 895 | 1318.86 | 423.86 | 47.36%
26-PC-37015 | Phase III: Hawk Point Substation Phase II Testing | Fixed fee | On Hold | Hill Country | Suzanne Mcmillan | 40400 | 28833.48 | 0 | 0 | 0% | 0 | 0% | 282 | 0 | 0 | 0%
26-PC-37016 | Aspen Ridge Built Environment Survey | Time and material | Final Billing/Invoice | Hill Country | Suzanne Mcmillan | 26000 | 19416.8 | 13591.76 | 0 | 0% | 0 | 70% | 185 | 146.06 | 0 | 0%
26-PC-37024 | Hackberry Bend Mine Expansion - Maritime Remote Sensing Survey | Fixed fee | In Progress | Hill Country | Danielle Villanueva | 78900 | 63394.72 | 10425.9 | 15.95 | 0.02516% | 0 | 16.42% | 906 | 155.75 | 0.25 | 0.02759%
26-PC-37032 | Raven Rock Section 106 Consultation | Fixed fee | Final Billing/Invoice | Hill Country | Gail Meza | 155000 | 112060.12 | 145678.16 | 33618.04 | 30% | 1 | 100% | 0 | 1798.09 | 0 | 0%
26-PC-37051 | On-Call: Sandpiper Rail Siding Section 106 Consultation | Fixed fee | Lab/Curation | Hill Country | Theresa Fernandez | 365900 | 243543.04 | 7245.79 | 0 | 0% | 0 | 2.975% | 0 | 159.25 | 0 | 0%
26-PC-37068 | Copper Flats Highway Widening - Data Recovery | Time and material | On Hold | Hill Country | Marcus Shea | 419100 | 298944.03 | 0 | 0 | 0% | 0 | 0% | 2361 | 0 | 0 | 0%
26-PC-37073 | Kestrel Butte Pipeline Curation | Fixed fee | In Progress | Hill Country | Marcus Shea | 441700 | 346822.84 | 8825.19 | 493.92 | 0.1424% | 0 | 2.402% | 3380 | 94.25 | 5 | 0.1479%
26-PC-37089 | Rushgrass Draw GIS Mapping | Time and material | In Progress | Hill Country | Gail Meza | 28900 | 19054.14 | 1063.18 | 79.74 | 0.4185% | 0 | 5.161% | 172 | 14.5 | 1.25 | 0.7267%
26-PC-37136 | Yarrow Point Housing Development - Section 106 Consultation | Fixed fee | In Progress | Hill Country | Marcus Shea | 153700 | 109797.26 | 38767.56 | 573.38 | 0.5222% | 0 | 34.79% | 0 | 531.25 | 12.25 | 0%
26-PC-37137 | Sea Oat Archaeological Testing | Fixed fee | Final Billing/Invoice | Hill Country | Gail Meza | 105600 | 78492.48 | 64062.46 | 0 | 0% | 0 | 81.62% | 927 | 704.05 | 0 | 0%
26-PC-37138 | Granite Pass Canal Lining - Environmental Review Support | Time and material | Final Reporting/Review | Hill Country | Gail Meza | 315800 | 223705.16 | 33971.44 | 302.07 | 0.135% | 0 | 15.05% | 1618 | 329.5 | 2.5 | 0.1545%
26-PC-37139 | Goldfinch Reservoir Environmental Review Support | Time and material | In Progress | Hill Country | Theresa Fernandez | 1070500 | 734587.52 | 66797.88 | 999.48 | 0.1361% | 0 | 8.957% | 9379 | 852.75 | 15.5 | 0.1653%
26-PC-37160 | Twin Buttes Environmental Review Support | Time and material | Completed | Hill Country | Samuel Wilkerson | 733800 | 451360.38 | 496365.43 | 45005.05 | 9.971% | 1 | 100% | 7049 | 6060.72 | 0 | 0%
26-PC-37166 | Stone Mill Airport Apron - Section 106 Consultation | Time and material | Completed | Hill Country | Marcus Shea | 252900 | 181708.65 | 201511.59 | 19802.94 | 10.9% | 1 | 100% | 3217 | 2639.11 | 94.4 | 2.934%
26-PC-37196 | Sea Oat Built Environment Survey | Fixed fee | In Progress | Hill Country | Suzanne Mcmillan | 26900 | 22881.14 | 0 | 0 | 0% | 0 | 0% | 220 | 0 | 0 | 0%
26-PC-37204 | On-Call: Saltgrass Housing Development Built Environment Survey | Time and material | In Progress | Hill Country | Gail Meza | 201900 | 145630.47 | 45387.98 | 573.45 | 0.3938% | 0 | 30.77% | 2560 | 816.5 | 15 | 0.5859%
26-PC-37224 | On-Call: Ember Valley Trail Class III Survey | Time and material | Final Billing/Invoice | Hill Country | Glen Delacruz | 168700 | 129802.56 | 117866.55 | 0 | 0% | 0 | 90.8% | 1306 | 1474.15 | 208.98 | 16%
26-PC-37271 | Maple Fork Wind Farm Built Environment Survey | Time and material | In Progress | Hill Country | Gail Meza | 879900 | 587259.92 | 171065.39 | 893.06 | 0.1521% | 0 | 28.98% | 0 | 2070 | 14 | 0%
26-PC-37282 | Windmill Flat Harbor Dredging GIS Mapping | Fixed fee | In Progress | Hill Country | Suzanne Mcmillan | 48800 | 41616.64 | 649.36 | 0 | 0% | 0 | 1.56% | 386 | 7.75 | 0 | 0%
26-PC-37311 | North Fork School Campus - Paleontological Monitoring | Time and material | On Hold | Hill Country | Marcus Shea | 49100 | 34527.12 | 0 | 0 | 0% | 0 | 0% | 334 | 0 | 0 | 0%
26-PC-37317 | Hackberry Bend Environmental Review Support | Time and material | In Progress | Hill Country | Danielle Villanueva | 348700 | 224737.15 | 7817.14 | 497.75 | 0.2215% | 0 | 3.257% | 0 | 144.25 | 11 | 0%
26-PC-37322 | Maple Fork Canal Lining Built Environment Survey | Time and material | In Progress | Hill Country | Danielle Villanueva | 30900 | 21095.43 | 2933.98 | 0 | 0% | 0 | 13.91% | 436 | 67.75 | 0 | 0%
26-PC-37329 | Stone Mill Battery Storage Built Environment Survey | Fixed fee | Final Reporting/Review | Hill Country | Glen Delacruz | 32600 | 25463.86 | 16175.73 | 570.78 | 2.242% | 0 | 61.28% | 360 | 215 | 8.5 | 2.361%
26-PC-37367 | Millbrook Trail - Cultural Resources Assessment | Time and material | Completed | Hill Country | Theresa Fernandez | 196400 | 130802.4 | 117597.88 | 0 | 0% | 0 | 89.9% | 1061 | 1461.96 | 402.36 | 37.92%
26-PC-37368 | Cedar Hollow Mine Expansion - Section 106 Consultation | Fixed fee | In Progress | Piedmont | Maria Parrish | 201100 | 123555.84 | 5568.92 | 0 | 0% | 0 | 4.507% | 2280 | 112.75 | 0 | 0%
26-PC-37428 | Ember Valley Section 106 Consultation | Fixed fee | In Progress | Piedmont | Megan Pineda | 57900 | 44206.65 | 12898.79 | 597.44 | 1.351% | 0 | 27.83% | 523 | 229.25 | 11.25 | 2.151%
26-PC-37441 | Juniper Wash Transmission Line Built Environment Survey | Time and material | Final Billing/Invoice | Piedmont | Megan Pineda | 91500 | 66758.4 | 47155.66 | 0 | 0% | 0 | 70.64% | 0 | 725.7 | 0 | 0%
26-PC-37477 | Dove Canyon Data Recovery | Fixed fee | On Hold | Piedmont | Annette Vaughan | 41100 | 28424.76 | 0 | 0 | 0% | 0 | 0% | 541 | 0 | 0 | 0%
26-PC-37511 | Badger Hollow Paleontological Monitoring | Time and material | Final Billing/Invoice | Piedmont | Jody Chung | 202900 | 142943.05 | 174521.6 | 31578.55 | 22.09% | 1 | 100% | 2343 | 2625.56 | 384.31 | 16.4%
26-PC-37513 | Harbor View Housing Development Paleontological Monitoring | Fixed fee | Final Reporting/Review | Piedmont | Jody Chung | 34700 | 23634.17 | 0 | 0 | 0% | 0 | 0% | 236 | 0 | 0 | 0%
26-PC-37520 | Elk Meadow Wastewater Plant Maritime Remote Sensing Survey | Fixed fee | Completed | Piedmont | Jody Chung | 59200 | 43476.48 | 51249.96 | 7773.48 | 17.88% | 1 | 100% | 481 | 753.85 | 272.85 | 56.73%
26-PC-37543 | Pebble Beach Road Historic Resources Evaluation | Fixed fee | In Progress | Piedmont | Maria Parrish | 330200 | 218394.28 | 98791.11 | 1217.56 | 0.5575% | 0 | 44.68% | 2677 | 1046.75 | 14.75 | 0.551%
26-PC-37559 | Badger Hollow Paleontological Monitoring | Time and material | In Progress | Piedmont | Jody Chung | 44300 | 28024.18 | 45539.17 | 19152.87 | 68.34% | 1 | 94.16% | 196 | 519.75 | 323.75 | 165.2%
26-PC-37671 | Harbor View Mixed-Use Development Architectural History Survey | Time and material | In Progress | Piedmont | Annette Vaughan | 145900 | 92486.01 | 6017.12 | 0 | 0% | 0 | 6.506% | 0 | 126.5 | 0 | 0%
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | Fixed fee | In Progress | Piedmont | Jody Chung | 40300 | 32312.54 | 25475.13 | 3257.38 | 10.08% | 1 | 68.76% | 428 | 398 | 65.5 | 15.3%
26-PC-37709 | Sage Flat Phase I Survey | Fixed fee | Final Reporting/Review | Piedmont | Maria Parrish | 31500 | 21725.55 | 30289.12 | 11868.64 | 54.63% | 1 | 84.79% | 336 | 437.25 | 157 | 46.73%
26-PC-37788 | Sumac Ridge Cultural Resources Assessment | Fixed fee | In Progress | Piedmont | Jody Chung | 1112800 | 826476.56 | 16908.48 | 257.7 | 0.03118% | 0 | 2.015% | 11079 | 308.25 | 6 | 0.05416%
26-PC-37801 | Slate Ridge Section 106 Consultation | Time and material | Completed | Piedmont | Megan Pineda | 72500 | 48408.25 | 54438.34 | 6030.09 | 12.46% | 1 | 100% | 600 | 810.36 | 210.36 | 35.06%
26-PC-37860 | Slate Ridge Phase II Testing | Fixed fee | Final Billing/Invoice | Piedmont | Annette Vaughan | 27600 | 19836.12 | 22675.01 | 2838.89 | 14.31% | 1 | 100% | 380 | 367.22 | 0.64 | 0.1684%
26-PC-37924 | Raven Rock Architectural History Survey | Time and material | Completed | Piedmont | Jody Chung | 33600 | 23886.24 | 31052.11 | 7165.87 | 30% | 1 | 100% | 337 | 495.85 | 158.85 | 47.14%
26-PC-37965 | Redbud Cultural Resources Assessment | Time and material | In Progress | Piedmont | Annette Vaughan | 55400 | 34625 | 31687.21 | 194.2 | 0.5609% | 0 | 90.95% | 590 | 577.75 | 4.5 | 0.7627%
26-PC-38019 | Phase II: Timber Gap Airport Apron Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | Prairie | Sherry Lloyd | 13700 | 9151.6 | 10657.91 | 1506.31 | 16.46% | 1 | 100% | 135 | 197.55 | 62.55 | 46.33%
26-PC-38025 | Granite Pass Section 106 Consultation | Time and material | In Progress | Prairie | Sherry Lloyd | 92200 | 64982.56 | 8252.27 | 245.07 | 0.3771% | 0 | 12.32% | 1167 | 149.5 | 5.25 | 0.4499%
26-PC-38124 | Lantern Bay Architectural History Survey | Fixed fee | Final Billing/Invoice | Prairie | Sherry Lloyd | 48700 | 38380.47 | 44857.7 | 6477.23 | 16.88% | 1 | 100% | 650 | 817.4 | 167.4 | 25.75%
26-PC-38153 | Harbor View Reservoir Environmental Review Support | Fixed fee | In Progress | Prairie | Sherry Lloyd | 109100 | 89766.43 | 50619.27 | 2340.67 | 2.608% | 0 | 53.78% | 0 | 1031.25 | 10.25 | 0%
26-PC-38215 | Phase I: Juniper Wash Cell Tower Historic Resources Evaluation | Fixed fee | In Progress | Prairie | Sherry Lloyd | 42800 | 37664 | 13083.3 | 506.11 | 1.344% | 0 | 33.39% | 1259 | 268.25 | 11.5 | 0.9134%
26-PC-38264 | On-Call: Coyote Springs Battery Storage Phase II Testing | Fixed fee | Final Reporting/Review | Prairie | Sherry Lloyd | 25500 | 17926.43 | 8296.03 | 629.38 | 3.511% | 0 | 42.77% | 281 | 160 | 21.75 | 7.74%
26-PC-38304 | Yarrow Point Cultural Resources Assessment | Time and material | In Progress | Prairie | Sherry Lloyd | 177100 | 125191.99 | 0 | 0 | 0% | 0 | 0% | 2349 | 0 | 0 | 0%
26-PC-38315 | Task Order 21: Larkspur Bridge Replacement Paleontological Monitoring | Fixed fee | Final Reporting/Review | Prairie | Sherry Lloyd | 735000 | 578298 | 32709.71 | 708.11 | 0.1224% | 0 | 5.534% | 8557 | 614 | 15.25 | 0.1782%
26-PC-38367 | Stone Mill Architectural History Survey | Time and material | In Progress | Prairie | Sherry Lloyd | 416500 | 276097.85 | 80601.23 | 1075.39 | 0.3895% | 0 | 28.8% | 5434 | 1354.5 | 24.5 | 0.4509%
26-PC-38379 | Sandpiper Levee Repair Historic Resources Evaluation | Time and material | On Hold | Prairie | Sherry Lloyd | 230500 | 167898.45 | 0 | 0 | 0% | 0 | 0% | 1663 | 0 | 0 | 0%
26-PC-38387 | Granite Pass Section 106 Consultation | Time and material | In Progress | Prairie | Sherry Lloyd | 182500 | 120358.75 | 52528.86 | 7411.52 | 6.158% | 1 | 37.49% | 1643 | 751.75 | 68.5 | 4.169%
26-PC-38390 | Redbud Curation | Fixed fee | Final Reporting/Review | Prairie | Sherry Lloyd | 85100 | 53630.02 | 1324.09 | 309.53 | 0.5772% | 0 | 1.892% | 1239 | 30.5 | 7.75 | 0.6255%
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | Time and material | In Progress | Prairie | Sherry Lloyd | 48300 | 32887.47 | 24978.26 | 0 | 0% | 0 | 75.95% | 395 | 440.75 | 45.75 | 11.58%
26-PC-38431 | Silver Lake Levee Repair - Archaeological Testing | Fixed fee | Final Billing/Invoice | Prairie | Sherry Lloyd | 254800 | 143528.84 | 186587.49 | 43058.65 | 30% | 1 | 100% | 1754 | 3106.89 | 1352.89 | 77.13%
26-PC-38438 | Slate Ridge Fiber Route Phase I Survey | Fixed fee | In Progress | Prairie | Sherry Lloyd | 41000 | 32762.53 | 0 | 0 | 0% | 0 | 0% | 388 | 0 | 0 | 0%
26-PC-38459 | Task Order 21: Sea Oat Highway Widening Cultural Resources Assessment | Fixed fee | Completed | Red Rock | Javier Newman | 96700 | 76702.44 | 59483.59 | 0 | 0% | 0 | 77.55% | 0 | 1113.49 | 0 | 0%
26-PC-38532 | Tansy Flat Wind Farm - Paleontological Monitoring | Fixed fee | On Hold | Red Rock | Marisa Odom | 46400 | 33663.2 | 0 | 0 | 0% | 0 | 0% | 552 | 0 | 0 | 0%
26-PC-38546 | Sparrow Hill Reservoir Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | Red Rock | Jeanette Chung | 103300 | 55430.78 | 59395.16 | 3964.38 | 7.152% | 1 | 100% | 0 | 1024.09 | 0 | 0%
26-PC-38550 | On-Call: Sage Flat School Campus Class III Survey | Fixed fee | Completed | Red Rock | Jeanette Chung | 385200 | 289636.74 | 262282.42 | 0 | 0% | 0 | 90.56% | 4183 | 4932.88 | 797.77 | 19.07%
26-PC-38571 | Stone Mill Transmission Line GIS Mapping | Fixed fee | Completed | Red Rock | Jeanette Chung | 593600 | 431665.92 | 350808.39 | 0 | 0% | 0 | 81.27% | 6438 | 5468.37 | 0 | 0%
26-PC-38573 | Cedar Hollow School Campus - Class III Survey | Fixed fee | In Progress | Red Rock | Marisa Odom | 100100 | 74784.71 | 833.24 | 15.69 | 0.02098% | 0 | 1.093% | 706 | 10.25 | 0.25 | 0.03541%
26-PC-38624 | Juniper Wash Built Environment Survey | Fixed fee | Cost Tracking on Closed Project | Red Rock | Bruce Suarez | 77900 | 56578.77 | 73552.4 | 16973.63 | 30% | 1 | 100% | 963 | 1311.5 | 348.5 | 36.19%
26-PC-38647 | Meadowlark Cultural Resources Assessment | Time and material | In Progress | Red Rock | Bruce Suarez | 793800 | 517795.74 | 177498.27 | 3923.39 | 0.7577% | 0 | 33.52% | 0 | 2937 | 69.25 | 0%
26-PC-38675 | On-Call: Lone Pine School Campus Data Recovery | Fixed fee | Final Reporting/Review | Red Rock | Jeanette Chung | 289700 | 228167.72 | 66526.13 | 571.18 | 0.2503% | 0 | 28.91% | 3409 | 1157.75 | 12 | 0.352%
26-PC-38691 | Elk Meadow Phase I Survey | Time and material | On Hold | Red Rock | Tina Aguirre | 1927200 | 1370431.92 | 0 | 0 | 0% | 0 | 0% | 32342 | 0 | 0 | 0%
26-PC-38709 | Timber Gap Airport Apron Phase I Survey | Fixed fee | In Progress | Red Rock | Bruce Suarez | 14100 | 11415.36 | 5537.78 | 271.82 | 2.381% | 0 | 46.13% | 243 | 108.5 | 7.75 | 3.189%
26-PC-38719 | Willow Springs Housing Development - Environmental Review Support | Fixed fee | In Progress | Red Rock | Javier Newman | 298600 | 193522.66 | 1014.85 | 0 | 0% | 0 | 0.5244% | 2806 | 14.5 | 0 | 0%
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | Time and material | In Progress | Red Rock | Tina Aguirre | 97700 | 60828.02 | 76641.92 | 30124.08 | 49.52% | 1 | 76.47% | 0 | 1607.25 | 85.5 | 0%
26-PC-38769 | On-Call: Elk Meadow Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | Red Rock | Marisa Odom | 40500 | 25733.7 | 21634.41 | 0 | 0% | 0 | 84.07% | 463 | 313.29 | 0 | 0%
26-PC-38844 | Juniper Wash Cell Tower Phase II Testing | Fixed fee | Final Billing/Invoice | Red Rock | Jeanette Chung | 319700 | 236322.24 | 307218.91 | 70896.67 | 30% | 1 | 100% | 3530 | 5102.86 | 1572.86 | 44.56%
26-PC-38856 | Task Order 6: Maple Fork Trail Section 106 Consultation | Fixed fee | Completed | Red Rock | Tina Aguirre | 137600 | 94200.96 | 122461.25 | 28260.29 | 30% | 1 | 100% | 1493 | 2160.15 | 667.15 | 44.69%
26-PC-38880 | Wildrye Trail - Archaeological Testing | Fixed fee | Completed | Red Rock | Lydia Cisneros | 141200 | 118636.24 | 92164.2 | 0 | 0% | 0 | 77.69% | 1615 | 1735.76 | 182.88 | 11.32%
26-PC-38898 | Redbud Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | Red Rock | Bruce Suarez | 150100 | 87478.28 | 21117.75 | 462.96 | 0.5292% | 0 | 23.61% | 1519 | 432.5 | 10 | 0.6583%
26-PC-38916 | Sparrow Hill Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | Red Rock | Tina Aguirre | 54500 | 42150.3 | 54795.39 | 12645.09 | 30% | 1 | 100% | 632 | 958.2 | 326.2 | 51.61%
26-PC-38924 | Wildrye Harbor Dredging - Architectural History Survey | Time and material | In Progress | Red Rock | Shelia Horne | 117200 | 83798 | 43360.22 | 4283.43 | 5.112% | 1 | 46.63% | 1279 | 800.5 | 97 | 7.584%
26-PC-38943 | Task Order 34: Fern Valley Wastewater Plant Archaeological Testing | Fixed fee | In Progress | Red Rock | Marisa Odom | 129100 | 80272.12 | 68583.91 | 11932.65 | 14.87% | 1 | 70.57% | 1494 | 1263 | 223.5 | 14.96%
26-PC-38966 | Task Order 12: Bramble Creek Battery Storage Cultural Resources Monitoring | Fixed fee | In Progress | Red Rock | Bruce Suarez | 269400 | 193052.04 | 8599.9 | 0 | 0% | 0 | 4.455% | 2573 | 184 | 0 | 0%
26-PC-38993 | Willow Springs Airport Apron - Section 106 Consultation | Time and material | In Progress | Red Rock | Lydia Cisneros | 201400 | 131514.2 | 37610.38 | 1101.25 | 0.8374% | 0 | 27.76% | 1544 | 505 | 16.25 | 1.052%
26-PC-39024 | On-Call: Goldfinch Water Main Phase I Survey | Time and material | In Progress | Red Rock | Marisa Odom | 211800 | 149416.47 | 5901.63 | 783.44 | 0.5243% | 0 | 3.425% | 1801 | 77 | 11 | 0.6108%
26-PC-39043 | Twin Buttes Reservoir - Archaeological Testing | Fixed fee | In Progress | Red Rock | Bruce Suarez | 123200 | 96884.48 | 15516.2 | 736.17 | 0.7598% | 0 | 15.26% | 2025 | 325.75 | 17 | 0.8395%
26-PC-39051 | Quail Run Fiber Route - Section 106 Consultation | Fixed fee | Final Billing/Invoice | Red Rock | Lydia Cisneros | 510900 | 377963.82 | 284190.67 | 0 | 0% | 0 | 75.19% | 5195 | 5362.68 | 201.54 | 3.879%
26-PC-39143 | Meadowlark Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | In Progress | Red Rock | Bruce Suarez | 500400 | 366543 | 3965.11 | 129.16 | 0.03524% | 0 | 1.047% | 3404 | 51.75 | 2 | 0.05875%
26-PC-39165 | Pebble Beach Road Phase I Survey | Fixed fee | Final Reporting/Review | Red Rock | Tina Aguirre | 94300 | 63218.72 | 58643.27 | 15574.23 | 24.64% | 1 | 68.13% | 395 | 514 | 192.5 | 48.73%
26-PC-39230 | Maple Fork Cultural Resources Assessment | Time and material | In Progress | Red Rock | Bruce Suarez | 575400 | 432643.26 | 40379.78 | 513.92 | 0.1188% | 0 | 9.214% | 3831 | 709.25 | 11 | 0.2871%
26-PC-39232 | Plover Cove Canal Lining Archaeological Testing | Fixed fee | Final Billing/Invoice | Red Rock | Tina Aguirre | 11000 | 8129 | 10389.8 | 2260.8 | 27.81% | 1 | 100% | 120 | 191.06 | 71.06 | 59.22%
26-PC-39249 | On-Call: Millbrook Levee Repair Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | Red Rock | Tina Aguirre | 126200 | 95785.8 | 0 | 0 | 0% | 0 | 0% | 925 | 0 | 0 | 0%
26-PC-39264 | Hackberry Bend Housing Development - Architectural History Survey | Fixed fee | Final Billing/Invoice | Red Rock | Bruce Suarez | 37100 | 30010.19 | 29858.41 | 0 | 0% | 0 | 99.49% | 312 | 478.53 | 166.53 | 53.38%
26-PC-39277 | Larkspur Battery Storage Archaeological Testing | Fixed fee | Final Reporting/Review | Red Rock | Bruce Suarez | 520900 | 341710.4 | 124.3 | 0 | 0% | 0 | 0.03638% | 6464 | 1.75 | 0 | 0%
26-PC-39303 | Maple Fork Wind Farm Historic Resources Evaluation | Fixed fee | Transferred Entity | Red Rock | Javier Newman | 41200 | 35687.44 | 8218.46 | 0 | 0% | 0 | 23.03% | 496 | 111 | 0 | 0%
26-PC-39335 | Windmill Flat Phase II Testing | Time and material | Completed | Red Rock | Javier Newman | 78700 | 52791.96 | 47697.57 | 0 | 0% | 0 | 90.35% | 722 | 872.93 | 150.93 | 20.9%
26-PC-39372 | Tamarack Environmental Review Support | Time and material | Lab/Curation | Red Rock | Shelia Horne | 12300 | 7953.18 | 14.5 | 0 | 0% | 0 | 0.1823% | 87 | 0.25 | 0 | 0%
26-PC-39390 | Juniper Wash Fiber Route Phase I Survey | Fixed fee | Final Reporting/Review | Red Rock | Javier Newman | 59600 | 37810.24 | 5396.13 | 199.31 | 0.5271% | 0 | 13.74% | 530 | 82.25 | 3.5 | 0.6604%
26-PC-39408 | Meadowlark Class III Survey | Fixed fee | Final Billing/Invoice | Red Rock | Javier Newman | 103000 | 73854.05 | 71114.94 | 0 | 0% | 0 | 96.29% | 1263 | 1089.23 | 6.54 | 0.5178%
26-PC-39446 | On-Call: Tamarack Bridge Replacement Architectural History Survey | Fixed fee | Transferred Entity | Red Rock | Jeanette Chung | 131200 | 102152.32 | 28568.4 | 2132.08 | 2.087% | 0 | 25.88% | 0 | 433 | 47 | 0%
26-PC-39534 | Aspen Ridge Park Improvements Maritime Remote Sensing Survey | Fixed fee | On Hold | Red Rock | Marisa Odom | 551900 | 348248.9 | 0 | 0 | 0% | 0 | 0% | 5966 | 0 | 0 | 0%
26-PC-39537 | Badger Hollow Cultural Resources Monitoring | Fixed fee | In Progress | Red Rock | Tina Aguirre | 82700 | 63951.91 | 5327.48 | 45.34 | 0.0709% | 0 | 8.26% | 868 | 112.75 | 0.75 | 0.08641%
26-PC-39565 | On-Call: Aspen Ridge Battery Storage Maritime Remote Sensing Survey | Time and material | In Progress | Red Rock | Lydia Cisneros | 97600 | 60541.28 | 19109.39 | 318.52 | 0.5261% | 0 | 31.04% | 904 | 390 | 12.25 | 1.355%
26-PC-39587 | Ember Valley Curation | Time and material | Cost Tracking on Closed Project | Red Rock | Javier Newman | 288900 | 211965.93 | 213449.22 | 1483.29 | 0.6998% | 0 | 100% | 2895 | 3415.61 | 520.61 | 17.98%
26-PC-39595 | Plover Cove Archaeological Testing | Fixed fee | Completed | Red Rock | Javier Newman | 66700 | 48564.27 | 44495.7 | 0 | 0% | 0 | 91.62% | 930 | 751.13 | 0 | 0%
26-PC-39619 | Hackberry Bend Transmission Line - Paleontological Monitoring | Fixed fee | In Progress | Red Rock | Lydia Cisneros | 79000 | 54115 | 1801.57 | 0 | 0% | 0 | 3.329% | 521 | 32 | 0 | 0%
26-PC-39638 | On-Call: North Fork Transmission Line Historic Resources Evaluation | Time and material | In Progress | Red Rock | Shelia Horne | 131700 | 85748.9 | 23512.46 | 554.19 | 0.6463% | 0 | 26.77% | 763 | 311.75 | 10.75 | 1.409%
26-PC-39644 | Ember Valley Reservoir - Section 106 Consultation | Time and material | Completed | Red Rock | Lydia Cisneros | 100300 | 69527.96 | 65771.97 | 0 | 0% | 0 | 94.6% | 1221 | 1322.86 | 101.86 | 8.342%
26-PC-39671 | Phase I: Pebble Beach Road Solar Class III Survey | Fixed fee | Completed | Red Rock | Tina Aguirre | 62500 | 46625 | 60612.5 | 13987.5 | 30% | 1 | 100% | 0 | 1064.29 | 0 | 0%
26-PC-39699 | Thistle Down Reservoir - Data Recovery | Fixed fee | In Progress | Red Rock | Jeanette Chung | 88200 | 62269.2 | 7012.08 | 587.24 | 0.9431% | 0 | 10.32% | 1628 | 141.75 | 14.25 | 0.8753%
26-PC-39711 | Sandpiper Canal Lining Phase II Testing | Fixed fee | Completed | Red Rock | Tina Aguirre | 69600 | 59125.2 | 67147.15 | 8021.95 | 13.57% | 1 | 100% | 1264 | 1096.97 | 0 | 0%
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Fixed fee | Cost Tracking on Closed Project | Red Rock | Tina Aguirre | 115900 | 86530.94 | 99694.97 | 13164.03 | 15.21% | 1 | 100% | 1149 | 1444.99 | 295.99 | 25.76%
26-PC-39730 | Coyote Springs Water Main - Phase I Survey | Fixed fee | Completed | Red Rock | Javier Newman | 25600 | 18618.88 | 17603.57 | 0 | 0% | 0 | 94.55% | 355 | 309.87 | 0 | 0%
26-PC-39744 | Phase III: Sumac Ridge Wastewater Plant Archaeological Testing | Time and material | In Progress | Red Rock | Bruce Suarez | 351100 | 225441.31 | 14063.63 | 100.62 | 0.04463% | 0 | 6.194% | 4331 | 298.75 | 2.25 | 0.05195%
26-PC-39778 | Thistle Down Battery Storage - Architectural History Survey | Time and material | In Progress | Red Rock | Marisa Odom | 35700 | 26613.7 | 1536.43 | 0 | 0% | 0 | 5.773% | 515 | 27.5 | 0 | 0%
26-PC-39780 | Phase I: Rushgrass Draw Mine Expansion Maritime Remote Sensing Survey | Time and material | In Progress | Red Rock | Shelia Horne | 113500 | 76714.65 | 5533.85 | 0 | 0% | 0 | 7.214% | 1009 | 116.25 | 0 | 0%
26-PC-39880 | Larkspur Section 106 Consultation | Time and material | In Progress | Red Rock | Jeanette Chung | 100200 | 73772.32 | 27101.22 | 1557.02 | 2.111% | 0 | 34.63% | 0 | 443.25 | 32.75 | 0%
26-PC-39913 | On-Call: Bramble Creek Rail Siding Cultural Resources Assessment | Fixed fee | On Hold | Red Rock | Javier Newman | 119400 | 78314.46 | 0 | 0 | 0% | 0 | 0% | 1224 | 0 | 0 | 0%
26-PC-39971 | Pebble Beach Road Environmental Review Support | Time and material | Final Reporting/Review | Red Rock | Marisa Odom | 114600 | 79406.34 | 65079.99 | 7962.42 | 10.03% | 1 | 71.93% | 780 | 1120.75 | 497.75 | 63.81%
26-PC-39990 | Falcon Mesa Solar - Phase I Survey | Time and material | In Progress | Red Rock | Tina Aguirre | 15600 | 10693.8 | 417.68 | 0 | 0% | 0 | 3.906% | 246 | 7.5 | 0 | 0%
26-PC-40009 | Oak Terrace Harbor Dredging Curation | Fixed fee | In Progress | Red Rock | Shelia Horne | 63600 | 43349.76 | 15804.89 | 276.34 | 0.6375% | 0 | 35.82% | 663 | 329.5 | 33 | 4.977%
26-PC-40038 | Badger Hollow Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Red Rock | Lydia Cisneros | 348700 | 275403.26 | 257330.22 | 0 | 0% | 0 | 93.44% | 0 | 4275.52 | 0 | 0%
26-PC-40055 | Twin Buttes Pipeline Architectural History Survey | Time and material | In Progress | Red Rock | Shelia Horne | 22000 | 14259.29 | 4910.87 | 0 | 0% | 0 | 34.44% | 219 | 79.25 | 0 | 0%
26-PC-40092 | Eagle Bend Environmental Review Support | Fixed fee | In Progress | Sierra | Angelica Poole | 3672000 | 2369908.8 | 9935.54 | 0 | 0% | 0 | 0.4192% | 48889 | 241.75 | 0 | 0%
26-PC-40108 | Hackberry Bend Trail - Phase II Testing | Fixed fee | Final Billing/Invoice | Sierra | Benjamin Mathis | 138800 | 89484.36 | 90632.27 | 1147.91 | 1.283% | 0 | 100% | 912 | 1492.31 | 580.31 | 63.63%
26-PC-40128 | Goldfinch Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | Sierra | Donna Herring | 67100 | 49016.55 | 50052.19 | 1035.64 | 2.113% | 0 | 100% | 494 | 806.94 | 312.94 | 63.35%
26-PC-40176 | On-Call: Twin Buttes Harbor Dredging Phase I Survey | Time and material | Final Reporting/Review | Sierra | Louis Huff | 143600 | 93138.96 | 23412.98 | 87.89 | 0.09436% | 0 | 25.04% | 1672 | 555.75 | 2.25 | 0.1346%
26-PC-40190 | Pebble Beach Road Trail - Section 106 Consultation | Fixed fee | On Hold | Sierra | Benjamin Mathis | 113900 | 91485.25 | 0 | 0 | 0% | 0 | 0% | 1167 | 0 | 0 | 0%
26-PC-40229 | Pine Hollow School Campus - Data Recovery | Time and material | Final Billing/Invoice | Sierra | Angelica Poole | 370800 | 229525.2 | 298382.76 | 68857.56 | 30% | 1 | 100% | 4070 | 4854.42 | 784.42 | 19.27%
26-PC-40289 | Windmill Flat Park Improvements Environmental Review Support | Fixed fee | Final Billing/Invoice | Sierra | Angelica Poole | 135800 | 109481.96 | 102903.26 | 0 | 0% | 0 | 93.99% | 0 | 1939.95 | 0 | 0%
26-PC-40296 | Twin Buttes Class III Survey | Fixed fee | In Progress | Sierra | Donna Herring | 6400 | 4648.32 | 790.8 | 39.08 | 0.8407% | 0 | 16.17% | 28 | 8.5 | 0.5 | 1.786%
26-PC-40304 | Willow Springs Fiber Route Archaeological Testing | Fixed fee | In Progress | Sierra | Donna Herring | 132900 | 101283.22 | 13790.75 | 0 | 0% | 0 | 13.62% | 2649 | 285.5 | 0 | 0%
26-PC-40329 | Yarrow Point Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | Sierra | Donna Herring | 416100 | 281325.21 | 365722.77 | 84397.56 | 30% | 1 | 100% | 2652 | 4984.24 | 2332.24 | 87.94%
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | Fixed fee | In Progress | Sierra | Donna Herring | 96900 | 68401.71 | 75128.43 | 13256.11 | 19.38% | 1 | 90.45% | 731 | 1262.75 | 531.75 | 72.74%
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Fixed fee | Final Reporting/Review | Sierra | Louis Huff | 19200 | 14098.56 | 18399.82 | 4301.26 | 30.51% | 1 | 100% | 0 | 275 | 17 | 0%
26-PC-40361 | Sea Oat Cultural Resources Assessment | Fixed fee | In Progress | Sierra | Donna Herring | 156300 | 102829.77 | 77565.5 | 9907.58 | 9.635% | 1 | 65.8% | 950 | 1052.75 | 267.5 | 28.16%
26-PC-40384 | Maple Fork Solar - Maritime Remote Sensing Survey | Time and material | In Progress | Sierra | Donna Herring | 102900 | 62220.33 | 30693.53 | 395.13 | 0.635% | 0 | 48.7% | 986 | 663 | 36.25 | 3.676%
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Fixed fee | Final Reporting/Review | Sierra | Donna Herring | 5900 | 4379.73 | 8489.9 | 4110.17 | 93.85% | 1 | 100% | 70 | 161 | 91 | 130%
26-PC-40443 | Pine Hollow Wastewater Plant - Built Environment Survey | Fixed fee | In Progress | Sierra | Donna Herring | 424500 | 299781.9 | 46117.81 | 531.76 | 0.1774% | 0 | 15.21% | 3895 | 660.25 | 6.5 | 0.1669%
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | Fixed fee | In Progress | Sierra | Donna Herring | 7500 | 5493 | 8125.75 | 2950.43 | 53.71% | 1 | 94.22% | 70 | 161.75 | 91.75 | 131.1%
26-PC-40590 | Wildrye Highway Widening - Environmental Review Support | Fixed fee | Final Reporting/Review | Sierra | Angelica Poole | 1002000 | 809716.2 | 123942.05 | 1776.79 | 0.2194% | 0 | 15.09% | 9548 | 2246.75 | 38.75 | 0.4058%
26-PC-40605 | Willow Springs Mixed-Use Development Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | Sierra | Louis Huff | 138400 | 95191.52 | 81646.35 | 0 | 0% | 0 | 85.77% | 1053 | 1379.89 | 326.89 | 31.04%
26-PC-40607 | Task Order 35: Cedar Hollow Housing Development Archaeological Testing | Fixed fee | On Hold | Sierra | Benjamin Mathis | 75100 | 47821.37 | 0 | 0 | 0% | 0 | 0% | 738 | 0 | 0 | 0%
26-PC-40640 | Cedar Hollow Mine Expansion Cultural Resources Monitoring | Time and material | Final Billing/Invoice | Sierra | Angelica Poole | 12900 | 9127.87 | 8897.34 | 0 | 0% | 0 | 97.47% | 117 | 154.69 | 37.69 | 32.21%
26-PC-40690 | Pine Hollow Wastewater Plant - Paleontological Monitoring | Time and material | In Progress | Coastal Bend | Duane Ballard | 252500 | 171094 | 65638.2 | 1070.45 | 0.6257% | 0 | 37.74% | 2923 | 1101 | 22.5 | 0.7698%
26-PC-40716 | Elk Meadow Architectural History Survey | Time and material | Final Billing/Invoice | Coastal Bend | Alexis Nixon | 6700 | 4710.77 | 5030.17 | 319.4 | 6.78% | 1 | 100% | 71 | 79.98 | 8.98 | 12.65%
26-PC-40729 | On-Call: Dove Canyon Cell Tower Section 106 Consultation | Fixed fee | In Progress | Coastal Bend | Alexis Nixon | 92500 | 58081.13 | 4896.27 | 0 | 0% | 0 | 8.43% | 0 | 79.25 | 0 | 0%
26-PC-40750 | On-Call: Willow Springs Highway Widening Historic Resources Evaluation | Time and material | In Progress | Coastal Bend | Steve Rubio | 494600 | 310521.94 | 17521.7 | 675.19 | 0.2174% | 0 | 5.425% | 7260 | 339 | 16.25 | 0.2238%
26-PC-40760 | Foxglove Canal Lining - Archaeological Testing | Fixed fee | Final Reporting/Review | Coastal Bend | Jared Choi | 77500 | 63893.46 | 18190.85 | 183.34 | 0.2869% | 0 | 28.18% | 0 | 332.5 | 3.75 | 0%
26-PC-40805 | Willow Springs Battery Storage - Section 106 Consultation | Time and material | Completed | Coastal Bend | Jared Choi | 15100 | 11494.12 | 13051.04 | 1556.92 | 13.55% | 1 | 100% | 183 | 205.32 | 22.32 | 12.2%
26-PC-40860 | Fern Valley Solar Data Recovery | Fixed fee | In Progress | Coastal Bend | Steve Rubio | 181300 | 145148.78 | 33204.33 | 618.85 | 0.4264% | 0 | 22.45% | 0 | 686.5 | 15.25 | 0%
26-PC-40902 | Badger Hollow Solar Environmental Review Support | Fixed fee | Final Billing/Invoice | Coastal Bend | Jared Choi | 86700 | 65666.58 | 63897.65 | 0 | 0% | 0 | 97.31% | 1042 | 1037.61 | 19.18 | 1.841%
26-PC-40966 | Harbor View Trail - GIS Mapping | Fixed fee | Final Reporting/Review | Coastal Bend | Duane Ballard | 225100 | 146315 | 34610.68 | 1054.58 | 0.7208% | 0 | 22.93% | 2386 | 703 | 23 | 0.964%
26-PC-40983 | Falcon Mesa Data Recovery | Fixed fee | Final Reporting/Review | Coastal Bend | Jared Choi | 7200 | 6217.91 | 4852.67 | 33.98 | 0.5465% | 0 | 77.5% | 42 | 71.75 | 29.75 | 70.83%
26-PC-41005 | Juniper Wash Architectural History Survey | Time and material | In Progress | Coastal Bend | Duane Ballard | 60000 | 38934 | 2404.39 | 75.92 | 0.195% | 0 | 5.981% | 665 | 47.5 | 1.75 | 0.2632%
26-PC-41046 | Wren Hollow Airport Apron - Data Recovery | Fixed fee | Final Billing/Invoice | Coastal Bend | Duane Ballard | 60200 | 47644.16 | 58991.23 | 11347.07 | 23.82% | 1 | 100% | 772 | 1059.02 | 287.02 | 37.18%
26-PC-41048 | Task Order 33: Granite Pass Battery Storage Phase I Survey | Time and material | In Progress | Coastal Bend | Jared Choi | 458200 | 315149.96 | 88143.15 | 2072.26 | 0.6575% | 0 | 27.31% | 3299 | 1414.75 | 48.25 | 1.463%
26-PC-41130 | Harbor View Highway Widening Data Recovery | Time and material | Cost Tracking on Closed Project | Coastal Bend | Steve Rubio | 290300 | 219699.04 | 201136.18 | 0 | 0% | 0 | 91.55% | 3721 | 3896.75 | 175.75 | 4.723%
26-PC-41176 | Wildrye Park Improvements - Environmental Review Support | Fixed fee | Final Reporting/Review | Coastal Bend | Steve Rubio | 109400 | 81568.64 | 30126.95 | 377.58 | 0.4629% | 0 | 36.47% | 0 | 482.25 | 5.75 | 0%
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | Fixed fee | In Progress | Coastal Bend | Jared Choi | 41400 | 27278.33 | 30232.83 | 2954.5 | 10.83% | 1 | 100% | 392 | 490 | 98 | 25%
26-PC-41222 | Sage Flat Transmission Line - Cultural Resources Assessment | Time and material | In Progress | Coastal Bend | Alexis Nixon | 26000 | 18522.4 | 3158.62 | 0 | 0% | 0 | 17.05% | 433 | 65 | 0 | 0%
26-PC-41229 | Windmill Flat Phase I Survey | Fixed fee | On Hold | Coastal Bend | Jared Choi | 214000 | 143615.4 | 0 | 0 | 0% | 0 | 0% | 1071 | 0 | 0 | 0%
26-PC-41230 | Phase I: Slate Ridge Battery Storage Phase I Survey | Fixed fee | In Progress | Coastal Bend | Alexis Nixon | 46400 | 35769.76 | 12661.46 | 58.41 | 0.1633% | 0 | 35.23% | 684 | 227 | 1.25 | 0.1827%
26-PC-41302 | Thistle Down Pipeline Architectural History Survey | Time and material | Completed | Coastal Bend | Duane Ballard | 20300 | 13056.96 | 13598.19 | 541.23 | 4.145% | 0 | 100% | 147 | 257.75 | 110.75 | 75.34%
26-PC-41334 | Fern Valley Housing Development - Data Recovery | Fixed fee | In Progress | Coastal Bend | Duane Ballard | 154000 | 99198.32 | 68260.63 | 4185.98 | 4.22% | 0 | 64.59% | 1559 | 1465.25 | 157.75 | 10.12%
26-PC-41386 | Task Order 11: Slate Ridge Harbor Dredging Class III Survey | Fixed fee | In Progress | Coastal Bend | Alexis Nixon | 302700 | 209680.29 | 7795.4 | 0 | 0% | 0 | 3.718% | 3122 | 147.75 | 0 | 0%
26-PC-41394 | Maple Fork Bridge Replacement - Class III Survey | Fixed fee | Cost Tracking on Closed Project | Coastal Bend | Duane Ballard | 15700 | 11219.22 | 10008.86 | 0 | 0% | 0 | 89.21% | 0 | 139.58 | 0 | 0%
26-PC-41406 | Task Order 27: Dove Canyon Battery Storage Section 106 Consultation | Fixed fee | In Progress | Coastal Bend | Alexis Nixon | 381600 | 257192.06 | 104836.49 | 1102.55 | 0.4287% | 0 | 40.33% | 4207 | 1890.75 | 24.75 | 0.5883%
26-PC-41425 | Pebble Beach Road GIS Mapping | Time and material | Transferred Entity | Coastal Bend | Steve Rubio | 268700 | 183253.4 | 63737.62 | 543.34 | 0.2965% | 0 | 34.48% | 1669 | 860.75 | 8.25 | 0.4943%
26-PC-41446 | Stone Mill Levee Repair Archaeological Testing | Time and material | In Progress | Coastal Bend | Jared Choi | 263000 | 172291.3 | 0 | 0 | 0% | 0 | 0% | 2444 | 0 | 0 | 0%
26-PC-41453 | Pebble Beach Road Cell Tower Environmental Review Support | Fixed fee | On Hold | Coastal Bend | Alexis Nixon | 28100 | 22286.11 | 0 | 0 | 0% | 0 | 0% | 206 | 0 | 0 | 0%
26-PC-41466 | Millbrook Cultural Resources Assessment | Time and material | Lab/Curation | Coastal Bend | Alexis Nixon | 857800 | 634085.76 | 178651.18 | 3482.57 | 0.5492% | 0 | 27.63% | 9294 | 2529.75 | 59.25 | 0.6375%
26-PC-41575 | Juniper Wash Highway Widening - Section 106 Consultation | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 131400 | 100941.48 | 10453.11 | 216.9 | 0.2149% | 0 | 10.14% | 1959 | 224.75 | 5 | 0.2552%
26-PC-41578 | Task Order 2: Pebble Beach Road Transmission Line Paleontological Monitoring | Time and material | On Hold | Coastal Bend | Diane Daniels | 340900 | 240285.42 | 0 | 0 | 0% | 0 | 0% | 3943 | 0 | 0 | 0%
26-PC-41623 | Eagle Bend Bridge Replacement - GIS Mapping | Time and material | On Hold | Coastal Bend | Duane Ballard | 113100 | 79124.76 | 0 | 0 | 0% | 0 | 0% | 1155 | 0 | 0 | 0%
26-PC-41644 | Granite Pass Built Environment Survey | Fixed fee | Transferred Entity | Coastal Bend | Alexis Nixon | 330600 | 258297.78 | 51878.28 | 2320.01 | 0.8982% | 0 | 19.19% | 5318 | 837 | 32.75 | 0.6158%
26-PC-41661 | Ember Valley Levee Repair Data Recovery | Fixed fee | In Progress | Coastal Bend | Diane Daniels | 4800 | 4028.16 | 4393.64 | 1638.6 | 40.68% | 1 | 68.39% | 49 | 57 | 21.5 | 43.88%
26-PC-41663 | On-Call: Plover Cove Highway Widening Cultural Resources Assessment | Time and material | On Hold | Coastal Bend | Duane Ballard | 510700 | 337572.7 | 0 | 0 | 0% | 0 | 0% | 5227 | 0 | 0 | 0%
26-PC-41667 | Kestrel Butte Transmission Line - Historic Resources Evaluation | Time and material | In Progress | Coastal Bend | Duane Ballard | 131800 | 98659.54 | 81942.28 | 18383.06 | 18.63% | 1 | 64.42% | 921 | 1272.25 | 433.5 | 47.07%
26-PC-41671 | Phase I: Slate Ridge Solar Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Coastal Bend | Diane Daniels | 256200 | 182542.5 | 237305.25 | 54762.75 | 30% | 1 | 100% | 2945 | 4191.94 | 1246.94 | 42.34%
26-PC-41683 | On-Call: Slate Ridge Levee Repair Built Environment Survey | Fixed fee | In Progress | Built Environment | Jesse Maynard | 250100 | 169042.59 | 4642.34 | 0 | 0% | 0 | 2.746% | 3721 | 82 | 0 | 0%
26-PC-41707 | Quail Run Solar Environmental Review Support | Fixed fee | Final Reporting/Review | Built Environment | Jenny Wilkinson | 27000 | 20358 | 5252.6 | 0 | 0% | 0 | 25.8% | 160 | 58.75 | 0 | 0%
26-PC-41721 | Thistle Down Curation | Time and material | In Progress | Built Environment | Melody Holloway | 67700 | 46692.69 | 23748.7 | 1065.39 | 2.282% | 0 | 48.58% | 670 | 323 | 14.25 | 2.127%
26-PC-41739 | Slate Ridge Historic Resources Evaluation | Fixed fee | In Progress | Built Environment | Melody Holloway | 240100 | 163268 | 18858.88 | 362.15 | 0.2218% | 0 | 11.33% | 1802 | 258.5 | 6.75 | 0.3746%
26-PC-41750 | Task Order 6: Copper Flats Wind Farm Maritime Remote Sensing Survey | Fixed fee | On Hold | Built Environment | Kathleen Cabrera | 825200 | 659196.16 | 0 | 0 | 0% | 0 | 0% | 7892 | 0 | 0 | 0%
26-PC-41776 | Sandpiper Battery Storage GIS Mapping | Time and material | Lab/Curation | Built Environment | Jenny Wilkinson | 457800 | 310067.94 | 25479.07 | 700.26 | 0.2258% | 0 | 7.991% | 4150 | 426.5 | 13.75 | 0.3313%
26-PC-41803 | Copper Flats Section 106 Consultation | Fixed fee | Lab/Curation | Built Environment | Jenny Wilkinson | 554800 | 392021.68 | 47452.97 | 534.2 | 0.1363% | 0 | 11.97% | 7918 | 690.25 | 11.25 | 0.1421%
26-PC-41821 | Blue Heron School Campus Curation | Time and material | In Progress | Built Environment | Jenny Wilkinson | 152400 | 98770.44 | 25864.78 | 161.69 | 0.1637% | 0 | 26.02% | 1738 | 389.25 | 2.25 | 0.1295%
26-PC-41863 | Silver Lake Canal Lining Cultural Resources Assessment | Fixed fee | In Progress | Built Environment | Jenny Wilkinson | 322500 | 224460 | 6449.34 | 76.2 | 0.03395% | 0 | 2.839% | 0 | 52.75 | 0.75 | 0%
26-PC-41865 | Phase II: Copper Flats Reservoir Class III Survey | Time and material | In Progress | Built Environment | Jenny Wilkinson | 67100 | 48325.42 | 0 | 0 | 0% | 0 | 0% | 1179 | 0 | 0 | 0%
26-PC-41884 | Foxglove Trail - Curation | Time and material | In Progress | Built Environment | Melody Holloway | 1099300 | 743556.08 | 69536.26 | 1805.93 | 0.2429% | 0 | 9.109% | 13210 | 1258 | 40.75 | 0.3085%
26-PC-41918 | Plover Cove Data Recovery | Fixed fee | In Progress | Built Environment | Melody Holloway | 121100 | 81064.34 | 6059.96 | 108.52 | 0.1339% | 0 | 7.342% | 1269 | 114.75 | 2.5 | 0.197%
26-PC-41947 | Juniper Wash Trail - Cultural Resources Monitoring | Fixed fee | Lab/Curation | Built Environment | Rickey Salas | 64400 | 52073.84 | 30061.89 | 1035.17 | 1.988% | 0 | 55.74% | 1031 | 608 | 20.75 | 2.013%
26-PC-41954 | Creosote Draw Class III Survey | Fixed fee | Completed | Built Environment | Kathleen Cabrera | 98400 | 77440.8 | 89638.03 | 12197.23 | 15.75% | 1 | 100% | 959 | 1508.09 | 549.09 | 57.26%
26-PC-41961 | Eagle Bend Data Recovery | Fixed fee | In Progress | Built Environment | Melody Holloway | 463200 | 369077.76 | 83505.48 | 867.93 | 0.2352% | 0 | 22.39% | 4333 | 1294.75 | 15.75 | 0.3635%
26-PC-41970 | North Fork School Campus - Cultural Resources Monitoring | Time and material | Final Reporting/Review | Built Environment | Melody Holloway | 292200 | 212405.41 | 60262.34 | 964.01 | 0.4539% | 0 | 27.92% | 4197 | 1171.5 | 21 | 0.5004%
26-PC-41987 | Wildrye Cultural Resources Monitoring | Fixed fee | Completed | Built Environment | Rickey Salas | 88100 | 66383.35 | 49349.09 | 0 | 0% | 0 | 74.34% | 735 | 701.02 | 0 | 0%
26-PC-42007 | On-Call: Wren Hollow Mixed-Use Development Architectural History Survey | Fixed fee | In Progress | Built Environment | Jesse Maynard | 341700 | 215752.53 | 23729.28 | 135.63 | 0.06286% | 0 | 10.94% | 2990 | 405.5 | 2.75 | 0.09197%
26-PC-42008 | Millbrook GIS Mapping | Time and material | In Progress | Built Environment | Kathleen Cabrera | 79400 | 54793.94 | 0 | 0 | 0% | 0 | 0% | 1033 | 0 | 0 | 0%
26-PC-42023 | North Fork Historic Resources Evaluation | Fixed fee | Transferred Entity | Built Environment | Jenny Wilkinson | 157000 | 111815.4 | 11876.63 | -295.92 | -0.2647% | 0 | 10.89% | 1522 | 174.25 | -6 | -0.3942%
26-PC-42040 | Millbrook Phase II Testing | Time and material | In Progress | Built Environment | Jenny Wilkinson | 129700 | 89350.33 | 9591.8 | 602.87 | 0.6747% | 0 | 10.06% | 862 | 124 | 7.75 | 0.8991%
26-PC-42099 | Fern Valley Substation Cultural Resources Monitoring | Time and material | In Progress | Built Environment | Jesse Maynard | 661800 | 445656.12 | 74965.46 | 2487.67 | 0.5582% | 0 | 16.26% | 0 | 1206 | 41 | 0%
26-PC-42105 | Creosote Draw Archaeological Testing | Time and material | Completed | Built Environment | Jesse Maynard | 671900 | 486652.56 | 589825.21 | 103172.65 | 21.2% | 1 | 100% | 5190 | 9354.79 | 4164.79 | 80.25%
26-PC-42108 | Sumac Ridge Mixed-Use Development Curation | Fixed fee | In Progress | Built Environment | Kathleen Cabrera | 1000600 | 761256.48 | 43963.83 | 381 | 0.05005% | 0 | 5.725% | 11018 | 442.25 | 3.75 | 0.03404%
26-PC-42222 | On-Call: Stone Mill Fiber Route Cultural Resources Monitoring | Time and material | On Hold | Built Environment | Rickey Salas | 30000 | 21213 | 0 | 0 | 0% | 0 | 0% | 270 | 0 | 0 | 0%
26-PC-42293 | Eagle Bend Water Main Phase II Testing | Fixed fee | In Progress | Paleontology | Charlene Sparks | 100800 | 88704 | 21724.75 | 465.3 | 0.5246% | 0 | 23.97% | 1244 | 397.75 | 11 | 0.8842%
26-PC-42406 | Saltgrass Cell Tower - Section 106 Consultation | Time and material | Final Billing/Invoice | Paleontology | Charlene Sparks | 92600 | 64853.52 | 55386.04 | 0 | 0% | 0 | 85.4% | 1079 | 1001.89 | 11.03 | 1.022%
26-PC-42427 | Phase II: Stone Mill Mine Expansion Section 106 Consultation | Time and material | In Progress | Paleontology | Travis Delgado | 926100 | 644195.16 | 140019.3 | 1989.73 | 0.3089% | 0 | 21.43% | 8174 | 2363.75 | 42.25 | 0.5169%
26-PC-42428 | Phase II: Yarrow Point Levee Repair Architectural History Survey | Fixed fee | Final Reporting/Review | Paleontology | Charlene Sparks | 921200 | 680214.08 | 17174.42 | 169.25 | 0.02488% | 0 | 2.5% | 0 | 342 | 4.5 | 0%
26-PC-42472 | Kestrel Butte Cultural Resources Monitoring | Fixed fee | In Progress | Paleontology | Travis Delgado | 129200 | 94328.92 | 3220.98 | 547.25 | 0.5802% | 0 | 2.834% | 1835 | 59.5 | 12.5 | 0.6812%
26-PC-42492 | Tamarack Class III Survey | Time and material | In Progress | Paleontology | Charlene Sparks | 60100 | 39629.94 | 9610.69 | 69.83 | 0.1762% | 0 | 24.07% | 616 | 172.75 | 1.75 | 0.2841%
26-PC-42510 | Lantern Bay Data Recovery | Time and material | In Progress | Paleontology | Charlene Sparks | 1304200 | 949196.76 | 96292.18 | 1915.02 | 0.2018% | 0 | 9.943% | 12435 | 1963.25 | 47 | 0.378%
26-PC-42554 | Task Order 36: Larkspur Pipeline Class III Survey | Fixed fee | In Progress | Paleontology | Charlene Sparks | 138900 | 102674.88 | 7211.42 | 197.37 | 0.1922% | 0 | 6.831% | 0 | 117 | 3 | 0%
26-PC-42585 | On-Call: Eagle Bend Reservoir Class III Survey | Fixed fee | Completed | Paleontology | Charlene Sparks | 29400 | 20518.26 | 14763.84 | 0 | 0% | 0 | 71.95% | 291 | 263.41 | 0 | 0%
26-PC-42598 | Badger Hollow Phase II Testing | Time and material | In Progress | Paleontology | Travis Delgado | 99400 | 74509.83 | 31770.68 | 593.44 | 0.7965% | 0 | 41.84% | 806 | 372.75 | 10 | 1.241%
26-PC-42616 | Goldfinch Section 106 Consultation | Fixed fee | Final Billing/Invoice | Paleontology | Charlene Sparks | 14600 | 11993.9 | 8413.18 | 0 | 0% | 0 | 70.15% | 176 | 135.11 | 0 | 0%
26-PC-42648 | Plover Cove Highway Widening - Architectural History Survey | Fixed fee | Final Billing/Invoice | Paleontology | Charlene Sparks | 330300 | 209145.96 | 157531.9 | 0 | 0% | 0 | 75.32% | 4191 | 2816.41 | 0 | 0%
26-PC-42664 | Foxglove Cell Tower GIS Mapping | Fixed fee | In Progress | Paleontology | Travis Delgado | 50700 | 32903.41 | 2075.33 | 0 | 0% | 0 | 6.307% | 0 | 27 | 0 | 0%
26-PC-42679 | Aspen Ridge Phase I Survey | Fixed fee | Final Reporting/Review | Maritime | Kyle Maynard | 214600 | 144103.9 | 69217.42 | 1989.36 | 1.381% | 0 | 46.65% | 1148 | 765 | 27.75 | 2.417%
26-PC-42692 | Quail Run Curation | Fixed fee | In Progress | Maritime | Rita Ayala | 300500 | 203889.25 | 26905.99 | 468 | 0.2295% | 0 | 12.97% | 1571 | 298.25 | 4 | 0.2546%
26-PC-42734 | On-Call: Lantern Bay Reservoir Architectural History Survey | Time and material | In Progress | Maritime | Rita Ayala | 77500 | 51615 | 25950.91 | 782.71 | 1.516% | 0 | 48.76% | 704 | 468 | 24 | 3.409%
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | Fixed fee | In Progress | Maritime | Kyle Maynard | 347000 | 256363.6 | 186528.08 | 5905.95 | 2.304% | 0 | 70.46% | 3715 | 2740.75 | 201.25 | 5.417%
26-PC-42759 | Cedar Hollow Pipeline - Section 106 Consultation | Time and material | Completed | Maritime | Kyle Maynard | 740600 | 515013.24 | 489411.31 | 0 | 0% | 0 | 95.03% | 7530 | 7634.55 | 104.55 | 1.388%
26-PC-42788 | Riverbend Bridge Replacement Data Recovery | Fixed fee | Final Billing/Invoice | Maritime | Kyle Maynard | 1595900 | 1047867.94 | 1257235.02 | 209367.08 | 19.98% | 1 | 100% | 20306 | 18392.25 | 1008.28 | 4.965%
26-PC-42811 | On-Call: Yarrow Point Bridge Replacement Archaeological Testing | Time and material | Completed | Maritime | Kyle Maynard | 8000 | 5034.4 | 6127.58 | 1093.18 | 21.71% | 1 | 100% | 50 | 76.33 | 26.33 | 52.66%
26-PC-42832 | Task Order 39: Saltgrass Levee Repair Class III Survey | Time and material | Final Reporting/Review | Maritime | Rita Ayala | 343600 | 243097 | 23563.54 | 235.67 | 0.09694% | 0 | 9.596% | 4994 | 475.75 | 5.25 | 0.1051%
26-PC-42838 | Phase III: Oak Terrace Pipeline Phase II Testing | Fixed fee | In Progress | Maritime | Rita Ayala | 47400 | 31824.36 | 13337.83 | 189.77 | 0.5963% | 0 | 41.31% | 596 | 221 | 4.5 | 0.755%
26-PC-42859 | On-Call: Redbud Canal Lining Phase II Testing | Fixed fee | On Hold | Maritime | Rita Ayala | 34400 | 26797.6 | 0 | 0 | 0% | 0 | 0% | 267 | 0 | 0 | 0%
26-PC-42880 | Phase I: Quail Run Harbor Dredging Curation | Fixed fee | In Progress | Maritime | Rita Ayala | 107200 | 87904 | 9955.87 | 0 | 0% | 0 | 11.33% | 1117 | 214 | 0 | 0%
26-PC-42898 | Sumac Ridge Architectural History Survey | Fixed fee | Final Billing/Invoice | Maritime | Kyle Maynard | 388100 | 247453.77 | 216501.93 | 0 | 0% | 0 | 87.49% | 2484 | 2914.54 | 430.54 | 17.33%
26-PC-42926 | Juniper Wash Transmission Line - Class III Survey | Fixed fee | In Progress | Maritime | Rita Ayala | 87800 | 68132.8 | 3601.54 | 0 | 0% | 0 | 5.286% | 1116 | 79.25 | 0 | 0%
26-PC-42940 | North Fork Water Main GIS Mapping | Time and material | Completed | Maritime | Kyle Maynard | 17600 | 11908.16 | 15335.83 | 3427.67 | 28.78% | 1 | 100% | 157 | 220.38 | 63.38 | 40.37%
26-PC-42951 | Quail Run Solar - Paleontological Monitoring | Fixed fee | Final Billing/Invoice | Maritime | Kyle Maynard | 209300 | 146631.97 | 157199.34 | 10567.37 | 7.207% | 1 | 100% | 1885 | 2442.74 | 557.74 | 29.59%
26-PC-42962 | Lone Pine Curation | Time and material | In Progress | Maritime | Rita Ayala | 1041700 | 704293.37 | 7965.32 | 0 | 0% | 0 | 1.131% | 0 | 114.5 | 0 | 0%
26-PC-42989 | North Fork Cultural Resources Monitoring | Time and material | In Progress | Maritime | Rita Ayala | 24000 | 15241.71 | 928.45 | 18.68 | 0.1226% | 0 | 5.969% | 0 | 20 | 0.5 | 0%
26-PC-43000 | Pebble Beach Road Park Improvements Curation | Fixed fee | Final Billing/Invoice | Maritime | Rita Ayala | 150700 | 99296.23 | 101028.81 | 1732.58 | 1.745% | 0 | 100% | 1048 | 1763.22 | 715.22 | 68.25%
26-PC-43026 | Fern Valley Phase I Survey | Fixed fee | On Hold | Maritime | Rita Ayala | 66700 | 42521.25 | 0 | 0 | 0% | 0 | 0% | 469 | 0 | 0 | 0%
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Time and material | Final Reporting/Review | Geospatial | Sylvia Callahan | 107600 | 77827.43 | 89098.75 | 11271.32 | 14.48% | 1 | 100% | 0 | 1363.5 | 3 | 0%
26-PC-43059 | Kestrel Butte Battery Storage - Phase II Testing | Fixed fee | Final Billing/Invoice | Geospatial | Sylvia Callahan | 44100 | 27527.22 | 34304.67 | 6777.45 | 24.62% | 1 | 100% | 518 | 559.44 | 45.8 | 8.842%
26-PC-43086 | On-Call: Silver Lake Transmission Line Archaeological Testing | Time and material | In Progress | Geospatial | Sylvia Callahan | 2118800 | 1431461.28 | 0 | 0 | 0% | 0 | 0% | 14495 | 0 | 0 | 0%
26-PC-43132 | Phase III: Ember Valley Highway Widening Phase II Testing | Fixed fee | Lab/Curation | Geospatial | Priscilla Pennington | 140700 | 112756.98 | 37690.1 | 1632.76 | 1.448% | 0 | 31.98% | 1530 | 655.5 | 50.75 | 3.317%
26-PC-43136 | Phase III: Harbor View Highway Widening Section 106 Consultation | Time and material | In Progress | Geospatial | Priscilla Pennington | 3831800 | 2564623.74 | 120256.62 | 2521.33 | 0.09831% | 0 | 4.591% | 32425 | 1526.25 | 44.25 | 0.1365%
26-PC-43168 | Task Order 35: Aspen Ridge Transmission Line Architectural History Survey | Fixed fee | Final Reporting/Review | Geospatial | Sylvia Callahan | 281200 | 164749.65 | 49236.49 | 1048.69 | 0.6365% | 0 | 29.25% | 2975 | 860 | 24.25 | 0.8151%
26-PC-43191 | Sandpiper Harbor Dredging - Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Meridian Central | Seth Zavala | 47200 | 37639.5 | 39248.37 | 1608.87 | 4.274% | 0 | 100% | 613 | 539.83 | 0 | 0%
26-PC-43199 | Thistle Down Airport Apron Phase I Survey | Fixed fee | Cost Tracking on Closed Project | Meridian Central | Mathew Shea | 42200 | 26341.24 | 24305.56 | 0 | 0% | 0 | 92.27% | 249 | 336.58 | 87.58 | 35.17%
26-PC-43222 | Blue Heron Highway Widening Phase II Testing | Time and material | On Hold | Meridian Central | Raymond Hensley | 15100 | 9664 | 0 | 0 | 0% | 0 | 0% | 138 | 0 | 0 | 0%
26-PC-43266 | Silver Lake Curation | Fixed fee | In Progress | Meridian Central | Mathew Shea | 21300 | 13227.3 | 288.09 | 0 | 0% | 0 | 2.178% | 192 | 5.75 | 0 | 0%
26-PC-43307 | Phase III: Aspen Ridge Mine Expansion Maritime Remote Sensing Survey | Time and material | In Progress | Meridian Central | Raymond Hensley | 239600 | 189451.72 | 52539.34 | 582.84 | 0.3076% | 0 | 27.42% | 3953 | 891.5 | 12 | 0.3036%
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | Fixed fee | In Progress | Meridian Central | Mathew Shea | 41200 | 27426.84 | 20599.46 | 3242.01 | 11.82% | 1 | 63.29% | 399 | 267 | 16.25 | 4.073%
26-PC-43338 | Sparrow Hill Bridge Replacement Section 106 Consultation | Time and material | In Progress | Meridian Central | Raymond Hensley | 121900 | 79125.29 | 0 | 0 | 0% | 0 | 0% | 1158 | 0 | 0 | 0%
26-PC-43341 | Phase III: Twin Buttes Wastewater Plant Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | Meridian Central | Seth Zavala | 87500 | 70376.25 | 55410.62 | 0 | 0% | 0 | 78.73% | 830 | 753.85 | 21.8 | 2.627%
26-PC-43364 | Goldfinch Class III Survey | Fixed fee | Transferred Entity | Meridian Central | Raymond Hensley | 24900 | 16624.07 | 22825.96 | 6201.89 | 37.31% | 1 | 100% | 191 | 356.5 | 165.5 | 86.65%
26-PC-43381 | Lantern Bay Canal Lining Archaeological Testing | Fixed fee | In Progress | Meridian Central | Clinton Solis | 309600 | 249847.2 | 19118.33 | 1063.92 | 0.4258% | 0 | 7.226% | 0 | 170 | 13 | 0%
26-PC-43404 | On-Call: Timber Gap Transmission Line Built Environment Survey | Fixed fee | Final Billing/Invoice | Meridian Central | Raymond Hensley | 190700 | 155973.53 | 202765.59 | 46792.06 | 30% | 1 | 100% | 1770 | 2998.76 | 1228.76 | 69.42%
26-PC-43429 | Stone Mill Highway Widening Curation | Fixed fee | Transferred Entity | Meridian Central | Clinton Solis | 202600 | 115400.96 | 5994.77 | 0 | 0% | 0 | 5.195% | 0 | 114.25 | 0 | 0%
26-PC-43478 | Tamarack Airport Apron Phase II Testing | Time and material | In Progress | Meridian Central | Clinton Solis | 531800 | 378109.8 | 117552.6 | 2742.19 | 0.7252% | 0 | 30.36% | 3100 | 1463.75 | 50 | 1.613%
26-PC-43493 | Millbrook Pipeline Cultural Resources Monitoring | Time and material | In Progress | Meridian Central | Raymond Hensley | 1164300 | 893116.35 | 66672.18 | 1348.45 | 0.151% | 0 | 7.314% | 10792 | 1003.5 | 27.25 | 0.2525%
26-PC-43519 | On-Call: Meadowlark Pipeline GIS Mapping | Fixed fee | Completed | Meridian Central | Raymond Hensley | 28100 | 19981.91 | 20035.99 | 54.08 | 0.2706% | 0 | 100% | 0 | 279.53 | 0 | 0%
26-PC-43527 | Maple Fork School Campus Phase II Testing | Time and material | In Progress | Meridian Central | Raymond Hensley | 333700 | 224680.21 | 53521.21 | 1977.61 | 0.8802% | 0 | 22.94% | 2004 | 599 | 18.75 | 0.9356%
26-PC-43528 | Quail Run Cell Tower GIS Mapping | Fixed fee | Final Reporting/Review | Meridian Central | Mathew Shea | 21800 | 14869.78 | 12713.55 | 1108.65 | 7.456% | 1 | 78.04% | 185 | 151 | 14.25 | 7.703%
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | Fixed fee | In Progress | Meridian Central | Clinton Solis | 136900 | 105043.37 | 100533.21 | 24689.24 | 23.5% | 1 | 72.2% | 931 | 1264.75 | 515 | 55.32%
26-PC-43563 | Thistle Down Section 106 Consultation | Time and material | In Progress | Meridian Central | Mathew Shea | 79800 | 52393.25 | 16759.41 | 461.62 | 0.8811% | 0 | 31.11% | 640 | 238 | 6.25 | 0.9766%
26-PC-43575 | On-Call: Fern Valley Substation Data Recovery | Fixed fee | Lab/Curation | Meridian Central | Mathew Shea | 113100 | 87831.71 | 61848.22 | 2531.64 | 2.882% | 0 | 67.53% | 0 | 788.5 | 44.75 | 0%
26-PC-43584 | On-Call: Wren Hollow Solar Architectural History Survey | Fixed fee | In Progress | Meridian Central | Mathew Shea | 223700 | 185536.78 | 0 | 0 | 0% | 0 | 0% | 2104 | 0 | 0 | 0%
26-PC-43695 | Willow Springs Maritime Remote Sensing Survey | Fixed fee | In Progress | Meridian Southwest | Alan Gay | 104700 | 73750.68 | 25376.37 | 630.69 | 0.8552% | 0 | 33.55% | 1052 | 408.25 | 14 | 1.331%
26-PC-43731 | Task Order 32: Dove Canyon Transmission Line Paleontological Monitoring | Time and material | In Progress | Meridian Southwest | Alan Gay | 17700 | 12905.07 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-43746 | Cedar Hollow Wastewater Plant - Paleontological Monitoring | Fixed fee | On Hold | Meridian Southwest | Alan Gay | 94200 | 53458.5 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-43762 | Hawk Point Substation Paleontological Monitoring | Fixed fee | In Progress | Meridian Southwest | Lynn Tran | 17500 | 15400 | 832.68 | 0 | 0% | 0 | 5.407% | 126 | 10.25 | 0 | 0%
26-PC-43818 | Plover Cove Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | Meridian Southwest | Lynn Tran | 277600 | 226882.48 | 26203.94 | 0 | 0% | 0 | 11.55% | 0 | 375.5 | 0 | 0%
26-PC-43874 | Oak Terrace Cell Tower - Class III Survey | Fixed fee | Transferred Entity | NH Gulf (USD) | Justin Mejia | 72100 | 51991.31 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0%
26-PC-43899 | On-Call: Foxglove Reservoir Cultural Resources Monitoring | Time and material | In Progress | NH Gulf (USD) | Justin Mejia | 154600 | 103767.52 | 12573.62 | 0 | 0% | 0 | 12.12% | 0 | 125.75 | 0 | 0%
26-PC-43915 | Task Order 5: Twin Buttes Bridge Replacement Phase I Survey | Fixed fee | Transferred Entity | NH Gulf (USD) | Javier Rangel | 202200 | 177936 | 1086.48 | 0 | 0% | 0 | 0.6106% | 2378 | 12.25 | 0 | 0%
26-PC-43927 | On-Call: Millbrook Cell Tower Architectural History Survey | Time and material | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 60000 | 39334.64 | 2279.19 | 75.84 | 0.1928% | 0 | 5.602% | 0 | 39.75 | 1.5 | 0%
26-PC-43957 | Meadowlark Rail Siding - GIS Mapping | Fixed fee | Completed | NH Gulf (USD) | Vanessa Duarte | 294000 | 218030.4 | 255258.13 | 37227.73 | 17.07% | 1 | 100% | 2122 | 3128.65 | 1006.65 | 47.44%
26-PC-43961 | On-Call: Sparrow Hill Fiber Route Architectural History Survey | Fixed fee | Transferred Entity | NH Gulf (USD) | Vanessa Duarte | 264600 | 211627.08 | 94998.53 | 3265.45 | 1.543% | 0 | 43.35% | 2992 | 1403.5 | 35.25 | 1.178%
26-PC-43963 | On-Call: Foxglove Trail Data Recovery | Fixed fee | In Progress | NH Gulf (USD) | Javier Rangel | 532600 | 335058.66 | 84187.72 | 1631.56 | 0.4869% | 0 | 24.64% | 6615 | 1367 | 32.5 | 0.4913%
26-PC-43979 | Pine Hollow Harbor Dredging - Historic Resources Evaluation | Fixed fee | Transferred Entity | NH Gulf (USD) | Justin Mejia | 98500 | 72742.25 | 0 | 0 | 0% | 0 | 0% | 890 | 0 | 0 | 0%
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Time and material | Transferred Entity | NH Gulf (USD) | Justin Mejia | 220800 | 146699.52 | 136849.08 | 48887.94 | 33.33% | 1 | 59.96% | 1754 | 1668.75 | 561.25 | 32%
26-PC-43991 | Saltgrass Water Main - Archaeological Testing | Fixed fee | In Progress | NH Gulf (USD) | Tonya Spence | 22500 | 13335.87 | 8191.4 | 170.68 | 1.28% | 0 | 60.14% | 74 | 68.75 | 3.5 | 4.73%
26-PC-44007 | Goldfinch Battery Storage Architectural History Survey | Time and material | Transferred Entity | NH Gulf (USD) | Randy Cantu | 226900 | 149799.38 | 8751.52 | 0 | 0% | 0 | 5.842% | 2606 | 170 | 0 | 0%
26-PC-44050 | On-Call: Hawk Point Canal Lining Archaeological Testing | Fixed fee | Transferred Entity | NH Gulf (USD) | Vanessa Duarte | 670400 | 477190.72 | 26569.32 | 1013.31 | 0.2123% | 0 | 5.356% | 5223 | 487.75 | 20.25 | 0.3877%
26-PC-44072 | Oak Terrace Water Main GIS Mapping | Fixed fee | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 106200 | 79469.46 | 41489.46 | 939.31 | 1.182% | 0 | 51.03% | 0 | 403.5 | 12.5 | 0%
26-PC-44090 | Eagle Bend Phase I Survey | Time and material | Transferred Entity | NH Gulf (USD) | Tonya Spence | 6300 | 4404.16 | 565.68 | 0 | 0% | 0 | 12.84% | 31 | 5.75 | 0 | 0%
26-PC-44129 | Tamarack Airport Apron - Section 106 Consultation | Fixed fee | In Progress | NH Gulf (USD) | Javier Rangel | 40400 | 30324.24 | 0 | 0 | 0% | 0 | 0% | 212 | 0 | 0 | 0%
26-PC-44173 | Timber Gap Harbor Dredging - Section 106 Consultation | Fixed fee | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 160600 | 111038.84 | 20184.1 | 822.44 | 0.7407% | 0 | 17.44% | 0 | 365 | 16.5 | 0%
26-PC-44201 | Plover Cove Section 106 Consultation | Time and material | Transferred Entity | NH Gulf (USD) | Javier Rangel | 165400 | 115267.26 | 39551.85 | 1384.2 | 1.201% | 0 | 33.11% | 1266 | 494 | 15 | 1.185%
26-PC-44220 | Dove Canyon GIS Mapping | Time and material | Transferred Entity | NH Gulf (USD) | Justin Mejia | 59700 | 47634.63 | 4924.66 | 165.22 | 0.3468% | 0 | 9.992% | 691 | 94 | 3.75 | 0.5427%
26-PC-44256 | On-Call: Twin Buttes Rail Siding Environmental Review Support | Fixed fee | Transferred Entity | NH Gulf (USD) | Susan Wilkins | 810700 | 574867.37 | 227909.57 | 5832.23 | 1.015% | 0 | 38.63% | 0 | 2726.25 | 84.25 | 0%
26-PC-44277 | Phase I: Sea Oat Harbor Dredging Architectural History Survey | Fixed fee | In Progress | NH Gulf (USD) | Tonya Spence | 49100 | 39677.71 | 23018.41 | 534.48 | 1.347% | 0 | 56.67% | 427 | 241.75 | 12.75 | 2.986%
26-PC-44290 | On-Call: Larkspur Park Improvements GIS Mapping | Fixed fee | Transferred Entity | NH Gulf (USD) | Justin Mejia | 206100 | 160077.87 | 33903.52 | 926.55 | 0.5788% | 0 | 20.6% | 1733 | 406.5 | 11.25 | 0.6492%
26-PC-44302 | Dove Canyon Cell Tower - Built Environment Survey | Fixed fee | Transferred Entity | NH Gulf (USD) | Vanessa Duarte | 90200 | 67334.3 | 29937.62 | 1286.99 | 1.911% | 0 | 42.55% | 389 | 216 | 10.75 | 2.763%

## Budget to Actual Costs by Task
Northstar
Budget to Actual Costs by Task (In USD)
As of September 26, 2026
Reporting Book: | ACCRUAL
As of Date: | 09/26/2026
Location: | Northstar
[5 empty] | Bookings | Original Budget | Total Revised Budget | Total Costs |  |  |  | Budgeted Project Hours | Total Hours
[8 empty] | Cost of Sales | Wages | Remaining Commit | Total Costs
[5 empty] | Inception To Date | Inception To Date | Inception To Date | Inception To Date | Inception To Date | Inception To Date | Inception To Date | Inception To Date | Inception To Date
[5 empty] | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026
| Task Project ID | Task status | Location Name | Project Manager Name | Contract Value | Original Budget | Revised Budget | Actual | Actual | Actual | Actual | Budgeted Hours | Actual Hours
All Tasks
NHT-001005 - Final Report | 23-PC-30060 | Completed |  |  | 397800 | 312273 | 312273 | 38818.87 | 338063.36 | 0 | 376882.23 | 3891 | 5938.27
NHT-001011 - Agency Consultation | 23-PC-30163 | Completed |  |  | 5129 | 3466.88 | 3466.88 | 572.3 | 2938.74 | 0 | 3511.04 | 47 | 54.91
NHT-001014 - Reporting | 23-PC-30163 | Completed |  |  | 28171 | 19043.92 | 19043.92 | 3143.7 | 16142.83 | 0 | 19286.53 | 252 | 373.09
NHT-001015 - Testing | 23-PC-30307 | Completed |  |  | 167753 | 95199.59 | 95199.59 | 10994.86 | 51475.95 | 0 | 62470.81 | 772 | 1028.69
NHT-001017 - Final Report | 23-PC-30307 | Completed |  |  | 72347 | 41057.16 | 41057.16 | 4741.8 | 22200.26 | 0 | 26942.06 | 346 | 475.31
NHT-001020 - Curation | 23-PC-30372 | In progress |  |  | 3713 | 2721.72 | 2721.72 | 278.09 | 1284.2 | 0 | 1562.29 | 52 | 20.96
NHT-001024 - Data Recovery Excavation | 23-PC-30372 | In progress |  |  | 12725 | 9327.55 | 9327.55 | 953.02 | 4401.07 | 0 | 5354.09 | 167 | 87.96
NHT-001028 - Agency Consultation | 23-PC-30372 | In progress |  |  | 2417 | 1771.48 | 1771.48 | 181 | 835.84 | 0 | 1016.84 | 26 | 17.2
NHT-001033 - Desktop Review | 23-PC-30372 | In progress |  |  | 3872 | 2837.87 | 2837.87 | 289.96 | 1339.01 | 0 | 1628.97 | 45 | 21.41
NHT-001040 - Prefield | 23-PC-30372 | In progress |  |  | 4373 | 3205.68 | 3205.68 | 327.54 | 1512.55 | 0 | 1840.09 | 67 | 27.65
NHT-001047 - Site Recordation | 23-PC-30543 | In progress |  |  | 162020 | 97375.51 | 129186.03 | 13554.97 | 77417.96 | 0 | 90972.93 | 1210 | 1450.79
NHT-001049 - GIS & Mapping | 23-PC-30543 | In progress |  |  | 158580 | 95307.64 | 126442.63 | 13267.11 | 75773.91 | 0 | 89041.02 | 1328 | 1299.14
NHT-001053 - Desktop Review | 23-PC-30644 | In progress |  |  | 13582 | 9059.46 | 9059.46 | 1272.01 | 4589.79 | 0 | 5861.8 | 144 | 85.54
NHT-001057 - Survey | 23-PC-30644 | In progress |  |  | 94518 | 63043.24 | 63043.24 | 8851.7 | 31939.53 | 0 | 40791.23 | 710 | 676.78
NHT-001060 - Lab Analysis | 23-PC-30667 | Completed |  |  | 69258 | 47393.53 | 47393.53 | 7615.36 | 43153.72 | 0 | 50769.08 | 668 | 761.19
NHT-001064 - Fieldwork | 23-PC-30667 | Completed |  |  | 141242 | 96651.62 | 96651.62 | 15530.33 | 88005.18 | 0 | 103535.51 | 1385 | 1988.22
NHT-001066 - Final Report | 23-PC-30869 | In progress |  |  | 49800 | 34501.44 | 34501.44 | 5731.27 | 22925.09 | 0 | 28656.36 | 399 | 488.25
NHT-001071 - Data Recovery Excavation | 23-PC-30881 | Completed |  |  | 86200 | 58650.48 | 58650.48 | 7848.72 | 53469.43 | 0 | 61318.15 | 0 | 871.79
NHT-001074 - Final Report | 23-PC-30933 | On hold |  |  | 96689 | 63427.77 | 63427.77 | 10050.45 | 42569.7 | 0 | 52620.15 | 1230 | 697.9
NHT-001077 - Background Research | 23-PC-30933 | On hold |  |  | 63321 | 41538.87 | 41538.87 | 6582.04 | 27878.92 | 0 | 34460.96 | 832 | 533.88
NHT-001079 - Monitoring | 23-PC-30933 | On hold |  |  | 423760 | 277986.79 | 277986.79 | 44048.41 | 186571.53 | 0 | 230619.94 | 5627 | 3919.26
NHT-001081 - GIS & Mapping | 23-PC-30933 | On hold |  |  | 119430 | 78345.77 | 78345.77 | 12414.28 | 52581.96 | 0 | 64996.24 | 1541 | 893.63
NHT-001084 - Monitoring | 23-PC-31003 | In progress |  |  | 15226 | 8337.99 | 8337.99 | 767.42 | 5905.79 | 0 | 6673.21 | 0 | 140.16
NHT-001089 - Project Management | 23-PC-31003 | In progress |  |  | 4074 | 2230.69 | 2230.69 | 205.31 | 1579.99 | 0 | 1785.3 | 0 | 34.98
NHT-001091 - Curation | 23-PC-31042 | In progress |  |  | 88541 | 59942.52 | 59942.52 | 6729.87 | 36970.6 | 0 | 43700.47 | 728 | 683.58
NHT-001092 - GIS & Mapping | 23-PC-31042 | In progress |  |  | 211159 | 142954.38 | 142954.38 | 16049.79 | 88169.62 | 0 | 104219.41 | 2025 | 2018.14
NHT-001097 - Site Recordation | 23-PC-31076 | Completed |  |  | 95100 | 65561.94 | 65561.94 | 2865.67 | 38665.76 | 0 | 41531.43 | 720 | 688.12
NHT-001102 - Desktop Review | 23-PC-31344 | In progress |  |  | 31028 | 24735.7 | 24735.7 | 2147.32 | 12361.59 | 0 | 14508.91 | 0 | 219.83
NHT-001109 - Monitoring | 23-PC-31344 | In progress |  |  | 76866 | 61277.44 | 61277.44 | 5319.52 | 30623.2 | 0 | 35942.72 | 0 | 695.65
NHT-001113 - Site Recordation | 23-PC-31344 | In progress |  |  | 99373 | 79219.97 | 79219.97 | 6877.12 | 39589.93 | 0 | 46467.05 | 0 | 699.8
NHT-001120 - Fieldwork | 23-PC-31344 | In progress |  |  | 124333 | 99118.41 | 99118.41 | 8604.52 | 49534.12 | 0 | 58138.64 | 0 | 1032.17
NHT-001124 - Background Research | 23-PC-31374 | Completed |  |  | 26049 | 17137.47 | 17137.47 | 3513.94 | 17156.3 | 0 | 20670.24 | 307 | 392.77
NHT-001128 - Fieldwork | 23-PC-31374 | In progress |  |  | 181839 | 119631.72 | 119631.72 | 24529.81 | 119763.16 | 0 | 144292.97 | 2404 | 2123.71
NHT-001134 - Final Report | 23-PC-31374 | In progress |  |  | 47812 | 31455.84 | 31455.84 | 6449.84 | 31490.4 | 0 | 37940.24 | 631 | 623.16
NHT-001136 - Final Report | 23-PC-31389 | Completed |  |  | 4601 | 2590.39 | 3140.96 | 502.24 | 3581.01 | 0 | 4083.25 | 65 | 70.71
NHT-001137 - Agency Consultation | 23-PC-31389 | Completed |  |  | 3284 | 1848.99 | 2241.98 | 358.49 | 2556.08 | 0 | 2914.57 | 48 | 45.7
NHT-001143 - Data Recovery Excavation | 23-PC-31389 | Completed |  |  | 19667 | 11073.3 | 13426.85 | 2146.96 | 15307.95 | 0 | 17454.91 | 368 | 319.78
NHT-001149 - Background Research | 23-PC-31389 | Completed |  |  | 3148 | 1772.44 | 2149.16 | 343.65 | 2450.25 | 0 | 2793.9 | 60 | 46.03
NHT-001152 - Curation | 23-PC-31405 | In progress |  |  | 12154 | 9273.78 | 9273.78 | 1031.71 | 5539.68 | 0 | 6571.39 | 149 | 113.88
NHT-001159 - Site Recordation | 23-PC-31405 | In progress |  |  | 34933 | 26654.1 | 26654.1 | 2965.27 | 15921.79 | 0 | 18887.06 | 501 | 360.04
NHT-001160 - Reporting | 23-PC-31405 | In progress |  |  | 45898 | 35019.57 | 35019.57 | 3895.92 | 20918.89 | 0 | 24814.81 | 485 | 507.37
NHT-001162 - Background Research | 23-PC-31405 | In progress |  |  | 15015 | 11456.55 | 11456.55 | 1274.54 | 6843.55 | 0 | 8118.09 | 173 | 130.11
NHT-001163 - Draft Report | 23-PC-31604 | Completed |  |  | 79584 | 54849.43 | 54849.43 | 5062.6 | 66241.66 | 0 | 71304.26 | 768 | 1221
NHT-001170 - Curation | 23-PC-31604 | Completed |  |  | 23541 | 16224.36 | 16224.36 | 1497.51 | 19594.16 | 0 | 21091.67 | 248 | 412.44
NHT-001173 - Agency Consultation | 23-PC-31604 | Completed |  |  | 27069 | 18655.78 | 18655.78 | 1721.93 | 22530.58 | 0 | 24252.51 | 262 | 426.46
NHT-001175 - Prefield | 23-PC-31604 | Completed |  |  | 50606 | 34877.79 | 34877.79 | 3219.22 | 42121.91 | 0 | 45341.13 | 619 | 768.58
NHT-001181 - Project Management | 23-PC-31765 | Completed |  |  | 4249 | 3523.27 | 3523.27 | 213.67 | 1802.1 | 0 | 2015.77 | 0 | 41.77
NHT-001188 - Survey | 23-PC-31765 | Completed |  |  | 14074 | 11669.58 | 11669.58 | 707.72 | 5968.83 | 0 | 6676.55 | 0 | 103.87
NHT-001190 - Agency Consultation | 23-PC-31765 | Completed |  |  | 1944 | 1612.32 | 1612.32 | 97.78 | 824.68 | 0 | 922.46 | 0 | 14.37
NHT-001191 - Site Recordation | 23-PC-31765 | Completed |  |  | 5393 | 4472.04 | 4472.04 | 271.21 | 2287.39 | 0 | 2558.6 | 0 | 37.97
NHT-001197 - Testing | 23-PC-31765 | Completed |  |  | 7040 | 5837.63 | 5837.63 | 354.03 | 2985.87 | 0 | 3339.9 | 0 | 55.04
NHT-001204 - Survey | 23-PC-31769 | Completed |  |  | 20944 | 17320.67 | 17320.67 | 4138.17 | 14844.27 | 0 | 18982.44 | 236 | 276.38
NHT-001210 - Final Report | 23-PC-31769 | Completed |  |  | 7691 | 6360.69 | 6360.69 | 1519.67 | 5451.28 | 0 | 6970.95 | 69 | 111.05
NHT-001216 - Desktop Review | 23-PC-31769 | Completed |  |  | 6165 | 5098.24 | 5098.24 | 1218.05 | 4369.32 | 0 | 5587.37 | 62 | 77.16
NHT-001218 - Testing | 23-PC-31812 | In progress |  |  | 140233 | 119030.12 | 119030.12 | 16580.55 | 73531.12 | 0 | 90111.67 | 2017 | 1307.3
NHT-001219 - Background Research | 23-PC-31812 | In progress |  |  | 36266 | 30782.74 | 30782.74 | 4287.94 | 19016.1 | 0 | 23304.04 | 466 | 361.77
NHT-001223 - Prefield | 23-PC-31812 | In progress |  |  | 46771 | 39698.92 | 39698.92 | 5529.94 | 24524.1 | 0 | 30054.04 | 708 | 396.6
NHT-001225 - Data Recovery Excavation | 23-PC-31812 | In progress |  |  | 237330 | 201445.5 | 201445.5 | 28060.77 | 124443.38 | 0 | 152504.15 | 2992 | 2582.13
NHT-001228 - Fieldwork | 23-PC-31844 | Completed |  |  | 90098 | 36685.04 | 48045.76 | 12633.97 | 45320.05 | 0 | 57954.02 | 0 | 914.76
NHT-001232 - Final Report | 23-PC-31844 | Completed |  |  | 25015 | 10185.44 | 13339.7 | 3507.77 | 12582.91 | 0 | 16090.68 | 0 | 277.77
NHT-001237 - Reporting | 23-PC-31844 | Completed |  |  | 47453 | 19321.41 | 25304.91 | 6654.11 | 23869.32 | 0 | 30523.43 | 0 | 469.5
NHT-001243 - Curation | 23-PC-31844 | Completed |  |  | 12734 | 5184.95 | 6790.64 | 1785.65 | 6405.39 | 0 | 8191.04 | 0 | 149.65
NHT-001250 - GIS & Mapping | 23-PC-31944 | Completed |  |  | 12930 | 9295.56 | 9295.56 | 1172.86 | 10325.74 | 0 | 11498.6 | 104 | 211.67
NHT-001255 - Curation | 23-PC-31944 | Completed |  |  | 10106 | 7265.35 | 7265.35 | 916.7 | 8070.54 | 0 | 8987.24 | 80 | 160.15
NHT-001259 - Reporting | 23-PC-31944 | Completed |  |  | 38890 | 27957.55 | 27957.55 | 3527.51 | 31055.97 | 0 | 34583.48 | 314 | 514.92
NHT-001261 - Project Management | 23-PC-31944 | Completed |  |  | 14074 | 10117.94 | 10117.94 | 1276.62 | 11239.27 | 0 | 12515.89 | 128 | 202.44
NHT-001267 - Data Recovery Excavation | 23-PC-31976 | Completed |  |  | 72100 | 51263.1 | 51263.1 | 6425.98 | 31152.87 | 0 | 37578.85 | 698 | 610.57
NHT-001273 - Desktop Review | 23-PC-32015 | In progress |  |  | 4528 | 3003.55 | 3297.13 | 248.38 | 1247.87 | 0 | 1496.25 | 51 | 24.44
NHT-001275 - Fieldwork | 23-PC-32015 | In progress |  |  | 29863 | 19808.66 | 21744.82 | 1638.07 | 8229.81 | 0 | 9867.88 | 282 | 153.04
NHT-001279 - Final Report | 23-PC-32015 | In progress |  |  | 6709 | 4449.94 | 4884.89 | 367.99 | 1848.8 | 0 | 2216.79 | 54 | 34.59
NHT-001283 - Project Management | 23-PC-32015 | In progress |  |  | 7837 | 5198.39 | 5706.5 | 429.88 | 2159.75 | 0 | 2589.63 | 68 | 46.57
NHT-001287 - Data Recovery Excavation | 23-PC-32015 | In progress |  |  | 40363 | 26773.94 | 29390.91 | 2214.04 | 11123.63 | 0 | 13337.67 | 397 | 189.45
NHT-001293 - Project Management | 23-PC-32135 | Completed |  |  | 39019 | 23898.94 | 29274.53 | 1782.82 | 18709.35 | 0 | 20492.17 | 0 | 313.04
NHT-001298 - Reporting | 23-PC-32135 | Completed |  |  | 39457 | 24167.04 | 29602.95 | 1802.82 | 18919.24 | 0 | 20722.06 | 0 | 349.45
NHT-001304 - Lab Analysis | 23-PC-32135 | Completed |  |  | 36824 | 22554.1 | 27627.19 | 1682.5 | 17656.54 | 0 | 19339.04 | 0 | 348.5
NHT-001308 - Site Recordation | 23-PC-32135 | Completed |  |  | 34828 | 21331.9 | 26130.08 | 1591.32 | 16699.74 | 0 | 18291.06 | 0 | 376.45
NHT-001312 - Final Report | 23-PC-32135 | Completed |  |  | 21472 | 13151.17 | 16109.27 | 981.05 | 10295.43 | 0 | 11276.48 | 0 | 198.38
NHT-001315 - Project Management | 23-PC-32278 | Completed |  |  | 3500 | 2281.3 | 2281.3 | 340.84 | 1398.13 | 0 | 1738.97 | 46 | 24
NHT-001316 - Curation | 23-PC-32329 | In progress |  |  | 149100 | 111109.32 | 111109.32 | 13567.49 | 85465.29 | 0 | 99032.78 | 1506 | 2324.85
NHT-001318 - Draft Report | 23-PC-32443 | In progress |  |  | 58237 | 40993.25 | 40993.25 | 2413.93 | 22926.57 | 0 | 25340.5 | 468 | 433.43
NHT-001322 - Prefield | 23-PC-32443 | In progress |  |  | 94363 | 66421.89 | 66421.89 | 3619.69 | 34378.45 | 0 | 37998.14 | 562 | 638.84
OVHD-Non-Posting - Overhead Non-Posting | 23-PC-32443 | In progress |  |  | 0 | 0 | 0 | 0 | 173.12 | 0 | 173.12 | 0 | 2.5
NHT-001328 - Curation | 23-PC-32474 | Completed |  |  | 6332 | 4766.87 | 5132.66 | 498.03 | 4857.13 | 0 | 5355.16 | 86 | 79.49
NHT-001330 - Testing | 23-PC-32474 | Completed |  |  | 19535 | 14707.44 | 15836.02 | 1536.59 | 14985.92 | 0 | 16522.51 | 285 | 305.63
NHT-001335 - Fieldwork | 23-PC-32474 | Completed |  |  | 21597 | 16259.58 | 17507.28 | 1698.76 | 16567.47 | 0 | 18266.23 | 308 | 286.51
NHT-001336 - Background Research | 23-PC-32474 | Completed |  |  | 5436 | 4092.39 | 4406.42 | 427.56 | 4169.88 | 0 | 4597.44 | 66 | 75.03
NHT-001341 - Lab Analysis | 23-PC-32520 | Completed |  |  | 519392 | 357133.92 | 357133.92 | 59322.22 | 220499.58 | 0 | 279821.8 | 3443 | 3502.42
NHT-001346 - Background Research | 23-PC-32520 | Completed |  |  | 241268 | 165896.17 | 165896.17 | 27556.41 | 102426.65 | 0 | 129983.06 | 1938 | 1893.63
NHT-001349 - Prefield | 23-PC-32520 | Completed |  |  | 355640 | 244537.79 | 244537.79 | 40619.28 | 150981.11 | 0 | 191600.39 | 3180 | 2323.97
NHT-001356 - Lab Analysis | 23-PC-32635 | Completed |  |  | 7888 | 5282.77 | 5282.77 | 1241.69 | 4615.33 | 0 | 5857.02 | 89 | 66.09
NHT-001359 - Site Recordation | 23-PC-32635 | Completed |  |  | 6812 | 4561.69 | 4561.69 | 1072.2 | 3985.36 | 0 | 5057.56 | 89 | 62.35
NHT-001363 - Testing | 23-PC-32635 | Completed |  |  | 10517 | 7043.17 | 7043.17 | 1655.47 | 6153.32 | 0 | 7808.79 | 113 | 95.86
NHT-001368 - Project Management | 23-PC-32635 | Completed |  |  | 7168 | 4800.49 | 4800.49 | 1128.33 | 4193.99 | 0 | 5322.32 | 76 | 84.95
NHT-001371 - GIS & Mapping | 23-PC-32635 | Completed |  |  | 4415 | 2956.84 | 2956.84 | 694.99 | 2583.27 | 0 | 3278.26 | 54 | 53.06
NHT-001376 - Project Management | 23-PC-33001 | In progress |  |  | 276122 | 171664.91 | 171664.91 | 13736.9 | 85089.68 | 0 | 98826.58 | 2723 | 1732.9
NHT-001383 - Desktop Review | 23-PC-33001 | In progress |  |  | 80278 | 49908.97 | 49908.97 | 3993.79 | 24738.53 | 0 | 28732.32 | 602 | 417.22
NHT-001387 - Background Research | 23-PC-33043 | Completed |  |  | 65325 | 31369.81 | 36246.29 | 4804.56 | 38873.25 | 0 | 43677.81 | 456 | 727.11
NHT-001391 - Monitoring | 23-PC-33043 | Completed |  |  | 232253 | 111530.3 | 128867.84 | 17081.83 | 138207.54 | 0 | 155289.37 | 1846 | 2117.21
NHT-001398 - Site Recordation | 23-PC-33043 | Completed |  |  | 81698 | 39232.03 | 45330.71 | 6008.73 | 48616.06 | 0 | 54624.79 | 664 | 866.04
NHT-001399 - GIS & Mapping | 23-PC-33043 | Completed |  |  | 63995 | 30731.01 | 35508.2 | 4706.72 | 38081.66 | 0 | 42788.38 | 601 | 793.25
NHT-001403 - Lab Analysis | 23-PC-33043 | Completed |  |  | 65529 | 31467.55 | 36359.22 | 4819.53 | 38994.37 | 0 | 43813.9 | 511 | 685.41
NHT-001404 - Curation | 23-PC-33070 | In progress |  |  | 10137 | 6310.38 | 6310.38 | 403.69 | 4908.02 | 0 | 5311.71 | 87 | 86.9
NHT-001407 - Draft Report | 23-PC-33070 | In progress |  |  | 30066 | 18716.15 | 18716.15 | 1197.32 | 14556.84 | 0 | 15754.16 | 241 | 273.49
NHT-001409 - Background Research | 23-PC-33070 | In progress |  |  | 14897 | 9273.22 | 9273.22 | 593.23 | 7212.43 | 0 | 7805.66 | 133 | 126.7
NHT-001414 - Fieldwork | 23-PC-33151 | In progress |  |  | 435282 | 339999.08 | 339999.08 | 42438.08 | 246256.34 | 0 | 288694.42 | 4262 | 4433.2
NHT-001421 - Testing | 23-PC-33151 | In progress |  |  | 201818 | 157639.73 | 157639.73 | 19676.31 | 114176.14 | 0 | 133852.45 | 1750 | 2012.35
NHT-001424 - Desktop Review | 23-PC-33193 | On hold |  |  | 2407 | 1883.84 | 1883.84 | 175.98 | 1147.18 | 0 | 1323.16 | 14 | 16.26
NHT-001427 - Final Report | 23-PC-33193 | On hold |  |  | 5183 | 4056.88 | 4056.88 | 378.98 | 2470.48 | 0 | 2849.46 | 31 | 41.69
NHT-001433 - Agency Consultation | 23-PC-33193 | On hold |  |  | 3310 | 2590.71 | 2590.71 | 242.01 | 1577.63 | 0 | 1819.64 | 23 | 39.61
NHT-001435 - Background Research | 23-PC-33218 | On hold |  |  | 57000 | 27900.6 | 36256.05 | 5604.24 | 23737.32 | 0 | 29341.56 | 422 | 401.36
NHT-001441 - GIS & Mapping | 23-PC-33299 | On hold |  |  | 71300 | 47214.86 | 47214.86 | 6073.41 | 30959.6 | 0 | 37033.01 | 408 | 521.71
NHT-001443 - Desktop Review | 23-PC-33395 | Completed |  |  | 10116 | 6627.14 | 6627.14 | 1404.29 | 7210.99 | 0 | 8615.28 | 55 | 108.68
NHT-001448 - Draft Report | 23-PC-33395 | Completed |  |  | 39738 | 26032.04 | 26032.04 | 5516.19 | 28325.46 | 0 | 33841.65 | 155 | 552.04
NHT-001449 - Prefield | 23-PC-33395 | Completed |  |  | 16269 | 10657.91 | 10657.91 | 2258.41 | 11596.87 | 0 | 13855.28 | 78 | 225.85
NHT-001452 - Data Recovery Excavation | 23-PC-33395 | Completed |  |  | 85413 | 55954.21 | 55954.21 | 11856.7 | 60883.79 | 0 | 72740.49 | 396 | 1356.51
NHT-001456 - Lab Analysis | 23-PC-33395 | Completed |  |  | 35364 | 23166.89 | 23166.89 | 4909.06 | 25207.89 | 0 | 30116.95 | 140 | 454.49
NHT-001458 - Prefield | 23-PC-33428 | Completed |  |  | 51768 | 36791.18 | 36791.18 | 8848.28 | 38980.25 | 0 | 47828.53 | 597 | 742.48
NHT-001465 - Data Recovery Excavation | 23-PC-33428 | Completed |  |  | 189402 | 134608.21 | 134608.21 | 32373.27 | 142617.41 | 0 | 174990.68 | 2165 | 2735.02
NHT-001470 - GIS & Mapping | 23-PC-33428 | Completed |  |  | 52730 | 37475.34 | 37475.34 | 9012.82 | 39705.12 | 0 | 48717.94 | 570 | 734.05
NHT-001472 - Lab Analysis | 23-PC-33471 | Completed |  |  | 20538 | 14662.27 | 14662.27 | 2122.84 | 9050.02 | 0 | 11172.86 | 0 | 166.3
NHT-001478 - Fieldwork | 23-PC-33471 | Completed |  |  | 55324 | 39495.88 | 39495.88 | 5718.32 | 24378.11 | 0 | 30096.43 | 0 | 433.18
NHT-001479 - Curation | 23-PC-33471 | Completed |  |  | 9875 | 7049.42 | 7049.42 | 1020.64 | 4351.13 | 0 | 5371.77 | 0 | 86.13
NHT-001482 - Reporting | 23-PC-33471 | Completed |  |  | 27463 | 19605.91 | 19605.91 | 2838.6 | 12101.4 | 0 | 14940 | 0 | 222.18
NHT-001487 - Draft Report | 23-PC-33551 | Completed |  |  | 18055 | 11737.39 | 11737.39 | 1038.71 | 7993.58 | 0 | 9032.29 | 0 | 143.6
NHT-001488 - GIS & Mapping | 23-PC-33551 | Completed |  |  | 7727 | 5023.17 | 5023.17 | 444.53 | 3420.96 | 0 | 3865.49 | 0 | 63.52
NHT-001492 - Monitoring | 23-PC-33551 | Completed |  |  | 27237 | 17706.73 | 17706.73 | 1566.98 | 12058.91 | 0 | 13625.89 | 0 | 183.91
NHT-001498 - Data Recovery Excavation | 23-PC-33551 | Completed |  |  | 27186 | 17673.73 | 17673.73 | 1564.06 | 12036.44 | 0 | 13600.5 | 0 | 225.02
NHT-001504 - Site Recordation | 23-PC-33551 | Completed |  |  | 15195 | 9878.52 | 9878.52 | 874.21 | 6727.62 | 0 | 7601.83 | 0 | 113.48
NHT-001511 - Fieldwork | 23-PC-33553 | Completed |  |  | 21600 | 15245.28 | 15245.28 | 1886.9 | 14664.89 | 0 | 16551.79 | 0 | 280.37
NHT-001514 - Reporting | 23-PC-33605 | Completed |  |  | 249055 | 151823.64 | 151823.64 | 21918.11 | 129241.31 | 0 | 151159.42 | 2819 | 2685.78
NHT-001516 - Project Management | 23-PC-33605 | Completed |  |  | 60045 | 36603.72 | 36603.72 | 5284.32 | 31159.26 | 0 | 36443.58 | 613 | 575.94
NHT-001523 - Final Report | 23-PC-33695 | On hold |  |  | 42600 | 27729 | 34191.4 | 3678.65 | 15381.73 | 0 | 19060.38 | 408 | 243.63
NHT-001530 - Reporting | 23-PC-33803 | On hold |  |  | 18516 | 9724.82 | 11222.56 | 471.88 | 5145.68 | 0 | 5617.56 | 0 | 91.66
NHT-001531 - Testing | 23-PC-33803 | On hold |  |  | 15283 | 8026.59 | 9262.78 | 389.47 | 4247.1 | 0 | 4636.57 | 0 | 74.06
NHT-001533 - Monitoring | 23-PC-33803 | On hold |  |  | 17981 | 9443.82 | 10898.28 | 458.24 | 4996.99 | 0 | 5455.23 | 0 | 95.91
NHT-001535 - Curation | 23-PC-33803 | On hold |  |  | 5228 | 2745.87 | 3168.77 | 133.24 | 1452.92 | 0 | 1586.16 | 0 | 24.72
NHT-001538 - Lab Analysis | 23-PC-33803 | On hold |  |  | 9392 | 4932.78 | 5692.49 | 239.35 | 2610.08 | 0 | 2849.43 | 0 | 45.08
NHT-001541 - Project Management | 23-PC-33858 | Completed |  |  | 10288 | 7019.74 | 7019.74 | 476.09 | 6229.44 | 0 | 6705.53 | 157 | 101.05
NHT-001548 - Curation | 23-PC-33858 | Completed |  |  | 6829 | 4659.16 | 4659.16 | 315.99 | 4134.63 | 0 | 4450.62 | 80 | 67.94
NHT-001553 - Testing | 23-PC-33858 | Completed |  |  | 23517 | 16045.88 | 16045.88 | 1088.27 | 14239.41 | 0 | 15327.68 | 287 | 232.43
NHT-001556 - Fieldwork | 23-PC-33858 | Completed |  |  | 27866 | 19012.77 | 19012.77 | 1289.49 | 16872.26 | 0 | 18161.75 | 299 | 249.41
NHT-001561 - Background Research | 23-PC-33879 | In progress |  |  | 36556 | 26664.15 | 26664.15 | 4447.51 | 17038.06 | 0 | 21485.57 | 0 | 308.03
NHT-001567 - Lab Analysis | 23-PC-33879 | In progress |  |  | 67792 | 49447.78 | 49447.78 | 8247.77 | 31596.53 | 0 | 39844.3 | 0 | 474.83
NHT-001574 - Testing | 23-PC-33879 | In progress |  |  | 133101 | 97083.18 | 97083.18 | 16193.24 | 62034.97 | 0 | 78228.21 | 0 | 941.38
NHT-001578 - Final Report | 23-PC-33879 | In progress |  |  | 63151 | 46062.53 | 46062.53 | 7683.12 | 29433.39 | 0 | 37116.51 | 0 | 553.85
NHT-001584 - Reporting | 23-PC-33998 | In progress |  |  | 76775 | 50440.86 | 50440.86 | 2703.5 | 28018.1 | 0 | 30721.6 | 0 | 519.54
NHT-001591 - Lab Analysis | 23-PC-33998 | In progress |  |  | 58702 | 38567.51 | 38567.51 | 2067.12 | 21422.88 | 0 | 23490 | 0 | 337.73
NHT-001596 - Agency Consultation | 23-PC-33998 | In progress |  |  | 19284 | 12669.77 | 12669.77 | 679.07 | 7037.61 | 0 | 7716.68 | 0 | 131.5
NHT-001601 - Site Recordation | 23-PC-33998 | In progress |  |  | 65262 | 42877.21 | 42877.21 | 2298.11 | 23816.77 | 0 | 26114.88 | 0 | 370.99
NHT-001604 - Desktop Review | 23-PC-33998 | In progress |  |  | 18777 | 12336.25 | 12336.25 | 661.19 | 6852.35 | 0 | 7513.54 | 0 | 106.77
NHT-001610 - Testing | 23-PC-34054 | Completed |  |  | 35604 | 24114.27 | 24114.27 | 5261.1 | 18653.01 | 0 | 23914.11 | 0 | 332.35
NHT-001617 - Data Recovery Excavation | 23-PC-34054 | Completed |  |  | 34301 | 23232.05 | 23232.05 | 5068.63 | 17970.59 | 0 | 23039.22 | 0 | 261.62
NHT-001621 - Draft Report | 23-PC-34054 | Completed |  |  | 29095 | 19706.38 | 19706.38 | 4299.42 | 15243.39 | 0 | 19542.81 | 0 | 250.14
NHT-001625 - Final Report | 23-PC-34135 | Completed |  |  | 108800 | 84537.6 | 84537.6 | 7710.57 | 89891.54 | 0 | 97602.11 | 0 | 1312.22
NHT-001628 - Desktop Review | 23-PC-34171 | In progress |  |  | 84159 | 58944.8 | 58944.8 | 5131.34 | 23696.4 | 0 | 28827.74 | 0 | 359.81
NHT-001635 - Project Management | 23-PC-34171 | In progress |  |  | 86478 | 60569.39 | 60569.39 | 5272.76 | 24349.51 | 0 | 29622.27 | 0 | 414.54
NHT-001636 - Curation | 23-PC-34171 | In progress |  |  | 50463 | 35344.25 | 35344.25 | 3076.83 | 14208.75 | 0 | 17285.58 | 0 | 243.16
NHT-001637 - Data Recovery Excavation | 23-PC-34229 | In progress |  |  | 41303 | 26982.61 | 29138.9 | 2171.83 | 19120.64 | 0 | 21292.47 | 266 | 329.39
NHT-001641 - Background Research | 23-PC-34229 | In progress |  |  | 7497 | 4897.57 | 5288.95 | 394.21 | 3470.55 | 0 | 3864.76 | 64 | 60.83
NHT-001647 - GIS & Mapping | 23-PC-34353 | In progress |  |  | 92928 | 61676.27 | 61676.27 | 5933.11 | 40060.01 | 0 | 45993.12 | 895 | 644.72
NHT-001651 - Fieldwork | 23-PC-34353 | In progress |  |  | 280172 | 185950.2 | 185950.2 | 17887.98 | 120778.5 | 0 | 138666.48 | 2466 | 2197.92
NHT-001653 - Monitoring | 23-PC-34403 | In progress |  |  | 46200 | 30187.08 | 30187.08 | 3237.06 | 20391.14 | 0 | 23628.2 | 397 | 303.4
NHT-001655 - Fieldwork | 23-PC-34440 | In progress |  |  | 418549 | 292858.73 | 292858.73 | 39875.99 | 173364.57 | 0 | 213240.56 | 2250 | 2953.49
NHT-001661 - Agency Consultation | 23-PC-34440 | In progress |  |  | 58451 | 40898.17 | 40898.17 | 5568.74 | 24210.63 | 0 | 29779.37 | 245 | 468.38
NHT-001664 - Lab Analysis | 23-PC-34473 | In progress |  |  | 15343 | 10664.7 | 10664.7 | 1317.24 | 5579.31 | 0 | 6896.55 | 123 | 78.11
NHT-001665 - Fieldwork | 23-PC-34473 | In progress |  |  | 36957 | 25689.03 | 25689.03 | 3172.96 | 13439.41 | 0 | 16612.37 | 336 | 258.8
NHT-001672 - Reporting | 23-PC-34510 | Completed |  |  | 31143 | 22354.89 | 22354.89 | 4484.32 | 15898.93 | 0 | 20383.25 | 184 | 313.04
NHT-001673 - Final Report | 23-PC-34510 | Completed |  |  | 17210 | 12353.18 | 12353.18 | 2478 | 8785.65 | 0 | 11263.65 | 107 | 129.75
NHT-001675 - Site Recordation | 23-PC-34510 | Completed |  |  | 21647 | 15537.93 | 15537.93 | 3116.85 | 11050.66 | 0 | 14167.51 | 133 | 199.58
NHT-001677 - Site Recordation | 23-PC-34522 | In progress |  |  | 111661 | 76398.24 | 76398.24 | 5803.88 | 37834.28 | 0 | 43638.16 | 664 | 610.57
NHT-001683 - Lab Analysis | 23-PC-34522 | In progress |  |  | 80539 | 55105 | 55105 | 4186.25 | 27289.34 | 0 | 31475.59 | 528 | 453.96
NHT-001689 - Curation | 23-PC-34567 | On hold |  |  | 4637 | 3653.19 | 3653.19 | 347.43 | 1500.59 | 0 | 1848.02 | 0 | 25.3
NHT-001694 - Desktop Review | 23-PC-34567 | On hold |  |  | 2639 | 2079.08 | 2079.08 | 197.73 | 854.01 | 0 | 1051.74 | 0 | 12.94
NHT-001696 - Reporting | 23-PC-34567 | On hold |  |  | 10624 | 8371.14 | 8371.14 | 796.11 | 3438.54 | 0 | 4234.65 | 0 | 57.69
NHT-001699 - Final Report | 23-PC-34745 | In progress |  |  | 614200 | 440258.56 | 440258.56 | 60024.16 | 232776.64 | 0 | 292800.8 | 3354 | 3980.82
NHT-001703 - Draft Report | 23-PC-34789 | In progress |  |  | 25283 | 17396.85 | 17396.85 | 1740.01 | 10513.61 | 0 | 12253.62 | 216 | 219.6
NHT-001705 - Background Research | 23-PC-34789 | In progress |  |  | 9906 | 6816.62 | 6816.62 | 681.79 | 4119.55 | 0 | 4801.34 | 109 | 84.24
NHT-001706 - Project Management | 23-PC-34789 | In progress |  |  | 10911 | 7507.94 | 7507.94 | 750.94 | 4537.35 | 0 | 5288.29 | 90 | 88.68
NHT-001710 - GIS & Mapping | 23-PC-34811 | Completed |  |  | 18778 | 11204.64 | 13488.52 | 845.93 | 10284.69 | 0 | 11130.62 | 0 | 230.02
NHT-001716 - Background Research | 23-PC-34811 | Completed |  |  | 15451 | 9219.83 | 11099.14 | 696.08 | 8462.84 | 0 | 9158.92 | 0 | 159.02
NHT-001718 - Data Recovery Excavation | 23-PC-34811 | Completed |  |  | 58973 | 35188.97 | 42361.67 | 2656.69 | 32299.79 | 0 | 34956.48 | 0 | 676.84
NHT-001721 - Project Management | 23-PC-34811 | Completed |  |  | 19398 | 11574.98 | 13934.35 | 873.89 | 10624.63 | 0 | 11498.52 | 0 | 234.57
NHT-001726 - Project Management | 23-PC-34826 | In progress |  |  | 168500 | 109642.95 | 109642.95 | 9943.89 | 51819.41 | 0 | 61763.3 | 1384 | 1139.36
NHT-001733 - Curation | 23-PC-34891 | Completed |  |  | 2711 | 2129.38 | 2129.38 | 312.19 | 1357.28 | 0 | 1669.47 | 28 | 28.24
NHT-001736 - Data Recovery Excavation | 23-PC-34891 | Completed |  |  | 15515 | 12184.72 | 12184.72 | 1786.41 | 7766.6 | 0 | 9553.01 | 140 | 155.33
NHT-001743 - Background Research | 23-PC-34891 | Completed |  |  | 4100 | 3220.48 | 3220.48 | 472.16 | 2052.74 | 0 | 2524.9 | 34 | 38.56
NHT-001750 - Final Report | 23-PC-34891 | Completed |  |  | 4274 | 3357.06 | 3357.06 | 492.18 | 2139.8 | 0 | 2631.98 | 35 | 47.41
NHT-001751 - Site Recordation | 23-PC-34902 | Completed |  |  | 37000 | 26270 | 26270 | 3022.49 | 14756.84 | 0 | 17779.33 | 550 | 358.24
NHT-001753 - Curation | 23-PC-34939 | In progress |  |  | 9616 | 5932.61 | 6870.61 | 369.57 | 4558.02 | 0 | 4927.59 | 97 | 101.5
NHT-001755 - Data Recovery Excavation | 23-PC-34939 | In progress |  |  | 51269 | 31629.98 | 36631.02 | 1970.38 | 24301.3 | 0 | 26271.68 | 494 | 501.14
NHT-001759 - Testing | 23-PC-34939 | In progress |  |  | 24934 | 15382.6 | 17814.75 | 958.25 | 11818.44 | 0 | 12776.69 | 255 | 277.65
NHT-001766 - Monitoring | 23-PC-34939 | In progress |  |  | 44635 | 27536.95 | 31890.83 | 1715.4 | 21156.62 | 0 | 22872.02 | 602 | 450.89
NHT-001767 - Project Management | 23-PC-34939 | In progress |  |  | 15346 | 9467.86 | 10964.83 | 589.8 | 7274.16 | 0 | 7863.96 | 139 | 151.27
NHT-001773 - Data Recovery Excavation | 23-PC-34947 | In progress |  |  | 285900 | 199615.38 | 199615.38 | 17765.72 | 116823.04 | 0 | 134588.76 | 2885 | 2202.8
NHT-001778 - Site Recordation | 23-PC-35003 | In progress |  |  | 187900 | 127170.72 | 127170.72 | 6082.68 | 79588.9 | 0 | 85671.58 | 0 | 1529.94
NHT-001779 - Data Recovery Excavation | 23-PC-35098 | Completed |  |  | 34589 | 28985.57 | 28985.57 | 2760.35 | 24039.17 | 0 | 26799.52 | 511 | 492.97
NHT-001786 - Reporting | 23-PC-35098 | Completed |  |  | 25826 | 21641.78 | 21641.78 | 2060.99 | 17948.6 | 0 | 20009.59 | 402 | 336.31
NHT-001793 - Background Research | 23-PC-35098 | Completed |  |  | 8234 | 6900.34 | 6900.34 | 657.13 | 5722.8 | 0 | 6379.93 | 117 | 125.25
NHT-001800 - Survey | 23-PC-35098 | Completed |  |  | 51351 | 43032.31 | 43032.31 | 4098.05 | 35688.81 | 0 | 39786.86 | 735 | 721.07
NHT-001803 - Project Management | 23-PC-35126 | In progress |  |  | 62049 | 44762.11 | 44762.11 | 4821.28 | 19165.21 | 0 | 23986.49 | 464 | 339.05
NHT-001809 - Prefield | 23-PC-35126 | In progress |  |  | 34558 | 24930.16 | 24930.16 | 2685.2 | 10674.02 | 0 | 13359.22 | 301 | 195.25
NHT-001815 - Agency Consultation | 23-PC-35126 | In progress |  |  | 33755 | 24351.06 | 24351.06 | 2622.83 | 10426.08 | 0 | 13048.91 | 271 | 199.62
NHT-001819 - Curation | 23-PC-35126 | In progress |  |  | 25178 | 18163.52 | 18163.52 | 1956.38 | 7776.84 | 0 | 9733.22 | 185 | 167.5
NHT-001823 - Monitoring | 23-PC-35126 | In progress |  |  | 117560 | 84807.49 | 84807.49 | 9134.54 | 36310.92 | 0 | 45445.46 | 753 | 698.39
NHT-001825 - Survey | 23-PC-35176 | In progress |  |  | 74700 | 53388.09 | 53388.09 | 6367.2 | 29006.14 | 0 | 35373.34 | 0 | 565
NHT-001830 - Site Recordation | 23-PC-35225 | In progress |  |  | 85726 | 67491.91 | 67491.91 | 5722.01 | 44471.05 | 0 | 50193.06 | 1128 | 980.08
NHT-001834 - Curation | 23-PC-35225 | In progress |  |  | 39253 | 30903.84 | 30903.84 | 2620.05 | 20362.83 | 0 | 22982.88 | 383 | 443.88
NHT-001840 - Monitoring | 23-PC-35225 | In progress |  |  | 213957 | 168448.19 | 168448.19 | 14281.14 | 110992.06 | 0 | 125273.2 | 2133 | 2867.08
NHT-001843 - Prefield | 23-PC-35225 | In progress |  |  | 68964 | 54295.73 | 54295.73 | 4603.23 | 35775.96 | 0 | 40379.19 | 698 | 691.83
NHT-001844 - Data Recovery Excavation | 23-PC-35425 | Completed |  |  | 19034 | 12688.36 | 12688.36 | 1610.65 | 8848.12 | 0 | 10458.77 | 0 | 158.02
NHT-001849 - Prefield | 23-PC-35425 | Completed |  |  | 4966 | 3310.04 | 3310.04 | 420.18 | 2308.23 | 0 | 2728.41 | 0 | 38.1
NHT-001856 - Desktop Review | 23-PC-35486 | In progress |  |  | 12201 | 9158.29 | 9158.29 | 1042.69 | 7167.49 | 0 | 8210.18 | 184 | 137.07
NHT-001857 - Survey | 23-PC-35486 | In progress |  |  | 63085 | 47351.27 | 47351.27 | 5391.06 | 37058.2 | 0 | 42449.26 | 1024 | 757.2
NHT-001858 - Draft Report | 23-PC-35486 | In progress |  |  | 40914 | 30710.16 | 30710.16 | 3496.42 | 24034.48 | 0 | 27530.9 | 616 | 509.85
NHT-001863 - GIS & Mapping | 23-PC-35533 | In progress |  |  | 2125 | 1529.69 | 1529.69 | 86.2 | 1078.65 | 0 | 1164.85 | 22 | 18.97
NHT-001866 - Survey | 23-PC-35533 | In progress |  |  | 7083 | 5099.31 | 5099.31 | 287.35 | 3595.74 | 0 | 3883.09 | 76 | 85.6
NHT-001870 - Curation | 23-PC-35533 | In progress |  |  | 2192 | 1577.86 | 1577.86 | 88.91 | 1112.61 | 0 | 1201.52 | 25 | 21.02
NHT-001871 - Desktop Review | 23-PC-35568 | In progress |  |  | 32122 | 21325.75 | 21325.75 | 886.31 | 11254.88 | 0 | 12141.19 | 326 | 219.88
NHT-001878 - Data Recovery Excavation | 23-PC-35568 | In progress |  |  | 221478 | 147039.29 | 147039.29 | 6111.01 | 77601.44 | 0 | 83712.45 | 2178 | 1479.26
NHT-001884 - Fieldwork | 23-PC-35682 | In progress |  |  | 98467 | 85764.65 | 85764.65 | 13433.7 | 68479.08 | 0 | 81912.78 | 0 | 1233.36
NHT-001889 - Curation | 23-PC-35682 | In progress |  |  | 19924 | 17353.67 | 17353.67 | 2718.18 | 13856.1 | 0 | 16574.28 | 0 | 308.99
NHT-001891 - Reporting | 23-PC-35682 | In progress |  |  | 96196 | 83786.84 | 83786.84 | 13123.9 | 66899.89 | 0 | 80023.79 | 0 | 1028.57
NHT-001893 - Background Research | 23-PC-35682 | In progress |  |  | 41198 | 35883.31 | 35883.31 | 5620.56 | 28651.16 | 0 | 34271.72 | 0 | 522.95
NHT-001898 - Project Management | 23-PC-35682 | In progress |  |  | 34615 | 30149.93 | 30149.93 | 4722.52 | 24073.31 | 0 | 28795.83 | 0 | 491.51
NHT-001900 - Fieldwork | 23-PC-35715 | On hold |  |  | 22039 | 16740.79 | 16740.79 | 2914.56 | 11030.74 | 0 | 13945.3 | 336 | 238.28
NHT-001904 - Survey | 23-PC-35715 | On hold |  |  | 11713 | 8897.28 | 8897.28 | 1549.02 | 5862.55 | 0 | 7411.57 | 145 | 123.41
NHT-001907 - Testing | 23-PC-35715 | On hold |  |  | 10748 | 8164.13 | 8164.13 | 1421.38 | 5379.47 | 0 | 6800.85 | 127 | 103.49
NHT-001908 - Reporting | 23-PC-36063 | In progress |  |  | 114600 | 77893.62 | 77893.62 | 9266.02 | 62011.05 | 0 | 71277.07 | 1250 | 1265.51
NHT-001910 - Background Research | 23-PC-36108 | On hold |  |  | 50200 | 40154.98 | 40154.98 | 3899.82 | 22450.31 | 0 | 26350.13 | 555 | 468.12
NHT-001916 - Agency Consultation | 23-PC-36231 | Completed |  |  | 35624 | 20667.98 | 24357.61 | 5020.93 | 26359.87 | 0 | 31380.8 | 272 | 454.8
NHT-001917 - Final Report | 23-PC-36231 | Completed |  |  | 67249 | 39015.65 | 45980.68 | 9478.17 | 49760.41 | 0 | 59238.58 | 522 | 702.68
NHT-001922 - Monitoring | 23-PC-36231 | Completed |  |  | 220548 | 127955.94 | 150798.52 | 31084.67 | 163194.54 | 0 | 194279.21 | 1782 | 2301.32
NHT-001925 - Background Research | 23-PC-36231 | Completed |  |  | 53699 | 31154.59 | 36716.28 | 7568.47 | 39734.45 | 0 | 47302.92 | 501 | 635.82
NHT-001931 - Prefield | 23-PC-36231 | Completed |  |  | 59380 | 34450.44 | 40600.5 | 8369.14 | 43937.97 | 0 | 52307.11 | 500 | 757.89
NHT-001937 - Agency Consultation | 23-PC-36385 | In progress |  |  | 76346 | 40395.87 | 50911.79 | 3391.49 | 32688.18 | 0 | 36079.67 | 577 | 600.95
NHT-001940 - Curation | 23-PC-36385 | In progress |  |  | 60473 | 31997.4 | 40327.01 | 2686.38 | 25892.17 | 0 | 28578.55 | 370 | 381.46
NHT-001943 - Reporting | 23-PC-36385 | In progress |  |  | 144343 | 76374.72 | 96256.71 | 6412.14 | 61802.12 | 0 | 68214.26 | 945 | 955.46
NHT-001950 - Project Management | 23-PC-36385 | In progress |  |  | 111738 | 59122.29 | 74513.1 | 4963.69 | 47841.53 | 0 | 52805.22 | 613 | 833.87
NHT-001954 - Agency Consultation | 23-PC-36422 | Completed |  |  | 7028 | 4545.78 | 5070.92 | 949.05 | 4237.01 | 0 | 5186.06 | 47 | 80.09
NHT-001955 - Lab Analysis | 23-PC-36422 | Completed |  |  | 17324 | 11204.28 | 12498.63 | 2339.18 | 10443.22 | 0 | 12782.4 | 115 | 169.46
NHT-001959 - Prefield | 23-PC-36422 | In progress |  |  | 11889 | 7689.61 | 8577.95 | 1605.41 | 7167.31 | 0 | 8772.72 | 113 | 133.07
NHT-001960 - Project Management | 23-PC-36422 | In progress |  |  | 14459 | 9351.26 | 10431.56 | 1952.32 | 8716.09 | 0 | 10668.41 | 90 | 140.97
NHT-001963 - Final Report | 23-PC-36426 | Completed |  |  | 45805 | 31655.97 | 31655.97 | 6454.25 | 24280.28 | 0 | 30734.53 | 416 | 314.77
NHT-001969 - Project Management | 23-PC-36426 | Completed |  |  | 30495 | 21074.96 | 21074.96 | 4296.91 | 16164.58 | 0 | 20461.49 | 169 | 261.1
NHT-001976 - Curation | 23-PC-36530 | In progress |  |  | 11908 | 7566.35 | 8677.44 | 515.85 | 7672.2 | 0 | 8188.05 | 124 | 123.41
NHT-001977 - Agency Consultation | 23-PC-36530 | In progress |  |  | 17748 | 11277.63 | 12933.7 | 768.87 | 11435.4 | 0 | 12204.27 | 162 | 166.27
NHT-001984 - Background Research | 23-PC-36530 | In progress |  |  | 21204 | 13473.51 | 15452.04 | 918.58 | 13662 | 0 | 14580.58 | 239 | 248.66
NHT-001986 - Testing | 23-PC-36530 | In progress |  |  | 61863 | 39308.61 | 45080.93 | 2679.92 | 39858.53 | 0 | 42538.45 | 692 | 617.51
NHT-001991 - Prefield | 23-PC-36530 | In progress |  |  | 28377 | 18031.35 | 20679.18 | 1229.31 | 18283.6 | 0 | 19512.91 | 263 | 293.53
NHT-001997 - Reporting | 23-PC-36687 | In progress |  |  | 41483 | 31270.16 | 31270.16 | 5005.43 | 21478.34 | 0 | 26483.77 | 298 | 380.3
NHT-002001 - Fieldwork | 23-PC-36687 | In progress |  |  | 97161 | 73240.02 | 73240.02 | 11723.57 | 50305.92 | 0 | 62029.49 | 607 | 816.18
NHT-002004 - Site Recordation | 23-PC-36687 | In progress |  |  | 41470 | 31259.95 | 31259.95 | 5003.8 | 21471.32 | 0 | 26475.12 | 270 | 363.03
NHT-002006 - Background Research | 23-PC-36687 | In progress |  |  | 20886 | 15743.67 | 15743.67 | 2520.1 | 10813.76 | 0 | 13333.86 | 115 | 169.6
NHT-002009 - Site Recordation | 23-PC-36734 | In progress |  |  | 38600 | 27753.4 | 27753.4 | 3574.21 | 22505.03 | 0 | 26079.24 | 337 | 473.27
OVHD-Non-Posting - Overhead Non-Posting | 23-PC-36734 | In progress |  |  | 0 | 0 | 0 | 0 | 9.9 | 0 | 9.9 | 0 | 0.25
NHT-002012 - Reporting | 23-PC-36776 | In progress |  |  | 145772 | 85627.81 | 107923 | 5685.52 | 62814.79 | 0 | 68500.31 | 1272 | 939.2
NHT-002017 - Draft Report | 23-PC-36776 | In progress |  |  | 232116 | 136347.26 | 171848.42 | 9053.2 | 100021.52 | 0 | 109074.72 | 2513 | 1605.3
NHT-002019 - Project Management | 23-PC-36776 | In progress |  |  | 79412 | 46647.65 | 58793.44 | 3097.32 | 34219.75 | 0 | 37317.07 | 769 | 578.11
NHT-002025 - Agency Consultation | 23-PC-37105 | In progress |  |  | 83320 | 54912.56 | 60283.3 | 7275.93 | 31070.2 | 0 | 38346.13 | 426 | 327.33
NHT-002030 - GIS & Mapping | 23-PC-37105 | Completed |  |  | 27480 | 18110.6 | 19881.91 | 3887.67 | 16601.43 | 0 | 20489.1 | 157 | 183.38
OVHD-Non-Posting - Overhead Non-Posting | 23-PC-37105 | In progress |  |  | 0 | 0 | 0 | 0 | 1184.1 | 0 | 1184.1 | 0 | 14.25
NHT-002039 - Curation | 23-PC-37245 | In progress |  |  | 3251 | 2338.54 | 2338.54 | 283.25 | 1010.14 | 0 | 1293.39 | 21 | 16.49
NHT-002043 - GIS & Mapping | 23-PC-37245 | In progress |  |  | 4876 | 3507.81 | 3507.81 | 424.88 | 1515.21 | 0 | 1940.09 | 33 | 19.61
NHT-002048 - Site Recordation | 23-PC-37245 | In progress |  |  | 396986 | 285591.5 | 285591.5 | 35055.36 | 125014.77 | 0 | 160070.13 | 2588 | 1969.76
NHT-002050 - Final Report | 23-PC-37245 | In progress |  |  | 4334 | 3118.05 | 3118.05 | 377.67 | 1346.85 | 0 | 1724.52 | 33 | 20
NHT-002054 - Data Recovery Excavation | 23-PC-37245 | In progress |  |  | 16253 | 11692.68 | 11692.68 | 1416.27 | 5050.7 | 0 | 6466.97 | 117 | 75.93
NHT-002060 - Site Recordation | 23-PC-37301 | Completed |  |  | 12823 | 9055.57 | 9055.57 | 1758.42 | 7644.88 | 0 | 9403.3 | 95 | 111.8
NHT-002067 - Survey | 23-PC-37301 | Completed |  |  | 26957 | 19036.97 | 19036.97 | 3696.6 | 16071.37 | 0 | 19767.97 | 180 | 259.67
NHT-002070 - Monitoring | 23-PC-37301 | Completed |  |  | 25444 | 17968.78 | 17968.78 | 3489.19 | 15169.58 | 0 | 18658.77 | 149 | 202.95
NHT-002072 - Agency Consultation | 23-PC-37301 | Completed |  |  | 6676 | 4714.46 | 4714.46 | 915.46 | 3980.03 | 0 | 4895.49 | 42 | 63.46
NHT-002076 - Site Recordation | 23-PC-37568 | In progress |  |  | 11461 | 9032.52 | 9032.52 | 1036.06 | 5439.29 | 0 | 6475.35 | 125 | 88.13
NHT-002083 - Survey | 23-PC-37568 | In progress |  |  | 22783 | 17954.96 | 17954.96 | 2059.48 | 10812.3 | 0 | 12871.78 | 296 | 194.88
NHT-002084 - Prefield | 23-PC-37568 | In progress |  |  | 10256 | 8082.97 | 8082.97 | 927.14 | 4867.48 | 0 | 5794.62 | 103 | 84.64
NHT-002090 - Project Management | 23-PC-37590 | In progress |  |  | 15404 | 12002.96 | 12002.96 | 1247.35 | 6090 | 0 | 7337.35 | 143 | 98.58
NHT-002091 - Lab Analysis | 23-PC-37590 | In progress |  |  | 20825 | 16226.38 | 16226.38 | 1686.25 | 8232.85 | 0 | 9919.1 | 160 | 161.26
NHT-002095 - Final Report | 23-PC-37590 | In progress |  |  | 10271 | 8003.46 | 8003.46 | 831.72 | 4060.76 | 0 | 4892.48 | 84 | 65.79
NHT-002097 - Desktop Review | 23-PC-37642 | Completed |  |  | 32888 | 21285.33 | 21285.33 | 1700.99 | 18310.63 | 0 | 20011.62 | 250 | 359.61
NHT-002101 - Fieldwork | 23-PC-37642 | Completed |  |  | 218785 | 141597.57 | 141597.57 | 11315.57 | 121808.77 | 0 | 133124.34 | 1782 | 1828.21
NHT-002105 - Background Research | 23-PC-37642 | Completed |  |  | 34827 | 22539.9 | 22539.9 | 1801.24 | 19389.86 | 0 | 21191.1 | 231 | 307.05
NHT-002107 - Background Research | 23-PC-37648 | Completed |  |  | 15663 | 10525.6 | 10525.6 | 870.8 | 8295.55 | 0 | 9166.35 | 149 | 153.27
NHT-002111 - Site Recordation | 23-PC-37648 | Completed |  |  | 33437 | 22469.6 | 22469.6 | 1858.96 | 17708.98 | 0 | 19567.94 | 240 | 371.95
NHT-002114 - Survey | 23-PC-37740 | Completed |  |  | 12909 | 7642.13 | 7642.13 | 534.95 | 4814.54 | 0 | 5349.49 | 144 | 88.57
NHT-002121 - Data Recovery Excavation | 23-PC-37740 | Completed |  |  | 13499 | 7991.49 | 7991.49 | 559.41 | 5034.64 | 0 | 5594.05 | 181 | 88.1
NHT-002122 - Draft Report | 23-PC-37740 | Completed |  |  | 7492 | 4435.18 | 4435.18 | 310.46 | 2794.16 | 0 | 3104.62 | 99 | 52.74
NHT-002128 - Lab Analysis | 23-PC-37763 | In progress |  |  | 17340 | 12413.95 | 12413.95 | 1575.66 | 5927.47 | 0 | 7503.13 | 192 | 93.31
NHT-002131 - GIS & Mapping | 23-PC-37763 | In progress |  |  | 17660 | 12642.55 | 12642.55 | 1604.67 | 6036.62 | 0 | 7641.29 | 188 | 104.31
NHT-002132 - GIS & Mapping | 23-PC-38089 | In progress |  |  | 15058 | 9951.77 | 11488.74 | 760.45 | 7079.28 | 0 | 7839.73 | 281 | 156.33
NHT-002138 - Reporting | 23-PC-38089 | In progress |  |  | 45197 | 29869.9 | 34483.07 | 2282.48 | 21248.22 | 0 | 23530.7 | 923 | 445.65
NHT-002142 - Fieldwork | 23-PC-38089 | In progress |  |  | 49845 | 32942.25 | 38029.94 | 2517.25 | 23433.76 | 0 | 25951.01 | 780 | 566.27
NHT-002148 - Desktop Review | 23-PC-38159 | Completed |  |  | 3444 | 2289.35 | 2289.35 | 273.12 | 2485.69 | 0 | 2758.81 | 0 | 38.57
NHT-002150 - Agency Consultation | 23-PC-38159 | Completed |  |  | 2342 | 1557.52 | 1557.52 | 185.82 | 1691.11 | 0 | 1876.93 | 0 | 38.28
NHT-002153 - Prefield | 23-PC-38159 | Completed |  |  | 2214 | 1472.33 | 1472.33 | 175.65 | 1598.6 | 0 | 1774.25 | 0 | 40.12
NHT-002156 - GIS & Mapping | 23-PC-38231 | In progress |  |  | 128200 | 90073.32 | 90073.32 | 9289.23 | 64434.85 | 0 | 73724.08 | 1080 | 1573.7
NHT-002161 - Fieldwork | 23-PC-38246 | In progress |  |  | 37244 | 24938.09 | 24938.09 | 2588.37 | 15512.16 | 0 | 18100.53 | 310 | 260.61
NHT-002162 - Prefield | 23-PC-38246 | In progress |  |  | 6424 | 4301.84 | 4301.84 | 446.5 | 2675.86 | 0 | 3122.36 | 58 | 50.91
NHT-002168 - Curation | 23-PC-38246 | In progress |  |  | 6916 | 4631.24 | 4631.24 | 480.69 | 2880.76 | 0 | 3361.45 | 59 | 51.28
NHT-002171 - Data Recovery Excavation | 23-PC-38246 | In progress |  |  | 29216 | 19562.91 | 19562.91 | 2030.48 | 12168.66 | 0 | 14199.14 | 233 | 264.91
NHT-002176 - Site Recordation | 23-PC-38498 | In progress |  |  | 7575 | 5000.24 | 5000.24 | 639.1 | 3538 | 0 | 4177.1 | 83 | 64.2
NHT-002183 - Data Recovery Excavation | 23-PC-38498 | In progress |  |  | 42610 | 28126.42 | 28126.42 | 3594.91 | 19901.29 | 0 | 23496.2 | 395 | 479.19
NHT-002186 - Agency Consultation | 23-PC-38498 | In progress |  |  | 5541 | 3657.83 | 3657.83 | 467.52 | 2588.16 | 0 | 3055.68 | 50 | 56.19
NHT-002187 - GIS & Mapping | 23-PC-38498 | In progress |  |  | 11974 | 7904.28 | 7904.28 | 1010.27 | 5592.8 | 0 | 6603.07 | 154 | 98.63
NHT-002193 - Reporting | 23-PC-38520 | In progress |  |  | 73916 | 48318.78 | 48318.78 | 4980.31 | 22998.95 | 0 | 27979.26 | 550 | 528.72
NHT-002196 - Testing | 23-PC-38520 | In progress |  |  | 74584 | 48755.67 | 48755.67 | 5025.33 | 23206.89 | 0 | 28232.22 | 530 | 477.09
NHT-002203 - Reporting | 23-PC-38666 | In progress |  |  | 71977 | 44978.21 | 44978.21 | 1934.46 | 22552.32 | 0 | 24486.78 | 612 | 532.76
NHT-002204 - Survey | 23-PC-38666 | In progress |  |  | 95619 | 59752.37 | 59752.37 | 2569.87 | 29960.16 | 0 | 32530.03 | 657 | 591.49
NHT-002207 - Project Management | 23-PC-38666 | In progress |  |  | 53293 | 33302.63 | 33302.63 | 1432.3 | 16698.12 | 0 | 18130.42 | 475 | 363.06
NHT-002214 - Monitoring | 23-PC-38666 | In progress |  |  | 147806 | 92364.33 | 92364.33 | 3972.47 | 46311.97 | 0 | 50284.44 | 1277 | 931.25
NHT-002215 - Prefield | 23-PC-38666 | In progress |  |  | 21605 | 13500.93 | 13500.93 | 580.66 | 6769.44 | 0 | 7350.1 | 220 | 130.29
NHT-002219 - Reporting | 23-PC-38759 | Completed |  |  | 43025 | 30255.18 | 30255.18 | 5469.64 | 27679.69 | 0 | 33149.33 | 525 | 630.16
NHT-002226 - Agency Consultation | 23-PC-38759 | Completed |  |  | 9375 | 6592.5 | 6592.5 | 1191.81 | 6031.3 | 0 | 7223.11 | 101 | 127.71
NHT-002227 - Fieldwork | 23-PC-38849 | In progress |  |  | 109400 | 83089.3 | 83089.3 | 11954.73 | 54093.51 | 0 | 66048.24 | 1032 | 997.41
NHT-002232 - Agency Consultation | 23-PC-39011 | Completed |  |  | 92770 | 69651.78 | 69651.78 | 9926.29 | 59006.27 | 0 | 68932.56 | 1392 | 1123.6
NHT-002233 - Prefield | 23-PC-39011 | Completed |  |  | 96530 | 72474.66 | 72474.66 | 10328.58 | 61397.71 | 0 | 71726.29 | 911 | 982.63
NHT-002235 - Final Report | 23-PC-39063 | Completed |  |  | 24200 | 17235.24 | 17235.24 | 1291.17 | 11005.66 | 0 | 12296.83 | 0 | 250.6
NHT-002238 - Background Research | 23-PC-39111 | Completed |  |  | 177806 | 120587.87 | 120587.87 | 18170.6 | 107143.89 | 0 | 125314.49 | 1023 | 2099.57
NHT-002239 - Project Management | 23-PC-39111 | Completed |  |  | 236694 | 160526.03 | 160526.03 | 24188.63 | 142629.48 | 0 | 166818.11 | 1713 | 3478.35
NHT-002241 - Survey | 23-PC-39135 | In progress |  |  | 13031 | 8537.7 | 8537.7 | 778.54 | 5602.93 | 0 | 6381.47 | 111 | 118.51
NHT-002246 - Monitoring | 23-PC-39135 | In progress |  |  | 14769 | 9676.86 | 9676.86 | 882.42 | 6350.5 | 0 | 7232.92 | 121 | 117.96
NHT-002252 - Fieldwork | 23-PC-39280 | Completed |  |  | 87249 | 59913.64 | 59913.64 | 6193 | 46738.57 | 0 | 52931.57 | 1202 | 787.29
NHT-002254 - Reporting | 23-PC-39280 | Completed |  |  | 35451 | 24344.45 | 24344.45 | 2516.37 | 18991.09 | 0 | 21507.46 | 503 | 386.48
NHT-002261 - Site Recordation | 23-PC-39323 | In progress |  |  | 116204 | 93915.86 | 93915.86 | 7795.18 | 64382.45 | 0 | 72177.63 | 1582 | 1255.58
NHT-002262 - Project Management | 23-PC-39323 | In progress |  |  | 146402 | 118322.3 | 118322.3 | 9820.96 | 81113.88 | 0 | 90934.84 | 1744 | 1283.42
NHT-002268 - Data Recovery Excavation | 23-PC-39323 | In progress |  |  | 220588 | 178278.91 | 178278.91 | 14797.47 | 122216.13 | 0 | 137013.6 | 2263 | 2597.16
NHT-002272 - Agency Consultation | 23-PC-39323 | In progress |  |  | 67406 | 54477.85 | 54477.85 | 4521.76 | 37346.38 | 0 | 41868.14 | 763 | 704.97
NHT-002273 - Final Report | 23-PC-39502 | Completed |  |  | 352700 | 238918.98 | 238918.98 | 21431.03 | 289163.64 | 0 | 310594.67 | 3268 | 6065.13
NHT-002280 - GIS & Mapping | 23-PC-39608 | Completed |  |  | 23524 | 16671.15 | 16671.15 | 2875.75 | 11290.52 | 0 | 14166.27 | 0 | 207.78
NHT-002281 - Survey | 23-PC-39608 | Completed |  |  | 41908 | 29700.54 | 29700.54 | 5123.31 | 20114.67 | 0 | 25237.98 | 0 | 334.24
NHT-002287 - Project Management | 23-PC-39608 | Completed |  |  | 24622 | 17449.65 | 17449.65 | 3010.04 | 11817.76 | 0 | 14827.8 | 0 | 214.78
NHT-002291 - Prefield | 23-PC-39608 | Completed |  |  | 12584 | 8918.51 | 8918.51 | 1538.43 | 6040.05 | 0 | 7578.48 | 0 | 129.16
NHT-002298 - Data Recovery Excavation | 23-PC-39608 | Completed |  |  | 64062 | 45400.44 | 45400.44 | 7831.53 | 30747.41 | 0 | 38578.94 | 0 | 686.38
NHT-002305 - Agency Consultation | 23-PC-39840 | In progress |  |  | 237700 | 132634.88 | 173575 | 16597.03 | 72157.13 | 0 | 88754.16 | 1867 | 1039.6
NHT-002306 - Lab Analysis | 23-PC-39856 | Completed |  |  | 91300 | 62922.2 | 72285.79 | 3143.98 | 33843.97 | 0 | 36987.95 | 1044 | 691.46
NHT-002307 - Final Report | 23-PC-39857 | In progress |  |  | 11266 | 6891.93 | 9495.59 | 333.24 | 5220.73 | 0 | 5553.97 | 0 | 107.48
NHT-002312 - Project Management | 23-PC-39857 | In progress |  |  | 13126 | 8029.72 | 11063.23 | 388.25 | 6082.63 | 0 | 6470.88 | 0 | 117.92
NHT-002318 - Monitoring | 23-PC-39857 | In progress |  |  | 44608 | 27288.87 | 37598.2 | 1319.47 | 20671.68 | 0 | 21991.15 | 0 | 367.28
NHT-002325 - Project Management | 23-PC-39918 | Completed |  |  | 11528 | 7874.61 | 7874.61 | 1287.01 | 6466.04 | 0 | 7753.05 | 85 | 110.55
NHT-002327 - Background Research | 23-PC-39918 | Completed |  |  | 10811 | 7384.82 | 7384.82 | 1206.95 | 6063.86 | 0 | 7270.81 | 107 | 100.3
NHT-002329 - Agency Consultation | 23-PC-39918 | Completed |  |  | 8438 | 5763.91 | 5763.91 | 942.04 | 4732.89 | 0 | 5674.93 | 90 | 91.26
NHT-002332 - Reporting | 23-PC-39918 | Completed |  |  | 23541 | 16081.18 | 16081.18 | 2628.27 | 13204.68 | 0 | 15832.95 | 220 | 272.6
NHT-002335 - Site Recordation | 23-PC-39918 | Completed |  |  | 20982 | 14332.91 | 14332.91 | 2342.53 | 11769.12 | 0 | 14111.65 | 209 | 238.74
NHT-002342 - Fieldwork | 23-PC-39996 | On hold |  |  | 304175 | 208420.45 | 208420.45 | 17173.99 | 118054.33 | 0 | 135228.32 | 3611 | 2311.08
NHT-002348 - Draft Report | 23-PC-39996 | On hold |  |  | 216784 | 148540.41 | 148540.41 | 12239.84 | 84136.84 | 0 | 96376.68 | 1995 | 1608.73
NHT-002353 - Prefield | 23-PC-39996 | On hold |  |  | 90941 | 62313.02 | 62313.02 | 5134.64 | 35295.58 | 0 | 40430.22 | 1009 | 610.43
NHT-002359 - Final Report | 23-PC-40028 | In progress |  |  | 16589 | 11551.21 | 11551.21 | 1057.3 | 6716.95 | 0 | 7774.25 | 0 | 139.51
NHT-002365 - Survey | 23-PC-40028 | In progress |  |  | 44604 | 31057.31 | 31057.31 | 2842.72 | 18059.64 | 0 | 20902.36 | 0 | 359.61
NHT-002366 - GIS & Mapping | 23-PC-40028 | In progress |  |  | 11377 | 7922.04 | 7922.04 | 725.11 | 4606.61 | 0 | 5331.72 | 0 | 93.21
NHT-002373 - Reporting | 23-PC-40028 | In progress |  |  | 28330 | 19726.11 | 19726.11 | 1805.56 | 11470.6 | 0 | 13276.16 | 0 | 250.41
NHT-002375 - Curation | 23-PC-40052 | In progress |  |  | 2589 | 1737.72 | 1737.72 | 312.53 | 1134.58 | 0 | 1447.11 | 27 | 28.76
NHT-002378 - Draft Report | 23-PC-40052 | In progress |  |  | 57630 | 38674.77 | 38674.77 | 7519.18 | 27296.6 | 0 | 34815.78 | 684 | 714.54
NHT-002384 - Survey | 23-PC-40052 | In progress |  |  | 11373 | 7632.41 | 7632.41 | 1568.56 | 5694.3 | 0 | 7262.86 | 156 | 149.16
NHT-002391 - Reporting | 23-PC-40052 | In progress |  |  | 26433 | 17739.38 | 17739.38 | 2907.77 | 10555.99 | 0 | 13463.76 | 278 | 265.97
NHT-002394 - Desktop Review | 23-PC-40052 | In progress |  |  | 21475 | 14412.17 | 14412.17 | 2834.5 | 10289.98 | 0 | 13124.48 | 229 | 287.91
OVHD-Non-Posting - Overhead Non-Posting | 23-PC-40052 | In progress |  |  | 0 | 0 | 0 | 0 | 316.41 | 0 | 316.41 | 0 | 8
NHT-002401 - Reporting | 23-PC-40150 | In progress |  |  | 37126 | 23730.36 | 23730.36 | 3176.51 | 12673.44 | 0 | 15849.95 | 439 | 264.26
NHT-002402 - Testing | 23-PC-40150 | In progress |  |  | 12894 | 8241.63 | 8241.63 | 925.65 | 3693.1 | 0 | 4618.75 | 155 | 91.88
NHT-002408 - Background Research | 23-PC-40150 | In progress |  |  | 35246 | 22529.5 | 22529.5 | 3055.38 | 12190.15 | 0 | 15245.53 | 435 | 267.17
NHT-002415 - Curation | 23-PC-40150 | In progress |  |  | 1272 | 813.34 | 813.34 | 93.6 | 373.45 | 0 | 467.05 | 17 | 6.45
NHT-002417 - Survey | 23-PC-40150 | In progress |  |  | 28162 | 18001.41 | 18001.41 | 2321.01 | 9260.21 | 0 | 11581.22 | 342 | 227.92
OVHD-Non-Posting - Overhead Non-Posting | 23-PC-40150 | In progress |  |  | 0 | 0 | 0 | 0 | 98.28 | 0 | 98.28 | 0 | 2.5
NHT-002425 - Site Recordation | 23-PC-40387 | Completed |  |  | 49500 | 33204.45 | 33204.45 | 2297.86 | 16537.07 | 0 | 18834.93 | 510 | 301.43
NHT-002429 - Testing | 23-PC-40387 | Completed |  |  | 70993 | 47622.37 | 47622.37 | 3295.63 | 23717.75 | 0 | 27013.38 | 765 | 457.3
NHT-002430 - Agency Consultation | 23-PC-40387 | Completed |  |  | 24507 | 16439.18 | 16439.18 | 1137.65 | 8187.33 | 0 | 9324.98 | 272 | 177.28
NHT-002432 - Fieldwork | 23-PC-40402 | In progress |  |  | 296067 | 217905.37 | 217905.37 | 38807.49 | 137590.18 | 0 | 176397.67 | 2718 | 2712.91
NHT-002438 - Draft Report | 23-PC-40402 | In progress |  |  | 115533 | 85032.23 | 85032.23 | 15143.67 | 53691.2 | 0 | 68834.87 | 1191 | 1102.84
NHT-002443 - Monitoring | 23-PC-40406 | In progress |  |  | 30832 | 17660.77 | 20844.49 | 1865.02 | 15245.24 | 0 | 17110.26 | 0 | 235.79
NHT-002448 - Testing | 23-PC-40406 | In progress |  |  | 11807 | 6762.95 | 7982.11 | 714.18 | 5837.95 | 0 | 6552.13 | 0 | 97.94
NHT-002449 - Desktop Review | 23-PC-40406 | In progress |  |  | 3215 | 1841.58 | 2173.57 | 194.48 | 1589.7 | 0 | 1784.18 | 0 | 31.95
NHT-002452 - Draft Report | 23-PC-40406 | In progress |  |  | 9252 | 5299.32 | 6254.63 | 559.62 | 4574.51 | 0 | 5134.13 | 0 | 84.11
NHT-002458 - GIS & Mapping | 23-PC-40406 | In progress |  |  | 4994 | 2860.65 | 3376.34 | 302.09 | 2469.39 | 0 | 2771.48 | 0 | 43.09
NHT-002461 - Reporting | 23-PC-40469 | In progress |  |  | 10105 | 7669.89 | 7669.89 | 1172.88 | 4307.87 | 0 | 5480.75 | 99 | 83.01
NHT-002468 - Draft Report | 23-PC-40469 | In progress |  |  | 9817 | 7451.21 | 7451.21 | 1139.44 | 4185.05 | 0 | 5324.49 | 100 | 89.88
NHT-002471 - Lab Analysis | 23-PC-40469 | In progress |  |  | 8050 | 6110.28 | 6110.28 | 934.39 | 3431.9 | 0 | 4366.29 | 91 | 66.64
NHT-002475 - Monitoring | 23-PC-40469 | In progress |  |  | 7763 | 5892.38 | 5892.38 | 901.07 | 3309.52 | 0 | 4210.59 | 65 | 63.42
NHT-002479 - Fieldwork | 23-PC-40469 | In progress |  |  | 18165 | 13786.34 | 13786.34 | 2108.2 | 7743.23 | 0 | 9851.43 | 167 | 140.2
NHT-002483 - Curation | 23-PC-40493 | In progress |  |  | 84700 | 57130.15 | 57130.15 | 5269.47 | 30822.78 | 0 | 36092.25 | 681 | 605.4
NHT-002484 - Survey | 23-PC-40519 | In progress |  |  | 194700 | 136847.52 | 157875.18 | 17622.46 | 96070.85 | 0 | 113693.31 | 1257 | 1697.63
NHT-002491 - Project Management | 23-PC-40537 | Completed |  |  | 15951 | 11492.99 | 12249.33 | 2043.75 | 11141.71 | 0 | 13185.46 | 121 | 208.52
NHT-002497 - Fieldwork | 23-PC-40537 | Completed |  |  | 37151 | 26767.89 | 28529.44 | 4760.01 | 25949.74 | 0 | 30709.75 | 309 | 468.12
NHT-002503 - Testing | 23-PC-40537 | Completed |  |  | 23398 | 16858.72 | 17968.17 | 2997.91 | 16343.44 | 0 | 19341.35 | 203 | 282.25
NHT-002507 - Reporting | 23-PC-40627 | In progress |  |  | 15854 | 8510.44 | 8510.44 | 558.78 | 4712.73 | 0 | 5271.51 | 0 | 92.05
NHT-002510 - Survey | 23-PC-40627 | In progress |  |  | 26568 | 14262.01 | 14262.01 | 936.42 | 7897.69 | 0 | 8834.11 | 0 | 124.35
NHT-002512 - Desktop Review | 23-PC-40627 | In progress |  |  | 7028 | 3772.52 | 3772.52 | 247.7 | 2089.07 | 0 | 2336.77 | 0 | 35.34
NHT-002516 - Draft Report | 23-PC-40627 | In progress |  |  | 11670 | 6264.47 | 6264.47 | 411.31 | 3469 | 0 | 3880.31 | 0 | 63.5
NHT-002523 - Project Management | 23-PC-40627 | In progress |  |  | 10180 | 5464.4 | 5464.4 | 358.78 | 3025.96 | 0 | 3384.74 | 0 | 52.68
NHT-002524 - Survey | 23-PC-40688 | On hold |  |  | 16309 | 10116.17 | 10116.17 | 1354.78 | 5522.26 | 0 | 6877.04 | 160 | 95.17
NHT-002529 - Project Management | 23-PC-40688 | On hold |  |  | 6292 | 3902.88 | 3902.88 | 522.68 | 2130.52 | 0 | 2653.2 | 60 | 43.1
NHT-002531 - Reporting | 23-PC-40688 | On hold |  |  | 18954 | 11757.33 | 11757.33 | 1574.56 | 6418.14 | 0 | 7992.7 | 168 | 135.66
NHT-002536 - Prefield | 23-PC-40688 | On hold |  |  | 4130 | 2561.54 | 2561.54 | 343.04 | 1398.3 | 0 | 1741.34 | 40 | 27.83
NHT-002543 - Data Recovery Excavation | 23-PC-40688 | On hold |  |  | 24815 | 15393.23 | 15393.23 | 2061.49 | 8402.92 | 0 | 10464.41 | 283 | 163.11
NHT-002545 - GIS & Mapping | 23-PC-40963 | On hold |  |  | 19197 | 11481.6 | 11481.6 | 1226.84 | 6791.73 | 0 | 8018.57 | 108 | 130.4
NHT-002546 - Site Recordation | 23-PC-40963 | On hold |  |  | 38803 | 23208.2 | 23208.2 | 2479.86 | 13728.38 | 0 | 16208.24 | 226 | 321.43
NHT-002552 - Site Recordation | 23-PC-41134 | In progress |  |  | 9550 | 7245.9 | 7245.9 | 1740.63 | 6393.15 | 0 | 8133.78 | 117 | 147.76
NHT-002559 - Lab Analysis | 23-PC-41134 | Completed |  |  | 6497 | 4929.36 | 4929.36 | 1184.14 | 4349.23 | 0 | 5533.37 | 80 | 73.31
NHT-002562 - Monitoring | 23-PC-41134 | In progress |  |  | 20674 | 15685.32 | 15685.32 | 3767.97 | 13839.38 | 0 | 17607.35 | 223 | 289.72
NHT-002569 - Data Recovery Excavation | 23-PC-41134 | In progress |  |  | 19579 | 14854.23 | 14854.23 | 3568.32 | 13106.07 | 0 | 16674.39 | 256 | 246.2
NHT-002571 - Draft Report | 23-PC-41207 | In progress |  |  | 16549 | 14562.88 | 14562.88 | 1181.99 | 9762.39 | 0 | 10944.38 | 253 | 190.81
NHT-002577 - Lab Analysis | 23-PC-41207 | In progress |  |  | 16551 | 14565.12 | 14565.12 | 1182.18 | 9763.9 | 0 | 10946.08 | 243 | 180.67
NHT-002579 - Data Recovery Excavation | 23-PC-41285 | Completed |  |  | 197551 | 124930.99 | 124930.99 | 11397.58 | 118120.31 | 0 | 129517.89 | 2319 | 2184.41
NHT-002586 - Draft Report | 23-PC-41285 | Completed |  |  | 114884 | 72652.8 | 72652.8 | 6628.18 | 68692.1 | 0 | 75320.28 | 1674 | 1173.16
NHT-002587 - Agency Consultation | 23-PC-41285 | Completed |  |  | 37165 | 23503.25 | 23503.25 | 2144.22 | 22221.96 | 0 | 24366.18 | 281 | 479.94
NHT-002593 - Survey | 23-PC-41314 | In progress |  |  | 38800 | 22168.08 | 29503.45 | 3789.99 | 17622.37 | 0 | 21412.36 | 0 | 392.97
NHT-002596 - Site Recordation | 23-PC-41361 | Completed |  |  | 84750 | 63604.68 | 63604.68 | 6881.65 | 64063.17 | 0 | 70944.82 | 768 | 1247.92
NHT-002600 - Fieldwork | 23-PC-41361 | Completed |  |  | 127081 | 95374.82 | 95374.82 | 10318.98 | 96062.32 | 0 | 106381.3 | 1406 | 1746.81
NHT-002603 - Agency Consultation | 23-PC-41361 | Completed |  |  | 28869 | 21665.85 | 21665.85 | 2344.12 | 21822.02 | 0 | 24166.14 | 299 | 502.38
NHT-002609 - Background Research | 23-PC-41378 | In progress |  |  | 30869 | 12168.73 | 16473.93 | 1621.41 | 7591.16 | 0 | 9212.57 | 0 | 158.22
NHT-002615 - Desktop Review | 23-PC-41378 | In progress |  |  | 16849 | 6641.88 | 8991.72 | 884.99 | 4143.37 | 0 | 5028.36 | 0 | 95.83
NHT-002618 - Prefield | 23-PC-41378 | In progress |  |  | 32881 | 12961.99 | 17547.85 | 1727.11 | 8086.02 | 0 | 9813.13 | 0 | 177.21
NHT-002622 - Final Report | 23-PC-41378 | In progress |  |  | 34960 | 13781.48 | 18657.27 | 1836.3 | 8597.24 | 0 | 10433.54 | 0 | 168.28
NHT-002623 - Site Recordation | 23-PC-41378 | In progress |  |  | 55241 | 21776.12 | 29480.33 | 2901.56 | 13584.51 | 0 | 16486.07 | 0 | 328.5
NHT-002628 - Reporting | 23-PC-41424 | Completed |  |  | 56676 | 46417.04 | 46417.04 | 5469.81 | 27088.56 | 0 | 32558.37 | 0 | 545.19
NHT-002631 - GIS & Mapping | 23-PC-41424 | Completed |  |  | 22636 | 18539.25 | 18539.25 | 2184.67 | 10819.34 | 0 | 13004.01 | 0 | 168.15
NHT-002632 - Lab Analysis | 23-PC-41424 | Completed |  |  | 35865 | 29373.84 | 29373.84 | 3461.43 | 17142.31 | 0 | 20603.74 | 0 | 350.4
NHT-002636 - Agency Consultation | 23-PC-41424 | Completed |  |  | 16823 | 13777.87 | 13777.87 | 1623.59 | 8040.64 | 0 | 9664.23 | 0 | 169.87
NHT-002641 - Curation | 23-PC-41429 | In progress |  |  | 177980 | 123447.03 | 123447.03 | 10395.53 | 71459.01 | 0 | 81854.54 | 1831 | 1398.36
NHT-002646 - Monitoring | 23-PC-41429 | In progress |  |  | 761746 | 528346.63 | 528346.63 | 44492.28 | 305840.67 | 0 | 350332.95 | 7550 | 5346.66
NHT-002652 - Testing | 23-PC-41429 | In progress |  |  | 497592 | 345129.85 | 345129.85 | 29063.53 | 199783.14 | 0 | 228846.67 | 4844 | 3694.52
NHT-002654 - Project Management | 23-PC-41429 | In progress |  |  | 195553 | 135635.85 | 135635.85 | 11421.95 | 78514.67 | 0 | 89936.62 | 2039 | 1193.62
NHT-002659 - Final Report | 23-PC-41429 | In progress |  |  | 291329 | 202065.76 | 202065.76 | 17016.04 | 116968.53 | 0 | 133984.57 | 2574 | 2175.07
NHT-002660 - Agency Consultation | 23-PC-41602 | Completed |  |  | 176893 | 104189.96 | 104189.96 | 12358.22 | 84950.59 | 0 | 97308.81 | 1566 | 1587.19
NHT-002664 - Monitoring | 23-PC-41602 | Completed |  |  | 578107 | 340505.04 | 340505.04 | 40388.11 | 277628.54 | 0 | 318016.65 | 5272 | 4430.73
NHT-002665 - GIS & Mapping | 23-PC-41613 | In progress |  |  | 38118 | 26373.67 | 26373.67 | 3730.31 | 18606.89 | 0 | 22337.2 | 285 | 397.31
NHT-002666 - Lab Analysis | 23-PC-41613 | In progress |  |  | 40379 | 27938.15 | 27938.15 | 3951.6 | 19710.65 | 0 | 23662.25 | 402 | 373.25
NHT-002673 - Background Research | 23-PC-41613 | In progress |  |  | 24652 | 17056.92 | 17056.92 | 2412.54 | 12033.83 | 0 | 14446.37 | 276 | 233.44
NHT-002675 - Agency Consultation | 23-PC-41613 | In progress |  |  | 24027 | 16624.22 | 16624.22 | 2351.34 | 11728.56 | 0 | 14079.9 | 162 | 219.9
NHT-002680 - Final Report | 23-PC-41613 | In progress |  |  | 24724 | 17106.65 | 17106.65 | 2419.58 | 12068.91 | 0 | 14488.49 | 269 | 202.64
NHT-002685 - Background Research | 23-PC-41787 | Completed |  |  | 5322 | 3540.16 | 3540.16 | 545.25 | 2500.82 | 0 | 3046.07 | 0 | 37.89
NHT-002687 - Agency Consultation | 23-PC-41787 | Completed |  |  | 5727 | 3809.77 | 3809.77 | 586.77 | 2691.27 | 0 | 3278.04 | 0 | 61.21
NHT-002688 - GIS & Mapping | 23-PC-41787 | Completed |  |  | 11763 | 7824.66 | 7824.66 | 1205.13 | 5527.45 | 0 | 6732.58 | 0 | 89.19
NHT-002690 - Reporting | 23-PC-41787 | Completed |  |  | 25188 | 16755.01 | 16755.01 | 2580.55 | 11835.97 | 0 | 14416.52 | 0 | 197.33
NHT-002694 - Survey | 23-PC-41802 | In progress |  |  | 37952 | 24710.73 | 24710.73 | 3527.47 | 12653.6 | 0 | 16181.07 | 393 | 218.56
NHT-002698 - Testing | 23-PC-41802 | In progress |  |  | 43358 | 28230.3 | 28230.3 | 4029.9 | 14455.87 | 0 | 18485.77 | 398 | 285.03
NHT-002699 - Site Recordation | 23-PC-41802 | In progress |  |  | 21090 | 13731.61 | 13731.61 | 1960.2 | 7031.54 | 0 | 8991.74 | 226 | 119.82
NHT-002705 - Desktop Review | 23-PC-41827 | In progress |  |  | 46143 | 25360.15 | 29630.05 | 3377.58 | 13854.97 | 0 | 17232.55 | 309 | 244.84
NHT-002710 - Project Management | 23-PC-41827 | In progress |  |  | 90230 | 49590.13 | 57939.63 | 6604.64 | 27092.5 | 0 | 33697.14 | 551 | 527.21
NHT-002713 - Site Recordation | 23-PC-41827 | In progress |  |  | 123571 | 67914.06 | 79348.76 | 9045.1 | 37103.38 | 0 | 46148.48 | 631 | 697.3
NHT-002716 - Data Recovery Excavation | 23-PC-41827 | In progress |  |  | 386156 | 212229.65 | 247962.77 | 28265.71 | 115947.08 | 0 | 144212.79 | 2871 | 2344.17
NHT-002723 - Prefield | 23-PC-41897 | In progress |  |  | 18800 | 12705.04 | 12705.04 | 2216.15 | 10520.32 | 0 | 12736.47 | 147 | 200.97
NHT-002730 - Monitoring | 23-PC-41934 | Completed |  |  | 148901 | 93420.08 | 93420.08 | 5939.77 | 47571.67 | 0 | 53511.44 | 1568 | 825.65
NHT-002733 - Prefield | 23-PC-41934 | Completed |  |  | 38590 | 24211.24 | 24211.24 | 1539.38 | 12328.93 | 0 | 13868.31 | 325 | 224.4
NHT-002738 - Testing | 23-PC-41934 | Completed |  |  | 76515 | 48005.77 | 48005.77 | 3052.27 | 24445.65 | 0 | 27497.92 | 699 | 424.13
NHT-002743 - Agency Consultation | 23-PC-41934 | Completed |  |  | 24132 | 15140.46 | 15140.46 | 962.65 | 7709.88 | 0 | 8672.53 | 249 | 130.8
NHT-002750 - Survey | 23-PC-41934 | Completed |  |  | 76562 | 48035.23 | 48035.23 | 3054.14 | 24460.65 | 0 | 27514.79 | 820 | 423.99
NHT-002757 - GIS & Mapping | 23-PC-42054 | Completed |  |  | 15748 | 10771.3 | 10771.3 | 1120.37 | 9449.15 | 0 | 10569.52 | 119 | 196.45
NHT-002760 - Lab Analysis | 23-PC-42054 | Completed |  |  | 19852 | 13579.1 | 13579.1 | 1412.42 | 11912.29 | 0 | 13324.71 | 146 | 172.14
NHT-002763 - Desktop Review | 23-PC-42154 | Completed |  |  | 13131 | 9051.08 | 9051.08 | 828.89 | 4771.74 | 0 | 5600.63 | 78 | 80.37
NHT-002765 - Curation | 23-PC-42154 | Completed |  |  | 16069 | 11076.48 | 11076.48 | 1014.38 | 5839.54 | 0 | 6853.92 | 113 | 117.17
NHT-002769 - Reporting | 23-PC-42199 | Completed |  |  | 78739 | 42632.76 | 57297.66 | 5804.89 | 48446.43 | 0 | 54251.32 | 0 | 841.07
NHT-002773 - Site Recordation | 23-PC-42199 | Completed |  |  | 62031 | 33586.01 | 45138.98 | 4573.08 | 38166 | 0 | 42739.08 | 0 | 542.74
NHT-002777 - Data Recovery Excavation | 23-PC-42199 | Completed |  |  | 129430 | 70079.06 | 94184.99 | 9541.99 | 79635.48 | 0 | 89177.47 | 0 | 1361.83
NHT-002783 - Reporting | 23-PC-42237 | In progress |  |  | 26444 | 15011.59 | 17839.04 | 593.87 | 9141.74 | 0 | 9735.61 | 402 | 178.05
NHT-002790 - Curation | 23-PC-42237 | In progress |  |  | 13042 | 7403.81 | 8798.33 | 292.9 | 4508.77 | 0 | 4801.67 | 199 | 91.06
NHT-002794 - Survey | 23-PC-42237 | In progress |  |  | 42814 | 24304.37 | 28882.14 | 961.51 | 14800.86 | 0 | 15762.37 | 556 | 302.53
NHT-002800 - Reporting | 23-PC-42377 | In progress |  |  | 15094 | 10434.81 | 10434.81 | 913.71 | 5058.27 | 0 | 5971.98 | 0 | 101.81
NHT-002804 - Agency Consultation | 23-PC-42377 | In progress |  |  | 5217 | 3606.75 | 3606.75 | 315.82 | 1748.37 | 0 | 2064.19 | 0 | 40.23
NHT-002807 - Prefield | 23-PC-42377 | In progress |  |  | 7498 | 5183.35 | 5183.35 | 453.88 | 2512.63 | 0 | 2966.51 | 0 | 47.09
NHT-002812 - Data Recovery Excavation | 23-PC-42377 | In progress |  |  | 32988 | 22804.22 | 22804.22 | 1996.84 | 11054.35 | 0 | 13051.19 | 0 | 212.5
NHT-002813 - Lab Analysis | 23-PC-42377 | In progress |  |  | 7503 | 5186.66 | 5186.66 | 454.16 | 2514.23 | 0 | 2968.39 | 0 | 41.92
NHT-002816 - Prefield | 23-PC-42405 | Completed |  |  | 757500 | 494268.75 | 494268.75 | 105699.15 | 531042.7 | 0 | 636741.85 | 8170 | 12394.07
NHT-002819 - Background Research | 23-PC-42451 | In progress |  |  | 38438 | 24538.58 | 27264.36 | 3423.58 | 15284.52 | 0 | 18708.1 | 295 | 273.11
NHT-002820 - Project Management | 23-PC-42451 | In progress |  |  | 63362 | 40450.42 | 44943.7 | 5643.58 | 25195.64 | 0 | 30839.22 | 552 | 567
NHT-002822 - Project Management | 23-PC-42496 | Completed |  |  | 39320 | 22172.32 | 22172.32 | 2940.96 | 17482.36 | 0 | 20423.32 | 280 | 356.55
NHT-002825 - GIS & Mapping | 23-PC-42496 | Completed |  |  | 52851 | 29802.73 | 29802.73 | 3953.06 | 23498.75 | 0 | 27451.81 | 344 | 487.59
NHT-002830 - Site Recordation | 23-PC-42496 | Completed |  |  | 33774 | 19044.93 | 19044.93 | 2526.14 | 15016.48 | 0 | 17542.62 | 196 | 306.56
NHT-002834 - Draft Report | 23-PC-42496 | Completed |  |  | 93419 | 52679.21 | 52679.21 | 6987.42 | 41536.31 | 0 | 48523.73 | 807 | 788.31
NHT-002838 - Curation | 23-PC-42496 | Completed |  |  | 34636 | 19531.41 | 19531.41 | 2590.66 | 15400.06 | 0 | 17990.72 | 180 | 296.05
NHT-002840 - Background Research | 23-PC-42771 | In progress |  |  | 4163 | 3105.66 | 3105.66 | 372.37 | 1984.39 | 0 | 2356.76 | 47 | 28.68
NHT-002843 - Testing | 23-PC-42771 | In progress |  |  | 13527 | 10090.93 | 10090.93 | 1209.9 | 6447.67 | 0 | 7657.57 | 195 | 104.41
NHT-002845 - Project Management | 23-PC-42771 | In progress |  |  | 7510 | 5602.61 | 5602.61 | 671.75 | 3579.84 | 0 | 4251.59 | 85 | 58.01
NHT-002847 - Desktop Review | 23-PC-42907 | In progress |  |  | 776962 | 338257.19 | 463870.52 | 40439.68 | 259113.52 | 0 | 299553.2 | 0 | 4961.19
NHT-002848 - GIS & Mapping | 23-PC-42907 | In progress |  |  | 860238 | 374511.73 | 513588.35 | 44774.03 | 286885.41 | 0 | 331659.44 | 0 | 4910.22
NHT-002850 - Fieldwork | 23-PC-42981 | In progress |  |  | 175800 | 129494.28 | 129494.28 | 12069.2 | 86054.34 | 0 | 98123.54 | 0 | 1463.54
NHT-002853 - GIS & Mapping | 23-PC-43008 | In progress |  |  | 69824 | 46754.34 | 46754.34 | 7339.05 | 26172.58 | 0 | 33511.63 | 580 | 462.96
NHT-002854 - Prefield | 23-PC-43008 | In progress |  |  | 69876 | 46788.78 | 46788.78 | 7344.45 | 26191.85 | 0 | 33536.3 | 438 | 444.01
NHT-002856 - Reporting | 23-PC-43158 | In progress |  |  | 47986 | 34933.79 | 34933.79 | 5329.59 | 26394.16 | 0 | 31723.75 | 509 | 452.95
NHT-002859 - Site Recordation | 23-PC-43158 | In progress |  |  | 25314 | 18428.61 | 18428.61 | 2811.51 | 13923.69 | 0 | 16735.2 | 296 | 287.51
NHT-002860 - Agency Consultation | 23-PC-43209 | In progress |  |  | 42918 | 30935.1 | 30935.1 | 2844.17 | 14289.38 | 0 | 17133.55 | 365 | 268.59
NHT-002862 - GIS & Mapping | 23-PC-43209 | In progress |  |  | 129742 | 93518.34 | 93518.34 | 8598.06 | 43197.48 | 0 | 51795.54 | 963 | 743.2
NHT-002863 - Curation | 23-PC-43209 | In progress |  |  | 74840 | 53944.56 | 53944.56 | 4959.66 | 24917.79 | 0 | 29877.45 | 522 | 456.15
NHT-002867 - Lab Analysis | 23-PC-43238 | In progress |  |  | 79364 | 39826.47 | 50223.25 | 4442.84 | 26844.75 | 0 | 31287.59 | 0 | 491.86
NHT-002871 - Site Recordation | 23-PC-43238 | In progress |  |  | 86827 | 43571.43 | 54945.85 | 4860.61 | 29369.01 | 0 | 34229.62 | 0 | 474.58
NHT-002874 - Draft Report | 23-PC-43238 | In progress |  |  | 96512 | 48431.76 | 61074.97 | 5402.8 | 32645.08 | 0 | 38047.88 | 0 | 534.73
NHT-002876 - GIS & Mapping | 23-PC-43238 | In progress |  |  | 42465 | 21309.64 | 26872.56 | 2377.19 | 14363.61 | 0 | 16740.8 | 0 | 229.89
NHT-002878 - Survey | 23-PC-43238 | In progress |  |  | 149132 | 74837.9 | 94374.5 | 8348.53 | 50443.96 | 0 | 58792.49 | 0 | 784.53
NHT-002880 - Prefield | 23-PC-43356 | Completed |  |  | 14868 | 9807.17 | 9807.17 | 1572.68 | 5575.87 | 0 | 7148.55 | 115 | 82.59
NHT-002885 - Survey | 23-PC-43356 | Completed |  |  | 37822 | 24946.87 | 24946.87 | 4000.49 | 14183.57 | 0 | 18184.06 | 244 | 213.78
NHT-002889 - Project Management | 23-PC-43356 | Completed |  |  | 13810 | 9109.36 | 9109.36 | 1460.78 | 5179.13 | 0 | 6639.91 | 98 | 84.26
NHT-002896 - Site Recordation | 23-PC-43408 | In progress |  |  | 48971 | 33878.23 | 33878.23 | 3987.07 | 14302.24 | 0 | 18289.31 | 0 | 225.96
NHT-002898 - Testing | 23-PC-43408 | In progress |  |  | 73083 | 50558.94 | 50558.94 | 5950.19 | 21344.28 | 0 | 27294.47 | 0 | 297.7
NHT-002905 - Reporting | 23-PC-43408 | In progress |  |  | 54246 | 37527.17 | 37527.17 | 4416.51 | 15842.7 | 0 | 20259.21 | 0 | 234.49
NHT-002910 - Prefield | 23-PC-43477 | Completed |  |  | 4886 | 3586.01 | 3586.01 | 715.97 | 3329.07 | 0 | 4045.04 | 0 | 51.93
NHT-002912 - Curation | 23-PC-43477 | Completed |  |  | 6118 | 4490.3 | 4490.3 | 896.52 | 4168.56 | 0 | 5065.08 | 0 | 70.87
NHT-002915 - Draft Report | 23-PC-43477 | Completed |  |  | 12813 | 9404.49 | 9404.49 | 1877.67 | 8730.65 | 0 | 10608.32 | 0 | 169.46
NHT-002921 - Survey | 23-PC-43477 | Completed |  |  | 19224 | 14110.13 | 14110.13 | 2817.19 | 13099.12 | 0 | 15916.31 | 0 | 218.71
NHT-002922 - Fieldwork | 23-PC-43477 | Completed |  |  | 26759 | 19642.27 | 19642.27 | 3921.72 | 18234.9 | 0 | 22156.62 | 0 | 309.61
NHT-002928 - Fieldwork | 23-PC-43564 | Completed |  |  | 156045 | 98495.59 | 98495.59 | 12714.8 | 82171.72 | 0 | 94886.52 | 0 | 1363.19
NHT-002930 - Final Report | 23-PC-43564 | Completed |  |  | 50294 | 31745.75 | 31745.75 | 4098.06 | 26484.47 | 0 | 30582.53 | 0 | 351.11
NHT-002935 - Project Management | 23-PC-43564 | Completed |  |  | 31611 | 19953.16 | 19953.16 | 2575.75 | 16646.29 | 0 | 19222.04 | 0 | 257.6
NHT-002941 - Background Research | 23-PC-43564 | Completed |  |  | 21011 | 13261.99 | 13261.99 | 1711.99 | 11064.06 | 0 | 12776.05 | 0 | 191.77
NHT-002944 - Desktop Review | 23-PC-43564 | Completed |  |  | 18039 | 11385.91 | 11385.91 | 1469.81 | 9498.91 | 0 | 10968.72 | 0 | 149.91
NHT-002949 - Data Recovery Excavation | 23-PC-43612 | In progress |  |  | 124995 | 69676.23 | 83693.76 | 8754.58 | 36605.96 | 0 | 45360.54 | 863 | 614.31
NHT-002953 - Site Recordation | 23-PC-43612 | In progress |  |  | 32724 | 18241.45 | 21911.29 | 2291.98 | 9583.56 | 0 | 11875.54 | 233 | 155.83
NHT-002959 - Testing | 23-PC-43612 | In progress |  |  | 44081 | 24572.24 | 29515.72 | 3087.42 | 12909.58 | 0 | 15997 | 355 | 230.45
NHT-002965 - Testing | 23-PC-43692 | In progress |  |  | 112600 | 77637.7 | 77637.7 | 7308.32 | 55694.47 | 0 | 63002.79 | 872 | 1100.93
NHT-002967 - Lab Analysis | 23-PC-43788 | Completed |  |  | 57800 | 30648.74 | 39628.4 | 3964.78 | 35290.51 | 0 | 39255.29 | 508 | 589.14
NHT-002970 - Monitoring | 23-PC-43811 | On hold |  |  | 34600 | 28596.9 | 28596.9 | 1650.52 | 14854.73 | 0 | 16505.25 | 0 | 243.85
NHT-002976 - Survey | 23-PC-43829 | In progress |  |  | 121453 | 91588.05 | 91588.05 | 8252.6 | 46764.7 | 0 | 55017.3 | 880 | 830.7
NHT-002977 - Project Management | 23-PC-43829 | In progress |  |  | 45047 | 33969.6 | 33969.6 | 3060.85 | 17344.82 | 0 | 20405.67 | 274 | 304.48
NHT-002984 - Draft Report | 23-PC-44023 | Completed |  |  | 155814 | 93601.88 | 102485.51 | 15273.7 | 65114.18 | 0 | 80387.88 | 855 | 970.44
NHT-002987 - Project Management | 23-PC-44023 | Completed |  |  | 83533 | 50180.98 | 54943.59 | 8188.39 | 34908.42 | 0 | 43096.81 | 360 | 561.23
NHT-002988 - Prefield | 23-PC-44023 | Completed |  |  | 59853 | 35955.38 | 39367.85 | 5867.1 | 25012.37 | 0 | 30879.47 | 350 | 353.16
NHT-002991 - Data Recovery Excavation | 23-PC-44147 | Completed |  |  | 42355 | 35548.57 | 35548.57 | 4129.97 | 38447.1 | 0 | 42577.07 | 0 | 569.26
NHT-002993 - Draft Report | 23-PC-44147 | Completed |  |  | 19359 | 16247.85 | 16247.85 | 1887.65 | 17572.65 | 0 | 19460.3 | 0 | 278.11
NHT-002994 - Fieldwork | 23-PC-44147 | Completed |  |  | 36472 | 30611 | 30611 | 3556.34 | 33106.94 | 0 | 36663.28 | 0 | 508.91
NHT-002996 - Monitoring | 23-PC-44147 | Completed |  |  | 27876 | 23396.31 | 23396.31 | 2718.15 | 25303.99 | 0 | 28022.14 | 0 | 443.01
NHT-003001 - GIS & Mapping | 23-PC-44147 | Completed |  |  | 12038 | 10103.6 | 10103.6 | 1173.82 | 10927.42 | 0 | 12101.24 | 0 | 153.63
NHT-003004 - Agency Consultation | 24-PC-30017 | Completed |  |  | 3325 | 2353.27 | 2353.27 | 257.06 | 2599.13 | 0 | 2856.19 | 0 | 47.73
NHT-003007 - GIS & Mapping | 24-PC-30017 | Completed |  |  | 7486 | 5298.4 | 5298.4 | 578.76 | 5851.96 | 0 | 6430.72 | 0 | 127.38
NHT-003009 - Project Management | 24-PC-30017 | Completed |  |  | 6356 | 4498.91 | 4498.91 | 491.43 | 4968.95 | 0 | 5460.38 | 0 | 93.56
NHT-003013 - Lab Analysis | 24-PC-30017 | Completed |  |  | 7633 | 5402.86 | 5402.86 | 590.18 | 5967.33 | 0 | 6557.51 | 0 | 112.82
NHT-003015 - Fieldwork | 24-PC-30233 | In progress |  |  | 4739 | 3024.58 | 3024.58 | 1360.83 | 7202.5 | 0 | 8563.33 | 79 | 146.37
NHT-003017 - Testing | 24-PC-30233 | Completed |  |  | 26327 | 16801.68 | 16801.68 | 3800.18 | 20113.27 | 0 | 23913.45 | 432 | 411.06
NHT-003020 - Site Recordation | 24-PC-30233 | Completed |  |  | 20346 | 12984.59 | 12984.59 | 3786.37 | 20040.17 | 0 | 23826.54 | 241 | 387.64
NHT-003023 - Curation | 24-PC-30233 | Completed |  |  | 41888 | 26733.21 | 26733.21 | 5671.22 | 30016.16 | 0 | 35687.38 | 580 | 626.47
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-30233 | In progress |  |  | 0 | 0 | 0 | 0 | 1718.26 | 0 | 1718.26 | 0 | 33.5
NHT-003034 - Agency Consultation | 24-PC-30378 | Completed |  |  | 133000 | 107304.4 | 107304.4 | 10816.28 | 64296.8 | 0 | 75113.08 | 1659 | 1134.55
NHT-003038 - Testing | 24-PC-30448 | In progress |  |  | 89724 | 66629.18 | 66629.18 | 4245.56 | 41405.63 | 0 | 45651.19 | 1132 | 689
NHT-003039 - Final Report | 24-PC-30448 | In progress |  |  | 52876 | 39265.58 | 39265.58 | 2501.98 | 24400.97 | 0 | 26902.95 | 908 | 546.55
NHT-003046 - Lab Analysis | 24-PC-30509 | Completed |  |  | 682700 | 517281.79 | 517281.79 | 41749.54 | 274534.86 | 0 | 316284.4 | 7437 | 4517.57
NHT-003048 - Final Report | 24-PC-30620 | Completed |  |  | 16861 | 12640.85 | 12640.85 | 1461.09 | 9282.22 | 0 | 10743.31 | 0 | 175.23
NHT-003052 - Curation | 24-PC-30620 | Completed |  |  | 12338 | 9249.75 | 9249.75 | 1069.13 | 6792.13 | 0 | 7861.26 | 0 | 148.49
NHT-003059 - Monitoring | 24-PC-30620 | Completed |  |  | 56328 | 42228.93 | 42228.93 | 4881.02 | 31008.85 | 0 | 35889.87 | 0 | 571.83
NHT-003062 - Site Recordation | 24-PC-30620 | Completed |  |  | 18873 | 14149.15 | 14149.15 | 1635.43 | 10389.78 | 0 | 12025.21 | 0 | 200.29
NHT-003067 - Agency Consultation | 24-PC-30679 | Completed |  |  | 16249 | 12220.75 | 12220.75 | 959.82 | 14849.81 | 0 | 15809.63 | 242 | 325.05
NHT-003072 - Project Management | 24-PC-30679 | In progress |  |  | 44351 | 33356.51 | 33356.51 | 2075.99 | 32118.41 | 0 | 34194.4 | 688 | 700.9
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-30679 | In progress |  |  | 0 | 0 | 0 | 0 | 592.85 | 0 | 592.85 | 0 | 13.25
NHT-003083 - Monitoring | 24-PC-30751 | In progress |  |  | 66013 | 41948.52 | 52369.78 | 4053.44 | 32464.05 | 0 | 36517.49 | 804 | 599.43
NHT-003085 - Final Report | 24-PC-30751 | In progress |  |  | 24787 | 15751.23 | 19664.31 | 1522.03 | 12189.92 | 0 | 13711.95 | 318 | 219.92
NHT-003091 - Agency Consultation | 24-PC-30843 | Completed |  |  | 7603 | 5755.73 | 5755.73 | 606.55 | 4667.77 | 0 | 5274.32 | 122 | 101.71
NHT-003092 - Background Research | 24-PC-30843 | Completed |  |  | 8995 | 6808.93 | 6808.93 | 717.53 | 5521.9 | 0 | 6239.43 | 135 | 110.43
NHT-003099 - Monitoring | 24-PC-30843 | Completed |  |  | 39861 | 30174.88 | 30174.88 | 3179.87 | 24471.17 | 0 | 27651.04 | 605 | 556.3
NHT-003102 - Data Recovery Excavation | 24-PC-30843 | Completed |  |  | 52141 | 39470.66 | 39470.66 | 4159.47 | 32009.84 | 0 | 36169.31 | 679 | 687.54
NHT-003109 - GIS & Mapping | 24-PC-30850 | Completed |  |  | 159761 | 111145.5 | 111145.5 | 12216.83 | 56033.63 | 0 | 68250.46 | 1193 | 979.46
NHT-003113 - Draft Report | 24-PC-30850 | Completed |  |  | 250952 | 174586.98 | 174586.98 | 19190.16 | 88017.44 | 0 | 107207.6 | 2163 | 2002.84
NHT-003119 - Data Recovery Excavation | 24-PC-30850 | Completed |  |  | 581087 | 404262.78 | 404262.78 | 44435.55 | 203807.74 | 0 | 248243.29 | 4976 | 3344
NHT-003125 - Desktop Review | 24-PC-31134 | On hold |  |  | 5053 | 3550.45 | 3550.45 | 367.7 | 1989.33 | 0 | 2357.03 | 50 | 31.34
NHT-003130 - Fieldwork | 24-PC-31134 | On hold |  |  | 29374 | 20641.44 | 20641.44 | 2137.69 | 11565.49 | 0 | 13703.18 | 249 | 256.78
NHT-003134 - GIS & Mapping | 24-PC-31134 | On hold |  |  | 10951 | 7695.04 | 7695.04 | 796.93 | 4311.57 | 0 | 5108.5 | 103 | 83.42
NHT-003141 - Draft Report | 24-PC-31134 | On hold |  |  | 13922 | 9783.18 | 9783.18 | 1013.18 | 5481.56 | 0 | 6494.74 | 100 | 98.13
NHT-003146 - Survey | 24-PC-31224 | Completed |  |  | 28395 | 16529.07 | 16529.07 | 3545.48 | 17942.29 | 0 | 21487.77 | 205 | 375.48
NHT-003151 - Final Report | 24-PC-31224 | Completed |  |  | 8634 | 5025.73 | 5025.73 | 1078.02 | 5455.43 | 0 | 6533.45 | 80 | 107.24
NHT-003157 - Monitoring | 24-PC-31224 | Completed |  |  | 27771 | 16165.28 | 16165.28 | 3467.46 | 17547.42 | 0 | 21014.88 | 193 | 354.59
NHT-003161 - Site Recordation | 24-PC-31267 | On hold |  |  | 19813 | 15018.49 | 15018.49 | 769.71 | 8732.93 | 0 | 9502.64 | 302 | 192.78
NHT-003168 - Final Report | 24-PC-31267 | On hold |  |  | 13430 | 10180.17 | 10180.17 | 521.74 | 5919.55 | 0 | 6441.29 | 234 | 109.71
NHT-003175 - Project Management | 24-PC-31267 | On hold |  |  | 13860 | 10505.82 | 10505.82 | 538.43 | 6108.91 | 0 | 6647.34 | 174 | 120.14
NHT-003181 - Survey | 24-PC-31267 | On hold |  |  | 50397 | 38200.52 | 38200.52 | 1957.83 | 22212.81 | 0 | 24170.64 | 782 | 521.13
NHT-003182 - Reporting | 24-PC-31282 | Completed |  |  | 94000 | 65640.2 | 65640.2 | 8132.97 | 65137.05 | 0 | 73270.02 | 1164 | 1351.09
NHT-003187 - Fieldwork | 24-PC-31358 | Completed |  |  | 486800 | 292851.19 | 396401.96 | 54540.03 | 326858.78 | 0 | 381398.81 | 5467 | 5967.12
NHT-003191 - Curation | 24-PC-31358 | Completed |  |  | 56469 | 33970.82 | 45982.73 | 6326.66 | 37915.71 | 0 | 44242.37 | 687 | 692.22
NHT-003193 - Desktop Review | 24-PC-31358 | Completed |  |  | 51831 | 31180.82 | 42206.21 | 5807.05 | 34801.72 | 0 | 40608.77 | 635 | 730.98
NHT-003197 - Final Report | 24-PC-31434 | In progress |  |  | 1992 | 1359.1 | 1359.1 | 160.32 | 835.44 | 0 | 995.76 | 16 | 16.12
NHT-003198 - Fieldwork | 24-PC-31434 | In progress |  |  | 10220 | 6973.39 | 6973.39 | 822.57 | 4286.57 | 0 | 5109.14 | 78 | 84.8
NHT-003204 - Project Management | 24-PC-31434 | In progress |  |  | 2362 | 1611.61 | 1611.61 | 190.1 | 990.66 | 0 | 1180.76 | 16 | 18.95
NHT-003207 - Lab Analysis | 24-PC-31434 | In progress |  |  | 3626 | 2473.76 | 2473.76 | 291.8 | 1520.62 | 0 | 1812.42 | 28 | 28.9
NHT-003211 - Desktop Review | 24-PC-31453 | In progress |  |  | 1912 | 1246.63 | 1246.63 | 209.45 | 742.59 | 0 | 952.04 | 21 | 13.28
NHT-003217 - Draft Report | 24-PC-31453 | In progress |  |  | 4365 | 2846.23 | 2846.23 | 478.2 | 1695.43 | 0 | 2173.63 | 42 | 37.83
NHT-003221 - Data Recovery Excavation | 24-PC-31453 | In progress |  |  | 7833 | 5106.41 | 5106.41 | 857.94 | 3041.78 | 0 | 3899.72 | 72 | 80.53
NHT-003223 - Curation | 24-PC-31453 | In progress |  |  | 1710 | 1115.05 | 1115.05 | 187.34 | 664.21 | 0 | 851.55 | 15 | 11.21
NHT-003226 - Site Recordation | 24-PC-31453 | In progress |  |  | 2480 | 1617.28 | 1617.28 | 271.72 | 963.38 | 0 | 1235.1 | 24 | 16.19
NHT-003233 - Background Research | 24-PC-31503 | Completed |  |  | 39215 | 26513.23 | 26513.23 | 5605.83 | 24212.41 | 0 | 29818.24 | 440 | 447.13
NHT-003239 - Prefield | 24-PC-31503 | Completed |  |  | 52537 | 35520.12 | 35520.12 | 7510.2 | 32437.68 | 0 | 39947.88 | 569 | 657.74
NHT-003240 - Desktop Review | 24-PC-31503 | Completed |  |  | 38148 | 25792.04 | 25792.04 | 5453.34 | 23553.8 | 0 | 29007.14 | 428 | 434.77
NHT-003242 - Agency Consultation | 24-PC-31514 | Completed |  |  | 9413 | 8283.55 | 8283.55 | 1428.13 | 7668.25 | 0 | 9096.38 | 0 | 129.44
NHT-003247 - Lab Analysis | 24-PC-31514 | Completed |  |  | 34174 | 30073.03 | 30073.03 | 5184.77 | 27839.23 | 0 | 33024 | 0 | 587.45
NHT-003250 - Site Recordation | 24-PC-31514 | Completed |  |  | 25882 | 22776.03 | 22776.03 | 3926.72 | 21084.24 | 0 | 25010.96 | 0 | 381.79
NHT-003251 - Monitoring | 24-PC-31514 | Completed |  |  | 42231 | 37163.39 | 37163.39 | 6407.19 | 34402.91 | 0 | 40810.1 | 0 | 631.85
NHT-003258 - Agency Consultation | 24-PC-31534 | Completed |  |  | 8025 | 4806.17 | 4806.17 | 1070.88 | 4717.64 | 0 | 5788.52 | 63 | 95.95
NHT-003261 - Testing | 24-PC-31534 | Completed |  |  | 28411 | 17015.33 | 17015.33 | 3791.22 | 16701.88 | 0 | 20493.1 | 222 | 376.81
NHT-003264 - Fieldwork | 24-PC-31534 | Completed |  |  | 49443 | 29611.26 | 29611.26 | 6597.75 | 29065.75 | 0 | 35663.5 | 457 | 556.34
NHT-003271 - Monitoring | 24-PC-31534 | Completed |  |  | 47886 | 28678.87 | 28678.87 | 6390 | 28150.56 | 0 | 34540.56 | 386 | 558.33
NHT-003272 - Draft Report | 24-PC-31534 | Completed |  |  | 23135 | 13855.78 | 13855.78 | 3087.24 | 13600.54 | 0 | 16687.78 | 216 | 299.33
NHT-003277 - Curation | 24-PC-31663 | In progress |  |  | 2428 | 1740.62 | 1740.62 | 120.43 | 1330.48 | 0 | 1450.91 | 20 | 26.76
NHT-003279 - Survey | 24-PC-31663 | In progress |  |  | 14216 | 10193.05 | 10193.05 | 705.21 | 7791.29 | 0 | 8496.5 | 135 | 141.56
NHT-003283 - Fieldwork | 24-PC-31663 | In progress |  |  | 18757 | 13449.04 | 13449.04 | 930.47 | 10280.09 | 0 | 11210.56 | 147 | 226.63
NHT-003289 - Prefield | 24-PC-31663 | In progress |  |  | 2778 | 1991.75 | 1991.75 | 137.8 | 1522.44 | 0 | 1660.24 | 21 | 29.81
NHT-003295 - Testing | 24-PC-31663 | In progress |  |  | 14421 | 10339.74 | 10339.74 | 715.36 | 7903.42 | 0 | 8618.78 | 164 | 158.63
NHT-003301 - Testing | 24-PC-31750 | Completed |  |  | 37465 | 29136.84 | 29136.84 | 3701.05 | 28035.78 | 0 | 31736.83 | 366 | 340.68
NHT-003306 - Lab Analysis | 24-PC-31750 | Completed |  |  | 29160 | 22678.08 | 22678.08 | 2211.6 | 16753.04 | 0 | 18964.64 | 224 | 261.83
NHT-003309 - Fieldwork | 24-PC-31750 | Completed |  |  | 81608 | 63465.5 | 63465.5 | 5531.6 | 41902.34 | 0 | 47433.94 | 695 | 617.02
NHT-003310 - GIS & Mapping | 24-PC-31750 | Completed |  |  | 31511 | 24506.27 | 24506.27 | 2813.36 | 21311.42 | 0 | 24124.78 | 297 | 300.49
NHT-003317 - Site Recordation | 24-PC-31750 | Completed |  |  | 77456 | 60237.75 | 60237.75 | 5192.77 | 39335.62 | 0 | 44528.39 | 474 | 467.98
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-31750 | Completed |  |  | 0 | 0 | 0 | 0 | 2345.13 | 0 | 2345.13 | 0 | 27.5
NHT-003322 - Lab Analysis | 24-PC-31819 | Completed |  |  | 6986 | 4833.12 | 4833.12 | 553.42 | 2314.06 | 0 | 2867.48 | 88 | 42.06
NHT-003324 - GIS & Mapping | 24-PC-31819 | Completed |  |  | 6045 | 4182.12 | 4182.12 | 478.88 | 2002.37 | 0 | 2481.25 | 71 | 37.61
NHT-003329 - Fieldwork | 24-PC-31819 | Completed |  |  | 19721 | 13642.75 | 13642.75 | 1562.19 | 6532.04 | 0 | 8094.23 | 283 | 106.35
NHT-003334 - Project Management | 24-PC-31819 | Completed |  |  | 5848 | 4045.49 | 4045.49 | 463.24 | 1936.95 | 0 | 2400.19 | 73 | 38.74
NHT-003335 - Final Report | 24-PC-31857 | In progress |  |  | 5220 | 3666.46 | 3666.46 | 534.14 | 2075.79 | 0 | 2609.93 | 70 | 45.33
NHT-003342 - Monitoring | 24-PC-31857 | In progress |  |  | 6225 | 4372.84 | 4372.84 | 626.77 | 2435.8 | 0 | 3062.57 | 110 | 45.34
NHT-003348 - Project Management | 24-PC-31857 | In progress |  |  | 3755 | 2637.18 | 2637.18 | 402.79 | 1565.36 | 0 | 1968.15 | 54 | 29.95
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-31857 | In progress |  |  | 0 | 0 | 0 | 0 | 24.57 | 0 | 24.57 | 0 | 0.5
NHT-003357 - GIS & Mapping | 24-PC-31924 | In progress |  |  | 186800 | 122646.08 | 147262.72 | 12591.13 | 85014.54 | 0 | 97605.67 | 2395 | 1498.57
NHT-003363 - Final Report | 24-PC-32088 | In progress |  |  | 138966 | 103877.1 | 103877.1 | 11867.47 | 49942.27 | 0 | 61809.74 | 2324 | 1023.91
NHT-003365 - Site Recordation | 24-PC-32088 | In progress |  |  | 166134 | 124185.15 | 124185.15 | 14187.57 | 59706.03 | 0 | 73893.6 | 2834 | 1041.72
NHT-003368 - Final Report | 24-PC-32201 | Completed |  |  | 14906 | 10570.08 | 10570.08 | 2728.03 | 14673.74 | 0 | 17401.77 | 203 | 240.93
NHT-003372 - Testing | 24-PC-32201 | In progress |  |  | 12448 | 8827.11 | 8827.11 | 1680.43 | 9038.81 | 0 | 10719.24 | 165 | 184.98
NHT-003378 - Prefield | 24-PC-32201 | In progress |  |  | 6482 | 4596.11 | 4596.11 | 1160.95 | 6244.58 | 0 | 7405.53 | 81 | 138.49
NHT-003384 - Fieldwork | 24-PC-32201 | In progress |  |  | 13389 | 9494.06 | 9494.06 | 2047.69 | 11014.23 | 0 | 13061.92 | 191 | 219.4
NHT-003391 - Lab Analysis | 24-PC-32201 | In progress |  |  | 4575 | 3244.02 | 3244.02 | 1491.1 | 8020.41 | 0 | 9511.51 | 57 | 171.51
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-32201 | In progress |  |  | 0 | 0 | 0 | 0 | 1430.77 | 0 | 1430.77 | 0 | 27.75
NHT-003396 - Background Research | 24-PC-32209 | In progress |  |  | 10011 | 5567.35 | 6953.07 | 1344.52 | 4909.71 | 0 | 6254.23 | 57 | 61.15
NHT-003403 - Fieldwork | 24-PC-32209 | In progress |  |  | 2989 | 1662.41 | 2076.18 | 546.94 | 1997.23 | 0 | 2544.17 | 17 | 23.61
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-32209 | In progress |  |  | 0 | 0 | 0 | 0 | 81.71 | 0 | 81.71 | 0 | 1
NHT-003405 - Data Recovery Excavation | 24-PC-32210 | In progress |  |  | 44284 | 35307.78 | 35307.78 | 5152.79 | 19384.28 | 0 | 24537.07 | 426 | 313.81
NHT-003407 - Site Recordation | 24-PC-32210 | In progress |  |  | 17341 | 13826.08 | 13826.08 | 2017.76 | 7590.64 | 0 | 9608.4 | 188 | 112.86
NHT-003413 - Agency Consultation | 24-PC-32210 | In progress |  |  | 7935 | 6326.59 | 6326.59 | 923.3 | 3473.36 | 0 | 4396.66 | 77 | 54.23
NHT-003419 - Reporting | 24-PC-32210 | In progress |  |  | 28248 | 22521.9 | 22521.9 | 3286.82 | 12364.72 | 0 | 15651.54 | 328 | 211.69
NHT-003424 - GIS & Mapping | 24-PC-32210 | In progress |  |  | 16592 | 13228.77 | 13228.77 | 1930.59 | 7262.71 | 0 | 9193.3 | 134 | 130.76
NHT-003429 - Reporting | 24-PC-32270 | Completed |  |  | 12535 | 8754.66 | 8754.66 | 1342.57 | 7263.66 | 0 | 8606.23 | 0 | 149.42
NHT-003431 - Survey | 24-PC-32270 | Completed |  |  | 12547 | 8762.94 | 8762.94 | 1343.85 | 7270.54 | 0 | 8614.39 | 0 | 149.22
NHT-003433 - Lab Analysis | 24-PC-32270 | Completed |  |  | 9797 | 6842.24 | 6842.24 | 1049.29 | 5676.94 | 0 | 6726.23 | 0 | 93.71
NHT-003437 - Final Report | 24-PC-32270 | Completed |  |  | 4205 | 2936.63 | 2936.63 | 450.35 | 2436.5 | 0 | 2886.85 | 0 | 40.3
NHT-003443 - Agency Consultation | 24-PC-32270 | Completed |  |  | 3116 | 2176.01 | 2176.01 | 333.7 | 1805.41 | 0 | 2139.11 | 0 | 36.16
NHT-003450 - Background Research | 24-PC-32479 | In progress |  |  | 13398 | 9534.01 | 9534.01 | 592.67 | 5774.05 | 0 | 6366.72 | 0 | 138.58
NHT-003454 - Prefield | 24-PC-32479 | In progress |  |  | 49191 | 35003.98 | 35003.98 | 2141.74 | 20865.69 | 0 | 23007.43 | 0 | 455.84
NHT-003459 - Testing | 24-PC-32479 | In progress |  |  | 31411 | 22352.41 | 22352.41 | 1408.02 | 13717.57 | 0 | 15125.59 | 0 | 330.15
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-32479 | In progress |  |  | 0 | 0 | 0 | 0 | 42.56 | 0 | 42.56 | 0 | 1
NHT-003461 - Fieldwork | 24-PC-32591 | Completed |  |  | 24489 | 16412.6 | 16412.6 | 4366.21 | 15941.74 | 0 | 20307.95 | 156 | 282.14
NHT-003468 - Testing | 24-PC-32591 | Completed |  |  | 11367 | 7618.02 | 7618.02 | 2026.61 | 7399.47 | 0 | 9426.08 | 88 | 142.03
NHT-003469 - Final Report | 24-PC-32591 | Completed |  |  | 5144 | 3447.58 | 3447.58 | 917.15 | 3348.67 | 0 | 4265.82 | 48 | 60.04
NHT-003475 - Agency Consultation | 24-PC-32640 | Completed |  |  | 2787 | 1522.55 | 2010.51 | 143.63 | 1452.25 | 0 | 1595.88 | 39 | 29.01
NHT-003476 - Curation | 24-PC-32640 | Completed |  |  | 4374 | 2389.05 | 3154.72 | 225.37 | 2278.74 | 0 | 2504.11 | 51 | 50.09
NHT-003478 - Data Recovery Excavation | 24-PC-32640 | Completed |  |  | 16441 | 8980.73 | 11859 | 847.19 | 8566.06 | 0 | 9413.25 | 268 | 167.58
NHT-003483 - Desktop Review | 24-PC-32640 | Completed |  |  | 3746 | 2046.07 | 2701.83 | 193.02 | 1951.6 | 0 | 2144.62 | 60 | 33.95
NHT-003484 - Testing | 24-PC-32640 | Completed |  |  | 11652 | 6364.6 | 8404.41 | 600.4 | 6070.73 | 0 | 6671.13 | 163 | 98.22
NHT-003489 - Reporting | 24-PC-32647 | Completed |  |  | 12713 | 10624.1 | 10624.1 | 2681.39 | 19565.52 | 0 | 22246.91 | 135 | 236.9
NHT-003490 - Data Recovery Excavation | 24-PC-32647 | Completed |  |  | 16864 | 14092.98 | 14092.98 | 2736.48 | 19967.5 | 0 | 22703.98 | 193 | 249.89
NHT-003496 - Monitoring | 24-PC-32647 | Completed |  |  | 54423 | 45481.72 | 45481.72 | 4740.17 | 34587.94 | 0 | 39328.11 | 610 | 429.06
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-32647 | Completed |  |  | 0 | 0 | 0 | 0 | 1082.66 | 0 | 1082.66 | 0 | 13.25
NHT-003505 - Data Recovery Excavation | 24-PC-32688 | In progress |  |  | 21181 | 18520.78 | 18520.78 | 2323.43 | 13700.22 | 0 | 16023.65 | 255 | 277.15
NHT-003510 - Project Management | 24-PC-32688 | In progress |  |  | 5623 | 4916.89 | 4916.89 | 616.82 | 3637.13 | 0 | 4253.95 | 65 | 62.94
NHT-003511 - Desktop Review | 24-PC-32688 | In progress |  |  | 3360 | 2937.75 | 2937.75 | 368.54 | 2173.12 | 0 | 2541.66 | 41 | 35.11
NHT-003514 - Monitoring | 24-PC-32688 | In progress |  |  | 21536 | 18831.06 | 18831.06 | 2362.36 | 13929.74 | 0 | 16292.1 | 227 | 292.98
NHT-003517 - Lab Analysis | 24-PC-32954 | In progress |  |  | 72543 | 47646.32 | 47646.32 | 3229.28 | 21803.87 | 0 | 25033.15 | 658 | 384.64
NHT-003522 - Agency Consultation | 24-PC-32954 | In progress |  |  | 21692 | 14247.08 | 14247.08 | 965.61 | 6519.74 | 0 | 7485.35 | 189 | 125.26
NHT-003527 - Data Recovery Excavation | 24-PC-32954 | In progress |  |  | 169877 | 111575.68 | 111575.68 | 7562.15 | 51059.17 | 0 | 58621.32 | 1325 | 938.61
NHT-003534 - Project Management | 24-PC-32954 | In progress |  |  | 67088 | 44063.08 | 44063.08 | 2986.42 | 20164.11 | 0 | 23150.53 | 590 | 390.08
NHT-003540 - Monitoring | 24-PC-33384 | In progress |  |  | 121791 | 87604.03 | 87604.03 | 7799.78 | 51289.47 | 0 | 59089.25 | 906 | 978.28
NHT-003544 - Data Recovery Excavation | 24-PC-33384 | In progress |  |  | 143999 | 103578.89 | 103578.89 | 9222.1 | 60642.26 | 0 | 69864.36 | 975 | 1142.36
NHT-003546 - Desktop Review | 24-PC-33384 | In progress |  |  | 22310 | 16047.41 | 16047.41 | 1428.77 | 9395.26 | 0 | 10824.03 | 213 | 169.49
NHT-003547 - Monitoring | 24-PC-33394 | In progress |  |  | 120981 | 80173.8 | 80173.8 | 4153.48 | 37381.26 | 0 | 41534.74 | 1278 | 707.1
NHT-003552 - Site Recordation | 24-PC-33394 | In progress |  |  | 42306 | 28036.04 | 28036.04 | 1452.43 | 13071.89 | 0 | 14524.32 | 426 | 244.29
NHT-003555 - Lab Analysis | 24-PC-33394 | In progress |  |  | 41415 | 27445.55 | 27445.55 | 1421.84 | 12796.57 | 0 | 14218.41 | 431 | 261.85
NHT-003560 - Final Report | 24-PC-33394 | In progress |  |  | 23075 | 15292.1 | 15292.1 | 792.22 | 7129.99 | 0 | 7922.21 | 237 | 150.53
NHT-003565 - Survey | 24-PC-33394 | In progress |  |  | 70423 | 46669.65 | 46669.65 | 2417.76 | 21759.86 | 0 | 24177.62 | 655 | 408.02
NHT-003570 - Draft Report | 24-PC-33448 | In progress |  |  | 239008 | 147396.2 | 147396.2 | 22013.35 | 91366.44 | 0 | 113379.79 | 2550 | 2135.89
NHT-003577 - Agency Consultation | 24-PC-33448 | In progress |  |  | 98867 | 60971.48 | 60971.48 | 10373.16 | 43053.82 | 0 | 53426.98 | 976 | 1038.63
NHT-003580 - Lab Analysis | 24-PC-33448 | In progress |  |  | 173381 | 106923.94 | 106923.94 | 15994.37 | 66384.63 | 0 | 82379 | 1409 | 1691.98
NHT-003586 - Reporting | 24-PC-33448 | In progress |  |  | 72364 | 44626.79 | 44626.79 | 8156.65 | 33854.17 | 0 | 42010.82 | 715 | 956.76
NHT-003588 - Fieldwork | 24-PC-33448 | In progress |  |  | 97380 | 60054.29 | 60054.29 | 10927.05 | 45352.73 | 0 | 56279.78 | 1089 | 1174.32
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-33448 | In progress |  |  | 0 | 0 | 0 | 0 | 279.17 | 0 | 279.17 | 0 | 6.75
NHT-003593 - Fieldwork | 24-PC-33531 | Completed |  |  | 640 | 482.54 | 482.54 | 62.56 | 279.29 | 0 | 341.85 | 13 | 6.49
NHT-003600 - Draft Report | 24-PC-33531 | Completed |  |  | 4945 | 3730.3 | 3730.3 | 520.74 | 2324.82 | 0 | 2845.56 | 107 | 56.56
NHT-003607 - Desktop Review | 24-PC-33531 | Completed |  |  | 13351 | 10070.66 | 10070.66 | 1397.17 | 6237.66 | 0 | 7634.83 | 213 | 147.4
NHT-003612 - Survey | 24-PC-33531 | Completed |  |  | 533 | 402.11 | 402.11 | 52.13 | 232.74 | 0 | 284.87 | 11 | 4.42
NHT-003617 - Monitoring | 24-PC-33531 | Completed |  |  | 12031 | 9074.84 | 9074.84 | 1275.5 | 5694.45 | 0 | 6969.95 | 190 | 121.17
NHT-003620 - Lab Analysis | 24-PC-33575 | Completed |  |  | 213398 | 156847.75 | 156847.75 | 12950.16 | 112117.23 | 0 | 125067.39 | 2815 | 2723.69
NHT-003625 - GIS & Mapping | 24-PC-33575 | Completed |  |  | 376202 | 276508.25 | 276508.25 | 18922 | 163818.95 | 0 | 182740.95 | 6927 | 3946.2
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-33575 | Completed |  |  | 0 | 0 | 0 | 0 | 1630.07 | 0 | 1630.07 | 0 | 36.75
NHT-003635 - Agency Consultation | 24-PC-33822 | In progress |  |  | 11749 | 9029.19 | 9029.19 | 1230.91 | 5997.54 | 0 | 7228.45 | 66 | 86.85
NHT-003637 - GIS & Mapping | 24-PC-33822 | In progress |  |  | 17264 | 13267.3 | 13267.3 | 1660.94 | 8092.84 | 0 | 9753.78 | 119 | 123.44
NHT-003639 - Curation | 24-PC-33822 | In progress |  |  | 4524 | 3476.76 | 3476.76 | 565.57 | 2755.69 | 0 | 3321.26 | 25 | 38.71
NHT-003642 - Draft Report | 24-PC-33822 | Completed |  |  | 8801 | 6763.33 | 6763.33 | 2000.08 | 9745.27 | 0 | 11745.35 | 57 | 146.14
NHT-003645 - Prefield | 24-PC-33822 | In progress |  |  | 22162 | 17031.67 | 17031.67 | 2295.54 | 11184.89 | 0 | 13480.43 | 164 | 169.16
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-33822 | In progress |  |  | 0 | 0 | 0 | 0 | 76.81 | 0 | 76.81 | 0 | 1
NHT-003653 - Background Research | 24-PC-33927 | Completed |  |  | 104000 | 77001.6 | 77001.6 | 8821.71 | 33273.12 | 0 | 42094.83 | 908 | 437.5
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-33927 | Completed |  |  | 0 | 0 | 0 | 0 | 114.33 | 0 | 114.33 | 0 | 1.5
NHT-003663 - Background Research | 24-PC-33981 | Completed |  |  | 5246 | 3306.95 | 3306.95 | 645 | 2643.4 | 0 | 3288.4 | 0 | 33.27
NHT-003668 - Draft Report | 24-PC-33981 | Completed |  |  | 4595 | 2896.43 | 2896.43 | 509.15 | 2086.63 | 0 | 2595.78 | 0 | 29.26
NHT-003669 - Lab Analysis | 24-PC-33981 | Completed |  |  | 18904 | 11917.64 | 11917.64 | 2102.84 | 8618.04 | 0 | 10720.88 | 0 | 133.37
NHT-003674 - Project Management | 24-PC-33981 | Completed |  |  | 18755 | 11822.98 | 11822.98 | 1905.54 | 7809.42 | 0 | 9714.96 | 0 | 84.87
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-33981 | Completed |  |  | 0 | 0 | 0 | 0 | 19.41 | 0 | 19.41 | 0 | 0.25
NHT-003677 - Survey | 24-PC-33985 | In progress |  |  | 39575 | 29245.93 | 29245.93 | 2482.24 | 23107.78 | 0 | 25590.02 | 458 | 428.73
NHT-003683 - Final Report | 24-PC-33985 | In progress |  |  | 14419 | 10655.9 | 10655.9 | 904.41 | 8419.43 | 0 | 9323.84 | 129 | 140.03
NHT-003685 - Reporting | 24-PC-33985 | In progress |  |  | 24306 | 17961.87 | 17961.87 | 1524.5 | 14192.02 | 0 | 15716.52 | 210 | 229.26
NHT-003692 - Lab Analysis | 24-PC-34015 | Completed |  |  | 3428 | 2210.84 | 2210.84 | 224.08 | 1643.26 | 0 | 1867.34 | 38 | 29.78
NHT-003699 - Final Report | 24-PC-34015 | Completed |  |  | 2880 | 1857.85 | 1857.85 | 188.3 | 1380.89 | 0 | 1569.19 | 30 | 20.23
NHT-003703 - Fieldwork | 24-PC-34015 | Completed |  |  | 9892 | 6380.31 | 6380.31 | 646.68 | 4742.32 | 0 | 5389 | 81 | 66.87
NHT-003710 - Desktop Review | 24-PC-34211 | On hold |  |  | 8918 | 6356.49 | 6356.49 | 1033.73 | 3665.04 | 0 | 4698.77 | 67 | 56.82
NHT-003717 - Curation | 24-PC-34211 | On hold |  |  | 8261 | 5888.23 | 5888.23 | 957.58 | 3395.05 | 0 | 4352.63 | 62 | 50.65
NHT-003723 - Testing | 24-PC-34211 | On hold |  |  | 29976 | 21367.44 | 21367.44 | 3474.89 | 12320.09 | 0 | 15794.98 | 189 | 204.67
NHT-003729 - Lab Analysis | 24-PC-34211 | On hold |  |  | 14086 | 10040.67 | 10040.67 | 1632.87 | 5789.27 | 0 | 7422.14 | 95 | 97.16
NHT-003734 - Project Management | 24-PC-34211 | On hold |  |  | 9659 | 6884.69 | 6884.69 | 1119.63 | 3969.59 | 0 | 5089.22 | 57 | 65.15
NHT-003736 - Final Report | 24-PC-34263 | In progress |  |  | 50051 | 37117.89 | 37117.89 | 2228.63 | 21480.2 | 0 | 23708.83 | 541 | 356.24
NHT-003741 - Site Recordation | 24-PC-34263 | In progress |  |  | 53564 | 39722.64 | 39722.64 | 2385.03 | 22987.59 | 0 | 25372.62 | 449 | 472.28
NHT-003743 - Agency Consultation | 24-PC-34263 | In progress |  |  | 30592 | 22687.39 | 22687.39 | 1362.19 | 13129.24 | 0 | 14491.43 | 331 | 226.01
NHT-003748 - Prefield | 24-PC-34263 | In progress |  |  | 35170 | 26082.33 | 26082.33 | 1566.03 | 15093.9 | 0 | 16659.93 | 355 | 231.11
NHT-003751 - Curation | 24-PC-34263 | In progress |  |  | 29923 | 22190.63 | 22190.63 | 1332.37 | 12841.77 | 0 | 14174.14 | 340 | 254.2
NHT-003752 - Prefield | 24-PC-34274 | Completed |  |  | 33507 | 26088.41 | 26088.41 | 1890.61 | 29103.06 | 0 | 30993.67 | 195 | 474.55
NHT-003756 - Desktop Review | 24-PC-34274 | Completed |  |  | 28393 | 22106.93 | 22106.93 | 1602.08 | 24661.5 | 0 | 26263.58 | 220 | 388.2
NHT-003757 - Project Management | 24-PC-34320 | In progress |  |  | 64434 | 34780.63 | 42125.66 | 4334.91 | 25979.14 | 0 | 30314.05 | 413 | 414.56
NHT-003764 - Site Recordation | 24-PC-34320 | In progress |  |  | 85656 | 46235.56 | 55999.65 | 5762.6 | 34535.31 | 0 | 40297.91 | 673 | 514.49
NHT-003770 - GIS & Mapping | 24-PC-34320 | In progress |  |  | 41563 | 22434.92 | 27172.75 | 2796.19 | 16757.59 | 0 | 19553.78 | 259 | 296.32
NHT-003777 - Final Report | 24-PC-34320 | In progress |  |  | 78750 | 42507.85 | 51484.71 | 5298 | 31750.92 | 0 | 37048.92 | 611 | 457.87
NHT-003781 - Reporting | 24-PC-34320 | In progress |  |  | 117997 | 63693.56 | 77144.46 | 7938.49 | 47575.44 | 0 | 55513.93 | 859 | 973.08
NHT-003787 - Reporting | 24-PC-34330 | In progress |  |  | 8849 | 6092.31 | 6092.31 | 541.15 | 3858.45 | 0 | 4399.6 | 0 | 61.67
NHT-003792 - GIS & Mapping | 24-PC-34330 | In progress |  |  | 7523 | 5179.47 | 5179.47 | 460.07 | 3280.32 | 0 | 3740.39 | 0 | 51.21
NHT-003793 - Lab Analysis | 24-PC-34330 | In progress |  |  | 6693 | 4608.23 | 4608.23 | 409.33 | 2918.54 | 0 | 3327.87 | 0 | 43.91
NHT-003797 - Testing | 24-PC-34330 | In progress |  |  | 12025 | 8279.12 | 8279.12 | 735.39 | 5243.41 | 0 | 5978.8 | 0 | 91.78
NHT-003801 - Curation | 24-PC-34330 | In progress |  |  | 3610 | 2485.82 | 2485.82 | 220.8 | 1574.35 | 0 | 1795.15 | 0 | 23.64
NHT-003803 - Fieldwork | 24-PC-34422 | Completed |  |  | 126462 | 72918.01 | 72918.01 | 13365.87 | 81427.53 | 0 | 94793.4 | 0 | 1376.9
NHT-003804 - Prefield | 24-PC-34422 | Completed |  |  | 36763 | 21197.43 | 21197.43 | 3885.49 | 23671.18 | 0 | 27556.67 | 0 | 428.42
NHT-003807 - Desktop Review | 24-PC-34422 | Completed |  |  | 20675 | 11921.3 | 11921.3 | 2185.17 | 13312.52 | 0 | 15497.69 | 0 | 235.34
NHT-003811 - Background Research | 24-PC-34458 | Completed |  |  | 5341 | 3922.6 | 3922.6 | 457.58 | 3984.9 | 0 | 4442.48 | 52 | 64.57
NHT-003816 - Survey | 24-PC-34458 | Completed |  |  | 27409 | 20131.96 | 20131.96 | 2348.41 | 20451.68 | 0 | 22800.09 | 274 | 289.2
NHT-003823 - Data Recovery Excavation | 24-PC-34458 | Completed |  |  | 31379 | 23048.41 | 23048.41 | 2688.61 | 23414.45 | 0 | 26103.06 | 317 | 379.72
NHT-003830 - Site Recordation | 24-PC-34458 | Completed |  |  | 14171 | 10408.38 | 10408.38 | 1214.15 | 10573.68 | 0 | 11787.83 | 158 | 171.97
NHT-003833 - Site Recordation | 24-PC-34499 | In progress |  |  | 19526 | 13275.48 | 14322.02 | 2888.59 | 11202.09 | 0 | 14090.68 | 117 | 169.67
NHT-003835 - Survey | 24-PC-34499 | Completed |  |  | 34900 | 23727.45 | 25597.96 | 5162.82 | 20021.66 | 0 | 25184.48 | 181 | 331.58
NHT-003839 - Desktop Review | 24-PC-34499 | In progress |  |  | 7285 | 4953.03 | 5343.49 | 1077.72 | 4179.45 | 0 | 5257.17 | 43 | 93.21
NHT-003840 - Background Research | 24-PC-34499 | In progress |  |  | 8354 | 5679.55 | 6127.28 | 1235.8 | 4792.5 | 0 | 6028.3 | 43 | 75.67
NHT-003844 - Reporting | 24-PC-34499 | Completed |  |  | 34135 | 23207.34 | 25036.83 | 5049.65 | 19582.78 | 0 | 24632.43 | 184 | 302.91
NHT-003847 - Data Recovery Excavation | 24-PC-34593 | In progress |  |  | 15617 | 12007 | 12007 | 1292.34 | 5693.25 | 0 | 6985.59 | 166 | 98.98
NHT-003849 - Survey | 24-PC-34593 | In progress |  |  | 7376 | 5671.75 | 5671.75 | 610.46 | 2689.32 | 0 | 3299.78 | 67 | 39.98
NHT-003850 - Monitoring | 24-PC-34593 | In progress |  |  | 9512 | 7314.07 | 7314.07 | 787.22 | 3468.04 | 0 | 4255.26 | 85 | 63.52
NHT-003853 - Project Management | 24-PC-34593 | In progress |  |  | 3361 | 2584.43 | 2584.43 | 278.16 | 1225.43 | 0 | 1503.59 | 32 | 18.24
NHT-003856 - Reporting | 24-PC-34593 | In progress |  |  | 7634 | 5869.9 | 5869.9 | 631.78 | 2783.27 | 0 | 3415.05 | 53 | 40.83
NHT-003863 - Agency Consultation | 24-PC-34654 | Completed |  |  | 23606 | 14488 | 17957.79 | 1305.31 | 12606.7 | 0 | 13912.01 | 0 | 287.27
NHT-003867 - Draft Report | 24-PC-34654 | Completed |  |  | 91794 | 56337.08 | 69829.49 | 2975.91 | 28741.36 | 0 | 31717.27 | 0 | 760.7
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-34654 | Completed |  |  | 0 | 0 | 0 | 0 | 1417.07 | 0 | 1417.07 | 0 | 32.25
NHT-003875 - Draft Report | 24-PC-34663 | In progress |  |  | 96083 | 65201.94 | 65201.94 | 9414.03 | 45002.35 | 0 | 54416.38 | 970 | 683.52
NHT-003879 - Site Recordation | 24-PC-34663 | In progress |  |  | 95254 | 64639.1 | 64639.1 | 9332.77 | 44613.88 | 0 | 53946.65 | 897 | 729.38
NHT-003882 - Data Recovery Excavation | 24-PC-34663 | In progress |  |  | 313763 | 212919.82 | 212919.82 | 30741.95 | 146957.18 | 0 | 177699.13 | 3263 | 2517.97
NHT-003888 - Curation | 24-PC-34803 | In progress |  |  | 24482 | 16841.14 | 16841.14 | 1761.08 | 15172.42 | 0 | 16933.5 | 285 | 323.59
NHT-003891 - Final Report | 24-PC-34803 | In progress |  |  | 33747 | 23214.79 | 23214.79 | 2427.58 | 20914.53 | 0 | 23342.11 | 410 | 449.3
NHT-003894 - Monitoring | 24-PC-34803 | Completed |  |  | 118271 | 81358.42 | 81358.42 | 8507.69 | 73296.95 | 0 | 81804.64 | 1574 | 1536.91
NHT-003895 - Monitoring | 24-PC-34919 | Completed |  |  | 5407 | 3671.67 | 3671.67 | 613.44 | 2757.12 | 0 | 3370.56 | 40 | 56.48
NHT-003901 - Data Recovery Excavation | 24-PC-34919 | Completed |  |  | 11066 | 7514.87 | 7514.87 | 1255.54 | 5643.03 | 0 | 6898.57 | 84 | 141.95
NHT-003902 - Project Management | 24-PC-34919 | Completed |  |  | 3527 | 2395.46 | 2395.46 | 400.22 | 1798.79 | 0 | 2199.01 | 29 | 31.75
NHT-003907 - Prefield | 24-PC-34975 | In progress |  |  | 80359 | 70715.93 | 70715.93 | 12692.72 | 47462.36 | 0 | 60155.08 | 1206 | 963.48
NHT-003908 - GIS & Mapping | 24-PC-34975 | In progress |  |  | 77984 | 68626.18 | 68626.18 | 12317.63 | 46059.78 | 0 | 58377.41 | 1012 | 953.65
NHT-003910 - Agency Consultation | 24-PC-34975 | In progress |  |  | 47557 | 41849.89 | 41849.89 | 7511.59 | 28088.36 | 0 | 35599.95 | 684 | 576.52
NHT-003916 - Reporting | 24-PC-35267 | Completed |  |  | 12769 | 9589.24 | 9589.24 | 741.73 | 4877.41 | 0 | 5619.14 | 165 | 91.72
NHT-003917 - Fieldwork | 24-PC-35267 | Completed |  |  | 26935 | 20228.36 | 20228.36 | 1564.65 | 10288.8 | 0 | 11853.45 | 348 | 216.34
NHT-003922 - Prefield | 24-PC-35267 | Completed |  |  | 7125 | 5350.61 | 5350.61 | 413.87 | 2721.5 | 0 | 3135.37 | 90 | 60.32
NHT-003928 - Lab Analysis | 24-PC-35267 | Completed |  |  | 9871 | 7413.49 | 7413.49 | 573.43 | 3770.75 | 0 | 4344.18 | 130 | 81.7
NHT-003932 - Testing | 24-PC-35412 | In progress |  |  | 177635 | 128270.43 | 128270.43 | 11445.43 | 104164.99 | 0 | 115610.42 | 0 | 2132.17
NHT-003935 - Lab Analysis | 24-PC-35412 | In progress |  |  | 123565 | 89226.09 | 89226.09 | 7961.55 | 72458.13 | 0 | 80419.68 | 0 | 1522.58
NHT-003938 - Draft Report | 24-PC-35419 | Completed |  |  | 8951 | 5186.92 | 5904.85 | 447.98 | 4761.06 | 0 | 5209.04 | 92 | 81.95
NHT-003941 - Data Recovery Excavation | 24-PC-35419 | Completed |  |  | 12257 | 7102.08 | 8085.11 | 613.38 | 6518.98 | 0 | 7132.36 | 99 | 130.93
NHT-003946 - Final Report | 24-PC-35419 | Completed |  |  | 3592 | 2081.56 | 2369.67 | 179.78 | 1910.66 | 0 | 2090.44 | 32 | 33.08
NHT-003947 - GIS & Mapping | 24-PC-35474 | In progress |  |  | 78356 | 45728.58 | 58999.05 | 4808.18 | 40552.05 | 0 | 45360.23 | 1495 | 949.86
NHT-003953 - Project Management | 24-PC-35474 | In progress |  |  | 78147 | 45606.84 | 58841.98 | 4795.38 | 40444.09 | 0 | 45239.47 | 1230 | 814.62
NHT-003958 - Reporting | 24-PC-35474 | In progress |  |  | 179658 | 104849.19 | 135276.51 | 11024.5 | 92980.14 | 0 | 104004.64 | 3429 | 1968.27
NHT-003960 - Desktop Review | 24-PC-35474 | In progress |  |  | 33439 | 19515.03 | 25178.31 | 2051.93 | 17305.9 | 0 | 19357.83 | 521 | 312.65
NHT-003963 - Testing | 24-PC-35559 | Completed |  |  | 81758 | 54050.17 | 54050.17 | 4187.92 | 41833.22 | 0 | 46021.14 | 854 | 970.19
NHT-003970 - Agency Consultation | 24-PC-35559 | Completed |  |  | 20060 | 13261.95 | 13261.95 | 1027.56 | 10264.35 | 0 | 11291.91 | 216 | 208.21
NHT-003973 - Data Recovery Excavation | 24-PC-35559 | Completed |  |  | 116382 | 76939.9 | 76939.9 | 5961.48 | 59549.19 | 0 | 65510.67 | 1179 | 1207.41
NHT-003977 - Prefield | 24-PC-35586 | In progress |  |  | 16195 | 11989.21 | 11989.21 | 580.28 | 8486.66 | 0 | 9066.94 | 0 | 163.52
NHT-003980 - Survey | 24-PC-35586 | In progress |  |  | 47121 | 34884.02 | 34884.02 | 1688.41 | 24692.95 | 0 | 26381.36 | 0 | 568.88
NHT-003986 - Monitoring | 24-PC-35586 | In progress |  |  | 55884 | 41370.53 | 41370.53 | 2002.36 | 29284.48 | 0 | 31286.84 | 0 | 556.12
NHT-003989 - Reporting | 24-PC-35661 | In progress |  |  | 14589 | 8493.81 | 10229.6 | 917.39 | 12241.58 | 0 | 13158.97 | 220 | 316.07
NHT-003995 - Prefield | 24-PC-35661 | In progress |  |  | 7446 | 4335.05 | 5220.96 | 629.71 | 8402.81 | 0 | 9032.52 | 87 | 195.22
NHT-003997 - Survey | 24-PC-35661 | In progress |  |  | 39657 | 23088.73 | 27807.11 | 1586.05 | 21164.28 | 0 | 22750.33 | 601 | 506.18
NHT-003998 - Desktop Review | 24-PC-35661 | In progress |  |  | 8208 | 4779.01 | 5755.64 | 583.37 | 7784.43 | 0 | 8367.8 | 97 | 193.76
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-35661 | In progress |  |  | 0 | 0 | 0 | 0 | 552.97 | 0 | 552.97 | 0 | 14.5
NHT-004006 - Project Management | 24-PC-35872 | In progress |  |  | 58746 | 40123.76 | 40123.76 | 4533.54 | 29746.11 | 0 | 34279.65 | 1128 | 647.82
NHT-004008 - Desktop Review | 24-PC-35872 | In progress |  |  | 11269 | 7696.83 | 7696.83 | 1688.03 | 11075.75 | 0 | 12763.78 | 205 | 282.88
NHT-004014 - Fieldwork | 24-PC-35872 | In progress |  |  | 65624 | 44820.36 | 44820.36 | 5046.83 | 33113.97 | 0 | 38160.8 | 1352 | 839.51
NHT-004021 - Draft Report | 24-PC-35872 | Completed |  |  | 32333 | 22083.67 | 22083.67 | 2930.03 | 19224.94 | 0 | 22154.97 | 657 | 479.4
NHT-004026 - Final Report | 24-PC-35872 | In progress |  |  | 57128 | 39018.68 | 39018.68 | 4396.78 | 28848.78 | 0 | 33245.56 | 980 | 697.48
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-35872 | In progress |  |  | 0 | 0 | 0 | 0 | 268.04 | 0 | 268.04 | 0 | 6.5
NHT-004035 - Desktop Review | 24-PC-35881 | Completed |  |  | 72000 | 52610.1 | 52610.1 | 3693.5 | 38278.09 | 0 | 41971.59 | 929 | 752.83
NHT-004037 - Agency Consultation | 24-PC-35881 | Completed |  |  | 82200 | 60063.84 | 60063.84 | 4216.79 | 43701.28 | 0 | 47918.07 | 775 | 758.61
NHT-004042 - Reporting | 24-PC-36099 | In progress |  |  | 4747 | 3346.65 | 3346.65 | 391.57 | 2425.51 | 0 | 2817.08 | 52 | 44.34
NHT-004047 - Site Recordation | 24-PC-36099 | In progress |  |  | 3792 | 2673.59 | 2673.59 | 312.83 | 1937.71 | 0 | 2250.54 | 48 | 40.85
NHT-004054 - Project Management | 24-PC-36099 | In progress |  |  | 4361 | 3074.26 | 3074.26 | 359.71 | 2228.1 | 0 | 2587.81 | 57 | 44.92
NHT-004058 - Project Management | 24-PC-36146 | Completed |  |  | 12113 | 8118.32 | 8118.32 | 1541.6 | 7916.06 | 0 | 9457.66 | 175 | 150.04
NHT-004064 - Reporting | 24-PC-36146 | Completed |  |  | 15772 | 10570.12 | 10570.12 | 2007.17 | 10306.78 | 0 | 12313.95 | 164 | 199.33
NHT-004067 - Agency Consultation | 24-PC-36146 | Completed |  |  | 6552 | 4391.38 | 4391.38 | 833.89 | 4281.98 | 0 | 5115.87 | 74 | 81.95
NHT-004069 - Final Report | 24-PC-36146 | Completed |  |  | 10481 | 7024.45 | 7024.45 | 1333.88 | 6849.45 | 0 | 8183.33 | 125 | 129.18
NHT-004074 - GIS & Mapping | 24-PC-36146 | Completed |  |  | 13382 | 8968.39 | 8968.39 | 1703.02 | 8744.96 | 0 | 10447.98 | 124 | 183.54
NHT-004080 - Background Research | 24-PC-36161 | In progress |  |  | 5700 | 4244.79 | 4244.79 | 214.83 | 3040.21 | 0 | 3255.04 | 69 | 55.44
NHT-004084 - Fieldwork | 24-PC-36184 | On hold |  |  | 1603 | 944.66 | 944.66 | 135.82 | 492.97 | 0 | 628.79 | 12 | 9.13
NHT-004090 - Testing | 24-PC-36184 | On hold |  |  | 1325 | 780.82 | 780.82 | 112.27 | 407.48 | 0 | 519.75 | 6 | 7.4
NHT-004091 - Curation | 24-PC-36184 | On hold |  |  | 572 | 337.07 | 337.07 | 48.46 | 175.9 | 0 | 224.36 | 3 | 3.17
NHT-004097 - Data Recovery Excavation | 24-PC-36290 | Completed |  |  | 56300 | 37721 | 37721 | 6280.44 | 28610.89 | 0 | 34891.33 | 604 | 463.6
NHT-004101 - Site Recordation | 24-PC-36445 | On hold |  |  | 29112 | 19834.57 | 19834.57 | 3910.57 | 16563.61 | 0 | 20474.18 | 216 | 226.7
NHT-004107 - Desktop Review | 24-PC-36445 | On hold |  |  | 14189 | 9666.65 | 9666.65 | 1905.87 | 8072.5 | 0 | 9978.37 | 109 | 107.63
NHT-004113 - Prefield | 24-PC-36445 | On hold |  |  | 20299 | 13829.46 | 13829.46 | 2726.6 | 11548.81 | 0 | 14275.41 | 146 | 200.4
NHT-004117 - Curation | 24-PC-36559 | Completed |  |  | 5695 | 4296.52 | 4296.52 | 482.25 | 2569.96 | 0 | 3052.21 | 0 | 42.18
NHT-004122 - GIS & Mapping | 24-PC-36559 | Completed |  |  | 6105 | 4606.58 | 4606.58 | 517.05 | 2755.43 | 0 | 3272.48 | 0 | 39.49
NHT-004128 - GIS & Mapping | 24-PC-36620 | In progress |  |  | 316711 | 217073.54 | 217073.54 | 16345.35 | 116543.69 | 0 | 132889.04 | 0 | 1980.87
NHT-004135 - Agency Consultation | 24-PC-36620 | In progress |  |  | 51389 | 35222.2 | 35222.2 | 3711.81 | 26465.52 | 0 | 30177.33 | 0 | 611.97
NHT-004138 - GIS & Mapping | 24-PC-36676 | Completed |  |  | 20551 | 12911.78 | 13692.02 | 1694.18 | 10582.47 | 0 | 12276.65 | 237 | 146.85
NHT-004139 - Reporting | 24-PC-36676 | Completed |  |  | 47130 | 29610.24 | 31399.55 | 3885.21 | 24268.5 | 0 | 28153.71 | 445 | 371.96
NHT-004141 - Testing | 24-PC-36676 | Completed |  |  | 25519 | 16033.18 | 17002.05 | 2103.74 | 13140.77 | 0 | 15244.51 | 278 | 208.37
NHT-004145 - Final Report | 24-PC-36710 | On hold |  |  | 138500 | 97600.95 | 97600.95 | 8089 | 57675.21 | 0 | 65764.21 | 1211 | 902.91
NHT-004148 - Curation | 24-PC-36932 | Completed |  |  | 150 | 95.32 | 95.32 | 7.24 | 59.82 | 0 | 67.06 | 1 | 1.17
NHT-004152 - Testing | 24-PC-36932 | Completed |  |  | 1768 | 1120.57 | 1120.57 | 89.25 | 737.17 | 0 | 826.42 | 20 | 15.33
NHT-004155 - Reporting | 24-PC-36932 | Completed |  |  | 10282 | 6517.69 | 6517.69 | 597.97 | 4938.71 | 0 | 5536.68 | 90 | 108.12
NHT-004161 - Monitoring | 24-PC-36978 | Completed |  |  | 42218 | 34124.23 | 34124.23 | 6203.43 | 35152.77 | 0 | 41356.2 | 361 | 430.68
NHT-004168 - Site Recordation | 24-PC-36978 | In progress |  |  | 27818 | 22485.68 | 22485.68 | 4087.66 | 23163.41 | 0 | 27251.07 | 241 | 387.47
NHT-004170 - Survey | 24-PC-36978 | Completed |  |  | 35094 | 28366.79 | 28366.79 | 5156.78 | 29221.78 | 0 | 34378.56 | 262 | 523.22
NHT-004176 - Background Research | 24-PC-36978 | Completed |  |  | 10030 | 8106.94 | 8106.94 | 1473.76 | 8351.29 | 0 | 9825.05 | 66 | 124.39
NHT-004183 - Draft Report | 24-PC-36978 | Completed |  |  | 25840 | 20886.66 | 20886.66 | 3796.98 | 21516.2 | 0 | 25313.18 | 279 | 324.96
NHT-004190 - Background Research | 24-PC-37107 | Completed |  |  | 127602 | 86131.57 | 91553.62 | 12803.22 | 49348.32 | 0 | 62151.54 | 1073 | 676.59
NHT-004192 - Prefield | 24-PC-37107 | Completed |  |  | 131798 | 88963.91 | 94564.27 | 13224.23 | 50971.08 | 0 | 64195.31 | 1073 | 738.2
NHT-004193 - Draft Report | 24-PC-37125 | In progress |  |  | 506214 | 343314.64 | 343314.64 | 46848.61 | 206387.11 | 0 | 253235.72 | 4118 | 2743.81
NHT-004198 - Fieldwork | 24-PC-37125 | In progress |  |  | 641440 | 435024.02 | 435024.02 | 59363.24 | 261519.14 | 0 | 320882.38 | 5150 | 3573.3
NHT-004205 - Desktop Review | 24-PC-37125 | In progress |  |  | 111546 | 75650.78 | 75650.78 | 10323.28 | 45478.24 | 0 | 55801.52 | 784 | 690.52
NHT-004210 - Survey | 24-PC-37167 | Completed |  |  | 65600 | 48603.04 | 48603.04 | 5847.38 | 27758.22 | 0 | 33605.6 | 0 | 434.21
NHT-004213 - Testing | 24-PC-37235 | In progress |  |  | 36356 | 22090.07 | 22090.07 | 2116.97 | 14847.88 | 0 | 16964.85 | 185 | 232.22
NHT-004218 - Final Report | 24-PC-37235 | In progress |  |  | 30644 | 18619.13 | 18619.13 | 2128.85 | 14931.24 | 0 | 17060.09 | 131 | 195.79
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-37235 | In progress |  |  | 0 | 0 | 0 | 0 | 215.52 | 0 | 215.52 | 0 | 3
NHT-004224 - Prefield | 24-PC-37266 | In progress |  |  | 870 | 516.85 | 516.85 | 61.3 | 268.28 | 0 | 329.58 | 11 | 5.89
NHT-004230 - Site Recordation | 24-PC-37266 | In progress |  |  | 36849 | 21884.48 | 21884.48 | 2849 | 12468.19 | 0 | 15317.19 | 556 | 254.84
NHT-004231 - Reporting | 24-PC-37266 | In progress |  |  | 3681 | 2186.13 | 2186.13 | 269.63 | 1180.01 | 0 | 1449.64 | 45 | 27.64
NHT-004234 - Reporting | 24-PC-37336 | In progress |  |  | 104716 | 85563.24 | 85563.24 | 9728.4 | 49110.76 | 0 | 58839.16 | 0 | 763.1
NHT-004236 - Prefield | 24-PC-37336 | In progress |  |  | 42318 | 34577.92 | 34577.92 | 3770.38 | 19033.6 | 0 | 22803.98 | 0 | 329.19
NHT-004242 - Testing | 24-PC-37336 | In progress |  |  | 82628 | 67515.3 | 67515.3 | 7981.28 | 40290.98 | 0 | 48272.26 | 0 | 599.75
NHT-004246 - Data Recovery Excavation | 24-PC-37336 | In progress |  |  | 48198 | 39382.89 | 39382.89 | 4405.96 | 22242.11 | 0 | 26648.07 | 0 | 326.68
NHT-004250 - Final Report | 24-PC-37336 | In progress |  |  | 20640 | 16865 | 16865 | 2490.98 | 12574.94 | 0 | 15065.92 | 0 | 184.89
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-37336 | In progress |  |  | 0 | 0 | 0 | 0 | 2462.61 | 0 | 2462.61 | 0 | 33.5
NHT-004255 - Testing | 24-PC-37372 | Completed |  |  | 272100 | 221924.76 | 221924.76 | 18350.25 | 178523.69 | 0 | 196873.94 | 0 | 3652.63
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-37372 | Completed |  |  | 0 | 0 | 0 | 0 | 2585.3 | 0 | 2585.3 | 0 | 53.25
NHT-004269 - Agency Consultation | 24-PC-37415 | In progress |  |  | 16594 | 12854.04 | 12854.04 | 921.18 | 6885.42 | 0 | 7806.6 | 0 | 134.44
NHT-004274 - Reporting | 24-PC-37415 | In progress |  |  | 65832 | 50992.54 | 50992.54 | 3654.35 | 27314.77 | 0 | 30969.12 | 0 | 508.57
NHT-004276 - Lab Analysis | 24-PC-37415 | In progress |  |  | 52338 | 40541.33 | 40541.33 | 2905.38 | 21716.45 | 0 | 24621.83 | 0 | 466.73
NHT-004282 - GIS & Mapping | 24-PC-37415 | In progress |  |  | 26949 | 20874.85 | 20874.85 | 1495.99 | 11181.86 | 0 | 12677.85 | 0 | 191.36
NHT-004286 - Curation | 24-PC-37415 | In progress |  |  | 29287 | 22685.84 | 22685.84 | 1625.77 | 12151.94 | 0 | 13777.71 | 0 | 217.42
NHT-004288 - Site Recordation | 24-PC-37442 | In progress |  |  | 96396 | 57355.7 | 57355.7 | 8054.33 | 38502.47 | 0 | 46556.8 | 0 | 794.92
NHT-004293 - Survey | 24-PC-37442 | In progress |  |  | 213004 | 126737.3 | 126737.3 | 17797.42 | 85077.84 | 0 | 102875.26 | 0 | 1681.39
NHT-004294 - Draft Report | 24-PC-37686 | In progress |  |  | 50600 | 28376.76 | 39155.85 | 4195.56 | 27831.64 | 0 | 32027.2 | 490 | 519.5
NHT-004295 - Survey | 24-PC-37823 | Completed |  |  | 13907 | 10419.55 | 10419.55 | 577.38 | 7019.86 | 0 | 7597.24 | 193 | 123.52
NHT-004297 - Prefield | 24-PC-37823 | Completed |  |  | 4124 | 3089.86 | 3089.86 | 171.22 | 2081.7 | 0 | 2252.92 | 48 | 35.36
NHT-004303 - Lab Analysis | 24-PC-37823 | Completed |  |  | 5530 | 4142.72 | 4142.72 | 229.57 | 2791.03 | 0 | 3020.6 | 49 | 45.15
NHT-004309 - Project Management | 24-PC-37823 | Completed |  |  | 2856 | 2139.46 | 2139.46 | 118.56 | 1441.4 | 0 | 1559.96 | 32 | 28.96
NHT-004312 - Background Research | 24-PC-37823 | Completed |  |  | 2483 | 1860.29 | 1860.29 | 103.09 | 1253.31 | 0 | 1356.4 | 19 | 20.24
NHT-004316 - Desktop Review | 24-PC-37942 | Completed |  |  | 61385 | 44129.82 | 44129.82 | 6381.66 | 28773.58 | 0 | 35155.24 | 592 | 445.12
NHT-004318 - Reporting | 24-PC-37942 | Completed |  |  | 59622 | 42862.42 | 42862.42 | 6642.24 | 29948.47 | 0 | 36590.71 | 643 | 523.65
NHT-004321 - Prefield | 24-PC-37942 | Completed |  |  | 120393 | 86550.22 | 86550.22 | 12586.6 | 56750.28 | 0 | 69336.88 | 1187 | 862.67
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-37942 | Completed |  |  | 0 | 0 | 0 | 0 | 411.62 | 0 | 411.62 | 0 | 6.25
NHT-004331 - Agency Consultation | 24-PC-38054 | Completed |  |  | 7929 | 6729.39 | 6729.39 | 325.66 | 4261.15 | 0 | 4586.81 | 0 | 104.56
NHT-004338 - Background Research | 24-PC-38054 | Completed |  |  | 9848 | 8358.42 | 8358.42 | 404.5 | 5292.68 | 0 | 5697.18 | 0 | 116.04
NHT-004344 - Project Management | 24-PC-38054 | Completed |  |  | 25090 | 21293.81 | 21293.81 | 1030.5 | 13483.58 | 0 | 14514.08 | 0 | 282.68
NHT-004346 - Lab Analysis | 24-PC-38054 | Completed |  |  | 17833 | 15134.47 | 15134.47 | 732.42 | 9583.38 | 0 | 10315.8 | 0 | 240.52
NHT-004351 - Project Management | 24-PC-38141 | In progress |  |  | 44367 | 32077.71 | 32077.71 | 3542.47 | 25978.11 | 0 | 29520.58 | 607 | 529.12
NHT-004358 - GIS & Mapping | 24-PC-38141 | In progress |  |  | 29154 | 21078.4 | 21078.4 | 2327.77 | 17070.32 | 0 | 19398.09 | 301 | 343.57
NHT-004365 - Curation | 24-PC-38141 | In progress |  |  | 16466 | 11904.59 | 11904.59 | 1314.67 | 9640.92 | 0 | 10955.59 | 234 | 190.26
NHT-004366 - Testing | 24-PC-38141 | In progress |  |  | 42213 | 30519.9 | 30519.9 | 3370.43 | 24716.51 | 0 | 28086.94 | 562 | 495.37
NHT-004369 - Background Research | 24-PC-38374 | In progress |  |  | 481100 | 330082.71 | 330082.71 | 25265.32 | 204419.41 | 0 | 229684.73 | 6959 | 4079.75
NHT-004374 - Prefield | 24-PC-38426 | Completed |  |  | 25169 | 20711.53 | 20711.53 | 4408.77 | 17416.84 | 0 | 21825.61 | 0 | 375.46
NHT-004376 - Reporting | 24-PC-38426 | Completed |  |  | 74081 | 60960.89 | 60960.89 | 12976.48 | 51263.51 | 0 | 64239.99 | 0 | 1223.74
NHT-004382 - Monitoring | 24-PC-38426 | Completed |  |  | 79832 | 65694.07 | 65694.07 | 13984.01 | 55243.76 | 0 | 69227.77 | 0 | 1134.35
NHT-004385 - Lab Analysis | 24-PC-38426 | Completed |  |  | 23918 | 19682.21 | 19682.21 | 4189.66 | 16551.25 | 0 | 20740.91 | 0 | 267.37
NHT-004390 - Background Research | 24-PC-38469 | In progress |  |  | 124616 | 69247.37 | 82601.2 | 14127.45 | 55716.34 | 0 | 69843.79 | 1080 | 1039.04
NHT-004392 - Lab Analysis | 24-PC-38469 | In progress |  |  | 67424 | 37466.55 | 44691.69 | 7529.27 | 29694.22 | 0 | 37223.49 | 670 | 472.15
NHT-004396 - Curation | 24-PC-38469 | In progress |  |  | 122327 | 67975.44 | 81083.99 | 13223.25 | 52150.33 | 0 | 65373.58 | 1214 | 903.81
NHT-004403 - Reporting | 24-PC-38469 | In progress |  |  | 212348 | 117998.6 | 140753.74 | 22389.03 | 88298.73 | 0 | 110687.76 | 2480 | 1875.52
NHT-004406 - Prefield | 24-PC-38469 | In progress |  |  | 129985 | 72230.72 | 86159.86 | 13378.32 | 52761.91 | 0 | 66140.23 | 1659 | 1072.88
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-38469 | In progress |  |  | 0 | 0 | 0 | 0 | 470.36 | 0 | 470.36 | 0 | 9.75
NHT-004413 - Curation | 24-PC-38486 | In progress |  |  | 21014 | 10602.94 | 14371.08 | 1525.1 | 14873.84 | 0 | 16398.94 | 203 | 322.98
NHT-004417 - Background Research | 24-PC-38486 | In progress |  |  | 27949 | 14101.86 | 19113.47 | 2028.38 | 19782.14 | 0 | 21810.52 | 279 | 369.31
NHT-004418 - Fieldwork | 24-PC-38486 | Completed |  |  | 104637 | 52796.18 | 71559.26 | 7594.08 | 74062.7 | 0 | 81656.78 | 1247 | 1612.54
NHT-004425 - Project Management | 24-PC-38579 | Completed |  |  | 59100 | 39502.44 | 39502.44 | 2115.66 | 32567.3 | 0 | 34682.96 | 508 | 631.12
NHT-004426 - Monitoring | 24-PC-38687 | In progress |  |  | 29276 | 21143.24 | 21143.24 | 2096.38 | 10091.94 | 0 | 12188.32 | 358 | 202.75
NHT-004432 - Prefield | 24-PC-38687 | In progress |  |  | 7354 | 5311.3 | 5311.3 | 526.63 | 2535.15 | 0 | 3061.78 | 80 | 62.32
NHT-004433 - Project Management | 24-PC-38687 | In progress |  |  | 12681 | 9158.14 | 9158.14 | 908.05 | 4371.29 | 0 | 5279.34 | 158 | 85.99
NHT-004440 - Testing | 24-PC-38687 | In progress |  |  | 19289 | 13930.24 | 13930.24 | 1381.21 | 6649.07 | 0 | 8030.28 | 236 | 151.02
NHT-004441 - GIS & Mapping | 24-PC-38790 | Completed |  |  | 168200 | 130489.56 | 130489.56 | 19437.91 | 112792.76 | 0 | 132230.67 | 1711 | 2212.09
NHT-004444 - Testing | 24-PC-38795 | Completed |  |  | 207073 | 117710.17 | 140016.21 | 10592.6 | 126973.71 | 0 | 137566.31 | 2171 | 2416.46
NHT-004449 - Data Recovery Excavation | 24-PC-38795 | Completed |  |  | 284393 | 161663.33 | 192298.49 | 14547.9 | 174385.88 | 0 | 188933.78 | 4300 | 3561.37
NHT-004456 - Reporting | 24-PC-38795 | Completed |  |  | 193034 | 109729.86 | 130523.64 | 9874.47 | 118365.37 | 0 | 128239.84 | 2464 | 2052.69
NHT-004462 - GIS & Mapping | 24-PC-38817 | Completed |  |  | 1966200 | 1268002.38 | 1268002.38 | 198219 | 1123241.02 | 0 | 1321460.02 | 14990 | 22156.26
NHT-004465 - Background Research | 24-PC-38847 | On hold |  |  | 70509 | 55560.93 | 55560.93 | 4055.93 | 32483.98 | 0 | 36539.91 | 1031 | 683.38
NHT-004471 - Agency Consultation | 24-PC-38847 | On hold |  |  | 48091 | 37895.87 | 37895.87 | 2766.39 | 22156.02 | 0 | 24922.41 | 739 | 444.66
NHT-004474 - Background Research | 24-PC-39091 | Completed |  |  | 100200 | 72685.08 | 72685.08 | 20215.85 | 82041.44 | 0 | 102257.29 | 1304 | 1547.33
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-39091 | In progress |  |  | 0 | 0 | 0 | 0 | 1413.71 | 0 | 1413.71 | 0 | 20.75
NHT-004483 - Agency Consultation | 24-PC-39206 | In progress |  |  | 16631 | 10848.2 | 10848.2 | 503.23 | 7359.77 | 0 | 7863 | 0 | 134.2
NHT-004485 - Reporting | 24-PC-39206 | In progress |  |  | 60321 | 39347.74 | 39347.74 | 1825.29 | 26694.81 | 0 | 28520.1 | 0 | 616.22
NHT-004491 - Final Report | 24-PC-39206 | In progress |  |  | 49648 | 32385.24 | 32385.24 | 1502.3 | 21971.21 | 0 | 23473.51 | 0 | 404.87
NHT-004495 - Testing | 24-PC-39213 | In progress |  |  | 597800 | 435557.08 | 435557.08 | 21068.62 | 310474.23 | 0 | 331542.85 | 5341 | 5422.97
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-39213 | In progress |  |  | 0 | 0 | 0 | 0 | 2879.71 | 0 | 2879.71 | 0 | 48.25
NHT-004499 - Background Research | 24-PC-39308 | Completed |  |  | 1084 | 712.5 | 712.5 | 98.13 | 634.17 | 0 | 732.3 | 9 | 13.55
NHT-004502 - Agency Consultation | 24-PC-39308 | Completed |  |  | 979 | 643.25 | 643.25 | 88.59 | 572.53 | 0 | 661.12 | 7 | 12.45
NHT-004504 - Testing | 24-PC-39308 | Completed |  |  | 2664 | 1750.15 | 1750.15 | 241.03 | 1557.74 | 0 | 1798.77 | 23 | 28.84
NHT-004506 - Data Recovery Excavation | 24-PC-39308 | Completed |  |  | 6273 | 4121.1 | 4121.1 | 567.57 | 3668.03 | 0 | 4235.6 | 49 | 77.54
NHT-004513 - Background Research | 24-PC-39405 | Completed |  |  | 26881 | 15244.14 | 18052.66 | 850.38 | 13090.31 | 0 | 13940.69 | 282 | 237.76
NHT-004517 - Desktop Review | 24-PC-39405 | Completed |  |  | 14056 | 7971.23 | 9439.82 | 444.67 | 6844.99 | 0 | 7289.66 | 141 | 136.03
NHT-004520 - Data Recovery Excavation | 24-PC-39405 | Completed |  |  | 118763 | 67348.38 | 79756.37 | 3756.98 | 57832.81 | 0 | 61589.79 | 1293 | 1191.81
NHT-004521 - Site Recordation | 24-PC-39479 | Completed |  |  | 107708 | 76171.45 | 76171.45 | 4690.16 | 48008.3 | 0 | 52698.46 | 1734 | 935.12
NHT-004526 - Survey | 24-PC-39479 | Completed |  |  | 87277 | 61722.01 | 61722.01 | 3957.34 | 40507.12 | 0 | 44464.46 | 1406 | 769.21
NHT-004533 - Data Recovery Excavation | 24-PC-39479 | Completed |  |  | 38015 | 26884.14 | 26884.14 | 1741.81 | 17829.13 | 0 | 19570.94 | 589 | 350.55
NHT-004538 - Lab Analysis | 24-PC-39511 | Completed |  |  | 33000 | 20462.4 | 23227.58 | 5274.77 | 24341.42 | 0 | 29616.19 | 0 | 501.33
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-39511 | In progress |  |  | 0 | 0 | 0 | 0 | 17.34 | 0 | 17.34 | 0 | 0.25
NHT-004546 - Fieldwork | 24-PC-39533 | In progress |  |  | 45629 | 35850.82 | 35850.82 | 2481.75 | 31514.82 | 0 | 33996.57 | 0 | 617.95
NHT-004549 - Draft Report | 24-PC-39533 | In progress |  |  | 21371 | 16791.08 | 16791.08 | 1162.35 | 14760.28 | 0 | 15922.63 | 0 | 322.81
NHT-004554 - Prefield | 24-PC-39694 | In progress |  |  | 136500 | 70843.68 | 93075.52 | 10588.63 | 66700.67 | 0 | 77289.3 | 1695 | 1240.48
NHT-004555 - Background Research | 24-PC-39789 | On hold |  |  | 8783 | 5701.87 | 7042.3 | 300.19 | 3190.34 | 0 | 3490.53 | 0 | 52.47
NHT-004557 - Desktop Review | 24-PC-39789 | On hold |  |  | 12742 | 8271.98 | 10216.59 | 435.49 | 4628.37 | 0 | 5063.86 | 0 | 104.72
NHT-004560 - Reporting | 24-PC-39789 | On hold |  |  | 30683 | 19919.69 | 24602.5 | 1048.71 | 11145.55 | 0 | 12194.26 | 0 | 223.27
NHT-004564 - Data Recovery Excavation | 24-PC-39789 | On hold |  |  | 53584 | 34787.26 | 42965.19 | 1831.43 | 19464.3 | 0 | 21295.73 | 0 | 413.99
NHT-004566 - Lab Analysis | 24-PC-39789 | On hold |  |  | 20208 | 13118.94 | 16203 | 690.67 | 7340.36 | 0 | 8031.03 | 0 | 123.45
NHT-004572 - Prefield | 24-PC-39822 | Completed |  |  | 17468 | 11521.94 | 13952.15 | 1222.36 | 11379.33 | 0 | 12601.69 | 194 | 228.2
NHT-004573 - Final Report | 24-PC-39822 | Completed |  |  | 14771 | 9743.09 | 11798.1 | 1033.65 | 9622.5 | 0 | 10656.15 | 181 | 195.28
NHT-004578 - Monitoring | 24-PC-39822 | Completed |  |  | 60800 | 40103.67 | 48562.36 | 4254.6 | 39607.31 | 0 | 43861.91 | 679 | 929.34
NHT-004580 - Curation | 24-PC-39822 | Completed |  |  | 16461 | 10857.62 | 13147.71 | 1151.89 | 10723.24 | 0 | 11875.13 | 171 | 194.24
NHT-004586 - Final Report | 24-PC-39825 | Completed |  |  | 2694 | 1595.18 | 2165.81 | 457.08 | 1761.75 | 0 | 2218.83 | 29 | 34.01
NHT-004589 - Project Management | 24-PC-39825 | Completed |  |  | 3805 | 2252.57 | 3058.36 | 645.44 | 2487.77 | 0 | 3133.21 | 48 | 50.13
NHT-004595 - Desktop Review | 24-PC-39825 | In progress |  |  | 3030 | 1794.06 | 2435.83 | 514.06 | 1981.38 | 0 | 2495.44 | 34 | 40.49
NHT-004596 - Site Recordation | 24-PC-39825 | Completed |  |  | 5406 | 3200.99 | 4346.05 | 917.2 | 3535.21 | 0 | 4452.41 | 88 | 70.97
NHT-004601 - Curation | 24-PC-39825 | In progress |  |  | 2865 | 1696.15 | 2302.9 | 486.01 | 1873.26 | 0 | 2359.27 | 39 | 30.91
NHT-004605 - Testing | 24-PC-39923 | In progress |  |  | 171460 | 111877.69 | 111877.69 | 6585.03 | 72254.76 | 0 | 78839.79 | 2067 | 1598.57
NHT-004608 - Agency Consultation | 24-PC-39923 | In progress |  |  | 125334 | 81780.63 | 81780.63 | 5561 | 61018.55 | 0 | 66579.55 | 1176 | 1470.06
NHT-004611 - Survey | 24-PC-39923 | In progress |  |  | 118106 | 77063.93 | 77063.93 | 5747.9 | 63069.29 | 0 | 68817.19 | 1630 | 1445.49
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-39923 | In progress |  |  | 0 | 0 | 0 | 0 | 1353.01 | 0 | 1353.01 | 0 | 29.25
NHT-004618 - Lab Analysis | 24-PC-39940 | In progress |  |  | 20400 | 16397.52 | 16397.52 | 865.85 | 9693.32 | 0 | 10559.17 | 268 | 168.48
NHT-004625 - Data Recovery Excavation | 24-PC-40067 | In progress |  |  | 93959 | 70516.39 | 70516.39 | 7348.92 | 51916.61 | 0 | 59265.53 | 641 | 986.74
NHT-004629 - Survey | 24-PC-40067 | In progress |  |  | 40828 | 30641.31 | 30641.31 | 3193.31 | 22559.2 | 0 | 25752.51 | 396 | 467.92
NHT-004630 - Draft Report | 24-PC-40067 | In progress |  |  | 31310 | 23498.05 | 23498.05 | 2448.87 | 17300.07 | 0 | 19748.94 | 271 | 357.58
NHT-004631 - Reporting | 24-PC-40067 | In progress |  |  | 52003 | 39028.3 | 39028.3 | 4067.37 | 28733.98 | 0 | 32801.35 | 430 | 596.56
NHT-004638 - Survey | 24-PC-40078 | Completed |  |  | 660822 | 419687.99 | 419687.99 | 56681.15 | 269072.6 | 0 | 325753.75 | 6253 | 4694.81
NHT-004640 - Monitoring | 24-PC-40078 | Completed |  |  | 764916 | 485798 | 485798 | 65609.67 | 311457.4 | 0 | 377067.07 | 7032 | 5368.98
NHT-004646 - Lab Analysis | 24-PC-40078 | Completed |  |  | 394362 | 250459.52 | 250459.52 | 33825.93 | 160575.95 | 0 | 194401.88 | 3404 | 3026.14
NHT-004650 - Monitoring | 24-PC-40091 | Completed |  |  | 121900 | 105126.56 | 105126.56 | 22204.94 | 95281.53 | 0 | 117486.47 | 1805 | 1676.67
NHT-004651 - Reporting | 24-PC-40102 | Completed |  |  | 217276 | 133455.68 | 154227.22 | 26178.95 | 142374.53 | 0 | 168553.48 | 2643 | 3259.37
NHT-004656 - Testing | 24-PC-40102 | Completed |  |  | 127189 | 78122.09 | 90281.31 | 15809.25 | 85978.76 | 0 | 101788.01 | 1581 | 2411.96
NHT-004659 - Lab Analysis | 24-PC-40102 | Completed |  |  | 61989 | 38074.65 | 44000.73 | 7747.19 | 42133.19 | 0 | 49880.38 | 640 | 981.85
NHT-004663 - Fieldwork | 24-PC-40102 | Completed |  |  | 47446 | 29141.98 | 33677.75 | 6063.77 | 32977.86 | 0 | 39041.63 | 598 | 726.93
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-40102 | Completed |  |  | 0 | 0 | 0 | 0 | 731.1 | 0 | 731.1 | 0 | 14.5
NHT-004669 - Testing | 24-PC-40218 | In progress |  |  | 35427 | 24026.46 | 24026.46 | 2172.74 | 10683.72 | 0 | 12856.46 | 230 | 178.21
NHT-004671 - Site Recordation | 24-PC-40218 | In progress |  |  | 14520 | 9847.17 | 9847.17 | 890.49 | 4378.69 | 0 | 5269.18 | 159 | 91.55
NHT-004678 - Project Management | 24-PC-40218 | In progress |  |  | 12742 | 8641.88 | 8641.88 | 781.5 | 3842.74 | 0 | 4624.24 | 115 | 68.26
NHT-004684 - Data Recovery Excavation | 24-PC-40218 | In progress |  |  | 33404 | 22654.82 | 22654.82 | 2048.7 | 10073.8 | 0 | 12122.5 | 354 | 166.95
NHT-004686 - Monitoring | 24-PC-40218 | In progress |  |  | 44907 | 30455.87 | 30455.87 | 2754.16 | 13542.66 | 0 | 16296.82 | 311 | 269.61
NHT-004690 - Draft Report | 24-PC-40271 | Completed |  |  | 499483 | 259891.85 | 329934.08 | 32963.92 | 369035.1 | 0 | 401999.02 | 5598 | 5813.32
NHT-004697 - Monitoring | 24-PC-40271 | Completed |  |  | 499134 | 259710.53 | 329703.88 | 32940.92 | 368777.62 | 0 | 401718.54 | 5313 | 7646.28
NHT-004700 - Desktop Review | 24-PC-40271 | Completed |  |  | 147583 | 76790.74 | 97486.24 | 9739.91 | 109039.5 | 0 | 118779.41 | 1601 | 2127.47
NHT-004701 - Prefield | 24-PC-40317 | In progress |  |  | 33954 | 23054.69 | 23054.69 | 2434.38 | 10583.69 | 0 | 13018.07 | 283 | 199.5
NHT-004707 - Monitoring | 24-PC-40317 | In progress |  |  | 115689 | 78553.03 | 78553.03 | 8294.53 | 36061.26 | 0 | 44355.79 | 1002 | 796.61
NHT-004713 - Draft Report | 24-PC-40317 | In progress |  |  | 76157 | 51710.48 | 51710.48 | 5460.19 | 23738.68 | 0 | 29198.87 | 892 | 456.12
NHT-004720 - Site Recordation | 24-PC-40427 | Completed |  |  | 121700 | 90556.97 | 90556.97 | 15879.38 | 87233.51 | 0 | 103112.89 | 0 | 1375.63
NHT-004724 - GIS & Mapping | 24-PC-40479 | In progress |  |  | 42819 | 33929.62 | 33929.62 | 1731.3 | 19909.99 | 0 | 21641.29 | 282 | 379.95
NHT-004731 - Lab Analysis | 24-PC-40479 | In progress |  |  | 41543 | 32918.61 | 32918.61 | 1679.71 | 19316.73 | 0 | 20996.44 | 258 | 355.36
NHT-004734 - Draft Report | 24-PC-40479 | In progress |  |  | 55238 | 43770.81 | 43770.81 | 2233.47 | 25684.84 | 0 | 27918.31 | 395 | 466.87
NHT-004739 - Survey | 24-PC-40561 | In progress |  |  | 1118176 | 623240.31 | 835853.32 | 54895.67 | 516549.32 | 0 | 571444.99 | 14189 | 6754.41
NHT-004741 - Project Management | 24-PC-40561 | In progress |  |  | 838378 | 467288.71 | 626700.19 | 43784.83 | 412000.14 | 0 | 455784.97 | 10306 | 5621.78
NHT-004746 - Desktop Review | 24-PC-40561 | In progress |  |  | 379246 | 211380.89 | 283491.64 | 20903.44 | 196694.12 | 0 | 217597.56 | 4469 | 2581.81
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-40561 | In progress |  |  | 0 | 0 | 0 | 0 | 838.52 | 0 | 838.52 | 0 | 16.25
NHT-004749 - Curation | 24-PC-40634 | In progress |  |  | 320136 | 264880.79 | 264880.79 | 23718.81 | 161470.77 | 0 | 185189.58 | 0 | 3806.51
NHT-004752 - Prefield | 24-PC-40634 | In progress |  |  | 140364 | 116136.91 | 116136.91 | 10863.91 | 73958.33 | 0 | 84822.24 | 0 | 1817.45
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-40634 | In progress |  |  | 0 | 0 | 0 | 0 | 165.66 | 0 | 165.66 | 0 | 3.5
NHT-004756 - Monitoring | 24-PC-40659 | Completed |  |  | 14375 | 10102.53 | 10102.53 | 1809.52 | 7470.08 | 0 | 9279.6 | 123 | 144.59
NHT-004759 - Survey | 24-PC-40659 | Completed |  |  | 17317 | 12170.97 | 12170.97 | 2180.01 | 8999.53 | 0 | 11179.54 | 138 | 168.68
NHT-004766 - Reporting | 24-PC-40659 | Completed |  |  | 12888 | 9057.47 | 9057.47 | 1622.34 | 6697.34 | 0 | 8319.68 | 98 | 141.17
NHT-004772 - GIS & Mapping | 24-PC-40659 | Completed |  |  | 5720 | 4019.87 | 4019.87 | 720.02 | 2972.4 | 0 | 3692.42 | 49 | 62.03
NHT-004779 - Desktop Review | 24-PC-40670 | Completed |  |  | 3935 | 3190.71 | 3190.71 | 572.86 | 8388.54 | 0 | 8961.4 | 60 | 193.07
NHT-004782 - Monitoring | 24-PC-40670 | Completed |  |  | 1916 | 1553.1 | 1553.1 | 224.69 | 3290.26 | 0 | 3514.95 | 28 | 75.97
NHT-004784 - Testing | 24-PC-40670 | Completed |  |  | 1728 | 1401.16 | 1401.16 | 292.79 | 4287.44 | 0 | 4580.23 | 30 | 97.45
NHT-004789 - Survey | 24-PC-40670 | Completed |  |  | 3327 | 2697.72 | 2697.72 | 374.79 | 5488.16 | 0 | 5862.95 | 53 | 130.43
NHT-004796 - Data Recovery Excavation | 24-PC-40670 | Completed |  |  | 11194 | 9075.99 | 9075.99 | 651.8 | 9544.53 | 0 | 10196.33 | 187 | 205.74
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-40670 | Completed |  |  | 0 | 0 | 0 | 0 | 486.24 | 0 | 486.24 | 0 | 11.25
NHT-004809 - Monitoring | 24-PC-40782 | In progress |  |  | 48400 | 37137.32 | 37137.32 | 8288.42 | 38553.64 | 0 | 46842.06 | 0 | 864.91
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-40782 | In progress |  |  | 0 | 0 | 0 | 0 | 520.32 | 0 | 520.32 | 0 | 12
NHT-004819 - Desktop Review | 24-PC-40824 | Completed |  |  | 2393 | 1578.41 | 1578.41 | 171.34 | 1508.5 | 0 | 1679.84 | 18 | 30.12
NHT-004820 - Draft Report | 24-PC-40824 | Completed |  |  | 7213 | 4757.56 | 4757.56 | 516.45 | 4546.81 | 0 | 5063.26 | 51 | 98.95
NHT-004821 - Survey | 24-PC-40824 | Completed |  |  | 10742 | 7085.42 | 7085.42 | 769.15 | 6771.56 | 0 | 7540.71 | 75 | 125.59
NHT-004823 - Monitoring | 24-PC-40824 | Completed |  |  | 11452 | 7553.89 | 7553.89 | 820.02 | 7219.28 | 0 | 8039.3 | 109 | 141.82
NHT-004829 - GIS & Mapping | 24-PC-40836 | On hold |  |  | 17000 | 11633.1 | 11633.1 | 1505.83 | 8668.7 | 0 | 10174.53 | 171 | 175.61
NHT-004834 - Desktop Review | 24-PC-40888 | Completed |  |  | 50660 | 34322.26 | 34322.26 | 6549.08 | 29633.69 | 0 | 36182.77 | 448 | 539.27
NHT-004836 - Background Research | 24-PC-40888 | Completed |  |  | 42082 | 28510.67 | 28510.67 | 5440.16 | 24615.99 | 0 | 30056.15 | 331 | 417.5
NHT-004838 - Testing | 24-PC-40888 | Completed |  |  | 195709 | 132592.65 | 132592.65 | 25300.2 | 114479.92 | 0 | 139780.12 | 1323 | 2287.68
NHT-004839 - Curation | 24-PC-40888 | Completed |  |  | 50872 | 34466.03 | 34466.03 | 6576.51 | 29757.82 | 0 | 36334.33 | 479 | 708.88
NHT-004844 - Fieldwork | 24-PC-40888 | Completed |  |  | 239977 | 162584.14 | 162584.14 | 31022.93 | 140374.44 | 0 | 171397.37 | 1930 | 2245.85
NHT-004848 - Final Report | 24-PC-40956 | Completed |  |  | 4009 | 3149.58 | 3149.58 | 708.69 | 2602.94 | 0 | 3311.63 | 0 | 54.67
NHT-004853 - Site Recordation | 24-PC-40956 | Completed |  |  | 4791 | 3764.58 | 3764.58 | 847.07 | 3111.2 | 0 | 3958.27 | 0 | 76.18
NHT-004859 - Monitoring | 24-PC-41023 | In progress |  |  | 41561 | 27422.32 | 27422.32 | 4205.4 | 17584.26 | 0 | 21789.66 | 406 | 332.24
NHT-004860 - Curation | 24-PC-41023 | In progress |  |  | 10168 | 6708.65 | 6708.65 | 1028.82 | 4301.85 | 0 | 5330.67 | 70 | 105
NHT-004866 - Final Report | 24-PC-41023 | In progress |  |  | 8871 | 5852.91 | 5852.91 | 897.59 | 3753.12 | 0 | 4650.71 | 58 | 69.86
NHT-004868 - Background Research | 24-PC-41066 | Completed |  |  | 3441 | 1747.23 | 2206.25 | 400.3 | 1621.42 | 0 | 2021.72 | 23 | 31.33
NHT-004869 - Final Report | 24-PC-41066 | Completed |  |  | 2738 | 1390.37 | 1755.64 | 318.54 | 1290.26 | 0 | 1608.8 | 24 | 24.63
NHT-004874 - Survey | 24-PC-41066 | Completed |  |  | 9993 | 5074.59 | 6407.76 | 1162.63 | 4709.21 | 0 | 5871.84 | 101 | 67.45
NHT-004879 - Fieldwork | 24-PC-41066 | Completed |  |  | 9135 | 4639.19 | 5857.97 | 1062.87 | 4305.15 | 0 | 5368.02 | 69 | 81.04
NHT-004885 - Lab Analysis | 24-PC-41066 | Completed |  |  | 5093 | 2586.5 | 3266.01 | 592.58 | 2400.26 | 0 | 2992.84 | 35 | 54.53
NHT-004889 - Fieldwork | 24-PC-41067 | Completed |  |  | 280673 | 187798.36 | 187798.36 | 21684.75 | 188846.88 | 0 | 210531.63 | 2587 | 3836.78
NHT-004894 - Agency Consultation | 24-PC-41067 | Completed |  |  | 28904 | 19339.73 | 19339.73 | 2233.13 | 19447.71 | 0 | 21680.84 | 275 | 369.68
NHT-004898 - Final Report | 24-PC-41067 | Completed |  |  | 54523 | 36481.22 | 36481.22 | 4212.43 | 36684.91 | 0 | 40897.34 | 525 | 663.07
NHT-004905 - Curation | 24-PC-41119 | Completed |  |  | 4058 | 2775.71 | 2775.71 | 567.01 | 6512.6 | 0 | 7079.61 | 23 | 83.54
NHT-004912 - Site Recordation | 24-PC-41119 | Completed |  |  | 5457 | 3732.65 | 3732.65 | 471.36 | 5413.95 | 0 | 5885.31 | 35 | 50.04
NHT-004913 - Fieldwork | 24-PC-41119 | Completed |  |  | 3843 | 2628.62 | 2628.62 | 337.43 | 3875.64 | 0 | 4213.07 | 25 | 56.18
NHT-004918 - Desktop Review | 24-PC-41119 | Completed |  |  | 1985 | 1357.46 | 1357.46 | 205.96 | 2365.56 | 0 | 2571.52 | 11 | 25.89
NHT-004925 - Prefield | 24-PC-41119 | Completed |  |  | 2657 | 1817.56 | 1817.56 | 213.3 | 2449.93 | 0 | 2663.23 | 15 | 26.15
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-41119 | Completed |  |  | 0 | 0 | 0 | 0 | 309.49 | 0 | 309.49 | 0 | 3.75
NHT-004933 - Fieldwork | 24-PC-41154 | In progress |  |  | 194900 | 131089.74 | 131089.74 | 9084.85 | 117093.56 | 0 | 126178.41 | 1042 | 2232.38
NHT-004939 - Reporting | 24-PC-41534 | On hold |  |  | 795200 | 579859.84 | 579859.84 | 54911.11 | 286151.68 | 0 | 341062.79 | 0 | 5601.2
NHT-004942 - Testing | 24-PC-41555 | Completed |  |  | 13285 | 9393.8 | 9393.8 | 1359.79 | 10362.57 | 0 | 11722.36 | 144 | 203.66
NHT-004945 - Data Recovery Excavation | 24-PC-41555 | Completed |  |  | 24915 | 17617.42 | 17617.42 | 2550.2 | 19434.29 | 0 | 21984.49 | 252 | 373.78
NHT-004951 - Survey | 24-PC-41572 | On hold |  |  | 75162 | 52877.09 | 56544.68 | 4825.63 | 35055.66 | 0 | 39881.29 | 986 | 582.66
NHT-004955 - Testing | 24-PC-41572 | On hold |  |  | 51638 | 36327.27 | 38846.95 | 3315.28 | 24083.71 | 0 | 27398.99 | 628 | 481.68
NHT-004956 - Site Recordation | 24-PC-41701 | On hold |  |  | 51552 | 32689.06 | 32689.06 | 5507.1 | 22447.72 | 0 | 27954.82 | 423 | 383.06
NHT-004961 - Fieldwork | 24-PC-41701 | On hold |  |  | 109485 | 69424.59 | 69424.59 | 11695.91 | 47674.18 | 0 | 59370.09 | 785 | 867.3
NHT-004967 - Prefield | 24-PC-41701 | On hold |  |  | 28063 | 17794.66 | 17794.66 | 2997.85 | 12219.67 | 0 | 15217.52 | 261 | 221.87
NHT-004970 - Desktop Review | 24-PC-41886 | Completed |  |  | 56892 | 39466.23 | 39466.23 | 4665.36 | 20003.45 | 0 | 24668.81 | 468 | 323.83
NHT-004973 - Monitoring | 24-PC-41886 | Completed |  |  | 10608 | 7358.52 | 7358.52 | 844.39 | 3620.45 | 0 | 4464.84 | 75 | 57.15
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-41886 | Completed |  |  | 0 | 0 | 0 | 0 | 173.55 | 0 | 173.55 | 0 | 2.75
NHT-004982 - Project Management | 24-PC-41904 | Completed |  |  | 13038 | 9060 | 9060 | 1575.27 | 7375.11 | 0 | 8950.38 | 133 | 142.83
NHT-004986 - Site Recordation | 24-PC-41904 | Completed |  |  | 18462 | 12829.35 | 12829.35 | 2230.64 | 10443.47 | 0 | 12674.11 | 148 | 177.09
NHT-004987 - Reporting | 24-PC-41969 | Completed |  |  | 3504 | 2611.51 | 2611.51 | 168.81 | 1553.72 | 0 | 1722.53 | 67 | 37.29
NHT-004991 - Lab Analysis | 24-PC-41969 | Completed |  |  | 2336 | 1741.01 | 1741.01 | 112.54 | 1035.81 | 0 | 1148.35 | 42 | 22.99
NHT-004996 - Curation | 24-PC-41969 | Completed |  |  | 49543 | 36919.58 | 36919.58 | 2397.09 | 22062.99 | 0 | 24460.08 | 801 | 436.26
NHT-005001 - Site Recordation | 24-PC-41969 | Completed |  |  | 161117 | 120063.7 | 120063.7 | 7827.81 | 72047.9 | 0 | 79875.71 | 2939 | 1903.88
NHT-005008 - Prefield | 24-PC-42121 | Completed |  |  | 12137 | 8602.45 | 9465.17 | 1804.75 | 7846.34 | 0 | 9651.09 | 110 | 102.37
NHT-005011 - Monitoring | 24-PC-42121 | In progress |  |  | 33211 | 23539 | 25899.67 | 4606.92 | 20029.02 | 0 | 24635.94 | 299 | 292.35
NHT-005014 - Desktop Review | 24-PC-42121 | In progress |  |  | 35369 | 25068.74 | 27582.83 | 4620.78 | 20089.26 | 0 | 24710.04 | 337 | 402.35
NHT-005015 - Background Research | 24-PC-42121 | In progress |  |  | 129884 | 92057.35 | 101289.55 | 16715.74 | 72673.25 | 0 | 89388.99 | 1172 | 1271.69
NHT-005018 - Site Recordation | 24-PC-42121 | In progress |  |  | 56699 | 40186.42 | 44216.62 | 7355.34 | 31978.03 | 0 | 39333.37 | 448 | 570.34
NHT-005023 - Final Report | 24-PC-42174 | On hold |  |  | 8981 | 6230.95 | 6230.95 | 409.03 | 2512.62 | 0 | 2921.65 | 74 | 42.32
NHT-005025 - Project Management | 24-PC-42174 | On hold |  |  | 11819 | 8200.09 | 8200.09 | 538.3 | 3306.67 | 0 | 3844.97 | 103 | 60.66
NHT-005032 - Reporting | 24-PC-42184 | In progress |  |  | 7178 | 5042.99 | 5042.99 | 274.7 | 1940.6 | 0 | 2215.3 | 73 | 33.9
NHT-005036 - Data Recovery Excavation | 24-PC-42184 | In progress |  |  | 9378 | 6589.47 | 6589.47 | 358.93 | 2535.71 | 0 | 2894.64 | 71 | 42.84
NHT-005039 - Desktop Review | 24-PC-42184 | In progress |  |  | 1848 | 1298.4 | 1298.4 | 70.73 | 499.64 | 0 | 570.37 | 12 | 9.16
NHT-005044 - Final Report | 24-PC-42184 | In progress |  |  | 2034 | 1428.91 | 1428.91 | 77.83 | 549.86 | 0 | 627.69 | 15 | 9.61
NHT-005048 - Lab Analysis | 24-PC-42184 | In progress |  |  | 5162 | 3626.79 | 3626.79 | 197.56 | 1395.63 | 0 | 1593.19 | 38 | 25.88
NHT-005051 - Testing | 24-PC-42267 | On hold |  |  | 19531 | 12316.89 | 13072.65 | 886.88 | 4269.44 | 0 | 5156.32 | 164 | 81.01
NHT-005052 - Background Research | 24-PC-42267 | On hold |  |  | 5738 | 3618.79 | 3840.83 | 260.57 | 1254.39 | 0 | 1514.96 | 58 | 19.56
NHT-005056 - Lab Analysis | 24-PC-42267 | On hold |  |  | 14216 | 8964.95 | 9515.03 | 645.53 | 3107.54 | 0 | 3753.07 | 125 | 58.89
NHT-005062 - Curation | 24-PC-42267 | On hold |  |  | 9515 | 6000.87 | 6369.08 | 432.1 | 2080.09 | 0 | 2512.19 | 75 | 43.75
NHT-005067 - Testing | 24-PC-42338 | Completed |  |  | 8117 | 5518.14 | 5518.14 | 931.1 | 4611.15 | 0 | 5542.25 | 88 | 74.77
NHT-005071 - Survey | 24-PC-42338 | Completed |  |  | 10705 | 7277.26 | 7277.26 | 1227.92 | 6081.14 | 0 | 7309.06 | 128 | 106.07
NHT-005077 - Prefield | 24-PC-42338 | Completed |  |  | 2878 | 1956.26 | 1956.26 | 330.09 | 1634.72 | 0 | 1964.81 | 27 | 30.68
NHT-005082 - Reporting | 24-PC-42437 | Completed |  |  | 113993 | 75087.08 | 75087.08 | 6981.25 | 69735.73 | 0 | 76716.98 | 1797 | 1407.68
NHT-005084 - Draft Report | 24-PC-42437 | In progress |  |  | 107738 | 70967.1 | 70967.1 | 6598.18 | 65909.36 | 0 | 72507.54 | 1249 | 1391.29
NHT-005085 - Final Report | 24-PC-42437 | In progress |  |  | 41769 | 27513.27 | 27513.27 | 2558.05 | 25552.43 | 0 | 28110.48 | 465 | 508.65
NHT-005089 - Prefield | 24-PC-42495 | Completed |  |  | 28252 | 21694.63 | 21694.63 | 2975.19 | 10672.49 | 0 | 13647.68 | 242 | 190.72
NHT-005090 - Curation | 24-PC-42495 | Completed |  |  | 17648 | 13551.98 | 13551.98 | 1858.52 | 6666.79 | 0 | 8525.31 | 198 | 134.86
NHT-005091 - Draft Report | 24-PC-42527 | Completed |  |  | 31700 | 16100.16 | 20415.55 | 3213.02 | 15576.59 | 0 | 18789.61 | 450 | 278.68
NHT-005098 - Project Management | 24-PC-42550 | In progress |  |  | 69322 | 49911.73 | 49911.73 | 5510.89 | 26295 | 0 | 31805.89 | 485 | 489.83
NHT-005099 - Lab Analysis | 24-PC-42550 | In progress |  |  | 127806 | 92020.69 | 92020.69 | 9681.81 | 46196.41 | 0 | 55878.22 | 979 | 941.52
NHT-005106 - Site Recordation | 24-PC-42550 | In progress |  |  | 22834 | 16440.35 | 16440.35 | 2488.99 | 11876.13 | 0 | 14365.12 | 179 | 213.33
NHT-005110 - Testing | 24-PC-42550 | In progress |  |  | 54920 | 39542.17 | 39542.17 | 4517.55 | 21555.33 | 0 | 26072.88 | 516 | 347.17
NHT-005116 - Final Report | 24-PC-42550 | In progress |  |  | 26418 | 19021.06 | 19021.06 | 2938.45 | 14020.73 | 0 | 16959.18 | 261 | 263.82
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-42550 | In progress |  |  | 0 | 0 | 0 | 0 | 223.28 | 0 | 223.28 | 0 | 4
NHT-005124 - Project Management | 24-PC-42638 | On hold |  |  | 417200 | 310521.96 | 310521.96 | 20559.2 | 146588.78 | 0 | 167147.98 | 4299 | 3293.98
NHT-005125 - Background Research | 24-PC-42674 | Completed |  |  | 17595 | 10435.85 | 12577.77 | 864.62 | 5636.29 | 0 | 6500.91 | 129 | 86.98
NHT-005131 - Fieldwork | 24-PC-42674 | Completed |  |  | 138505 | 82150.49 | 99011.57 | 6806.25 | 44368.55 | 0 | 51174.8 | 1112 | 694.7
NHT-005134 - Testing | 24-PC-42697 | Completed |  |  | 49619 | 27746.3 | 35246.43 | 4004.36 | 24598.25 | 0 | 28602.61 | 0 | 426.49
NHT-005137 - GIS & Mapping | 24-PC-42697 | Completed |  |  | 27587 | 15426.46 | 19596.4 | 2226.36 | 13676.19 | 0 | 15902.55 | 0 | 229.59
NHT-005139 - Fieldwork | 24-PC-42697 | Completed |  |  | 42794 | 23929.95 | 30398.47 | 3453.59 | 21214.89 | 0 | 24668.48 | 0 | 381.59
NHT-005144 - Lab Analysis | 24-PC-42846 | Completed |  |  | 59177 | 35216.69 | 42453.37 | 5383 | 38381.27 | 0 | 43764.27 | 0 | 704.97
NHT-005147 - Desktop Review | 24-PC-42846 | Completed |  |  | 14131 | 8409.48 | 10137.54 | 1285.42 | 9165.16 | 0 | 10450.58 | 0 | 147.52
NHT-005150 - Survey | 24-PC-42846 | Completed |  |  | 68170 | 40568.04 | 48904.38 | 6200.98 | 44213.5 | 0 | 50414.48 | 0 | 767.86
NHT-005154 - Prefield | 24-PC-42846 | Completed |  |  | 19722 | 11736.94 | 14148.76 | 1794.04 | 12791.62 | 0 | 14585.66 | 0 | 236.39
NHT-005155 - Survey | 24-PC-43044 | In progress |  |  | 639100 | 498050.63 | 498050.63 | 56971.04 | 294702.03 | 0 | 351673.07 | 9052 | 4656.57
NHT-005158 - Desktop Review | 24-PC-43116 | Completed |  |  | 424400 | 314395.52 | 314395.52 | 43632.91 | 168792.85 | 0 | 212425.76 | 0 | 3473.56
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-43116 | Completed |  |  | 0 | 0 | 0 | 0 | 417.69 | 0 | 417.69 | 0 | 6.5
NHT-005171 - Lab Analysis | 24-PC-43150 | In progress |  |  | 81590 | 53072.48 | 60262.39 | 4347 | 46686.89 | 0 | 51033.89 | 870 | 1137.54
NHT-005173 - Site Recordation | 24-PC-43150 | In progress |  |  | 123738 | 80489.8 | 91394.03 | 5904.58 | 63415.35 | 0 | 69319.93 | 1938 | 1271.2
NHT-005178 - Agency Consultation | 24-PC-43150 | In progress |  |  | 96172 | 62557.8 | 71032.73 | 5121.11 | 55000.92 | 0 | 60122.03 | 1497 | 1082.74
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-43150 | In progress |  |  | 0 | 0 | 0 | 0 | 379.33 | 0 | 379.33 | 0 | 8.75
NHT-005192 - Data Recovery Excavation | 24-PC-43157 | In progress |  |  | 10133 | 7288.49 | 7288.49 | 1741.89 | 7989.32 | 0 | 9731.21 | 0 | 171.34
NHT-005198 - Draft Report | 24-PC-43157 | Completed |  |  | 3929 | 2826.02 | 2826.02 | 675.39 | 3097.75 | 0 | 3773.14 | 0 | 53.61
NHT-005199 - Project Management | 24-PC-43157 | Completed |  |  | 2438 | 1753.97 | 1753.97 | 419.18 | 1922.62 | 0 | 2341.8 | 0 | 30.94
NHT-005200 - Desktop Review | 24-PC-43157 | Completed |  |  | 1044 | 750.74 | 750.74 | 179.42 | 822.92 | 0 | 1002.34 | 0 | 13.68
NHT-005205 - Background Research | 24-PC-43157 | Completed |  |  | 2156 | 1550.99 | 1550.99 | 370.67 | 1700.12 | 0 | 2070.79 | 0 | 25.96
NHT-005207 - Site Recordation | 24-PC-43251 | Completed |  |  | 38382 | 26533.52 | 26533.52 | 3696.31 | 18980.43 | 0 | 22676.74 | 341 | 310.9
NHT-005211 - Final Report | 24-PC-43251 | Completed |  |  | 22030 | 15229.32 | 15229.32 | 2121.55 | 10894.11 | 0 | 13015.66 | 220 | 212.75
NHT-005212 - Testing | 24-PC-43251 | Completed |  |  | 41057 | 28382.74 | 28382.74 | 3953.92 | 20303.25 | 0 | 24257.17 | 374 | 369.33
NHT-005213 - Reporting | 24-PC-43251 | Completed |  |  | 61631 | 42605.45 | 42605.45 | 5935.24 | 30477.3 | 0 | 36412.54 | 631 | 525.53
NHT-005217 - Reporting | 24-PC-43406 | Completed |  |  | 18263 | 13207.71 | 13207.71 | 977.59 | 10660.37 | 0 | 11637.96 | 286 | 168.69
NHT-005222 - Background Research | 24-PC-43406 | Completed |  |  | 5519 | 3991.42 | 3991.42 | 295.43 | 3221.6 | 0 | 3517.03 | 102 | 43.68
NHT-005224 - Draft Report | 24-PC-43406 | Completed |  |  | 14918 | 10788.71 | 10788.71 | 798.54 | 8707.9 | 0 | 9506.44 | 225 | 136.91
NHT-005228 - Final Report | 24-PC-43670 | Completed |  |  | 16643 | 11558.56 | 12728.93 | 1374.24 | 7607.74 | 0 | 8981.98 | 0 | 126.59
NHT-005230 - Lab Analysis | 24-PC-43670 | Completed |  |  | 39721 | 27585.8 | 30379.02 | 3279.79 | 18156.74 | 0 | 21436.53 | 0 | 335.9
NHT-005232 - Reporting | 24-PC-43670 | Completed |  |  | 44588 | 30966.09 | 34101.59 | 3681.68 | 20381.61 | 0 | 24063.29 | 0 | 384.08
NHT-005236 - Data Recovery Excavation | 24-PC-43670 | Completed |  |  | 99082 | 68811.93 | 75779.53 | 8181.34 | 45291.42 | 0 | 53472.76 | 0 | 707.17
NHT-005243 - Prefield | 24-PC-43670 | Completed |  |  | 20366 | 14144.26 | 15576.45 | 1681.67 | 9309.63 | 0 | 10991.3 | 0 | 148.05
NHT-005246 - Monitoring | 24-PC-43715 | In progress |  |  | 229384 | 176258.95 | 176258.95 | 16021.01 | 124514.14 | 0 | 140535.15 | 2156 | 2382.61
NHT-005248 - Survey | 24-PC-43715 | In progress |  |  | 220882 | 169725.49 | 169725.49 | 15427.15 | 119898.73 | 0 | 135325.88 | 1958 | 2182.45
NHT-005249 - Reporting | 24-PC-43715 | In progress |  |  | 222289 | 170806.86 | 170806.86 | 15525.44 | 120662.63 | 0 | 136188.07 | 2105 | 1930.59
NHT-005253 - Data Recovery Excavation | 24-PC-43715 | In progress |  |  | 331045 | 254374.94 | 254374.94 | 23121.33 | 179697.41 | 0 | 202818.74 | 2865 | 2843.62
NHT-005259 - Fieldwork | 24-PC-43719 | Completed |  |  | 163321 | 84364.55 | 102412.03 | 6126.14 | 66804.11 | 0 | 72930.25 | 1358 | 876.21
NHT-005263 - Desktop Review | 24-PC-43719 | Completed |  |  | 27948 | 14436.8 | 17525.16 | 1048.33 | 11431.79 | 0 | 12480.12 | 255 | 182.28
NHT-005267 - Survey | 24-PC-43719 | Completed |  |  | 190831 | 98574.65 | 119661.98 | 7158.01 | 78056.37 | 0 | 85214.38 | 2209 | 1369.32
NHT-005272 - Desktop Review | 24-PC-43782 | Completed |  |  | 48472 | 28198.65 | 34924.68 | 7590.65 | 29986.83 | 0 | 37577.48 | 353 | 429.77
NHT-005279 - Survey | 24-PC-43782 | Completed |  |  | 247977 | 144260.71 | 178670.2 | 38832.79 | 153408.76 | 0 | 192241.55 | 2096 | 2449.47
NHT-005286 - Reporting | 24-PC-43782 | Completed |  |  | 204348 | 118879.96 | 147235.57 | 32000.69 | 126418.55 | 0 | 158419.24 | 1569 | 2608.54
NHT-005292 - Background Research | 24-PC-43782 | Completed |  |  | 70703 | 41131.72 | 50942.58 | 11072.04 | 43740.02 | 0 | 54812.06 | 563 | 866.02
NHT-005297 - Fieldwork | 24-PC-43786 | Completed |  |  | 87575 | 45172.62 | 49187.38 | 5047.13 | 27100.22 | 0 | 32147.35 | 0 | 506.75
NHT-005304 - Curation | 24-PC-43786 | Completed |  |  | 13878 | 7158.6 | 7794.83 | 799.83 | 4294.63 | 0 | 5094.46 | 0 | 65.37
NHT-005308 - Draft Report | 24-PC-43786 | Completed |  |  | 38321 | 19767.05 | 21523.86 | 2208.57 | 11858.76 | 0 | 14067.33 | 0 | 203.42
NHT-005311 - Reporting | 24-PC-43786 | Completed |  |  | 61110 | 31522.15 | 34323.72 | 3521.97 | 18910.95 | 0 | 22432.92 | 0 | 339.71
NHT-005312 - Prefield | 24-PC-43786 | Completed |  |  | 19516 | 10066.86 | 10961.57 | 1124.77 | 6039.37 | 0 | 7164.14 | 0 | 99.58
NHT-005319 - Curation | 24-PC-43877 | Completed |  |  | 31661 | 27861.89 | 27861.89 | 2696.83 | 17279.72 | 0 | 19976.55 | 355 | 280.28
NHT-005321 - GIS & Mapping | 24-PC-43877 | Completed |  |  | 49133 | 43237.21 | 43237.21 | 4185.06 | 26815.37 | 0 | 31000.43 | 537 | 389.15
NHT-005327 - Testing | 24-PC-43877 | Completed |  |  | 57837 | 50896.09 | 50896.09 | 4926.39 | 31565.37 | 0 | 36491.76 | 626 | 444.1
NHT-005333 - Site Recordation | 24-PC-43877 | Completed |  |  | 49873 | 43888.67 | 43888.67 | 4248.11 | 27219.4 | 0 | 31467.51 | 575 | 536.33
NHT-005334 - Final Report | 24-PC-43877 | Completed |  |  | 24596 | 21644.14 | 21644.14 | 2095 | 13423.52 | 0 | 15518.52 | 228 | 180.52
NHT-005336 - Reporting | 24-PC-44022 | Completed |  |  | 1072900 | 541701.35 | 625022.97 | 44173.59 | 300932.56 | 0 | 345106.15 | 6255 | 4992.21
NHT-005340 - Site Recordation | 24-PC-44113 | Completed |  |  | 108512 | 79679.71 | 79679.71 | 9938.79 | 71670.16 | 0 | 81608.95 | 664 | 966.97
NHT-005343 - Curation | 24-PC-44113 | Completed |  |  | 41829 | 30715.14 | 30715.14 | 4667.2 | 33655.86 | 0 | 38323.06 | 235 | 426.12
NHT-005347 - GIS & Mapping | 24-PC-44113 | Completed |  |  | 44727 | 32843.05 | 32843.05 | 5198.2 | 37484.96 | 0 | 42683.16 | 278 | 505.22
NHT-005352 - Monitoring | 24-PC-44113 | Completed |  |  | 41417 | 30412.75 | 30412.75 | 6571.62 | 47388.89 | 0 | 53960.51 | 234 | 640.6
NHT-005355 - Final Report | 24-PC-44113 | Completed |  |  | 28015 | 20571.7 | 20571.7 | 3431.28 | 24743.43 | 0 | 28174.71 | 182 | 319.3
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-44113 | Completed |  |  | 0 | 0 | 0 | 0 | 1589.22 | 0 | 1589.22 | 0 | 25
NHT-005358 - Survey | 24-PC-44158 | Completed |  |  | 23200 | 15583.44 | 15583.44 | 2567.05 | 13458.23 | 0 | 16025.28 | 132 | 166.61
OVHD-Non-Posting - Overhead Non-Posting | 24-PC-44158 | Completed |  |  | 0 | 0 | 0 | 0 | 18.76 | 0 | 18.76 | 0 | 0.25
NHT-005370 - Desktop Review | 25-PC-30034 | Completed |  |  | 418 | 304.49 | 304.49 | 10.02 | 124.03 | 0 | 134.05 | 6 | 2.96
NHT-005375 - Draft Report | 25-PC-30034 | Completed |  |  | 10991 | 7999.41 | 7999.41 | 468.61 | 5798.24 | 0 | 6266.85 | 168 | 137.79
NHT-005380 - Project Management | 25-PC-30034 | Completed |  |  | 65465 | 47645.26 | 47645.26 | 1951.15 | 24142.2 | 0 | 26093.35 | 830 | 574.28
NHT-005383 - Site Recordation | 25-PC-30034 | Completed |  |  | 15123 | 11006.53 | 11006.53 | 821.59 | 10165.74 | 0 | 10987.33 | 215 | 241.42
NHT-005388 - Testing | 25-PC-30034 | Completed |  |  | 9903 | 7207.13 | 7207.13 | 510.01 | 6310.51 | 0 | 6820.52 | 128 | 153.4
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30034 | Completed |  |  | 0 | 0 | 0 | 0 | 527.36 | 0 | 527.36 | 0 | 12.25
NHT-005397 - GIS & Mapping | 25-PC-30077 | In progress |  |  | 103400 | 51740.95 | 71293.1 | 10503.04 | 54715.41 | 0 | 65218.45 | 718 | 1198.47
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30077 | In progress |  |  | 0 | 0 | 0 | 0 | 425.56 | 0 | 425.56 | 0 | 10
NHT-005405 - Lab Analysis | 25-PC-30140 | In progress |  |  | 103486 | 66530.59 | 66530.59 | 5621.05 | 34244.51 | 0 | 39865.56 | 892 | 476.03
NHT-005408 - Draft Report | 25-PC-30140 | In progress |  |  | 89436 | 57498.71 | 57498.71 | 4852.16 | 29560.36 | 0 | 34412.52 | 852 | 405.95
NHT-005413 - Testing | 25-PC-30140 | In progress |  |  | 64278 | 41324.58 | 41324.58 | 2994.73 | 18244.52 | 0 | 21239.25 | 693 | 274.76
NHT-005415 - Reporting | 25-PC-30204 | Completed |  |  | 32738 | 20889.58 | 22668.71 | 2719.99 | 14828.33 | 0 | 17548.32 | 0 | 293.28
NHT-005420 - Data Recovery Excavation | 25-PC-30204 | Completed |  |  | 55271 | 35267.13 | 38270.76 | 4592.07 | 25034.14 | 0 | 29626.21 | 0 | 523.91
NHT-005421 - Survey | 25-PC-30204 | Completed |  |  | 47250 | 30149.27 | 32717.02 | 3925.67 | 21401.25 | 0 | 25326.92 | 0 | 515.6
NHT-005427 - Monitoring | 25-PC-30204 | Completed |  |  | 35107 | 22400.81 | 24308.64 | 2916.76 | 15901.06 | 0 | 18817.82 | 0 | 362.82
NHT-005430 - Prefield | 25-PC-30204 | Completed |  |  | 9034 | 5764.21 | 6255.13 | 750.54 | 4091.68 | 0 | 4842.22 | 0 | 83.9
NHT-005433 - Testing | 25-PC-30254 | Completed |  |  | 22606 | 14522.1 | 14522.1 | 788.45 | 9067.15 | 0 | 9855.6 | 188 | 135.51
NHT-005437 - Site Recordation | 25-PC-30254 | Completed |  |  | 3842 | 2468.36 | 2468.36 | 160.31 | 1843.51 | 0 | 2003.82 | 23 | 28.33
NHT-005438 - Final Report | 25-PC-30254 | Completed |  |  | 11763 | 7556.31 | 7556.31 | 472.06 | 5428.64 | 0 | 5900.7 | 78 | 81.02
NHT-005441 - Prefield | 25-PC-30254 | Completed |  |  | 17477 | 11227.04 | 11227.04 | 610.21 | 7017.45 | 0 | 7627.66 | 115 | 94.46
NHT-005445 - Draft Report | 25-PC-30254 | Completed |  |  | 21412 | 13755.23 | 13755.23 | 793.69 | 9127.47 | 0 | 9921.16 | 165 | 121.14
NHT-005449 - Site Recordation | 25-PC-30345 | In progress |  |  | 160400 | 92631 | 92631 | 5447.24 | 69315.66 | 0 | 74762.9 | 1097 | 1188.97
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30345 | In progress |  |  | 0 | 0 | 0 | 0 | 893.24 | 0 | 893.24 | 0 | 17.75
NHT-005453 - Monitoring | 25-PC-30348 | In progress |  |  | 7582 | 5538.82 | 5538.82 | 430.02 | 3123.95 | 0 | 3553.97 | 97 | 56.09
NHT-005460 - Desktop Review | 25-PC-30348 | In progress |  |  | 1051 | 767.95 | 767.95 | 59.62 | 433.13 | 0 | 492.75 | 12 | 7.6
NHT-005467 - Agency Consultation | 25-PC-30348 | In progress |  |  | 1687 | 1232.3 | 1232.3 | 95.68 | 695.03 | 0 | 790.71 | 19 | 14.98
NHT-005471 - GIS & Mapping | 25-PC-30348 | In progress |  |  | 3702 | 2704 | 2704 | 209.94 | 1525.07 | 0 | 1735.01 | 50 | 28.91
NHT-005478 - Survey | 25-PC-30348 | In progress |  |  | 6778 | 4951.33 | 4951.33 | 384.42 | 2792.59 | 0 | 3177.01 | 78 | 55.62
NHT-005485 - Final Report | 25-PC-30418 | Completed |  |  | 55526 | 27460.01 | 37571.83 | 4628.25 | 20907.26 | 0 | 25535.51 | 637 | 541.06
NHT-005486 - Background Research | 25-PC-30418 | Completed |  |  | 164342 | 81274.42 | 111202.77 | 13749.12 | 62109.07 | 0 | 75858.19 | 1837 | 1496.71
NHT-005490 - Prefield | 25-PC-30418 | Completed |  |  | 45082 | 22294.81 | 30504.6 | 4494.66 | 20303.79 | 0 | 24798.45 | 512 | 486.3
NHT-005494 - Lab Analysis | 25-PC-30418 | Completed |  |  | 61761 | 30543.33 | 41790.55 | 5788.99 | 26150.65 | 0 | 31939.64 | 786 | 689.45
NHT-005501 - Fieldwork | 25-PC-30418 | Completed |  |  | 18089 | 8945.61 | 12239.72 | 1862.37 | 8412.89 | 0 | 10275.26 | 184 | 199.91
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30418 | Completed |  |  | 0 | 0 | 0 | 0 | 230.46 | 0 | 230.46 | 0 | 6
NHT-005509 - Prefield | 25-PC-30581 | Completed |  |  | 9240 | 6110.52 | 6110.52 | 994.39 | 6336 | 0 | 7330.39 | 77 | 123.31
NHT-005514 - Project Management | 25-PC-30581 | In progress |  |  | 10460 | 6917.09 | 6917.09 | 852.89 | 5434.39 | 0 | 6287.28 | 72 | 86.56
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30581 | In progress |  |  | 0 | 0 | 0 | 0 | 65.86 | 0 | 65.86 | 0 | 1
NHT-005526 - Draft Report | 25-PC-30694 | Completed |  |  | 68511 | 51081.63 | 51081.63 | 4316.4 | 62089.72 | 0 | 66406.12 | 546 | 1225.05
NHT-005532 - Monitoring | 25-PC-30694 | Completed |  |  | 138654 | 103380.5 | 103380.5 | 8735.66 | 125659 | 0 | 134394.66 | 1593 | 2263.48
NHT-005536 - GIS & Mapping | 25-PC-30694 | Completed |  |  | 41523 | 30959.33 | 30959.33 | 2616.06 | 37631.07 | 0 | 40247.13 | 332 | 786.18
NHT-005539 - Reporting | 25-PC-30694 | Completed |  |  | 109512 | 81652.46 | 81652.46 | 6899.63 | 99248.56 | 0 | 106148.19 | 1044 | 2077.88
NHT-005546 - Project Management | 25-PC-30717 | In progress |  |  | 232866 | 119567.14 | 147780.26 | 12598.47 | 82357.46 | 0 | 94955.93 | 1722 | 1622.6
NHT-005548 - Background Research | 25-PC-30717 | Completed |  |  | 91234 | 46844.84 | 57898.38 | 10244.41 | 66968.73 | 0 | 77213.14 | 936 | 1367.87
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30717 | In progress |  |  | 0 | 0 | 0 | 0 | 2204.04 | 0 | 2204.04 | 0 | 47
NHT-005561 - Background Research | 25-PC-30725 | Completed |  |  | 654 | 434.84 | 434.84 | 113.62 | 451.67 | 0 | 565.29 | 5 | 9.31
NHT-005565 - Testing | 25-PC-30725 | Completed |  |  | 1716 | 1140.14 | 1140.14 | 297.92 | 1184.27 | 0 | 1482.19 | 15 | 21.15
NHT-005571 - Data Recovery Excavation | 25-PC-30725 | Completed |  |  | 5030 | 3341.58 | 3341.58 | 873.16 | 3470.89 | 0 | 4344.05 | 33 | 72.82
NHT-005576 - Project Management | 25-PC-30739 | Completed |  |  | 32993 | 29034.19 | 29034.19 | 3798.54 | 15217.97 | 0 | 19016.51 | 0 | 356.6
NHT-005578 - Desktop Review | 25-PC-30739 | Completed |  |  | 111399 | 98031.56 | 98031.56 | 7873.04 | 31541.57 | 0 | 39414.61 | 0 | 797.01
NHT-005582 - Reporting | 25-PC-30739 | Completed |  |  | 32442 | 28548.95 | 28548.95 | 3615.67 | 14485.36 | 0 | 18101.03 | 0 | 324.89
NHT-005584 - Final Report | 25-PC-30739 | Completed |  |  | 30435 | 26782.46 | 26782.46 | 3562.34 | 14271.69 | 0 | 17834.03 | 0 | 353.57
NHT-005588 - Draft Report | 25-PC-30739 | Completed |  |  | 36931 | 32498.84 | 32498.84 | 2818 | 11289.69 | 0 | 14107.69 | 0 | 253.84
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30739 | Completed |  |  | 0 | 0 | 0 | 0 | 958.39 | 0 | 958.39 | 0 | 22.25
NHT-005594 - Fieldwork | 25-PC-30772 | Completed |  |  | 15944 | 9034.89 | 10847.12 | 1262.11 | 12155.74 | 0 | 13417.85 | 129 | 220.19
NHT-005600 - Lab Analysis | 25-PC-30772 | In progress |  |  | 23520 | 13328.44 | 16001.85 | 1751.14 | 16865.8 | 0 | 18616.94 | 176 | 343.54
NHT-005601 - Final Report | 25-PC-30772 | In progress |  |  | 12724 | 7210.36 | 8656.62 | 861.3 | 8295.39 | 0 | 9156.69 | 109 | 150.48
NHT-005607 - Monitoring | 25-PC-30772 | In progress |  |  | 11112 | 6297.16 | 7560.25 | 1372.22 | 13216.28 | 0 | 14588.5 | 103 | 234.85
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30772 | In progress |  |  | 0 | 0 | 0 | 0 | 636.93 | 0 | 636.93 | 0 | 12.5
NHT-005615 - Draft Report | 25-PC-30803 | Completed |  |  | 47956 | 31286.77 | 31286.77 | 6632.04 | 26863 | 0 | 33495.04 | 264 | 459.79
NHT-005620 - Testing | 25-PC-30803 | In progress |  |  | 83044 | 54177.63 | 54177.63 | 10953.82 | 44368.27 | 0 | 55322.09 | 449 | 722.42
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-30803 | In progress |  |  | 0 | 0 | 0 | 0 | 1366.77 | 0 | 1366.77 | 0 | 24.5
NHT-005627 - Final Report | 25-PC-30824 | In progress |  |  | 33245 | 17645.85 | 23458.6 | 1295.55 | 14898.84 | 0 | 16194.39 | 577 | 242.46
NHT-005632 - Testing | 25-PC-30824 | In progress |  |  | 61718 | 32758.6 | 43549.67 | 2405.12 | 27658.93 | 0 | 30064.05 | 1107 | 479.17
NHT-005634 - Draft Report | 25-PC-30824 | In progress |  |  | 73796 | 39169.2 | 52072.01 | 2875.79 | 33071.56 | 0 | 35947.35 | 1312 | 770.34
NHT-005637 - Site Recordation | 25-PC-30824 | In progress |  |  | 37641 | 19979.35 | 26560.79 | 1466.88 | 16869.08 | 0 | 18335.96 | 576 | 306.12
NHT-005642 - Desktop Review | 25-PC-30928 | On hold |  |  | 6818 | 5103.28 | 5103.28 | 598.55 | 3501.12 | 0 | 4099.67 | 139 | 77.86
NHT-005643 - Testing | 25-PC-30928 | On hold |  |  | 25209 | 18868.72 | 18868.72 | 2213.07 | 12944.94 | 0 | 15158.01 | 407 | 226.55
NHT-005647 - Lab Analysis | 25-PC-30928 | On hold |  |  | 17416 | 13036.16 | 13036.16 | 1528.98 | 8943.5 | 0 | 10472.48 | 195 | 196.84
NHT-005650 - Draft Report | 25-PC-30928 | On hold |  |  | 22457 | 16808.99 | 16808.99 | 1971.49 | 11531.86 | 0 | 13503.35 | 373 | 199.52
NHT-005655 - Desktop Review | 25-PC-31024 | On hold |  |  | 84934 | 41949.02 | 56743.4 | 107.59 | 1115.04 | 0 | 1222.63 | 562 | 20.4
NHT-005658 - Final Report | 25-PC-31024 | On hold |  |  | 103082 | 50912.02 | 68867.43 | 130.58 | 1353.29 | 0 | 1483.87 | 698 | 30.77
NHT-005662 - Prefield | 25-PC-31024 | On hold |  |  | 103991 | 51360.85 | 69474.55 | 131.73 | 1365.22 | 0 | 1496.95 | 769 | 26.94
NHT-005665 - Reporting | 25-PC-31024 | On hold |  |  | 305381 | 150827.39 | 204020.44 | 386.85 | 4009.14 | 0 | 4395.99 | 2477 | 78.92
NHT-005672 - Lab Analysis | 25-PC-31024 | On hold |  |  | 173212 | 85549.48 | 115720.65 | 219.42 | 2273.98 | 0 | 2493.4 | 1184 | 37.23
NHT-005674 - Background Research | 25-PC-31109 | In progress |  |  | 174700 | 109484.49 | 109484.49 | 23130.7 | 135996.21 | 0 | 159126.91 | 785 | 1570.09
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31109 | In progress |  |  | 0 | 0 | 0 | 0 | 3765.35 | 0 | 3765.35 | 0 | 39.5
NHT-005680 - Agency Consultation | 25-PC-31114 | In progress |  |  | 229400 | 157964.84 | 157964.84 | 25651.38 | 101551.78 | 0 | 127203.16 | 2257 | 2344.44
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31114 | In progress |  |  | 0 | 0 | 0 | 0 | 415.64 | 0 | 415.64 | 0 | 10
NHT-005693 - Draft Report | 25-PC-31144 | Completed |  |  | 78700 | 54208.56 | 54208.56 | 7747.21 | 40977.36 | 0 | 48724.57 | 466 | 694.99
NHT-005700 - Background Research | 25-PC-31180 | Completed |  |  | 80000 | 45712.3 | 60701.89 | 7627.47 | 56012.02 | 0 | 63639.49 | 0 | 633.43
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31180 | In progress |  |  | 0 | 0 | 0 | 0 | 456.87 | 0 | 456.87 | 0 | 4
NHT-005714 - Testing | 25-PC-31242 | In progress |  |  | 102647 | 62839.75 | 70417.6 | 5093.58 | 46170.95 | 0 | 51264.53 | 1213 | 1081.74
NHT-005718 - Prefield | 25-PC-31242 | In progress |  |  | 295953 | 181180.73 | 203029.33 | 4632.77 | 41993.87 | 0 | 46626.64 | 3076 | 935.91
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31242 | In progress |  |  | 0 | 0 | 0 | 0 | 354.78 | 0 | 354.78 | 0 | 9
NHT-005721 - Curation | 25-PC-31263 | Completed |  |  | 13654 | 9358.43 | 9358.43 | 1511.35 | 14959.24 | 0 | 16470.59 | 154 | 294.06
NHT-005724 - Final Report | 25-PC-31263 | Completed |  |  | 64792 | 44408.6 | 44408.6 | 3797.56 | 37587.83 | 0 | 41385.39 | 773 | 798.87
NHT-005727 - Background Research | 25-PC-31263 | Completed |  |  | 78962 | 54120.52 | 54120.52 | 3655.21 | 36178.9 | 0 | 39834.11 | 750 | 778.23
NHT-005730 - Prefield | 25-PC-31263 | Completed |  |  | 45992 | 31522.81 | 31522.81 | 2168.3 | 21461.64 | 0 | 23629.94 | 598 | 450.55
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31263 | Completed |  |  | 0 | 0 | 0 | 0 | 1014.26 | 0 | 1014.26 | 0 | 18.25
NHT-005740 - Reporting | 25-PC-31275 | Completed |  |  | 6717 | 4973.13 | 4973.13 | 822.91 | 5606.07 | 0 | 6428.98 | 77 | 127.47
NHT-005745 - Agency Consultation | 25-PC-31275 | Completed |  |  | 1821 | 1348.56 | 1348.56 | 223.15 | 1520.19 | 0 | 1743.34 | 22 | 34.93
NHT-005751 - Desktop Review | 25-PC-31275 | Completed |  |  | 1703 | 1260.79 | 1260.79 | 208.62 | 1421.25 | 0 | 1629.87 | 20 | 28.8
NHT-005753 - Monitoring | 25-PC-31275 | Completed |  |  | 11524 | 8532.29 | 8532.29 | 1411.85 | 9618.24 | 0 | 11030.09 | 147 | 179.66
NHT-005759 - GIS & Mapping | 25-PC-31275 | Completed |  |  | 3135 | 2321.19 | 2321.19 | 384.09 | 2616.62 | 0 | 3000.71 | 47 | 52.5
NHT-005762 - Testing | 25-PC-31298 | In progress |  |  | 9859 | 6786.44 | 7247.75 | 653.38 | 4772.04 | 0 | 5425.42 | 66 | 86.65
NHT-005768 - Survey | 25-PC-31298 | In progress |  |  | 15812 | 10885.38 | 11625.3 | 1434.61 | 10477.94 | 0 | 11912.55 | 128 | 203.5
NHT-005775 - Monitoring | 25-PC-31298 | In progress |  |  | 7444 | 5124 | 5472.31 | 517.39 | 3778.84 | 0 | 4296.23 | 82 | 81.83
NHT-005776 - Agency Consultation | 25-PC-31298 | In progress |  |  | 14985 | 10315.18 | 11016.36 | 1055.57 | 7709.56 | 0 | 8765.13 | 144 | 138.56
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31298 | In progress |  |  | 0 | 0 | 0 | 0 | 108.59 | 0 | 108.59 | 0 | 2.25
NHT-005781 - Final Report | 25-PC-31330 | Completed |  |  | 17546 | 12889.06 | 12889.06 | 2690.63 | 11470.17 | 0 | 14160.8 | 219 | 235.24
NHT-005786 - Fieldwork | 25-PC-31330 | Completed |  |  | 5954 | 4374.04 | 4374.04 | 1557.01 | 6637.57 | 0 | 8194.58 | 70 | 122.91
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31330 | Completed |  |  | 0 | 0 | 0 | 0 | -232.28 | 0 | -232.28 | 0 | -3.25
NHT-005793 - Project Management | 25-PC-31417 | Completed |  |  | 52000 | 38781.6 | 38781.6 | 7519.04 | 43112.69 | 0 | 50631.73 | 707 | 769.84
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31417 | In progress |  |  | 0 | 0 | 0 | 0 | 868.56 | 0 | 868.56 | 0 | 12
NHT-005802 - Testing | 25-PC-31420 | Completed |  |  | 13016 | 6486.03 | 8756.04 | 1948.72 | 8039.9 | 0 | 9988.62 | 166 | 200.86
NHT-005808 - Lab Analysis | 25-PC-31420 | Completed |  |  | 25655 | 12784.43 | 17258.77 | 2516.2 | 10381.15 | 0 | 12897.35 | 258 | 259.8
NHT-005814 - Reporting | 25-PC-31420 | Completed |  |  | 63529 | 31658.38 | 42738.28 | 2678.77 | 11051.83 | 0 | 13730.6 | 692 | 278.62
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31420 | Completed |  |  | 0 | 0 | 0 | 0 | 590.13 | 0 | 590.13 | 0 | 15
NHT-005820 - Project Management | 25-PC-31555 | Completed |  |  | 12842 | 9839.31 | 9839.31 | 761.25 | 11014.98 | 0 | 11776.23 | 104 | 185.39
NHT-005822 - Data Recovery Excavation | 25-PC-31555 | In progress |  |  | 44649 | 34210.36 | 34210.36 | 1837.64 | 26589.96 | 0 | 28427.6 | 406 | 396.62
NHT-005825 - Testing | 25-PC-31555 | In progress |  |  | 11809 | 9047.99 | 9047.99 | 657.95 | 9520.2 | 0 | 10178.15 | 131 | 159.16
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31555 | In progress |  |  | 0 | 0 | 0 | 0 | 506.12 | 0 | 506.12 | 0 | 12.5
NHT-005834 - Testing | 25-PC-31590 | Completed |  |  | 10257 | 7210.93 | 7210.93 | 662.51 | 6364 | 0 | 7026.51 | 92 | 102.53
NHT-005835 - Monitoring | 25-PC-31590 | Completed |  |  | 6543 | 4599.47 | 4599.47 | 797.46 | 7660.36 | 0 | 8457.82 | 47 | 142.73
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31590 | In progress |  |  | 0 | 0 | 0 | 0 | 47.27 | 0 | 47.27 | 0 | 1
NHT-005842 - Site Recordation | 25-PC-31616 | Completed |  |  | 8895 | 6473.08 | 6473.08 | 1045.58 | 9713.5 | 0 | 10759.08 | 0 | 163.31
NHT-005848 - Background Research | 25-PC-31616 | Completed |  |  | 12938 | 9414.94 | 9414.94 | 1245.62 | 11571.95 | 0 | 12817.57 | 0 | 208.93
NHT-005849 - Final Report | 25-PC-31616 | Completed |  |  | 8467 | 6161.29 | 6161.29 | 1061.92 | 9865.3 | 0 | 10927.22 | 0 | 180.83
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31616 | Completed |  |  | 0 | 0 | 0 | 0 | 64.42 | 0 | 64.42 | 0 | 1.5
NHT-005856 - Draft Report | 25-PC-31775 | In progress |  |  | 6072 | 3656.43 | 3656.43 | 174.97 | 1318.81 | 0 | 1493.78 | 0 | 27.48
NHT-005861 - Prefield | 25-PC-31775 | In progress |  |  | 60229 | 36269.98 | 36269.98 | 1965.27 | 14812.71 | 0 | 16777.98 | 0 | 413.96
NHT-005868 - Desktop Review | 25-PC-31775 | In progress |  |  | 96899 | 58352.63 | 58352.63 | 3128.62 | 23581.1 | 0 | 26709.72 | 0 | 564.39
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31775 | In progress |  |  | 0 | 0 | 0 | 0 | 51.51 | 0 | 51.51 | 0 | 1.25
NHT-005876 - Prefield | 25-PC-31784 | Completed |  |  | 42476 | 33568.78 | 33568.78 | 5871.5 | 32879.53 | 0 | 38751.03 | 466 | 645.07
NHT-005883 - GIS & Mapping | 25-PC-31784 | Completed |  |  | 26957 | 21304.34 | 21304.34 | 5326.81 | 29829.39 | 0 | 35156.2 | 296 | 601.53
NHT-005889 - Draft Report | 25-PC-31784 | In progress |  |  | 93409 | 73820.48 | 73820.48 | 7749.95 | 43398.54 | 0 | 51148.49 | 1189 | 893.93
NHT-005894 - Fieldwork | 25-PC-31784 | Completed |  |  | 12990 | 10266.22 | 10266.22 | 2884.2 | 16151.13 | 0 | 19035.33 | 215 | 333.29
NHT-005900 - Background Research | 25-PC-31784 | Completed |  |  | 40968 | 32377.22 | 32377.22 | 6017.08 | 33694.8 | 0 | 39711.88 | 435 | 685.16
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31784 | In progress |  |  | 0 | 0 | 0 | 0 | 1860.7 | 0 | 1860.7 | 0 | 31.75
NHT-005905 - Testing | 25-PC-31821 | Completed |  |  | 99051 | 68279.76 | 86180.76 | 14530.39 | 50913.01 | 0 | 65443.4 | 1176 | 1156.42
NHT-005907 - Monitoring | 25-PC-31821 | Completed |  |  | 112349 | 77447.16 | 97751.6 | 18175.18 | 63683.98 | 0 | 81859.16 | 1336 | 1503.52
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31821 | Completed |  |  | 0 | 0 | 0 | 0 | 2037.93 | 0 | 2037.93 | 0 | 48
NHT-005915 - Project Management | 25-PC-31895 | Completed |  |  | 5332 | 3744.91 | 3744.91 | 369.98 | 3932.13 | 0 | 4302.11 | 0 | 87.95
NHT-005916 - Draft Report | 25-PC-31895 | Completed |  |  | 13005 | 9134.67 | 9134.67 | 902.47 | 9591.33 | 0 | 10493.8 | 0 | 245.83
NHT-005918 - Monitoring | 25-PC-31895 | Completed |  |  | 22563 | 15848.58 | 15848.58 | 1565.77 | 16640.89 | 0 | 18206.66 | 0 | 311.84
NHT-005923 - Testing | 25-PC-31905 | Completed |  |  | 137784 | 94781.56 | 94781.56 | 6768.49 | 33559.79 | 0 | 40328.28 | 1346 | 765.95
NHT-005925 - Reporting | 25-PC-31905 | Completed |  |  | 65998 | 45400.34 | 45400.34 | 5271.03 | 26135.07 | 0 | 31406.1 | 798 | 587.49
NHT-005932 - Final Report | 25-PC-31905 | Completed |  |  | 72087 | 49588.47 | 49588.47 | 6651.91 | 32981.81 | 0 | 39633.72 | 892 | 773.42
NHT-005938 - GIS & Mapping | 25-PC-31905 | Completed |  |  | 55731 | 38337.27 | 38337.27 | 3640.97 | 18052.83 | 0 | 21693.8 | 640 | 421.68
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31905 | Completed |  |  | 0 | 0 | 0 | 0 | 1470.66 | 0 | 1470.66 | 0 | 34.25
NHT-005947 - GIS & Mapping | 25-PC-31961 | Completed |  |  | 3928 | 2732.03 | 2732.03 | 1469.1 | 6901.52 | 0 | 8370.62 | 51 | 173.11
NHT-005949 - Lab Analysis | 25-PC-31961 | Completed |  |  | 17767 | 12356.35 | 12356.35 | 2328.54 | 10938.97 | 0 | 13267.51 | 301 | 282.84
NHT-005952 - Data Recovery Excavation | 25-PC-31961 | Completed |  |  | 3818 | 2655.46 | 2655.46 | 848.07 | 3984.03 | 0 | 4832.1 | 47 | 97.67
NHT-005953 - Site Recordation | 25-PC-31961 | Completed |  |  | 6952 | 4835.36 | 4835.36 | 1018.33 | 4783.87 | 0 | 5802.2 | 94 | 116.22
NHT-005958 - Fieldwork | 25-PC-31961 | Completed |  |  | 2735 | 1902.4 | 1902.4 | 1260.18 | 5920.05 | 0 | 7180.23 | 29 | 148.75
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-31961 | Completed |  |  | 0 | 0 | 0 | 0 | 341.69 | 0 | 341.69 | 0 | 8.5
NHT-005965 - Curation | 25-PC-31983 | Completed |  |  | 33456 | 22920.46 | 22920.46 | 4114.1 | 19261.49 | 0 | 23375.59 | 385 | 310.74
NHT-005966 - Background Research | 25-PC-31983 | Completed |  |  | 29870 | 20463.69 | 20463.69 | 3673.13 | 17196.91 | 0 | 20870.04 | 342 | 324.78
NHT-005967 - Fieldwork | 25-PC-31983 | Completed |  |  | 170268 | 116651.01 | 116651.01 | 20938.26 | 98029.11 | 0 | 118967.37 | 1479 | 2092.26
NHT-005972 - Final Report | 25-PC-31983 | Completed |  |  | 37906 | 25969.49 | 25969.49 | 4661.39 | 21823.78 | 0 | 26485.17 | 347 | 501.16
NHT-005977 - Curation | 25-PC-32000 | On hold |  |  | 9133 | 7508.01 | 7508.01 | 439.95 | 2493.07 | 0 | 2933.02 | 0 | 46.34
NHT-005981 - GIS & Mapping | 25-PC-32000 | On hold |  |  | 13413 | 11026.58 | 11026.58 | 646.13 | 3661.43 | 0 | 4307.56 | 0 | 60.22
NHT-005982 - Fieldwork | 25-PC-32000 | On hold |  |  | 38654 | 31777.93 | 31777.93 | 1862.13 | 10552.02 | 0 | 12414.15 | 0 | 164.79
NHT-005989 - Fieldwork | 25-PC-32021 | In progress |  |  | 148200 | 111253.74 | 111253.74 | 7560.44 | 49710.67 | 0 | 57271.11 | 1469 | 1149.76
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32021 | In progress |  |  | 0 | 0 | 0 | 0 | 442.17 | 0 | 442.17 | 0 | 9
NHT-005999 - Desktop Review | 25-PC-32024 | In progress |  |  | 46668 | 33834.56 | 33834.56 | 3591.09 | 18627.09 | 0 | 22218.18 | 319 | 307.56
NHT-006006 - GIS & Mapping | 25-PC-32024 | In progress |  |  | 32832 | 23802.94 | 23802.94 | 3080.95 | 15980.95 | 0 | 19061.9 | 246 | 261.21
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32024 | In progress |  |  | 0 | 0 | 0 | 0 | 682.45 | 0 | 682.45 | 0 | 15.75
NHT-006013 - Site Recordation | 25-PC-32112 | Completed |  |  | 26193 | 18227.39 | 18227.39 | 2702.58 | 14846.64 | 0 | 17549.22 | 345 | 312
NHT-006015 - Background Research | 25-PC-32112 | Completed |  |  | 11407 | 7938.45 | 7938.45 | 1177.03 | 6466.05 | 0 | 7643.08 | 208 | 117.98
NHT-006017 - Agency Consultation | 25-PC-32144 | Completed |  |  | 1086 | 822.7 | 822.7 | 88.77 | 980.74 | 0 | 1069.51 | 0 | 17.36
NHT-006021 - Survey | 25-PC-32144 | Completed |  |  | 3346 | 2535.33 | 2535.33 | 273.56 | 3022.37 | 0 | 3295.93 | 0 | 50.35
NHT-006022 - Reporting | 25-PC-32144 | Completed |  |  | 2526 | 1914.25 | 1914.25 | 206.55 | 2281.98 | 0 | 2488.53 | 0 | 40.68
NHT-006027 - Desktop Review | 25-PC-32144 | Completed |  |  | 1022 | 774.25 | 774.25 | 83.54 | 922.98 | 0 | 1006.52 | 0 | 17.26
NHT-006031 - Data Recovery Excavation | 25-PC-32144 | Completed |  |  | 4120 | 3122.85 | 3122.85 | 336.96 | 3722.74 | 0 | 4059.7 | 0 | 61.8
NHT-006035 - Agency Consultation | 25-PC-32241 | Completed |  |  | 66077 | 46240.4 | 46240.4 | 8800 | 32742.96 | 0 | 41542.96 | 527 | 542.1
NHT-006039 - Background Research | 25-PC-32241 | Completed |  |  | 44108 | 30867.06 | 30867.06 | 4730.41 | 17600.88 | 0 | 22331.29 | 290 | 309.53
NHT-006043 - Reporting | 25-PC-32241 | Completed |  |  | 40470 | 28320.85 | 28320.85 | 4038.89 | 15027.85 | 0 | 19066.74 | 274 | 243.45
NHT-006047 - Final Report | 25-PC-32241 | Completed |  |  | 109073 | 76329.15 | 76329.15 | 11926.06 | 44374.4 | 0 | 56300.46 | 936 | 707.54
NHT-006048 - Curation | 25-PC-32241 | Completed |  |  | 71772 | 50226.24 | 50226.24 | 6192.63 | 23041.47 | 0 | 29234.1 | 399 | 314.51
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32241 | Completed |  |  | 0 | 0 | 0 | 0 | 1467.23 | 0 | 1467.23 | 0 | 14.25
NHT-006057 - Curation | 25-PC-32264 | Completed |  |  | 89481 | 51129.27 | 51129.27 | 4190.84 | 37302.63 | 0 | 41493.47 | 768 | 653.61
NHT-006064 - Desktop Review | 25-PC-32264 | Completed |  |  | 65871 | 37638.44 | 37638.44 | 3085.06 | 27460.06 | 0 | 30545.12 | 547 | 555.74
NHT-006067 - Testing | 25-PC-32264 | Completed |  |  | 232051 | 132594.33 | 132594.33 | 10868.17 | 96737.47 | 0 | 107605.64 | 1799 | 1816.13
NHT-006072 - GIS & Mapping | 25-PC-32264 | Completed |  |  | 143905 | 82227.6 | 82227.6 | 6739.83 | 59991.19 | 0 | 66731.02 | 1166 | 871.68
NHT-006079 - Site Recordation | 25-PC-32264 | Completed |  |  | 204692 | 116960.76 | 116960.76 | 9586.76 | 85331.63 | 0 | 94918.39 | 1659 | 1598.44
NHT-006082 - Final Report | 25-PC-32323 | In progress |  |  | 19333 | 14489.86 | 14489.86 | 5392.03 | 39105.17 | 0 | 44497.2 | 151 | 623.08
NHT-006089 - GIS & Mapping | 25-PC-32323 | In progress |  |  | 105250 | 78884.97 | 78884.97 | 7282.89 | 52818.56 | 0 | 60101.45 | 944 | 885.98
NHT-006096 - Survey | 25-PC-32323 | In progress |  |  | 76717 | 57499.52 | 57499.52 | 6417.54 | 46542.58 | 0 | 52960.12 | 547 | 814.88
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32323 | In progress |  |  | 0 | 0 | 0 | 0 | 4241.71 | 0 | 4241.71 | 0 | 67.75
NHT-006102 - Prefield | 25-PC-32346 | Completed |  |  | 5718 | 4147.15 | 4147.15 | 663.95 | 3108.5 | 0 | 3772.45 | 41 | 54.46
NHT-006103 - Desktop Review | 25-PC-32346 | Completed |  |  | 6137 | 4450.98 | 4450.98 | 712.59 | 3336.24 | 0 | 4048.83 | 40 | 63.59
NHT-006105 - Survey | 25-PC-32346 | Completed |  |  | 28345 | 20558.93 | 20558.93 | 3291.45 | 15409.97 | 0 | 18701.42 | 207 | 307.07
NHT-006108 - Survey | 25-PC-32402 | Completed |  |  | 94086 | 82795.81 | 82795.81 | 9739.68 | 40927.14 | 0 | 50666.82 | 1247 | 930.1
NHT-006109 - Site Recordation | 25-PC-32402 | Completed |  |  | 107408 | 94518.6 | 94518.6 | 10661.79 | 44801.92 | 0 | 55463.71 | 1418 | 1210.97
NHT-006112 - Project Management | 25-PC-32402 | Completed |  |  | 97257 | 85586.36 | 85586.36 | 10321.34 | 43371.32 | 0 | 53692.66 | 1303 | 1181.03
NHT-006113 - Final Report | 25-PC-32402 | Completed |  |  | 102549 | 90243.23 | 90243.23 | 9335.52 | 39228.81 | 0 | 48564.33 | 1517 | 840.53
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32402 | Completed |  |  | 0 | 0 | 0 | 0 | 249.58 | 0 | 249.58 | 0 | 6
NHT-006124 - Agency Consultation | 25-PC-32447 | In progress |  |  | 5030 | 3172.21 | 3522.7 | 751.51 | 5433.17 | 0 | 6184.68 | 59 | 114.97
NHT-006130 - Survey | 25-PC-32447 | In progress |  |  | 33559 | 21165.16 | 23503.57 | 2958.63 | 21389.9 | 0 | 24348.53 | 366 | 443.9
NHT-006137 - Background Research | 25-PC-32447 | In progress |  |  | 13751 | 8672.83 | 9631.05 | 1948.38 | 14086.15 | 0 | 16034.53 | 104 | 342.72
NHT-006143 - Final Report | 25-PC-32447 | In progress |  |  | 17445 | 11001.98 | 12217.53 | 1774.9 | 12831.92 | 0 | 14606.82 | 156 | 266.67
NHT-006149 - Project Management | 25-PC-32447 | Completed |  |  | 18415 | 11614.2 | 12897.39 | 1847.67 | 13358 | 0 | 15205.67 | 155 | 250.18
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32447 | In progress |  |  | 0 | 0 | 0 | 0 | 323.01 | 0 | 323.01 | 0 | 7.75
NHT-006154 - Project Management | 25-PC-32495 | In progress |  |  | 57027 | 40808.5 | 40808.5 | 6454.34 | 24361 | 0 | 30815.34 | 329 | 357.92
NHT-006160 - Testing | 25-PC-32495 | Completed |  |  | 40858 | 29238.18 | 29238.18 | 8423.94 | 31794.99 | 0 | 40218.93 | 192 | 417.62
NHT-006167 - Agency Consultation | 25-PC-32495 | Completed |  |  | 20915 | 14966.6 | 14966.6 | 9463.17 | 35717.45 | 0 | 45180.62 | 130 | 505.88
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32495 | In progress |  |  | 0 | 0 | 0 | 0 | 1376.65 | 0 | 1376.65 | 0 | 17
NHT-006174 - Prefield | 25-PC-32500 | Completed |  |  | 41444 | 21974.87 | 29133.22 | 4968.55 | 25143.87 | 0 | 30112.42 | 333 | 503.93
NHT-006175 - Project Management | 25-PC-32500 | Completed |  |  | 54256 | 28768.68 | 38140.14 | 6504.64 | 32917.43 | 0 | 39422.07 | 480 | 581.85
NHT-006178 - Prefield | 25-PC-32630 | On hold |  |  | 865400 | 644117.22 | 644117.22 | 49111.93 | 291943.11 | 0 | 341055.04 | 9408 | 5316.19
NHT-006183 - Data Recovery Excavation | 25-PC-32750 | In progress |  |  | 14675 | 9094.38 | 10411.77 | 602.57 | 6374.77 | 0 | 6977.34 | 168 | 123.94
NHT-006184 - Survey | 25-PC-32750 | In progress |  |  | 7210 | 4468.52 | 5115.82 | 220.7 | 2334.86 | 0 | 2555.56 | 87 | 38.2
NHT-006186 - Fieldwork | 25-PC-32750 | In progress |  |  | 4892 | 3031.77 | 3470.94 | 285.77 | 3023.26 | 0 | 3309.03 | 59 | 37.57
NHT-006189 - Curation | 25-PC-32750 | Completed |  |  | 8723 | 5406.1 | 6189.22 | 546.54 | 5782.03 | 0 | 6328.57 | 126 | 109.8
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32750 | In progress |  |  | 0 | 0 | 0 | 0 | 80.43 | 0 | 80.43 | 0 | 1.75
NHT-006199 - Agency Consultation | 25-PC-32776 | In progress |  |  | 40234 | 28952.19 | 28952.19 | 1335.53 | 17633.02 | 0 | 18968.55 | 492 | 357.64
NHT-006203 - Project Management | 25-PC-32776 | In progress |  |  | 46266 | 33293.21 | 33293.21 | 2064.55 | 27258.38 | 0 | 29322.93 | 791 | 563.6
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32776 | In progress |  |  | 0 | 0 | 0 | 0 | 985 | 0 | 985 | 0 | 18.75
NHT-006209 - Desktop Review | 25-PC-32795 | In progress |  |  | 94 | 64.57 | 64.57 | 3.37 | 38.81 | 0 | 42.18 | 1 | 0.59
NHT-006212 - Data Recovery Excavation | 25-PC-32795 | In progress |  |  | 5334 | 3677.01 | 3677.01 | 314.18 | 3613 | 0 | 3927.18 | 38 | 56.18
NHT-006213 - Curation | 25-PC-32795 | In progress |  |  | 11472 | 7909.28 | 7909.28 | 713.23 | 8202.11 | 0 | 8915.34 | 99 | 120
NHT-006215 - Final Report | 25-PC-32819 | Completed |  |  | 18214 | 11711.61 | 11711.61 | 776.11 | 10311.21 | 0 | 11087.32 | 132 | 176.91
NHT-006216 - Site Recordation | 25-PC-32819 | Completed |  |  | 31586 | 20309.79 | 20309.79 | 1345.9 | 17881.27 | 0 | 19227.17 | 193 | 353.79
NHT-006218 - Prefield | 25-PC-32838 | In progress |  |  | 20941 | 16488.66 | 16488.66 | 2245.55 | 11644.51 | 0 | 13890.06 | 0 | 111.28
NHT-006220 - Fieldwork | 25-PC-32838 | Completed |  |  | 2149 | 1692.27 | 1692.27 | 333.68 | 1730.3 | 0 | 2063.98 | 0 | 15.68
NHT-006221 - Draft Report | 25-PC-32838 | In progress |  |  | 4694 | 3696.27 | 3696.27 | 627.09 | 3251.85 | 0 | 3878.94 | 0 | 28.87
NHT-006224 - Survey | 25-PC-32838 | In progress |  |  | 14816 | 11666.04 | 11666.04 | 1609.47 | 8346.04 | 0 | 9955.51 | 0 | 73.34
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32838 | In progress |  |  | 0 | 0 | 0 | 0 | 1081.95 | 0 | 1081.95 | 0 | 9.5
NHT-006235 - Draft Report | 25-PC-32861 | In progress |  |  | 59200 | 31694.67 | 41555.52 | 10328.34 | 39278.03 | 0 | 49606.37 | 0 | 509.07
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32861 | In progress |  |  | 0 | 0 | 0 | 0 | 288.99 | 0 | 288.99 | 0 | 4.5
NHT-006244 - Site Recordation | 25-PC-32867 | In progress |  |  | 62468 | 35862.87 | 35862.87 | 3075.57 | 11822.46 | 0 | 14898.03 | 418 | 236.29
NHT-006248 - Fieldwork | 25-PC-32867 | Completed |  |  | 14253 | 8182.47 | 8182.47 | 2116.84 | 8137.09 | 0 | 10253.93 | 104 | 175.18
NHT-006254 - Curation | 25-PC-32867 | In progress |  |  | 2727 | 1565.58 | 1565.58 | 314.9 | 1210.47 | 0 | 1525.37 | 17 | 22.22
NHT-006256 - Prefield | 25-PC-32867 | In progress |  |  | 33178 | 19047.71 | 19047.71 | 1917.79 | 7371.97 | 0 | 9289.76 | 271 | 129.65
NHT-006263 - Lab Analysis | 25-PC-32867 | In progress |  |  | 31474 | 18069.18 | 18069.18 | 2672.25 | 10272.09 | 0 | 12944.34 | 232 | 191.21
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32867 | In progress |  |  | 0 | 0 | 0 | 0 | 1575.32 | 0 | 1575.32 | 0 | 30.75
NHT-006274 - Lab Analysis | 25-PC-32885 | In progress |  |  | 1706300 | 1090543.53 | 1213962.27 | 26234.13 | 269464.17 | 0 | 295698.3 | 17831 | 4257.24
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32885 | In progress |  |  | 0 | 0 | 0 | 0 | 2416.88 | 0 | 2416.88 | 0 | 31.25
NHT-006287 - Curation | 25-PC-32899 | Completed |  |  | 42960 | 37048.59 | 37048.59 | 8042.44 | 37773.22 | 0 | 45815.66 | 584 | 594.29
NHT-006288 - Background Research | 25-PC-32899 | In progress |  |  | 16640 | 14350.45 | 14350.45 | 5051.69 | 23726.42 | 0 | 28778.11 | 213 | 349.43
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32899 | In progress |  |  | 0 | 0 | 0 | 0 | 229.82 | 0 | 229.82 | 0 | 4
NHT-006292 - Prefield | 25-PC-32911 | Completed |  |  | 5578 | 2678.21 | 3659.89 | 721.42 | 5733.02 | 0 | 6454.44 | 29 | 85.27
NHT-006299 - Curation | 25-PC-32911 | Completed |  |  | 2253 | 1081.91 | 1478.49 | 518.48 | 4120.23 | 0 | 4638.71 | 11 | 60.81
NHT-006304 - Survey | 25-PC-32911 | Completed |  |  | 5469 | 2626.36 | 3589.05 | 488.76 | 3884.11 | 0 | 4372.87 | 28 | 56.97
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32911 | Completed |  |  | 0 | 0 | 0 | 0 | 997.39 | 0 | 997.39 | 0 | 14.75
NHT-006312 - Data Recovery Excavation | 25-PC-32926 | In progress |  |  | 328400 | 212343.44 | 212343.44 | 5269.58 | 56004.6 | 0 | 61274.18 | 2847 | 792.34
NHT-006319 - Reporting | 25-PC-32952 | In progress |  |  | 299000 | 160514.68 | 202368.34 | 7596.21 | 92748.24 | 0 | 100344.45 | 0 | 1446.94
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-32952 | In progress |  |  | 0 | 0 | 0 | 0 | 938.39 | 0 | 938.39 | 0 | 16.75
NHT-006328 - Lab Analysis | 25-PC-33065 | In progress |  |  | 9989 | 8075.79 | 8075.79 | 1366.3 | 5940.1 | 0 | 7306.4 | 81 | 122.31
NHT-006335 - Monitoring | 25-PC-33065 | In progress |  |  | 16757 | 13548.65 | 13548.65 | 2292.21 | 9965.63 | 0 | 12257.84 | 144 | 154.83
NHT-006341 - Reporting | 25-PC-33065 | In progress |  |  | 12782 | 10334.09 | 10334.09 | 1748.36 | 7601.17 | 0 | 9349.53 | 102 | 117.58
NHT-006348 - Curation | 25-PC-33065 | In progress |  |  | 4633 | 3745.77 | 3745.77 | 633.73 | 2755.18 | 0 | 3388.91 | 40 | 40.84
NHT-006349 - Prefield | 25-PC-33065 | In progress |  |  | 6239 | 5044.1 | 5044.1 | 853.38 | 3710.16 | 0 | 4563.54 | 56 | 53.71
NHT-006356 - Agency Consultation | 25-PC-33088 | In progress |  |  | 754447 | 543428.14 | 543428.14 | 80783.71 | 346643.33 | 0 | 427427.04 | 10743 | 10805.05
NHT-006361 - Testing | 25-PC-33088 | In progress |  |  | 13353 | 9618.2 | 9618.2 | 1426.16 | 6119.67 | 0 | 7545.83 | 228 | 145.91
NHT-006368 - Lab Analysis | 25-PC-33105 | In progress |  |  | 1249 | 829.37 | 829.37 | 351.59 | 3242.02 | 0 | 3593.61 | 7 | 51.62
NHT-006370 - Draft Report | 25-PC-33105 | Completed |  |  | 1268 | 842.25 | 842.25 | 245.81 | 2266.64 | 0 | 2512.45 | 10 | 35.52
NHT-006377 - Agency Consultation | 25-PC-33105 | In progress |  |  | 382 | 253.59 | 253.59 | 101.78 | 938.52 | 0 | 1040.3 | 2 | 14.6
NHT-006382 - Data Recovery Excavation | 25-PC-33105 | Completed |  |  | 601 | 398.79 | 398.79 | 147.4 | 1359.23 | 0 | 1506.63 | 4 | 21
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33105 | In progress |  |  | 0 | 0 | 0 | 0 | 353.21 | 0 | 353.21 | 0 | 5.5
NHT-006387 - Monitoring | 25-PC-33136 | In progress |  |  | 7197 | 4313.15 | 4851.31 | 698.22 | 2672.02 | 0 | 3370.24 | 91 | 58.11
NHT-006391 - Agency Consultation | 25-PC-33136 | In progress |  |  | 5949 | 3565.05 | 4009.86 | 421.43 | 1612.77 | 0 | 2034.2 | 78 | 35.11
NHT-006396 - Survey | 25-PC-33136 | In progress |  |  | 2089 | 1251.75 | 1407.93 | 100.35 | 384.03 | 0 | 484.38 | 20 | 8.15
NHT-006401 - Reporting | 25-PC-33136 | In progress |  |  | 9866 | 5912.03 | 6649.67 | 659.27 | 2522.95 | 0 | 3182.22 | 118 | 53.33
NHT-006408 - Background Research | 25-PC-33136 | In progress |  |  | 8099 | 4853.69 | 5459.29 | 591.61 | 2264.01 | 0 | 2855.62 | 119 | 49.02
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33136 | In progress |  |  | 0 | 0 | 0 | 0 | 615.86 | 0 | 615.86 | 0 | 13.25
NHT-006416 - Project Management | 25-PC-33183 | Completed |  |  | 9065 | 6887.95 | 6887.95 | 1566.77 | 14102.37 | 0 | 15669.14 | 153 | 245.75
NHT-006421 - Draft Report | 25-PC-33183 | In progress |  |  | 37441 | 28447.64 | 28447.64 | 1742.01 | 15679.69 | 0 | 17421.7 | 489 | 290.79
NHT-006428 - Testing | 25-PC-33183 | In progress |  |  | 29848 | 22678.54 | 22678.54 | 1908.16 | 17175.11 | 0 | 19083.27 | 414 | 287.75
NHT-006431 - GIS & Mapping | 25-PC-33183 | In progress |  |  | 21719 | 16501.92 | 16501.92 | 1487.35 | 13387.51 | 0 | 14874.86 | 323 | 233.82
NHT-006437 - Reporting | 25-PC-33183 | Completed |  |  | 6427 | 4883.05 | 4883.05 | 816.76 | 7351.59 | 0 | 8168.35 | 85 | 153.76
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33183 | In progress |  |  | 0 | 0 | 0 | 0 | 1528.1 | 0 | 1528.1 | 0 | 32
NHT-006442 - Monitoring | 25-PC-33206 | In progress |  |  | 48800 | 39449.92 | 39449.92 | 4039.81 | 17408.89 | 0 | 21448.7 | 478 | 312.74
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33206 | In progress |  |  | 0 | 0 | 0 | 0 | 748.05 | 0 | 748.05 | 0 | 9.25
NHT-006444 - Prefield | 25-PC-33238 | Completed |  |  | 949900 | 561552.6 | 642400.18 | 121160.38 | 548233.97 | 0 | 669394.35 | 9427 | 8871.31
NHT-006447 - Site Recordation | 25-PC-33294 | In progress |  |  | 38488 | 25537.05 | 25537.05 | 3449.77 | 13735.87 | 0 | 17185.64 | 250 | 303.69
NHT-006453 - Desktop Review | 25-PC-33294 | In progress |  |  | 56340 | 37381.62 | 37381.62 | 3258 | 12972.29 | 0 | 16230.29 | 434 | 276.63
NHT-006456 - Draft Report | 25-PC-33294 | In progress |  |  | 42372 | 28113.53 | 28113.53 | 4294.35 | 17098.7 | 0 | 21393.05 | 300 | 370.74
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33294 | In progress |  |  | 0 | 0 | 0 | 0 | 757.29 | 0 | 757.29 | 0 | 16.25
NHT-006468 - Final Report | 25-PC-33321 | Completed |  |  | 6637 | 4662.61 | 4662.61 | 838.57 | 3193 | 0 | 4031.57 | 54 | 59.54
NHT-006470 - Testing | 25-PC-33321 | Completed |  |  | 13493 | 9479.11 | 9479.11 | 1704.81 | 6491.39 | 0 | 8196.2 | 98 | 108.34
NHT-006472 - Draft Report | 25-PC-33321 | Completed |  |  | 14807 | 10402.2 | 10402.2 | 1870.83 | 7123.53 | 0 | 8994.36 | 137 | 147.42
NHT-006473 - Survey | 25-PC-33321 | Completed |  |  | 43542 | 30587.69 | 30587.69 | 5501.16 | 20946.76 | 0 | 26447.92 | 415 | 431.54
NHT-006480 - Project Management | 25-PC-33321 | Completed |  |  | 8721 | 6126.39 | 6126.39 | 1101.82 | 4195.41 | 0 | 5297.23 | 78 | 83.84
NHT-006483 - Draft Report | 25-PC-33332 | In progress |  |  | 44281 | 33862.05 | 33862.05 | 3063.77 | 17566.07 | 0 | 20629.84 | 448 | 379.64
NHT-006489 - Prefield | 25-PC-33332 | In progress |  |  | 46719 | 35725.65 | 35725.65 | 3425.08 | 19637.58 | 0 | 23062.66 | 389 | 462.86
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33332 | In progress |  |  | 0 | 0 | 0 | 0 | 449.31 | 0 | 449.31 | 0 | 9.75
NHT-006492 - Monitoring | 25-PC-33348 | In progress |  |  | 69703 | 50757.75 | 50757.75 | 4137.26 | 22649.39 | 0 | 26786.65 | 531 | 347
NHT-006496 - Reporting | 25-PC-33348 | In progress |  |  | 39841 | 29012.24 | 29012.24 | 2759.73 | 15108.16 | 0 | 17867.89 | 299 | 248.08
NHT-006500 - Background Research | 25-PC-33348 | In progress |  |  | 52156 | 37979.95 | 37979.95 | 3238.66 | 17730.02 | 0 | 20968.68 | 364 | 242.33
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33348 | In progress |  |  | 0 | 0 | 0 | 0 | 192.66 | 0 | 192.66 | 0 | 3
NHT-006508 - Final Report | 25-PC-33367 | Completed |  |  | 150800 | 100689.16 | 100689.16 | 4623 | 27793.19 | 0 | 32416.19 | 3249 | 654.39
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33367 | Completed |  |  | 0 | 0 | 0 | 0 | 371.02 | 0 | 371.02 | 0 | 9.25
NHT-006521 - Agency Consultation | 25-PC-33412 | Completed |  |  | 133431 | 91320.08 | 91320.08 | 12228.55 | 74498.73 | 0 | 86727.28 | 1210 | 1410.73
NHT-006525 - Lab Analysis | 25-PC-33412 | Completed |  |  | 298531 | 204314.92 | 204314.92 | 27359.53 | 166679.69 | 0 | 194039.22 | 3515 | 2771.85
NHT-006531 - Monitoring | 25-PC-33412 | Completed |  |  | 741625 | 507567.92 | 507567.92 | 67967.72 | 414072.87 | 0 | 482040.59 | 7938 | 5461.16
NHT-006538 - Desktop Review | 25-PC-33412 | Completed |  |  | 162613 | 111292.36 | 111292.36 | 14903.01 | 90792.07 | 0 | 105695.08 | 1668 | 1657.31
NHT-006543 - Testing | 25-PC-33414 | Completed |  |  | 81800 | 64082.12 | 64082.12 | 7006.1 | 64484.69 | 0 | 71490.79 | 657 | 1041.03
NHT-006549 - Lab Analysis | 25-PC-33473 | In progress |  |  | 19213 | 13456.8 | 13456.8 | 967.64 | 9689.65 | 0 | 10657.29 | 145 | 239.89
NHT-006554 - Fieldwork | 25-PC-33473 | In progress |  |  | 22387 | 15679.84 | 15679.84 | 1075.14 | 10766.18 | 0 | 11841.32 | 188 | 237.17
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33473 | In progress |  |  | 0 | 0 | 0 | 0 | 198.9 | 0 | 198.9 | 0 | 4.5
NHT-006564 - Curation | 25-PC-33522 | Completed |  |  | 23042 | 13553.74 | 15760.3 | 1221.44 | 12565.2 | 0 | 13786.64 | 0 | 192.94
NHT-006568 - GIS & Mapping | 25-PC-33522 | Completed |  |  | 3488 | 2051.78 | 2385.81 | 109.52 | 1126.63 | 0 | 1236.15 | 0 | 17.23
NHT-006570 - Testing | 25-PC-33522 | Completed |  |  | 5513 | 3242.91 | 3770.85 | 369.27 | 3798.73 | 0 | 4168 | 0 | 61.76
NHT-006576 - Draft Report | 25-PC-33522 | Completed |  |  | 20490 | 12052.77 | 14014.97 | 553.09 | 5689.71 | 0 | 6242.8 | 0 | 75.76
NHT-006578 - Final Report | 25-PC-33522 | Completed |  |  | 9267 | 5450.88 | 6338.29 | 776.49 | 7987.91 | 0 | 8764.4 | 0 | 121.99
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33522 | Completed |  |  | 0 | 0 | 0 | 0 | 627.45 | 0 | 627.45 | 0 | 13
NHT-006588 - Survey | 25-PC-33528 | Completed |  |  | 43510 | 32937.28 | 32937.28 | 4182.6 | 22458.18 | 0 | 26640.78 | 395 | 323.76
NHT-006590 - Curation | 25-PC-33528 | Completed |  |  | 9669 | 7319.43 | 7319.43 | 929.47 | 4990.73 | 0 | 5920.2 | 71 | 82.11
NHT-006591 - Background Research | 25-PC-33528 | Completed |  |  | 9062 | 6860.12 | 6860.12 | 871.14 | 4677.55 | 0 | 5548.69 | 66 | 83.32
NHT-006595 - Data Recovery Excavation | 25-PC-33528 | Completed |  |  | 76259 | 57727.67 | 57727.67 | 7330.66 | 39361.42 | 0 | 46692.08 | 834 | 669.62
NHT-006600 - Project Management | 25-PC-33535 | On hold |  |  | 31353 | 23762.2 | 23762.2 | 1259.3 | 14287.66 | 0 | 15546.96 | 396 | 281.74
NHT-006606 - Agency Consultation | 25-PC-33535 | On hold |  |  | 22718 | 17217.88 | 17217.88 | 912.48 | 10352.72 | 0 | 11265.2 | 345 | 183.51
NHT-006613 - Site Recordation | 25-PC-33535 | On hold |  |  | 46456 | 35209.6 | 35209.6 | 1865.97 | 21170.74 | 0 | 23036.71 | 729 | 356.48
NHT-006619 - Desktop Review | 25-PC-33535 | On hold |  |  | 19973 | 15137.27 | 15137.27 | 802.22 | 9101.69 | 0 | 9903.91 | 313 | 166.93
NHT-006620 - Draft Report | 25-PC-33561 | Completed |  |  | 41328 | 26681.45 | 26681.45 | 3342.79 | 21418.59 | 0 | 24761.38 | 0 | 413.61
NHT-006623 - Final Report | 25-PC-33561 | Completed |  |  | 27118 | 17507.64 | 17507.64 | 2193.44 | 14054.29 | 0 | 16247.73 | 0 | 248.62
NHT-006624 - Desktop Review | 25-PC-33561 | Completed |  |  | 15082 | 9737.13 | 9737.13 | 1219.92 | 7816.5 | 0 | 9036.42 | 0 | 137.58
NHT-006628 - Reporting | 25-PC-33561 | Completed |  |  | 48672 | 31422.1 | 31422.1 | 3936.72 | 25224.17 | 0 | 29160.89 | 0 | 500.05
NHT-006630 - Project Management | 25-PC-33640 | In progress |  |  | 1444500 | 1192145.85 | 1192145.85 | 71304.06 | 282978.69 | 0 | 354282.75 | 0 | 4489.4
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33640 | In progress |  |  | 0 | 0 | 0 | 0 | 2237.53 | 0 | 2237.53 | 0 | 41
NHT-006637 - Testing | 25-PC-33680 | In progress |  |  | 35580 | 26656.28 | 26656.28 | 2066.64 | 8559.9 | 0 | 10626.54 | 313 | 151.64
NHT-006638 - Desktop Review | 25-PC-33680 | In progress |  |  | 13419 | 10053.43 | 10053.43 | 1144.85 | 4741.88 | 0 | 5886.73 | 143 | 75.26
NHT-006644 - GIS & Mapping | 25-PC-33680 | In progress |  |  | 23889 | 17898.01 | 17898.01 | 807.94 | 3346.44 | 0 | 4154.38 | 277 | 73.4
NHT-006648 - Fieldwork | 25-PC-33680 | In progress |  |  | 3964 | 2970.01 | 2970.01 | 118.24 | 489.74 | 0 | 607.98 | 45 | 9.48
NHT-006653 - Data Recovery Excavation | 25-PC-33680 | In progress |  |  | 29948 | 22436.83 | 22436.83 | 2049.7 | 8489.7 | 0 | 10539.4 | 279 | 164.01
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33680 | In progress |  |  | 0 | 0 | 0 | 0 | 78.64 | 0 | 78.64 | 0 | 2
NHT-006663 - Testing | 25-PC-33744 | Completed |  |  | 5052 | 3487.63 | 3487.63 | 594.57 | 3121.49 | 0 | 3716.06 | 78 | 69.2
NHT-006670 - Prefield | 25-PC-33744 | In progress |  |  | 25835 | 17836.7 | 17836.7 | 1896.5 | 9956.63 | 0 | 11853.13 | 403 | 203.65
NHT-006677 - Fieldwork | 25-PC-33744 | In progress |  |  | 37447 | 25853.68 | 25853.68 | 3054.99 | 16038.67 | 0 | 19093.66 | 493 | 372.39
NHT-006678 - Background Research | 25-PC-33744 | In progress |  |  | 10975 | 7576.83 | 7576.83 | 991.88 | 5207.39 | 0 | 6199.27 | 193 | 121.83
NHT-006679 - Monitoring | 25-PC-33744 | In progress |  |  | 7791 | 5379 | 5379 | 568.07 | 2982.36 | 0 | 3550.43 | 144 | 81.16
NHT-006681 - Background Research | 25-PC-33750 | Completed |  |  | 40821 | 30089.28 | 30089.28 | 1510.26 | 23131.52 | 0 | 24641.78 | 0 | 508.11
NHT-006682 - GIS & Mapping | 25-PC-33750 | Completed |  |  | 12450 | 9177.12 | 9177.12 | 928.29 | 14217.87 | 0 | 15146.16 | 0 | 301.73
NHT-006689 - Survey | 25-PC-33750 | Completed |  |  | 16329 | 12035.76 | 12035.76 | 1238.94 | 18975.81 | 0 | 20214.75 | 0 | 394.39
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33750 | Completed |  |  | 0 | 0 | 0 | 0 | 284.05 | 0 | 284.05 | 0 | 6.5
NHT-006698 - Project Management | 25-PC-33795 | Completed |  |  | 45418 | 27691.53 | 27691.53 | 4300.65 | 22747.44 | 0 | 27048.09 | 330 | 366.69
NHT-006702 - Agency Consultation | 25-PC-33795 | Completed |  |  | 20903 | 12744.45 | 12744.45 | 1979.28 | 10469.04 | 0 | 12448.32 | 169 | 144.67
NHT-006706 - Data Recovery Excavation | 25-PC-33795 | Completed |  |  | 108179 | 65956.67 | 65956.67 | 10243.43 | 54180.64 | 0 | 64424.07 | 907 | 737.47
NHT-006707 - Prefield | 25-PC-33798 | Completed |  |  | 34052 | 28113.08 | 28113.08 | 1098.32 | 12175.93 | 0 | 13274.25 | 525 | 236.06
NHT-006710 - Data Recovery Excavation | 25-PC-33798 | Completed |  |  | 54886 | 45314.53 | 45314.53 | 1574.1 | 17450.31 | 0 | 19024.41 | 612 | 313.28
NHT-006711 - Site Recordation | 25-PC-33798 | Completed |  |  | 18978 | 15668.22 | 15668.22 | 1005.7 | 11149.07 | 0 | 12154.77 | 215 | 221.92
NHT-006714 - Curation | 25-PC-33798 | Completed |  |  | 38779 | 32015.79 | 32015.79 | 1346.07 | 14922.44 | 0 | 16268.51 | 501 | 257.89
NHT-006716 - Draft Report | 25-PC-33798 | Completed |  |  | 8605 | 7104.06 | 7104.06 | 520.23 | 5767.27 | 0 | 6287.5 | 101 | 112.59
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33798 | Completed |  |  | 0 | 0 | 0 | 0 | 1440.22 | 0 | 1440.22 | 0 | 28.25
NHT-006726 - Curation | 25-PC-33827 | On hold |  |  | 19605 | 11907.02 | 15361.1 | 184.55 | 1912.58 | 0 | 2097.13 | 259 | 25.88
NHT-006731 - Agency Consultation | 25-PC-33827 | On hold |  |  | 14378 | 8732.38 | 11265.54 | 135.34 | 1402.65 | 0 | 1537.99 | 170 | 21.98
NHT-006735 - Reporting | 25-PC-33827 | On hold |  |  | 53990 | 32791.88 | 42304.4 | 508.24 | 5267.24 | 0 | 5775.48 | 640 | 85.26
NHT-006738 - Project Management | 25-PC-33827 | On hold |  |  | 44527 | 27043.92 | 34889.02 | 419.16 | 4343.97 | 0 | 4763.13 | 591 | 62.99
NHT-006739 - Site Recordation | 25-PC-33841 | In progress |  |  | 586500 | 416356.35 | 416356.35 | 16111.81 | 243316.74 | 0 | 259428.55 | 6037 | 5998.86
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33841 | In progress |  |  | 0 | 0 | 0 | 0 | 439.4 | 0 | 439.4 | 0 | 10
NHT-006753 - Lab Analysis | 25-PC-33846 | Completed |  |  | 1198 | 755.16 | 868.79 | 129.35 | 762.6 | 0 | 891.95 | 13 | 15.44
NHT-006757 - Curation | 25-PC-33846 | Completed |  |  | 1373 | 865.43 | 995.65 | 124.26 | 732.59 | 0 | 856.85 | 20 | 12.52
NHT-006761 - Prefield | 25-PC-33846 | Completed |  |  | 4211 | 2654.12 | 3053.49 | 509.98 | 3006.56 | 0 | 3516.54 | 37 | 56.88
NHT-006764 - Draft Report | 25-PC-33846 | Completed |  |  | 587 | 369.65 | 425.28 | 78.75 | 464.26 | 0 | 543.01 | 6 | 9.69
NHT-006770 - Final Report | 25-PC-33846 | Completed |  |  | 7831 | 4935.63 | 5678.28 | 842.39 | 4966.16 | 0 | 5808.55 | 87 | 91.47
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33846 | Completed |  |  | 0 | 0 | 0 | 0 | -233.63 | 0 | -233.63 | 0 | -3.5
NHT-006782 - Agency Consultation | 25-PC-33855 | Completed |  |  | 3538 | 2205.04 | 2490.41 | 135.91 | 1183.59 | 0 | 1319.5 | 44 | 24.12
NHT-006786 - Background Research | 25-PC-33855 | Completed |  |  | 4815 | 3000.83 | 3389.18 | 329.64 | 2870.79 | 0 | 3200.43 | 61 | 62.09
NHT-006788 - Site Recordation | 25-PC-33855 | Completed |  |  | 264 | 164.37 | 185.65 | 5.85 | 50.96 | 0 | 56.81 | 4 | 0.97
NHT-006794 - Curation | 25-PC-33855 | Completed |  |  | 23990 | 14950.31 | 16885.1 | 878.05 | 7646.69 | 0 | 8524.74 | 326 | 147.05
NHT-006795 - Reporting | 25-PC-33855 | Completed |  |  | 1393 | 867.8 | 980.1 | 55.5 | 483.32 | 0 | 538.82 | 16 | 9.25
NHT-006796 - Curation | 25-PC-33915 | In progress |  |  | 272400 | 198225.48 | 198225.48 | 26399.94 | 106232.51 | 0 | 132632.45 | 0 | 1648.65
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33915 | In progress |  |  | 0 | 0 | 0 | 0 | 700.59 | 0 | 700.59 | 0 | 11
NHT-006800 - Site Recordation | 25-PC-33919 | Completed |  |  | 8309 | 4921.22 | 4921.22 | 1210.02 | 4391.92 | 0 | 5601.94 | 35 | 78.5
NHT-006801 - Agency Consultation | 25-PC-33919 | Completed |  |  | 3158 | 1870.69 | 1870.69 | 459.96 | 1669.49 | 0 | 2129.45 | 13 | 25.26
NHT-006802 - Data Recovery Excavation | 25-PC-33919 | Completed |  |  | 25433 | 15064.24 | 15064.24 | 3703.97 | 13444.02 | 0 | 17147.99 | 128 | 222.73
NHT-006803 - Testing | 25-PC-33919 | Completed |  |  | 8600 | 5093.5 | 5093.5 | 1252.38 | 4545.68 | 0 | 5798.06 | 40 | 81.87
NHT-006807 - Monitoring | 25-PC-33922 | In progress |  |  | 5766 | 4203.83 | 4203.83 | 828.13 | 11952.94 | 0 | 12781.07 | 48 | 159.67
NHT-006814 - Reporting | 25-PC-33922 | In progress |  |  | 2541 | 1852.57 | 1852.57 | 108.45 | 1565.35 | 0 | 1673.8 | 29 | 20.97
NHT-006821 - Project Management | 25-PC-33922 | In progress |  |  | 6252 | 4558.56 | 4558.56 | 954.91 | 13782.77 | 0 | 14737.68 | 68 | 183.83
NHT-006826 - Data Recovery Excavation | 25-PC-33922 | In progress |  |  | 7541 | 5498.15 | 5498.15 | 209.7 | 3026.71 | 0 | 3236.41 | 82 | 40.19
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-33922 | In progress |  |  | 0 | 0 | 0 | 0 | 1461.14 | 0 | 1461.14 | 0 | 19.5
NHT-006837 - Final Report | 25-PC-33969 | In progress |  |  | 87 | 67.03 | 67.03 | 6.68 | 31.73 | 0 | 38.41 | 1 | 0.69
NHT-006844 - Desktop Review | 25-PC-33969 | In progress |  |  | 55 | 41.89 | 41.89 | 4.18 | 19.83 | 0 | 24.01 | 1 | 0.39
NHT-006845 - Prefield | 25-PC-33969 | In progress |  |  | 76 | 58.65 | 58.65 | 5.85 | 27.77 | 0 | 33.62 | 1 | 0.57
NHT-006852 - GIS & Mapping | 25-PC-33969 | In progress |  |  | 5982 | 4592.86 | 4592.86 | 474.64 | 2253.2 | 0 | 2727.84 | 58 | 49.89
NHT-006859 - Agency Consultation | 25-PC-33969 | In progress |  |  | 7000 | 5374.53 | 5374.53 | 552.6 | 2623.24 | 0 | 3175.84 | 95 | 50.86
NHT-006866 - GIS & Mapping | 25-PC-34036 | Completed |  |  | 5771 | 3400.25 | 3843.58 | 787.58 | 3407.8 | 0 | 4195.38 | 34 | 62.01
NHT-006868 - Desktop Review | 25-PC-34036 | Completed |  |  | 25130 | 14808.3 | 16739.02 | 2064.43 | 8932.62 | 0 | 10997.05 | 186 | 137.28
NHT-006872 - Reporting | 25-PC-34036 | Completed |  |  | 7428 | 4376.64 | 4947.26 | 856.98 | 3708.11 | 0 | 4565.09 | 51 | 52.34
NHT-006878 - Prefield | 25-PC-34036 | Completed |  |  | 10332 | 6087.85 | 6881.59 | 1216.87 | 5265.32 | 0 | 6482.19 | 71 | 96.49
NHT-006885 - Monitoring | 25-PC-34036 | Completed |  |  | 13639 | 8036.49 | 9084.29 | 2229.44 | 9646.61 | 0 | 11876.05 | 92 | 170.35
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34036 | Completed |  |  | 0 | 0 | 0 | 0 | 561.54 | 0 | 561.54 | 0 | 11.5
NHT-006889 - Final Report | 25-PC-34077 | In progress |  |  | 106690 | 84488.19 | 84488.19 | 4789.25 | 49536.54 | 0 | 54325.79 | 997 | 607.69
NHT-006890 - Curation | 25-PC-34077 | In progress |  |  | 242893 | 192346.9 | 192346.9 | 6544.07 | 67687.26 | 0 | 74231.33 | 1810 | 834.17
NHT-006891 - Site Recordation | 25-PC-34077 | In progress |  |  | 112552 | 89129.91 | 89129.91 | 4755.89 | 49191.51 | 0 | 53947.4 | 914 | 613.07
NHT-006893 - Background Research | 25-PC-34077 | In progress |  |  | 118365 | 93732.95 | 93732.95 | 3878.24 | 40113.75 | 0 | 43991.99 | 947 | 495.32
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34077 | In progress |  |  | 0 | 0 | 0 | 0 | 3014.41 | 0 | 3014.41 | 0 | 36.75
NHT-006898 - Lab Analysis | 25-PC-34088 | In progress |  |  | 36183 | 20330.52 | 22215.98 | 1513.87 | 11765.64 | 0 | 13279.51 | 164 | 176.95
NHT-006899 - Curation | 25-PC-34088 | In progress |  |  | 11117 | 6246.54 | 6825.84 | 465.13 | 3614.98 | 0 | 4080.11 | 47 | 45.92
NHT-006904 - Monitoring | 25-PC-34090 | In progress |  |  | 53532 | 37894.99 | 37894.99 | 3676.37 | 15052.85 | 0 | 18729.22 | 599 | 323.01
NHT-006907 - Testing | 25-PC-34090 | In progress |  |  | 12668 | 8967.99 | 8967.99 | 1040.96 | 4262.21 | 0 | 5303.17 | 145 | 88.75
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34090 | In progress |  |  | 0 | 0 | 0 | 0 | 35.61 | 0 | 35.61 | 0 | 0.75
NHT-006919 - Draft Report | 25-PC-34144 | Completed |  |  | 23400 | 16230.24 | 16230.24 | 1905.07 | 17338.06 | 0 | 19243.13 | 0 | 291.52
NHT-006921 - Draft Report | 25-PC-34151 | In progress |  |  | 181924 | 120379.08 | 120379.08 | 3333.08 | 37429.19 | 0 | 40762.27 | 0 | 483.59
NHT-006926 - Prefield | 25-PC-34151 | In progress |  |  | 156389 | 103482.5 | 103482.5 | 3548.27 | 39845.65 | 0 | 43393.92 | 0 | 523.98
NHT-006930 - Desktop Review | 25-PC-34151 | In progress |  |  | 166787 | 110363.09 | 110363.09 | 3390.23 | 38070.99 | 0 | 41461.22 | 0 | 500.57
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34151 | In progress |  |  | 0 | 0 | 0 | 0 | 1192.28 | 0 | 1192.28 | 0 | 15.25
NHT-006942 - GIS & Mapping | 25-PC-34176 | In progress |  |  | 18442 | 12776.71 | 12776.71 | 3098.92 | 13653.7 | 0 | 16752.62 | 99 | 205.13
NHT-006943 - Curation | 25-PC-34176 | In progress |  |  | 32543 | 22545.41 | 22545.41 | 4458.39 | 19643.43 | 0 | 24101.82 | 184 | 294.28
NHT-006947 - Project Management | 25-PC-34176 | In progress |  |  | 2015 | 1396.28 | 1396.28 | 243.85 | 1074.39 | 0 | 1318.24 | 11 | 16.57
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34176 | In progress |  |  | 0 | 0 | 0 | 0 | 456.61 | 0 | 456.61 | 0 | 7
NHT-006950 - Monitoring | 25-PC-34374 | In progress |  |  | 3223 | 2256.33 | 2256.33 | 138.1 | 698.87 | 0 | 836.97 | 23 | 13.47
NHT-006956 - Testing | 25-PC-34374 | In progress |  |  | 3537 | 2476.94 | 2476.94 | 151.6 | 767.21 | 0 | 918.81 | 24 | 9.17
NHT-006963 - Draft Report | 25-PC-34374 | In progress |  |  | 3518 | 2462.85 | 2462.85 | 150.74 | 762.84 | 0 | 913.58 | 27 | 12.54
NHT-006970 - Site Recordation | 25-PC-34374 | In progress |  |  | 2929 | 2050.39 | 2050.39 | 125.5 | 635.08 | 0 | 760.58 | 21 | 11.19
NHT-006972 - Agency Consultation | 25-PC-34374 | In progress |  |  | 893 | 624.9 | 624.9 | 38.25 | 193.55 | 0 | 231.8 | 7 | 3.34
NHT-006973 - GIS & Mapping | 25-PC-34382 | Completed |  |  | 4480 | 2788.16 | 3382.76 | 747.59 | 3650 | 0 | 4397.59 | 38 | 64.29
NHT-006977 - Site Recordation | 25-PC-34382 | Completed |  |  | 8848 | 5506.9 | 6681.3 | 1476.57 | 7209.12 | 0 | 8685.69 | 64 | 126.23
NHT-006982 - Prefield | 25-PC-34382 | Completed |  |  | 4519 | 2812.49 | 3412.28 | 754.11 | 3681.85 | 0 | 4435.96 | 35 | 57.22
NHT-006986 - Data Recovery Excavation | 25-PC-34382 | Completed |  |  | 16753 | 10426.06 | 12649.53 | 2795.55 | 13648.84 | 0 | 16444.39 | 113 | 238.39
NHT-006988 - Final Report | 25-PC-34451 | Completed |  |  | 5363 | 3759.81 | 3759.81 | 678.94 | 3705.24 | 0 | 4384.18 | 36 | 54.28
NHT-006992 - Agency Consultation | 25-PC-34451 | Completed |  |  | 19030 | 13339.59 | 13339.59 | 2041.06 | 11138.89 | 0 | 13179.95 | 126 | 162.29
NHT-006994 - Reporting | 25-PC-34451 | In progress |  |  | 12236 | 8577.65 | 8577.65 | 1220.82 | 6662.53 | 0 | 7883.35 | 79 | 99.47
NHT-006995 - Lab Analysis | 25-PC-34451 | In progress |  |  | 4214 | 2953.91 | 2953.91 | 950.72 | 5188.5 | 0 | 6139.22 | 33 | 73.35
NHT-007002 - Survey | 25-PC-34451 | In progress |  |  | 5557 | 3895.44 | 3895.44 | 1402.96 | 7656.57 | 0 | 9059.53 | 36 | 111.92
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34451 | In progress |  |  | 0 | 0 | 0 | 0 | 1039.16 | 0 | 1039.16 | 0 | 14.5
NHT-007014 - Desktop Review | 25-PC-34537 | On hold |  |  | 6811 | 4968.28 | 5480.39 | 306.85 | 2109.32 | 0 | 2416.17 | 62 | 36.27
NHT-007019 - Data Recovery Excavation | 25-PC-34537 | On hold |  |  | 40400 | 29467.08 | 32504.44 | 1819.98 | 12510.5 | 0 | 14330.48 | 352 | 212.47
NHT-007026 - Site Recordation | 25-PC-34537 | On hold |  |  | 12417 | 9056.9 | 9990.46 | 559.38 | 3845.19 | 0 | 4404.57 | 121 | 73.4
NHT-007027 - Testing | 25-PC-34537 | On hold |  |  | 19272 | 14057.06 | 15506.01 | 868.2 | 5968.05 | 0 | 6836.25 | 147 | 81.74
NHT-007033 - Reporting | 25-PC-34652 | In progress |  |  | 41289 | 35454.7 | 35454.7 | 3132.75 | 40992.07 | 0 | 44124.82 | 298 | 594.46
NHT-007040 - Final Report | 25-PC-34652 | In progress |  |  | 20094 | 17254.91 | 17254.91 | 2346.62 | 30705.38 | 0 | 33052 | 157 | 490.58
NHT-007047 - Fieldwork | 25-PC-34652 | In progress |  |  | 88070 | 75625.81 | 75625.81 | 2856.58 | 37378.2 | 0 | 40234.78 | 749 | 626.62
NHT-007051 - Desktop Review | 25-PC-34652 | In progress |  |  | 61247 | 52592.67 | 52592.67 | 2252.03 | 29467.66 | 0 | 31719.69 | 529 | 445.9
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34652 | In progress |  |  | 0 | 0 | 0 | 0 | 2125.49 | 0 | 2125.49 | 0 | 36.5
NHT-007064 - Monitoring | 25-PC-34681 | In progress |  |  | 316396 | 190628.1 | 190628.1 | 8784.88 | 31389.78 | 0 | 40174.66 | 2593 | 557.46
NHT-007065 - Survey | 25-PC-34681 | In progress |  |  | 284674 | 171516.38 | 171516.38 | 12156.06 | 43435.53 | 0 | 55591.59 | 2081 | 751.73
NHT-007072 - Agency Consultation | 25-PC-34681 | In progress |  |  | 114130 | 68763.52 | 68763.52 | 13351.15 | 47705.79 | 0 | 61056.94 | 824 | 799.65
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34681 | In progress |  |  | 0 | 0 | 0 | 0 | 2674.89 | 0 | 2674.89 | 0 | 43.5
NHT-007080 - Data Recovery Excavation | 25-PC-34732 | In progress |  |  | 79188 | 59461.9 | 59461.9 | 3063.25 | 33403.98 | 0 | 36467.23 | 439 | 528.06
NHT-007085 - Site Recordation | 25-PC-34732 | In progress |  |  | 22612 | 16979.72 | 16979.72 | 874.73 | 9538.71 | 0 | 10413.44 | 115 | 157.15
NHT-007092 - Prefield | 25-PC-34768 | Completed |  |  | 9362 | 6951.42 | 6951.42 | 1536.62 | 7449.44 | 0 | 8986.06 | 0 | 122.1
NHT-007094 - Monitoring | 25-PC-34768 | Completed |  |  | 60881 | 45204.33 | 45204.33 | 9992.45 | 48442.94 | 0 | 58435.39 | 0 | 766.12
NHT-007098 - Project Management | 25-PC-34768 | Completed |  |  | 14562 | 10812.2 | 10812.2 | 2390.05 | 11586.83 | 0 | 13976.88 | 0 | 173.17
NHT-007101 - Agency Consultation | 25-PC-34768 | Completed |  |  | 10559 | 7839.84 | 7839.84 | 1733 | 8401.52 | 0 | 10134.52 | 0 | 145.83
NHT-007108 - Lab Analysis | 25-PC-34768 | Completed |  |  | 24036 | 17846.71 | 17846.71 | 3945.03 | 19125.32 | 0 | 23070.35 | 0 | 335.31
NHT-007111 - Fieldwork | 25-PC-34772 | Completed |  |  | 3849 | 2604.05 | 2604.05 | 33 | 153.42 | 0 | 186.42 | 24 | 3.02
NHT-007118 - Reporting | 25-PC-34772 | Completed |  |  | 133356 | 90215.21 | 90215.21 | 1314.21 | 6110.71 | 0 | 7424.92 | 998 | 142.33
NHT-007123 - Project Management | 25-PC-34772 | Completed |  |  | 1155 | 781.21 | 781.21 | 9.9 | 46.03 | 0 | 55.93 | 8 | 0.98
NHT-007128 - Lab Analysis | 25-PC-34772 | Completed |  |  | 48540 | 32837.38 | 32837.38 | 753.64 | 3504.21 | 0 | 4257.85 | 356 | 82.58
NHT-007129 - Agency Consultation | 25-PC-34780 | In progress |  |  | 13970 | 8776.17 | 8776.17 | 1730.54 | 15791.05 | 0 | 17521.59 | 108 | 273.86
NHT-007131 - GIS & Mapping | 25-PC-34780 | In progress |  |  | 20087 | 12618.87 | 12618.87 | 2067.14 | 18862.45 | 0 | 20929.59 | 148 | 322.57
NHT-007136 - Desktop Review | 25-PC-34780 | In progress |  |  | 13518 | 8491.73 | 8491.73 | 1028.29 | 9383.09 | 0 | 10411.38 | 104 | 153.56
NHT-007139 - Lab Analysis | 25-PC-34780 | In progress |  |  | 14466 | 9087.79 | 9087.79 | 1906.53 | 17396.93 | 0 | 19303.46 | 131 | 274.59
NHT-007144 - Survey | 25-PC-34780 | Completed |  |  | 20159 | 12663.48 | 12663.48 | 1421.52 | 12971.21 | 0 | 14392.73 | 171 | 224.18
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34780 | In progress |  |  | 0 | 0 | 0 | 0 | 645.54 | 0 | 645.54 | 0 | 10.25
NHT-007152 - Final Report | 25-PC-34843 | Completed |  |  | 49944 | 36274.64 | 36274.64 | 3909.99 | 31315.17 | 0 | 35225.16 | 497 | 601.65
NHT-007157 - Background Research | 25-PC-34843 | Completed |  |  | 33575 | 24385.44 | 24385.44 | 2628.47 | 21051.46 | 0 | 23679.93 | 257 | 455.79
NHT-007162 - Prefield | 25-PC-34843 | Completed |  |  | 43192 | 31370.24 | 31370.24 | 3381.35 | 27081.29 | 0 | 30462.64 | 423 | 523.71
NHT-007165 - GIS & Mapping | 25-PC-34843 | Completed |  |  | 61289 | 44514.08 | 44514.08 | 4798.12 | 38428.12 | 0 | 43226.24 | 576 | 921.69
NHT-007172 - Reporting | 25-PC-34850 | In progress |  |  | 66270 | 38529.48 | 38529.48 | 5348.02 | 20870.48 | 0 | 26218.5 | 483 | 388.24
NHT-007175 - Survey | 25-PC-34850 | Completed |  |  | 31215 | 18148.17 | 18148.17 | 7163.99 | 27957.3 | 0 | 35121.29 | 232 | 507.87
NHT-007177 - GIS & Mapping | 25-PC-34850 | In progress |  |  | 103815 | 60358.17 | 60358.17 | 6482.54 | 25297.91 | 0 | 31780.45 | 923 | 410.89
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34850 | In progress |  |  | 0 | 0 | 0 | 0 | 1380.02 | 0 | 1380.02 | 0 | 22.5
NHT-007186 - Curation | 25-PC-34871 | Completed |  |  | 338100 | 260979.39 | 260979.39 | 18795.22 | 129795.76 | 0 | 148590.98 | 3386 | 2088.35
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-34871 | Completed |  |  | 0 | 0 | 0 | 0 | 1770.83 | 0 | 1770.83 | 0 | 27
NHT-007192 - Testing | 25-PC-35024 | In progress |  |  | 2352 | 1730 | 1730 | 187.81 | 957.36 | 0 | 1145.17 | 28 | 23.04
NHT-007196 - Agency Consultation | 25-PC-35024 | In progress |  |  | 57703 | 42440.3 | 42440.3 | 5040.02 | 25691.79 | 0 | 30731.81 | 673 | 594.33
NHT-007197 - Prefield | 25-PC-35024 | In progress |  |  | 915 | 672.78 | 672.78 | 73.04 | 372.31 | 0 | 445.35 | 9 | 7.87
NHT-007199 - GIS & Mapping | 25-PC-35024 | In progress |  |  | 79755 | 58659.89 | 58659.89 | 6683.05 | 34067.28 | 0 | 40750.33 | 792 | 787.62
NHT-007204 - Background Research | 25-PC-35024 | In progress |  |  | 83675 | 61543.23 | 61543.23 | 7051.22 | 35944.05 | 0 | 42995.27 | 1184 | 795.51
NHT-007211 - Lab Analysis | 25-PC-35040 | In progress |  |  | 18257 | 12498.73 | 12498.73 | 2436.64 | 13804.13 | 0 | 16240.77 | 232 | 328.62
NHT-007215 - Fieldwork | 25-PC-35040 | In progress |  |  | 43162 | 29548.45 | 29548.45 | 4129.51 | 23394.54 | 0 | 27524.05 | 425 | 505.57
NHT-007220 - Site Recordation | 25-PC-35040 | Completed |  |  | 9981 | 6833.26 | 6833.26 | 1976.02 | 11194.62 | 0 | 13170.64 | 142 | 236.52
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35040 | In progress |  |  | 0 | 0 | 0 | 0 | 12.33 | 0 | 12.33 | 0 | 0.25
NHT-007229 - Desktop Review | 25-PC-35084 | Completed |  |  | 22700 | 10895.31 | 14799.96 | 1577.51 | 11741.08 | 0 | 13318.59 | 261 | 308.94
NHT-007230 - Agency Consultation | 25-PC-35084 | Completed |  |  | 63431 | 30444.49 | 41355.15 | 2592.55 | 19295.76 | 0 | 21888.31 | 792 | 439.99
NHT-007232 - Survey | 25-PC-35084 | Completed |  |  | 66573 | 31952.01 | 43402.92 | 2277.37 | 16949.95 | 0 | 19227.32 | 942 | 421.12
NHT-007237 - Background Research | 25-PC-35084 | Completed |  |  | 36615 | 17573.52 | 23871.5 | 2977.85 | 22163.39 | 0 | 25141.24 | 393 | 555.28
NHT-007243 - Reporting | 25-PC-35084 | Completed |  |  | 15581 | 7478.39 | 10158.48 | 1539.8 | 11460.4 | 0 | 13000.2 | 178 | 286.25
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35084 | Completed |  |  | 0 | 0 | 0 | 0 | 348.69 | 0 | 348.69 | 0 | 8.75
NHT-007248 - Data Recovery Excavation | 25-PC-35131 | In progress |  |  | 311900 | 227562.24 | 227562.24 | 7166.22 | 88383.33 | 0 | 95549.55 | 6216 | 1950.68
NHT-007251 - Site Recordation | 25-PC-35138 | In progress |  |  | 256329 | 150108.81 | 162841.95 | 19999.7 | 91804.18 | 0 | 111803.88 | 2259 | 1754
NHT-007255 - Agency Consultation | 25-PC-35138 | In progress |  |  | 158601 | 92878.39 | 100756.88 | 18450.8 | 84694.29 | 0 | 103145.09 | 1654 | 1612.11
NHT-007262 - Project Management | 25-PC-35138 | In progress |  |  | 219959 | 128810.38 | 139736.84 | 20175.54 | 92611.36 | 0 | 112786.9 | 2163 | 1713.92
NHT-007264 - Final Report | 25-PC-35138 | In progress |  |  | 180111 | 105475.06 | 114422.08 | 16642.68 | 76394.56 | 0 | 93037.24 | 2298 | 1317.18
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35138 | In progress |  |  | 0 | 0 | 0 | 0 | 4473.89 | 0 | 4473.89 | 0 | 82.75
NHT-007275 - Draft Report | 25-PC-35168 | Completed |  |  | 330300 | 212151.69 | 212151.69 | 13878.64 | 190218.95 | 0 | 204097.59 | 4369 | 3761.44
NHT-007280 - Reporting | 25-PC-35182 | In progress |  |  | 11938 | 8448.53 | 8448.53 | 1603.22 | 6123.88 | 0 | 7727.1 | 103 | 150.96
NHT-007281 - Site Recordation | 25-PC-35182 | Completed |  |  | 1917 | 1356.41 | 1356.41 | 598.63 | 2286.62 | 0 | 2885.25 | 17 | 56.51
NHT-007282 - Monitoring | 25-PC-35182 | In progress |  |  | 7558 | 5349.12 | 5349.12 | 977.71 | 3734.6 | 0 | 4712.31 | 61 | 85.26
NHT-007288 - Curation | 25-PC-35182 | In progress |  |  | 2937 | 2078.41 | 2078.41 | 1128.98 | 4312.43 | 0 | 5441.41 | 25 | 104.83
NHT-007294 - Testing | 25-PC-35182 | In progress |  |  | 8850 | 6263.17 | 6263.17 | 1451.71 | 5545.18 | 0 | 6996.89 | 67 | 127.74
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35182 | In progress |  |  | 0 | 0 | 0 | 0 | 335.79 | 0 | 335.79 | 0 | 7.5
NHT-007301 - Fieldwork | 25-PC-35272 | In progress |  |  | 20312 | 14647.22 | 14647.22 | 1296.17 | 10600.59 | 0 | 11896.76 | 291 | 259.39
NHT-007308 - Project Management | 25-PC-35272 | In progress |  |  | 10348 | 7461.87 | 7461.87 | 1082.15 | 8850.25 | 0 | 9932.4 | 131 | 217.61
NHT-007315 - Desktop Review | 25-PC-35272 | In progress |  |  | 3104 | 2238.61 | 2238.61 | 395.73 | 3236.41 | 0 | 3632.14 | 40 | 82
NHT-007318 - GIS & Mapping | 25-PC-35272 | In progress |  |  | 9541 | 6879.75 | 6879.75 | 954.24 | 7804.1 | 0 | 8758.34 | 121 | 201.54
NHT-007324 - Draft Report | 25-PC-35272 | Completed |  |  | 6595 | 4755.44 | 4755.44 | 821.29 | 6716.82 | 0 | 7538.11 | 82 | 165.05
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35272 | In progress |  |  | 0 | 0 | 0 | 0 | 367.99 | 0 | 367.99 | 0 | 9.25
NHT-007336 - Monitoring | 25-PC-35295 | In progress |  |  | 80400 | 54551.4 | 54551.4 | 2659.01 | 37027.67 | 0 | 39686.68 | 973 | 559.52
NHT-007340 - Draft Report | 25-PC-35340 | Completed |  |  | 4615 | 3311.3 | 3311.3 | 3348.86 | 13826.47 | 0 | 17175.33 | 39 | 328.02
NHT-007344 - Lab Analysis | 25-PC-35340 | In progress |  |  | 14785 | 10608.2 | 10608.2 | 3654.65 | 15088.97 | 0 | 18743.62 | 109 | 351.71
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35340 | In progress |  |  | 0 | 0 | 0 | 0 | 368.68 | 0 | 368.68 | 0 | 7.5
NHT-007356 - Draft Report | 25-PC-35361 | In progress |  |  | 16701 | 13329.49 | 13329.49 | 1401.32 | 12072.97 | 0 | 13474.29 | 213 | 305.91
NHT-007361 - Monitoring | 25-PC-35361 | In progress |  |  | 4414 | 3522.75 | 3522.75 | 740.17 | 6376.88 | 0 | 7117.05 | 53 | 152.23
NHT-007362 - Agency Consultation | 25-PC-35361 | In progress |  |  | 2721 | 2171.29 | 2171.29 | 389.75 | 3357.81 | 0 | 3747.56 | 38 | 78.43
NHT-007364 - Final Report | 25-PC-35361 | In progress |  |  | 1264 | 1008.78 | 1008.78 | 298.28 | 2569.77 | 0 | 2868.05 | 17 | 58.23
NHT-007368 - Site Recordation | 25-PC-35431 | On hold |  |  | 304700 | 252565.83 | 252565.83 | 464.85 | 6272.14 | 0 | 6736.99 | 4186 | 136.04
NHT-007369 - Lab Analysis | 25-PC-35442 | Completed |  |  | 35333 | 26549.74 | 26549.74 | 6479.21 | 22971.73 | 0 | 29450.94 | 333 | 444.77
NHT-007371 - Project Management | 25-PC-35442 | Completed |  |  | 29192 | 21934.69 | 21934.69 | 5352.94 | 18978.62 | 0 | 24331.56 | 390 | 339.28
NHT-007378 - Agency Consultation | 25-PC-35442 | Completed |  |  | 22075 | 16586.81 | 16586.81 | 4047.85 | 14351.46 | 0 | 18399.31 | 219 | 268.65
NHT-007381 - Project Management | 25-PC-35470 | Completed |  |  | 258161 | 173716.53 | 173716.53 | 18756.47 | 166951.12 | 0 | 185707.59 | 2147 | 3169.04
NHT-007387 - Background Research | 25-PC-35470 | Completed |  |  | 225839 | 151967.07 | 151967.07 | 16408.14 | 146048.7 | 0 | 162456.84 | 2088 | 2511.98
NHT-007391 - Background Research | 25-PC-35485 | Completed |  |  | 51465 | 29518.92 | 34207.42 | 3435.31 | 29995.17 | 0 | 33430.48 | 532 | 407.79
NHT-007392 - Lab Analysis | 25-PC-35485 | In progress |  |  | 54340 | 31168.4 | 36118.88 | 3430.28 | 29951.3 | 0 | 33381.58 | 521 | 481.79
NHT-007395 - Survey | 25-PC-35485 | Completed |  |  | 8584 | 4923.32 | 5705.3 | 1858.37 | 16226.3 | 0 | 18084.67 | 88 | 254.73
NHT-007401 - Project Management | 25-PC-35485 | Completed |  |  | 22511 | 12912.02 | 14962.85 | 3060.3 | 26720.88 | 0 | 29781.18 | 203 | 412.27
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35485 | In progress |  |  | 0 | 0 | 0 | 0 | 4355.03 | 0 | 4355.03 | 0 | 55
NHT-007406 - Testing | 25-PC-35496 | Completed |  |  | 2233 | 1488.62 | 1488.62 | 393.42 | 2351.15 | 0 | 2744.57 | 19 | 23.2
NHT-007413 - Survey | 25-PC-35496 | Completed |  |  | 494 | 329.22 | 329.22 | 102.86 | 614.74 | 0 | 717.6 | 4 | 6.82
NHT-007419 - Agency Consultation | 25-PC-35496 | Completed |  |  | 910 | 606.88 | 606.88 | 295.14 | 1763.82 | 0 | 2058.96 | 8 | 17.76
NHT-007420 - Lab Analysis | 25-PC-35496 | In progress |  |  | 11563 | 7707.6 | 7707.6 | 626.61 | 3744.75 | 0 | 4371.36 | 124 | 63.25
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35496 | In progress |  |  | 0 | 0 | 0 | 0 | 534.21 | 0 | 534.21 | 0 | 5.75
NHT-007423 - Desktop Review | 25-PC-35525 | In progress |  |  | 61659 | 48957.99 | 48957.99 | 4317.78 | 16317.47 | 0 | 20635.25 | 442 | 268.46
NHT-007430 - GIS & Mapping | 25-PC-35525 | In progress |  |  | 14095 | 11191.17 | 11191.17 | 2553.12 | 9648.59 | 0 | 12201.71 | 119 | 127.78
NHT-007432 - Final Report | 25-PC-35525 | In progress |  |  | 14572 | 11569.83 | 11569.83 | 3651.55 | 13799.71 | 0 | 17451.26 | 93 | 199.63
NHT-007439 - Fieldwork | 25-PC-35525 | In progress |  |  | 8474 | 6728.21 | 6728.21 | 2070.78 | 7825.74 | 0 | 9896.52 | 53 | 99.07
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35525 | In progress |  |  | 0 | 0 | 0 | 0 | 1245.65 | 0 | 1245.65 | 0 | 15.5
NHT-007450 - Fieldwork | 25-PC-35553 | In progress |  |  | 210667 | 127194.02 | 158772.81 | 10862.5 | 75080.67 | 0 | 85943.17 | 3001 | 1233.32
NHT-007456 - GIS & Mapping | 25-PC-35553 | In progress |  |  | 79319 | 47890.58 | 59780.5 | 7004.66 | 48415.62 | 0 | 55420.28 | 1074 | 975.42
NHT-007460 - Testing | 25-PC-35553 | In progress |  |  | 169988 | 102633.49 | 128114.57 | 9059.24 | 62616.67 | 0 | 71675.91 | 2950 | 1117.33
NHT-007462 - Desktop Review | 25-PC-35553 | In progress |  |  | 86284 | 52095.51 | 65029.4 | 7237.49 | 50024.89 | 0 | 57262.38 | 1327 | 959.49
NHT-007468 - Project Management | 25-PC-35553 | In progress |  |  | 43642 | 26350 | 32891.99 | 5128.63 | 35448.67 | 0 | 40577.3 | 510 | 696.7
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35553 | In progress |  |  | 0 | 0 | 0 | 0 | 3461.14 | 0 | 3461.14 | 0 | 62
NHT-007474 - Prefield | 25-PC-35620 | Completed |  |  | 137050 | 97195.97 | 97195.97 | 17210.28 | 70597.28 | 0 | 87807.56 | 0 | 1112.46
NHT-007479 - Survey | 25-PC-35620 | Completed |  |  | 465617 | 330215.41 | 330215.41 | 58470.53 | 239848.52 | 0 | 298319.05 | 0 | 4981.43
NHT-007481 - Monitoring | 25-PC-35620 | Completed |  |  | 719067 | 509962.31 | 509962.31 | 90297.94 | 370405.81 | 0 | 460703.75 | 0 | 7544.11
NHT-007487 - Reporting | 25-PC-35620 | Completed |  |  | 412323 | 292419.57 | 292419.57 | 51778.11 | 212395.91 | 0 | 264174.02 | 0 | 4697.4
NHT-007490 - Site Recordation | 25-PC-35620 | Completed |  |  | 273143 | 193712.98 | 193712.98 | 34300.34 | 140701.4 | 0 | 175001.74 | 0 | 2216.12
NHT-007495 - Monitoring | 25-PC-35740 | In progress |  |  | 14790 | 6535.41 | 7819.29 | 10.03 | 146.7 | 0 | 156.73 | 106 | 2.54
NHT-007496 - Lab Analysis | 25-PC-35740 | In progress |  |  | 4564 | 2017.02 | 2413.26 | 3.1 | 45.28 | 0 | 48.38 | 37 | 0.77
NHT-007503 - Desktop Review | 25-PC-35740 | In progress |  |  | 1810 | 799.89 | 957.03 | 1.23 | 17.96 | 0 | 19.19 | 15 | 0.31
NHT-007508 - Curation | 25-PC-35740 | In progress |  |  | 3656 | 1615.74 | 1933.16 | 2.48 | 36.27 | 0 | 38.75 | 25 | 0.76
NHT-007509 - GIS & Mapping | 25-PC-35740 | In progress |  |  | 3780 | 1670.24 | 1998.36 | 2.56 | 37.49 | 0 | 40.05 | 23 | 0.73
NHT-007511 - Project Management | 25-PC-35761 | In progress |  |  | 204800 | 136396.8 | 136396.8 | 14147.85 | 122437.51 | 0 | 136585.36 | 2527 | 2926.42
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35761 | In progress |  |  | 0 | 0 | 0 | 0 | 3492.33 | 0 | 3492.33 | 0 | 83
NHT-007515 - Prefield | 25-PC-35779 | Completed |  |  | 7015 | 3552.16 | 4776.2 | 1379.82 | 5955.48 | 0 | 7335.3 | 41 | 110.66
NHT-007519 - Site Recordation | 25-PC-35779 | In progress |  |  | 13203 | 6685.89 | 8989.8 | 2424.39 | 10463.97 | 0 | 12888.36 | 103 | 211.99
NHT-007525 - Fieldwork | 25-PC-35779 | Completed |  |  | 11129 | 5635.38 | 7577.29 | 2181.49 | 9415.57 | 0 | 11597.06 | 74 | 158.86
NHT-007528 - GIS & Mapping | 25-PC-35779 | In progress |  |  | 31296 | 15847.91 | 21308.98 | 2878.23 | 12422.81 | 0 | 15301.04 | 163 | 235.23
NHT-007532 - Data Recovery Excavation | 25-PC-35779 | In progress |  |  | 62157 | 31475.31 | 42321.48 | 4112.87 | 17751.64 | 0 | 21864.51 | 365 | 316.01
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35779 | In progress |  |  | 0 | 0 | 0 | 0 | 1539.83 | 0 | 1539.83 | 0 | 29
NHT-007536 - Project Management | 25-PC-35850 | Completed |  |  | 53400 | 37978.08 | 37978.08 | 3977.21 | 28097.06 | 0 | 32074.27 | 355 | 584.04
NHT-007543 - Agency Consultation | 25-PC-35897 | In progress |  |  | 30010 | 21889.1 | 21889.1 | 1739.45 | 18422.86 | 0 | 20162.31 | 277 | 447.76
NHT-007546 - Fieldwork | 25-PC-35897 | In progress |  |  | 53690 | 39161.68 | 39161.68 | 3075.88 | 32577.25 | 0 | 35653.13 | 595 | 720.22
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35897 | In progress |  |  | 0 | 0 | 0 | 0 | 176.71 | 0 | 176.71 | 0 | 4.25
NHT-007555 - GIS & Mapping | 25-PC-35958 | Completed |  |  | 67300 | 54896.61 | 54896.61 | 6313.97 | 55587.73 | 0 | 61901.7 | 806 | 1102.39
NHT-007560 - Prefield | 25-PC-35963 | In progress |  |  | 255493 | 172610.81 | 172610.81 | 15032.3 | 118107.36 | 0 | 133139.66 | 1830 | 2479.74
NHT-007565 - Draft Report | 25-PC-35963 | In progress |  |  | 64507 | 43581.19 | 43581.19 | 7596.36 | 59683.85 | 0 | 67280.21 | 480 | 1134.68
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35963 | In progress |  |  | 0 | 0 | 0 | 0 | 1621.72 | 0 | 1621.72 | 0 | 30.5
NHT-007571 - Site Recordation | 25-PC-35970 | In progress |  |  | 4391 | 2923.45 | 3209.79 | 182.01 | 733.02 | 0 | 915.03 | 0 | 17.88
NHT-007577 - GIS & Mapping | 25-PC-35970 | In progress |  |  | 21133 | 14069.33 | 15447.36 | 1000.23 | 4028.25 | 0 | 5028.48 | 0 | 105.42
NHT-007579 - Testing | 25-PC-35970 | In progress |  |  | 538 | 358.1 | 393.17 | 14.03 | 56.49 | 0 | 70.52 | 0 | 1.39
NHT-007580 - Agency Consultation | 25-PC-35970 | In progress |  |  | 27138 | 18066.4 | 19835.94 | 1159.4 | 4669.27 | 0 | 5828.67 | 0 | 119.99
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-35970 | In progress |  |  | 0 | 0 | 0 | 0 | 115 | 0 | 115 | 0 | 2.75
NHT-007589 - Data Recovery Excavation | 25-PC-36007 | On hold |  |  | 7773 | 5819.03 | 5819.03 | 10.09 | 46.93 | 0 | 57.02 | 89 | 0.84
NHT-007596 - Monitoring | 25-PC-36007 | On hold |  |  | 8401 | 6288.54 | 6288.54 | 10.9 | 50.72 | 0 | 61.62 | 108 | 0.96
NHT-007600 - Lab Analysis | 25-PC-36007 | On hold |  |  | 3596 | 2692.13 | 2692.13 | 4.67 | 21.71 | 0 | 26.38 | 32 | 0.41
NHT-007602 - Agency Consultation | 25-PC-36007 | On hold |  |  | 1930 | 1444.92 | 1444.92 | 2.51 | 11.65 | 0 | 14.16 | 19 | 0.24
NHT-007604 - Data Recovery Excavation | 25-PC-36030 | Completed |  |  | 89200 | 52267.27 | 57064.52 | 6387.03 | 53867.98 | 0 | 60255.01 | 963 | 1014.76
NHT-007611 - Final Report | 25-PC-36051 | In progress |  |  | 405400 | 250415.58 | 250415.58 | 16624.91 | 153017.05 | 0 | 169641.96 | 3587 | 2787.64
NHT-007613 - Data Recovery Excavation | 25-PC-36071 | Completed |  |  | 145312 | 119810.09 | 119810.09 | 13748.07 | 99872.3 | 0 | 113620.37 | 1597 | 1725.13
NHT-007618 - Testing | 25-PC-36071 | Completed |  |  | 99888 | 82357.31 | 82357.31 | 9450.4 | 68652.11 | 0 | 78102.51 | 1157 | 1275.65
NHT-007622 - Agency Consultation | 25-PC-36093 | Completed |  |  | 213300 | 157884.66 | 157884.66 | 9698.44 | 101074.58 | 0 | 110773.02 | 2595 | 2427.66
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36093 | Completed |  |  | 0 | 0 | 0 | 0 | 703.27 | 0 | 703.27 | 0 | 18
NHT-007631 - Survey | 25-PC-36129 | In progress |  |  | 10206 | 6981.68 | 6981.68 | 1433.35 | 10896.23 | 0 | 12329.58 | 104 | 141.74
NHT-007637 - Testing | 25-PC-36129 | Completed |  |  | 18194 | 12446.32 | 12446.32 | 1880.23 | 14293.44 | 0 | 16173.67 | 189 | 177.21
NHT-007641 - Data Recovery Excavation | 25-PC-36129 | In progress |  |  | 61942 | 42374.57 | 42374.57 | 3251.77 | 24719.87 | 0 | 27971.64 | 707 | 402.36
NHT-007642 - Background Research | 25-PC-36129 | In progress |  |  | 3719 | 2544.34 | 2544.34 | 837.42 | 6366 | 0 | 7203.42 | 49 | 82.81
NHT-007648 - Draft Report | 25-PC-36129 | In progress |  |  | 20139 | 13777.31 | 13777.31 | 1746.95 | 13280.25 | 0 | 15027.2 | 205 | 223.5
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36129 | In progress |  |  | 0 | 0 | 0 | 0 | 857.27 | 0 | 857.27 | 0 | 11.75
NHT-007656 - GIS & Mapping | 25-PC-36197 | On hold |  |  | 7956 | 5969.11 | 5969.11 | 311.02 | 4473.89 | 0 | 4784.91 | 0 | 91.14
NHT-007662 - Agency Consultation | 25-PC-36197 | On hold |  |  | 2818 | 2114.61 | 2114.61 | 110.18 | 1584.92 | 0 | 1695.1 | 0 | 22.07
NHT-007666 - Curation | 25-PC-36197 | On hold |  |  | 5788 | 4342.47 | 4342.47 | 226.26 | 3254.71 | 0 | 3480.97 | 0 | 71.13
NHT-007668 - Draft Report | 25-PC-36197 | On hold |  |  | 10432 | 7827.55 | 7827.55 | 407.86 | 5866.79 | 0 | 6274.65 | 0 | 110.99
NHT-007670 - Reporting | 25-PC-36197 | On hold |  |  | 8906 | 6682.03 | 6682.03 | 348.16 | 5008.22 | 0 | 5356.38 | 0 | 111.38
NHT-007671 - Testing | 25-PC-36251 | Completed |  |  | 19206 | 14917.5 | 14917.5 | 3819.82 | 20234 | 0 | 24053.82 | 124 | 251.27
NHT-007674 - Lab Analysis | 25-PC-36251 | Completed |  |  | 3409 | 2647.9 | 2647.9 | 901.24 | 4773.95 | 0 | 5675.19 | 27 | 58.52
NHT-007677 - GIS & Mapping | 25-PC-36251 | Completed |  |  | 1992 | 1546.94 | 1546.94 | 438.28 | 2321.64 | 0 | 2759.92 | 18 | 30.46
NHT-007683 - Final Report | 25-PC-36251 | Completed |  |  | 10263 | 7971.56 | 7971.56 | 1683.85 | 8919.57 | 0 | 10603.42 | 79 | 109.3
NHT-007685 - Prefield | 25-PC-36251 | Completed |  |  | 4330 | 3362.74 | 3362.74 | 951.83 | 5041.97 | 0 | 5993.8 | 29 | 68.82
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36251 | Completed |  |  | 0 | 0 | 0 | 0 | 249.4 | 0 | 249.4 | 0 | 3.25
NHT-007696 - Project Management | 25-PC-36263 | In progress |  |  | 28100 | 19141.72 | 19141.72 | 2800.86 | 13524.8 | 0 | 16325.66 | 0 | 242.13
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36263 | In progress |  |  | 0 | 0 | 0 | 0 | 247.45 | 0 | 247.45 | 0 | 5.5
NHT-007704 - Fieldwork | 25-PC-36313 | Completed |  |  | 93028 | 65203.23 | 65203.23 | 18478.6 | 66285.61 | 0 | 84764.21 | 653 | 1077.47
NHT-007711 - Curation | 25-PC-36313 | Completed |  |  | 17587 | 12326.85 | 12326.85 | 3493.43 | 12531.47 | 0 | 16024.9 | 121 | 182.87
NHT-007718 - Final Report | 25-PC-36313 | Completed |  |  | 24485 | 17161.51 | 17161.51 | 4863.57 | 17446.39 | 0 | 22309.96 | 158 | 300.32
NHT-007720 - Curation | 25-PC-36332 | In progress |  |  | 509837 | 331309.41 | 362304.83 | 21820.86 | 177478.79 | 0 | 199299.65 | 6851 | 3281.12
NHT-007727 - Background Research | 25-PC-36332 | In progress |  |  | 361163 | 234696.36 | 256653.22 | 14816.15 | 120506.42 | 0 | 135322.57 | 4774 | 2480.88
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36332 | In progress |  |  | 0 | 0 | 0 | 0 | 1497.11 | 0 | 1497.11 | 0 | 31.5
NHT-007738 - Reporting | 25-PC-36336 | Completed |  |  | 1819 | 1292.01 | 1292.01 | 304.43 | 1535.98 | 0 | 1840.41 | 14 | 24.61
NHT-007740 - Data Recovery Excavation | 25-PC-36336 | In progress |  |  | 12671 | 9000.51 | 9000.51 | 1298.12 | 6549.49 | 0 | 7847.61 | 104 | 106.39
NHT-007747 - Background Research | 25-PC-36336 | In progress |  |  | 14207 | 10090.64 | 10090.64 | 1223.78 | 6174.41 | 0 | 7398.19 | 93 | 120.54
NHT-007750 - Desktop Review | 25-PC-36336 | Completed |  |  | 7703 | 5471.76 | 5471.76 | 1084.03 | 5469.31 | 0 | 6553.34 | 67 | 73.97
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36336 | In progress |  |  | 0 | 0 | 0 | 0 | 59.59 | 0 | 59.59 | 0 | 1.25
NHT-007756 - Survey | 25-PC-36352 | In progress |  |  | 1286596 | 750412.91 | 892402.45 | 17573.52 | 104558.96 | 0 | 122132.48 | 6597 | 1446.93
NHT-007757 - Agency Consultation | 25-PC-36352 | In progress |  |  | 1976304 | 1152688.27 | 1370794.43 | 27228.48 | 162004.02 | 0 | 189232.5 | 9364 | 2320.18
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36352 | In progress |  |  | 0 | 0 | 0 | 0 | 1935.75 | 0 | 1935.75 | 0 | 31.5
NHT-007764 - Survey | 25-PC-36366 | In progress |  |  | 60621 | 51539.91 | 51539.91 | 4101.07 | 16119.03 | 0 | 20220.1 | 0 | 292.45
NHT-007766 - Reporting | 25-PC-36366 | In progress |  |  | 58879 | 50058.99 | 50058.99 | 3716.59 | 14607.87 | 0 | 18324.46 | 0 | 255.12
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36366 | In progress |  |  | 0 | 0 | 0 | 0 | 156.71 | 0 | 156.71 | 0 | 3.25
NHT-007771 - Testing | 25-PC-36464 | In progress |  |  | 10357 | 5374.95 | 7365.64 | 384.92 | 5505.81 | 0 | 5890.73 | 0 | 94.25
NHT-007774 - Draft Report | 25-PC-36464 | In progress |  |  | 13515 | 7013.63 | 9611.23 | 532.47 | 7616.39 | 0 | 8148.86 | 0 | 106.65
NHT-007781 - Desktop Review | 25-PC-36464 | In progress |  |  | 47244 | 24517.59 | 33598 | 1837.34 | 26281.11 | 0 | 28118.45 | 0 | 396.45
NHT-007786 - Curation | 25-PC-36464 | In progress |  |  | 31184 | 16183.12 | 22176.76 | 1217.5 | 17415 | 0 | 18632.5 | 0 | 272.56
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36464 | In progress |  |  | 0 | 0 | 0 | 0 | -605.25 | 0 | -605.25 | 0 | -5
NHT-007789 - Final Report | 25-PC-36485 | In progress |  |  | 1111 | 868.56 | 868.56 | 136.73 | 1583.36 | 0 | 1720.09 | 8 | 20.05
NHT-007795 - Background Research | 25-PC-36485 | Completed |  |  | 3087 | 2412.83 | 2412.83 | 362.38 | 4196.47 | 0 | 4558.85 | 23 | 54.46
NHT-007800 - Fieldwork | 25-PC-36485 | Completed |  |  | 8007 | 6258.22 | 6258.22 | 770.63 | 8924.16 | 0 | 9694.79 | 48 | 120.53
NHT-007802 - Data Recovery Excavation | 25-PC-36485 | In progress |  |  | 12990 | 10152.88 | 10152.88 | 900.23 | 10424.89 | 0 | 11325.12 | 115 | 148.41
NHT-007808 - Survey | 25-PC-36485 | In progress |  |  | 7905 | 6178.47 | 6178.47 | 537.97 | 6229.9 | 0 | 6767.87 | 47 | 84.95
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36485 | In progress |  |  | 0 | 0 | 0 | 0 | 211.03 | 0 | 211.03 | 0 | 2.75
NHT-007814 - Final Report | 25-PC-36507 | In progress |  |  | 88300 | 54269.18 | 54269.18 | 5716.91 | 35772.74 | 0 | 41489.65 | 568 | 654.6
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36507 | In progress |  |  | 0 | 0 | 0 | 0 | 546.42 | 0 | 546.42 | 0 | 12
NHT-007823 - Desktop Review | 25-PC-36532 | On hold |  |  | 7151 | 4970.14 | 4970.14 | 309.41 | 2052.49 | 0 | 2361.9 | 44 | 31.99
NHT-007824 - Reporting | 25-PC-36532 | On hold |  |  | 24285 | 16877.51 | 16877.51 | 1050.68 | 6969.78 | 0 | 8020.46 | 176 | 117.7
NHT-007825 - Testing | 25-PC-36532 | On hold |  |  | 22845 | 15877.32 | 15877.32 | 988.42 | 6556.75 | 0 | 7545.17 | 170 | 94.58
NHT-007826 - GIS & Mapping | 25-PC-36532 | On hold |  |  | 13019 | 9048.53 | 9048.53 | 563.3 | 3736.71 | 0 | 4300.01 | 129 | 58.31
NHT-007833 - Background Research | 25-PC-36573 | In progress |  |  | 116000 | 66050.4 | 66050.4 | 10037.07 | 38686.56 | 0 | 48723.63 | 559 | 531.73
NHT-007840 - Survey | 25-PC-36637 | Completed |  |  | 19780 | 16039.34 | 16039.34 | 2466.1 | 10864.17 | 0 | 13330.27 | 135 | 210.17
NHT-007841 - GIS & Mapping | 25-PC-36637 | Completed |  |  | 4199 | 3405.15 | 3405.15 | 523.55 | 2306.46 | 0 | 2830.01 | 33 | 36.53
NHT-007842 - Fieldwork | 25-PC-36637 | Completed |  |  | 20421 | 16559.47 | 16559.47 | 2546.08 | 11216.48 | 0 | 13762.56 | 156 | 170.42
NHT-007843 - Site Recordation | 25-PC-36641 | In progress |  |  | 39412 | 25566.39 | 25566.39 | 11290.34 | 54565.02 | 0 | 65855.36 | 354 | 902.01
NHT-007846 - Desktop Review | 25-PC-36641 | Completed |  |  | 141888 | 92042.92 | 92042.92 | 16723.99 | 80825.25 | 0 | 97549.24 | 1337 | 1426.32
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36641 | In progress |  |  | 0 | 0 | 0 | 0 | 1385.58 | 0 | 1385.58 | 0 | 22.5
NHT-007857 - Fieldwork | 25-PC-36645 | Completed |  |  | 18379 | 14690.01 | 14690.01 | 1382.28 | 20715.07 | 0 | 22097.35 | 376 | 366.39
NHT-007863 - Reporting | 25-PC-36645 | In progress |  |  | 7021 | 5612.21 | 5612.21 | 992 | 14866.33 | 0 | 15858.33 | 149 | 239.96
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36645 | In progress |  |  | 0 | 0 | 0 | 0 | 966.92 | 0 | 966.92 | 0 | 20.25
NHT-007867 - Site Recordation | 25-PC-36646 | In progress |  |  | 51891 | 37750.52 | 37750.52 | 2399.91 | 27037.51 | 0 | 29437.42 | 546 | 351.29
NHT-007872 - Lab Analysis | 25-PC-36646 | Completed |  |  | 28478 | 20717.88 | 20717.88 | 1676.01 | 18881.97 | 0 | 20557.98 | 321 | 237.17
NHT-007876 - Testing | 25-PC-36646 | In progress |  |  | 35715 | 25982.76 | 25982.76 | 1609.41 | 18131.74 | 0 | 19741.15 | 392 | 269.82
NHT-007881 - Reporting | 25-PC-36646 | In progress |  |  | 21316 | 15507.34 | 15507.34 | 1073.35 | 12092.45 | 0 | 13165.8 | 230 | 181.57
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36646 | In progress |  |  | 0 | 0 | 0 | 0 | 538.19 | 0 | 538.19 | 0 | 6.75
NHT-007893 - Desktop Review | 25-PC-36657 | Completed |  |  | 255700 | 150017.49 | 186833.25 | 6584.56 | 81846.01 | 0 | 88430.57 | 1796 | 1054.66
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36657 | Completed |  |  | 0 | 0 | 0 | 0 | 549.98 | 0 | 549.98 | 0 | 9.5
NHT-007899 - Final Report | 25-PC-36697 | Completed |  |  | 29703 | 20132.55 | 20132.55 | 4175.94 | 15068.01 | 0 | 19243.95 | 348 | 191.66
NHT-007903 - Fieldwork | 25-PC-36697 | Completed |  |  | 92492 | 62691.06 | 62691.06 | 13003.51 | 46920.52 | 0 | 59924.03 | 958 | 746.99
NHT-007908 - Project Management | 25-PC-36697 | Completed |  |  | 30224 | 20485.96 | 20485.96 | 4249.24 | 15332.52 | 0 | 19581.76 | 363 | 225.15
NHT-007909 - Prefield | 25-PC-36697 | Completed |  |  | 25558 | 17323.13 | 17323.13 | 3593.2 | 12965.32 | 0 | 16558.52 | 242 | 203.9
NHT-007915 - Agency Consultation | 25-PC-36697 | Completed |  |  | 19423 | 13165.02 | 13165.02 | 2730.72 | 9853.23 | 0 | 12583.95 | 213 | 129.87
NHT-007921 - Site Recordation | 25-PC-36761 | Completed |  |  | 74000 | 56358.4 | 56358.4 | 10704.82 | 55109.96 | 0 | 65814.78 | 393 | 829.6
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36761 | Completed |  |  | 0 | 0 | 0 | 0 | 264.37 | 0 | 264.37 | 0 | 6.25
NHT-007932 - Testing | 25-PC-36799 | Completed |  |  | 15031 | 12056.13 | 12056.13 | 1202.82 | 14478.93 | 0 | 15681.75 | 70 | 244.77
NHT-007938 - Curation | 25-PC-36799 | Completed |  |  | 17869 | 14332.96 | 14332.96 | 1308.87 | 15755.41 | 0 | 17064.28 | 91 | 239.05
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36799 | Completed |  |  | 0 | 0 | 0 | 0 | 302.49 | 0 | 302.49 | 0 | 4
NHT-007941 - Survey | 25-PC-36809 | In progress |  |  | 24200 | 16235.78 | 16235.78 | 5363.38 | 20799.14 | 0 | 26162.52 | 182 | 296.08
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36809 | In progress |  |  | 0 | 0 | 0 | 0 | 258.05 | 0 | 258.05 | 0 | 6.75
NHT-007950 - Site Recordation | 25-PC-36832 | In progress |  |  | 33479 | 22397.22 | 22397.22 | 2465.4 | 10113.17 | 0 | 12578.57 | 237 | 146.39
NHT-007954 - Draft Report | 25-PC-36832 | In progress |  |  | 44921 | 30052.38 | 30052.38 | 3308.05 | 13569.76 | 0 | 16877.81 | 328 | 186.18
NHT-007955 - GIS & Mapping | 25-PC-36838 | Completed |  |  | 54278 | 29915.02 | 40257 | 7375.45 | 30012.07 | 0 | 37387.52 | 380 | 430.53
NHT-007961 - Project Management | 25-PC-36838 | Completed |  |  | 29262 | 16127.33 | 21702.75 | 5452 | 22185.19 | 0 | 27637.19 | 176 | 325.99
NHT-007963 - Desktop Review | 25-PC-36838 | Completed |  |  | 112284 | 61884.23 | 83278.35 | 12992.2 | 52867.64 | 0 | 65859.84 | 1039 | 743.46
NHT-007967 - Site Recordation | 25-PC-36838 | Completed |  |  | 20576 | 11340.52 | 15261.08 | 4983.07 | 20277.01 | 0 | 25260.08 | 145 | 295.08
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-36838 | Completed |  |  | 0 | 0 | 0 | 0 | 2632.24 | 0 | 2632.24 | 0 | 38.25
NHT-007972 - Testing | 25-PC-36876 | Completed |  |  | 89840 | 64163.61 | 64163.61 | 18350.79 | 65061.9 | 0 | 83412.69 | 0 | 985
NHT-007979 - Project Management | 25-PC-36876 | Completed |  |  | 43916 | 31364.61 | 31364.61 | 8970.28 | 31803.72 | 0 | 40774 | 0 | 528.85
NHT-007980 - Site Recordation | 25-PC-36876 | Completed |  |  | 48882 | 34911.66 | 34911.66 | 9984.74 | 35400.43 | 0 | 45385.17 | 0 | 542.56
NHT-007982 - Data Recovery Excavation | 25-PC-36876 | Completed |  |  | 154362 | 110245.52 | 110245.52 | 31530.21 | 111788.95 | 0 | 143319.16 | 0 | 1589.3
NHT-007984 - Lab Analysis | 25-PC-36896 | Completed |  |  | 51170 | 32595.1 | 32595.1 | 7727.77 | 31105.24 | 0 | 38833.01 | 240 | 448.72
NHT-007987 - Testing | 25-PC-36896 | Completed |  |  | 78504 | 50007.55 | 50007.55 | 11855.97 | 47721.77 | 0 | 59577.74 | 296 | 608.86
NHT-007989 - Project Management | 25-PC-36896 | Completed |  |  | 37757 | 24050.97 | 24050.97 | 5702.09 | 22951.64 | 0 | 28653.73 | 148 | 331.77
NHT-007990 - Agency Consultation | 25-PC-36896 | Completed |  |  | 16769 | 10681.78 | 10681.78 | 2532.48 | 10193.54 | 0 | 12726.02 | 77 | 130.36
NHT-007993 - Desktop Review | 25-PC-36909 | Completed |  |  | 4235 | 3058.19 | 3058.19 | 377.51 | 2849.09 | 0 | 3226.6 | 41 | 38.86
NHT-007998 - Monitoring | 25-PC-36909 | Completed |  |  | 20968 | 15143.65 | 15143.65 | 1869.38 | 14108.23 | 0 | 15977.61 | 202 | 234.21
NHT-007999 - GIS & Mapping | 25-PC-36909 | Completed |  |  | 9131 | 6594.23 | 6594.23 | 814.01 | 6143.36 | 0 | 6957.37 | 79 | 85.81
NHT-008002 - Prefield | 25-PC-36909 | Completed |  |  | 7566 | 5464.11 | 5464.11 | 674.51 | 5090.51 | 0 | 5765.02 | 59 | 80.1
NHT-008004 - Background Research | 25-PC-36971 | Completed |  |  | 7777 | 5929.88 | 5929.88 | 1125.49 | 6583.35 | 0 | 7708.84 | 69 | 113.38
NHT-008008 - Reporting | 25-PC-36971 | Completed |  |  | 25726 | 19615.8 | 19615.8 | 3723.08 | 21777.46 | 0 | 25500.54 | 252 | 286.41
NHT-008011 - Fieldwork | 25-PC-36971 | Completed |  |  | 40864 | 31159.19 | 31159.19 | 5914.01 | 34592.95 | 0 | 40506.96 | 302 | 482.79
NHT-008014 - GIS & Mapping | 25-PC-36971 | Completed |  |  | 10733 | 8183.88 | 8183.88 | 1553.3 | 9085.74 | 0 | 10639.04 | 92 | 163.5
NHT-008021 - Draft Report | 25-PC-36988 | Completed |  |  | 66466 | 46831.61 | 46831.61 | 2815.1 | 41170.81 | 0 | 43985.91 | 314 | 508.2
NHT-008025 - Reporting | 25-PC-36988 | Completed |  |  | 46389 | 32685.49 | 32685.49 | 1964.76 | 28734.61 | 0 | 30699.37 | 305 | 333.56
NHT-008030 - Monitoring | 25-PC-36988 | Completed |  |  | 54564 | 38445.67 | 38445.67 | 2311.01 | 33798.52 | 0 | 36109.53 | 344 | 451.45
NHT-008033 - Fieldwork | 25-PC-36988 | Completed |  |  | 78581 | 55368.83 | 55368.83 | 3328.28 | 48676.07 | 0 | 52004.35 | 407 | 803.32
NHT-008034 - Curation | 25-PC-36993 | Completed |  |  | 90420 | 57470.64 | 57470.64 | 6757.61 | 42930.67 | 0 | 49688.28 | 804 | 539.14
NHT-008037 - Monitoring | 25-PC-36993 | Completed |  |  | 204231 | 129809.08 | 129809.08 | 15263.42 | 96967.61 | 0 | 112231.03 | 1778 | 1511.53
NHT-008043 - Survey | 25-PC-36993 | Completed |  |  | 407349 | 258911.48 | 258911.48 | 30443.74 | 193407.32 | 0 | 223851.06 | 3937 | 2874.71
NHT-008048 - Desktop Review | 25-PC-37164 | Completed |  |  | 75400 | 50299.34 | 50299.34 | 11090.03 | 78032.52 | 0 | 89122.55 | 503 | 1003.96
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37164 | In progress |  |  | 0 | 0 | 0 | 0 | 1779.37 | 0 | 1779.37 | 0 | 16.75
NHT-008059 - Lab Analysis | 25-PC-37188 | In progress |  |  | 44157 | 32062.22 | 32062.22 | 1600.34 | 18156.92 | 0 | 19757.26 | 313 | 268.32
NHT-008063 - Survey | 25-PC-37188 | In progress |  |  | 56678 | 41153.86 | 41153.86 | 1759.58 | 19963.62 | 0 | 21723.2 | 439 | 353.74
NHT-008065 - Reporting | 25-PC-37188 | In progress |  |  | 30765 | 22338.68 | 22338.68 | 1003.64 | 11387.03 | 0 | 12390.67 | 154 | 196.6
NHT-008069 - Prefield | 25-PC-37359 | Completed |  |  | 42030 | 30353.87 | 30353.87 | 3310.36 | 23172.52 | 0 | 26482.88 | 412 | 321.84
NHT-008075 - Reporting | 25-PC-37359 | Completed |  |  | 131022 | 94624.51 | 94624.51 | 10319.65 | 72237.55 | 0 | 82557.2 | 1186 | 1174.16
NHT-008076 - GIS & Mapping | 25-PC-37359 | Completed |  |  | 55348 | 39972.1 | 39972.1 | 4359.31 | 30515.2 | 0 | 34874.51 | 518 | 432.81
NHT-008077 - Site Recordation | 25-PC-37371 | In progress |  |  | 58762 | 31003.42 | 40036.8 | 5438.9 | 19530.59 | 0 | 24969.49 | 452 | 366.35
NHT-008080 - Survey | 25-PC-37371 | In progress |  |  | 115535 | 60957.57 | 78718.61 | 6420.67 | 23056.04 | 0 | 29476.71 | 687 | 416.23
NHT-008087 - Data Recovery Excavation | 25-PC-37371 | In progress |  |  | 118403 | 62471.09 | 80673.11 | 6561 | 23559.95 | 0 | 30120.95 | 659 | 434.24
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37371 | In progress |  |  | 0 | 0 | 0 | 0 | 1510.29 | 0 | 1510.29 | 0 | 26.5
NHT-008091 - Data Recovery Excavation | 25-PC-37392 | Completed |  |  | 6676 | 5717.3 | 5717.3 | 1009.41 | 9441.22 | 0 | 10450.63 | 57 | 140.71
NHT-008092 - Agency Consultation | 25-PC-37392 | In progress |  |  | 52524 | 44981.58 | 44981.58 | 3458.49 | 32347.88 | 0 | 35806.37 | 538 | 450.38
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37392 | In progress |  |  | 0 | 0 | 0 | 0 | 773.53 | 0 | 773.53 | 0 | 8.25
NHT-008103 - Draft Report | 25-PC-37461 | Completed |  |  | 62057 | 44891.89 | 44891.89 | 11263.38 | 47096.08 | 0 | 58359.46 | 421 | 920.33
NHT-008104 - Desktop Review | 25-PC-37461 | Completed |  |  | 21143 | 15294.99 | 15294.99 | 3837.51 | 16045.97 | 0 | 19883.48 | 139 | 283.27
NHT-008110 - Draft Report | 25-PC-37487 | Completed |  |  | 43400 | 25324.73 | 34525.12 | 3533.34 | 22070.54 | 0 | 25603.88 | 0 | 408.62
NHT-008111 - Lab Analysis | 25-PC-37509 | In progress |  |  | 458200 | 301449.78 | 301449.78 | 23357.26 | 217439.23 | 0 | 240796.49 | 5452 | 3527.4
NHT-008117 - Background Research | 25-PC-37522 | Completed |  |  | 2597 | 1886.42 | 1886.42 | 401.72 | 1920.95 | 0 | 2322.67 | 27 | 45.8
NHT-008119 - Prefield | 25-PC-37522 | Completed |  |  | 6221 | 4518.4 | 4518.4 | 555.47 | 2656.15 | 0 | 3211.62 | 58 | 59.3
NHT-008123 - Desktop Review | 25-PC-37522 | Completed |  |  | 6036 | 4384.81 | 4384.81 | 553.02 | 2644.43 | 0 | 3197.45 | 68 | 61.61
NHT-008130 - Lab Analysis | 25-PC-37522 | Completed |  |  | 2430 | 1765.26 | 1765.26 | 690.71 | 3302.85 | 0 | 3993.56 | 24 | 53.13
NHT-008131 - Testing | 25-PC-37522 | Completed |  |  | 4216 | 3062.71 | 3062.71 | 1133.48 | 5420.02 | 0 | 6553.5 | 50 | 120.66
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37522 | Completed |  |  | 0 | 0 | 0 | 0 | 220.6 | 0 | 220.6 | 0 | 5.5
NHT-008139 - Survey | 25-PC-37544 | Completed |  |  | 634610 | 405262.06 | 405262.06 | 22824.2 | 294178.52 | 0 | 317002.72 | 4290 | 4931.62
NHT-008141 - Draft Report | 25-PC-37544 | Completed |  |  | 374990 | 239468.5 | 239468.5 | 13486.77 | 173829.48 | 0 | 187316.25 | 2946 | 2974.01
NHT-008143 - Desktop Review | 25-PC-37612 | On hold |  |  | 7917 | 5580.16 | 5580.16 | 265.66 | 3821.35 | 0 | 4087.01 | 75 | 56.37
NHT-008149 - Fieldwork | 25-PC-37612 | On hold |  |  | 54384 | 38329.72 | 38329.72 | 1824.77 | 26248.55 | 0 | 28073.32 | 630 | 532.67
NHT-008151 - Survey | 25-PC-37612 | On hold |  |  | 36053 | 25410.34 | 25410.34 | 1209.71 | 17401.24 | 0 | 18610.95 | 399 | 292.46
NHT-008155 - Lab Analysis | 25-PC-37612 | On hold |  |  | 20671 | 14568.91 | 14568.91 | 693.58 | 9976.93 | 0 | 10670.51 | 246 | 185.52
NHT-008160 - Project Management | 25-PC-37612 | On hold |  |  | 15375 | 10835.99 | 10835.99 | 515.87 | 7420.59 | 0 | 7936.46 | 139 | 126.6
NHT-008164 - Survey | 25-PC-37630 | Completed |  |  | 528200 | 324693.9 | 365998.97 | 65660.22 | 410138.44 | 0 | 475798.66 | 4239 | 6994.37
NHT-008166 - Final Report | 25-PC-37675 | Completed |  |  | 23441 | 17348.88 | 17348.88 | 1434.5 | 12358.73 | 0 | 13793.23 | 140 | 201.19
NHT-008173 - Monitoring | 25-PC-37675 | Completed |  |  | 58768 | 43493.71 | 43493.71 | 3596.28 | 30983.37 | 0 | 34579.65 | 294 | 491.3
NHT-008180 - Lab Analysis | 25-PC-37675 | Completed |  |  | 47691 | 35296.4 | 35296.4 | 2918.49 | 25143.9 | 0 | 28062.39 | 306 | 511.84
NHT-008184 - GIS & Mapping | 25-PC-37732 | In progress |  |  | 13172 | 8280.16 | 8280.16 | 1469.63 | 5618.42 | 0 | 7088.05 | 87 | 89.38
NHT-008191 - Desktop Review | 25-PC-37732 | Completed |  |  | 4385 | 2756.37 | 2756.37 | 1572.43 | 6011.44 | 0 | 7583.87 | 23 | 90.87
NHT-008197 - Fieldwork | 25-PC-37732 | In progress |  |  | 3988 | 2507.08 | 2507.08 | 854.37 | 3266.27 | 0 | 4120.64 | 24 | 49.06
NHT-008203 - Background Research | 25-PC-37732 | In progress |  |  | 24990 | 15708.76 | 15708.76 | 2073.71 | 7927.83 | 0 | 10001.54 | 166 | 124.66
NHT-008210 - Prefield | 25-PC-37732 | In progress |  |  | 26365 | 16572.57 | 16572.57 | 2370.82 | 9063.7 | 0 | 11434.52 | 136 | 136.76
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37732 | In progress |  |  | 0 | 0 | 0 | 0 | 65.86 | 0 | 65.86 | 0 | 1
NHT-008215 - GIS & Mapping | 25-PC-37786 | Completed |  |  | 72200 | 44893.96 | 44893.96 | 10674.64 | 46693.75 | 0 | 57368.39 | 432 | 505.39
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37786 | Completed |  |  | 0 | 0 | 0 | 0 | 22.13 | 0 | 22.13 | 0 | 0.5
NHT-008223 - Fieldwork | 25-PC-37841 | On hold |  |  | 135197 | 63818.21 | 80059.94 | 2944.2 | 16683.78 | 0 | 19627.98 | 719 | 261.14
NHT-008224 - Desktop Review | 25-PC-37841 | On hold |  |  | 19466 | 9188.75 | 11527.28 | 423.91 | 2402.18 | 0 | 2826.09 | 97 | 41.62
NHT-008226 - Testing | 25-PC-37841 | On hold |  |  | 49104 | 23178.77 | 29077.76 | 1069.33 | 6059.55 | 0 | 7128.88 | 242 | 115.74
NHT-008230 - GIS & Mapping | 25-PC-37841 | On hold |  |  | 40133 | 18944.22 | 23765.53 | 873.98 | 4952.53 | 0 | 5826.51 | 235 | 84.88
NHT-008233 - Reporting | 25-PC-37881 | In progress |  |  | 3051 | 2325.38 | 2325.38 | 222.84 | 2338.56 | 0 | 2561.4 | 47 | 46.75
NHT-008234 - Prefield | 25-PC-37881 | Completed |  |  | 4849 | 3695.21 | 3695.21 | 353.91 | 3713.99 | 0 | 4067.9 | 68 | 76.03
NHT-008238 - Monitoring | 25-PC-37903 | Completed |  |  | 195600 | 128411.4 | 128411.4 | 20366.05 | 146568.77 | 0 | 166934.82 | 2171 | 2581.33
NHT-008242 - Prefield | 25-PC-37920 | In progress |  |  | 138600 | 92806.56 | 92806.56 | 5320.64 | 38756.06 | 0 | 44076.7 | 2102 | 928.45
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37920 | In progress |  |  | 0 | 0 | 0 | 0 | 634.58 | 0 | 634.58 | 0 | 15
NHT-008250 - Draft Report | 25-PC-37975 | Completed |  |  | 22390 | 16147.4 | 16147.4 | 2380.69 | 14135.25 | 0 | 16515.94 | 150 | 177.08
NHT-008254 - Testing | 25-PC-37975 | In progress |  |  | 44919 | 32395.86 | 32395.86 | 3284.81 | 19503.41 | 0 | 22788.22 | 320 | 285.35
NHT-008255 - Final Report | 25-PC-37975 | In progress |  |  | 80791 | 58266.46 | 58266.46 | 5747.15 | 34123.34 | 0 | 39870.49 | 610 | 522.51
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-37975 | In progress |  |  | 0 | 0 | 0 | 0 | 79.88 | 0 | 79.88 | 0 | 2
NHT-008263 - Reporting | 25-PC-37979 | Completed |  |  | 60737 | 40012.63 | 45551.21 | 10470.44 | 42950.16 | 0 | 53420.6 | 396 | 920.24
NHT-008269 - Final Report | 25-PC-37979 | Completed |  |  | 21783 | 14350.4 | 16336.8 | 3755.19 | 15403.94 | 0 | 19159.13 | 157 | 325.44
NHT-008276 - Curation | 25-PC-37979 | Completed |  |  | 24370 | 16054.58 | 18276.87 | 4201.14 | 17233.23 | 0 | 21434.37 | 233 | 379.42
NHT-008282 - Lab Analysis | 25-PC-37979 | Completed |  |  | 36251 | 23882.01 | 27187.78 | 6249.4 | 25635.31 | 0 | 31884.71 | 262 | 546.67
NHT-008289 - Data Recovery Excavation | 25-PC-37979 | Completed |  |  | 87159 | 57419.42 | 65367.47 | 15025.41 | 61634.88 | 0 | 76660.29 | 587 | 1479.56
NHT-008295 - Draft Report | 25-PC-37994 | On hold |  |  | 70372 | 46965.99 | 46965.99 | 1058.66 | 12513.84 | 0 | 13572.5 | 0 | 225.01
NHT-008299 - Data Recovery Excavation | 25-PC-37994 | On hold |  |  | 158891 | 106044.32 | 106044.32 | 2390.33 | 28254.95 | 0 | 30645.28 | 0 | 529.42
NHT-008302 - Testing | 25-PC-37994 | On hold |  |  | 97037 | 64762.31 | 64762.31 | 1459.8 | 17255.58 | 0 | 18715.38 | 0 | 409.61
NHT-008309 - Draft Report | 25-PC-38006 | In progress |  |  | 18835 | 12724.83 | 12724.83 | 1210.31 | 6385.1 | 0 | 7595.41 | 238 | 135.65
NHT-008313 - Data Recovery Excavation | 25-PC-38006 | In progress |  |  | 27419 | 18523.94 | 18523.94 | 1510.71 | 7969.93 | 0 | 9480.64 | 394 | 184.78
NHT-008320 - Survey | 25-PC-38006 | In progress |  |  | 65746 | 44418.43 | 44418.43 | 3004.64 | 15851.28 | 0 | 18855.92 | 873 | 337.93
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38006 | In progress |  |  | 0 | 0 | 0 | 0 | 537.19 | 0 | 537.19 | 0 | 12.25
NHT-008328 - Testing | 25-PC-38036 | Completed |  |  | 8067 | 6900.93 | 6900.93 | 619.01 | 8352.2 | 0 | 8971.21 | 103 | 180.12
NHT-008329 - Project Management | 25-PC-38036 | Completed |  |  | 3641 | 3114.23 | 3114.23 | 279.35 | 3769.15 | 0 | 4048.5 | 47 | 77.01
NHT-008336 - Lab Analysis | 25-PC-38036 | Completed |  |  | 4335 | 3707.84 | 3707.84 | 332.59 | 4487.6 | 0 | 4820.19 | 54 | 98.87
NHT-008340 - Data Recovery Excavation | 25-PC-38036 | Completed |  |  | 11257 | 9629.42 | 9629.42 | 863.76 | 11654.49 | 0 | 12518.25 | 145 | 283.87
NHT-008345 - Survey | 25-PC-38042 | In progress |  |  | 2353 | 1847.46 | 1847.46 | 148.94 | 1370.85 | 0 | 1519.79 | 17 | 17.45
NHT-008351 - Project Management | 25-PC-38042 | In progress |  |  | 4293 | 3370.92 | 3370.92 | 282.02 | 2595.78 | 0 | 2877.8 | 23 | 34.45
NHT-008356 - Monitoring | 25-PC-38042 | In progress |  |  | 5044 | 3960.68 | 3960.68 | 332.23 | 3057.86 | 0 | 3390.09 | 29 | 38.15
NHT-008358 - Draft Report | 25-PC-38042 | In progress |  |  | 12610 | 9903.73 | 9903.73 | 787.17 | 7245.18 | 0 | 8032.35 | 67 | 85.58
NHT-008359 - Agency Consultation | 25-PC-38070 | In progress |  |  | 23038 | 20273.54 | 20273.54 | 1071.87 | 11538.35 | 0 | 12610.22 | 0 | 247.25
NHT-008364 - Survey | 25-PC-38070 | In progress |  |  | 88933 | 78261.33 | 78261.33 | 4137.69 | 44541.12 | 0 | 48678.81 | 0 | 945.33
NHT-008369 - Background Research | 25-PC-38070 | In progress |  |  | 20829 | 18329.13 | 18329.13 | 969.07 | 10431.72 | 0 | 11400.79 | 0 | 243.04
NHT-008376 - Reporting | 25-PC-38107 | In progress |  |  | 134653 | 88845.51 | 119909.22 | 4784.72 | 28031.51 | 0 | 32816.23 | 0 | 717.69
NHT-008380 - Monitoring | 25-PC-38107 | In progress |  |  | 99947 | 65946.49 | 89003.86 | 5212.06 | 30535.07 | 0 | 35747.13 | 0 | 729.26
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38107 | In progress |  |  | 0 | 0 | 0 | 0 | 858.71 | 0 | 858.71 | 0 | 21.5
NHT-008389 - Testing | 25-PC-38180 | In progress |  |  | 4487 | 3008.14 | 3008.14 | 327.67 | 2152.64 | 0 | 2480.31 | 58 | 49.2
NHT-008392 - Desktop Review | 25-PC-38180 | In progress |  |  | 9064 | 6076.19 | 6076.19 | 546.01 | 3587.11 | 0 | 4133.12 | 112 | 83.09
NHT-008397 - Site Recordation | 25-PC-38180 | In progress |  |  | 11749 | 7876.79 | 7876.79 | 951.34 | 6249.97 | 0 | 7201.31 | 175 | 140.56
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38180 | In progress |  |  | 0 | 0 | 0 | 0 | 116.7 | 0 | 116.7 | 0 | 2.5
NHT-008401 - Final Report | 25-PC-38196 | In progress |  |  | 577294 | 356825.39 | 356825.39 | 14788.88 | 196416.01 | 0 | 211204.89 | 4663 | 4754.77
NHT-008405 - Background Research | 25-PC-38196 | In progress |  |  | 583406 | 360603.28 | 360603.28 | 14989.12 | 199075.45 | 0 | 214064.57 | 5732 | 5853.77
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38196 | In progress |  |  | 0 | 0 | 0 | 0 | 130.49 | 0 | 130.49 | 0 | 2.75
NHT-008413 - Reporting | 25-PC-38282 | In progress |  |  | 704368 | 371164.82 | 462687.7 | 31694.67 | 243911.12 | 0 | 275605.79 | 9433 | 5022.99
NHT-008418 - Project Management | 25-PC-38282 | In progress |  |  | 230057 | 121228.1 | 151120.88 | 10351.96 | 79665.1 | 0 | 90017.06 | 2990 | 1785.46
NHT-008420 - Prefield | 25-PC-38282 | In progress |  |  | 399675 | 210607.74 | 262540 | 17984.3 | 138400.96 | 0 | 156385.26 | 4906 | 2791.95
NHT-008423 - Prefield | 25-PC-38296 | In progress |  |  | 117425 | 75457.67 | 75457.67 | 4368.36 | 19214.93 | 0 | 23583.29 | 1014 | 445.69
NHT-008428 - Project Management | 25-PC-38296 | In progress |  |  | 17810 | 11444.45 | 11444.45 | 1963.56 | 8637.04 | 0 | 10600.6 | 143 | 205.16
NHT-008432 - Testing | 25-PC-38296 | In progress |  |  | 37765 | 24267.68 | 24267.68 | 3428.2 | 15079.46 | 0 | 18507.66 | 325 | 360.68
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38296 | In progress |  |  | 0 | 0 | 0 | 0 | 1231.77 | 0 | 1231.77 | 0 | 29.25
NHT-008445 - Lab Analysis | 25-PC-38332 | In progress |  |  | 532571 | 403785.95 | 446508.33 | 49093.34 | 301474.11 | 0 | 350567.45 | 9084 | 6942.87
NHT-008450 - Draft Report | 25-PC-38332 | In progress |  |  | 93754 | 71082.92 | 78603.82 | 8561.3 | 52573.52 | 0 | 61134.82 | 1498 | 1101.92
NHT-008457 - Monitoring | 25-PC-38332 | In progress |  |  | 273475 | 207344.48 | 229282.47 | 25270.61 | 155182.65 | 0 | 180453.26 | 3379 | 3561.87
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38332 | In progress |  |  | 0 | 0 | 0 | 0 | 167.65 | 0 | 167.65 | 0 | 3.5
NHT-008466 - GIS & Mapping | 25-PC-38333 | In progress |  |  | 39842 | 23894.11 | 26179.62 | 1331.61 | 17691.34 | 0 | 19022.95 | 416 | 415.11
NHT-008472 - Survey | 25-PC-38333 | In progress |  |  | 38458 | 23064.62 | 25270.78 | 1283.65 | 17054.27 | 0 | 18337.92 | 310 | 357.89
NHT-008473 - Site Recordation | 25-PC-38352 | In progress |  |  | 136400 | 86736.76 | 86736.76 | 10080.21 | 52921.09 | 0 | 63001.3 | 1342 | 1037.92
NHT-008476 - Data Recovery Excavation | 25-PC-38461 | Completed |  |  | 60641 | 46451.12 | 46451.12 | 5447.4 | 39947.61 | 0 | 45395.01 | 0 | 761.42
NHT-008479 - Reporting | 25-PC-38461 | Completed |  |  | 36017 | 27589.02 | 27589.02 | 3235.41 | 23726.34 | 0 | 26961.75 | 0 | 465.93
NHT-008485 - Project Management | 25-PC-38461 | Completed |  |  | 21387 | 16382.11 | 16382.11 | 1921.16 | 14088.49 | 0 | 16009.65 | 0 | 269.05
NHT-008491 - Survey | 25-PC-38461 | Completed |  |  | 69355 | 53126.15 | 53126.15 | 6230.19 | 45688.08 | 0 | 51918.27 | 0 | 793.89
NHT-008493 - Prefield | 25-PC-38540 | In progress |  |  | 116253 | 83771.59 | 83771.59 | 7417.02 | 72170.86 | 0 | 79587.88 | 1180 | 1323.75
NHT-008496 - Agency Consultation | 25-PC-38540 | In progress |  |  | 258306 | 186135.66 | 186135.66 | 10205.32 | 99302.22 | 0 | 109507.54 | 2812 | 1782.31
NHT-008499 - Data Recovery Excavation | 25-PC-38540 | Completed |  |  | 121841 | 87798.59 | 87798.59 | 11043.01 | 107453.18 | 0 | 118496.19 | 1304 | 1951.04
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38540 | In progress |  |  | 0 | 0 | 0 | 0 | 3988.28 | 0 | 3988.28 | 0 | 68.75
NHT-008513 - Monitoring | 25-PC-38563 | In progress |  |  | 45895 | 35825.35 | 35825.35 | 3811.94 | 20783.15 | 0 | 24595.09 | 819 | 548.6
NHT-008516 - Desktop Review | 25-PC-38563 | In progress |  |  | 18859 | 14721.42 | 14721.42 | 2661.83 | 14512.61 | 0 | 17174.44 | 299 | 354.45
NHT-008521 - GIS & Mapping | 25-PC-38563 | Completed |  |  | 22763 | 17768.86 | 17768.86 | 3725.53 | 20312.04 | 0 | 24037.57 | 385 | 456.43
NHT-008528 - Curation | 25-PC-38563 | In progress |  |  | 60550 | 47265.2 | 47265.2 | 4958.68 | 27035.28 | 0 | 31993.96 | 1051 | 679.46
NHT-008533 - Testing | 25-PC-38563 | In progress |  |  | 28333 | 22117.01 | 22117.01 | 3389.51 | 18480.04 | 0 | 21869.55 | 410 | 492.41
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38563 | In progress |  |  | 0 | 0 | 0 | 0 | 767.64 | 0 | 767.64 | 0 | 18.25
NHT-008538 - Lab Analysis | 25-PC-38596 | In progress |  |  | 38043 | 31720.08 | 31720.08 | 2946.27 | 13421.9 | 0 | 16368.17 | 0 | 245.49
NHT-008542 - Draft Report | 25-PC-38596 | In progress |  |  | 36538 | 30465.05 | 30465.05 | 2829.7 | 12890.85 | 0 | 15720.55 | 0 | 255.8
NHT-008548 - GIS & Mapping | 25-PC-38596 | In progress |  |  | 19026 | 15863.84 | 15863.84 | 1473.49 | 6712.56 | 0 | 8186.05 | 0 | 115.63
NHT-008553 - Final Report | 25-PC-38596 | In progress |  |  | 17371 | 14484.16 | 14484.16 | 1345.34 | 6128.77 | 0 | 7474.11 | 0 | 128.68
NHT-008557 - Survey | 25-PC-38596 | In progress |  |  | 67022 | 55883.27 | 55883.27 | 5190.63 | 23646.22 | 0 | 28836.85 | 0 | 568.08
NHT-008562 - Site Recordation | 25-PC-38606 | In progress |  |  | 11495 | 7696.49 | 8857.54 | 1067.48 | 4114.47 | 0 | 5181.95 | 112 | 86.22
NHT-008567 - Final Report | 25-PC-38606 | In progress |  |  | 4927 | 3299.24 | 3796.95 | 457.59 | 1763.74 | 0 | 2221.33 | 49 | 35.57
NHT-008568 - Testing | 25-PC-38606 | In progress |  |  | 18378 | 12305.39 | 14161.71 | 1706.73 | 6578.35 | 0 | 8285.08 | 218 | 125.4
NHT-008574 - Desktop Review | 25-PC-38659 | Completed |  |  | 3059900 | 2017698.06 | 2017698.06 | 295853.1 | 1497195.98 | 0 | 1793049.08 | 0 | 26327.98
NHT-008576 - Curation | 25-PC-38701 | In progress |  |  | 75852 | 47885.41 | 47885.41 | 8314.9 | 30592.64 | 0 | 38907.54 | 640 | 619.41
NHT-008578 - Data Recovery Excavation | 25-PC-38701 | In progress |  |  | 80548 | 50849.91 | 50849.91 | 6671.2 | 24545.05 | 0 | 31216.25 | 777 | 492.64
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38701 | In progress |  |  | 0 | 0 | 0 | 0 | 900.4 | 0 | 900.4 | 0 | 20.75
NHT-008582 - Monitoring | 25-PC-38754 | In progress |  |  | 18686 | 12175.56 | 12175.56 | 2873.45 | 17407.37 | 0 | 20280.82 | 245 | 337.27
NHT-008586 - Reporting | 25-PC-38754 | Completed |  |  | 7878 | 5133.21 | 5133.21 | 1032.68 | 6255.97 | 0 | 7288.65 | 104 | 113.95
NHT-008589 - Fieldwork | 25-PC-38754 | Completed |  |  | 22958 | 14959.81 | 14959.81 | 2813.57 | 17044.58 | 0 | 19858.15 | 244 | 349.42
NHT-008596 - Desktop Review | 25-PC-38754 | In progress |  |  | 14378 | 9368.66 | 9368.66 | 1788.15 | 10832.58 | 0 | 12620.73 | 147 | 218.87
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38754 | In progress |  |  | 0 | 0 | 0 | 0 | 722.04 | 0 | 722.04 | 0 | 13
NHT-008602 - Data Recovery Excavation | 25-PC-38835 | Completed |  |  | 10400 | 5866.64 | 5866.64 | 3099.01 | 15188.03 | 0 | 18287.04 | 62 | 298.74
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-38835 | Completed |  |  | 0 | 0 | 0 | 0 | -269.51 | 0 | -269.51 | 0 | -3.25
NHT-008614 - Draft Report | 25-PC-38879 | In progress |  |  | 17588 | 10333.15 | 10333.15 | 1378.81 | 8331.13 | 0 | 9709.94 | 110 | 193.94
NHT-008619 - Prefield | 25-PC-38879 | In progress |  |  | 51770 | 30414.96 | 30414.96 | 3031.8 | 18318.88 | 0 | 21350.68 | 301 | 404.62
NHT-008622 - Lab Analysis | 25-PC-38879 | In progress |  |  | 50342 | 29575.64 | 29575.64 | 2971.15 | 17952.46 | 0 | 20923.61 | 301 | 511.15
NHT-008625 - Lab Analysis | 25-PC-38970 | Completed |  |  | 29692 | 21746.69 | 21746.69 | 1956.21 | 22194.54 | 0 | 24150.75 | 441 | 422.63
NHT-008629 - Agency Consultation | 25-PC-38970 | Completed |  |  | 17249 | 12633.4 | 12633.4 | 1136.43 | 12893.56 | 0 | 14029.99 | 237 | 258.76
NHT-008635 - GIS & Mapping | 25-PC-38970 | Completed |  |  | 43037 | 31520.17 | 31520.17 | 2835.38 | 32169.28 | 0 | 35004.66 | 581 | 587.08
NHT-008638 - Draft Report | 25-PC-38970 | Completed |  |  | 70122 | 51356.98 | 51356.98 | 4619.78 | 52414.6 | 0 | 57034.38 | 1029 | 1098.76
NHT-008645 - GIS & Mapping | 25-PC-39035 | In progress |  |  | 40343 | 28885.27 | 28885.27 | 5438.82 | 22209.47 | 0 | 27648.29 | 397 | 476.77
NHT-008652 - Agency Consultation | 25-PC-39035 | In progress |  |  | 42970 | 30766.58 | 30766.58 | 5474.42 | 22354.83 | 0 | 27829.25 | 369 | 484.67
NHT-008656 - Monitoring | 25-PC-39035 | In progress |  |  | 42079 | 30128.62 | 30128.62 | 5934.71 | 24234.42 | 0 | 30169.13 | 367 | 499.36
NHT-008662 - Curation | 25-PC-39035 | Completed |  |  | 11326 | 8109.25 | 8109.25 | 2627.06 | 10727.63 | 0 | 13354.69 | 85 | 231.09
NHT-008669 - Data Recovery Excavation | 25-PC-39035 | In progress |  |  | 107282 | 76814.28 | 76814.28 | 10916.33 | 44576.88 | 0 | 55493.21 | 760 | 928.22
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39035 | In progress |  |  | 0 | 0 | 0 | 0 | 2973.49 | 0 | 2973.49 | 0 | 64.75
NHT-008674 - Project Management | 25-PC-39055 | Completed |  |  | 128700 | 84460.6 | 90984.64 | 15728.21 | 93495.44 | 0 | 109223.65 | 0 | 2039.45
NHT-008679 - GIS & Mapping | 25-PC-39085 | Completed |  |  | 120700 | 69209.38 | 69209.38 | 8243.62 | 60050.71 | 0 | 68294.33 | 1216 | 1141.9
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39085 | In progress |  |  | 0 | 0 | 0 | 0 | 402.51 | 0 | 402.51 | 0 | 8.5
NHT-008689 - Agency Consultation | 25-PC-39093 | In progress |  |  | 49539 | 36460.71 | 36460.71 | 2469.79 | 14914.84 | 0 | 17384.63 | 0 | 377
NHT-008695 - Testing | 25-PC-39093 | In progress |  |  | 50561 | 37212.89 | 37212.89 | 2565.06 | 15490.16 | 0 | 18055.22 | 0 | 394.26
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39093 | In progress |  |  | 0 | 0 | 0 | 0 | 782.06 | 0 | 782.06 | 0 | 18.75
NHT-008708 - Prefield | 25-PC-39118 | In progress |  |  | 90300 | 58198.35 | 58198.35 | 7274.12 | 36236.97 | 0 | 43511.09 | 858 | 865.03
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39118 | In progress |  |  | 0 | 0 | 0 | 0 | 308.89 | 0 | 308.89 | 0 | 7.75
NHT-008715 - GIS & Mapping | 25-PC-39187 | Completed |  |  | 10003 | 6931.21 | 6931.21 | 575.7 | 2830.82 | 0 | 3406.52 | 57 | 57.54
NHT-008720 - Monitoring | 25-PC-39187 | Completed |  |  | 15239 | 10558.82 | 10558.82 | 877.01 | 4312.4 | 0 | 5189.41 | 76 | 80.92
NHT-008721 - Agency Consultation | 25-PC-39187 | Completed |  |  | 2858 | 1980.46 | 1980.46 | 164.5 | 808.85 | 0 | 973.35 | 17 | 15.57
NHT-008722 - Agency Consultation | 25-PC-39222 | Completed |  |  | 3993 | 3201.82 | 3201.82 | 505.55 | 2399.89 | 0 | 2905.44 | 57 | 48.54
NHT-008723 - GIS & Mapping | 25-PC-39222 | Completed |  |  | 6437 | 5161.4 | 5161.4 | 814.95 | 3868.66 | 0 | 4683.61 | 91 | 70.78
NHT-008726 - Prefield | 25-PC-39222 | Completed |  |  | 3730 | 2990.71 | 2990.71 | 472.21 | 2241.65 | 0 | 2713.86 | 50 | 45.93
NHT-008730 - Fieldwork | 25-PC-39222 | Completed |  |  | 12840 | 10294.67 | 10294.67 | 1625.45 | 7716.25 | 0 | 9341.7 | 161 | 131.66
NHT-008734 - Lab Analysis | 25-PC-39318 | In progress |  |  | 64649 | 43276.33 | 43276.33 | 1845.31 | 28313.26 | 0 | 30158.57 | 473 | 449.76
NHT-008740 - Monitoring | 25-PC-39318 | In progress |  |  | 39651 | 26542.09 | 26542.09 | 1059.89 | 16262.28 | 0 | 17322.17 | 337 | 288.08
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39318 | In progress |  |  | 0 | 0 | 0 | 0 | 145.5 | 0 | 145.5 | 0 | 3
NHT-008752 - Site Recordation | 25-PC-39358 | Completed |  |  | 6043 | 4284.65 | 4284.65 | 569.41 | 7683.15 | 0 | 8252.56 | 80 | 145.28
NHT-008755 - Fieldwork | 25-PC-39358 | Completed |  |  | 14999 | 10634.01 | 10634.01 | 572.84 | 7729.34 | 0 | 8302.18 | 128 | 143.15
NHT-008756 - Background Research | 25-PC-39358 | Completed |  |  | 9398 | 6663.44 | 6663.44 | 436.33 | 5887.55 | 0 | 6323.88 | 97 | 102.07
NHT-008757 - Draft Report | 25-PC-39358 | Completed |  |  | 20595 | 14601.86 | 14601.86 | 544.52 | 7347.33 | 0 | 7891.85 | 182 | 163
NHT-008764 - Agency Consultation | 25-PC-39358 | Completed |  |  | 4865 | 3449.14 | 3449.14 | 490.07 | 6612.69 | 0 | 7102.76 | 42 | 121.4
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39358 | Completed |  |  | 0 | 0 | 0 | 0 | 555.69 | 0 | 555.69 | 0 | 12.75
NHT-008777 - Final Report | 25-PC-39398 | Completed |  |  | 15400 | 9907.07 | 12090.14 | 547.16 | 7269.43 | 0 | 7816.59 | 217 | 140.29
NHT-008784 - Project Management | 25-PC-39398 | Completed |  |  | 20105 | 12933.4 | 15783.34 | 714.3 | 9490.04 | 0 | 10204.34 | 327 | 168.73
NHT-008790 - Desktop Review | 25-PC-39398 | Completed |  |  | 11282 | 7257.83 | 8857.13 | 400.85 | 5325.52 | 0 | 5726.37 | 131 | 103.04
NHT-008793 - Monitoring | 25-PC-39398 | Completed |  |  | 46141 | 29682.83 | 36223.59 | 1639.36 | 21780.13 | 0 | 23419.49 | 613 | 380.09
NHT-008797 - Prefield | 25-PC-39398 | Completed |  |  | 10372 | 6672.17 | 8142.41 | 368.5 | 4895.78 | 0 | 5264.28 | 140 | 93.05
NHT-008803 - Final Report | 25-PC-39422 | In progress |  |  | 13803 | 10925.45 | 10925.45 | 365.14 | 2480.94 | 0 | 2846.08 | 145 | 48
NHT-008808 - Project Management | 25-PC-39422 | In progress |  |  | 43097 | 34110.9 | 34110.9 | 1150.43 | 7816.64 | 0 | 8967.07 | 483 | 161.09
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39422 | In progress |  |  | 0 | 0 | 0 | 0 | -154.89 | 0 | -154.89 | 0 | -3.25
NHT-008819 - Prefield | 25-PC-39424 | In progress |  |  | 19700 | 13882.59 | 13882.59 | 2830.6 | 13572.49 | 0 | 16403.09 | 213 | 235.46
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39424 | In progress |  |  | 0 | 0 | 0 | 0 | -135.25 | 0 | -135.25 | 0 | -2.25
NHT-008829 - Curation | 25-PC-39458 | In progress |  |  | 63010 | 44377.9 | 44377.9 | 1433.62 | 20468.2 | 0 | 21901.82 | 756 | 337.65
NHT-008830 - Survey | 25-PC-39458 | In progress |  |  | 135336 | 95317.77 | 95317.77 | 3183.39 | 45450.42 | 0 | 48633.81 | 2019 | 669.79
NHT-008833 - Desktop Review | 25-PC-39458 | In progress |  |  | 52367 | 36881.77 | 36881.77 | 2434.58 | 34759.25 | 0 | 37193.83 | 699 | 549.41
NHT-008836 - Draft Report | 25-PC-39458 | In progress |  |  | 94287 | 66406.06 | 66406.06 | 2281.52 | 32573.94 | 0 | 34855.46 | 1239 | 460.79
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39458 | In progress |  |  | 0 | 0 | 0 | 0 | 1001.38 | 0 | 1001.38 | 0 | 16
NHT-008850 - Site Recordation | 25-PC-39489 | Completed |  |  | 122797 | 91336.22 | 91336.22 | 7325.55 | 76876.16 | 0 | 84201.71 | 0 | 1477.71
NHT-008855 - Reporting | 25-PC-39489 | Completed |  |  | 167529 | 124608.02 | 124608.02 | 9994.08 | 104880.45 | 0 | 114874.53 | 0 | 1734.24
NHT-008862 - Testing | 25-PC-39489 | Completed |  |  | 127731 | 95006.32 | 95006.32 | 7619.9 | 79965.22 | 0 | 87585.12 | 0 | 1655.77
NHT-008864 - Agency Consultation | 25-PC-39489 | Completed |  |  | 41943 | 31197.44 | 31197.44 | 2502.17 | 26258.36 | 0 | 28760.53 | 0 | 502.54
NHT-008868 - Lab Analysis | 25-PC-39554 | In progress |  |  | 86700 | 63594.45 | 63594.45 | 10096.63 | 45160.57 | 0 | 55257.2 | 889 | 964.62
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39554 | In progress |  |  | 0 | 0 | 0 | 0 | 218.82 | 0 | 218.82 | 0 | 4.75
NHT-008876 - Curation | 25-PC-39569 | Completed |  |  | 35274 | 22215.85 | 22215.85 | 2193.6 | 17392.1 | 0 | 19585.7 | 384 | 330.41
NHT-008878 - Background Research | 25-PC-39569 | Completed |  |  | 35875 | 22594.22 | 22594.22 | 2230.96 | 17688.32 | 0 | 19919.28 | 427 | 385.25
NHT-008881 - Draft Report | 25-PC-39569 | Completed |  |  | 86049 | 54193.86 | 54193.86 | 5351.12 | 42426.71 | 0 | 47777.83 | 835 | 924.69
NHT-008885 - Site Recordation | 25-PC-39569 | Completed |  |  | 147102 | 92644.21 | 92644.21 | 9147.71 | 72528.31 | 0 | 81676.02 | 1408 | 1417.49
NHT-008892 - Fieldwork | 25-PC-39661 | Completed |  |  | 1468900 | 1021032.39 | 1021032.39 | 89672.57 | 825353.7 | 0 | 915026.27 | 0 | 15175.87
NHT-008899 - Monitoring | 25-PC-39765 | Completed |  |  | 14456 | 10360.35 | 10360.35 | 5071.08 | 20653.27 | 0 | 25724.35 | 137 | 343.53
NHT-008901 - Background Research | 25-PC-39765 | Completed |  |  | 10866 | 7787.87 | 7787.87 | 3800.57 | 15478.78 | 0 | 19279.35 | 124 | 285.17
NHT-008902 - Prefield | 25-PC-39765 | In progress |  |  | 15330 | 10986.99 | 10986.99 | 2692.7 | 10966.69 | 0 | 13659.39 | 166 | 214.39
NHT-008906 - Draft Report | 25-PC-39765 | Completed |  |  | 10348 | 7416.49 | 7416.49 | 3099.07 | 12621.76 | 0 | 15720.83 | 95 | 204.26
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39765 | In progress |  |  | 0 | 0 | 0 | 0 | 813.12 | 0 | 813.12 | 0 | 14
NHT-008915 - Fieldwork | 25-PC-39808 | In progress |  |  | 40821 | 19908.79 | 25795.11 | 797.93 | 10194.45 | 0 | 10992.38 | 407 | 216.23
NHT-008921 - Final Report | 25-PC-39808 | In progress |  |  | 30036 | 14648.84 | 18979.98 | 742.33 | 9484.13 | 0 | 10226.46 | 363 | 202.8
NHT-008925 - Desktop Review | 25-PC-39808 | In progress |  |  | 12695 | 6191.29 | 8021.83 | 695.26 | 8882.68 | 0 | 9577.94 | 126 | 177.28
NHT-008932 - GIS & Mapping | 25-PC-39808 | In progress |  |  | 36628 | 17863.73 | 23145.4 | 730.47 | 9332.6 | 0 | 10063.07 | 382 | 203.67
NHT-008936 - Background Research | 25-PC-39808 | In progress |  |  | 20420 | 9959.25 | 12903.84 | 564.25 | 7208.89 | 0 | 7773.14 | 185 | 159.65
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39808 | In progress |  |  | 0 | 0 | 0 | 0 | 398.19 | 0 | 398.19 | 0 | 9
NHT-008941 - Draft Report | 25-PC-39873 | In progress |  |  | 7351 | 5552.77 | 5552.77 | 614.78 | 2506.3 | 0 | 3121.08 | 0 | 44.26
NHT-008948 - Prefield | 25-PC-39873 | In progress |  |  | 9959 | 7522.87 | 7522.87 | 572.62 | 2334.42 | 0 | 2907.04 | 0 | 38.65
NHT-008953 - Reporting | 25-PC-39873 | In progress |  |  | 13573 | 10253.29 | 10253.29 | 1449.43 | 5908.94 | 0 | 7358.37 | 0 | 102.67
NHT-008958 - Final Report | 25-PC-39873 | In progress |  |  | 44112 | 33322.04 | 33322.04 | 2242.24 | 9140.96 | 0 | 11383.2 | 0 | 160.95
NHT-008962 - Site Recordation | 25-PC-39873 | In progress |  |  | 18305 | 13827.85 | 13827.85 | 1522.32 | 6206.08 | 0 | 7728.4 | 0 | 112.03
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39873 | In progress |  |  | 0 | 0 | 0 | 0 | 1017.05 | 0 | 1017.05 | 0 | 15.75
NHT-008973 - Reporting | 25-PC-39885 | In progress |  |  | 75783 | 47849.54 | 47849.54 | 4755.98 | 24765.93 | 0 | 29521.91 | 562 | 359.48
NHT-008977 - GIS & Mapping | 25-PC-39885 | In progress |  |  | 9817 | 6198.3 | 6198.3 | 836.5 | 4355.93 | 0 | 5192.43 | 58 | 62.92
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39885 | In progress |  |  | 0 | 0 | 0 | 0 | 238.66 | 0 | 238.66 | 0 | 3.5
NHT-008982 - Data Recovery Excavation | 25-PC-39896 | In progress |  |  | 190864 | 119630.8 | 141080.29 | 10946.28 | 93304.71 | 0 | 104250.99 | 1458 | 1915.43
NHT-008986 - Site Recordation | 25-PC-39896 | In progress |  |  | 269720 | 169056.64 | 199368.05 | 15579.55 | 132798.08 | 0 | 148377.63 | 2571 | 2470.31
NHT-008990 - Desktop Review | 25-PC-39896 | In progress |  |  | 270316 | 169430.96 | 199809.49 | 15520.52 | 132294.94 | 0 | 147815.46 | 2271 | 2321.1
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-39896 | In progress |  |  | 0 | 0 | 0 | 0 | -2.6 | 0 | -2.6 | 0 | -0.25
NHT-008997 - Desktop Review | 25-PC-39951 | Completed |  |  | 18676 | 13981.22 | 13981.22 | 1178.79 | 9941.85 | 0 | 11120.64 | 255 | 195.17
NHT-008998 - Background Research | 25-PC-39951 | Completed |  |  | 15379 | 11512.4 | 11512.4 | 970.63 | 8186.3 | 0 | 9156.93 | 219 | 167.4
NHT-009002 - Project Management | 25-PC-39951 | Completed |  |  | 31281 | 23417.13 | 23417.13 | 1974.35 | 16651.58 | 0 | 18625.93 | 421 | 338.87
NHT-009005 - Prefield | 25-PC-39951 | Completed |  |  | 21864 | 16367.17 | 16367.17 | 1379.95 | 11638.46 | 0 | 13018.41 | 246 | 226.37
NHT-009006 - Project Management | 25-PC-40020 | On hold |  |  | 26765 | 13566.39 | 18447.94 | 1205.81 | 4376.63 | 0 | 5582.44 | 307 | 80.51
NHT-009007 - Prefield | 25-PC-40020 | On hold |  |  | 19397 | 9831.98 | 13369.79 | 873.89 | 3171.88 | 0 | 4045.77 | 247 | 70.99
NHT-009010 - Survey | 25-PC-40020 | On hold |  |  | 86091 | 43637.62 | 59339.58 | 3878.58 | 14077.86 | 0 | 17956.44 | 1222 | 264.84
NHT-009017 - Agency Consultation | 25-PC-40020 | On hold |  |  | 12769 | 6472.04 | 8800.85 | 575.25 | 2087.93 | 0 | 2663.18 | 195 | 45.13
NHT-009020 - Lab Analysis | 25-PC-40020 | On hold |  |  | 41178 | 20871.97 | 28382.26 | 1855.14 | 6733.47 | 0 | 8588.61 | 474 | 130.83
NHT-009021 - Monitoring | 25-PC-40099 | Completed |  |  | 665100 | 389294.01 | 460201.14 | 41280.04 | 556981.44 | 0 | 598261.48 | 7130 | 11047.87
NHT-009024 - Reporting | 25-PC-40170 | Completed |  |  | 260400 | 190690.92 | 190690.92 | 22024.8 | 111458.84 | 0 | 133483.64 | 2511 | 2161.11
NHT-009029 - Reporting | 25-PC-40205 | Completed |  |  | 14805 | 9919.52 | 9919.52 | 695.47 | 8577.49 | 0 | 9272.96 | 140 | 151.13
NHT-009036 - Fieldwork | 25-PC-40205 | Completed |  |  | 22736 | 15233.27 | 15233.27 | 1068.03 | 13172.34 | 0 | 14240.37 | 208 | 247.76
NHT-009038 - Monitoring | 25-PC-40205 | Completed |  |  | 26205 | 17557.16 | 17557.16 | 1230.95 | 15181.81 | 0 | 16412.76 | 188 | 302.42
NHT-009040 - Survey | 25-PC-40205 | Completed |  |  | 15658 | 10490.8 | 10490.8 | 735.53 | 9071.49 | 0 | 9807.02 | 126 | 182.22
NHT-009042 - Lab Analysis | 25-PC-40205 | Completed |  |  | 8696 | 5826.25 | 5826.25 | 408.49 | 5038.01 | 0 | 5446.5 | 92 | 90.42
NHT-009043 - Monitoring | 25-PC-40231 | In progress |  |  | 53960 | 36347.72 | 36347.72 | 2989.25 | 19182.14 | 0 | 22171.39 | 728 | 454.17
NHT-009050 - Site Recordation | 25-PC-40231 | In progress |  |  | 34340 | 23131.16 | 23131.16 | 2321.74 | 14898.68 | 0 | 17220.42 | 562 | 347.49
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40231 | In progress |  |  | 0 | 0 | 0 | 0 | 842.98 | 0 | 842.98 | 0 | 19.75
NHT-009061 - Fieldwork | 25-PC-40248 | Completed |  |  | 80113 | 42208.18 | 54473.79 | 9756.84 | 47636.3 | 0 | 57393.14 | 632 | 913.77
NHT-009067 - Survey | 25-PC-40248 | Completed |  |  | 49414 | 26034.49 | 33600.05 | 6018.12 | 29382.61 | 0 | 35400.73 | 483 | 587.55
NHT-009070 - Curation | 25-PC-40248 | Completed |  |  | 12355 | 6509.58 | 8401.25 | 1504.75 | 7346.74 | 0 | 8851.49 | 123 | 134.55
NHT-009074 - Prefield | 25-PC-40248 | Completed |  |  | 22618 | 11916.28 | 15379.12 | 2754.56 | 13448.75 | 0 | 16203.31 | 267 | 265.84
NHT-009080 - GIS & Mapping | 25-PC-40383 | In progress |  |  | 72593 | 54176.05 | 54176.05 | 3943.32 | 45016.58 | 0 | 48959.9 | 761 | 953.15
NHT-009082 - Background Research | 25-PC-40383 | In progress |  |  | 120607 | 90009.11 | 90009.11 | 5677.69 | 64816.05 | 0 | 70493.74 | 1127 | 1198.29
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40383 | In progress |  |  | 0 | 0 | 0 | 0 | 808.96 | 0 | 808.96 | 0 | 18.75
NHT-009091 - Data Recovery Excavation | 25-PC-40465 | In progress |  |  | 127600 | 86041.09 | 94627.43 | 8695.42 | 50358.85 | 0 | 59054.27 | 2142 | 1162.17
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40465 | In progress |  |  | 0 | 0 | 0 | 0 | 914.13 | 0 | 914.13 | 0 | 20.75
NHT-009100 - Data Recovery Excavation | 25-PC-40482 | In progress |  |  | 32180 | 26464.35 | 26464.35 | 1463.74 | 6740.26 | 0 | 8204 | 0 | 128.8
NHT-009107 - Monitoring | 25-PC-40482 | Completed |  |  | 5086 | 4183 | 4183 | 912.22 | 4200.61 | 0 | 5112.83 | 0 | 67.07
NHT-009111 - Curation | 25-PC-40482 | In progress |  |  | 4681 | 3849.81 | 3849.81 | 496.03 | 2284.14 | 0 | 2780.17 | 0 | 46.41
NHT-009114 - Background Research | 25-PC-40482 | In progress |  |  | 10157 | 8353.23 | 8353.23 | 496.19 | 2284.88 | 0 | 2781.07 | 0 | 41.2
NHT-009116 - Fieldwork | 25-PC-40482 | In progress |  |  | 21096 | 17349.29 | 17349.29 | 1365.69 | 6288.76 | 0 | 7654.45 | 0 | 116.02
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40482 | In progress |  |  | 0 | 0 | 0 | 0 | 364.48 | 0 | 364.48 | 0 | 7.75
NHT-009123 - Reporting | 25-PC-40501 | Completed |  |  | 756174 | 496050.31 | 496050.31 | 79481.07 | 396453.47 | 0 | 475934.54 | 6059 | 8578.4
NHT-009127 - Lab Analysis | 25-PC-40501 | Completed |  |  | 490226 | 321588.09 | 321588.09 | 51527.37 | 257019.74 | 0 | 308547.11 | 3887 | 5489.4
NHT-009133 - Testing | 25-PC-40503 | Completed |  |  | 43400 | 30119.6 | 30119.6 | 8388.12 | 33443.16 | 0 | 41831.28 | 0 | 749.42
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40503 | Completed |  |  | 0 | 0 | 0 | 0 | 532.95 | 0 | 532.95 | 0 | 13
NHT-009138 - Project Management | 25-PC-40523 | In progress |  |  | 45327 | 31651.88 | 31651.88 | 8997.76 | 34246.71 | 0 | 43244.47 | 523 | 673.6
NHT-009140 - Draft Report | 25-PC-40523 | Completed |  |  | 25673 | 17927.42 | 17927.42 | 6740.56 | 25655.48 | 0 | 32396.04 | 357 | 552.58
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40523 | In progress |  |  | 0 | 0 | 0 | 0 | 759.09 | 0 | 759.09 | 0 | 18.75
NHT-009152 - Survey | 25-PC-40541 | In progress |  |  | 25000 | 16850 | 16850 | 1812.06 | 9373.48 | 0 | 11185.54 | 0 | 255.61
NHT-009157 - Background Research | 25-PC-40572 | In progress |  |  | 7679 | 5852.53 | 5852.53 | 418.28 | 4002.16 | 0 | 4420.44 | 148 | 111.21
NHT-009160 - Reporting | 25-PC-40572 | In progress |  |  | 19687 | 15003.71 | 15003.71 | 479.62 | 4589.05 | 0 | 5068.67 | 342 | 131.45
NHT-009163 - Draft Report | 25-PC-40572 | In progress |  |  | 22543 | 17180.26 | 17180.26 | 656.83 | 6284.52 | 0 | 6941.35 | 371 | 181.64
NHT-009166 - Lab Analysis | 25-PC-40572 | In progress |  |  | 38391 | 29256.93 | 29256.93 | 944.68 | 9038.67 | 0 | 9983.35 | 800 | 251.9
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40572 | In progress |  |  | 0 | 0 | 0 | 0 | 175.61 | 0 | 175.61 | 0 | 4.75
NHT-009173 - Final Report | 25-PC-40595 | Completed |  |  | 597122 | 495790.5 | 495790.5 | 38781.15 | 147905.89 | 0 | 186687.04 | 4750 | 2291.91
NHT-009177 - Curation | 25-PC-40595 | Completed |  |  | 429887 | 356935.24 | 356935.24 | 29482.88 | 112443.6 | 0 | 141926.48 | 3439 | 1930.54
NHT-009183 - Monitoring | 25-PC-40595 | Completed |  |  | 541291 | 449433.75 | 449433.75 | 36906.18 | 140755.02 | 0 | 177661.2 | 3742 | 2556.54
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40595 | Completed |  |  | 0 | 0 | 0 | 0 | 1793.94 | 0 | 1793.94 | 0 | 30.75
NHT-009190 - Background Research | 25-PC-40677 | Completed |  |  | 37047 | 25951.43 | 25951.43 | 5934.82 | 21875.58 | 0 | 27810.4 | 251 | 454.71
NHT-009193 - Reporting | 25-PC-40677 | Completed |  |  | 75331 | 52769.01 | 52769.01 | 10315.16 | 38021.39 | 0 | 48336.55 | 497 | 715.87
NHT-009199 - Project Management | 25-PC-40677 | Completed |  |  | 50608 | 35450.92 | 35450.92 | 7818.14 | 28817.42 | 0 | 36635.56 | 406 | 528.38
NHT-009202 - Prefield | 25-PC-40677 | Completed |  |  | 21198 | 14849.34 | 14849.34 | 3224.42 | 11885.13 | 0 | 15109.55 | 137 | 211.46
NHT-009206 - Monitoring | 25-PC-40677 | Completed |  |  | 40816 | 28591.8 | 28591.8 | 5445.14 | 20070.61 | 0 | 25515.75 | 360 | 368.28
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40677 | Completed |  |  | 0 | 0 | 0 | 0 | 290.24 | 0 | 290.24 | 0 | 7
NHT-009211 - Reporting | 25-PC-40680 | Completed |  |  | 10044 | 6669.14 | 6669.14 | 801.12 | 4635.02 | 0 | 5436.14 | 101 | 136.42
NHT-009215 - Background Research | 25-PC-40680 | Completed |  |  | 56 | 37.26 | 37.26 | 3.71 | 21.45 | 0 | 25.16 | 1 | 0.5
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40680 | Completed |  |  | 0 | 0 | 0 | 0 | 166.85 | 0 | 166.85 | 0 | 4.25
NHT-009222 - Monitoring | 25-PC-40708 | Completed |  |  | 37049 | 22840.93 | 22840.93 | 3519.54 | 15201.41 | 0 | 18720.95 | 250 | 318.03
NHT-009224 - GIS & Mapping | 25-PC-40708 | Completed |  |  | 13851 | 8538.92 | 8538.92 | 1315.75 | 5682.94 | 0 | 6998.69 | 95 | 119.68
NHT-009231 - Data Recovery Excavation | 25-PC-40722 | In progress |  |  | 25204 | 15630.63 | 18077.38 | 828.82 | 10844.75 | 0 | 11673.57 | 107 | 191.62
NHT-009236 - Desktop Review | 25-PC-40722 | In progress |  |  | 23090 | 14319.19 | 16560.66 | 815.37 | 10668.78 | 0 | 11484.15 | 134 | 180.43
NHT-009242 - Final Report | 25-PC-40722 | In progress |  |  | 83698 | 51906.08 | 60031.26 | 2823.29 | 36941.33 | 0 | 39764.62 | 461 | 472.48
NHT-009243 - Prefield | 25-PC-40722 | In progress |  |  | 34608 | 21462.3 | 24821.93 | 1242.55 | 16258.11 | 0 | 17500.66 | 178 | 277.42
NHT-009247 - Survey | 25-PC-40810 | Completed |  |  | 16646 | 11577.2 | 11577.2 | 1212.23 | 10493.26 | 0 | 11705.49 | 242 | 241.12
NHT-009249 - Prefield | 25-PC-40810 | Completed |  |  | 19284 | 13411.88 | 13411.88 | 1195.98 | 10352.72 | 0 | 11548.7 | 272 | 249.12
NHT-009253 - Curation | 25-PC-40810 | Completed |  |  | 11771 | 8186.78 | 8186.78 | 1203.27 | 10415.8 | 0 | 11619.07 | 158 | 240.39
NHT-009256 - Lab Analysis | 25-PC-40810 | Completed |  |  | 2399 | 1668.69 | 1668.69 | 181.7 | 1572.86 | 0 | 1754.56 | 34 | 35.16
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40810 | Completed |  |  | 0 | 0 | 0 | 0 | 928.41 | 0 | 928.41 | 0 | 21.25
NHT-009260 - Data Recovery Excavation | 25-PC-40847 | Completed |  |  | 34355 | 25137.7 | 25137.7 | 3489.18 | 20424.04 | 0 | 23913.22 | 262 | 328.03
NHT-009262 - Draft Report | 25-PC-40847 | Completed |  |  | 12445 | 9105.86 | 9105.86 | 1947.58 | 11400.2 | 0 | 13347.78 | 78 | 215.34
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40847 | Completed |  |  | 0 | 0 | 0 | 0 | 233.89 | 0 | 233.89 | 0 | 5.25
NHT-009270 - Survey | 25-PC-40880 | In progress |  |  | 9953 | 6594.84 | 6594.84 | 546.38 | 3063.88 | 0 | 3610.26 | 0 | 73.94
NHT-009276 - Lab Analysis | 25-PC-40880 | In progress |  |  | 16918 | 11210.01 | 11210.01 | 1025.89 | 5752.79 | 0 | 6778.68 | 0 | 134.41
NHT-009279 - Agency Consultation | 25-PC-40880 | In progress |  |  | 18929 | 12542.23 | 12542.23 | 1151.61 | 6457.75 | 0 | 7609.36 | 0 | 155.18
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-40880 | In progress |  |  | 0 | 0 | 0 | 0 | 282.79 | 0 | 282.79 | 0 | 6.75
NHT-009290 - Curation | 25-PC-40925 | Completed |  |  | 3872 | 2606.71 | 2606.71 | 277.67 | 1961.61 | 0 | 2239.28 | 43 | 35.91
NHT-009291 - Final Report | 25-PC-40925 | Completed |  |  | 7967 | 5363.39 | 5363.39 | 571.31 | 4036.06 | 0 | 4607.37 | 83 | 78.34
NHT-009295 - Lab Analysis | 25-PC-40925 | Completed |  |  | 7690 | 5176.93 | 5176.93 | 551.45 | 3895.75 | 0 | 4447.2 | 91 | 74.93
NHT-009299 - Reporting | 25-PC-40925 | Completed |  |  | 15471 | 10414.97 | 10414.97 | 1109.42 | 7837.48 | 0 | 8946.9 | 159 | 152.02
NHT-009301 - Final Report | 25-PC-40944 | Completed |  |  | 101400 | 73160.1 | 73160.1 | 13790.68 | 81317.45 | 0 | 95108.13 | 0 | 1555.77
NHT-009307 - Agency Consultation | 25-PC-41075 | In progress |  |  | 82100 | 61304.07 | 61304.07 | 2571.31 | 31435.57 | 0 | 34006.88 | 880 | 696.23
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41075 | In progress |  |  | 0 | 0 | 0 | 0 | 740.58 | 0 | 740.58 | 0 | 18.25
NHT-009316 - Curation | 25-PC-41083 | On hold |  |  | 193500 | 140887.35 | 140887.35 | 5217.81 | 21268.52 | 0 | 26486.33 | 1762 | 378.82
NHT-009320 - GIS & Mapping | 25-PC-41097 | Completed |  |  | 94104 | 60970.23 | 60970.23 | 7176.09 | 42157.22 | 0 | 49333.31 | 454 | 1003
NHT-009327 - Final Report | 25-PC-41097 | Completed |  |  | 103696 | 67184.39 | 67184.39 | 7977.1 | 46862.84 | 0 | 54839.94 | 616 | 1056.64
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41097 | Completed |  |  | 0 | 0 | 0 | 0 | 1793.09 | 0 | 1793.09 | 0 | 39
NHT-009339 - Final Report | 25-PC-41187 | In progress |  |  | 71086 | 39978.88 | 39978.88 | 1808.45 | 26557.57 | 0 | 28366.02 | 0 | 606.47
NHT-009342 - Background Research | 25-PC-41187 | In progress |  |  | 27814 | 15642.48 | 15642.48 | 867.14 | 12734.21 | 0 | 13601.35 | 0 | 266.2
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41187 | In progress |  |  | 0 | 0 | 0 | 0 | 502.25 | 0 | 502.25 | 0 | 10.75
NHT-009349 - Project Management | 25-PC-41252 | Completed |  |  | 33000 | 22089.27 | 25325 | 4434.49 | 19015.1 | 0 | 23449.59 | 349 | 401.39
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41252 | Completed |  |  | 0 | 0 | 0 | 0 | 138.12 | 0 | 138.12 | 0 | 3.25
NHT-009357 - GIS & Mapping | 25-PC-41265 | Completed |  |  | 21850 | 17497.12 | 17497.12 | 2609.96 | 14013.98 | 0 | 16623.94 | 288 | 276.33
NHT-009362 - Data Recovery Excavation | 25-PC-41265 | Completed |  |  | 67950 | 54414.72 | 54414.72 | 8116.77 | 43582.43 | 0 | 51699.2 | 852 | 1029.88
NHT-009366 - Site Recordation | 25-PC-41341 | In progress |  |  | 167900 | 131616.81 | 131616.81 | 20763.57 | 84102.93 | 0 | 104866.5 | 1459 | 1576.42
NHT-009368 - Testing | 25-PC-41372 | Completed |  |  | 65579 | 47997.12 | 47997.12 | 7233.94 | 33867.98 | 0 | 41101.92 | 0 | 606.42
NHT-009372 - Curation | 25-PC-41372 | Completed |  |  | 20521 | 15019.47 | 15019.47 | 2263.68 | 10598.12 | 0 | 12861.8 | 0 | 198.95
NHT-009377 - Curation | 25-PC-41383 | In progress |  |  | 82864 | 45034.76 | 54218.13 | 6088.59 | 35886.18 | 0 | 41974.77 | 0 | 857.72
NHT-009383 - GIS & Mapping | 25-PC-41383 | In progress |  |  | 252608 | 137287.03 | 165282.24 | 18464.33 | 108828.84 | 0 | 127293.17 | 0 | 1967.08
NHT-009388 - Background Research | 25-PC-41383 | In progress |  |  | 6728 | 3656.67 | 4402.33 | 480.61 | 2832.74 | 0 | 3313.35 | 0 | 79.43
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41383 | In progress |  |  | 0 | 0 | 0 | 0 | 63.75 | 0 | 63.75 | 0 | 1.5
NHT-009400 - Monitoring | 25-PC-41385 | Completed |  |  | 16197 | 10735.42 | 10735.42 | 3963.09 | 25896.09 | 0 | 29859.18 | 69 | 282.37
NHT-009407 - GIS & Mapping | 25-PC-41385 | In progress |  |  | 17142 | 11361.72 | 11361.72 | 6129.59 | 40052.64 | 0 | 46182.23 | 72 | 445.79
NHT-009414 - Desktop Review | 25-PC-41385 | Completed |  |  | 62561 | 41465.69 | 41465.69 | 5594.75 | 36557.82 | 0 | 42152.57 | 293 | 385.09
NHT-009418 - Reporting | 25-PC-41385 | In progress |  |  | 83900 | 55608.61 | 55608.61 | 6720.9 | 43916.42 | 0 | 50637.32 | 385 | 563.54
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41385 | In progress |  |  | 0 | 0 | 0 | 0 | 2224.66 | 0 | 2224.66 | 0 | 24
NHT-009425 - Curation | 25-PC-41476 | Completed |  |  | 21863 | 15146.82 | 15146.82 | 3977.55 | 15713.31 | 0 | 19690.86 | 207 | 268.45
NHT-009427 - Testing | 25-PC-41476 | Completed |  |  | 68875 | 47716.53 | 47716.53 | 12530.37 | 49501.15 | 0 | 62031.52 | 594 | 912.2
NHT-009430 - Agency Consultation | 25-PC-41476 | Completed |  |  | 22460 | 15560.3 | 15560.3 | 4086.13 | 16142.25 | 0 | 20228.38 | 202 | 251.62
NHT-009436 - Draft Report | 25-PC-41476 | Completed |  |  | 68349 | 47352.11 | 47352.11 | 12434.66 | 49123.08 | 0 | 61557.74 | 707 | 866.79
NHT-009438 - Project Management | 25-PC-41476 | Completed |  |  | 30353 | 21028.56 | 21028.56 | 5522.1 | 21815.02 | 0 | 27337.12 | 257 | 469.65
NHT-009442 - Reporting | 25-PC-41479 | In progress |  |  | 410225 | 262297.84 | 262297.84 | 9746.16 | 62086.53 | 0 | 71832.69 | 6281 | 1325.35
NHT-009445 - Agency Consultation | 25-PC-41479 | In progress |  |  | 17802 | 11382.89 | 11382.89 | 681.86 | 4343.67 | 0 | 5025.53 | 151 | 93.92
NHT-009451 - Curation | 25-PC-41479 | In progress |  |  | 76162 | 48697.93 | 48697.93 | 2370.67 | 15102.02 | 0 | 17472.69 | 916 | 316.45
NHT-009456 - Data Recovery Excavation | 25-PC-41479 | In progress |  |  | 66391 | 42450.33 | 42450.33 | 2527.53 | 16101.28 | 0 | 18628.81 | 702 | 313.39
NHT-009463 - GIS & Mapping | 25-PC-41479 | In progress |  |  | 63020 | 40294.85 | 40294.85 | 2271.8 | 14472.19 | 0 | 16743.99 | 682 | 327.96
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41479 | In progress |  |  | 0 | 0 | 0 | 0 | 652.02 | 0 | 652.02 | 0 | 13.75
NHT-009467 - Agency Consultation | 25-PC-41500 | Completed |  |  | 30418 | 18985.93 | 21997.71 | 5432.67 | 24518.13 | 0 | 29950.8 | 554 | 469.45
NHT-009470 - Curation | 25-PC-41500 | Completed |  |  | 39438 | 24615.34 | 28520.12 | 5234.37 | 23623.19 | 0 | 28857.56 | 677 | 499.16
NHT-009471 - Data Recovery Excavation | 25-PC-41500 | Completed |  |  | 35099 | 21907.37 | 25382.59 | 4736.51 | 21376.27 | 0 | 26112.78 | 587 | 437.59
NHT-009474 - Lab Analysis | 25-PC-41500 | In progress |  |  | 25245 | 15756.78 | 18256.31 | 3489.57 | 15748.73 | 0 | 19238.3 | 521 | 316.11
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41500 | In progress |  |  | 0 | 0 | 0 | 0 | 1388.68 | 0 | 1388.68 | 0 | 33.25
NHT-009483 - Project Management | 25-PC-41514 | Completed |  |  | 1723 | 1034.27 | 1100.98 | 162.08 | 679.24 | 0 | 841.32 | 19 | 15.75
NHT-009490 - Data Recovery Excavation | 25-PC-41514 | Completed |  |  | 28877 | 17336.96 | 18455.16 | 2302.41 | 9648.88 | 0 | 11951.29 | 324 | 240.23
NHT-009494 - Site Recordation | 25-PC-41514 | Completed |  |  | 14748 | 8854.05 | 9425.11 | 1953.47 | 8186.55 | 0 | 10140.02 | 177 | 208.36
NHT-009497 - Lab Analysis | 25-PC-41514 | Completed |  |  | 3352 | 2012.32 | 2142.11 | 315.53 | 1322.33 | 0 | 1637.86 | 36 | 31.13
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41514 | Completed |  |  | 0 | 0 | 0 | 0 | 83.1 | 0 | 83.1 | 0 | 2
NHT-009505 - Agency Consultation | 25-PC-41600 | Completed |  |  | 647300 | 439366.44 | 488406.31 | 101587.09 | 384475.55 | 0 | 486062.64 | 8132 | 8472.13
NHT-009508 - Testing | 25-PC-41603 | Completed |  |  | 21419 | 13234.8 | 14746.06 | 2108.69 | 17061.19 | 0 | 19169.88 | 253 | 314.02
NHT-009514 - Curation | 25-PC-41603 | Completed |  |  | 5273 | 3258.34 | 3630.4 | 519.15 | 4200.38 | 0 | 4719.53 | 55 | 83.87
NHT-009515 - Draft Report | 25-PC-41603 | Completed |  |  | 17550 | 10844.19 | 12082.46 | 1727.79 | 13979.41 | 0 | 15707.2 | 193 | 269.8
NHT-009520 - Monitoring | 25-PC-41603 | Completed |  |  | 29558 | 18263.77 | 20349.27 | 2909.94 | 23544.1 | 0 | 26454.04 | 318 | 431.35
NHT-009522 - Prefield | 25-PC-41635 | In progress |  |  | 170291 | 116428.22 | 116428.22 | 12046.75 | 70698.21 | 0 | 82744.96 | 1415 | 1606.76
NHT-009525 - Fieldwork | 25-PC-41635 | Completed |  |  | 61571 | 42096.01 | 42096.01 | 7722.85 | 45322.75 | 0 | 53045.6 | 505 | 1056.18
NHT-009530 - Background Research | 25-PC-41635 | In progress |  |  | 180438 | 123365.28 | 123365.28 | 12787.5 | 75045.36 | 0 | 87832.86 | 1445 | 1519.94
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41635 | In progress |  |  | 0 | 0 | 0 | 0 | 908.29 | 0 | 908.29 | 0 | 21
NHT-009538 - Fieldwork | 25-PC-41722 | In progress |  |  | 89496 | 63900.37 | 63900.37 | 5881.26 | 46043.83 | 0 | 51925.09 | 1736 | 1195.53
NHT-009543 - Final Report | 25-PC-41722 | In progress |  |  | 62604 | 44699.03 | 44699.03 | 4309.02 | 33734.93 | 0 | 38043.95 | 837 | 777.83
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41722 | In progress |  |  | 0 | 0 | 0 | 0 | 1015.62 | 0 | 1015.62 | 0 | 22.5
NHT-009547 - Lab Analysis | 25-PC-41764 | In progress |  |  | 20700 | 13328.34 | 15642.78 | 1280.38 | 13269.45 | 0 | 14549.83 | 286 | 347.8
NHT-009549 - Lab Analysis | 25-PC-41834 | In progress |  |  | 102957 | 88007.73 | 88007.73 | 2652.41 | 26982.3 | 0 | 29634.71 | 1358 | 615.49
NHT-009556 - Background Research | 25-PC-41834 | In progress |  |  | 32629 | 27891.6 | 27891.6 | 1088.82 | 11076.3 | 0 | 12165.12 | 345 | 258.09
NHT-009561 - Prefield | 25-PC-41834 | In progress |  |  | 27482 | 23491.4 | 23491.4 | 828.39 | 8426.96 | 0 | 9255.35 | 275 | 230.64
NHT-009563 - Agency Consultation | 25-PC-41834 | In progress |  |  | 7032 | 6010.75 | 6010.75 | 278.71 | 2835.28 | 0 | 3113.99 | 91 | 68.1
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-41834 | In progress |  |  | 0 | 0 | 0 | 0 | 306.45 | 0 | 306.45 | 0 | 6.75
NHT-009572 - Final Report | 25-PC-41843 | Completed |  |  | 54000 | 26607.55 | 35988.02 | 4991.24 | 18663.91 | 0 | 23655.15 | 0 | 398.96
NHT-009575 - Data Recovery Excavation | 25-PC-41854 | Completed |  |  | 5624 | 3671.73 | 3671.73 | 1259.26 | 6191.99 | 0 | 7451.25 | 72 | 122.82
NHT-009581 - Background Research | 25-PC-41854 | In progress |  |  | 21344 | 13935.56 | 13935.56 | 1898.82 | 9336.78 | 0 | 11235.6 | 320 | 196.67
NHT-009584 - Monitoring | 25-PC-41854 | In progress |  |  | 12732 | 8312.84 | 8312.84 | 1892.13 | 9303.9 | 0 | 11196.03 | 185 | 211.54
NHT-009586 - Lab Analysis | 25-PC-41931 | Completed |  |  | 8208 | 5359.86 | 5359.86 | 404.31 | 4915.54 | 0 | 5319.85 | 72 | 92.59
NHT-009593 - Draft Report | 25-PC-41931 | Completed |  |  | 22489 | 14685 | 14685 | 1107.73 | 13467.64 | 0 | 14575.37 | 215 | 282.79
NHT-009597 - Monitoring | 25-PC-41931 | Completed |  |  | 25503 | 16653.74 | 16653.74 | 1256.23 | 15273.17 | 0 | 16529.4 | 179 | 283.12
NHT-009598 - Draft Report | 25-PC-41967 | On hold |  |  | 7356 | 5590.64 | 5590.64 | 125.89 | 1447.68 | 0 | 1573.57 | 93 | 30.46
NHT-009599 - Monitoring | 25-PC-41967 | On hold |  |  | 12135 | 9222.56 | 9222.56 | 207.67 | 2388.16 | 0 | 2595.83 | 149 | 49.48
NHT-009603 - Desktop Review | 25-PC-41967 | On hold |  |  | 2182 | 1658.1 | 1658.1 | 37.34 | 429.36 | 0 | 466.7 | 33 | 8.04
NHT-009604 - Data Recovery Excavation | 25-PC-41967 | On hold |  |  | 15627 | 11876.7 | 11876.7 | 267.42 | 3075.44 | 0 | 3342.86 | 195 | 66.69
NHT-009608 - Project Management | 25-PC-42076 | In progress |  |  | 119988 | 85502.87 | 85502.87 | 3725.54 | 29549.47 | 0 | 33275.01 | 1858 | 527.21
NHT-009611 - Background Research | 25-PC-42076 | In progress |  |  | 93844 | 66873.56 | 66873.56 | 3331.97 | 26427.81 | 0 | 29759.78 | 1342 | 452.71
NHT-009617 - Survey | 25-PC-42076 | In progress |  |  | 105768 | 75370.53 | 75370.53 | 3831.61 | 30390.76 | 0 | 34222.37 | 1405 | 530.07
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42076 | In progress |  |  | 0 | 0 | 0 | 0 | 1734.87 | 0 | 1734.87 | 0 | 26.5
NHT-009620 - Draft Report | 25-PC-42078 | Completed |  |  | 168830 | 123178.34 | 123178.34 | 14881.31 | 87748.41 | 0 | 102629.72 | 0 | 1815.38
NHT-009622 - GIS & Mapping | 25-PC-42078 | Completed |  |  | 116356 | 84893.45 | 84893.45 | 10256.07 | 60475.46 | 0 | 70731.53 | 0 | 1073.7
NHT-009625 - Testing | 25-PC-42078 | Completed |  |  | 148714 | 108501.65 | 108501.65 | 13108.21 | 77293.21 | 0 | 90401.42 | 0 | 1573.17
NHT-009628 - Lab Analysis | 25-PC-42084 | In progress |  |  | 407726 | 266938.16 | 266938.16 | 12869.84 | 80389.85 | 0 | 93259.69 | 3597 | 1664.07
NHT-009633 - Site Recordation | 25-PC-42084 | In progress |  |  | 589841 | 386169.25 | 386169.25 | 18618.3 | 116296.92 | 0 | 134915.22 | 4217 | 1872.96
NHT-009639 - Curation | 25-PC-42084 | In progress |  |  | 296633 | 194205.33 | 194205.33 | 9363.18 | 58485.97 | 0 | 67849.15 | 2466 | 1009.05
NHT-009646 - Lab Analysis | 25-PC-42097 | In progress |  |  | 179700 | 138548.7 | 138548.7 | 9490.12 | 54746.43 | 0 | 64236.55 | 1033 | 760.73
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42097 | In progress |  |  | 0 | 0 | 0 | 0 | 764.26 | 0 | 764.26 | 0 | 11.5
NHT-009653 - GIS & Mapping | 25-PC-42115 | Completed |  |  | 110400 | 90660.48 | 90660.48 | 7471.56 | 48692.27 | 0 | 56163.83 | 1078 | 1104.04
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42115 | Completed |  |  | 0 | 0 | 0 | 0 | 1755.29 | 0 | 1755.29 | 0 | 32.5
NHT-009662 - Curation | 25-PC-42136 | In progress |  |  | 31700 | 17555.9 | 23936.32 | 3807.07 | 14066.49 | 0 | 17873.56 | 224 | 202.87
NHT-009666 - Site Recordation | 25-PC-42163 | Completed |  |  | 18338 | 12453.66 | 12453.66 | 807.18 | 8566.63 | 0 | 9373.81 | 197 | 160.11
NHT-009667 - Final Report | 25-PC-42163 | Completed |  |  | 25238 | 17139.02 | 17139.02 | 1221.11 | 12959.69 | 0 | 14180.8 | 225 | 262.17
NHT-009674 - Agency Consultation | 25-PC-42163 | Completed |  |  | 7124 | 4837.69 | 4837.69 | 316.25 | 3356.42 | 0 | 3672.67 | 85 | 60.25
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42163 | Completed |  |  | 0 | 0 | 0 | 0 | 34.77 | 0 | 34.77 | 0 | 0.75
NHT-009683 - Lab Analysis | 25-PC-42227 | Completed |  |  | 17900 | 12066.39 | 12066.39 | 1533.57 | 12798.86 | 0 | 14332.43 | 0 | 216.11
NHT-009685 - Agency Consultation | 25-PC-42253 | In progress |  |  | 67000 | 45781.1 | 45781.1 | 2230.25 | 24967.92 | 0 | 27198.17 | 826 | 527.41
NHT-009688 - Agency Consultation | 25-PC-42282 | In progress |  |  | 16409 | 9574.73 | 9574.73 | 1092 | 4592.88 | 0 | 5684.88 | 219 | 113.24
NHT-009693 - Prefield | 25-PC-42282 | In progress |  |  | 4583 | 2674.28 | 2674.28 | 327.03 | 1375.45 | 0 | 1702.48 | 48 | 31.01
NHT-009700 - Data Recovery Excavation | 25-PC-42282 | In progress |  |  | 12008 | 7006.49 | 7006.49 | 811.11 | 3411.46 | 0 | 4222.57 | 150 | 74.76
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42282 | In progress |  |  | 0 | 0 | 0 | 0 | 127.64 | 0 | 127.64 | 0 | 3
NHT-009708 - Curation | 25-PC-42303 | Completed |  |  | 147500 | 99769 | 99769 | 20881.65 | 108818.05 | 0 | 129699.7 | 916 | 2149.7
NHT-009709 - Survey | 25-PC-42315 | In progress |  |  | 15606 | 11075.32 | 11075.32 | 1351.82 | 5470.53 | 0 | 6822.35 | 109 | 72.39
NHT-009712 - Background Research | 25-PC-42315 | In progress |  |  | 25594 | 18164.32 | 18164.32 | 3026.93 | 12249.4 | 0 | 15276.33 | 181 | 149.19
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42315 | In progress |  |  | 0 | 0 | 0 | 0 | 826.73 | 0 | 826.73 | 0 | 7.5
NHT-009723 - Project Management | 25-PC-42323 | In progress |  |  | 22961 | 16791.06 | 16791.06 | 1070.23 | 10089.96 | 0 | 11160.19 | 0 | 138.42
NHT-009727 - Background Research | 25-PC-42323 | In progress |  |  | 20436 | 14944.65 | 14944.65 | 770.59 | 7264.99 | 0 | 8035.58 | 0 | 87.07
NHT-009731 - Curation | 25-PC-42323 | In progress |  |  | 36403 | 26622.03 | 26622.03 | 1379.73 | 13007.9 | 0 | 14387.63 | 0 | 162.54
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42323 | In progress |  |  | 0 | 0 | 0 | 0 | 317.16 | 0 | 317.16 | 0 | 4
NHT-009737 - Site Recordation | 25-PC-42343 | In progress |  |  | 1129 | 701.08 | 747.49 | 73.31 | 432.28 | 0 | 505.59 | 14 | 8.92
NHT-009742 - Reporting | 25-PC-42343 | In progress |  |  | 1483 | 921.12 | 982.09 | 96.32 | 567.95 | 0 | 664.27 | 18 | 11.61
NHT-009745 - Fieldwork | 25-PC-42343 | In progress |  |  | 2683 | 1665.91 | 1776.19 | 174.2 | 1027.19 | 0 | 1201.39 | 34 | 16.94
NHT-009752 - Draft Report | 25-PC-42343 | In progress |  |  | 805 | 499.54 | 532.61 | 52.24 | 308.01 | 0 | 360.25 | 11 | 5.86
NHT-009758 - Monitoring | 25-PC-42364 | In progress |  |  | 594900 | 400715.25 | 426353.2 | 44723.17 | 224684.11 | 0 | 269407.28 | 7627 | 5518.76
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42364 | In progress |  |  | 0 | 0 | 0 | 0 | 9.4 | 0 | 9.4 | 0 | 0.25
NHT-009762 - Background Research | 25-PC-42399 | In progress |  |  | 208580 | 155329.54 | 155329.54 | 15724.28 | 75352.05 | 0 | 91076.33 | 3118 | 1502.85
NHT-009765 - Lab Analysis | 25-PC-42399 | In progress |  |  | 384735 | 286511.78 | 286511.78 | 23136.38 | 110871.4 | 0 | 134007.78 | 6196 | 2065.7
NHT-009768 - Desktop Review | 25-PC-42399 | In progress |  |  | 90485 | 67384.54 | 67384.54 | 10244.04 | 49090.28 | 0 | 59334.32 | 1075 | 921.59
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42399 | In progress |  |  | 0 | 0 | 0 | 0 | 2743.58 | 0 | 2743.58 | 0 | 55.25
NHT-009782 - Final Report | 25-PC-42528 | In progress |  |  | 60983 | 43243.27 | 43243.27 | 1540.37 | 10374.1 | 0 | 11914.47 | 564 | 227.31
NHT-009784 - Site Recordation | 25-PC-42528 | In progress |  |  | 71017 | 50357.93 | 50357.93 | 1883.34 | 12683.89 | 0 | 14567.23 | 597 | 261.16
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42528 | In progress |  |  | 0 | 0 | 0 | 0 | -145.47 | 0 | -145.47 | 0 | -3.5
NHT-009789 - Background Research | 25-PC-42569 | Completed |  |  | 13221 | 10158.64 | 10158.64 | 1070.53 | 7493.7 | 0 | 8564.23 | 120 | 142.11
NHT-009794 - GIS & Mapping | 25-PC-42569 | Completed |  |  | 22227 | 17079.61 | 17079.61 | 1799.87 | 12599.07 | 0 | 14398.94 | 186 | 212.58
NHT-009797 - Reporting | 25-PC-42569 | Completed |  |  | 52564 | 40390.45 | 40390.45 | 4256.39 | 29794.75 | 0 | 34051.14 | 593 | 548.85
NHT-009800 - Prefield | 25-PC-42569 | Completed |  |  | 17688 | 13591.18 | 13591.18 | 1432.25 | 10025.77 | 0 | 11458.02 | 186 | 192.5
NHT-009805 - Curation | 25-PC-42601 | Completed |  |  | 302100 | 177364.48 | 213521.46 | 6601.68 | 55610.11 | 0 | 62211.79 | 1670 | 603.13
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42601 | Completed |  |  | 0 | 0 | 0 | 0 | 661.38 | 0 | 661.38 | 0 | 6
NHT-009811 - Reporting | 25-PC-42717 | In progress |  |  | 29658 | 21804.74 | 21804.74 | 1517.33 | 15641.21 | 0 | 17158.54 | 215 | 236.34
NHT-009816 - Desktop Review | 25-PC-42717 | In progress |  |  | 35175 | 25860.1 | 25860.1 | 1669.59 | 17210.69 | 0 | 18880.28 | 295 | 368.52
NHT-009823 - Survey | 25-PC-42717 | Completed |  |  | 9000 | 6616.67 | 6616.67 | 667.61 | 6881.98 | 0 | 7549.59 | 53 | 116.72
NHT-009826 - Curation | 25-PC-42717 | In progress |  |  | 31457 | 23127.43 | 23127.43 | 1802.75 | 18583.35 | 0 | 20386.1 | 179 | 347.59
NHT-009831 - Data Recovery Excavation | 25-PC-42717 | In progress |  |  | 25010 | 18387.62 | 18387.62 | 1381.46 | 14240.58 | 0 | 15622.04 | 171 | 204.85
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-42717 | In progress |  |  | 0 | 0 | 0 | 0 | 389.14 | 0 | 389.14 | 0 | 10
NHT-009839 - Testing | 25-PC-42747 | On hold |  |  | 42528 | 28999.54 | 28999.54 | 2284.67 | 13471.68 | 0 | 15756.35 | 647 | 250.18
NHT-009846 - Fieldwork | 25-PC-42747 | On hold |  |  | 86372 | 58897.37 | 58897.37 | 4640.11 | 27360.66 | 0 | 32000.77 | 1156 | 405.85
NHT-009848 - Agency Consultation | 25-PC-43037 | Completed |  |  | 28447 | 22310.62 | 22310.62 | 4744.56 | 22367.23 | 0 | 27111.79 | 210 | 428.74
NHT-009852 - Site Recordation | 25-PC-43037 | Completed |  |  | 89860 | 70477.41 | 70477.41 | 14987.69 | 70656.24 | 0 | 85643.93 | 616 | 1307.83
NHT-009856 - Testing | 25-PC-43037 | Completed |  |  | 80384 | 63045.52 | 63045.52 | 13407.23 | 63205.5 | 0 | 76612.73 | 516 | 865.89
NHT-009862 - Project Management | 25-PC-43037 | Completed |  |  | 51509 | 40398.31 | 40398.31 | 8591.08 | 40500.82 | 0 | 49091.9 | 334 | 798.39
NHT-009869 - Lab Analysis | 25-PC-43061 | Completed |  |  | 51965 | 39613.44 | 39613.44 | 6150.72 | 31583.73 | 0 | 37734.45 | 725 | 643.54
NHT-009871 - Background Research | 25-PC-43061 | Completed |  |  | 34982 | 26666.61 | 26666.61 | 4140.48 | 21261.25 | 0 | 25401.73 | 403 | 398.91
NHT-009877 - Desktop Review | 25-PC-43061 | Completed |  |  | 19553 | 14904.9 | 14904.9 | 2314.26 | 11883.65 | 0 | 14197.91 | 204 | 188.83
NHT-009881 - Draft Report | 25-PC-43073 | Completed |  |  | 20645 | 14786.13 | 14786.13 | 2193.39 | 15168.29 | 0 | 17361.68 | 217 | 242.41
NHT-009883 - Curation | 25-PC-43073 | Completed |  |  | 8382 | 6002.88 | 6002.88 | 660.38 | 4566.81 | 0 | 5227.19 | 76 | 68.14
NHT-009889 - Background Research | 25-PC-43073 | Completed |  |  | 32973 | 23615.39 | 23615.39 | 2674.74 | 18497.1 | 0 | 21171.84 | 256 | 272.97
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43073 | Completed |  |  | 0 | 0 | 0 | 0 | 824.08 | 0 | 824.08 | 0 | 8
NHT-009893 - Prefield | 25-PC-43075 | On hold |  |  | 62815 | 39297.04 | 39297.04 | 2242.8 | 11516.69 | 0 | 13759.49 | 511 | 236.8
NHT-009894 - Draft Report | 25-PC-43075 | On hold |  |  | 158632 | 99240.01 | 99240.01 | 5663.91 | 29084.03 | 0 | 34747.94 | 1058 | 510.99
NHT-009899 - Site Recordation | 25-PC-43075 | On hold |  |  | 84135 | 52634.83 | 52634.83 | 3004.02 | 15425.57 | 0 | 18429.59 | 505 | 250.77
NHT-009904 - Final Report | 25-PC-43075 | On hold |  |  | 75518 | 47244.28 | 47244.28 | 2696.37 | 13845.77 | 0 | 16542.14 | 474 | 218.73
NHT-009908 - Data Recovery Excavation | 25-PC-43106 | Completed |  |  | 63000 | 41082.3 | 41082.3 | 3440.95 | 33164.89 | 0 | 36605.84 | 677 | 701.86
NHT-009909 - Monitoring | 25-PC-43203 | In progress |  |  | 65849 | 54522.99 | 54522.99 | 14885.69 | 62276.32 | 0 | 77162.01 | 757 | 1029.13
NHT-009910 - Curation | 25-PC-43203 | Completed |  |  | 12842 | 10633.3 | 10633.3 | 9912.34 | 41469.62 | 0 | 51381.96 | 150 | 738.81
NHT-009914 - Agency Consultation | 25-PC-43203 | In progress |  |  | 49709 | 41158.91 | 41158.91 | 12587.22 | 52660.33 | 0 | 65247.55 | 524 | 879.14
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43203 | In progress |  |  | 0 | 0 | 0 | 0 | 1942.78 | 0 | 1942.78 | 0 | 30
NHT-009918 - Background Research | 25-PC-43244 | Completed |  |  | 276529 | 152326.38 | 203688.89 | 11745.3 | 168951.63 | 0 | 180696.93 | 0 | 2602.13
NHT-009924 - Project Management | 25-PC-43244 | Completed |  |  | 518371 | 285545.52 | 381827.82 | 22017.32 | 316710.6 | 0 | 338727.92 | 0 | 5992.79
NHT-009929 - Monitoring | 25-PC-43286 | In progress |  |  | 6117 | 4248.14 | 4248.14 | 3742.57 | 13801.9 | 0 | 17544.47 | 60 | 221.11
NHT-009935 - Testing | 25-PC-43286 | In progress |  |  | 2114 | 1468.29 | 1468.29 | 5701.45 | 21025.92 | 0 | 26727.37 | 15 | 328.45
NHT-009939 - Agency Consultation | 25-PC-43286 | In progress |  |  | 6781 | 4709.26 | 4709.26 | 3860.26 | 14235.94 | 0 | 18096.2 | 65 | 225.48
NHT-009940 - Site Recordation | 25-PC-43286 | In progress |  |  | 688 | 477.96 | 477.96 | 1498.74 | 5527.1 | 0 | 7025.84 | 6 | 77.35
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43286 | In progress |  |  | 0 | 0 | 0 | 0 | 1774.48 | 0 | 1774.48 | 0 | 24
NHT-009950 - Project Management | 25-PC-43315 | Completed |  |  | 715500 | 625275.45 | 625275.45 | 39814.45 | 528963.39 | 0 | 568777.84 | 7995 | 9051.77
NHT-009954 - Desktop Review | 25-PC-43434 | Completed |  |  | 551800 | 378424.44 | 378424.44 | 28393.85 | 377232.51 | 0 | 405626.36 | 4019 | 6540.98
NHT-009960 - Survey | 25-PC-43455 | On hold |  |  | 36907 | 26989.57 | 26989.57 | 223.19 | 2465.89 | 0 | 2689.08 | 469 | 35.44
NHT-009962 - Curation | 25-PC-43455 | On hold |  |  | 10278 | 7516.38 | 7516.38 | 62.16 | 686.73 | 0 | 748.89 | 123 | 10
NHT-009967 - Fieldwork | 25-PC-43455 | On hold |  |  | 28354 | 20735.53 | 20735.53 | 171.47 | 1894.48 | 0 | 2065.95 | 429 | 37.14
NHT-009972 - Reporting | 25-PC-43455 | On hold |  |  | 23117 | 16905.32 | 16905.32 | 139.8 | 1544.54 | 0 | 1684.34 | 357 | 25.67
NHT-009976 - Draft Report | 25-PC-43455 | On hold |  |  | 17444 | 12757.13 | 12757.13 | 105.5 | 1165.55 | 0 | 1271.05 | 280 | 21.18
NHT-009982 - Background Research | 25-PC-43511 | Completed |  |  | 339169 | 169454.68 | 231922.21 | 20200.43 | 281298.45 | 0 | 301498.88 | 2777 | 4639.47
NHT-009985 - Final Report | 25-PC-43511 | Completed |  |  | 361791 | 180757.46 | 247391.64 | 21547.81 | 300061.32 | 0 | 321609.13 | 3277 | 3874.51
NHT-009991 - Curation | 25-PC-43511 | Completed |  |  | 325240 | 162495.56 | 222397.71 | 19370.84 | 269746.18 | 0 | 289117.02 | 2558 | 4543.49
NHT-009992 - Testing | 25-PC-43566 | In progress |  |  | 53787 | 34800.59 | 34800.59 | 5111.87 | 43350.95 | 0 | 48462.82 | 0 | 653.88
NHT-009999 - Curation | 25-PC-43566 | Completed |  |  | 15786 | 10213.41 | 10213.41 | 2162.04 | 18335.1 | 0 | 20497.14 | 0 | 305.12
NHT-010002 - Draft Report | 25-PC-43566 | Completed |  |  | 7610 | 4923.67 | 4923.67 | 1783.06 | 15121.18 | 0 | 16904.24 | 0 | 262.56
NHT-010003 - Final Report | 25-PC-43566 | Completed |  |  | 37017 | 23949.73 | 23949.73 | 4746.12 | 40249.28 | 0 | 44995.4 | 0 | 586.9
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43566 | In progress |  |  | 0 | 0 | 0 | 0 | 598.43 | 0 | 598.43 | 0 | 7.5
NHT-010017 - Data Recovery Excavation | 25-PC-43590 | Completed |  |  | 24800 | 14642.64 | 16619.52 | 1444.95 | 9932.64 | 0 | 11377.59 | 218 | 171.8
NHT-010023 - Site Recordation | 25-PC-43621 | In progress |  |  | 33781 | 24298.74 | 24298.74 | 4101.28 | 18770.87 | 0 | 22872.15 | 0 | 368.23
NHT-010025 - Reporting | 25-PC-43621 | In progress |  |  | 19019 | 13680.3 | 13680.3 | 2698.37 | 12350 | 0 | 15048.37 | 0 | 286.1
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43621 | In progress |  |  | 0 | 0 | 0 | 0 | 66.37 | 0 | 66.37 | 0 | 1
NHT-010028 - Draft Report | 25-PC-43639 | Completed |  |  | 14974 | 10001.09 | 10001.09 | 5575.33 | 22918.49 | 0 | 28493.82 | 99 | 374.24
NHT-010034 - Reporting | 25-PC-43639 | Completed |  |  | 122026 | 81501.21 | 81501.21 | 13902.02 | 57146.93 | 0 | 71048.95 | 1068 | 968.22
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43639 | Completed |  |  | 0 | 0 | 0 | 0 | 1376.14 | 0 | 1376.14 | 0 | 23.5
NHT-010039 - Final Report | 25-PC-43653 | Completed |  |  | 31976 | 26949.24 | 26949.24 | 5143.34 | 24996.28 | 0 | 30139.62 | 0 | 414.24
NHT-010042 - Monitoring | 25-PC-43653 | Completed |  |  | 11335 | 9552.97 | 9552.97 | 4878.39 | 23708.63 | 0 | 28587.02 | 0 | 405.58
NHT-010049 - Testing | 25-PC-43653 | Completed |  |  | 49489 | 41709.63 | 41709.63 | 7323.44 | 35591.35 | 0 | 42914.79 | 0 | 564.17
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43653 | Completed |  |  | 0 | 0 | 0 | 0 | 1603.6 | 0 | 1603.6 | 0 | 31.5
NHT-010051 - Survey | 25-PC-43752 | Completed |  |  | 20671 | 11292.72 | 14914.03 | 3489.89 | 15898.36 | 0 | 19388.25 | 0 | 272.65
NHT-010058 - Site Recordation | 25-PC-43752 | Completed |  |  | 6009 | 3282.51 | 4335.14 | 1014.42 | 4621.26 | 0 | 5635.68 | 0 | 70.32
NHT-010064 - Data Recovery Excavation | 25-PC-43752 | Completed |  |  | 23220 | 12684.93 | 16752.7 | 3920.13 | 17858.37 | 0 | 21778.5 | 0 | 307.94
NHT-010067 - Reporting | 25-PC-43771 | Completed |  |  | 31500 | 20147.4 | 20147.4 | 918.89 | 9864.01 | 0 | 10782.9 | 366 | 242.16
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43771 | Completed |  |  | 0 | 0 | 0 | 0 | 561.48 | 0 | 561.48 | 0 | 12
NHT-010074 - Desktop Review | 25-PC-43844 | Completed |  |  | 3225 | 1659.24 | 2156.63 | 642.55 | 3502.94 | 0 | 4145.49 | 19 | 43.05
NHT-010080 - Final Report | 25-PC-43844 | Completed |  |  | 5634 | 2898.9 | 3767.91 | 1322.21 | 7208.18 | 0 | 8530.39 | 36 | 104.17
NHT-010085 - Testing | 25-PC-43844 | In progress |  |  | 36923 | 18999.04 | 24694.39 | 2189.93 | 11938.64 | 0 | 14128.57 | 206 | 178.08
NHT-010089 - Fieldwork | 25-PC-43844 | Completed |  |  | 4918 | 2530.42 | 3288.97 | 810.12 | 4416.46 | 0 | 5226.58 | 29 | 59.45
NHT-010090 - Data Recovery Excavation | 25-PC-43853 | Completed |  |  | 94914 | 67512.45 | 67512.45 | 5254.7 | 42736.6 | 0 | 47991.3 | 745 | 720.28
NHT-010094 - Background Research | 25-PC-43853 | Completed |  |  | 67886 | 48287.19 | 48287.19 | 5463.13 | 44431.77 | 0 | 49894.9 | 686 | 748.28
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43853 | Completed |  |  | 0 | 0 | 0 | 0 | 1353.01 | 0 | 1353.01 | 0 | 19.75
NHT-010102 - Monitoring | 25-PC-43859 | Completed |  |  | 662633 | 506649.1 | 506649.1 | 47912.92 | 338481.61 | 0 | 386394.53 | 7506 | 5646.38
NHT-010104 - Survey | 25-PC-43859 | Completed |  |  | 962655 | 736046.23 | 736046.23 | 69606.61 | 491737.01 | 0 | 561343.62 | 11411 | 8906.02
NHT-010106 - Prefield | 25-PC-43859 | Completed |  |  | 177512 | 135725.55 | 135725.55 | 12835.33 | 90675.38 | 0 | 103510.71 | 2427 | 1439.06
NHT-010109 - Fieldwork | 25-PC-43863 | In progress |  |  | 127385 | 105220.39 | 105220.39 | 2535.97 | 19786.1 | 0 | 22322.07 | 0 | 245.6
NHT-010112 - Data Recovery Excavation | 25-PC-43863 | In progress |  |  | 84234 | 69577.21 | 69577.21 | 2320.58 | 18105.6 | 0 | 20426.18 | 0 | 259.88
NHT-010113 - Final Report | 25-PC-43863 | In progress |  |  | 333581 | 275537.6 | 275537.6 | 4597.53 | 35870.72 | 0 | 40468.25 | 0 | 441.04
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43863 | In progress |  |  | 0 | 0 | 0 | 0 | 447.95 | 0 | 447.95 | 0 | 8.25
NHT-010117 - Lab Analysis | 25-PC-43932 | Completed |  |  | 2757 | 1392.69 | 1893.49 | 232.99 | 1825.37 | 0 | 2058.36 | 27 | 37.03
NHT-010120 - Fieldwork | 25-PC-43932 | Completed |  |  | 1050 | 530.16 | 720.81 | 43.52 | 340.98 | 0 | 384.5 | 12 | 7.28
NHT-010126 - Curation | 25-PC-43932 | Completed |  |  | 18645 | 9418.63 | 12805.52 | 749.05 | 5868.61 | 0 | 6617.66 | 204 | 116.59
NHT-010133 - GIS & Mapping | 25-PC-43932 | Completed |  |  | 11264 | 5690.14 | 7736.28 | 452.61 | 3546.05 | 0 | 3998.66 | 108 | 72.64
NHT-010136 - Final Report | 25-PC-43932 | Completed |  |  | 2184 | 1103.38 | 1500.15 | 202.57 | 1587.04 | 0 | 1789.61 | 23 | 33.07
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43932 | Completed |  |  | 0 | 0 | 0 | 0 | 25.02 | 0 | 25.02 | 0 | 0.5
NHT-010145 - Lab Analysis | 25-PC-43944 | In progress |  |  | 25573 | 20670.47 | 20670.47 | 1348.56 | 5902.92 | 0 | 7251.48 | 424 | 126.11
NHT-010146 - Background Research | 25-PC-43944 | In progress |  |  | 3975 | 3212.97 | 3212.97 | 312.88 | 1369.53 | 0 | 1682.41 | 67 | 32.48
NHT-010149 - Survey | 25-PC-43944 | In progress |  |  | 1114 | 900.52 | 900.52 | 34.8 | 152.31 | 0 | 187.11 | 19 | 3.64
NHT-010154 - Site Recordation | 25-PC-43944 | In progress |  |  | 32618 | 26364.93 | 26364.93 | 1315.67 | 5758.9 | 0 | 7074.57 | 467 | 118.64
NHT-010155 - Fieldwork | 25-PC-43944 | In progress |  |  | 11520 | 9311.95 | 9311.95 | 878.2 | 3844.03 | 0 | 4722.23 | 165 | 88.52
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43944 | In progress |  |  | 0 | 0 | 0 | 0 | 693.95 | 0 | 693.95 | 0 | 15.75
NHT-010162 - Project Management | 25-PC-43966 | Completed |  |  | 47800 | 30211.65 | 34547.14 | 5552.7 | 21800.51 | 0 | 27353.21 | 217 | 251.05
NHT-010169 - Site Recordation | 25-PC-43993 | Completed |  |  | 4151 | 2926.21 | 2926.21 | 1027.33 | 3751.74 | 0 | 4779.07 | 19 | 45.27
NHT-010172 - Draft Report | 25-PC-43993 | Completed |  |  | 15731 | 11090.4 | 11090.4 | 556.54 | 2032.43 | 0 | 2588.97 | 78 | 35.61
NHT-010178 - Background Research | 25-PC-43993 | Completed |  |  | 2657 | 1873.44 | 1873.44 | 131.16 | 478.98 | 0 | 610.14 | 14 | 7.93
NHT-010182 - Project Management | 25-PC-43993 | Completed |  |  | 4295 | 3027.97 | 3027.97 | 1162.1 | 4243.96 | 0 | 5406.06 | 20 | 47.85
NHT-010189 - Testing | 25-PC-43993 | Completed |  |  | 1066 | 751.48 | 751.48 | 176.04 | 642.87 | 0 | 818.91 | 5 | 7.24
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-43993 | Completed |  |  | 0 | 0 | 0 | 0 | 198.6 | 0 | 198.6 | 0 | 4
NHT-010195 - Desktop Review | 25-PC-44046 | Completed |  |  | 320300 | 220526.55 | 220526.55 | 46752.14 | 228580.14 | 0 | 275332.28 | 0 | 3025.95
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-44046 | Completed |  |  | 0 | 0 | 0 | 0 | 1307.63 | 0 | 1307.63 | 0 | 16.5
NHT-010201 - Fieldwork | 25-PC-44140 | In progress |  |  | 53282 | 35651.3 | 35651.3 | 2583.76 | 18090.42 | 0 | 20674.18 | 372 | 278.22
NHT-010202 - Curation | 25-PC-44140 | In progress |  |  | 19927 | 13333.23 | 13333.23 | 2969.74 | 20792.84 | 0 | 23762.58 | 175 | 319.12
NHT-010205 - Monitoring | 25-PC-44140 | Completed |  |  | 18930 | 12666.15 | 12666.15 | 2566.31 | 17968.21 | 0 | 20534.52 | 167 | 316.13
NHT-010206 - Survey | 25-PC-44140 | In progress |  |  | 57761 | 38647.41 | 38647.41 | 4084.52 | 28598.12 | 0 | 32682.64 | 479 | 433.78
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-44140 | In progress |  |  | 0 | 0 | 0 | 0 | 2381.53 | 0 | 2381.53 | 0 | 39
NHT-010218 - Background Research | 25-PC-44186 | Completed |  |  | 131460 | 82780.18 | 82780.18 | 4054.96 | 49837.14 | 0 | 53892.1 | 2307 | 1068.42
NHT-010221 - Data Recovery Excavation | 25-PC-44186 | Completed |  |  | 204479 | 128760.73 | 128760.73 | 6225.17 | 76510.05 | 0 | 82735.22 | 3352 | 1693.23
NHT-010223 - Desktop Review | 25-PC-44186 | Completed |  |  | 201061 | 126607.99 | 126607.99 | 5872.69 | 72177.87 | 0 | 78050.56 | 3437 | 1543.58
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-44186 | Completed |  |  | 0 | 0 | 0 | 0 | 693.06 | 0 | 693.06 | 0 | 16.25
NHT-010231 - Lab Analysis | 25-PC-44198 | Completed |  |  | 14260 | 6013.84 | 8223.17 | 1130.71 | 14205.48 | 0 | 15336.19 | 0 | 149.68
NHT-010236 - Final Report | 25-PC-44198 | Completed |  |  | 8003 | 3375 | 4614.88 | 702 | 8819.48 | 0 | 9521.48 | 0 | 83.57
NHT-010243 - Prefield | 25-PC-44198 | Completed |  |  | 8837 | 3726.92 | 5096.09 | 356.62 | 4480.3 | 0 | 4836.92 | 0 | 48.64
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-44198 | Completed |  |  | 0 | 0 | 0 | 0 | 1581.53 | 0 | 1581.53 | 0 | 10.5
NHT-010250 - GIS & Mapping | 25-PC-44241 | Completed |  |  | 62584 | 41049.17 | 41049.17 | 9818.96 | 43544.96 | 0 | 53363.92 | 0 | 517.12
NHT-010257 - Monitoring | 25-PC-44241 | Completed |  |  | 154658 | 101439.83 | 101439.83 | 24264.41 | 107607.37 | 0 | 131871.78 | 0 | 1588.19
NHT-010258 - Prefield | 25-PC-44241 | Completed |  |  | 55259 | 36244.66 | 36244.66 | 8669.72 | 38448.34 | 0 | 47118.06 | 0 | 575.18
NHT-010260 - Final Report | 25-PC-44241 | Completed |  |  | 76199 | 49978.67 | 49978.67 | 11954.9 | 53017.37 | 0 | 64972.27 | 0 | 870.83
NHT-010267 - Lab Analysis | 25-PC-44312 | Completed |  |  | 59278 | 43391.66 | 43391.66 | 9790.59 | 37897.42 | 0 | 47688.01 | 196 | 498.61
NHT-010269 - Background Research | 25-PC-44312 | Completed |  |  | 37722 | 27612.34 | 27612.34 | 6175.93 | 23905.78 | 0 | 30081.71 | 126 | 289.33
OVHD-Non-Posting - Overhead Non-Posting | 25-PC-44312 | In progress |  |  | 0 | 0 | 0 | 0 | 1272.45 | 0 | 1272.45 | 0 | 15.25
NHT-010274 - Site Recordation | 26-PC-30013 | Completed |  |  | 62300 | 43902.81 | 43902.81 | 1556.08 | 7580.31 | 0 | 9136.39 | 685 | 123.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30013 | Completed |  |  | 0 | 0 | 0 | 0 | 410.1 | 0 | 410.1 | 0 | 6
NHT-010278 - Monitoring | 26-PC-30057 | In progress |  |  | 197500 | 144017 | 144017 | 12956.55 | 55295.94 | 0 | 68252.49 | 1736 | 923
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30057 | In progress |  |  | 0 | 0 | 0 | 0 | 665.35 | 0 | 665.35 | 0 | 9.25
NHT-010288 - Reporting | 26-PC-30065 | In progress |  |  | 16666 | 13172.78 | 13172.78 | 317.76 | 3884.08 | 0 | 4201.84 | 116 | 47
NHT-010290 - Curation | 26-PC-30065 | In progress |  |  | 66150 | 52285.15 | 52285.15 | 461.43 | 5640.18 | 0 | 6101.61 | 427 | 68.25
NHT-010291 - Monitoring | 26-PC-30065 | In progress |  |  | 16348 | 12921.1 | 12921.1 | 69.3 | 847.06 | 0 | 916.36 | 111 | 10.25
NHT-010295 - Testing | 26-PC-30065 | In progress |  |  | 32936 | 26032.81 | 26032.81 | 672.71 | 8222.68 | 0 | 8895.39 | 225 | 99.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30065 | In progress |  |  | 0 | 0 | 0 | 0 | 723.1 | 0 | 723.1 | 0 | 8.75
NHT-010303 - Final Report | 26-PC-30094 | In progress |  |  | 57005 | 47615.94 | 47615.94 | 126.18 | 1976.82 | 0 | 2103 | 857 | 46
NHT-010306 - Survey | 26-PC-30094 | In progress |  |  | 41395 | 34577.58 | 34577.58 | 69.81 | 1093.65 | 0 | 1163.46 | 624 | 26.25
NHT-010311 - Reporting | 26-PC-30115 | Completed |  |  | 13196 | 11612.6 | 11612.6 | 1374.45 | 10372.98 | 0 | 11747.43 | 165 | 221.79
NHT-010318 - Desktop Review | 26-PC-30115 | Completed |  |  | 5404 | 4755.4 | 4755.4 | 562.84 | 4247.77 | 0 | 4810.61 | 91 | 80.33
NHT-010323 - Survey | 26-PC-30123 | In progress |  |  | 143184 | 108719.63 | 108719.63 | 1319.74 | 12181.39 | 0 | 13501.13 | 1139 | 197.75
NHT-010329 - Prefield | 26-PC-30123 | In progress |  |  | 64245 | 48781.51 | 48781.51 | 1204.74 | 11119.94 | 0 | 12324.68 | 761 | 180
NHT-010331 - Monitoring | 26-PC-30123 | In progress |  |  | 69771 | 52976.82 | 52976.82 | 1702.78 | 15716.88 | 0 | 17419.66 | 714 | 228.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30123 | In progress |  |  | 0 | 0 | 0 | 0 | 1725.33 | 0 | 1725.33 | 0 | 25.25
NHT-010340 - GIS & Mapping | 26-PC-30139 | In progress |  |  | 105833 | 87735.74 | 87735.74 | 1595.56 | 7747.5 | 0 | 9343.06 | 1003 | 93.75
NHT-010345 - Fieldwork | 26-PC-30139 | In progress |  |  | 133767 | 110892.66 | 110892.66 | 1025.41 | 4979.06 | 0 | 6004.47 | 1192 | 60.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30139 | In progress |  |  | 0 | 0 | 0 | 0 | 537.16 | 0 | 537.16 | 0 | 6.5
NHT-010353 - GIS & Mapping | 26-PC-30180 | Completed |  |  | 72772 | 50191.04 | 50191.04 | 1813.83 | 12138.5 | 0 | 13952.33 | 1302 | 315
NHT-010354 - Fieldwork | 26-PC-30180 | Completed |  |  | 42928 | 29607.25 | 29607.25 | 857.18 | 5736.43 | 0 | 6593.61 | 578 | 148.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30180 | Completed |  |  | 0 | 0 | 0 | 0 | 159.59 | 0 | 159.59 | 0 | 4.25
NHT-010366 - Draft Report | 26-PC-30185 | Completed |  |  | 48717 | 38724.18 | 38724.18 | 231.84 | 2234.58 | 0 | 2466.42 | 661 | 41.25
NHT-010373 - Data Recovery Excavation | 26-PC-30185 | Completed |  |  | 2342 | 1861.74 | 1861.74 | 0 | 0 | 0 | 0 | 23 | 0
NHT-010375 - Prefield | 26-PC-30185 | Completed |  |  | 546 | 434.41 | 434.41 | 0 | 0 | 0 | 0 | 7 | 0
NHT-010381 - Agency Consultation | 26-PC-30185 | Completed |  |  | 390 | 310.29 | 310.29 | 0 | 0 | 0 | 0 | 5 | 0
NHT-010388 - Reporting | 26-PC-30185 | Completed |  |  | 1405 | 1117.04 | 1117.04 | 0 | 0 | 0 | 0 | 15 | 0
NHT-010391 - GIS & Mapping | 26-PC-30203 | In progress |  |  | 58731 | 44623.47 | 44623.47 | 541.77 | 2761.68 | 0 | 3303.45 | 1457 | 74.25
NHT-010394 - Agency Consultation | 26-PC-30203 | In progress |  |  | 76069 | 57797.57 | 57797.57 | 544.99 | 2778.15 | 0 | 3323.14 | 1468 | 74.5
NHT-010400 - Draft Report | 26-PC-30211 | Completed |  |  | 341467 | 183110.42 | 231203.11 | 0 | 0 | 0 | 0 | 4663 | 0
NHT-010403 - Background Research | 26-PC-30211 | Completed |  |  | 205229 | 110053.47 | 138958.26 | 0 | 0 | 0 | 0 | 3094 | 0
NHT-010405 - Project Management | 26-PC-30211 | Completed |  |  | 189404 | 101567.08 | 128242.97 | 0 | 0 | 0 | 0 | 2748 | 0
NHT-010408 - GIS & Mapping | 26-PC-30273 | Completed |  |  | 2302 | 1596.27 | 1596.27 | 8.22 | 106.48 | 0 | 114.7 | 0 | 2.75
NHT-010412 - Prefield | 26-PC-30273 | Completed |  |  | 68339 | 47379.4 | 47379.4 | 291.32 | 3775.2 | 0 | 4066.52 | 0 | 97.5
NHT-010415 - Background Research | 26-PC-30273 | Completed |  |  | 6559 | 4547.09 | 4547.09 | 20.92 | 271.04 | 0 | 291.96 | 0 | 7
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30273 | Completed |  |  | 0 | 0 | 0 | 0 | 309.76 | 0 | 309.76 | 0 | 8
NHT-010421 - GIS & Mapping | 26-PC-30287 | In progress |  |  | 3768 | 2310.71 | 2310.71 | 134.66 | 1349.33 | 0 | 1483.99 | 0 | 33.75
NHT-010422 - Fieldwork | 26-PC-30287 | In progress |  |  | 6332 | 3882.61 | 3882.61 | 142.65 | 1429.29 | 0 | 1571.94 | 0 | 35.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30287 | In progress |  |  | 0 | 0 | 0 | 0 | 59.97 | 0 | 59.97 | 0 | 1.5
NHT-010429 - Desktop Review | 26-PC-30329 | In progress |  |  | 74721 | 48501.49 | 48501.49 | 2470.27 | 27978.7 | 0 | 30448.97 | 778 | 568.25
NHT-010434 - Lab Analysis | 26-PC-30329 | In progress |  |  | 345212 | 224077.12 | 224077.12 | 1907.76 | 21607.57 | 0 | 23515.33 | 3884 | 496.5
NHT-010439 - Curation | 26-PC-30329 | In progress |  |  | 63667 | 41326.15 | 41326.15 | 1960.94 | 22209.91 | 0 | 24170.85 | 650 | 472
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30329 | In progress |  |  | 0 | 0 | 0 | 0 | 1101.92 | 0 | 1101.92 | 0 | 25.5
NHT-010445 - Project Management | 26-PC-30338 | Completed |  |  | 1364 | 742.8 | 965.2 | 0 | 0 | 0 | 0 | 17 | 0
NHT-010449 - Testing | 26-PC-30338 | Completed |  |  | 20743 | 11293.24 | 14674.66 | 44.11 | 216.89 | 0 | 261 | 245 | 5.75
NHT-010454 - Fieldwork | 26-PC-30338 | Completed |  |  | 98973 | 53885.19 | 70019.47 | 74.79 | 367.77 | 0 | 442.56 | 1297 | 9.75
NHT-010461 - Desktop Review | 26-PC-30338 | Completed |  |  | 147220 | 80153.15 | 104152.58 | 65.21 | 320.62 | 0 | 385.83 | 1855 | 8.5
NHT-010468 - GIS & Mapping | 26-PC-30349 | In progress |  |  | 25905 | 14814.96 | 14814.96 | 171.44 | 989.06 | 0 | 1160.5 | 358 | 25.75
NHT-010470 - Fieldwork | 26-PC-30349 | In progress |  |  | 29869 | 17082.08 | 17082.08 | 1028.58 | 5933.94 | 0 | 6962.52 | 460 | 108.5
NHT-010472 - Testing | 26-PC-30349 | In progress |  |  | 28408 | 16246.79 | 16246.79 | 572.51 | 3302.87 | 0 | 3875.38 | 425 | 78
NHT-010474 - Draft Report | 26-PC-30349 | In progress |  |  | 100018 | 57200.15 | 57200.15 | 838.88 | 4839.61 | 0 | 5678.49 | 1194 | 101.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30349 | In progress |  |  | 0 | 0 | 0 | 0 | -32.21 | 0 | -32.21 | 0 | 1.5
NHT-010478 - Site Recordation | 26-PC-30351 | In progress |  |  | 78113 | 52147.95 | 52147.95 | 3983.41 | 17679.2 | 0 | 21662.61 | 917 | 265.75
NHT-010481 - Agency Consultation | 26-PC-30351 | In progress |  |  | 83074 | 55460.16 | 55460.16 | 4317.36 | 19161.33 | 0 | 23478.69 | 909 | 387.25
NHT-010487 - Data Recovery Excavation | 26-PC-30351 | In progress |  |  | 148986 | 99463.68 | 99463.68 | 4061.32 | 18024.99 | 0 | 22086.31 | 1565 | 387.5
NHT-010492 - Survey | 26-PC-30351 | In progress |  |  | 83627 | 55829.09 | 55829.09 | 3851.21 | 17092.48 | 0 | 20943.69 | 832 | 285.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30351 | In progress |  |  | 0 | 0 | 0 | 0 | 425.94 | 0 | 425.94 | 0 | 6.5
NHT-010500 - Background Research | 26-PC-30396 | In progress |  |  | 3595 | 2739.72 | 2739.72 | 0 | 0 | 0 | 0 | 39 | 0
NHT-010505 - Testing | 26-PC-30396 | In progress |  |  | 13158 | 10028.09 | 10028.09 | 0 | 0 | 0 | 0 | 142 | 0
NHT-010512 - Agency Consultation | 26-PC-30396 | In progress |  |  | 1901 | 1448.59 | 1448.59 | 0 | 0 | 0 | 0 | 20 | 0
NHT-010516 - Data Recovery Excavation | 26-PC-30396 | In progress |  |  | 12646 | 9637.33 | 9637.33 | 0 | 0 | 0 | 0 | 109 | 0
NHT-010517 - GIS & Mapping | 26-PC-30402 | Completed |  |  | 33086 | 19789.59 | 25987.54 | 0 | 0 | 0 | 0 | 248 | 0
NHT-010520 - Project Management | 26-PC-30402 | Completed |  |  | 34231 | 20474.23 | 26886.6 | 0 | 0 | 0 | 0 | 255 | 0
NHT-010522 - Lab Analysis | 26-PC-30402 | Completed |  |  | 55429 | 33153.44 | 43536.85 | 0 | 0 | 0 | 0 | 415 | 0
NHT-010527 - Final Report | 26-PC-30402 | Completed |  |  | 28254 | 16899.68 | 22192.53 | 0 | 0 | 0 | 0 | 224 | 0
NHT-010529 - Site Recordation | 26-PC-30425 | Completed |  |  | 19182 | 13891.62 | 13891.62 | 2171.12 | 10987.19 | 0 | 13158.31 | 265 | 201.08
NHT-010533 - Curation | 26-PC-30425 | Completed |  |  | 11862 | 8590.79 | 8590.79 | 1342.65 | 6794.64 | 0 | 8137.29 | 169 | 143.45
NHT-010537 - Agency Consultation | 26-PC-30425 | Completed |  |  | 6388 | 4626.42 | 4626.42 | 723.06 | 3659.14 | 0 | 4382.2 | 71 | 72.82
NHT-010540 - Testing | 26-PC-30425 | Completed |  |  | 20668 | 14967.19 | 14967.19 | 2339.23 | 11837.88 | 0 | 14177.11 | 324 | 263.8
NHT-010542 - Background Research | 26-PC-30432 | Completed |  |  | 7764 | 5320.93 | 5320.93 | 683.26 | 4739.42 | 0 | 5422.68 | 69 | 100.73
NHT-010548 - Agency Consultation | 26-PC-30432 | Completed |  |  | 7209 | 4940.1 | 4940.1 | 634.36 | 4400.21 | 0 | 5034.57 | 51 | 71.84
NHT-010554 - GIS & Mapping | 26-PC-30432 | Completed |  |  | 12814 | 8781.21 | 8781.21 | 1127.59 | 7821.54 | 0 | 8949.13 | 97 | 156.52
NHT-010557 - Data Recovery Excavation | 26-PC-30432 | Completed |  |  | 43201 | 29606.06 | 29606.06 | 3801.69 | 26370.5 | 0 | 30172.19 | 278 | 559.82
NHT-010559 - Reporting | 26-PC-30432 | Completed |  |  | 22112 | 15153.13 | 15153.13 | 1945.81 | 13497.09 | 0 | 15442.9 | 164 | 248.49
NHT-010561 - Final Report | 26-PC-30457 | Completed |  |  | 469978 | 357277.17 | 357277.17 | 8433.85 | 43318.42 | 0 | 51752.27 | 3995 | 657.75
NHT-010568 - Reporting | 26-PC-30457 | Completed |  |  | 249822 | 189914.79 | 189914.79 | 6292.69 | 32320.91 | 0 | 38613.6 | 2213 | 467.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30457 | Completed |  |  | 0 | 0 | 0 | 0 | 1103.34 | 0 | 1103.34 | 0 | 12.75
NHT-010579 - GIS & Mapping | 26-PC-30480 | Completed |  |  | 47568 | 28720.21 | 35101.08 | 8666.97 | 35779.02 | 0 | 44445.99 | 489 | 808.39
NHT-010585 - Background Research | 26-PC-30480 | Completed |  |  | 27144 | 16388.54 | 20029.63 | 4945.61 | 20416.49 | 0 | 25362.1 | 267 | 362.46
NHT-010588 - Fieldwork | 26-PC-30480 | Completed |  |  | 97386 | 58798.74 | 71862.27 | 17743.83 | 73250.2 | 0 | 90994.03 | 667 | 1318.72
NHT-010590 - Desktop Review | 26-PC-30480 | Completed |  |  | 22202 | 13404.76 | 16382.94 | 4045.19 | 16699.36 | 0 | 20744.55 | 144 | 341.49
NHT-010597 - Project Management | 26-PC-30501 | In progress |  |  | 4603 | 2939.47 | 3298.25 | 278.16 | 2469.4 | 0 | 2747.56 | 46 | 43.75
NHT-010601 - Background Research | 26-PC-30501 | In progress |  |  | 6087 | 3886.61 | 4360.99 | 568.17 | 5044 | 0 | 5612.17 | 56 | 107.75
NHT-010606 - Survey | 26-PC-30501 | Completed |  |  | 2181 | 1392.39 | 1562.34 | 293.2 | 2602.87 | 0 | 2896.07 | 27 | 61.5
NHT-010609 - Monitoring | 26-PC-30501 | In progress |  |  | 4051 | 2586.86 | 2902.6 | 331.02 | 2938.69 | 0 | 3269.71 | 38 | 63
NHT-010613 - Reporting | 26-PC-30501 | In progress |  |  | 2978 | 1901.87 | 2134.01 | 300.73 | 2669.74 | 0 | 2970.47 | 32 | 51
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30501 | In progress |  |  | 0 | 0 | 0 | 0 | 578.34 | 0 | 578.34 | 0 | 12.75
NHT-010621 - GIS & Mapping | 26-PC-30528 | In progress |  |  | 68363 | 44819.1 | 44819.1 | 2871.14 | 19835.68 | 0 | 22706.82 | 0 | 473.25
NHT-010627 - Curation | 26-PC-30528 | In progress |  |  | 44537 | 29198.14 | 29198.14 | 3440.21 | 23767.21 | 0 | 27207.42 | 0 | 554.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30528 | In progress |  |  | 0 | 0 | 0 | 0 | 576.57 | 0 | 576.57 | 0 | 13.5
NHT-010632 - Survey | 26-PC-30554 | In progress |  |  | 83241 | 47480.79 | 47480.79 | 590.43 | 2862.36 | 0 | 3452.79 | 0 | 66.25
NHT-010633 - Agency Consultation | 26-PC-30554 | In progress |  |  | 56559 | 32261.13 | 32261.13 | 1036.11 | 5023.05 | 0 | 6059.16 | 0 | 131.5
NHT-010639 - Final Report | 26-PC-30577 | On hold |  |  | 5754 | 3592 | 4485.34 | 0 | 0 | 0 | 0 | 51 | 0
NHT-010645 - Data Recovery Excavation | 26-PC-30577 | On hold |  |  | 16435 | 10258.4 | 12809.71 | 0 | 0 | 0 | 0 | 163 | 0
NHT-010648 - Background Research | 26-PC-30577 | On hold |  |  | 4739 | 2958.44 | 3694.21 | 0 | 0 | 0 | 0 | 45 | 0
NHT-010652 - Reporting | 26-PC-30577 | On hold |  |  | 13825 | 8630.03 | 10776.36 | 0 | 0 | 0 | 0 | 112 | 0
NHT-010659 - Lab Analysis | 26-PC-30577 | On hold |  |  | 6047 | 3774.86 | 4713.69 | 0 | 0 | 0 | 0 | 49 | 0
NHT-010660 - Testing | 26-PC-30588 | In progress |  |  | 48503 | 37696.15 | 37696.15 | 342.36 | 3419.84 | 0 | 3762.2 | 722 | 71.5
NHT-010667 - Project Management | 26-PC-30588 | In progress |  |  | 48497 | 37692.25 | 37692.25 | 491.99 | 4914.53 | 0 | 5406.52 | 946 | 102.75
NHT-010669 - Fieldwork | 26-PC-30589 | Completed |  |  | 143200 | 108502.64 | 108502.64 | 28210.69 | 112842.74 | 0 | 141053.43 | 0 | 2161.7
NHT-010673 - Draft Report | 26-PC-30602 | In progress |  |  | 60748 | 40525.86 | 43791.61 | 2073.3 | 16139.31 | 0 | 18212.61 | 513 | 267.75
NHT-010675 - Site Recordation | 26-PC-30602 | In progress |  |  | 151152 | 100835.59 | 108961.37 | 1776.31 | 13827.39 | 0 | 15603.7 | 1242 | 226.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30602 | In progress |  |  | 0 | 0 | 0 | 0 | 1501.21 | 0 | 1501.21 | 0 | 21.25
NHT-010683 - Final Report | 26-PC-30634 | Completed |  |  | 21200 | 11167.32 | 13865.34 | 1369.9 | 16655.04 | 0 | 18024.94 | 159 | 294.02
NHT-010688 - Agency Consultation | 26-PC-30754 | Completed |  |  | 7087 | 4939.25 | 4939.25 | 177.78 | 1222.1 | 0 | 1399.88 | 79 | 27.5
NHT-010693 - Reporting | 26-PC-30754 | Completed |  |  | 38593 | 26895.56 | 26895.56 | 282.99 | 1945.28 | 0 | 2228.27 | 583 | 44.75
NHT-010700 - Prefield | 26-PC-30754 | Completed |  |  | 938 | 653.48 | 653.48 | 0 | 0 | 0 | 0 | 15 | 0
NHT-010707 - Final Report | 26-PC-30754 | Completed |  |  | 106682 | 74346.48 | 74346.48 | 653.35 | 4491.13 | 0 | 5144.48 | 1641 | 102.25
NHT-010710 - Reporting | 26-PC-30781 | Completed |  |  | 76486 | 47903.42 | 47903.42 | 7252.34 | 48109.06 | 0 | 55361.4 | 626 | 1069.19
NHT-010711 - Desktop Review | 26-PC-30781 | Completed |  |  | 18745 | 11739.98 | 11739.98 | 1777.38 | 11790.38 | 0 | 13567.76 | 142 | 217.62
NHT-010717 - Curation | 26-PC-30781 | Completed |  |  | 18469 | 11566.91 | 11566.91 | 1751.18 | 11616.57 | 0 | 13367.75 | 165 | 193.52
NHT-010723 - Desktop Review | 26-PC-30815 | In progress |  |  | 133864 | 100813.14 | 100813.14 | 1629.85 | 18006.91 | 0 | 19636.76 | 1141 | 303.75
NHT-010730 - Data Recovery Excavation | 26-PC-30815 | In progress |  |  | 102136 | 76918.46 | 76918.46 | 934.84 | 10328.29 | 0 | 11263.13 | 773 | 174.25
NHT-010737 - Data Recovery Excavation | 26-PC-30871 | Completed |  |  | 110139 | 74872.29 | 74872.29 | 11265.12 | 58272.72 | 0 | 69537.84 | 997 | 1112.53
NHT-010742 - Testing | 26-PC-30871 | Completed |  |  | 55100 | 37457.17 | 37457.17 | 5635.73 | 29152.72 | 0 | 34788.45 | 613 | 608.07
NHT-010749 - Site Recordation | 26-PC-30871 | Completed |  |  | 40461 | 27505.4 | 27505.4 | 4138.41 | 21407.31 | 0 | 25545.72 | 472 | 383.98
NHT-010752 - Testing | 26-PC-30896 | Completed |  |  | 60983 | 42255.32 | 42255.32 | 6703.53 | 33679.18 | 0 | 40382.71 | 0 | 569.75
NHT-010754 - Desktop Review | 26-PC-30896 | Completed |  |  | 18844 | 13056.75 | 13056.75 | 2071.37 | 10406.75 | 0 | 12478.12 | 0 | 200.73
NHT-010761 - Survey | 26-PC-30896 | Completed |  |  | 78273 | 54235.42 | 54235.42 | 8604.09 | 43227.8 | 0 | 51831.89 | 0 | 652.28
NHT-010762 - Monitoring | 26-PC-30917 | Completed |  |  | 140186 | 90518.29 | 90518.29 | 16560.95 | 73444.22 | 0 | 90005.17 | 972 | 1306.29
NHT-010766 - Project Management | 26-PC-30917 | Completed |  |  | 69614 | 44949.57 | 44949.57 | 8223.84 | 36470.94 | 0 | 44694.78 | 383 | 747.94
NHT-010771 - Fieldwork | 26-PC-30945 | In progress |  |  | 32006 | 21444.33 | 21444.33 | 981.3 | 7031.29 | 0 | 8012.59 | 0 | 144.25
NHT-010775 - Site Recordation | 26-PC-30945 | In progress |  |  | 27236 | 18248.4 | 18248.4 | 1502.95 | 10769.05 | 0 | 12272 | 0 | 219.5
NHT-010780 - Survey | 26-PC-30945 | In progress |  |  | 37457 | 25096.28 | 25096.28 | 1130.33 | 8099.14 | 0 | 9229.47 | 0 | 166.25
NHT-010781 - Draft Report | 26-PC-30945 | Completed |  |  | 13523 | 9060.27 | 9060.27 | 1489.92 | 10675.69 | 0 | 12165.61 | 0 | 217.5
NHT-010787 - Monitoring | 26-PC-30945 | In progress |  |  | 69278 | 46415.72 | 46415.72 | 1630.11 | 11680.14 | 0 | 13310.25 | 0 | 234.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30945 | In progress |  |  | 0 | 0 | 0 | 0 | 1131.84 | 0 | 1131.84 | 0 | 23.25
NHT-010799 - Data Recovery Excavation | 26-PC-30967 | Completed |  |  | 30685 | 19266.98 | 19266.98 | 2051.23 | 14199.9 | 0 | 16251.13 | 258 | 289
NHT-010801 - Lab Analysis | 26-PC-30967 | Completed |  |  | 29908 | 18779.48 | 18779.48 | 2065.51 | 14298.71 | 0 | 16364.22 | 235 | 312
NHT-010807 - Reporting | 26-PC-30967 | Completed |  |  | 16346 | 10263.71 | 10263.71 | 2517.01 | 17424.3 | 0 | 19941.31 | 119 | 331.75
NHT-010810 - Monitoring | 26-PC-30967 | Completed |  |  | 37819 | 23746.28 | 23746.28 | 1609.64 | 11142.92 | 0 | 12752.56 | 338 | 236.75
NHT-010816 - Testing | 26-PC-30967 | Completed |  |  | 58642 | 36821.41 | 36821.41 | 3115.77 | 21569.35 | 0 | 24685.12 | 482 | 452.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-30967 | Completed |  |  | 0 | 0 | 0 | 0 | 1611.81 | 0 | 1611.81 | 0 | 31.75
NHT-010824 - Desktop Review | 26-PC-30985 | Completed |  |  | 15284 | 8357.05 | 9893.83 | 2241.55 | 10351.45 | 0 | 12593 | 128 | 233.6
NHT-010826 - Final Report | 26-PC-30985 | Completed |  |  | 31216 | 17068.35 | 20207.04 | 4578.13 | 21141.7 | 0 | 25719.83 | 248 | 409.66
NHT-010830 - Background Research | 26-PC-31002 | In progress |  |  | 211500 | 164758.5 | 164758.5 | 3835.57 | 18670.3 | 0 | 22505.87 | 1533 | 287.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31002 | In progress |  |  | 0 | 0 | 0 | 0 | 189.82 | 0 | 189.82 | 0 | 1.5
NHT-010841 - Data Recovery Excavation | 26-PC-31037 | In progress |  |  | 128746 | 100357.47 | 100357.47 | 3788.29 | 19141.96 | 0 | 22930.25 | 1350 | 324.5
NHT-010845 - Monitoring | 26-PC-31037 | In progress |  |  | 39754 | 30988.28 | 30988.28 | 4228.3 | 21365.3 | 0 | 25593.6 | 380 | 378.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31037 | In progress |  |  | 0 | 0 | 0 | 0 | 657.66 | 0 | 657.66 | 0 | 13.75
NHT-010853 - Curation | 26-PC-31064 | Completed |  |  | 74500 | 53043.19 | 60394.3 | 12977.94 | 63362.89 | 0 | 76340.83 | 948 | 895.92
NHT-010860 - Data Recovery Excavation | 26-PC-31084 | Completed |  |  | 17439 | 9067.98 | 9067.98 | 1373.38 | 6385.83 | 0 | 7759.21 | 78 | 141.08
NHT-010862 - Background Research | 26-PC-31084 | Completed |  |  | 3765 | 1957.87 | 1957.87 | 296.53 | 1378.77 | 0 | 1675.3 | 23 | 28.53
NHT-010865 - Prefield | 26-PC-31084 | Completed |  |  | 7096 | 3690.15 | 3690.15 | 558.89 | 2598.67 | 0 | 3157.56 | 43 | 58.12
NHT-010869 - Testing | 26-PC-31098 | On hold |  |  | 414100 | 297365.21 | 297365.21 | 0 | 0 | 0 | 0 | 2837 | 0
NHT-010874 - Data Recovery Excavation | 26-PC-31155 | Completed |  |  | 23921 | 15206.67 | 15206.67 | 1534.16 | 15512.05 | 0 | 17046.21 | 165 | 359.11
NHT-010875 - Background Research | 26-PC-31155 | Completed |  |  | 7344 | 4668.61 | 4668.61 | 471 | 4762.37 | 0 | 5233.37 | 53 | 78.08
NHT-010877 - Testing | 26-PC-31155 | Completed |  |  | 20425 | 12984.34 | 12984.34 | 1309.96 | 13245.1 | 0 | 14555.06 | 191 | 233.56
NHT-010884 - Agency Consultation | 26-PC-31155 | Completed |  |  | 4910 | 3121 | 3121 | 314.87 | 3183.68 | 0 | 3498.55 | 40 | 67.65
NHT-010885 - Prefield | 26-PC-31174 | Completed |  |  | 1284 | 707.86 | 870.55 | 80.78 | 711.15 | 0 | 791.93 | 13 | 11.59
NHT-010888 - Testing | 26-PC-31174 | Completed |  |  | 3116 | 1718.69 | 2113.7 | 196.12 | 1726.66 | 0 | 1922.78 | 27 | 37.42
NHT-010889 - Data Recovery Excavation | 26-PC-31182 | In progress |  |  | 645 | 506.01 | 506.01 | 0 | 0 | 0 | 0 | 11 | 0
NHT-010895 - GIS & Mapping | 26-PC-31182 | In progress |  |  | 51809 | 40654.97 | 40654.97 | 708.02 | 3284.69 | 0 | 3992.71 | 810 | 81.25
NHT-010900 - Fieldwork | 26-PC-31182 | In progress |  |  | 5399 | 4236.27 | 4236.27 | 194.92 | 904.25 | 0 | 1099.17 | 98 | 20.5
NHT-010907 - Final Report | 26-PC-31182 | In progress |  |  | 5920 | 4645.5 | 4645.5 | 124.21 | 576.26 | 0 | 700.47 | 113 | 13.25
NHT-010912 - Site Recordation | 26-PC-31182 | In progress |  |  | 9627 | 7554.23 | 7554.23 | 142.63 | 661.68 | 0 | 804.31 | 179 | 17.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31182 | In progress |  |  | 0 | 0 | 0 | 0 | 408.02 | 0 | 408.02 | 0 | 9.25
NHT-010921 - Testing | 26-PC-31186 | Completed |  |  | 11528 | 8414.35 | 8414.35 | 967.93 | 6046.08 | 0 | 7014.01 | 150 | 131.22
NHT-010924 - Project Management | 26-PC-31186 | Completed |  |  | 7379 | 5386.1 | 5386.1 | 619.58 | 3870.15 | 0 | 4489.73 | 101 | 70.44
NHT-010927 - Monitoring | 26-PC-31186 | Completed |  |  | 18752 | 13686.85 | 13686.85 | 1574.46 | 9834.6 | 0 | 11409.06 | 263 | 226.87
NHT-010931 - Final Report | 26-PC-31186 | Completed |  |  | 5441 | 3971.39 | 3971.39 | 456.84 | 2853.62 | 0 | 3310.46 | 59 | 46.84
NHT-010937 - Fieldwork | 26-PC-31209 | Completed |  |  | 353219 | 281374.03 | 281374.03 | 43011.16 | 285318.35 | 0 | 328329.51 | 6016 | 4925.37
NHT-010938 - Prefield | 26-PC-31209 | Completed |  |  | 57335 | 45673.25 | 45673.25 | 6981.67 | 46313.49 | 0 | 53295.16 | 885 | 1010.43
NHT-010939 - Monitoring | 26-PC-31209 | Completed |  |  | 291169 | 231945.55 | 231945.55 | 35455.47 | 235196.97 | 0 | 270652.44 | 3798 | 4249.45
NHT-010946 - Reporting | 26-PC-31209 | Completed |  |  | 258977 | 206300.79 | 206300.79 | 31535.38 | 209192.71 | 0 | 240728.09 | 3580 | 4919.16
NHT-010953 - Site Recordation | 26-PC-31216 | In progress |  |  | 45021 | 28993.63 | 28993.63 | 462.83 | 4028.05 | 0 | 4490.88 | 372 | 56.75
NHT-010956 - Survey | 26-PC-31216 | In progress |  |  | 57498 | 37028.23 | 37028.23 | 573.12 | 4987.98 | 0 | 5561.1 | 308 | 75.5
NHT-010959 - Reporting | 26-PC-31216 | In progress |  |  | 24199 | 15584.07 | 15584.07 | 286.01 | 2489.15 | 0 | 2775.16 | 177 | 42.5
NHT-010965 - Project Management | 26-PC-31216 | In progress |  |  | 13963 | 8992.4 | 8992.4 | 86.3 | 751.1 | 0 | 837.4 | 103 | 17.5
NHT-010972 - Agency Consultation | 26-PC-31216 | In progress |  |  | 31719 | 20427.27 | 20427.27 | 131.57 | 1145.05 | 0 | 1276.62 | 258 | 20.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31216 | In progress |  |  | 0 | 0 | 0 | 0 | 1439.96 | 0 | 1439.96 | 0 | 23
NHT-010982 - Survey | 26-PC-31238 | In progress |  |  | 269921 | 125418.37 | 172792.29 | 1747.52 | 22249.64 | 0 | 23997.16 | 4073 | 544.25
NHT-010987 - Agency Consultation | 26-PC-31238 | In progress |  |  | 218143 | 101359.63 | 139645.91 | 2520.65 | 32093.34 | 0 | 34613.99 | 2502 | 783
NHT-010990 - Final Report | 26-PC-31238 | In progress |  |  | 344636 | 160134.7 | 220621.92 | 2290.07 | 29157.54 | 0 | 31447.61 | 4602 | 724.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31238 | In progress |  |  | 0 | 0 | 0 | 0 | 1027.92 | 0 | 1027.92 | 0 | 25.75
NHT-011001 - Testing | 26-PC-31276 | Completed |  |  | 35773 | 26629.6 | 26629.6 | 4340.47 | 23483.03 | 0 | 27823.5 | 260 | 469.34
NHT-011008 - Lab Analysis | 26-PC-31276 | Completed |  |  | 20939 | 15586.67 | 15586.67 | 2540.54 | 13744.95 | 0 | 16285.49 | 204 | 294.57
NHT-011009 - Monitoring | 26-PC-31276 | Completed |  |  | 52010 | 38716.02 | 38716.02 | 6310.47 | 34141.32 | 0 | 40451.79 | 454 | 751.68
NHT-011013 - Site Recordation | 26-PC-31276 | Completed |  |  | 23678 | 17626.27 | 17626.27 | 2872.98 | 15543.54 | 0 | 18416.52 | 239 | 317.77
NHT-011020 - Lab Analysis | 26-PC-31316 | Completed |  |  | 90777 | 67293.19 | 67293.19 | 1930.44 | 19555.42 | 0 | 21485.86 | 505 | 230.5
NHT-011025 - Final Report | 26-PC-31316 | Completed |  |  | 57423 | 42567.47 | 42567.47 | 556.58 | 5638.15 | 0 | 6194.73 | 407 | 57.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31316 | Completed |  |  | 0 | 0 | 0 | 0 | 581.01 | 0 | 581.01 | 0 | 5.25
NHT-011033 - Monitoring | 26-PC-31421 | Completed |  |  | 307669 | 221367.53 | 221367.53 | 28777.78 | 259000.01 | 0 | 287777.79 | 3948 | 5305.87
NHT-011036 - Fieldwork | 26-PC-31421 | Completed |  |  | 432731 | 311350.27 | 311350.27 | 40475.53 | 364279.82 | 0 | 404755.35 | 4543 | 6465.4
NHT-011041 - Draft Report | 26-PC-31448 | In progress |  |  | 1585 | 991.37 | 1232.75 | 127.33 | 617.3 | 0 | 744.63 | 26 | 10.5
NHT-011046 - Prefield | 26-PC-31448 | In progress |  |  | 20820 | 13021.51 | 16192.01 | 624.47 | 3027.38 | 0 | 3651.85 | 371 | 49.75
NHT-011047 - Reporting | 26-PC-31448 | In progress |  |  | 2368 | 1481.35 | 1842.03 | 160.2 | 776.64 | 0 | 936.84 | 27 | 12
NHT-011048 - Background Research | 26-PC-31448 | In progress |  |  | 1027 | 642.17 | 798.52 | 47.74 | 231.44 | 0 | 279.18 | 15 | 5.5
NHT-011053 - Reporting | 26-PC-31473 | In progress |  |  | 180800 | 112403.36 | 112403.36 | 1167.52 | 5740.9 | 0 | 6908.42 | 0 | 97.5
NHT-011059 - Background Research | 26-PC-31484 | In progress |  |  | 22251 | 16392.21 | 16392.21 | 635.12 | 2238.58 | 0 | 2873.7 | 343 | 50.75
NHT-011062 - Lab Analysis | 26-PC-31484 | In progress |  |  | 1952 | 1437.83 | 1437.83 | 147.05 | 518.29 | 0 | 665.34 | 25 | 11.75
NHT-011065 - Site Recordation | 26-PC-31484 | In progress |  |  | 1070 | 788.6 | 788.6 | 78.22 | 275.69 | 0 | 353.91 | 17 | 6.25
NHT-011068 - Fieldwork | 26-PC-31484 | In progress |  |  | 6527 | 4808.42 | 4808.42 | 466.17 | 1643.1 | 0 | 2109.27 | 98 | 37.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31484 | In progress |  |  | 0 | 0 | 0 | 0 | 55.14 | 0 | 55.14 | 0 | 1.25
NHT-011076 - Lab Analysis | 26-PC-31505 | In progress |  |  | 44400 | 34032.6 | 34032.6 | 4414.31 | 19029.18 | 0 | 23443.49 | 394 | 423
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31505 | In progress |  |  | 0 | 0 | 0 | 0 | 417.62 | 0 | 417.62 | 0 | 9.5
NHT-011083 - Site Recordation | 26-PC-31537 | In progress |  |  | 87300 | 54449.01 | 54449.01 | 386.77 | 2436.37 | 0 | 2823.14 | 309 | 18.75
NHT-011086 - GIS & Mapping | 26-PC-31568 | In progress |  |  | 121225 | 63126.61 | 78671.09 | 1243.06 | 11636.09 | 0 | 12879.15 | 1785 | 280
NHT-011091 - Testing | 26-PC-31568 | In progress |  |  | 107875 | 56174.39 | 70006.93 | 1097.3 | 10271.72 | 0 | 11369.02 | 1501 | 244.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31568 | In progress |  |  | 0 | 0 | 0 | 0 | 649.28 | 0 | 649.28 | 0 | 16.5
NHT-011096 - Desktop Review | 26-PC-31638 | In progress |  |  | 15004 | 8847.54 | 9520.52 | 435.44 | 2951.38 | 0 | 3386.82 | 133 | 67
NHT-011101 - Agency Consultation | 26-PC-31638 | In progress |  |  | 155296 | 91574.36 | 98539.92 | 1305.89 | 8851.2 | 0 | 10157.09 | 1454 | 202.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31638 | In progress |  |  | 0 | 0 | 0 | 0 | 167.32 | 0 | 167.32 | 0 | 3.75
NHT-011111 - Prefield | 26-PC-31648 | In progress |  |  | 388400 | 288425.84 | 288425.84 | 21667.82 | 101518.45 | 0 | 123186.27 | 0 | 1870
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31648 | In progress |  |  | 0 | 0 | 0 | 0 | 1341.46 | 0 | 1341.46 | 0 | 21
NHT-011119 - Prefield | 26-PC-31678 | In progress |  |  | 892800 | 641923.2 | 641923.2 | 41686.98 | 169426.65 | 0 | 211113.63 | 0 | 3184.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31678 | In progress |  |  | 0 | 0 | 0 | 0 | 2665.75 | 0 | 2665.75 | 0 | 45
NHT-011132 - Agency Consultation | 26-PC-31692 | In progress |  |  | 103839 | 61252.96 | 71521.68 | 464.15 | 2890.37 | 0 | 3354.52 | 0 | 65.75
NHT-011134 - Draft Report | 26-PC-31692 | In progress |  |  | 145637 | 85909.09 | 100311.27 | 848.9 | 5286.32 | 0 | 6135.22 | 0 | 111.25
NHT-011135 - Reporting | 26-PC-31692 | In progress |  |  | 263392 | 155370.72 | 181417.73 | 1297.41 | 8079.38 | 0 | 9376.79 | 0 | 179
NHT-011138 - Desktop Review | 26-PC-31692 | In progress |  |  | 102432 | 60423.33 | 70552.96 | 806.27 | 5020.9 | 0 | 5827.17 | 0 | 105.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31692 | In progress |  |  | 0 | 0 | 0 | 0 | 615.44 | 0 | 615.44 | 0 | 14
NHT-011145 - Agency Consultation | 26-PC-31700 | Completed |  |  | 4095 | 2823.49 | 2823.49 | 216.68 | 2597.37 | 0 | 2814.05 | 25 | 52.15
NHT-011149 - Curation | 26-PC-31700 | Completed |  |  | 5997 | 4134.71 | 4134.71 | 317.31 | 3803.58 | 0 | 4120.89 | 38 | 79.17
NHT-011154 - GIS & Mapping | 26-PC-31700 | Completed |  |  | 8527 | 5879.35 | 5879.35 | 451.2 | 5408.5 | 0 | 5859.7 | 60 | 114.13
NHT-011156 - Site Recordation | 26-PC-31700 | Completed |  |  | 10996 | 7581.77 | 7581.77 | 581.84 | 6974.58 | 0 | 7556.42 | 69 | 151.47
NHT-011161 - Reporting | 26-PC-31700 | Completed |  |  | 19585 | 13504.08 | 13504.08 | 1036.34 | 12422.61 | 0 | 13458.95 | 146 | 255.69
NHT-011163 - GIS & Mapping | 26-PC-31716 | In progress |  |  | 13300 | 9413.74 | 9413.74 | 542.82 | 1895.66 | 0 | 2438.48 | 0 | 46
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31716 | In progress |  |  | 0 | 0 | 0 | 0 | 51.51 | 0 | 51.51 | 0 | 1.25
NHT-011168 - Prefield | 26-PC-31728 | In progress |  |  | 19404 | 15645.62 | 15645.62 | 85.59 | 364.89 | 0 | 450.48 | 155 | 5.75
NHT-011172 - Desktop Review | 26-PC-31728 | In progress |  |  | 11214 | 9042.05 | 9042.05 | 155.61 | 663.39 | 0 | 819 | 112 | 15
NHT-011175 - Site Recordation | 26-PC-31728 | In progress |  |  | 7882 | 6354.88 | 6354.88 | 59.65 | 254.3 | 0 | 313.95 | 57 | 6
NHT-011176 - Reporting | 26-PC-31802 | Completed |  |  | 12550 | 9734.9 | 9734.9 | 719.96 | 3771.87 | 0 | 4491.83 | 112 | 84.75
NHT-011179 - Project Management | 26-PC-31802 | Completed |  |  | 20293 | 15741.74 | 15741.74 | 578.81 | 3032.38 | 0 | 3611.19 | 198 | 63.5
NHT-011182 - GIS & Mapping | 26-PC-31802 | Completed |  |  | 7037 | 5458.37 | 5458.37 | 958.24 | 5020.16 | 0 | 5978.4 | 68 | 110
NHT-011189 - Site Recordation | 26-PC-31802 | Completed |  |  | 6097 | 4729.54 | 4729.54 | 775.72 | 4063.98 | 0 | 4839.7 | 74 | 91.5
NHT-011194 - Lab Analysis | 26-PC-31802 | Completed |  |  | 7723 | 5990.54 | 5990.54 | 723.7 | 3791.43 | 0 | 4515.13 | 83 | 85.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31802 | Completed |  |  | 0 | 0 | 0 | 0 | 338.64 | 0 | 338.64 | 0 | 8
NHT-011207 - Reporting | 26-PC-31823 | Completed |  |  | 29278 | 20661.79 | 20661.79 | 280.72 | 2663.72 | 0 | 2944.44 | 302 | 48.5
NHT-011213 - Survey | 26-PC-31823 | Completed |  |  | 46781 | 33013.42 | 33013.42 | 319.59 | 3032.55 | 0 | 3352.14 | 480 | 60.25
NHT-011217 - Prefield | 26-PC-31823 | Completed |  |  | 97841 | 69046.02 | 69046.02 | 477.46 | 4530.4 | 0 | 5007.86 | 974 | 70
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31823 | Completed |  |  | 0 | 0 | 0 | 0 | 40.49 | 0 | 40.49 | 0 | 1
NHT-011228 - Project Management | 26-PC-31830 | Completed |  |  | 39359 | 24723.18 | 26977.15 | 506.56 | 6158.65 | 0 | 6665.21 | 517 | 93.25
NHT-011230 - Final Report | 26-PC-31830 | Completed |  |  | 47341 | 29737.17 | 32448.24 | 1588.26 | 19309.98 | 0 | 20898.24 | 577 | 287.75
NHT-011237 - Agency Consultation | 26-PC-31872 | Completed |  |  | 24433 | 17479.78 | 17479.78 | 398.16 | 4464.04 | 0 | 4862.2 | 244 | 97.25
NHT-011238 - Site Recordation | 26-PC-31872 | Completed |  |  | 11068 | 7917.9 | 7917.9 | 786.08 | 8813.25 | 0 | 9599.33 | 101 | 156.75
NHT-011241 - Testing | 26-PC-31872 | Completed |  |  | 5412 | 3871.75 | 3871.75 | 277.16 | 3107.43 | 0 | 3384.59 | 42 | 72
NHT-011245 - Draft Report | 26-PC-31872 | Completed |  |  | 22887 | 16373.09 | 16373.09 | 410.67 | 4604.33 | 0 | 5015 | 235 | 89
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-31872 | Completed |  |  | 0 | 0 | 0 | 0 | 1139.84 | 0 | 1139.84 | 0 | 18
NHT-011253 - Reporting | 26-PC-31881 | In progress |  |  | 125300 | 80579.84 | 94955.6 | 0 | 0 | 0 | 0 | 0 | 0
NHT-011256 - Reporting | 26-PC-32047 | In progress |  |  | 73200 | 51825.6 | 51825.6 | 3660.09 | 32373.51 | 0 | 36033.6 | 883 | 744.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32047 | In progress |  |  | 0 | 0 | 0 | 0 | 204.96 | 0 | 204.96 | 0 | 3
NHT-011266 - Prefield | 26-PC-32069 | Completed |  |  | 128076 | 97952.43 | 97952.43 | 734.89 | 7566.66 | 0 | 8301.55 | 0 | 176.5
NHT-011271 - Testing | 26-PC-32069 | Completed |  |  | 256800 | 196400.82 | 196400.82 | 1072.29 | 11040.56 | 0 | 12112.85 | 0 | 266.5
NHT-011272 - Desktop Review | 26-PC-32069 | Completed |  |  | 363037 | 277650.26 | 277650.26 | 1253.71 | 12908.64 | 0 | 14162.35 | 0 | 317.5
NHT-011276 - Reporting | 26-PC-32069 | Completed |  |  | 38562 | 29492.25 | 29492.25 | 638.77 | 6576.93 | 0 | 7215.7 | 0 | 153.25
NHT-011280 - Survey | 26-PC-32069 | Completed |  |  | 58225 | 44530.8 | 44530.8 | 677.86 | 6979.41 | 0 | 7657.27 | 0 | 164
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32069 | Completed |  |  | 0 | 0 | 0 | 0 | 866.6 | 0 | 866.6 | 0 | 20
NHT-011292 - Testing | 26-PC-32076 | Completed |  |  | 50383 | 38170.2 | 38170.2 | 2443.89 | 31499.03 | 0 | 33942.92 | 783 | 572.99
NHT-011299 - Site Recordation | 26-PC-32076 | Completed |  |  | 42071 | 31873.16 | 31873.16 | 2040.72 | 26302.55 | 0 | 28343.27 | 668 | 426.14
NHT-011304 - Survey | 26-PC-32076 | Completed |  |  | 56017 | 42438.42 | 42438.42 | 2717.17 | 35021.25 | 0 | 37738.42 | 838 | 676.8
NHT-011308 - Background Research | 26-PC-32076 | Completed |  |  | 17329 | 13128.3 | 13128.3 | 840.55 | 10833.81 | 0 | 11674.36 | 256 | 197.97
NHT-011312 - Draft Report | 26-PC-32094 | In progress |  |  | 19000 | 11274.6 | 11274.6 | 1030.18 | 4959.26 | 0 | 5989.44 | 65 | 47.25
NHT-011318 - Testing | 26-PC-32165 | In progress |  |  | 403429 | 317336.98 | 317336.98 | 974.12 | 3556.66 | 0 | 4530.78 | 5225 | 90.5
NHT-011322 - Final Report | 26-PC-32165 | In progress |  |  | 97571 | 76749.62 | 76749.62 | 1255.44 | 4583.83 | 0 | 5839.27 | 1171 | 116.75
NHT-011328 - Lab Analysis | 26-PC-32188 | In progress |  |  | 16305 | 13339.13 | 13339.13 | 0 | 0 | 0 | 0 | 207 | 0
NHT-011329 - Reporting | 26-PC-32188 | In progress |  |  | 18789 | 15371.54 | 15371.54 | 0 | 0 | 0 | 0 | 298 | 0
NHT-011331 - Fieldwork | 26-PC-32188 | In progress |  |  | 43224 | 35361.46 | 35361.46 | 0 | 0 | 0 | 0 | 462 | 0
NHT-011332 - Desktop Review | 26-PC-32188 | In progress |  |  | 5029 | 4113.83 | 4113.83 | 0 | 0 | 0 | 0 | 79 | 0
NHT-011336 - Prefield | 26-PC-32188 | In progress |  |  | 8153 | 6670.19 | 6670.19 | 0 | 0 | 0 | 0 | 83 | 0
NHT-011339 - Final Report | 26-PC-32227 | Completed |  |  | 5609 | 3825.15 | 3825.15 | 754.38 | 3216.06 | 0 | 3970.44 | 51 | 63.79
NHT-011346 - Agency Consultation | 26-PC-32227 | Completed |  |  | 4102 | 2797.24 | 2797.24 | 551.66 | 2351.83 | 0 | 2903.49 | 37 | 42.23
NHT-011352 - Testing | 26-PC-32227 | Completed |  |  | 23189 | 15815.41 | 15815.41 | 3119.08 | 13297.09 | 0 | 16416.17 | 228 | 250.17
NHT-011358 - Prefield | 26-PC-32288 | In progress |  |  | 1907 | 1367.73 | 1367.73 | 0 | 0 | 0 | 0 | 21 | 0
NHT-011361 - Monitoring | 26-PC-32288 | In progress |  |  | 6809 | 4884.74 | 4884.74 | 0 | 0 | 0 | 0 | 59 | 0
NHT-011366 - Fieldwork | 26-PC-32288 | In progress |  |  | 274025 | 196585.9 | 196585.9 | 261.05 | 1350.37 | 0 | 1611.42 | 2367 | 19.5
NHT-011370 - GIS & Mapping | 26-PC-32288 | In progress |  |  | 109588 | 78618.64 | 78618.64 | 247.66 | 1281.13 | 0 | 1528.79 | 963 | 18.5
NHT-011372 - Data Recovery Excavation | 26-PC-32288 | In progress |  |  | 8171 | 5861.69 | 5861.69 | 0 | 0 | 0 | 0 | 83 | 0
NHT-011374 - Data Recovery Excavation | 26-PC-32303 | In progress |  |  | 18700 | 13411.64 | 13411.64 | 155.15 | 487.18 | 0 | 642.33 | 195 | 12.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32303 | In progress |  |  | 0 | 0 | 0 | 0 | 210.16 | 0 | 210.16 | 0 | 5.5
NHT-011385 - Project Management | 26-PC-32322 | In progress |  |  | 105014 | 80924.17 | 80924.17 | 1572.46 | 6533.37 | 0 | 8105.83 | 613 | 67
NHT-011387 - Site Recordation | 26-PC-32322 | In progress |  |  | 125909 | 97025.4 | 97025.4 | 1388.27 | 5768.08 | 0 | 7156.35 | 633 | 79.25
NHT-011392 - Testing | 26-PC-32322 | In progress |  |  | 86577 | 66715.93 | 66715.93 | 2828.32 | 11751.35 | 0 | 14579.67 | 599 | 146
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32322 | In progress |  |  | 0 | 0 | 0 | 0 | 788.06 | 0 | 788.06 | 0 | 6.25
NHT-011401 - Desktop Review | 26-PC-32369 | In progress |  |  | 730600 | 470798.64 | 470798.64 | 5140.41 | 39695.22 | 0 | 44835.63 | 9652 | 980
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32369 | In progress |  |  | 0 | 0 | 0 | 0 | 1060.88 | 0 | 1060.88 | 0 | 26.25
NHT-011410 - Final Report | 26-PC-32382 | Completed |  |  | 14188 | 10860.75 | 10860.75 | 1474.96 | 11131.53 | 0 | 12606.49 | 107 | 189.98
NHT-011412 - Monitoring | 26-PC-32382 | Completed |  |  | 44222 | 33851.63 | 33851.63 | 4597.26 | 34695.6 | 0 | 39292.86 | 326 | 607.67
NHT-011418 - Survey | 26-PC-32382 | Completed |  |  | 52441 | 40143.32 | 40143.32 | 5451.72 | 41144.15 | 0 | 46595.87 | 381 | 677.74
NHT-011419 - Project Management | 26-PC-32382 | Completed |  |  | 14455 | 11065.65 | 11065.65 | 1502.79 | 11341.54 | 0 | 12844.33 | 134 | 227.14
NHT-011425 - Testing | 26-PC-32382 | Completed |  |  | 55194 | 42251.4 | 42251.4 | 5738 | 43304.79 | 0 | 49042.79 | 498 | 759.04
NHT-011427 - Desktop Review | 26-PC-32394 | In progress |  |  | 3264 | 2268.88 | 2268.88 | 1748.19 | 7742.02 | 0 | 9490.21 | 23 | 94.75
NHT-011431 - Monitoring | 26-PC-32394 | Completed |  |  | 7932 | 5513.58 | 5513.58 | 2255.58 | 9989.05 | 0 | 12244.63 | 51 | 122.25
NHT-011433 - Fieldwork | 26-PC-32394 | In progress |  |  | 2504 | 1740.41 | 1740.41 | 1688.23 | 7476.46 | 0 | 9164.69 | 16 | 91.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32394 | In progress |  |  | 0 | 0 | 0 | 0 | 204.27 | 0 | 204.27 | 0 | 2.5
NHT-011443 - Lab Analysis | 26-PC-32396 | Completed |  |  | 70539 | 46943.66 | 52191.97 | 443.69 | 2120.99 | 0 | 2564.68 | 958 | 49.5
NHT-011445 - Final Report | 26-PC-32396 | Completed |  |  | 128039 | 85210.01 | 94736.54 | 171.39 | 819.28 | 0 | 990.67 | 2136 | 19.25
NHT-011448 - Reporting | 26-PC-32396 | Completed |  |  | 2939 | 1955.95 | 2174.63 | 0 | 0 | 0 | 0 | 50 | 0
NHT-011453 - Draft Report | 26-PC-32396 | Completed |  |  | 2613 | 1738.63 | 1933 | 0 | 0 | 0 | 0 | 33 | 0
NHT-011460 - Project Management | 26-PC-32396 | Completed |  |  | 1470 | 977.98 | 1087.31 | 0 | 0 | 0 | 0 | 20 | 0
NHT-011463 - GIS & Mapping | 26-PC-32420 | In progress |  |  | 1889 | 1311.32 | 1438.38 | 0 | 0 | 0 | 0 | 0 | 0
NHT-011469 - Site Recordation | 26-PC-32420 | In progress |  |  | 222338 | 154383.1 | 169342.91 | 1519.32 | 5421.46 | 0 | 6940.78 | 0 | 62.5
NHT-011470 - Prefield | 26-PC-32420 | In progress |  |  | 39681 | 27553.33 | 30223.26 | 352.83 | 1259.04 | 0 | 1611.87 | 0 | 25.5
NHT-011475 - Project Management | 26-PC-32420 | In progress |  |  | 15513 | 10771.93 | 11815.73 | 220.18 | 785.68 | 0 | 1005.86 | 0 | 11.5
NHT-011479 - Curation | 26-PC-32420 | In progress |  |  | 44779 | 31092.82 | 34105.73 | 134.02 | 478.24 | 0 | 612.26 | 0 | 12.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32420 | In progress |  |  | 0 | 0 | 0 | 0 | 380.64 | 0 | 380.64 | 0 | 9.75
NHT-011487 - Survey | 26-PC-32442 | In progress |  |  | 27978 | 17455.19 | 17455.19 | 719.38 | 5775.09 | 0 | 6494.47 | 310 | 127
NHT-011492 - Final Report | 26-PC-32442 | In progress |  |  | 25422 | 15861.07 | 15861.07 | 442.7 | 3553.9 | 0 | 3996.6 | 311 | 81.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32442 | In progress |  |  | 0 | 0 | 0 | 0 | 170.24 | 0 | 170.24 | 0 | 4
NHT-011498 - Testing | 26-PC-32453 | In progress |  |  | 103800 | 58312.8 | 74927.88 | 975.34 | 3540.13 | 0 | 4515.47 | 1150 | 85.5
NHT-011500 - Desktop Review | 26-PC-32540 | Completed |  |  | 517062 | 382419.23 | 382419.23 | 4728.18 | 20434 | 0 | 25162.18 | 3169 | 231.25
NHT-011504 - Prefield | 26-PC-32540 | Completed |  |  | 329038 | 243356.33 | 243356.33 | 5397.81 | 23328 | 0 | 28725.81 | 2282 | 314
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32540 | Completed |  |  | 0 | 0 | 0 | 0 | 1749.34 | 0 | 1749.34 | 0 | 21.75
NHT-011515 - Testing | 26-PC-32556 | In progress |  |  | 29739 | 20993.36 | 20993.36 | 772.2 | 4020.21 | 0 | 4792.41 | 0 | 98
NHT-011519 - Fieldwork | 26-PC-32556 | In progress |  |  | 9946 | 7020.6 | 7020.6 | 632.56 | 3293.22 | 0 | 3925.78 | 0 | 78.25
NHT-011525 - Final Report | 26-PC-32556 | In progress |  |  | 6015 | 4245.67 | 4245.67 | 421.01 | 2191.88 | 0 | 2612.89 | 0 | 52.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32556 | In progress |  |  | 0 | 0 | 0 | 0 | -198.31 | 0 | -198.31 | 0 | -4.75
NHT-011534 - Curation | 26-PC-32563 | Completed |  |  | 116652 | 75088.71 | 75088.71 | 5348.35 | 26773.23 | 0 | 32121.58 | 1757 | 663.25
NHT-011539 - Project Management | 26-PC-32563 | Completed |  |  | 135925 | 87495.16 | 87495.16 | 3111.77 | 15577.2 | 0 | 18688.97 | 1662 | 379
NHT-011540 - Testing | 26-PC-32563 | Completed |  |  | 282323 | 181731.26 | 181731.26 | 5506.68 | 27565.85 | 0 | 33072.53 | 4111 | 645.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32563 | Completed |  |  | 0 | 0 | 0 | 0 | 1802.81 | 0 | 1802.81 | 0 | 45.75
NHT-011553 - Curation | 26-PC-32569 | Completed |  |  | 191800 | 122498.04 | 155949 | 11505.49 | 139882.57 | 0 | 151388.06 | 2174 | 2263.96
NHT-011554 - Reporting | 26-PC-32594 | In progress |  |  | 53024 | 40181.43 | 40181.43 | 2613.5 | 20561.87 | 0 | 23175.37 | 664 | 314.75
NHT-011556 - Project Management | 26-PC-32594 | In progress |  |  | 41376 | 31354.89 | 31354.89 | 1692.26 | 13313.99 | 0 | 15006.25 | 520 | 248
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32594 | In progress |  |  | 0 | 0 | 0 | 0 | 608.97 | 0 | 608.97 | 0 | 13.25
NHT-011567 - GIS & Mapping | 26-PC-32614 | In progress |  |  | 7174 | 5011.63 | 5011.63 | 0 | 0 | 0 | 0 | 86 | 0
NHT-011572 - Curation | 26-PC-32614 | In progress |  |  | 4007 | 2799.07 | 2799.07 | 0 | 0 | 0 | 0 | 55 | 0
NHT-011573 - Agency Consultation | 26-PC-32614 | In progress |  |  | 3267 | 2282.27 | 2282.27 | 0 | 0 | 0 | 0 | 30 | 0
NHT-011580 - Site Recordation | 26-PC-32614 | In progress |  |  | 6270 | 4379.88 | 4379.88 | 0 | 0 | 0 | 0 | 74 | 0
NHT-011585 - Testing | 26-PC-32614 | In progress |  |  | 8982 | 6275.57 | 6275.57 | 0 | 0 | 0 | 0 | 92 | 0
NHT-011586 - Final Report | 26-PC-32646 | In progress |  |  | 18356 | 12812.28 | 12812.28 | 855.78 | 5830.03 | 0 | 6685.81 | 263 | 138
NHT-011588 - Reporting | 26-PC-32646 | In progress |  |  | 30244 | 21110.52 | 21110.52 | 1186.38 | 8082.22 | 0 | 9268.6 | 408 | 194
NHT-011590 - Monitoring | 26-PC-32668 | Completed |  |  | 102718 | 70443.95 | 70443.95 | 8248.25 | 63475.63 | 0 | 71723.88 | 829 | 1085.27
NHT-011595 - Survey | 26-PC-32668 | Completed |  |  | 93074 | 63830.46 | 63830.46 | 7473.87 | 57516.33 | 0 | 64990.2 | 861 | 1033.77
NHT-011597 - Data Recovery Excavation | 26-PC-32668 | Completed |  |  | 85873 | 58891.39 | 58891.39 | 6895.56 | 53065.84 | 0 | 59961.4 | 898 | 854.79
NHT-011600 - Curation | 26-PC-32668 | Completed |  |  | 18935 | 12985.68 | 12985.68 | 1520.49 | 11701.13 | 0 | 13221.62 | 159 | 207.66
NHT-011601 - Site Recordation | 26-PC-32707 | In progress |  |  | 98926 | 69307.7 | 69307.7 | 1541.99 | 17232.93 | 0 | 18774.92 | 0 | 308.5
NHT-011606 - Data Recovery Excavation | 26-PC-32707 | Completed |  |  | 22838 | 16000.24 | 16000.24 | 1616.94 | 18070.53 | 0 | 19687.47 | 0 | 327
NHT-011608 - Reporting | 26-PC-32707 | In progress |  |  | 112279 | 78663.12 | 78663.12 | 1884.1 | 21056.27 | 0 | 22940.37 | 0 | 348.25
NHT-011609 - Agency Consultation | 26-PC-32707 | In progress |  |  | 22904 | 16046.25 | 16046.25 | 1334.07 | 14909.26 | 0 | 16243.33 | 0 | 268
NHT-011614 - Survey | 26-PC-32707 | In progress |  |  | 70453 | 49359.13 | 49359.13 | 2159 | 24128.58 | 0 | 26287.58 | 0 | 459.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32707 | In progress |  |  | 0 | 0 | 0 | 0 | 2767.56 | 0 | 2767.56 | 0 | 47.5
NHT-011625 - Final Report | 26-PC-32711 | In progress |  |  | 9492 | 6877.55 | 6877.55 | 444.8 | 3389.67 | 0 | 3834.47 | 88 | 55.25
NHT-011626 - Reporting | 26-PC-32711 | In progress |  |  | 1772 | 1283.91 | 1283.91 | 30.02 | 228.79 | 0 | 258.81 | 15 | 5.25
NHT-011627 - Draft Report | 26-PC-32711 | In progress |  |  | 8066 | 5844.47 | 5844.47 | 173.93 | 1325.51 | 0 | 1499.44 | 85 | 30.75
NHT-011630 - Desktop Review | 26-PC-32711 | In progress |  |  | 42770 | 30991.73 | 30991.73 | 443.96 | 3383.26 | 0 | 3827.22 | 409 | 53
NHT-011632 - Reporting | 26-PC-32725 | Completed |  |  | 2742 | 1949.36 | 1949.36 | 100.76 | 723.85 | 0 | 824.61 | 30 | 17.5
NHT-011633 - Draft Report | 26-PC-32725 | Completed |  |  | 12036 | 8557.95 | 8557.95 | 639.2 | 4591.97 | 0 | 5231.17 | 121 | 110.25
NHT-011640 - Final Report | 26-PC-32725 | Completed |  |  | 5526 | 3928.66 | 3928.66 | 394.15 | 2831.58 | 0 | 3225.73 | 53 | 68
NHT-011645 - Lab Analysis | 26-PC-32725 | Completed |  |  | 5996 | 4263.33 | 4263.33 | 237.73 | 1707.88 | 0 | 1945.61 | 67 | 41
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32725 | Completed |  |  | 0 | 0 | 0 | 0 | 204.88 | 0 | 204.88 | 0 | 5
NHT-011648 - Prefield | 26-PC-32727 | Completed |  |  | 13412 | 9052.08 | 9052.08 | 475.96 | 6960.89 | 0 | 7436.85 | 172 | 123.72
NHT-011654 - Draft Report | 26-PC-32727 | Completed |  |  | 30355 | 20486.4 | 20486.4 | 1077.18 | 15753.68 | 0 | 16830.86 | 345 | 262.37
NHT-011658 - Project Management | 26-PC-32727 | Completed |  |  | 26333 | 17772.01 | 17772.01 | 934.45 | 13666.36 | 0 | 14600.81 | 300 | 285.84
NHT-011664 - Site Recordation | 26-PC-32731 | Completed |  |  | 3649 | 2850.79 | 2850.79 | 189.54 | 1989.05 | 0 | 2178.59 | 0 | 28.45
NHT-011666 - Testing | 26-PC-32731 | Completed |  |  | 3784 | 2956.38 | 2956.38 | 196.56 | 2062.72 | 0 | 2259.28 | 0 | 44.58
NHT-011671 - Reporting | 26-PC-32731 | Completed |  |  | 6429 | 5022.01 | 5022.01 | 333.89 | 3503.95 | 0 | 3837.84 | 0 | 61.73
NHT-011675 - Agency Consultation | 26-PC-32731 | Completed |  |  | 1727 | 1349.13 | 1349.13 | 89.7 | 941.31 | 0 | 1031.01 | 0 | 16.88
NHT-011680 - Fieldwork | 26-PC-32731 | Completed |  |  | 10411 | 8132.89 | 8132.89 | 540.72 | 5674.47 | 0 | 6215.19 | 0 | 99.82
NHT-011681 - Testing | 26-PC-32744 | Completed |  |  | 98109 | 66756.95 | 72002.45 | 16271.14 | 71208.14 | 0 | 87479.28 | 709 | 1322.01
NHT-011684 - Prefield | 26-PC-32744 | Completed |  |  | 20498 | 13947.53 | 15043.47 | 3399.53 | 14877.51 | 0 | 18277.04 | 188 | 262.05
NHT-011690 - Agency Consultation | 26-PC-32744 | Completed |  |  | 18493 | 12583.02 | 13571.74 | 3066.95 | 13422.02 | 0 | 16488.97 | 166 | 214.38
NHT-011691 - Monitoring | 26-PC-32745 | In progress |  |  | 36700 | 24346.66 | 24346.66 | 757.51 | 6526.25 | 0 | 7283.76 | 0 | 89.5
NHT-011695 - GIS & Mapping | 26-PC-32745 | In progress |  |  | 11117 | 7374.8 | 7374.8 | 457.62 | 3942.55 | 0 | 4400.17 | 0 | 64
NHT-011702 - Background Research | 26-PC-32745 | In progress |  |  | 38577 | 25592.18 | 25592.18 | 1023.36 | 8816.63 | 0 | 9839.99 | 0 | 134.5
NHT-011703 - Data Recovery Excavation | 26-PC-32745 | In progress |  |  | 48906 | 32444.38 | 32444.38 | 1635.27 | 14088.53 | 0 | 15723.8 | 0 | 189.75
NHT-011708 - Background Research | 26-PC-32773 | In progress |  |  | 16233 | 10967.09 | 10967.09 | 539.07 | 4745.97 | 0 | 5285.04 | 0 | 101.5
NHT-011715 - Desktop Review | 26-PC-32773 | In progress |  |  | 15512 | 10479.61 | 10479.61 | 187.01 | 1646.45 | 0 | 1833.46 | 0 | 37.25
NHT-011718 - Curation | 26-PC-32773 | In progress |  |  | 383 | 258.72 | 258.72 | 0 | 0 | 0 | 0 | 0 | 0
NHT-011724 - Prefield | 26-PC-32773 | In progress |  |  | 2937 | 1984.57 | 1984.57 | 167.56 | 1475.18 | 0 | 1642.74 | 0 | 30.25
NHT-011728 - Testing | 26-PC-32773 | In progress |  |  | 13035 | 8806.37 | 8806.37 | 569.83 | 5016.7 | 0 | 5586.53 | 0 | 113.5
NHT-011729 - Draft Report | 26-PC-32803 | Completed |  |  | 93605 | 52784.84 | 62639.59 | 8276.22 | 69071.61 | 0 | 77347.83 | 867 | 1301.54
NHT-011733 - GIS & Mapping | 26-PC-32803 | Completed |  |  | 28586 | 16119.89 | 19129.43 | 2527.46 | 21093.7 | 0 | 23621.16 | 239 | 329.35
NHT-011740 - Prefield | 26-PC-32803 | Completed |  |  | 37158 | 20953.7 | 24865.69 | 3285.37 | 27418.98 | 0 | 30704.35 | 346 | 555.04
NHT-011745 - Project Management | 26-PC-32803 | Completed |  |  | 38951 | 21964.57 | 26065.29 | 3443.86 | 28741.76 | 0 | 32185.62 | 341 | 526.77
NHT-011747 - Desktop Review | 26-PC-32852 | In progress |  |  | 148800 | 95395.68 | 95395.68 | 1403.6 | 16767.19 | 0 | 18170.79 | 1154 | 296.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32852 | In progress |  |  | 0 | 0 | 0 | 0 | 57.77 | 0 | 57.77 | 0 | 0.75
NHT-011756 - GIS & Mapping | 26-PC-32946 | On hold |  |  | 151600 | 96190.2 | 96190.2 | 0 | 0 | 0 | 0 | 1376 | 0
NHT-011757 - Survey | 26-PC-32973 | On hold |  |  | 76607 | 41880.63 | 49775.12 | 0 | 0 | 0 | 0 | 536 | 0
NHT-011764 - Prefield | 26-PC-32973 | On hold |  |  | 12422 | 6791.02 | 8071.12 | 0 | 0 | 0 | 0 | 95 | 0
NHT-011767 - Monitoring | 26-PC-32973 | On hold |  |  | 27967 | 15289.35 | 18171.38 | 0 | 0 | 0 | 0 | 185 | 0
NHT-011768 - Fieldwork | 26-PC-32973 | On hold |  |  | 66992 | 36624.45 | 43528.14 | 0 | 0 | 0 | 0 | 491 | 0
NHT-011775 - Lab Analysis | 26-PC-32973 | On hold |  |  | 19212 | 10502.95 | 12482.75 | 0 | 0 | 0 | 0 | 116 | 0
NHT-011777 - Final Report | 26-PC-32985 | In progress |  |  | 44794 | 31856.57 | 37523.27 | 3640.36 | 21643.55 | 0 | 25283.91 | 0 | 366
NHT-011781 - Desktop Review | 26-PC-32985 | In progress |  |  | 61706 | 43884.81 | 51691.11 | 4011.3 | 23849.01 | 0 | 27860.31 | 0 | 396
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-32985 | In progress |  |  | 0 | 0 | 0 | 0 | 1122.84 | 0 | 1122.84 | 0 | 22.5
NHT-011792 - Final Report | 26-PC-33011 | Completed |  |  | 120687 | 81229.33 | 97670.14 | 12679.64 | 99529.53 | 0 | 112209.17 | 0 | 2163.02
NHT-011798 - Agency Consultation | 26-PC-33011 | Completed |  |  | 65064 | 43791.83 | 52655.3 | 6835.76 | 53657.71 | 0 | 60493.47 | 0 | 976.19
NHT-011801 - Background Research | 26-PC-33011 | Completed |  |  | 60794 | 40917.74 | 49199.49 | 6387.13 | 50136.12 | 0 | 56523.25 | 0 | 898
NHT-011806 - Lab Analysis | 26-PC-33011 | Completed |  |  | 129129 | 86911.9 | 104502.86 | 13566.67 | 106492.32 | 0 | 120058.99 | 0 | 2295.66
NHT-011808 - Survey | 26-PC-33011 | Completed |  |  | 214926 | 144658.76 | 173937.67 | 22580.75 | 177248.98 | 0 | 199829.73 | 0 | 3711.44
NHT-011814 - Curation | 26-PC-33017 | In progress |  |  | 171469 | 98013.56 | 128591.1 | 6368.78 | 41515.51 | 0 | 47884.29 | 0 | 594.75
NHT-011818 - Survey | 26-PC-33017 | In progress |  |  | 178406 | 101978.47 | 133792.95 | 7317.43 | 47699.32 | 0 | 55016.75 | 0 | 682
NHT-011822 - GIS & Mapping | 26-PC-33017 | In progress |  |  | 238725 | 136457.93 | 179029.05 | 4652.57 | 30328.23 | 0 | 34980.8 | 0 | 443
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33017 | In progress |  |  | 0 | 0 | 0 | 0 | 3185.68 | 0 | 3185.68 | 0 | 44
NHT-011829 - Monitoring | 26-PC-33033 | On hold |  |  | 39608 | 33369.52 | 33369.52 | 0 | 0 | 0 | 0 | 314 | 0
NHT-011831 - Site Recordation | 26-PC-33033 | On hold |  |  | 20669 | 17413.56 | 17413.56 | 0 | 0 | 0 | 0 | 197 | 0
NHT-011836 - Testing | 26-PC-33033 | On hold |  |  | 30508 | 25702.83 | 25702.83 | 0 | 0 | 0 | 0 | 277 | 0
NHT-011843 - Prefield | 26-PC-33033 | On hold |  |  | 14427 | 12154.98 | 12154.98 | 0 | 0 | 0 | 0 | 140 | 0
NHT-011850 - Project Management | 26-PC-33033 | On hold |  |  | 15988 | 13470.11 | 13470.11 | 0 | 0 | 0 | 0 | 134 | 0
NHT-011855 - Project Management | 26-PC-33099 | In progress |  |  | 101746 | 75333 | 75333 | 1113.73 | 8167.32 | 0 | 9281.05 | 996 | 110.75
NHT-011859 - Curation | 26-PC-33099 | In progress |  |  | 43596 | 32278.54 | 32278.54 | 516.83 | 3790.1 | 0 | 4306.93 | 409 | 55.5
NHT-011863 - Survey | 26-PC-33099 | In progress |  |  | 12743 | 9434.88 | 9434.88 | 588.27 | 4314 | 0 | 4902.27 | 155 | 60
NHT-011870 - Final Report | 26-PC-33099 | In progress |  |  | 6815 | 5045.54 | 5045.54 | 362.45 | 2657.97 | 0 | 3020.42 | 68 | 35.75
NHT-011874 - Prefield | 26-PC-33127 | In progress |  |  | 46710 | 24054.89 | 31217.84 | 1387.91 | 7648.36 | 0 | 9036.27 | 0 | 79.75
NHT-011879 - Fieldwork | 26-PC-33127 | In progress |  |  | 34479 | 17756.43 | 23043.87 | 912.74 | 5029.82 | 0 | 5942.56 | 0 | 49.75
NHT-011881 - Lab Analysis | 26-PC-33127 | In progress |  |  | 43135 | 22214.47 | 28829.41 | 1023 | 5637.43 | 0 | 6660.43 | 0 | 72.25
NHT-011887 - Desktop Review | 26-PC-33127 | In progress |  |  | 14759 | 7600.92 | 9864.29 | 245.41 | 1352.4 | 0 | 1597.81 | 0 | 20
NHT-011894 - Testing | 26-PC-33127 | In progress |  |  | 40417 | 20814.54 | 27012.61 | 994.75 | 5481.79 | 0 | 6476.54 | 0 | 59
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33127 | In progress |  |  | 0 | 0 | 0 | 0 | 711.81 | 0 | 711.81 | 0 | 6.25
NHT-011901 - Lab Analysis | 26-PC-33162 | In progress |  |  | 53640 | 36045.83 | 36045.83 | 633.95 | 2988.61 | 0 | 3622.56 | 0 | 74.75
NHT-011905 - Agency Consultation | 26-PC-33162 | In progress |  |  | 14714 | 9887.82 | 9887.82 | 252.53 | 1190.49 | 0 | 1443.02 | 0 | 28.5
NHT-011907 - Final Report | 26-PC-33162 | In progress |  |  | 13546 | 9103.15 | 9103.15 | 271.07 | 1277.9 | 0 | 1548.97 | 0 | 32.5
NHT-011911 - Agency Consultation | 26-PC-33217 | Completed |  |  | 10687 | 7660.49 | 7660.49 | 569.61 | 8330.54 | 0 | 8900.15 | 112 | 136.55
NHT-011912 - Project Management | 26-PC-33217 | Completed |  |  | 18013 | 12911.67 | 12911.67 | 960.07 | 14041.03 | 0 | 15001.1 | 163 | 244.84
NHT-011917 - Data Recovery Excavation | 26-PC-33223 | Completed |  |  | 20992 | 15401.31 | 15401.31 | 4384.75 | 15636.95 | 0 | 20021.7 | 186 | 275.85
NHT-011918 - Draft Report | 26-PC-33223 | Completed |  |  | 11352 | 8329.31 | 8329.31 | 2371.35 | 8456.75 | 0 | 10828.1 | 94 | 157.78
NHT-011925 - Desktop Review | 26-PC-33223 | Completed |  |  | 3733 | 2739.08 | 2739.08 | 779.82 | 2780.99 | 0 | 3560.81 | 36 | 48.12
NHT-011927 - Agency Consultation | 26-PC-33223 | Completed |  |  | 2314 | 1697.76 | 1697.76 | 483.35 | 1723.74 | 0 | 2207.09 | 20 | 40.71
NHT-011928 - Reporting | 26-PC-33223 | Completed |  |  | 13209 | 9691.46 | 9691.46 | 2759.16 | 9839.74 | 0 | 12598.9 | 131 | 173.29
NHT-011934 - Survey | 26-PC-33255 | Completed |  |  | 59162 | 43596.64 | 43596.64 | 8096.47 | 48129.03 | 0 | 56225.5 | 601 | 888.86
NHT-011939 - Agency Consultation | 26-PC-33255 | Completed |  |  | 11138 | 8207.43 | 8207.43 | 1524.23 | 9060.69 | 0 | 10584.92 | 95 | 128.79
NHT-011944 - Agency Consultation | 26-PC-33257 | Completed |  |  | 7781 | 5493.68 | 5493.68 | 1109.08 | 4408.71 | 0 | 5517.79 | 57 | 83.25
NHT-011947 - Site Recordation | 26-PC-33257 | Completed |  |  | 14751 | 10414.18 | 10414.18 | 2102.44 | 8357.45 | 0 | 10459.89 | 119 | 160.74
NHT-011954 - Background Research | 26-PC-33257 | Completed |  |  | 9653 | 6814.88 | 6814.88 | 1375.8 | 5468.99 | 0 | 6844.79 | 41 | 113.19
NHT-011958 - Draft Report | 26-PC-33257 | Completed |  |  | 17386 | 12274.3 | 12274.3 | 2477.96 | 9850.19 | 0 | 12328.15 | 114 | 170.48
NHT-011963 - GIS & Mapping | 26-PC-33257 | Completed |  |  | 10429 | 7362.96 | 7362.96 | 1486.45 | 5908.83 | 0 | 7395.28 | 59 | 105.23
NHT-011968 - Curation | 26-PC-33276 | In progress |  |  | 34084 | 22621.56 | 22621.56 | 820.39 | 5163.63 | 0 | 5984.02 | 419 | 131
NHT-011972 - Survey | 26-PC-33276 | In progress |  |  | 11868 | 7876.52 | 7876.52 | 125.27 | 788.48 | 0 | 913.75 | 133 | 9.75
NHT-011976 - Final Report | 26-PC-33276 | In progress |  |  | 12492 | 8290.92 | 8290.92 | 246.48 | 1551.38 | 0 | 1797.86 | 159 | 36.25
NHT-011979 - Site Recordation | 26-PC-33276 | In progress |  |  | 5756 | 3820.54 | 3820.54 | 113.92 | 717.06 | 0 | 830.98 | 67 | 19
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33276 | In progress |  |  | 0 | 0 | 0 | 0 | 597.9 | 0 | 597.9 | 0 | 14.25
NHT-011984 - Lab Analysis | 26-PC-33413 | Completed |  |  | 80270 | 53829.07 | 53829.07 | 5294.33 | 64367.84 | 0 | 69662.17 | 1149 | 1355.92
NHT-011986 - Project Management | 26-PC-33413 | Completed |  |  | 67830 | 45486.67 | 45486.67 | 4473.81 | 54392.15 | 0 | 58865.96 | 920 | 929.54
NHT-011992 - Monitoring | 26-PC-33413 | Completed |  |  | 192944 | 129388.36 | 129388.36 | 12725.91 | 154720.3 | 0 | 167446.21 | 2121 | 2435.41
NHT-011998 - Site Recordation | 26-PC-33413 | Completed |  |  | 143756 | 96402.78 | 96402.78 | 9481.64 | 115276.72 | 0 | 124758.36 | 2143 | 2136.44
NHT-012003 - GIS & Mapping | 26-PC-33485 | In progress |  |  | 179434 | 129515.76 | 129515.76 | 1840.74 | 9003.12 | 0 | 10843.86 | 1149 | 150.5
NHT-012004 - Data Recovery Excavation | 26-PC-33485 | In progress |  |  | 22600 | 16312.35 | 16312.35 | 387.6 | 1895.75 | 0 | 2283.35 | 163 | 28.25
NHT-012009 - Survey | 26-PC-33485 | In progress |  |  | 223624 | 161412.29 | 161412.29 | 939.78 | 4596.53 | 0 | 5536.31 | 1463 | 82.75
NHT-012015 - Curation | 26-PC-33485 | In progress |  |  | 38670 | 27911.88 | 27911.88 | 677.36 | 3313 | 0 | 3990.36 | 293 | 50.75
NHT-012021 - Project Management | 26-PC-33485 | In progress |  |  | 99472 | 71798.56 | 71798.56 | 1099.64 | 5378.41 | 0 | 6478.05 | 658 | 75.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33485 | In progress |  |  | 0 | 0 | 0 | 0 | 657.93 | 0 | 657.93 | 0 | 8.75
NHT-012029 - GIS & Mapping | 26-PC-33505 | In progress |  |  | 41408 | 31992 | 31992 | 64.63 | 284.73 | 0 | 349.36 | 146 | 2.5
NHT-012032 - Prefield | 26-PC-33505 | In progress |  |  | 61845 | 47781.15 | 47781.15 | 148.65 | 654.87 | 0 | 803.52 | 256 | 5.75
NHT-012033 - Final Report | 26-PC-33505 | In progress |  |  | 1847 | 1427.11 | 1427.11 | 0 | 0 | 0 | 0 | 9 | 0
NHT-012037 - Testing | 26-PC-33533 | Completed |  |  | 18795 | 13773.4 | 13773.4 | 2166.56 | 15738.87 | 0 | 17905.43 | 213 | 285.71
NHT-012043 - Site Recordation | 26-PC-33533 | Completed |  |  | 11032 | 8084.12 | 8084.12 | 1271.63 | 9237.72 | 0 | 10509.35 | 120 | 167.15
NHT-012050 - Project Management | 26-PC-33533 | Completed |  |  | 7873 | 5769.04 | 5769.04 | 907.47 | 6592.28 | 0 | 7499.75 | 94 | 116.88
NHT-012053 - Desktop Review | 26-PC-33563 | In progress |  |  | 5508 | 3217.81 | 3794.69 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012060 - Agency Consultation | 26-PC-33563 | In progress |  |  | 5600 | 3271.75 | 3858.29 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012067 - Reporting | 26-PC-33563 | In progress |  |  | 22127 | 12928.01 | 15245.69 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012074 - Prefield | 26-PC-33563 | In progress |  |  | 10122 | 5913.96 | 6974.19 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012081 - Lab Analysis | 26-PC-33563 | In progress |  |  | 17743 | 10366.77 | 12225.28 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012087 - Final Report | 26-PC-33588 | Completed |  |  | 64978 | 38304.65 | 44446.72 | 729.55 | 8749.3 | 0 | 9478.85 | 580 | 178.25
NHT-012089 - Site Recordation | 26-PC-33588 | Completed |  |  | 12851 | 7575.69 | 8790.44 | 302.5 | 3627.76 | 0 | 3930.26 | 144 | 76.75
NHT-012096 - Monitoring | 26-PC-33588 | Completed |  |  | 114957 | 67768.27 | 78634.78 | 693.49 | 8316.73 | 0 | 9010.22 | 998 | 180.25
NHT-012102 - Data Recovery Excavation | 26-PC-33588 | Completed |  |  | 14614 | 8614.99 | 9996.38 | 156.78 | 1880.2 | 0 | 2036.98 | 161 | 38
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33588 | Completed |  |  | 0 | 0 | 0 | 0 | 980.47 | 0 | 980.47 | 0 | 21.25
NHT-012112 - Monitoring | 26-PC-33624 | Completed |  |  | 18155 | 12828.17 | 12828.17 | 1083.98 | 15592.64 | 0 | 16676.62 | 0 | 231.82
NHT-012115 - Desktop Review | 26-PC-33624 | Completed |  |  | 5477 | 3869.96 | 3869.96 | 327.01 | 4703.94 | 0 | 5030.95 | 0 | 99.34
NHT-012122 - Background Research | 26-PC-33624 | Completed |  |  | 4903 | 3464.21 | 3464.21 | 292.73 | 4210.75 | 0 | 4503.48 | 0 | 71.25
NHT-012125 - Site Recordation | 26-PC-33624 | Completed |  |  | 14005 | 9896.23 | 9896.23 | 836.23 | 12028.87 | 0 | 12865.1 | 0 | 202.9
NHT-012130 - Testing | 26-PC-33624 | Completed |  |  | 11960 | 8451.13 | 8451.13 | 714.12 | 10272.34 | 0 | 10986.46 | 0 | 168.18
NHT-012134 - Desktop Review | 26-PC-33660 | In progress |  |  | 23720 | 17022.05 | 20618.8 | 539.59 | 2091.22 | 0 | 2630.81 | 282 | 43
NHT-012141 - Reporting | 26-PC-33660 | In progress |  |  | 56074 | 40241.75 | 48744.81 | 1242.2 | 4814.26 | 0 | 6056.46 | 698 | 100.5
NHT-012143 - Curation | 26-PC-33660 | In progress |  |  | 23688 | 16999.21 | 20591.13 | 2015 | 7809.34 | 0 | 9824.34 | 339 | 156.25
NHT-012148 - Lab Analysis | 26-PC-33660 | In progress |  |  | 4918 | 3528.99 | 4274.67 | 497.97 | 1929.93 | 0 | 2427.9 | 56 | 37.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33660 | In progress |  |  | 0 | 0 | 0 | 0 | 113.22 | 0 | 113.22 | 0 | 3
NHT-012155 - Monitoring | 26-PC-33684 | Completed |  |  | 14852 | 10799.09 | 10799.09 | 144.81 | 1221.37 | 0 | 1366.18 | 175 | 28
NHT-012157 - Agency Consultation | 26-PC-33684 | Completed |  |  | 9148 | 6651.31 | 6651.31 | 120.25 | 1014.16 | 0 | 1134.41 | 86 | 23.25
NHT-012161 - Project Management | 26-PC-33703 | Completed |  |  | 13745 | 11718.2 | 11718.2 | 1373.55 | 7404.51 | 0 | 8778.06 | 120 | 116.5
NHT-012162 - Site Recordation | 26-PC-33703 | Completed |  |  | 4383 | 3737.03 | 3737.03 | 636.19 | 3429.55 | 0 | 4065.74 | 39 | 51.25
NHT-012168 - Survey | 26-PC-33703 | Completed |  |  | 1594 | 1359.34 | 1359.34 | 647.43 | 3490.14 | 0 | 4137.57 | 16 | 48.75
NHT-012173 - Draft Report | 26-PC-33703 | Completed |  |  | 1978 | 1686.85 | 1686.85 | 719.84 | 3880.51 | 0 | 4600.35 | 22 | 59.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33703 | Completed |  |  | 0 | 0 | 0 | 0 | 346.9 | 0 | 346.9 | 0 | 5.25
NHT-012186 - Desktop Review | 26-PC-33705 | In progress |  |  | 112139 | 88556.07 | 88556.07 | 3129.44 | 27985.8 | 0 | 31115.24 | 0 | 461.5
NHT-012192 - Draft Report | 26-PC-33705 | In progress |  |  | 40632 | 32086.91 | 32086.91 | 1251.99 | 11196.29 | 0 | 12448.28 | 0 | 196.25
NHT-012197 - Prefield | 26-PC-33705 | In progress |  |  | 33622 | 26551.52 | 26551.52 | 2157.67 | 19295.58 | 0 | 21453.25 | 0 | 355.5
NHT-012203 - Agency Consultation | 26-PC-33705 | In progress |  |  | 24807 | 19590.14 | 19590.14 | 1406.39 | 12577.02 | 0 | 13983.41 | 0 | 224.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33705 | In progress |  |  | 0 | 0 | 0 | 0 | 1257.27 | 0 | 1257.27 | 0 | 21.5
NHT-012212 - Final Report | 26-PC-33719 | In progress |  |  | 63521 | 49990.91 | 49990.91 | 262.24 | 1010.79 | 0 | 1273.03 | 1199 | 24.75
NHT-012218 - Data Recovery Excavation | 26-PC-33719 | In progress |  |  | 87535 | 68889.96 | 68889.96 | 262.24 | 1010.79 | 0 | 1273.03 | 1624 | 24.75
NHT-012220 - Reporting | 26-PC-33719 | In progress |  |  | 88915 | 69976.43 | 69976.43 | 610.78 | 2354.15 | 0 | 2964.93 | 1842 | 53.75
NHT-012225 - Agency Consultation | 26-PC-33719 | In progress |  |  | 107048 | 84246.74 | 84246.74 | 450.32 | 1735.7 | 0 | 2186.02 | 2593 | 42.5
NHT-012231 - Project Management | 26-PC-33719 | In progress |  |  | 47181 | 37131.36 | 37131.36 | 243.35 | 937.96 | 0 | 1181.31 | 923 | 21.75
NHT-012232 - Lab Analysis | 26-PC-33727 | Completed |  |  | 123904 | 97685.99 | 97685.99 | 8157.16 | 82477.99 | 0 | 90635.15 | 1062 | 1378.38
NHT-012239 - Project Management | 26-PC-33727 | Completed |  |  | 61296 | 48325.69 | 48325.69 | 4035.39 | 40802.23 | 0 | 44837.62 | 631 | 769.43
NHT-012243 - Reporting | 26-PC-33743 | In progress |  |  | 98341 | 66645.36 | 66645.36 | 2545.88 | 20304.68 | 0 | 22850.56 | 452 | 327
NHT-012249 - Lab Analysis | 26-PC-33743 | In progress |  |  | 13459 | 9121.5 | 9121.5 | 1855.95 | 14802.13 | 0 | 16658.08 | 59 | 224.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33743 | In progress |  |  | 0 | 0 | 0 | 0 | 2018.1 | 0 | 2018.1 | 0 | 28.75
NHT-012252 - Lab Analysis | 26-PC-33773 | On hold |  |  | 13193 | 8156.18 | 8156.18 | 0 | 0 | 0 | 0 | 98 | 0
NHT-012255 - Background Research | 26-PC-33773 | On hold |  |  | 5214 | 3222.99 | 3222.99 | 0 | 0 | 0 | 0 | 46 | 0
NHT-012257 - Monitoring | 26-PC-33773 | On hold |  |  | 22793 | 14090.67 | 14090.67 | 0 | 0 | 0 | 0 | 201 | 0
NHT-012259 - Prefield | 26-PC-33834 | In progress |  |  | 8388 | 5583.01 | 6472.97 | 662.45 | 3361.41 | 0 | 4023.86 | 136 | 76.5
NHT-012261 - Background Research | 26-PC-33834 | In progress |  |  | 16212 | 10791.24 | 12511.41 | 1398.5 | 7096.31 | 0 | 8494.81 | 246 | 160
NHT-012264 - Curation | 26-PC-33834 | In progress |  |  | 9579 | 6376.33 | 7392.75 | 444.88 | 2257.42 | 0 | 2702.3 | 163 | 47
NHT-012266 - Survey | 26-PC-33834 | In progress |  |  | 67662 | 45038.2 | 52217.51 | 1640.96 | 8326.63 | 0 | 9967.59 | 1123 | 189.5
NHT-012270 - Monitoring | 26-PC-33834 | In progress |  |  | 102959 | 68533.01 | 79457.51 | 2002.49 | 10161.13 | 0 | 12163.62 | 1678 | 231.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-33834 | In progress |  |  | 0 | 0 | 0 | 0 | 373.49 | 0 | 373.49 | 0 | 8.5
NHT-012272 - Final Report | 26-PC-33896 | In progress |  |  | 69800 | 48734.36 | 48734.36 | 1902.77 | 13319.38 | 0 | 15222.15 | 518 | 173.75
NHT-012276 - Background Research | 26-PC-33903 | Completed |  |  | 514787 | 392628.02 | 392628.02 | 66617.94 | 363175.2 | 0 | 429793.14 | 4828 | 5600.66
NHT-012278 - Prefield | 26-PC-33903 | Completed |  |  | 686313 | 523450.95 | 523450.95 | 88814.91 | 484184.51 | 0 | 572999.42 | 7412 | 9103.91
NHT-012284 - Background Research | 26-PC-33913 | Completed |  |  | 30252 | 19469.99 | 19469.99 | 200.81 | 933.69 | 0 | 1134.5 | 272 | 12.25
NHT-012285 - Curation | 26-PC-33913 | Completed |  |  | 78 | 50.4 | 50.4 | 0 | 0 | 0 | 0 | 1 | 0
NHT-012291 - Reporting | 26-PC-33913 | Completed |  |  | 235 | 151.19 | 151.19 | 0 | 0 | 0 | 0 | 2 | 0
NHT-012292 - Draft Report | 26-PC-33913 | Completed |  |  | 209 | 134.39 | 134.39 | 0 | 0 | 0 | 0 | 1 | 0
NHT-012295 - Monitoring | 26-PC-33913 | Completed |  |  | 326 | 209.99 | 209.99 | 0 | 0 | 0 | 0 | 2 | 0
NHT-012302 - Testing | 26-PC-33950 | Completed |  |  | 120148 | 92550.34 | 92550.34 | 10798.54 | 65247.49 | 0 | 76046.03 | 846 | 1096.74
NHT-012303 - Monitoring | 26-PC-33950 | Completed |  |  | 124306 | 95752.73 | 95752.73 | 11172.18 | 67505.15 | 0 | 78677.33 | 871 | 1037.95
NHT-012304 - Project Management | 26-PC-33950 | Completed |  |  | 53098 | 40901.59 | 40901.59 | 4772.29 | 28835.4 | 0 | 33607.69 | 344 | 360.16
NHT-012305 - Reporting | 26-PC-33950 | Completed |  |  | 73591 | 56687.04 | 56687.04 | 6614.1 | 39964.06 | 0 | 46578.16 | 689 | 682.56
NHT-012306 - Survey | 26-PC-33950 | Completed |  |  | 112557 | 86702.41 | 86702.41 | 10116.21 | 61124.72 | 0 | 71240.93 | 903 | 972.04
NHT-012313 - Monitoring | 26-PC-34101 | In progress |  |  | 23539 | 14371.63 | 16356.14 | 3679.53 | 18503.2 | 0 | 22182.73 | 0 | 279.25
NHT-012320 - Background Research | 26-PC-34101 | Completed |  |  | 33182 | 20260.05 | 23057.66 | 4783.75 | 24055.9 | 0 | 28839.65 | 0 | 363.5
NHT-012324 - Desktop Review | 26-PC-34101 | Completed |  |  | 19679 | 12014.96 | 13674.05 | 4569.86 | 22980.37 | 0 | 27550.23 | 0 | 339.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34101 | In progress |  |  | 0 | 0 | 0 | 0 | 2378.57 | 0 | 2378.57 | 0 | 35.5
NHT-012337 - Monitoring | 26-PC-34114 | In progress |  |  | 84793 | 57108.34 | 57108.34 | 84.1 | 1297.04 | 0 | 1381.14 | 1609 | 31
NHT-012338 - Desktop Review | 26-PC-34114 | In progress |  |  | 41031 | 27634.33 | 27634.33 | 215.78 | 3328.03 | 0 | 3543.81 | 715 | 80
NHT-012344 - Lab Analysis | 26-PC-34114 | In progress |  |  | 6135 | 4131.69 | 4131.69 | 20.41 | 314.73 | 0 | 335.14 | 113 | 7.75
NHT-012345 - Background Research | 26-PC-34114 | In progress |  |  | 44976 | 30291.43 | 30291.43 | 195.47 | 3014.68 | 0 | 3210.15 | 780 | 71.75
NHT-012346 - Survey | 26-PC-34114 | In progress |  |  | 39565 | 26646.96 | 26646.96 | 67.14 | 1035.56 | 0 | 1102.7 | 678 | 25.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34114 | In progress |  |  | 0 | 0 | 0 | 0 | 142.13 | 0 | 142.13 | 0 | 3.5
NHT-012356 - Monitoring | 26-PC-34198 | In progress |  |  | 65600 | 47297.6 | 47297.6 | 783.39 | 8160.14 | 0 | 8943.53 | 583 | 167.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34198 | In progress |  |  | 0 | 0 | 0 | 0 | 60.99 | 0 | 60.99 | 0 | 1.25
NHT-012363 - Desktop Review | 26-PC-34247 | Completed |  |  | 9723 | 6716.51 | 6716.51 | 1833.61 | 6897.86 | 0 | 8731.47 | 73 | 111.95
NHT-012366 - GIS & Mapping | 26-PC-34247 | Completed |  |  | 17597 | 12156.19 | 12156.19 | 3318.64 | 12484.4 | 0 | 15803.04 | 103 | 221.81
NHT-012368 - Background Research | 26-PC-34247 | Completed |  |  | 12654 | 8741.17 | 8741.17 | 2386.34 | 8977.18 | 0 | 11363.52 | 89 | 131.92
NHT-012370 - Testing | 26-PC-34247 | Completed |  |  | 30799 | 21276.01 | 21276.01 | 5808.35 | 21850.46 | 0 | 27658.81 | 314 | 334.96
NHT-012372 - Survey | 26-PC-34247 | Completed |  |  | 35427 | 24473.08 | 24473.08 | 6681.15 | 25133.86 | 0 | 31815.01 | 279 | 410.05
NHT-012374 - Desktop Review | 26-PC-34297 | In progress |  |  | 41700 | 29306.76 | 29306.76 | 198.87 | 2256.3 | 0 | 2455.17 | 611 | 51.75
NHT-012376 - Desktop Review | 26-PC-34336 | In progress |  |  | 21014 | 15031.51 | 15031.51 | 806.93 | 5628.92 | 0 | 6435.85 | 285 | 137.75
NHT-012379 - Final Report | 26-PC-34336 | In progress |  |  | 9638 | 6894.28 | 6894.28 | 360.43 | 2514.28 | 0 | 2874.71 | 118 | 61.5
NHT-012380 - Data Recovery Excavation | 26-PC-34336 | In progress |  |  | 25848 | 18488.66 | 18488.66 | 317.67 | 2215.96 | 0 | 2533.63 | 369 | 54.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34336 | In progress |  |  | 0 | 0 | 0 | 0 | 428.82 | 0 | 428.82 | 0 | 10.5
NHT-012394 - Desktop Review | 26-PC-34394 | In progress |  |  | 9131 | 5486.02 | 6421.04 | 0 | 0 | 0 | 0 | 45 | 0
NHT-012399 - Final Report | 26-PC-34394 | In progress |  |  | 14499 | 8711.33 | 10196.07 | 0 | 0 | 0 | 0 | 99 | 0
NHT-012405 - GIS & Mapping | 26-PC-34394 | In progress |  |  | 23309 | 14003.96 | 16390.77 | 0 | 0 | 0 | 0 | 185 | 0
NHT-012406 - Draft Report | 26-PC-34394 | In progress |  |  | 44828 | 26933.06 | 31523.48 | 0 | 0 | 0 | 0 | 294 | 0
NHT-012413 - Reporting | 26-PC-34394 | In progress |  |  | 42433 | 25493.66 | 29838.75 | 0 | 0 | 0 | 0 | 261 | 0
NHT-012416 - Fieldwork | 26-PC-34400 | In progress |  |  | 4093 | 2481.75 | 2852.53 | 57.48 | 238.8 | 0 | 296.28 | 20 | 2
NHT-012421 - Agency Consultation | 26-PC-34400 | In progress |  |  | 1451 | 879.81 | 1011.26 | 28.74 | 119.4 | 0 | 148.14 | 5 | 1
NHT-012422 - Curation | 26-PC-34400 | In progress |  |  | 28656 | 17374.09 | 19969.77 | 193.98 | 805.95 | 0 | 999.93 | 133 | 6.75
NHT-012423 - Desktop Review | 26-PC-34432 | Completed |  |  | 19348 | 13230.05 | 13230.05 | 807.58 | 3151.15 | 0 | 3958.73 | 145 | 52.75
NHT-012427 - Lab Analysis | 26-PC-34432 | Completed |  |  | 97540 | 66697.85 | 66697.85 | 621.69 | 2425.81 | 0 | 3047.5 | 637 | 49.75
NHT-012429 - Agency Consultation | 26-PC-34432 | Completed |  |  | 1012 | 692.12 | 692.12 | 0 | 0 | 0 | 0 | 8 | 0
NHT-012431 - Testing | 26-PC-34472 | Completed |  |  | 25400 | 13601.12 | 16500.99 | 2180.63 | 12755.17 | 0 | 14935.8 | 284 | 209.3
NHT-012438 - Lab Analysis | 26-PC-34477 | In progress |  |  | 89371 | 66089.65 | 66089.65 | 710.72 | 7483.61 | 0 | 8194.33 | 1267 | 144.25
NHT-012441 - Fieldwork | 26-PC-34477 | In progress |  |  | 123129 | 91054.1 | 91054.1 | 765.6 | 8061.41 | 0 | 8827.01 | 1331 | 148
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34477 | In progress |  |  | 0 | 0 | 0 | 0 | 347.14 | 0 | 347.14 | 0 | 8.5
NHT-012444 - Project Management | 26-PC-34487 | In progress |  |  | 488600 | 348176.36 | 348176.36 | 11687.65 | 120236.43 | 0 | 131924.08 | 7902 | 2182
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34487 | In progress |  |  | 0 | 0 | 0 | 0 | 3978.79 | 0 | 3978.79 | 0 | 67.75
NHT-012457 - Survey | 26-PC-34552 | Completed |  |  | 219768 | 183615.9 | 183615.9 | 499.03 | 2854.23 | 0 | 3353.26 | 3892 | 58.5
NHT-012458 - Final Report | 26-PC-34552 | Completed |  |  | 25732 | 21499.35 | 21499.35 | 40.52 | 231.75 | 0 | 272.27 | 465 | 4.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34552 | Completed |  |  | 0 | 0 | 0 | 0 | 256.15 | 0 | 256.15 | 0 | 5.25
NHT-012470 - Reporting | 26-PC-34574 | Completed |  |  | 335007 | 233064.66 | 233064.66 | 15608.56 | 236142.4 | 0 | 251750.96 | 4880 | 3748.56
NHT-012473 - Agency Consultation | 26-PC-34574 | Completed |  |  | 95546 | 66471.23 | 66471.23 | 4451.64 | 67349.01 | 0 | 71800.65 | 1002 | 1007.5
NHT-012480 - Prefield | 26-PC-34574 | Completed |  |  | 216896 | 150894.21 | 150894.21 | 10105.53 | 152886.85 | 0 | 162992.38 | 2240 | 2315.58
NHT-012482 - Background Research | 26-PC-34574 | Completed |  |  | 118242 | 82260.63 | 82260.63 | 5509.07 | 83346.92 | 0 | 88855.99 | 1236 | 1188.95
NHT-012486 - Monitoring | 26-PC-34574 | Completed |  |  | 591709 | 411652.45 | 411652.45 | 27568.75 | 417088.53 | 0 | 444657.28 | 7659 | 6964.01
NHT-012490 - Testing | 26-PC-34602 | In progress |  |  | 36800 | 21328.5 | 26501.12 | 2257.67 | 20716.08 | 0 | 22973.75 | 239 | 361
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34602 | In progress |  |  | 0 | 0 | 0 | 0 | 301.19 | 0 | 301.19 | 0 | 5.25
NHT-012498 - Curation | 26-PC-34611 | In progress |  |  | 59388 | 42890.17 | 42890.17 | 0 | 0 | 0 | 0 | 737 | 0
NHT-012501 - Lab Analysis | 26-PC-34611 | In progress |  |  | 93471 | 67504.54 | 67504.54 | 0 | 0 | 0 | 0 | 1150 | 0
NHT-012505 - Site Recordation | 26-PC-34611 | In progress |  |  | 80199 | 57919.77 | 57919.77 | 0 | 0 | 0 | 0 | 1070 | 0
NHT-012506 - GIS & Mapping | 26-PC-34611 | In progress |  |  | 81869 | 59125.5 | 59125.5 | 0 | 0 | 0 | 0 | 985 | 0
NHT-012510 - Background Research | 26-PC-34611 | In progress |  |  | 50873 | 36740.78 | 36740.78 | 0 | 0 | 0 | 0 | 601 | 0
NHT-012515 - Monitoring | 26-PC-34628 | Completed |  |  | 38890 | 25640 | 25640 | 3872.28 | 20179.12 | 0 | 24051.4 | 210 | 317.17
NHT-012520 - Prefield | 26-PC-34628 | Completed |  |  | 10784 | 7109.72 | 7109.72 | 1073.74 | 5595.47 | 0 | 6669.21 | 65 | 93.37
NHT-012523 - Data Recovery Excavation | 26-PC-34628 | Completed |  |  | 30375 | 20026.31 | 20026.31 | 3024.47 | 15761.04 | 0 | 18785.51 | 191 | 263.77
NHT-012528 - Lab Analysis | 26-PC-34628 | Completed |  |  | 16260 | 10720.4 | 10720.4 | 1619.04 | 8437.13 | 0 | 10056.17 | 92 | 154.62
NHT-012529 - Draft Report | 26-PC-34628 | Completed |  |  | 25191 | 16608.52 | 16608.52 | 2508.3 | 13071.18 | 0 | 15579.48 | 168 | 195.47
NHT-012531 - Prefield | 26-PC-34631 | Completed |  |  | 438600 | 344257.14 | 344257.14 | 52560.64 | 286540.26 | 0 | 339100.9 | 3690 | 4753.55
NHT-012535 - Draft Report | 26-PC-34701 | Completed |  |  | 248300 | 138920.73 | 162629.9 | 36152.63 | 175266.24 | 0 | 211418.87 | 1594 | 2982.55
NHT-012539 - Draft Report | 26-PC-34711 | Completed |  |  | 6554 | 4927.1 | 4927.1 | 580.67 | 3627.06 | 0 | 4207.73 | 0 | 73.36
NHT-012546 - Fieldwork | 26-PC-34711 | Completed |  |  | 8699 | 6540.21 | 6540.21 | 770.77 | 4814.55 | 0 | 5585.32 | 0 | 78.28
NHT-012548 - Survey | 26-PC-34711 | Completed |  |  | 9459 | 7111.45 | 7111.45 | 838.1 | 5235.07 | 0 | 6073.17 | 0 | 97.72
NHT-012551 - Project Management | 26-PC-34711 | Completed |  |  | 2253 | 1693.84 | 1693.84 | 199.62 | 1246.92 | 0 | 1446.54 | 0 | 20.41
NHT-012556 - Testing | 26-PC-34711 | Completed |  |  | 7035 | 5288.6 | 5288.6 | 623.27 | 3893.18 | 0 | 4516.45 | 0 | 60.29
NHT-012557 - Prefield | 26-PC-34725 | In progress |  |  | 107600 | 89211.16 | 89211.16 | 681.13 | 8355.81 | 0 | 9036.94 | 1060 | 124.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34725 | In progress |  |  | 0 | 0 | 0 | 0 | 979.69 | 0 | 979.69 | 0 | 13.5
NHT-012569 - Project Management | 26-PC-34757 | Completed |  |  | 3406 | 2350.97 | 2350.97 | 1712.66 | 8604.55 | 0 | 10317.21 | 22 | 124.5
NHT-012576 - Background Research | 26-PC-34757 | In progress |  |  | 6885 | 4752.25 | 4752.25 | 965.4 | 4850.26 | 0 | 5815.66 | 46 | 69.75
NHT-012579 - Data Recovery Excavation | 26-PC-34757 | Completed |  |  | 1406 | 970.65 | 970.65 | 430.33 | 2162.02 | 0 | 2592.35 | 10 | 25.25
NHT-012586 - Site Recordation | 26-PC-34757 | In progress |  |  | 24205 | 16705.72 | 16705.72 | 2261.47 | 11361.85 | 0 | 13623.32 | 143 | 170.25
NHT-012588 - Testing | 26-PC-34757 | In progress |  |  | 7898 | 5451.17 | 5451.17 | 2848.51 | 14311.2 | 0 | 17159.71 | 60 | 207.25
NHT-012589 - GIS & Mapping | 26-PC-34794 | Completed |  |  | 40000 | 25252 | 25252 | 4792.83 | 28034.77 | 0 | 32827.6 | 407 | 524.71
NHT-012590 - Project Management | 26-PC-34906 | In progress |  |  | 81100 | 44369.15 | 60821.43 | 2517.76 | 27930.21 | 0 | 30447.97 | 1147 | 588
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34906 | In progress |  |  | 0 | 0 | 0 | 0 | 1023.99 | 0 | 1023.99 | 0 | 21.75
NHT-012603 - Fieldwork | 26-PC-34965 | Completed |  |  | 131600 | 95225.76 | 95225.76 | 0 | 0 | 0 | 0 | 824 | 0
NHT-012610 - Monitoring | 26-PC-34982 | Completed |  |  | 10600 | 7895.94 | 7895.94 | 1580.72 | 16163.81 | 0 | 17744.53 | 110 | 235.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-34982 | In progress |  |  | 0 | 0 | 0 | 0 | 1073.56 | 0 | 1073.56 | 0 | 11.75
NHT-012619 - Monitoring | 26-PC-35012 | Completed |  |  | 71918 | 52140.37 | 52140.37 | 10394.7 | 51849.05 | 0 | 62243.75 | 0 | 1072.57
NHT-012626 - Curation | 26-PC-35012 | Completed |  |  | 26384 | 19128.48 | 19128.48 | 3813.46 | 19021.61 | 0 | 22835.07 | 0 | 347.02
NHT-012633 - Lab Analysis | 26-PC-35012 | Completed |  |  | 51066 | 37022.95 | 37022.95 | 7380.9 | 36816.1 | 0 | 44197 | 0 | 769.31
NHT-012640 - Prefield | 26-PC-35012 | Completed |  |  | 30332 | 21990.7 | 21990.7 | 4384.07 | 21867.84 | 0 | 26251.91 | 0 | 416.04
NHT-012647 - Agency Consultation | 26-PC-35056 | Completed |  |  | 77728 | 65796.93 | 65796.93 | 3683.11 | 17036.88 | 0 | 20719.99 | 865 | 413.75
NHT-012654 - Prefield | 26-PC-35056 | Completed |  |  | 15072 | 12758.27 | 12758.27 | 3266.13 | 15108.11 | 0 | 18374.24 | 167 | 365.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35056 | Completed |  |  | 0 | 0 | 0 | 0 | 166.99 | 0 | 166.99 | 0 | 3.5
NHT-012666 - Prefield | 26-PC-35062 | In progress |  |  | 53954 | 37539.76 | 41892.21 | 834.67 | 4248.39 | 0 | 5083.06 | 455 | 79
NHT-012667 - Agency Consultation | 26-PC-35062 | In progress |  |  | 60186 | 41875.71 | 46730.9 | 607.24 | 3090.81 | 0 | 3698.05 | 526 | 61.75
NHT-012668 - GIS & Mapping | 26-PC-35062 | In progress |  |  | 6701 | 4662.37 | 5202.94 | 108.36 | 551.52 | 0 | 659.88 | 75 | 8
NHT-012674 - Site Recordation | 26-PC-35062 | In progress |  |  | 31697 | 22053.89 | 24610.88 | 781.79 | 3979.21 | 0 | 4761 | 304 | 64.25
NHT-012677 - Testing | 26-PC-35062 | In progress |  |  | 114762 | 79847.42 | 89105.13 | 1453.37 | 7397.51 | 0 | 8850.88 | 768 | 116.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35062 | In progress |  |  | 0 | 0 | 0 | 0 | 754.86 | 0 | 754.86 | 0 | 12.25
NHT-012683 - Site Recordation | 26-PC-35063 | Completed |  |  | 9189 | 5748.9 | 5748.9 | 817.53 | 6063.91 | 0 | 6881.44 | 0 | 154.5
NHT-012686 - Curation | 26-PC-35063 | Completed |  |  | 18766 | 11739.84 | 11739.84 | 1411.3 | 10468.09 | 0 | 11879.39 | 0 | 261.75
NHT-012692 - Background Research | 26-PC-35063 | Completed |  |  | 7776 | 4864.64 | 4864.64 | 746.13 | 5534.33 | 0 | 6280.46 | 0 | 136.5
NHT-012693 - Reporting | 26-PC-35063 | Completed |  |  | 31905 | 19959.86 | 19959.86 | 548.82 | 4070.78 | 0 | 4619.6 | 0 | 103.5
NHT-012694 - Data Recovery Excavation | 26-PC-35063 | Completed |  |  | 44464 | 27816.52 | 27816.52 | 844.17 | 6261.52 | 0 | 7105.69 | 0 | 143
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35063 | Completed |  |  | 0 | 0 | 0 | 0 | 249.91 | 0 | 249.91 | 0 | 6.25
NHT-012705 - Data Recovery Excavation | 26-PC-35103 | In progress |  |  | 9702 | 6321.51 | 6321.51 | 4933.95 | 19726.6 | 0 | 24660.55 | 85 | 329.75
NHT-012710 - Fieldwork | 26-PC-35103 | Completed |  |  | 13055 | 8507.24 | 8507.24 | 3572.27 | 14282.42 | 0 | 17854.69 | 111 | 242.5
NHT-012714 - Survey | 26-PC-35103 | Completed |  |  | 6843 | 4458.61 | 4458.61 | 2413.51 | 9649.52 | 0 | 12063.03 | 56 | 141.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35103 | In progress |  |  | 0 | 0 | 0 | 0 | 1709.01 | 0 | 1709.01 | 0 | 23.75
NHT-012728 - Fieldwork | 26-PC-35111 | Completed |  |  | 114800 | 81129.16 | 81129.16 | 9285.48 | 64408.83 | 0 | 73694.31 | 683 | 1250.58
NHT-012731 - Agency Consultation | 26-PC-35158 | In progress |  |  | 14744 | 8558.67 | 9837.63 | 502.2 | 2658.8 | 0 | 3161 | 105 | 37.5
NHT-012737 - Desktop Review | 26-PC-35158 | In progress |  |  | 214 | 124.39 | 142.98 | 0 | 0 | 0 | 0 | 2 | 0
NHT-012740 - Background Research | 26-PC-35158 | In progress |  |  | 20751 | 12044.95 | 13844.87 | 371.62 | 1967.44 | 0 | 2339.06 | 155 | 22
NHT-012746 - Monitoring | 26-PC-35158 | In progress |  |  | 5891 | 3419.47 | 3930.45 | 390.2 | 2065.82 | 0 | 2456.02 | 47 | 23.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35158 | In progress |  |  | 0 | 0 | 0 | 0 | 470.69 | 0 | 470.69 | 0 | 6.25
NHT-012755 - Curation | 26-PC-35193 | In progress |  |  | 102600 | 54115.25 | 74022.89 | 6964.72 | 51986.52 | 0 | 58951.24 | 1368 | 1062
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35193 | In progress |  |  | 0 | 0 | 0 | 0 | 576.26 | 0 | 576.26 | 0 | 14
NHT-012766 - Agency Consultation | 26-PC-35201 | Completed |  |  | 17492 | 13578.79 | 13578.79 | 19.14 | 188.86 | 0 | 208 | 0 | 4.75
NHT-012768 - Testing | 26-PC-35201 | Completed |  |  | 34108 | 26478.29 | 26478.29 | 92.32 | 911.15 | 0 | 1003.47 | 0 | 24.5
NHT-012772 - Survey | 26-PC-35220 | In progress |  |  | 68439 | 43499.61 | 43499.61 | 187.31 | 677.91 | 0 | 865.22 | 614 | 14.75
NHT-012776 - Reporting | 26-PC-35220 | In progress |  |  | 7383 | 4692.7 | 4692.7 | 61.99 | 224.34 | 0 | 286.33 | 74 | 5.5
NHT-012781 - Curation | 26-PC-35220 | In progress |  |  | 451 | 286.71 | 286.71 | 0 | 0 | 0 | 0 | 4 | 0
NHT-012782 - Data Recovery Excavation | 26-PC-35220 | In progress |  |  | 32776 | 20832.47 | 20832.47 | 380.97 | 1378.8 | 0 | 1759.77 | 292 | 30
NHT-012787 - Background Research | 26-PC-35220 | In progress |  |  | 451 | 286.71 | 286.71 | 0 | 0 | 0 | 0 | 5 | 0
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35220 | In progress |  |  | 0 | 0 | 0 | 0 | 163.16 | 0 | 163.16 | 0 | 4
NHT-012796 - Data Recovery Excavation | 26-PC-35245 | Completed |  |  | 81709 | 55096.45 | 55096.45 | 11623.92 | 41942.53 | 0 | 53566.45 | 0 | 890.48
NHT-012797 - Fieldwork | 26-PC-35245 | Completed |  |  | 96262 | 64910.04 | 64910.04 | 13694.33 | 49413.2 | 0 | 63107.53 | 0 | 860.98
NHT-012801 - GIS & Mapping | 26-PC-35245 | Completed |  |  | 33564 | 22631.88 | 22631.88 | 4774.74 | 17228.67 | 0 | 22003.41 | 0 | 286.52
NHT-012807 - Project Management | 26-PC-35245 | Completed |  |  | 29365 | 19800.5 | 19800.5 | 4177.39 | 15073.26 | 0 | 19250.65 | 0 | 301.26
NHT-012808 - GIS & Mapping | 26-PC-35248 | Completed |  |  | 107400 | 75437.76 | 75437.76 | 7515.76 | 58411.94 | 0 | 65927.7 | 855 | 1037.73
NHT-012810 - Site Recordation | 26-PC-35302 | In progress |  |  | 14822 | 12447.12 | 12447.12 | 926.84 | 3650.44 | 0 | 4577.28 | 211 | 86
NHT-012813 - Fieldwork | 26-PC-35302 | In progress |  |  | 35108 | 29484.48 | 29484.48 | 1289.51 | 5078.82 | 0 | 6368.33 | 463 | 120.5
NHT-012819 - Project Management | 26-PC-35302 | In progress |  |  | 13294 | 11163.92 | 11163.92 | 1267 | 4990.17 | 0 | 6257.17 | 180 | 113.25
NHT-012826 - Data Recovery Excavation | 26-PC-35302 | In progress |  |  | 19176 | 16104 | 16104 | 1967.39 | 7748.76 | 0 | 9716.15 | 240 | 180
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35302 | In progress |  |  | 0 | 0 | 0 | 0 | 199.2 | 0 | 199.2 | 0 | 4.25
NHT-012839 - Final Report | 26-PC-35318 | In progress |  |  | 97448 | 65758.18 | 65758.18 | 1565.33 | 14321.33 | 0 | 15886.66 | 1240 | 329.75
NHT-012841 - Background Research | 26-PC-35318 | In progress |  |  | 56452 | 38093.54 | 38093.54 | 900.57 | 8239.35 | 0 | 9139.92 | 694 | 184.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35318 | In progress |  |  | 0 | 0 | 0 | 0 | 135.63 | 0 | 135.63 | 0 | 2.75
NHT-012846 - Draft Report | 26-PC-35381 | In progress |  |  | 38296 | 22334.73 | 25136 | 804.7 | 11295.02 | 0 | 12099.72 | 336 | 207.75
NHT-012847 - Site Recordation | 26-PC-35381 | Completed |  |  | 21214 | 12372.2 | 13923.96 | 1148.17 | 16115.98 | 0 | 17264.15 | 161 | 263
NHT-012852 - Final Report | 26-PC-35381 | In progress |  |  | 18290 | 10667.07 | 12004.97 | 482.32 | 6769.95 | 0 | 7252.27 | 160 | 133.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35381 | In progress |  |  | 0 | 0 | 0 | 0 | 280.66 | 0 | 280.66 | 0 | 6.75
NHT-012863 - Final Report | 26-PC-35401 | In progress |  |  | 312900 | 152268.46 | 205376.26 | 2278.13 | 19031.64 | 0 | 21309.77 | 1873 | 311.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35401 | In progress |  |  | 0 | 0 | 0 | 0 | -215.94 | 0 | -215.94 | 0 | -0.5
NHT-012867 - Site Recordation | 26-PC-35449 | In progress |  |  | 62825 | 44480.06 | 44480.06 | 1918.42 | 7346.52 | 0 | 9264.94 | 387 | 113.25
NHT-012871 - Reporting | 26-PC-35449 | In progress |  |  | 82975 | 58746.34 | 58746.34 | 2637.36 | 10099.66 | 0 | 12737.02 | 513 | 140.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35449 | In progress |  |  | 0 | 0 | 0 | 0 | 113.47 | 0 | 113.47 | 0 | 1
NHT-012883 - Reporting | 26-PC-35510 | In progress |  |  | 16298 | 12697.67 | 12697.67 | 815.64 | 9195.94 | 0 | 10011.58 | 192 | 173.25
NHT-012889 - Desktop Review | 26-PC-35510 | Completed |  |  | 8864 | 6905.66 | 6905.66 | 869.75 | 9806.11 | 0 | 10675.86 | 82 | 244.25
NHT-012893 - Agency Consultation | 26-PC-35510 | Completed |  |  | 18818 | 14661.2 | 14661.2 | 1238.69 | 13965.74 | 0 | 15204.43 | 168 | 293.25
NHT-012898 - Fieldwork | 26-PC-35510 | In progress |  |  | 24920 | 19415.46 | 19415.46 | 786.34 | 8865.63 | 0 | 9651.97 | 304 | 176.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35510 | In progress |  |  | 0 | 0 | 0 | 0 | 836.44 | 0 | 836.44 | 0 | 18.5
NHT-012909 - Curation | 26-PC-35583 | In progress |  |  | 1654 | 1189.01 | 1189.01 | 0 | 0 | 0 | 0 | 22 | 0
NHT-012914 - Desktop Review | 26-PC-35583 | In progress |  |  | 1378 | 990.85 | 990.85 | 0 | 0 | 0 | 0 | 19 | 0
NHT-012915 - Agency Consultation | 26-PC-35583 | In progress |  |  | 36668 | 26356.5 | 26356.5 | 239.66 | 1230.63 | 0 | 1470.29 | 450 | 28.5
NHT-012922 - Lab Analysis | 26-PC-35588 | Completed |  |  | 112287 | 98318.38 | 98318.38 | 12142.32 | 115671.57 | 0 | 127813.89 | 982 | 2424.92
NHT-012929 - Curation | 26-PC-35588 | Completed |  |  | 36513 | 31970.9 | 31970.9 | 3948.41 | 37613.76 | 0 | 41562.17 | 321 | 711.39
NHT-012934 - Fieldwork | 26-PC-35596 | Completed |  |  | 89259 | 67506.63 | 67506.63 | 1755.68 | 13645 | 0 | 15400.68 | 1351 | 315.25
NHT-012935 - Reporting | 26-PC-35596 | Completed |  |  | 107941 | 81635.73 | 81635.73 | 1877.6 | 14592.57 | 0 | 16470.17 | 2244 | 326.75
NHT-012937 - Desktop Review | 26-PC-35598 | Completed |  |  | 5409 | 3825.01 | 3825.01 | 512.17 | 4460.34 | 0 | 4972.51 | 55 | 79.98
NHT-012943 - Reporting | 26-PC-35598 | Completed |  |  | 16691 | 11801.9 | 11801.9 | 1580.27 | 13762.2 | 0 | 15342.47 | 232 | 254.33
NHT-012946 - Curation | 26-PC-35635 | In progress |  |  | 33409 | 20753.57 | 20753.57 | 769.29 | 9156.7 | 0 | 9925.99 | 0 | 198.5
NHT-012949 - Project Management | 26-PC-35635 | In progress |  |  | 72605 | 45102.19 | 45102.19 | 722.27 | 8596.96 | 0 | 9319.23 | 0 | 175
NHT-012952 - Fieldwork | 26-PC-35635 | In progress |  |  | 41836 | 25988.58 | 25988.58 | 907.91 | 10806.56 | 0 | 11714.47 | 0 | 202.5
NHT-012955 - Data Recovery Excavation | 26-PC-35635 | In progress |  |  | 75750 | 47055.98 | 47055.98 | 564.95 | 6724.49 | 0 | 7289.44 | 0 | 138.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35635 | In progress |  |  | 0 | 0 | 0 | 0 | 1810.57 | 0 | 1810.57 | 0 | 37.75
NHT-012965 - Final Report | 26-PC-35650 | In progress |  |  | 19165 | 11530.97 | 12417.69 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012970 - Testing | 26-PC-35650 | In progress |  |  | 50852 | 30596.61 | 32949.46 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012972 - Monitoring | 26-PC-35650 | In progress |  |  | 85283 | 51313.57 | 55259.51 | 0 | 0 | 0 | 0 | 0 | 0
NHT-012973 - Monitoring | 26-PC-35698 | Completed |  |  | 129780 | 71024.39 | 89197.66 | 15074.4 | 100882.55 | 0 | 115956.95 | 1109 | 1662.64
NHT-012980 - Project Management | 26-PC-35698 | Completed |  |  | 48911 | 26767.59 | 33616.72 | 5681.23 | 38020.51 | 0 | 43701.74 | 360 | 686.77
NHT-012987 - Testing | 26-PC-35698 | Completed |  |  | 95309 | 52159.78 | 65506.1 | 11070.53 | 74087.4 | 0 | 85157.93 | 789 | 1635.71
NHT-012990 - Draft Report | 26-PC-35730 | In progress |  |  | 655 | 438.75 | 438.75 | 0 | 0 | 0 | 0 | 6 | 0
NHT-012992 - Reporting | 26-PC-35730 | In progress |  |  | 737 | 493.59 | 493.59 | 0 | 0 | 0 | 0 | 8 | 0
NHT-012995 - Survey | 26-PC-35730 | In progress |  |  | 62036 | 41533.04 | 41533.04 | 254.77 | 924.74 | 0 | 1179.51 | 731 | 24
NHT-012996 - Agency Consultation | 26-PC-35730 | In progress |  |  | 205 | 137.11 | 137.11 | 0 | 0 | 0 | 0 | 2 | 0
NHT-013000 - GIS & Mapping | 26-PC-35730 | In progress |  |  | 11167 | 7476.11 | 7476.11 | 204.65 | 742.8 | 0 | 947.45 | 105 | 19.75
NHT-013007 - Curation | 26-PC-35766 | Completed |  |  | 3442 | 2561.63 | 2561.63 | 414.51 | 2567.56 | 0 | 2982.07 | 42 | 58.58
NHT-013014 - Survey | 26-PC-35766 | Completed |  |  | 12650 | 9415.98 | 9415.98 | 1523.63 | 9437.79 | 0 | 10961.42 | 181 | 216.06
NHT-013017 - Testing | 26-PC-35766 | Completed |  |  | 10208 | 7597.48 | 7597.48 | 1229.38 | 7615.08 | 0 | 8844.46 | 162 | 157.59
NHT-013018 - Site Recordation | 26-PC-35789 | In progress |  |  | 2084 | 1412.32 | 1412.32 | 4.44 | 46.97 | 0 | 51.41 | 35 | 1.25
NHT-013020 - Monitoring | 26-PC-35789 | In progress |  |  | 1716 | 1162.94 | 1162.94 | 3.04 | 32.11 | 0 | 35.15 | 38 | 0.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35789 | In progress |  |  | 0 | 0 | 0 | 0 | 9.39 | 0 | 9.39 | 0 | 0.25
NHT-013029 - Desktop Review | 26-PC-35803 | In progress |  |  | 77727 | 48889.98 | 48889.98 | 15.85 | 107.95 | 0 | 123.8 | 695 | 2.5
NHT-013034 - Draft Report | 26-PC-35803 | In progress |  |  | 5173 | 3254.12 | 3254.12 | 0 | 0 | 0 | 0 | 63 | 0
NHT-013039 - Lab Analysis | 26-PC-35811 | In progress |  |  | 14845 | 9818.56 | 9818.56 | 0 | 0 | 0 | 0 | 175 | 0
NHT-013043 - Agency Consultation | 26-PC-35811 | In progress |  |  | 4655 | 3078.74 | 3078.74 | 0 | 0 | 0 | 0 | 50 | 0
NHT-013049 - Testing | 26-PC-35828 | In progress |  |  | 3075 | 2020.04 | 2020.04 | 475.38 | 1931.08 | 0 | 2406.46 | 19 | 23
NHT-013053 - Draft Report | 26-PC-35828 | In progress |  |  | 15272 | 10033.48 | 10033.48 | 1371.18 | 5570.01 | 0 | 6941.19 | 88 | 75.25
NHT-013057 - Fieldwork | 26-PC-35828 | In progress |  |  | 29953 | 19679.58 | 19679.58 | 1900.12 | 7718.64 | 0 | 9618.76 | 201 | 109.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35828 | In progress |  |  | 0 | 0 | 0 | 0 | 52.27 | 0 | 52.27 | 0 | 1.25
NHT-013065 - GIS & Mapping | 26-PC-35920 | In progress |  |  | 13124 | 7275.46 | 9073.94 | 0 | 0 | 0 | 0 | 108 | 0
NHT-013069 - Desktop Review | 26-PC-35920 | In progress |  |  | 9827 | 5447.73 | 6794.4 | 0 | 0 | 0 | 0 | 103 | 0
NHT-013070 - Project Management | 26-PC-35920 | In progress |  |  | 14781 | 8194.77 | 10220.51 | 0 | 0 | 0 | 0 | 186 | 0
NHT-013076 - Background Research | 26-PC-35920 | In progress |  |  | 14233 | 7890.45 | 9840.95 | 0 | 0 | 0 | 0 | 171 | 0
NHT-013078 - Curation | 26-PC-35920 | In progress |  |  | 9635 | 5341.59 | 6662.02 | 0 | 0 | 0 | 0 | 104 | 0
NHT-013079 - GIS & Mapping | 26-PC-35937 | Completed |  |  | 22154 | 15376.94 | 15376.94 | 139.24 | 725.61 | 0 | 864.85 | 393 | 18
NHT-013083 - Lab Analysis | 26-PC-35937 | Completed |  |  | 3473 | 2410.9 | 2410.9 | 45.68 | 238.06 | 0 | 283.74 | 55 | 6.25
NHT-013089 - Project Management | 26-PC-35937 | Completed |  |  | 48073 | 33367.33 | 33367.33 | 628.28 | 3274.04 | 0 | 3902.32 | 1091 | 80.25
NHT-013095 - Reporting | 26-PC-35984 | Completed |  |  | 49828 | 26523.9 | 31285.23 | 1066.03 | 3684.69 | 0 | 4750.72 | 538 | 80.5
NHT-013102 - Data Recovery Excavation | 26-PC-35984 | Completed |  |  | 18494 | 9844.65 | 11611.87 | 476.63 | 1647.46 | 0 | 2124.09 | 190 | 36.25
NHT-013108 - Draft Report | 26-PC-35984 | Completed |  |  | 6878 | 3661.05 | 4318.24 | 601.03 | 2077.44 | 0 | 2678.47 | 76 | 45.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-35984 | Completed |  |  | 0 | 0 | 0 | 0 | 606.39 | 0 | 606.39 | 0 | 14.5
NHT-013114 - Agency Consultation | 26-PC-36056 | Completed |  |  | 559500 | 461307.75 | 461307.75 | 88241.64 | 386175.79 | 0 | 474417.43 | 7519 | 7880.12
NHT-013119 - Fieldwork | 26-PC-36110 | In progress |  |  | 285268 | 208416.67 | 208416.67 | 1208.07 | 10673.55 | 0 | 11881.62 | 4698 | 242.75
NHT-013123 - Lab Analysis | 26-PC-36110 | In progress |  |  | 118246 | 86390.65 | 86390.65 | 912.66 | 8063.52 | 0 | 8976.18 | 1549 | 183
NHT-013124 - Curation | 26-PC-36110 | In progress |  |  | 372586 | 272211.34 | 272211.34 | 1927.38 | 17028.77 | 0 | 18956.15 | 6359 | 386.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36110 | In progress |  |  | 0 | 0 | 0 | 0 | 667.12 | 0 | 667.12 | 0 | 15.5
NHT-013131 - Data Recovery Excavation | 26-PC-36112 | Completed |  |  | 14115 | 8684.94 | 10490.91 | 859.2 | 12778.97 | 0 | 13638.17 | 157 | 245.93
NHT-013138 - Site Recordation | 26-PC-36112 | Completed |  |  | 7762 | 4775.63 | 5768.69 | 472.45 | 7026.83 | 0 | 7499.28 | 94 | 165.64
NHT-013143 - Monitoring | 26-PC-36112 | Completed |  |  | 16140 | 9931.22 | 11996.33 | 982.51 | 14612.74 | 0 | 15595.25 | 197 | 278.84
NHT-013150 - Background Research | 26-PC-36112 | Completed |  |  | 1783 | 1097.03 | 1325.15 | 108.53 | 1614.17 | 0 | 1722.7 | 18 | 33.77
NHT-013152 - Reporting | 26-PC-36208 | Completed |  |  | 16676 | 11366.59 | 11366.59 | 2236.56 | 9660.06 | 0 | 11896.62 | 195 | 179.93
NHT-013159 - Survey | 26-PC-36208 | Completed |  |  | 13991 | 9536.18 | 9536.18 | 1876.4 | 8104.45 | 0 | 9980.85 | 142 | 153.13
NHT-013160 - Project Management | 26-PC-36208 | Completed |  |  | 5933 | 4043.79 | 4043.79 | 795.68 | 3436.66 | 0 | 4232.34 | 64 | 60.65
NHT-013166 - Curation | 26-PC-36247 | In progress |  |  | 333 | 251.55 | 251.55 | 0 | 0 | 0 | 0 | 3 | 0
NHT-013171 - Final Report | 26-PC-36247 | In progress |  |  | 41414 | 31275.29 | 31275.29 | 34.73 | 303.68 | 0 | 338.41 | 388 | 6.75
NHT-013174 - Fieldwork | 26-PC-36247 | In progress |  |  | 1665 | 1257.73 | 1257.73 | 0 | 0 | 0 | 0 | 18 | 0
NHT-013178 - Draft Report | 26-PC-36247 | In progress |  |  | 888 | 670.79 | 670.79 | 0 | 0 | 0 | 0 | 9 | 0
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36247 | In progress |  |  | 0 | 0 | 0 | 0 | 56.24 | 0 | 56.24 | 0 | 1.25
NHT-013185 - Site Recordation | 26-PC-36281 | In progress |  |  | 72 | 47.09 | 47.09 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013192 - Fieldwork | 26-PC-36281 | In progress |  |  | 180 | 117.74 | 117.74 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013193 - Draft Report | 26-PC-36281 | In progress |  |  | 25420 | 16640.17 | 16640.17 | 26.38 | 112.48 | 0 | 138.86 | 0 | 2.5
NHT-013194 - Data Recovery Excavation | 26-PC-36281 | In progress |  |  | 180 | 117.74 | 117.74 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013200 - Final Report | 26-PC-36281 | In progress |  |  | 48 | 31.4 | 31.4 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013205 - Data Recovery Excavation | 26-PC-36361 | Completed |  |  | 172467 | 141681.56 | 141681.56 | 22546.3 | 125784.59 | 0 | 148330.89 | 1165 | 2180.36
NHT-013209 - Project Management | 26-PC-36361 | Completed |  |  | 29005 | 23827.51 | 23827.51 | 3791.76 | 21154.02 | 0 | 24945.78 | 256 | 339.64
NHT-013215 - Prefield | 26-PC-36361 | Completed |  |  | 33371 | 27414.16 | 27414.16 | 4362.51 | 24338.24 | 0 | 28700.75 | 340 | 352.61
NHT-013216 - Monitoring | 26-PC-36361 | Completed |  |  | 108557 | 89179.87 | 89179.87 | 14191.51 | 79173.7 | 0 | 93365.21 | 820 | 1188.99
NHT-013218 - Data Recovery Excavation | 26-PC-36394 | In progress |  |  | 56201 | 29493.34 | 36207.98 | 211.25 | 1069.1 | 0 | 1280.35 | 558 | 16
NHT-013219 - Agency Consultation | 26-PC-36394 | In progress |  |  | 5699 | 2990.58 | 3671.44 | 132.69 | 671.47 | 0 | 804.16 | 52 | 8.75
NHT-013226 - Fieldwork | 26-PC-36396 | In progress |  |  | 77700 | 43484.4 | 47283.31 | 759.96 | 5100.48 | 0 | 5860.44 | 467 | 78.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36396 | In progress |  |  | 0 | 0 | 0 | 0 | 76.74 | 0 | 76.74 | 0 | 1
NHT-013239 - Final Report | 26-PC-36416 | Completed |  |  | 125205 | 74733.22 | 98145.02 | 14005.92 | 49056.75 | 0 | 63062.67 | 793 | 716.75
NHT-013240 - Desktop Review | 26-PC-36416 | Completed |  |  | 257898 | 153936.5 | 202160.45 | 17435.51 | 61069.15 | 0 | 78504.66 | 1827 | 875
NHT-013241 - Lab Analysis | 26-PC-36416 | Completed |  |  | 206497 | 123255.28 | 161867.66 | 15232.79 | 53353.95 | 0 | 68586.74 | 1046 | 787
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36416 | Completed |  |  | 0 | 0 | 0 | 0 | 2001.46 | 0 | 2001.46 | 0 | 30
NHT-013249 - Project Management | 26-PC-36477 | Completed |  |  | 34034 | 24946.8 | 24946.8 | 2108.01 | 30322.84 | 0 | 32430.85 | 254 | 536.05
NHT-013252 - Final Report | 26-PC-36477 | Completed |  |  | 36066 | 26436.5 | 26436.5 | 2233.88 | 32133.56 | 0 | 34367.44 | 333 | 477.92
NHT-013255 - GIS & Mapping | 26-PC-36537 | In progress |  |  | 62550 | 43171.84 | 43171.84 | 1904.06 | 8710.08 | 0 | 10614.14 | 464 | 176.5
NHT-013258 - Prefield | 26-PC-36537 | In progress |  |  | 9585 | 6615.4 | 6615.4 | 1001.43 | 4581.01 | 0 | 5582.44 | 68 | 85
NHT-013263 - Curation | 26-PC-36537 | In progress |  |  | 33743 | 23289.5 | 23289.5 | 1025.11 | 4689.34 | 0 | 5714.45 | 298 | 97.25
NHT-013270 - Testing | 26-PC-36537 | In progress |  |  | 19422 | 13405.32 | 13405.32 | 872.77 | 3992.47 | 0 | 4865.24 | 158 | 80.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36537 | In progress |  |  | 0 | 0 | 0 | 0 | 515.57 | 0 | 515.57 | 0 | 9.75
NHT-013279 - Final Report | 26-PC-36548 | Completed |  |  | 25327 | 15272.06 | 15272.06 | 2843.26 | 14600.03 | 0 | 17443.29 | 143 | 208.34
NHT-013283 - Project Management | 26-PC-36548 | Completed |  |  | 34373 | 20727.04 | 20727.04 | 3858.83 | 19814.98 | 0 | 23673.81 | 252 | 242.66
NHT-013289 - Data Recovery Excavation | 26-PC-36555 | On hold |  |  | 78266 | 41975.61 | 52980.36 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013292 - Lab Analysis | 26-PC-36555 | On hold |  |  | 22370 | 11997.44 | 15142.81 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013298 - Testing | 26-PC-36555 | On hold |  |  | 45020 | 24145.12 | 30475.26 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013299 - Draft Report | 26-PC-36555 | On hold |  |  | 40027 | 21467.03 | 27095.04 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013305 - Project Management | 26-PC-36555 | On hold |  |  | 20417 | 10950.12 | 13820.91 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013310 - Site Recordation | 26-PC-36581 | In progress |  |  | 127600 | 76674.84 | 76674.84 | 2812.76 | 25980.03 | 0 | 28792.79 | 831 | 388.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36581 | In progress |  |  | 0 | 0 | 0 | 0 | 506.84 | 0 | 506.84 | 0 | 9.25
NHT-013319 - Lab Analysis | 26-PC-36595 | Completed |  |  | 12240 | 9027.31 | 9027.31 | 1176.16 | 9714.2 | 0 | 10890.36 | 74 | 130.19
NHT-013322 - Fieldwork | 26-PC-36595 | Completed |  |  | 17683 | 13041.22 | 13041.22 | 1699.13 | 14033.55 | 0 | 15732.68 | 97 | 189.77
NHT-013327 - Background Research | 26-PC-36595 | Completed |  |  | 5777 | 4260.22 | 4260.22 | 555.06 | 4584.39 | 0 | 5139.45 | 36 | 80.67
NHT-013333 - Draft Report | 26-PC-36602 | In progress |  |  | 166810 | 94031.63 | 121404.78 | 3570.08 | 13278.32 | 0 | 16848.4 | 1743 | 184.25
NHT-013334 - Background Research | 26-PC-36602 | In progress |  |  | 47243 | 26630.81 | 34383.19 | 2824.52 | 10505.31 | 0 | 13329.83 | 470 | 146
NHT-013339 - Fieldwork | 26-PC-36602 | In progress |  |  | 182547 | 102902.72 | 132858.31 | 2358.32 | 8771.39 | 0 | 11129.71 | 1272 | 165
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36602 | In progress |  |  | 0 | 0 | 0 | 0 | 372.63 | 0 | 372.63 | 0 | 4.25
NHT-013352 - Monitoring | 26-PC-36616 | Completed |  |  | 31589 | 15939.1 | 20720.59 | 2281.4 | 13030 | 0 | 15311.4 | 256 | 174.53
NHT-013353 - Desktop Review | 26-PC-36616 | Completed |  |  | 5164 | 2605.56 | 3387.19 | 372.94 | 2130.01 | 0 | 2502.95 | 35 | 31.77
NHT-013360 - Data Recovery Excavation | 26-PC-36616 | Completed |  |  | 35474 | 17899.95 | 23269.67 | 2562.06 | 14632.97 | 0 | 17195.03 | 241 | 249.51
NHT-013367 - Curation | 26-PC-36616 | Completed |  |  | 6873 | 3467.8 | 4508.09 | 496.35 | 2834.88 | 0 | 3331.23 | 54 | 51.04
NHT-013372 - Background Research | 26-PC-36726 | In progress |  |  | 153200 | 110288.68 | 110288.68 | 864.28 | 11060.52 | 0 | 11924.8 | 1117 | 140
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36726 | In progress |  |  | 0 | 0 | 0 | 0 | 79.11 | 0 | 79.11 | 0 | 0.75
NHT-013386 - Final Report | 26-PC-36749 | In progress |  |  | 69169 | 60329.09 | 60329.09 | 3510.31 | 33776.99 | 0 | 37287.3 | 814 | 464.75
NHT-013388 - Fieldwork | 26-PC-36749 | In progress |  |  | 129831 | 113238.71 | 113238.71 | 4221.15 | 40616.88 | 0 | 44838.03 | 1538 | 510
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36749 | In progress |  |  | 0 | 0 | 0 | 0 | 1008.6 | 0 | 1008.6 | 0 | 10.5
NHT-013399 - Curation | 26-PC-36750 | In progress |  |  | 121800 | 80948.28 | 80948.28 | 922.42 | 12270.13 | 0 | 13192.55 | 1714 | 205
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36750 | In progress |  |  | 0 | 0 | 0 | 0 | 175.91 | 0 | 175.91 | 0 | 4.25
NHT-013407 - Prefield | 26-PC-36775 | Completed |  |  | 82918 | 53187.97 | 70832.42 | 27.61 | 113.91 | 0 | 141.52 | 1580 | 3
NHT-013413 - Survey | 26-PC-36775 | Completed |  |  | 7882 | 5055.89 | 6733.12 | 0 | 0 | 0 | 0 | 146 | 0
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36775 | Completed |  |  | 0 | 0 | 0 | 0 | 18.98 | 0 | 18.98 | 0 | 0.5
NHT-013426 - Lab Analysis | 26-PC-36802 | Completed |  |  | 51181 | 37387.66 | 37387.66 | 0 | 0 | 0 | 0 | 536 | 0
NHT-013431 - Prefield | 26-PC-36802 | Completed |  |  | 20419 | 14916.14 | 14916.14 | 0 | 0 | 0 | 0 | 193 | 0
NHT-013438 - Lab Analysis | 26-PC-36828 | In progress |  |  | 240 | 162.4 | 162.4 | 0 | 0 | 0 | 0 | 2 | 0
NHT-013440 - GIS & Mapping | 26-PC-36828 | In progress |  |  | 5855 | 3960.1 | 3960.1 | 36.71 | 257 | 0 | 293.71 | 36 | 4
NHT-013442 - Curation | 26-PC-36828 | In progress |  |  | 21645 | 14640.73 | 14640.73 | 68.84 | 481.88 | 0 | 550.72 | 153 | 7.5
NHT-013445 - Reporting | 26-PC-36828 | In progress |  |  | 360 | 243.61 | 243.61 | 0 | 0 | 0 | 0 | 2 | 0
NHT-013450 - Prefield | 26-PC-36861 | In progress |  |  | 23627 | 17176.64 | 17176.64 | 137.37 | 565.63 | 0 | 703 | 0 | 12.5
NHT-013452 - Lab Analysis | 26-PC-36861 | In progress |  |  | 181427 | 131897.63 | 131897.63 | 530.24 | 2183.31 | 0 | 2713.55 | 0 | 48.25
NHT-013453 - Monitoring | 26-PC-36861 | In progress |  |  | 5754 | 4183.29 | 4183.29 | 0 | 0 | 0 | 0 | 0 | 0
NHT-013458 - Reporting | 26-PC-36861 | In progress |  |  | 23879 | 17359.78 | 17359.78 | 239.02 | 984.19 | 0 | 1223.21 | 0 | 21.75
NHT-013459 - Desktop Review | 26-PC-36861 | In progress |  |  | 229213 | 166637.96 | 166637.96 | 659.35 | 2715 | 0 | 3374.35 | 0 | 60
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36861 | In progress |  |  | 0 | 0 | 0 | 0 | 271.5 | 0 | 271.5 | 0 | 6
NHT-013462 - Survey | 26-PC-36944 | Completed |  |  | 102000 | 68921.4 | 68921.4 | 2581.59 | 9770.5 | 0 | 12352.09 | 851 | 177.75
NHT-013466 - Draft Report | 26-PC-36945 | In progress |  |  | 496500 | 329824.95 | 329824.95 | 17957.69 | 119541.19 | 0 | 137498.88 | 3948 | 1389.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-36945 | In progress |  |  | 0 | 0 | 0 | 0 | 2795.55 | 0 | 2795.55 | 0 | 38
NHT-013470 - Monitoring | 26-PC-36949 | Completed |  |  | 67762 | 37093.01 | 47342.84 | 5190.33 | 49444.69 | 0 | 54635.02 | 585 | 954.04
NHT-013471 - GIS & Mapping | 26-PC-36949 | Completed |  |  | 22099 | 12096.85 | 15439.54 | 1692.68 | 16125 | 0 | 17817.68 | 207 | 230.03
NHT-013476 - Curation | 26-PC-36949 | Completed |  |  | 10439 | 5714.14 | 7293.11 | 799.56 | 7616.9 | 0 | 8416.46 | 103 | 134.79
NHT-013477 - GIS & Mapping | 26-PC-37015 | On hold |  |  | 11819 | 8435 | 8435 | 0 | 0 | 0 | 0 | 84 | 0
NHT-013479 - Monitoring | 26-PC-37015 | On hold |  |  | 28581 | 20398.48 | 20398.48 | 0 | 0 | 0 | 0 | 198 | 0
NHT-013486 - Curation | 26-PC-37016 | Completed |  |  | 4092 | 3056.09 | 3056.09 | 415.02 | 1724.25 | 0 | 2139.27 | 21 | 20.64
NHT-013488 - Survey | 26-PC-37016 | Completed |  |  | 21908 | 16360.71 | 16360.71 | 2221.78 | 9230.71 | 0 | 11452.49 | 164 | 125.42
NHT-013491 - Survey | 26-PC-37024 | In progress |  |  | 28983 | 21705.79 | 23288.1 | 616.02 | 2745.11 | 0 | 3361.13 | 358 | 54.75
NHT-013496 - Data Recovery Excavation | 26-PC-37024 | In progress |  |  | 28525 | 21361.85 | 22919.1 | 459.94 | 2049.55 | 0 | 2509.49 | 313 | 40.75
NHT-013497 - Monitoring | 26-PC-37024 | In progress |  |  | 5753 | 4308.29 | 4622.36 | 220 | 980.33 | 0 | 1200.33 | 71 | 17.25
NHT-013500 - Site Recordation | 26-PC-37024 | In progress |  |  | 1572 | 1177.03 | 1262.84 | 100.21 | 446.53 | 0 | 546.74 | 15 | 7
NHT-013501 - Background Research | 26-PC-37024 | In progress |  |  | 14067 | 10534.38 | 11302.32 | 511.77 | 2280.49 | 0 | 2792.26 | 149 | 35.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37024 | In progress |  |  | 0 | 0 | 0 | 0 | 15.95 | 0 | 15.95 | 0 | 0.25
NHT-013507 - Final Report | 26-PC-37032 | Completed |  |  | 81720 | 46775.36 | 59081.27 | 14055.43 | 62750.23 | 0 | 76805.66 | 0 | 1026.82
NHT-013514 - Prefield | 26-PC-37032 | Completed |  |  | 73280 | 41944 | 52978.85 | 12603.67 | 56268.83 | 0 | 68872.5 | 0 | 771.27
NHT-013521 - Fieldwork | 26-PC-37051 | Completed |  |  | 137580 | 91573.56 | 91573.56 | 184.44 | 2488.65 | 0 | 2673.09 | 0 | 58.75
NHT-013523 - Survey | 26-PC-37051 | Completed |  |  | 228320 | 151969.48 | 151969.48 | 315.52 | 4257.18 | 0 | 4572.7 | 0 | 100.5
NHT-013526 - Survey | 26-PC-37068 | On hold |  |  | 343980 | 245361.28 | 245361.28 | 0 | 0 | 0 | 0 | 2016 | 0
NHT-013531 - Desktop Review | 26-PC-37068 | On hold |  |  | 75120 | 53582.75 | 53582.75 | 0 | 0 | 0 | 0 | 345 | 0
NHT-013533 - Prefield | 26-PC-37073 | In progress |  |  | 248217 | 194899.84 | 194899.84 | 991.93 | 4268.83 | 0 | 5260.76 | 1946 | 52
NHT-013535 - Lab Analysis | 26-PC-37073 | In progress |  |  | 193483 | 151923 | 151923 | 578.95 | 2491.56 | 0 | 3070.51 | 1434 | 37.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37073 | In progress |  |  | 0 | 0 | 0 | 0 | 493.92 | 0 | 493.92 | 0 | 5
NHT-013544 - Monitoring | 26-PC-37089 | In progress |  |  | 4025 | 2068.94 | 2653.92 | 18.25 | 111.63 | 0 | 129.88 | 23 | 1.75
NHT-013546 - Background Research | 26-PC-37089 | In progress |  |  | 24467 | 12575.72 | 16131.43 | 119.96 | 733.6 | 0 | 853.56 | 147 | 11.5
NHT-013547 - Project Management | 26-PC-37089 | In progress |  |  | 408 | 209.54 | 268.79 | 0 | 0 | 0 | 0 | 2 | 0
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37089 | In progress |  |  | 0 | 0 | 0 | 0 | 79.74 | 0 | 79.74 | 0 | 1.25
NHT-013557 - Background Research | 26-PC-37136 | In progress |  |  | 38744 | 21716.42 | 27677.2 | 1753.45 | 8653.3 | 0 | 10406.75 | 0 | 152.25
NHT-013558 - Prefield | 26-PC-37136 | In progress |  |  | 114956 | 64434.05 | 82120.06 | 4681.96 | 23105.47 | 0 | 27787.43 | 0 | 366.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37136 | In progress |  |  | 0 | 0 | 0 | 0 | 573.38 | 0 | 573.38 | 0 | 12.25
NHT-013565 - Curation | 26-PC-37137 | Completed |  |  | 17187 | 12775.21 | 12775.21 | 2262.58 | 8164.05 | 0 | 10426.63 | 177 | 105.85
NHT-013570 - Project Management | 26-PC-37137 | Completed |  |  | 18909 | 14054.94 | 14054.94 | 2489.22 | 8981.86 | 0 | 11471.08 | 164 | 125.03
NHT-013573 - Fieldwork | 26-PC-37137 | Completed |  |  | 69504 | 51662.33 | 51662.33 | 9149.75 | 33015 | 0 | 42164.75 | 586 | 473.17
NHT-013574 - Site Recordation | 26-PC-37138 | Completed |  |  | 123094 | 64247.5 | 87196.24 | 1174.77 | 4826.89 | 0 | 6001.66 | 724 | 81.75
NHT-013581 - Lab Analysis | 26-PC-37138 | Completed |  |  | 18398 | 9602.91 | 13033 | 662.8 | 2723.33 | 0 | 3386.13 | 95 | 38.75
NHT-013587 - Final Report | 26-PC-37138 | Completed |  |  | 61702 | 32205.05 | 43708.45 | 1715.04 | 7046.76 | 0 | 8761.8 | 260 | 79
NHT-013588 - Background Research | 26-PC-37138 | Completed |  |  | 82868 | 43252.48 | 58701.95 | 1945.65 | 7994.29 | 0 | 9939.94 | 393 | 72.75
NHT-013590 - Testing | 26-PC-37138 | Completed |  |  | 29738 | 15521.39 | 21065.52 | 1092.2 | 4487.64 | 0 | 5579.84 | 146 | 54.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37138 | Completed |  |  | 0 | 0 | 0 | 0 | 302.07 | 0 | 302.07 | 0 | 2.5
NHT-013598 - Draft Report | 26-PC-37139 | In progress |  |  | 1070500 | 579542.04 | 734587.52 | 7614.96 | 58183.44 | 0 | 65798.4 | 9379 | 837.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37139 | In progress |  |  | 0 | 0 | 0 | 0 | 999.48 | 0 | 999.48 | 0 | 15.5
NHT-013604 - GIS & Mapping | 26-PC-37160 | Completed |  |  | 122075 | 75088.42 | 75088.42 | 13129.5 | 69445.97 | 0 | 82575.47 | 1182 | 982.9
NHT-013610 - Background Research | 26-PC-37160 | Completed |  |  | 62613 | 38513.32 | 38513.32 | 6734.2 | 35619.27 | 0 | 42353.47 | 554 | 481.59
NHT-013613 - Curation | 26-PC-37160 | Completed |  |  | 84460 | 51951.52 | 51951.52 | 9083.92 | 48047.67 | 0 | 57131.59 | 824 | 585.94
NHT-013620 - Fieldwork | 26-PC-37160 | Completed |  |  | 332804 | 204707.16 | 204707.16 | 35793.84 | 189324.64 | 0 | 225118.48 | 3208 | 2764.81
NHT-013621 - Draft Report | 26-PC-37160 | Completed |  |  | 131848 | 81099.96 | 81099.96 | 14180.64 | 75005.78 | 0 | 89186.42 | 1281 | 1245.48
NHT-013626 - Reporting | 26-PC-37166 | Completed |  |  | 92639 | 66561.23 | 66561.23 | 10629.39 | 63185.8 | 0 | 73815.19 | 1166 | 902.72
NHT-013628 - Prefield | 26-PC-37166 | Completed |  |  | 39051 | 28058.36 | 28058.36 | 4480.73 | 26635.47 | 0 | 31116.2 | 359 | 453.4
NHT-013635 - Agency Consultation | 26-PC-37166 | Completed |  |  | 19356 | 13907.09 | 13907.09 | 2220.87 | 13201.84 | 0 | 15422.71 | 210 | 205.7
NHT-013642 - Data Recovery Excavation | 26-PC-37166 | Completed |  |  | 101854 | 73181.97 | 73181.97 | 11686.68 | 69470.81 | 0 | 81157.49 | 1482 | 1077.29
NHT-013644 - Monitoring | 26-PC-37196 | In progress |  |  | 5936 | 5049.15 | 5049.15 | 0 | 0 | 0 | 0 | 54 | 0
NHT-013649 - Draft Report | 26-PC-37196 | In progress |  |  | 3468 | 2949.76 | 2949.76 | 0 | 0 | 0 | 0 | 28 | 0
NHT-013651 - Fieldwork | 26-PC-37196 | In progress |  |  | 7855 | 6681.67 | 6681.67 | 0 | 0 | 0 | 0 | 66 | 0
NHT-013656 - Survey | 26-PC-37196 | In progress |  |  | 6855 | 5830.88 | 5830.88 | 0 | 0 | 0 | 0 | 54 | 0
NHT-013662 - Final Report | 26-PC-37196 | In progress |  |  | 2786 | 2369.68 | 2369.68 | 0 | 0 | 0 | 0 | 18 | 0
NHT-013665 - Final Report | 26-PC-37204 | In progress |  |  | 56759 | 40940.6 | 40940.6 | 3447.71 | 20357.55 | 0 | 23805.26 | 798 | 406.5
NHT-013672 - Monitoring | 26-PC-37204 | In progress |  |  | 145141 | 104689.87 | 104689.87 | 3042.77 | 17966.5 | 0 | 21009.27 | 1762 | 395
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37204 | In progress |  |  | 0 | 0 | 0 | 0 | 573.45 | 0 | 573.45 | 0 | 15
NHT-013684 - Data Recovery Excavation | 26-PC-37224 | Completed |  |  | 72645 | 50647.37 | 55895.05 | 5329.3 | 45425.92 | 0 | 50755.22 | 585 | 544.17
NHT-013688 - Reporting | 26-PC-37224 | Completed |  |  | 78246 | 54552.8 | 60205.13 | 5740.24 | 48928.71 | 0 | 54668.95 | 581 | 774.72
NHT-013695 - Agency Consultation | 26-PC-37224 | Completed |  |  | 17809 | 12415.94 | 13702.38 | 1306.45 | 11135.93 | 0 | 12442.38 | 140 | 155.26
NHT-013696 - Background Research | 26-PC-37271 | In progress |  |  | 170966 | 93744.35 | 114105.79 | 6486.27 | 30596.52 | 0 | 37082.79 | 0 | 448.75
NHT-013702 - Draft Report | 26-PC-37271 | In progress |  |  | 259877 | 142495.76 | 173446.08 | 6315.88 | 29792.77 | 0 | 36108.65 | 0 | 449.25
NHT-013704 - Survey | 26-PC-37271 | In progress |  |  | 288023 | 157928.72 | 192231.1 | 8825.07 | 41628.98 | 0 | 50454.05 | 0 | 604
NHT-013709 - Reporting | 26-PC-37271 | In progress |  |  | 161034 | 88298.39 | 107476.95 | 8138.16 | 38388.68 | 0 | 46526.84 | 0 | 554
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37271 | In progress |  |  | 0 | 0 | 0 | 0 | 893.06 | 0 | 893.06 | 0 | 14
NHT-013717 - Testing | 26-PC-37282 | In progress |  |  | 14444 | 12318.2 | 12318.2 | 57.27 | 271.87 | 0 | 329.14 | 106 | 2.25
NHT-013719 - Curation | 26-PC-37282 | In progress |  |  | 197 | 168.15 | 168.15 | 0 | 0 | 0 | 0 | 2 | 0
NHT-013725 - GIS & Mapping | 26-PC-37282 | In progress |  |  | 34159 | 29130.29 | 29130.29 | 55.72 | 264.5 | 0 | 320.22 | 278 | 5.5
NHT-013727 - Testing | 26-PC-37311 | On hold |  |  | 28587 | 20102.48 | 20102.48 | 0 | 0 | 0 | 0 | 204 | 0
NHT-013729 - GIS & Mapping | 26-PC-37311 | On hold |  |  | 20513 | 14424.64 | 14424.64 | 0 | 0 | 0 | 0 | 130 | 0
NHT-013730 - Data Recovery Excavation | 26-PC-37317 | In progress |  |  | 36715 | 23662.98 | 23662.98 | 273.45 | 1278.31 | 0 | 1551.76 | 0 | 28.25
NHT-013734 - Background Research | 26-PC-37317 | In progress |  |  | 109098 | 70313.19 | 70313.19 | 275.87 | 1289.62 | 0 | 1565.49 | 0 | 28.5
NHT-013736 - Desktop Review | 26-PC-37317 | In progress |  |  | 92369 | 59532.11 | 59532.11 | 222.63 | 1040.75 | 0 | 1263.38 | 0 | 23
NHT-013741 - Reporting | 26-PC-37317 | In progress |  |  | 65106 | 41960.92 | 41960.92 | 411.4 | 1923.13 | 0 | 2334.53 | 0 | 42.5
NHT-013743 - Curation | 26-PC-37317 | In progress |  |  | 45412 | 29267.95 | 29267.95 | 106.48 | 497.75 | 0 | 604.23 | 0 | 11
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37317 | In progress |  |  | 0 | 0 | 0 | 0 | 497.75 | 0 | 497.75 | 0 | 11
NHT-013755 - Draft Report | 26-PC-37322 | In progress |  |  | 30900 | 21095.43 | 21095.43 | 187.77 | 2746.21 | 0 | 2933.98 | 436 | 67.75
NHT-013758 - GIS & Mapping | 26-PC-37329 | Completed |  |  | 32600 | 25463.86 | 25463.86 | 2377.83 | 13227.12 | 0 | 15604.95 | 360 | 206.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37329 | Completed |  |  | 0 | 0 | 0 | 0 | 570.78 | 0 | 570.78 | 0 | 8.5
NHT-013770 - GIS & Mapping | 26-PC-37367 | Completed |  |  | 19483 | 12975.62 | 12975.62 | 2274.82 | 9390.91 | 0 | 11665.73 | 131 | 129.6
NHT-013777 - Monitoring | 26-PC-37367 | Completed |  |  | 82094 | 54674.94 | 54674.94 | 9585.32 | 39570.17 | 0 | 49155.49 | 460 | 633
NHT-013784 - Final Report | 26-PC-37367 | Completed |  |  | 18322 | 12202.22 | 12202.22 | 2139.23 | 8831.18 | 0 | 10970.41 | 93 | 120.15
NHT-013785 - Data Recovery Excavation | 26-PC-37367 | Completed |  |  | 76501 | 50949.62 | 50949.62 | 8932.22 | 36874.03 | 0 | 45806.25 | 377 | 579.21
NHT-013786 - Survey | 26-PC-37368 | In progress |  |  | 178913 | 109924.59 | 109924.59 | 799.18 | 3061.62 | 0 | 3860.8 | 1937 | 79.25
NHT-013787 - Background Research | 26-PC-37368 | In progress |  |  | 996 | 611.65 | 611.65 | 0 | 0 | 0 | 0 | 14 | 0
NHT-013791 - Draft Report | 26-PC-37368 | In progress |  |  | 21191 | 13019.6 | 13019.6 | 353.58 | 1354.54 | 0 | 1708.12 | 329 | 33.5
NHT-013794 - Final Report | 26-PC-37428 | In progress |  |  | 3745 | 2859.18 | 2859.18 | 452.62 | 2863.62 | 0 | 3316.24 | 36 | 43.75
NHT-013796 - Data Recovery Excavation | 26-PC-37428 | In progress |  |  | 23388 | 17856.51 | 17856.51 | 538.5 | 3406.98 | 0 | 3945.48 | 230 | 77.75
NHT-013797 - Reporting | 26-PC-37428 | In progress |  |  | 30767 | 23490.96 | 23490.96 | 750.22 | 4746.47 | 0 | 5496.69 | 257 | 104.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37428 | In progress |  |  | 0 | 0 | 0 | 0 | 140.38 | 0 | 140.38 | 0 | 3.5
NHT-013799 - Background Research | 26-PC-37441 | Completed |  |  | 14433 | 10530.47 | 10530.47 | 981.86 | 6456.48 | 0 | 7438.34 | 0 | 116.94
NHT-013802 - Testing | 26-PC-37441 | Completed |  |  | 42141 | 30746.2 | 30746.2 | 2866.77 | 18851.19 | 0 | 21717.96 | 0 | 321.92
NHT-013804 - Lab Analysis | 26-PC-37441 | Completed |  |  | 34926 | 25481.73 | 25481.73 | 2375.92 | 15623.44 | 0 | 17999.36 | 0 | 286.84
NHT-013805 - Monitoring | 26-PC-37477 | On hold |  |  | 41100 | 28424.76 | 28424.76 | 0 | 0 | 0 | 0 | 541 | 0
NHT-013810 - Site Recordation | 26-PC-37511 | Completed |  |  | 94591 | 66639.69 | 66639.69 | 7485.26 | 73876.27 | 0 | 81361.53 | 1201 | 1099.25
NHT-013815 - Survey | 26-PC-37511 | Completed |  |  | 108309 | 76303.36 | 76303.36 | 8570.73 | 84589.34 | 0 | 93160.07 | 1142 | 1526.31
NHT-013817 - Data Recovery Excavation | 26-PC-37513 | Completed |  |  | 14239 | 9698.06 | 9698.06 | 0 | 0 | 0 | 0 | 112 | 0
NHT-013819 - Monitoring | 26-PC-37513 | Completed |  |  | 14613 | 9953.02 | 9953.02 | 0 | 0 | 0 | 0 | 92 | 0
NHT-013820 - Site Recordation | 26-PC-37513 | Completed |  |  | 5848 | 3983.09 | 3983.09 | 0 | 0 | 0 | 0 | 32 | 0
NHT-013822 - Background Research | 26-PC-37520 | Completed |  |  | 8745 | 6422.53 | 6422.53 | 1370.33 | 6200.54 | 0 | 7570.87 | 59 | 127.14
NHT-013829 - Site Recordation | 26-PC-37520 | Completed |  |  | 19148 | 14062.02 | 14062.02 | 3000.3 | 13575.97 | 0 | 16576.27 | 183 | 232.7
NHT-013836 - Agency Consultation | 26-PC-37520 | Completed |  |  | 14821 | 10884.3 | 10884.3 | 2322.3 | 10508.08 | 0 | 12830.38 | 114 | 202.38
NHT-013840 - Final Report | 26-PC-37520 | Completed |  |  | 16486 | 12107.63 | 12107.63 | 2583.31 | 11689.13 | 0 | 14272.44 | 125 | 191.63
NHT-013845 - Survey | 26-PC-37543 | In progress |  |  | 46643 | 30849.56 | 30849.56 | 3426.14 | 15800.67 | 0 | 19226.81 | 409 | 206.25
NHT-013846 - Background Research | 26-PC-37543 | In progress |  |  | 43147 | 28537.75 | 28537.75 | 2468.78 | 11385.5 | 0 | 13854.28 | 389 | 164.75
NHT-013853 - Fieldwork | 26-PC-37543 | In progress |  |  | 109724 | 72571.59 | 72571.59 | 3990.46 | 18403.18 | 0 | 22393.64 | 861 | 248.75
NHT-013856 - Reporting | 26-PC-37543 | In progress |  |  | 53074 | 35102.83 | 35102.83 | 4549.84 | 20982.92 | 0 | 25532.76 | 454 | 250
NHT-013862 - Project Management | 26-PC-37543 | In progress |  |  | 77612 | 51332.55 | 51332.55 | 2952.01 | 13614.05 | 0 | 16566.06 | 564 | 162.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37543 | In progress |  |  | 0 | 0 | 0 | 0 | 1217.56 | 0 | 1217.56 | 0 | 14.75
NHT-013875 - Lab Analysis | 26-PC-37559 | Completed |  |  | 4599 | 2909.31 | 2909.31 | 796.72 | 4363.29 | 0 | 5160.01 | 24 | 56
NHT-013878 - Survey | 26-PC-37559 | In progress |  |  | 8612 | 5447.98 | 5447.98 | 2405.45 | 13173.68 | 0 | 15579.13 | 38 | 179.75
NHT-013885 - Curation | 26-PC-37559 | Completed |  |  | 6052 | 3828.74 | 3828.74 | 1527.22 | 8363.91 | 0 | 9891.13 | 27 | 118.5
NHT-013887 - Monitoring | 26-PC-37559 | In progress |  |  | 25037 | 15838.15 | 15838.15 | 2192.56 | 12007.71 | 0 | 14200.27 | 107 | 155.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37559 | In progress |  |  | 0 | 0 | 0 | 0 | 708.63 | 0 | 708.63 | 0 | 10.25
NHT-013896 - Monitoring | 26-PC-37671 | In progress |  |  | 21081 | 13363.5 | 13363.5 | 179.69 | 688.39 | 0 | 868.08 | 0 | 18.25
NHT-013900 - Curation | 26-PC-37671 | In progress |  |  | 48584 | 30797.24 | 30797.24 | 337.23 | 1291.91 | 0 | 1629.14 | 0 | 34.25
NHT-013901 - Background Research | 26-PC-37671 | In progress |  |  | 76235 | 48325.27 | 48325.27 | 728.62 | 2791.28 | 0 | 3519.9 | 0 | 74
NHT-013906 - GIS & Mapping | 26-PC-37705 | In progress |  |  | 2876 | 2305.72 | 2305.72 | 817.66 | 4468.41 | 0 | 5286.07 | 32 | 93
NHT-013908 - Desktop Review | 26-PC-37705 | In progress |  |  | 12071 | 9678.54 | 9678.54 | 998.1 | 5454.48 | 0 | 6452.58 | 127 | 104.75
NHT-013913 - Survey | 26-PC-37705 | In progress |  |  | 8589 | 6886.39 | 6886.39 | 607.3 | 3318.8 | 0 | 3926.1 | 79 | 65.25
NHT-013916 - Fieldwork | 26-PC-37705 | In progress |  |  | 1693 | 1357.54 | 1357.54 | 144.82 | 791.44 | 0 | 936.26 | 19 | 12
NHT-013920 - Project Management | 26-PC-37705 | In progress |  |  | 15071 | 12084.35 | 12084.35 | 1329.82 | 7267.27 | 0 | 8597.09 | 171 | 118.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37705 | In progress |  |  | 0 | 0 | 0 | 0 | 277.03 | 0 | 277.03 | 0 | 4.5
NHT-013928 - Draft Report | 26-PC-37709 | Completed |  |  | 3368 | 2323.05 | 2323.05 | 937.49 | 5235.17 | 0 | 6172.66 | 42 | 78.25
NHT-013931 - GIS & Mapping | 26-PC-37709 | Completed |  |  | 13389 | 9234.38 | 9234.38 | 1084.1 | 6053.84 | 0 | 7137.94 | 143 | 92
NHT-013934 - Agency Consultation | 26-PC-37709 | Completed |  |  | 2833 | 1954.22 | 1954.22 | 906.57 | 5062.48 | 0 | 5969.05 | 28 | 86.5
NHT-013936 - Final Report | 26-PC-37709 | Completed |  |  | 9870 | 6807.14 | 6807.14 | 850.29 | 4748.22 | 0 | 5598.51 | 101 | 96.25
NHT-013943 - Desktop Review | 26-PC-37709 | Completed |  |  | 2040 | 1406.76 | 1406.76 | 643.76 | 3594.93 | 0 | 4238.69 | 22 | 66.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37709 | Completed |  |  | 0 | 0 | 0 | 0 | 1172.27 | 0 | 1172.27 | 0 | 17.75
NHT-013953 - Reporting | 26-PC-37788 | In progress |  |  | 573171 | 425693.94 | 425693.94 | 1089.51 | 3854.76 | 0 | 4944.27 | 6200 | 89.75
NHT-013960 - Agency Consultation | 26-PC-37788 | In progress |  |  | 539629 | 400782.62 | 400782.62 | 2579.63 | 9126.88 | 0 | 11706.51 | 4879 | 212.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37788 | In progress |  |  | 0 | 0 | 0 | 0 | 257.7 | 0 | 257.7 | 0 | 6
NHT-013966 - Prefield | 26-PC-37801 | Completed |  |  | 40051 | 26742.25 | 26742.25 | 4571.17 | 25502.3 | 0 | 30073.47 | 337 | 468.52
NHT-013968 - Agency Consultation | 26-PC-37801 | Completed |  |  | 32449 | 21666 | 21666 | 3703.46 | 20661.41 | 0 | 24364.87 | 263 | 341.84
NHT-013973 - Final Report | 26-PC-37860 | Completed |  |  | 13233 | 9510.88 | 9510.88 | 1630.81 | 9241.24 | 0 | 10872.05 | 188 | 188.64
NHT-013974 - GIS & Mapping | 26-PC-37860 | Completed |  |  | 14367 | 10325.24 | 10325.24 | 1770.44 | 10032.52 | 0 | 11802.96 | 192 | 178.58
NHT-013977 - Testing | 26-PC-37924 | Completed |  |  | 14536 | 10333.76 | 10333.76 | 1907.61 | 11526.28 | 0 | 13433.89 | 116 | 197.97
NHT-013982 - Fieldwork | 26-PC-37924 | Completed |  |  | 19064 | 13552.48 | 13552.48 | 2501.79 | 15116.43 | 0 | 17618.22 | 221 | 297.88
NHT-013986 - Lab Analysis | 26-PC-37965 | In progress |  |  | 55400 | 34625 | 34625 | 4943.2 | 26549.81 | 0 | 31493.01 | 590 | 573.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-37965 | In progress |  |  | 0 | 0 | 0 | 0 | 194.2 | 0 | 194.2 | 0 | 4.5
NHT-013996 - Curation | 26-PC-38019 | Completed |  |  | 1273 | 850.12 | 850.12 | 85.14 | 904.9 | 0 | 990.04 | 9 | 21.85
NHT-014001 - Project Management | 26-PC-38019 | Completed |  |  | 1344 | 897.68 | 897.68 | 89.91 | 955.53 | 0 | 1045.44 | 14 | 20.49
NHT-014004 - Data Recovery Excavation | 26-PC-38019 | Completed |  |  | 4482 | 2994.14 | 2994.14 | 299.88 | 3187.08 | 0 | 3486.96 | 38 | 61.85
NHT-014011 - Agency Consultation | 26-PC-38019 | Completed |  |  | 970 | 648.28 | 648.28 | 64.93 | 690.05 | 0 | 754.98 | 10 | 15.53
NHT-014013 - Monitoring | 26-PC-38019 | Completed |  |  | 5631 | 3761.38 | 3761.38 | 376.72 | 4003.77 | 0 | 4380.49 | 64 | 77.83
NHT-014015 - Site Recordation | 26-PC-38025 | In progress |  |  | 683 | 481.69 | 481.69 | 0 | 0 | 0 | 0 | 10 | 0
NHT-014021 - Final Report | 26-PC-38025 | In progress |  |  | 28738 | 20254.59 | 20254.59 | 194.9 | 1248.7 | 0 | 1443.6 | 396 | 26.75
NHT-014026 - Reporting | 26-PC-38025 | In progress |  |  | 24075 | 16967.78 | 16967.78 | 274.13 | 1756.34 | 0 | 2030.47 | 268 | 33.5
NHT-014032 - Survey | 26-PC-38025 | In progress |  |  | 16711 | 11778.17 | 11778.17 | 72.86 | 466.8 | 0 | 539.66 | 209 | 10
NHT-014034 - Monitoring | 26-PC-38025 | In progress |  |  | 21993 | 15500.33 | 15500.33 | 539.16 | 3454.31 | 0 | 3993.47 | 284 | 74
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38025 | In progress |  |  | 0 | 0 | 0 | 0 | 245.07 | 0 | 245.07 | 0 | 5.25
NHT-014041 - Lab Analysis | 26-PC-38124 | Completed |  |  | 9421 | 7424.57 | 7424.57 | 971.89 | 7705.68 | 0 | 8677.57 | 125 | 171.77
NHT-014042 - GIS & Mapping | 26-PC-38124 | Completed |  |  | 8932 | 7039.39 | 7039.39 | 921.47 | 7305.92 | 0 | 8227.39 | 113 | 175.55
NHT-014047 - Survey | 26-PC-38124 | Completed |  |  | 30347 | 23916.51 | 23916.51 | 3130.7 | 24822.04 | 0 | 27952.74 | 412 | 470.08
NHT-014053 - Project Management | 26-PC-38153 | In progress |  |  | 13324 | 8460.66 | 10962.88 | 1386.66 | 11454.41 | 0 | 12841.07 | 0 | 257.75
NHT-014055 - Reporting | 26-PC-38153 | In progress |  |  | 42345 | 26888.44 | 34840.61 | 1597.28 | 13194.15 | 0 | 14791.43 | 0 | 304.5
NHT-014058 - Lab Analysis | 26-PC-38153 | In progress |  |  | 17644 | 11203.92 | 14517.45 | 1356.05 | 11201.56 | 0 | 12557.61 | 0 | 260.75
NHT-014063 - Fieldwork | 26-PC-38153 | In progress |  |  | 35787 | 22724.72 | 29445.49 | 1076.27 | 8890.41 | 0 | 9966.68 | 0 | 198
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38153 | In progress |  |  | 0 | 0 | 0 | 0 | 462.48 | 0 | 462.48 | 0 | 10.25
NHT-014067 - Monitoring | 26-PC-38215 | In progress |  |  | 42800 | 37664 | 37664 | 1962.5 | 10614.69 | 0 | 12577.19 | 1259 | 256.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38215 | In progress |  |  | 0 | 0 | 0 | 0 | 506.11 | 0 | 506.11 | 0 | 11.5
NHT-014069 - Data Recovery Excavation | 26-PC-38264 | Completed |  |  | 14725 | 9030.78 | 10351.45 | 316.54 | 1938.91 | 0 | 2255.45 | 164 | 42.75
NHT-014073 - Testing | 26-PC-38264 | Completed |  |  | 5086 | 3119.06 | 3575.2 | 270.35 | 1656 | 0 | 1926.35 | 55 | 36
NHT-014076 - Curation | 26-PC-38264 | Completed |  |  | 2800 | 1717.4 | 1968.55 | 234.58 | 1436.89 | 0 | 1671.47 | 28 | 32.5
NHT-014080 - Final Report | 26-PC-38264 | Completed |  |  | 1201 | 736.74 | 844.48 | 87.94 | 538.69 | 0 | 626.63 | 15 | 12.5
NHT-014082 - Background Research | 26-PC-38264 | Completed |  |  | 1688 | 1035.34 | 1186.75 | 193.96 | 1188.1 | 0 | 1382.06 | 19 | 26.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38264 | Completed |  |  | 0 | 0 | 0 | 0 | 434.07 | 0 | 434.07 | 0 | 10
NHT-014088 - Prefield | 26-PC-38304 | In progress |  |  | 30634 | 21655.44 | 21655.44 | 0 | 0 | 0 | 0 | 342 | 0
NHT-014091 - Survey | 26-PC-38304 | In progress |  |  | 72729 | 51412.01 | 51412.01 | 0 | 0 | 0 | 0 | 1130 | 0
NHT-014095 - Curation | 26-PC-38304 | In progress |  |  | 17549 | 12405.15 | 12405.15 | 0 | 0 | 0 | 0 | 196 | 0
NHT-014101 - Lab Analysis | 26-PC-38304 | In progress |  |  | 56188 | 39719.39 | 39719.39 | 0 | 0 | 0 | 0 | 681 | 0
NHT-014108 - Reporting | 26-PC-38315 | Completed |  |  | 153607 | 120857.65 | 120857.65 | 2158.47 | 12506.38 | 0 | 14664.85 | 1513 | 270.25
NHT-014115 - Desktop Review | 26-PC-38315 | Completed |  |  | 581393 | 457440.35 | 457440.35 | 2551.73 | 14785.02 | 0 | 17336.75 | 7044 | 328.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38315 | Completed |  |  | 0 | 0 | 0 | 0 | 708.11 | 0 | 708.11 | 0 | 15.25
NHT-014123 - Project Management | 26-PC-38367 | In progress |  |  | 132029 | 87521.91 | 87521.91 | 4422.72 | 15873.62 | 0 | 20296.34 | 1660 | 341
NHT-014130 - Final Report | 26-PC-38367 | In progress |  |  | 116967 | 77537.41 | 77537.41 | 6877.96 | 24685.74 | 0 | 31563.7 | 1460 | 553.25
NHT-014133 - Monitoring | 26-PC-38367 | In progress |  |  | 83002 | 55022.3 | 55022.3 | 2421.27 | 8690.2 | 0 | 11111.47 | 1015 | 153
NHT-014140 - Survey | 26-PC-38367 | In progress |  |  | 84502 | 56016.23 | 56016.23 | 3607.31 | 12947.02 | 0 | 16554.33 | 1299 | 282.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38367 | In progress |  |  | 0 | 0 | 0 | 0 | 1075.39 | 0 | 1075.39 | 0 | 24.5
NHT-014148 - Monitoring | 26-PC-38379 | On hold |  |  | 230500 | 138229.08 | 167898.45 | 0 | 0 | 0 | 0 | 1663 | 0
NHT-014154 - Data Recovery Excavation | 26-PC-38387 | In progress |  |  | 78659 | 51875.78 | 51875.78 | 1500.89 | 17009.14 | 0 | 18510.03 | 765 | 301.25
NHT-014156 - Draft Report | 26-PC-38387 | In progress |  |  | 82815 | 54616.22 | 54616.22 | 1033.07 | 11707.49 | 0 | 12740.56 | 680 | 184
NHT-014159 - Curation | 26-PC-38387 | In progress |  |  | 21026 | 13866.75 | 13866.75 | 1668.35 | 18906.94 | 0 | 20575.29 | 198 | 253.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38387 | In progress |  |  | 0 | 0 | 0 | 0 | 702.98 | 0 | 702.98 | 0 | 13
NHT-014164 - Testing | 26-PC-38390 | Completed |  |  | 85100 | 53630.02 | 53630.02 | 105.93 | 908.63 | 0 | 1014.56 | 1239 | 22.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38390 | Completed |  |  | 0 | 0 | 0 | 0 | 309.53 | 0 | 309.53 | 0 | 7.75
NHT-014166 - Fieldwork | 26-PC-38410 | In progress |  |  | 48300 | 32887.47 | 32887.47 | 4071.46 | 20906.8 | 0 | 24978.26 | 395 | 440.75
NHT-014171 - Testing | 26-PC-38431 | Completed |  |  | 105482 | 59417.81 | 59417.81 | 15989.34 | 61253.82 | 0 | 77243.16 | 748 | 1161.19
NHT-014173 - Background Research | 26-PC-38431 | Completed |  |  | 69248 | 39007.55 | 39007.55 | 10496.93 | 40212.89 | 0 | 50709.82 | 468 | 826.12
NHT-014176 - Project Management | 26-PC-38431 | Completed |  |  | 80070 | 45103.48 | 45103.48 | 12137.34 | 46497.17 | 0 | 58634.51 | 538 | 1119.58
NHT-014181 - Prefield | 26-PC-38438 | In progress |  |  | 5693 | 3517.51 | 4549.45 | 0 | 0 | 0 | 0 | 47 | 0
NHT-014188 - GIS & Mapping | 26-PC-38438 | In progress |  |  | 5642 | 3486.03 | 4508.74 | 0 | 0 | 0 | 0 | 59 | 0
NHT-014195 - Survey | 26-PC-38438 | In progress |  |  | 21441 | 13246.29 | 17132.38 | 0 | 0 | 0 | 0 | 202 | 0
NHT-014201 - Testing | 26-PC-38438 | In progress |  |  | 8224 | 5081.26 | 6571.96 | 0 | 0 | 0 | 0 | 80 | 0
NHT-014205 - Desktop Review | 26-PC-38459 | Completed |  |  | 96700 | 76702.44 | 76702.44 | 7019.06 | 52464.53 | 0 | 59483.59 | 0 | 1113.49
NHT-014209 - Desktop Review | 26-PC-38532 | On hold |  |  | 2430 | 1763.22 | 1763.22 | 0 | 0 | 0 | 0 | 29 | 0
NHT-014216 - Reporting | 26-PC-38532 | On hold |  |  | 7246 | 5256.67 | 5256.67 | 0 | 0 | 0 | 0 | 84 | 0
NHT-014219 - Testing | 26-PC-38532 | On hold |  |  | 10849 | 7871.18 | 7871.18 | 0 | 0 | 0 | 0 | 152 | 0
NHT-014224 - Site Recordation | 26-PC-38532 | On hold |  |  | 7333 | 5320.11 | 5320.11 | 0 | 0 | 0 | 0 | 88 | 0
NHT-014226 - Data Recovery Excavation | 26-PC-38532 | On hold |  |  | 18542 | 13452.02 | 13452.02 | 0 | 0 | 0 | 0 | 199 | 0
NHT-014230 - Agency Consultation | 26-PC-38546 | Completed |  |  | 11708 | 6282.51 | 6282.51 | 673.18 | 6058.65 | 0 | 6731.83 | 0 | 105.21
NHT-014235 - Fieldwork | 26-PC-38546 | Completed |  |  | 91592 | 49148.27 | 49148.27 | 5266.34 | 47396.99 | 0 | 52663.33 | 0 | 918.88
NHT-014240 - Monitoring | 26-PC-38550 | Completed |  |  | 101390 | 65595.43 | 76236.32 | 5591.94 | 63444.35 | 0 | 69036.29 | 1065 | 1332.34
NHT-014245 - Reporting | 26-PC-38550 | Completed |  |  | 78078 | 50513.79 | 58708.13 | 4306.25 | 48857.28 | 0 | 53163.53 | 846 | 798.11
NHT-014252 - Fieldwork | 26-PC-38550 | Completed |  |  | 109323 | 70727.64 | 82201.1 | 6029.45 | 68408.27 | 0 | 74437.72 | 1285 | 1526
NHT-014256 - GIS & Mapping | 26-PC-38550 | Completed |  |  | 42937 | 27778.74 | 32285 | 2368.11 | 26867.79 | 0 | 29235.9 | 370 | 528.08
NHT-014257 - Lab Analysis | 26-PC-38550 | Completed |  |  | 53472 | 34594.3 | 40206.19 | 2949.13 | 33459.85 | 0 | 36408.98 | 617 | 748.35
NHT-014263 - Survey | 26-PC-38571 | Completed |  |  | 334178 | 243014.01 | 243014.01 | 38116.31 | 159377.51 | 0 | 197493.82 | 3271 | 3001.96
NHT-014268 - Site Recordation | 26-PC-38571 | Completed |  |  | 164979 | 119972.63 | 119972.63 | 18817.49 | 78682.46 | 0 | 97499.95 | 1951 | 1557.62
NHT-014269 - Curation | 26-PC-38571 | Completed |  |  | 94443 | 68679.28 | 68679.28 | 10772.22 | 45042.4 | 0 | 55814.62 | 1216 | 908.79
NHT-014275 - Site Recordation | 26-PC-38573 | In progress |  |  | 1121 | 837.31 | 837.31 | 0 | 0 | 0 | 0 | 10 | 0
NHT-014276 - Survey | 26-PC-38573 | In progress |  |  | 4950 | 3698.12 | 3698.12 | 4.5 | 31.39 | 0 | 35.89 | 39 | 0.5
NHT-014280 - Testing | 26-PC-38573 | In progress |  |  | 1681 | 1255.97 | 1255.97 | 0 | 0 | 0 | 0 | 15 | 0
NHT-014282 - Background Research | 26-PC-38573 | In progress |  |  | 13441 | 10041.97 | 10041.97 | 9.47 | 66.06 | 0 | 75.53 | 111 | 1
NHT-014286 - Project Management | 26-PC-38573 | In progress |  |  | 78907 | 58951.34 | 58951.34 | 88.52 | 617.61 | 0 | 706.13 | 531 | 8.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38573 | In progress |  |  | 0 | 0 | 0 | 0 | 15.69 | 0 | 15.69 | 0 | 0.25
NHT-014295 - Draft Report | 26-PC-38624 | Completed |  |  | 54875 | 39855.71 | 39855.71 | 3419.62 | 48392.8 | 0 | 51812.42 | 703 | 921.05
NHT-014297 - Prefield | 26-PC-38624 | Completed |  |  | 23025 | 16723.06 | 16723.06 | 1434.84 | 20305.14 | 0 | 21739.98 | 260 | 390.45
NHT-014301 - Curation | 26-PC-38647 | In progress |  |  | 343041 | 223765.72 | 223765.72 | 6805.99 | 49596.95 | 0 | 56402.94 | 0 | 943.25
NHT-014302 - Data Recovery Excavation | 26-PC-38647 | In progress |  |  | 198391 | 129410.48 | 129410.48 | 6547.15 | 47710.71 | 0 | 54257.86 | 0 | 874.5
NHT-014309 - Survey | 26-PC-38647 | In progress |  |  | 252368 | 164619.54 | 164619.54 | 7591.66 | 55322.42 | 0 | 62914.08 | 0 | 1050
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38647 | In progress |  |  | 0 | 0 | 0 | 0 | 3923.39 | 0 | 3923.39 | 0 | 69.25
NHT-014320 - Reporting | 26-PC-38675 | Completed |  |  | 84215 | 66327.76 | 66327.76 | 2522.69 | 13306.6 | 0 | 15829.29 | 1120 | 271.25
NHT-014324 - Site Recordation | 26-PC-38675 | Completed |  |  | 35743 | 28151.29 | 28151.29 | 2930.63 | 15458.41 | 0 | 18389.04 | 436 | 321.25
NHT-014327 - Agency Consultation | 26-PC-38675 | Completed |  |  | 112136 | 88318.21 | 88318.21 | 3375.22 | 17803.52 | 0 | 21178.74 | 1196 | 370.5
NHT-014332 - Testing | 26-PC-38675 | Completed |  |  | 57606 | 45370.46 | 45370.46 | 1682.59 | 8875.29 | 0 | 10557.88 | 657 | 182.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38675 | Completed |  |  | 0 | 0 | 0 | 0 | 571.18 | 0 | 571.18 | 0 | 12
NHT-014338 - GIS & Mapping | 26-PC-38691 | On hold |  |  | 280778 | 199661.53 | 199661.53 | 0 | 0 | 0 | 0 | 4738 | 0
NHT-014342 - Site Recordation | 26-PC-38691 | On hold |  |  | 476860 | 339095.22 | 339095.22 | 0 | 0 | 0 | 0 | 6824 | 0
NHT-014347 - Project Management | 26-PC-38691 | On hold |  |  | 474086 | 337122.27 | 337122.27 | 0 | 0 | 0 | 0 | 10647 | 0
NHT-014350 - Testing | 26-PC-38691 | On hold |  |  | 695476 | 494552.9 | 494552.9 | 0 | 0 | 0 | 0 | 10133 | 0
NHT-014356 - Reporting | 26-PC-38709 | In progress |  |  | 189 | 153.21 | 153.21 | 0 | 0 | 0 | 0 | 3 | 0
NHT-014363 - Project Management | 26-PC-38709 | In progress |  |  | 8651 | 7003.74 | 7003.74 | 637.23 | 2170.23 | 0 | 2807.46 | 173 | 53
NHT-014366 - Site Recordation | 26-PC-38709 | In progress |  |  | 636 | 514.74 | 514.74 | 117.74 | 400.99 | 0 | 518.73 | 9 | 10
NHT-014368 - Desktop Review | 26-PC-38709 | In progress |  |  | 4540 | 3675.58 | 3675.58 | 441.19 | 1502.57 | 0 | 1943.76 | 57 | 38.75
NHT-014370 - Final Report | 26-PC-38709 | In progress |  |  | 84 | 68.09 | 68.09 | 0 | 0 | 0 | 0 | 1 | 0
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38709 | In progress |  |  | 0 | 0 | 0 | 0 | 267.83 | 0 | 267.83 | 0 | 6.75
NHT-014374 - Reporting | 26-PC-38719 | In progress |  |  | 20681 | 13403.43 | 13403.43 | 12.81 | 92.18 | 0 | 104.99 | 250 | 1.5
NHT-014376 - Monitoring | 26-PC-38719 | In progress |  |  | 71417 | 46285.15 | 46285.15 | 49.09 | 353.34 | 0 | 402.43 | 736 | 5.75
NHT-014377 - Data Recovery Excavation | 26-PC-38719 | In progress |  |  | 25091 | 16261.2 | 16261.2 | 21.35 | 153.63 | 0 | 174.98 | 224 | 2.5
NHT-014380 - GIS & Mapping | 26-PC-38719 | In progress |  |  | 170767 | 110674.6 | 110674.6 | 32.02 | 230.44 | 0 | 262.46 | 1494 | 3.75
NHT-014386 - Draft Report | 26-PC-38719 | In progress |  |  | 10644 | 6898.28 | 6898.28 | 8.54 | 61.45 | 0 | 69.99 | 102 | 1
NHT-014390 - Agency Consultation | 26-PC-38737 | Completed |  |  | 17383 | 10822.66 | 10822.66 | 3474.48 | 33584.16 | 0 | 37058.64 | 0 | 772
NHT-014397 - Monitoring | 26-PC-38737 | In progress |  |  | 80317 | 50005.36 | 50005.36 | 3346.65 | 32348.53 | 0 | 35695.18 | 0 | 749.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38737 | In progress |  |  | 0 | 0 | 0 | 0 | 3888.1 | 0 | 3888.1 | 0 | 85.5
NHT-014406 - Site Recordation | 26-PC-38769 | Completed |  |  | 19465 | 12367.96 | 12367.96 | 1861.2 | 8536.58 | 0 | 10397.78 | 233 | 154.87
NHT-014411 - Testing | 26-PC-38769 | Completed |  |  | 21035 | 13365.74 | 13365.74 | 2011.36 | 9225.27 | 0 | 11236.63 | 230 | 158.42
NHT-014413 - Project Management | 26-PC-38844 | Completed |  |  | 319700 | 236322.24 | 236322.24 | 22734.2 | 284484.71 | 0 | 307218.91 | 3530 | 5102.86
NHT-014414 - Final Report | 26-PC-38856 | Completed |  |  | 46107 | 31565.16 | 31565.16 | 3241.74 | 37792.97 | 0 | 41034.71 | 559 | 737.84
NHT-014418 - Lab Analysis | 26-PC-38856 | Completed |  |  | 91493 | 62635.8 | 62635.8 | 6432.7 | 74993.84 | 0 | 81426.54 | 934 | 1422.31
NHT-014420 - Draft Report | 26-PC-38880 | Completed |  |  | 50872 | 42742.33 | 42742.33 | 2025.5 | 31179.46 | 0 | 33204.96 | 693 | 695.38
NHT-014424 - Testing | 26-PC-38880 | Completed |  |  | 67430 | 56654.67 | 56654.67 | 2684.8 | 41328.17 | 0 | 44012.97 | 625 | 805.5
NHT-014427 - Prefield | 26-PC-38880 | Completed |  |  | 22898 | 19239.24 | 19239.24 | 911.72 | 14034.55 | 0 | 14946.27 | 297 | 234.88
NHT-014431 - Site Recordation | 26-PC-38898 | In progress |  |  | 150100 | 87478.28 | 87478.28 | 2576.37 | 18078.42 | 0 | 20654.79 | 1519 | 422.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38898 | In progress |  |  | 0 | 0 | 0 | 0 | 462.96 | 0 | 462.96 | 0 | 10
NHT-014438 - Monitoring | 26-PC-38916 | Completed |  |  | 33622 | 26003.11 | 26003.11 | 2839.54 | 30964.5 | 0 | 33804.04 | 366 | 574.68
NHT-014444 - Data Recovery Excavation | 26-PC-38916 | Completed |  |  | 20878 | 16147.19 | 16147.19 | 1763.27 | 19228.08 | 0 | 20991.35 | 266 | 383.52
NHT-014445 - Fieldwork | 26-PC-38924 | In progress |  |  | 17631 | 12606.17 | 12606.17 | 889.35 | 8602.2 | 0 | 9491.55 | 217 | 172.75
NHT-014446 - Desktop Review | 26-PC-38924 | In progress |  |  | 12218 | 8735.9 | 8735.9 | 639.12 | 6181.83 | 0 | 6820.95 | 133 | 135.75
NHT-014447 - Final Report | 26-PC-38924 | Completed |  |  | 13385 | 9570.03 | 9570.03 | 1181.02 | 11423.31 | 0 | 12604.33 | 162 | 231.5
NHT-014454 - Background Research | 26-PC-38924 | In progress |  |  | 50783 | 36309.82 | 36309.82 | 807.38 | 7809.32 | 0 | 8616.7 | 538 | 165.5
NHT-014457 - Monitoring | 26-PC-38924 | In progress |  |  | 23183 | 16576.08 | 16576.08 | 428.91 | 4148.65 | 0 | 4577.56 | 229 | 70.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38924 | In progress |  |  | 0 | 0 | 0 | 0 | 1249.13 | 0 | 1249.13 | 0 | 24.75
NHT-014464 - Final Report | 26-PC-38943 | In progress |  |  | 47744 | 22145.11 | 29685.87 | 1245.09 | 14494.11 | 0 | 15739.2 | 518 | 312.25
NHT-014469 - Prefield | 26-PC-38943 | In progress |  |  | 36154 | 16769.84 | 22480.23 | 1145.79 | 13338.14 | 0 | 14483.93 | 371 | 236
NHT-014476 - Data Recovery Excavation | 26-PC-38943 | In progress |  |  | 32971 | 15293.34 | 20500.97 | 1489.04 | 17334.04 | 0 | 18823.08 | 458 | 344.25
NHT-014478 - Site Recordation | 26-PC-38943 | Completed |  |  | 12231 | 5673.23 | 7605.05 | 1401.04 | 16309.54 | 0 | 17710.58 | 147 | 326.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38943 | In progress |  |  | 0 | 0 | 0 | 0 | 1827.12 | 0 | 1827.12 | 0 | 44.25
NHT-014489 - Survey | 26-PC-38966 | In progress |  |  | 16062 | 11510.22 | 11510.22 | 13.07 | 109.04 | 0 | 122.11 | 132 | 1.75
NHT-014494 - Reporting | 26-PC-38966 | In progress |  |  | 78351 | 56146.58 | 56146.58 | 389.48 | 3250.51 | 0 | 3639.99 | 737 | 78.25
NHT-014495 - Fieldwork | 26-PC-38966 | In progress |  |  | 174987 | 125395.24 | 125395.24 | 517.64 | 4320.16 | 0 | 4837.8 | 1704 | 104
NHT-014502 - Final Report | 26-PC-38993 | In progress |  |  | 54346 | 35487.88 | 35487.88 | 1549.44 | 15542.34 | 0 | 17091.78 | 524 | 227.5
NHT-014506 - Curation | 26-PC-38993 | In progress |  |  | 114685 | 74889.45 | 74889.45 | 965.52 | 9685.01 | 0 | 10650.53 | 786 | 142.75
NHT-014511 - Site Recordation | 26-PC-38993 | In progress |  |  | 32369 | 21136.87 | 21136.87 | 794.75 | 7972.07 | 0 | 8766.82 | 234 | 118.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-38993 | In progress |  |  | 0 | 0 | 0 | 0 | 1101.25 | 0 | 1101.25 | 0 | 16.25
NHT-014519 - Survey | 26-PC-39024 | In progress |  |  | 175497 | 94196.01 | 123805.81 | 465.73 | 2090.6 | 0 | 2556.33 | 1498 | 31.5
NHT-014525 - Project Management | 26-PC-39024 | In progress |  |  | 36303 | 19485.54 | 25610.66 | 466.73 | 2095.13 | 0 | 2561.86 | 303 | 34.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39024 | In progress |  |  | 0 | 0 | 0 | 0 | 783.44 | 0 | 783.44 | 0 | 11
NHT-014534 - Final Report | 26-PC-39043 | In progress |  |  | 41585 | 32702.39 | 32702.39 | 383.9 | 5074.13 | 0 | 5458.03 | 679 | 113.75
NHT-014541 - Survey | 26-PC-39043 | In progress |  |  | 23928 | 18817.15 | 18817.15 | 318.54 | 4210.15 | 0 | 4528.69 | 414 | 98
NHT-014545 - Background Research | 26-PC-39043 | In progress |  |  | 15734 | 12373.11 | 12373.11 | 46.34 | 612.45 | 0 | 658.79 | 224 | 14
NHT-014547 - Desktop Review | 26-PC-39043 | In progress |  |  | 14078 | 11070.72 | 11070.72 | 195.04 | 2577.86 | 0 | 2772.9 | 291 | 55.25
NHT-014553 - Monitoring | 26-PC-39043 | In progress |  |  | 27875 | 21921.11 | 21921.11 | 95.77 | 1265.85 | 0 | 1361.62 | 417 | 27.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39043 | In progress |  |  | 0 | 0 | 0 | 0 | 736.17 | 0 | 736.17 | 0 | 17
NHT-014562 - Monitoring | 26-PC-39051 | Completed |  |  | 232796 | 172222.62 | 172222.62 | 17870.18 | 111623.87 | 0 | 129494.05 | 2427 | 2628.54
NHT-014564 - Survey | 26-PC-39051 | Completed |  |  | 278104 | 205741.2 | 205741.2 | 21348.13 | 133348.49 | 0 | 154696.62 | 2768 | 2734.14
NHT-014569 - Site Recordation | 26-PC-39143 | In progress |  |  | 137577 | 100774.88 | 100774.88 | 225.37 | 1209.02 | 0 | 1434.39 | 1023 | 18.25
NHT-014574 - GIS & Mapping | 26-PC-39143 | In progress |  |  | 96883 | 70967.13 | 70967.13 | 104.43 | 560.22 | 0 | 664.65 | 586 | 9
NHT-014577 - Draft Report | 26-PC-39143 | In progress |  |  | 265940 | 194800.99 | 194800.99 | 272.9 | 1464.01 | 0 | 1736.91 | 1795 | 22.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39143 | In progress |  |  | 0 | 0 | 0 | 0 | 129.16 | 0 | 129.16 | 0 | 2
NHT-014589 - Project Management | 26-PC-39165 | Completed |  |  | 28378 | 19024.3 | 19024.3 | 4611.28 | 16641.67 | 0 | 21252.95 | 107 | 197.25
NHT-014590 - Curation | 26-PC-39165 | Completed |  |  | 21867 | 14659.9 | 14659.9 | 5960.78 | 21511.9 | 0 | 27472.68 | 104 | 199.5
NHT-014595 - Background Research | 26-PC-39165 | Completed |  |  | 44055 | 29534.52 | 29534.52 | 2036.24 | 7348.6 | 0 | 9384.84 | 184 | 110.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39165 | Completed |  |  | 0 | 0 | 0 | 0 | 532.8 | 0 | 532.8 | 0 | 6.75
NHT-014603 - Desktop Review | 26-PC-39230 | In progress |  |  | 242691 | 182479.45 | 182479.45 | 1972.66 | 15572.82 | 0 | 17545.48 | 1738 | 317.5
NHT-014608 - Site Recordation | 26-PC-39230 | In progress |  |  | 332709 | 250163.81 | 250163.81 | 2509.5 | 19810.88 | 0 | 22320.38 | 2093 | 380.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39230 | In progress |  |  | 0 | 0 | 0 | 0 | 513.92 | 0 | 513.92 | 0 | 11
NHT-014616 - Testing | 26-PC-39232 | Completed |  |  | 6139 | 4536.94 | 4536.94 | 388.52 | 5410.21 | 0 | 5798.73 | 67 | 108.79
NHT-014617 - Draft Report | 26-PC-39232 | Completed |  |  | 4861 | 3592.06 | 3592.06 | 307.6 | 4283.47 | 0 | 4591.07 | 53 | 82.27
NHT-014621 - Site Recordation | 26-PC-39249 | Completed |  |  | 32006 | 24292.58 | 24292.58 | 0 | 0 | 0 | 0 | 241 | 0
NHT-014628 - Lab Analysis | 26-PC-39249 | Completed |  |  | 25918 | 19671.42 | 19671.42 | 0 | 0 | 0 | 0 | 191 | 0
NHT-014634 - Survey | 26-PC-39249 | Completed |  |  | 68276 | 51821.8 | 51821.8 | 0 | 0 | 0 | 0 | 493 | 0
NHT-014638 - Desktop Review | 26-PC-39264 | Completed |  |  | 12659 | 10239.59 | 10239.59 | 2220.94 | 7966.86 | 0 | 10187.8 | 99 | 146.82
NHT-014644 - Project Management | 26-PC-39264 | Completed |  |  | 24441 | 19770.6 | 19770.6 | 4288.19 | 15382.42 | 0 | 19670.61 | 213 | 331.71
NHT-014650 - Prefield | 26-PC-39277 | Completed |  |  | 2778 | 1822.6 | 1822.6 | 0 | 0 | 0 | 0 | 27 | 0
NHT-014656 - Final Report | 26-PC-39277 | Completed |  |  | 499071 | 327389.96 | 327389.96 | 11.93 | 112.37 | 0 | 124.3 | 6200 | 1.75
NHT-014661 - Data Recovery Excavation | 26-PC-39277 | Completed |  |  | 11907 | 7811.15 | 7811.15 | 0 | 0 | 0 | 0 | 137 | 0
NHT-014666 - Testing | 26-PC-39277 | Completed |  |  | 7144 | 4686.69 | 4686.69 | 0 | 0 | 0 | 0 | 100 | 0
NHT-014673 - Final Report | 26-PC-39303 | Completed |  |  | 14250 | 12343.05 | 12343.05 | 812.09 | 3601.44 | 0 | 4413.53 | 132 | 67.25
NHT-014676 - Monitoring | 26-PC-39303 | Completed |  |  | 26950 | 23344.39 | 23344.39 | 700.11 | 3104.82 | 0 | 3804.93 | 364 | 43.75
NHT-014678 - Draft Report | 26-PC-39335 | Completed |  |  | 26966 | 18088.62 | 18088.62 | 1797.74 | 14545.34 | 0 | 16343.08 | 214 | 278.7
NHT-014680 - Fieldwork | 26-PC-39335 | Completed |  |  | 34723 | 23292.52 | 23292.52 | 2314.93 | 18729.88 | 0 | 21044.81 | 340 | 404.92
NHT-014685 - Final Report | 26-PC-39335 | Completed |  |  | 8481 | 5689.12 | 5689.12 | 565.41 | 4574.71 | 0 | 5140.12 | 84 | 92.63
NHT-014691 - Desktop Review | 26-PC-39335 | Completed |  |  | 8530 | 5721.7 | 5721.7 | 568.65 | 4600.91 | 0 | 5169.56 | 84 | 96.68
NHT-014694 - Final Report | 26-PC-39372 | Completed |  |  | 12105 | 7826.76 | 7826.76 | 1.35 | 13.15 | 0 | 14.5 | 86 | 0.25
NHT-014700 - Background Research | 26-PC-39372 | Completed |  |  | 65 | 42.14 | 42.14 | 0 | 0 | 0 | 0 | 0 | 0
NHT-014702 - Site Recordation | 26-PC-39372 | Completed |  |  | 130 | 84.28 | 84.28 | 0 | 0 | 0 | 0 | 1 | 0
NHT-014703 - Project Management | 26-PC-39390 | Completed |  |  | 6608 | 4191.87 | 4191.87 | 127.24 | 476.39 | 0 | 603.63 | 54 | 9
NHT-014704 - Monitoring | 26-PC-39390 | Completed |  |  | 7384 | 4684.25 | 4684.25 | 116.72 | 437.03 | 0 | 553.75 | 74 | 7.25
NHT-014708 - Data Recovery Excavation | 26-PC-39390 | Completed |  |  | 26684 | 16929.29 | 16929.29 | 413.39 | 1547.8 | 0 | 1961.19 | 235 | 34
NHT-014711 - Draft Report | 26-PC-39390 | Completed |  |  | 10160 | 6445.25 | 6445.25 | 208.39 | 780.23 | 0 | 988.62 | 92 | 13.75
NHT-014713 - Testing | 26-PC-39390 | Completed |  |  | 8764 | 5559.58 | 5559.58 | 229.68 | 859.95 | 0 | 1089.63 | 75 | 14.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39390 | Completed |  |  | 0 | 0 | 0 | 0 | 199.31 | 0 | 199.31 | 0 | 3.5
NHT-014724 - Prefield | 26-PC-39408 | Completed |  |  | 22561 | 11898.84 | 16176.62 | 2149.58 | 13427.08 | 0 | 15576.66 | 225 | 231.54
NHT-014730 - Fieldwork | 26-PC-39408 | Completed |  |  | 80439 | 42425.05 | 57677.43 | 7664.28 | 47874 | 0 | 55538.28 | 1038 | 857.69
NHT-014736 - Final Report | 26-PC-39446 | Completed |  |  | 26990 | 21014.29 | 21014.29 | 1798.38 | 12304.73 | 0 | 14103.11 | 0 | 204.75
NHT-014741 - Testing | 26-PC-39446 | Completed |  |  | 48967 | 38125.59 | 38125.59 | 948 | 6486.3 | 0 | 7434.3 | 0 | 91.25
NHT-014745 - Project Management | 26-PC-39446 | Completed |  |  | 55243 | 43012.44 | 43012.44 | 624.69 | 4274.22 | 0 | 4898.91 | 0 | 90
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39446 | Completed |  |  | 0 | 0 | 0 | 0 | 2132.08 | 0 | 2132.08 | 0 | 47
NHT-014755 - Data Recovery Excavation | 26-PC-39534 | On hold |  |  | 551900 | 348248.9 | 348248.9 | 0 | 0 | 0 | 0 | 5966 | 0
NHT-014758 - Curation | 26-PC-39537 | In progress |  |  | 82700 | 63951.91 | 63951.91 | 410.21 | 4871.93 | 0 | 5282.14 | 868 | 112
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39537 | In progress |  |  | 0 | 0 | 0 | 0 | 45.34 | 0 | 45.34 | 0 | 0.75
NHT-014769 - Draft Report | 26-PC-39565 | In progress |  |  | 16839 | 10445.49 | 10445.49 | 555.34 | 6536.66 | 0 | 7092 | 196 | 144.5
NHT-014771 - Curation | 26-PC-39565 | In progress |  |  | 30075 | 18655.76 | 18655.76 | 268.31 | 3158.11 | 0 | 3426.42 | 225 | 70.25
NHT-014774 - Survey | 26-PC-39565 | In progress |  |  | 6642 | 4120.13 | 4120.13 | 262.58 | 3090.72 | 0 | 3353.3 | 60 | 64.75
NHT-014778 - Final Report | 26-PC-39565 | In progress |  |  | 44044 | 27319.9 | 27319.9 | 385.19 | 4533.96 | 0 | 4919.15 | 423 | 103
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39565 | In progress |  |  | 0 | 0 | 0 | 0 | 318.52 | 0 | 318.52 | 0 | 7.5
NHT-014787 - Reporting | 26-PC-39587 | Completed |  |  | 248052 | 181995.74 | 181995.74 | 34271.36 | 148997.95 | 0 | 183269.31 | 2478 | 2879.36
NHT-014791 - Agency Consultation | 26-PC-39587 | Completed |  |  | 40848 | 29970.19 | 29970.19 | 5643.64 | 24536.27 | 0 | 30179.91 | 417 | 536.25
NHT-014795 - Prefield | 26-PC-39595 | Completed |  |  | 20938 | 15244.75 | 15244.75 | 1801.82 | 12165.77 | 0 | 13967.59 | 278 | 266.25
NHT-014802 - Testing | 26-PC-39595 | Completed |  |  | 45762 | 33319.52 | 33319.52 | 3938.12 | 26589.99 | 0 | 30528.11 | 652 | 484.88
NHT-014809 - Monitoring | 26-PC-39619 | In progress |  |  | 6672 | 4570.63 | 4570.63 | 13.49 | 84.97 | 0 | 98.46 | 57 | 1.5
NHT-014814 - Draft Report | 26-PC-39619 | In progress |  |  | 67643 | 46335.31 | 46335.31 | 222.87 | 1403.9 | 0 | 1626.77 | 436 | 29.5
NHT-014821 - Fieldwork | 26-PC-39619 | In progress |  |  | 4685 | 3209.06 | 3209.06 | 10.46 | 65.88 | 0 | 76.34 | 28 | 1
NHT-014823 - Project Management | 26-PC-39638 | In progress |  |  | 15173 | 7242.63 | 9879.02 | 616.48 | 2263.65 | 0 | 2880.13 | 113 | 34.5
NHT-014829 - GIS & Mapping | 26-PC-39638 | In progress |  |  | 18087 | 8633.37 | 11776 | 1039.58 | 3817.25 | 0 | 4856.83 | 99 | 57
NHT-014836 - Reporting | 26-PC-39638 | In progress |  |  | 11501 | 5489.8 | 7488.14 | 855.43 | 3141.05 | 0 | 3996.48 | 64 | 44.25
NHT-014843 - Draft Report | 26-PC-39638 | In progress |  |  | 57112 | 27262.14 | 37185.8 | 1279.43 | 4698.01 | 0 | 5977.44 | 312 | 104
NHT-014849 - Monitoring | 26-PC-39638 | In progress |  |  | 29827 | 14237.39 | 19419.94 | 1123.18 | 4124.21 | 0 | 5247.39 | 175 | 61.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39638 | In progress |  |  | 0 | 0 | 0 | 0 | 554.19 | 0 | 554.19 | 0 | 10.75
NHT-014856 - Site Recordation | 26-PC-39644 | Completed |  |  | 39598 | 27449.32 | 27449.32 | 3090.01 | 22876.46 | 0 | 25966.47 | 455 | 463.94
NHT-014857 - Testing | 26-PC-39644 | Completed |  |  | 60702 | 42078.64 | 42078.64 | 4736.85 | 35068.65 | 0 | 39805.5 | 766 | 858.92
NHT-014864 - Prefield | 26-PC-39671 | Completed |  |  | 6532 | 4873.09 | 4873.09 | 1336.69 | 4998.33 | 0 | 6335.02 | 0 | 109.88
NHT-014868 - Data Recovery Excavation | 26-PC-39671 | Completed |  |  | 28554 | 21301.2 | 21301.2 | 5842.93 | 21848.64 | 0 | 27691.57 | 0 | 525.04
NHT-014873 - Site Recordation | 26-PC-39671 | Completed |  |  | 11181 | 8340.67 | 8340.67 | 2287.84 | 8555.02 | 0 | 10842.86 | 0 | 161.62
NHT-014878 - Desktop Review | 26-PC-39671 | Completed |  |  | 6811 | 5081.15 | 5081.15 | 1393.76 | 5211.74 | 0 | 6605.5 | 0 | 93.49
NHT-014883 - GIS & Mapping | 26-PC-39671 | Completed |  |  | 9422 | 7028.89 | 7028.89 | 1928.02 | 7209.53 | 0 | 9137.55 | 0 | 174.26
NHT-014887 - Background Research | 26-PC-39699 | In progress |  |  | 15324 | 10818.41 | 10818.41 | 61.23 | 631.39 | 0 | 692.62 | 329 | 13.75
NHT-014893 - Reporting | 26-PC-39699 | In progress |  |  | 19323 | 13642.02 | 13642.02 | 139.79 | 1441.51 | 0 | 1581.3 | 350 | 30
NHT-014894 - Prefield | 26-PC-39699 | In progress |  |  | 17775 | 12549 | 12549 | 122.92 | 1267.54 | 0 | 1390.46 | 332 | 30
NHT-014897 - Testing | 26-PC-39699 | In progress |  |  | 22971 | 16217.86 | 16217.86 | 185.71 | 1914.91 | 0 | 2100.62 | 418 | 44
NHT-014901 - Lab Analysis | 26-PC-39699 | In progress |  |  | 12807 | 9041.91 | 9041.91 | 58.33 | 601.51 | 0 | 659.84 | 199 | 9.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39699 | In progress |  |  | 0 | 0 | 0 | 0 | 587.24 | 0 | 587.24 | 0 | 14.25
NHT-014913 - Prefield | 26-PC-39711 | Completed |  |  | 12962 | 11011.49 | 11011.49 | 1688.24 | 10817.26 | 0 | 12505.5 | 233 | 187.66
NHT-014920 - Draft Report | 26-PC-39711 | Completed |  |  | 48117 | 40875.45 | 40875.45 | 6266.88 | 40154.44 | 0 | 46421.32 | 893 | 776.68
NHT-014927 - Background Research | 26-PC-39711 | Completed |  |  | 8521 | 7238.26 | 7238.26 | 1109.74 | 7110.59 | 0 | 8220.33 | 138 | 132.63
NHT-014931 - Desktop Review | 26-PC-39725 | Completed |  |  | 19151 | 14298.02 | 14298.02 | 1383.75 | 15089.45 | 0 | 16473.2 | 227 | 299.12
NHT-014934 - Reporting | 26-PC-39725 | Completed |  |  | 96749 | 72232.92 | 72232.92 | 6990.63 | 76231.14 | 0 | 83221.77 | 922 | 1145.87
NHT-014937 - Prefield | 26-PC-39730 | Completed |  |  | 6371 | 4633.69 | 4633.69 | 455.63 | 3925.39 | 0 | 4381.02 | 87 | 76.45
NHT-014938 - Monitoring | 26-PC-39730 | Completed |  |  | 19229 | 13985.19 | 13985.19 | 1375.14 | 11847.41 | 0 | 13222.55 | 268 | 233.42
NHT-014943 - Reporting | 26-PC-39744 | In progress |  |  | 47328 | 30389.25 | 30389.25 | 265.11 | 3980.31 | 0 | 4245.42 | 516 | 91.75
NHT-014945 - Agency Consultation | 26-PC-39744 | In progress |  |  | 99410 | 63831.15 | 63831.15 | 220.19 | 3305.85 | 0 | 3526.04 | 1269 | 74
NHT-014950 - Testing | 26-PC-39744 | In progress |  |  | 204362 | 131220.91 | 131220.91 | 386.64 | 5804.91 | 0 | 6191.55 | 2546 | 130.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39744 | In progress |  |  | 0 | 0 | 0 | 0 | 100.62 | 0 | 100.62 | 0 | 2.25
NHT-014959 - Lab Analysis | 26-PC-39778 | In progress |  |  | 580 | 326.58 | 432.63 | 4.43 | 45.9 | 0 | 50.33 | 8 | 0.75
NHT-014964 - Site Recordation | 26-PC-39778 | In progress |  |  | 7858 | 4422.27 | 5858.31 | 21.97 | 227.7 | 0 | 249.67 | 97 | 3.75
NHT-014967 - Monitoring | 26-PC-39778 | In progress |  |  | 710 | 399.36 | 529.04 | 1.3 | 13.5 | 0 | 14.8 | 10 | 0.25
NHT-014970 - Data Recovery Excavation | 26-PC-39778 | In progress |  |  | 6927 | 3898.04 | 5163.84 | 52.59 | 545.02 | 0 | 597.61 | 107 | 11.25
NHT-014972 - Fieldwork | 26-PC-39778 | In progress |  |  | 19625 | 11043.67 | 14629.88 | 54.92 | 569.1 | 0 | 624.02 | 293 | 11.5
NHT-014973 - Final Report | 26-PC-39780 | In progress |  |  | 113500 | 76714.65 | 76714.65 | 415.04 | 5118.81 | 0 | 5533.85 | 1009 | 116.25
NHT-014975 - Project Management | 26-PC-39880 | In progress |  |  | 22591 | 15640.96 | 16632.46 | 3530.86 | 11665.51 | 0 | 15196.37 | 0 | 247.5
NHT-014978 - Site Recordation | 26-PC-39880 | In progress |  |  | 77609 | 53733.63 | 57139.86 | 2404.31 | 7943.52 | 0 | 10347.83 | 0 | 163
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39880 | In progress |  |  | 0 | 0 | 0 | 0 | 1557.02 | 0 | 1557.02 | 0 | 32.75
NHT-014982 - Data Recovery Excavation | 26-PC-39913 | On hold |  |  | 49169 | 32249.4 | 32249.4 | 0 | 0 | 0 | 0 | 487 | 0
NHT-014987 - Monitoring | 26-PC-39913 | On hold |  |  | 29960 | 19650.64 | 19650.64 | 0 | 0 | 0 | 0 | 296 | 0
NHT-014992 - Prefield | 26-PC-39913 | On hold |  |  | 12116 | 7947.1 | 7947.1 | 0 | 0 | 0 | 0 | 153 | 0
NHT-014995 - Final Report | 26-PC-39913 | On hold |  |  | 9751 | 6395.9 | 6395.9 | 0 | 0 | 0 | 0 | 84 | 0
NHT-014996 - Project Management | 26-PC-39913 | On hold |  |  | 18404 | 12071.42 | 12071.42 | 0 | 0 | 0 | 0 | 204 | 0
NHT-015002 - Testing | 26-PC-39971 | Completed |  |  | 24924 | 17269.55 | 17269.55 | 1890.33 | 14889.13 | 0 | 16779.46 | 195 | 271.25
NHT-015003 - Prefield | 26-PC-39971 | Completed |  |  | 18138 | 12568 | 12568 | 2053.38 | 16173.41 | 0 | 18226.79 | 96 | 330.25
NHT-015004 - Project Management | 26-PC-39971 | Completed |  |  | 43218 | 29945.64 | 29945.64 | 977.03 | 7695.54 | 0 | 8672.57 | 304 | 147
NHT-015009 - Background Research | 26-PC-39971 | Completed |  |  | 14908 | 10330.05 | 10330.05 | 1104.54 | 8699.9 | 0 | 9804.44 | 80 | 168.25
NHT-015011 - Final Report | 26-PC-39971 | Completed |  |  | 13412 | 9293.1 | 9293.1 | 1068.44 | 8415.53 | 0 | 9483.97 | 105 | 164.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-39971 | Completed |  |  | 0 | 0 | 0 | 0 | 2112.76 | 0 | 2112.76 | 0 | 39.75
NHT-015016 - Reporting | 26-PC-39990 | In progress |  |  | 13199 | 9047.68 | 9047.68 | 37.19 | 251.11 | 0 | 288.3 | 212 | 5.25
NHT-015022 - GIS & Mapping | 26-PC-39990 | In progress |  |  | 2401 | 1646.12 | 1646.12 | 16.69 | 112.69 | 0 | 129.38 | 34 | 2.25
NHT-015029 - Data Recovery Excavation | 26-PC-40009 | In progress |  |  | 33574 | 22884.25 | 22884.25 | 372.87 | 4808.35 | 0 | 5181.22 | 347 | 105.5
NHT-015030 - Prefield | 26-PC-40009 | In progress |  |  | 22349 | 15232.84 | 15232.84 | 368.08 | 4746.58 | 0 | 5114.66 | 232 | 107
NHT-015034 - Monitoring | 26-PC-40009 | In progress |  |  | 7677 | 5232.67 | 5232.67 | 412.81 | 5323.26 | 0 | 5736.07 | 84 | 120.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40009 | In progress |  |  | 0 | 0 | 0 | 0 | -227.06 | 0 | -227.06 | 0 | -3.5
NHT-015045 - Project Management | 26-PC-40038 | Completed |  |  | 161858 | 127835.77 | 127835.77 | 21619.85 | 97826.83 | 0 | 119446.68 | 0 | 2373.67
NHT-015052 - GIS & Mapping | 26-PC-40038 | Completed |  |  | 134397 | 106146.45 | 106146.45 | 17951.71 | 81229 | 0 | 99180.71 | 0 | 1378.28
NHT-015053 - Background Research | 26-PC-40038 | Completed |  |  | 52445 | 41421.04 | 41421.04 | 7005.21 | 31697.62 | 0 | 38702.83 | 0 | 523.57
NHT-015058 - Data Recovery Excavation | 26-PC-40055 | In progress |  |  | 19959 | 11601.92 | 12936.56 | 479.06 | 4217.61 | 0 | 4696.67 | 196 | 74.25
NHT-015059 - Fieldwork | 26-PC-40055 | In progress |  |  | 2041 | 1186.26 | 1322.73 | 21.85 | 192.35 | 0 | 214.2 | 23 | 5
NHT-015061 - Monitoring | 26-PC-40092 | In progress |  |  | 870885 | 562068.87 | 562068.87 | 399.15 | 4085.74 | 0 | 4484.89 | 11980 | 107
NHT-015062 - Final Report | 26-PC-40092 | In progress |  |  | 2801115 | 1807839.93 | 1807839.93 | 485.11 | 4965.54 | 0 | 5450.65 | 36909 | 134.75
NHT-015069 - Background Research | 26-PC-40108 | Completed |  |  | 138800 | 89484.36 | 89484.36 | 13232.31 | 77399.96 | 0 | 90632.27 | 912 | 1492.31
NHT-015076 - Reporting | 26-PC-40128 | Completed |  |  | 15190 | 11096.42 | 11096.42 | 1982.9 | 9347.97 | 0 | 11330.87 | 130 | 174.2
NHT-015081 - Monitoring | 26-PC-40128 | Completed |  |  | 21489 | 15697.1 | 15697.1 | 2805.03 | 13223.72 | 0 | 16028.75 | 159 | 286.09
NHT-015086 - Draft Report | 26-PC-40128 | Completed |  |  | 16750 | 12235.93 | 12235.93 | 2186.53 | 10307.93 | 0 | 12494.46 | 113 | 173.92
NHT-015088 - Background Research | 26-PC-40128 | Completed |  |  | 5441 | 3974.76 | 3974.76 | 710.28 | 3348.46 | 0 | 4058.74 | 31 | 76.06
NHT-015093 - Project Management | 26-PC-40128 | Completed |  |  | 8230 | 6012.34 | 6012.34 | 1074.39 | 5064.98 | 0 | 6139.37 | 61 | 96.67
NHT-015095 - Draft Report | 26-PC-40176 | Completed |  |  | 14907 | 9668.88 | 9668.88 | 310.5 | 4306.37 | 0 | 4616.87 | 173 | 110.25
NHT-015096 - Prefield | 26-PC-40176 | Completed |  |  | 22518 | 14605.11 | 14605.11 | 173.91 | 2411.95 | 0 | 2585.86 | 271 | 61.75
NHT-015097 - Monitoring | 26-PC-40176 | Completed |  |  | 24275 | 15745.03 | 15745.03 | 324.58 | 4501.67 | 0 | 4826.25 | 311 | 115.25
NHT-015102 - GIS & Mapping | 26-PC-40176 | Completed |  |  | 30061 | 19497.76 | 19497.76 | 354.15 | 4911.79 | 0 | 5265.94 | 299 | 122.25
NHT-015104 - Agency Consultation | 26-PC-40176 | Completed |  |  | 51839 | 33622.18 | 33622.18 | 405.53 | 5624.64 | 0 | 6030.17 | 618 | 144
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40176 | Completed |  |  | 0 | 0 | 0 | 0 | 87.89 | 0 | 87.89 | 0 | 2.25
NHT-015118 - GIS & Mapping | 26-PC-40190 | On hold |  |  | 28179 | 20959.18 | 22633.77 | 0 | 0 | 0 | 0 | 328 | 0
NHT-015120 - Data Recovery Excavation | 26-PC-40190 | On hold |  |  | 85721 | 63757.4 | 68851.48 | 0 | 0 | 0 | 0 | 839 | 0
NHT-015121 - Data Recovery Excavation | 26-PC-40229 | Completed |  |  | 118236 | 73187.34 | 73187.34 | 9799.78 | 85343.76 | 0 | 95143.54 | 1413 | 1436.57
NHT-015123 - GIS & Mapping | 26-PC-40229 | Completed |  |  | 31169 | 19293.66 | 19293.66 | 2583.42 | 22498.34 | 0 | 25081.76 | 247 | 467.73
NHT-015129 - Testing | 26-PC-40229 | Completed |  |  | 89939 | 55672.55 | 55672.55 | 7454.55 | 64919.76 | 0 | 72374.31 | 901 | 1185.93
NHT-015136 - Survey | 26-PC-40229 | Completed |  |  | 98260 | 60823.06 | 60823.06 | 8144.21 | 70925.77 | 0 | 79069.98 | 1140 | 1350
NHT-015138 - Site Recordation | 26-PC-40229 | Completed |  |  | 33196 | 20548.59 | 20548.59 | 2751.46 | 23961.71 | 0 | 26713.17 | 369 | 414.19
NHT-015139 - Data Recovery Excavation | 26-PC-40289 | Completed |  |  | 61690 | 49734.36 | 49734.36 | 3879.91 | 42865.95 | 0 | 46745.86 | 0 | 874.61
NHT-015141 - Desktop Review | 26-PC-40289 | Completed |  |  | 11285 | 9097.91 | 9097.91 | 709.75 | 7841.47 | 0 | 8551.22 | 0 | 139.93
NHT-015145 - Survey | 26-PC-40289 | Completed |  |  | 45148 | 36398.47 | 36398.47 | 2839.54 | 31371.77 | 0 | 34211.31 | 0 | 706.64
NHT-015147 - Prefield | 26-PC-40289 | Completed |  |  | 17677 | 14251.22 | 14251.22 | 1111.77 | 12283.1 | 0 | 13394.87 | 0 | 218.77
NHT-015148 - Draft Report | 26-PC-40296 | In progress |  |  | 924 | 671.08 | 671.08 | 27.68 | 136.76 | 0 | 164.44 | 4 | 1.75
NHT-015154 - Data Recovery Excavation | 26-PC-40296 | In progress |  |  | 85 | 61.45 | 61.45 | 0 | 0 | 0 | 0 | 0 | 0
NHT-015161 - Desktop Review | 26-PC-40296 | In progress |  |  | 3923 | 2849.24 | 2849.24 | 63.26 | 312.59 | 0 | 375.85 | 18 | 4
NHT-015162 - Lab Analysis | 26-PC-40296 | In progress |  |  | 1468 | 1066.55 | 1066.55 | 35.59 | 175.84 | 0 | 211.43 | 6 | 2.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40296 | In progress |  |  | 0 | 0 | 0 | 0 | 39.08 | 0 | 39.08 | 0 | 0.5
NHT-015166 - Desktop Review | 26-PC-40304 | In progress |  |  | 132900 | 73563.57 | 101283.22 | 1875.54 | 11915.21 | 0 | 13790.75 | 2649 | 285.5
NHT-015169 - Draft Report | 26-PC-40329 | Completed |  |  | 186111 | 125830.31 | 125830.31 | 33370.2 | 130209.19 | 0 | 163579.39 | 1157 | 2142.87
NHT-015175 - Agency Consultation | 26-PC-40329 | Completed |  |  | 73103 | 49424.61 | 49424.61 | 13107.41 | 51144.59 | 0 | 64252 | 523 | 1032.02
NHT-015176 - Reporting | 26-PC-40329 | Completed |  |  | 156886 | 106070.29 | 106070.29 | 28129.84 | 109761.54 | 0 | 137891.38 | 972 | 1809.35
NHT-015180 - Curation | 26-PC-40334 | Completed |  |  | 16385 | 11566.48 | 11566.48 | 956.15 | 12616.47 | 0 | 13572.62 | 109 | 261.5
NHT-015181 - Desktop Review | 26-PC-40334 | In progress |  |  | 26723 | 18863.52 | 18863.52 | 1498.71 | 19775.39 | 0 | 21274.1 | 225 | 359
NHT-015185 - Agency Consultation | 26-PC-40334 | In progress |  |  | 23415 | 16528.47 | 16528.47 | 946.9 | 12494.43 | 0 | 13441.33 | 170 | 257.75
NHT-015191 - Background Research | 26-PC-40334 | Completed |  |  | 9449 | 6670.17 | 6670.17 | 983.88 | 12982.39 | 0 | 13966.27 | 74 | 136.25
NHT-015196 - Prefield | 26-PC-40334 | In progress |  |  | 20928 | 14773.07 | 14773.07 | 798.22 | 10532.6 | 0 | 11330.82 | 153 | 220.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40334 | In progress |  |  | 0 | 0 | 0 | 0 | 1543.29 | 0 | 1543.29 | 0 | 28
NHT-015202 - Survey | 26-PC-40344 | Completed |  |  | 19200 | 14098.56 | 14098.56 | 3753.56 | 13927.04 | 0 | 17680.6 | 0 | 258
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40344 | Completed |  |  | 0 | 0 | 0 | 0 | 719.22 | 0 | 719.22 | 0 | 17
NHT-015208 - Reporting | 26-PC-40361 | Completed |  |  | 26042 | 17133.34 | 17133.34 | 1851.49 | 18141.6 | 0 | 19993.09 | 165 | 300.25
NHT-015209 - Fieldwork | 26-PC-40361 | In progress |  |  | 98834 | 65022.38 | 65022.38 | 2764.35 | 27086.18 | 0 | 29850.53 | 613 | 448.25
NHT-015210 - Final Report | 26-PC-40361 | Completed |  |  | 31424 | 20674.05 | 20674.05 | 2442.62 | 23933.7 | 0 | 26376.32 | 172 | 289
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40361 | In progress |  |  | 0 | 0 | 0 | 0 | 1345.56 | 0 | 1345.56 | 0 | 15.25
NHT-015216 - Prefield | 26-PC-40384 | In progress |  |  | 21161 | 10021.26 | 12795.33 | 898.96 | 9071.68 | 0 | 9970.64 | 250 | 217.5
NHT-015222 - Site Recordation | 26-PC-40384 | In progress |  |  | 31814 | 15066.4 | 19237.06 | 614.14 | 6197.5 | 0 | 6811.64 | 303 | 143.5
NHT-015227 - Data Recovery Excavation | 26-PC-40384 | In progress |  |  | 14111 | 6682.82 | 8532.74 | 712.99 | 7195.01 | 0 | 7908 | 147 | 173
NHT-015233 - Monitoring | 26-PC-40384 | In progress |  |  | 35814 | 16960.28 | 21655.2 | 505.63 | 5102.49 | 0 | 5608.12 | 286 | 118.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40384 | In progress |  |  | 0 | 0 | 0 | 0 | 395.13 | 0 | 395.13 | 0 | 10.25
NHT-015242 - Final Report | 26-PC-40422 | Completed |  |  | 2415 | 1411.97 | 1792.72 | 852.19 | 3636.39 | 0 | 4488.58 | 29 | 87
NHT-015243 - Lab Analysis | 26-PC-40422 | Completed |  |  | 3485 | 2037.57 | 2587.01 | 743.91 | 3174.33 | 0 | 3918.24 | 41 | 72.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40422 | Completed |  |  | 0 | 0 | 0 | 0 | 83.08 | 0 | 83.08 | 0 | 1.75
NHT-015253 - Background Research | 26-PC-40443 | In progress |  |  | 191535 | 135262.34 | 135262.34 | 1397.78 | 9567.81 | 0 | 10965.59 | 1655 | 142.5
NHT-015254 - Agency Consultation | 26-PC-40443 | In progress |  |  | 175003 | 123587.02 | 123587.02 | 3062.15 | 20960.39 | 0 | 24022.54 | 1698 | 330.25
NHT-015257 - Data Recovery Excavation | 26-PC-40443 | In progress |  |  | 57962 | 40932.54 | 40932.54 | 1350.91 | 9247.01 | 0 | 10597.92 | 542 | 181
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40443 | In progress |  |  | 0 | 0 | 0 | 0 | 531.76 | 0 | 531.76 | 0 | 6.5
NHT-015265 - Data Recovery Excavation | 26-PC-40464 | In progress |  |  | 2448 | 1792.55 | 1792.55 | 311.92 | 3660.21 | 0 | 3972.13 | 20 | 79.25
NHT-015271 - Desktop Review | 26-PC-40464 | Completed |  |  | 485 | 355.5 | 355.5 | 84.16 | 987.49 | 0 | 1071.65 | 4 | 21.5
NHT-015273 - Project Management | 26-PC-40464 | In progress |  |  | 4567 | 3344.95 | 3344.95 | 237.73 | 2789.54 | 0 | 3027.27 | 46 | 60.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40464 | In progress |  |  | 0 | 0 | 0 | 0 | 54.7 | 0 | 54.7 | 0 | 0.75
NHT-015283 - GIS & Mapping | 26-PC-40590 | Completed |  |  | 120524 | 97395.79 | 97395.79 | 2525.76 | 23958.85 | 0 | 26484.61 | 1124 | 438
NHT-015290 - Data Recovery Excavation | 26-PC-40590 | Completed |  |  | 113316 | 91570.28 | 91570.28 | 1764.44 | 16737.16 | 0 | 18501.6 | 952 | 344.25
NHT-015297 - Site Recordation | 26-PC-40590 | Completed |  |  | 175738 | 142014.16 | 142014.16 | 2281.77 | 21644.38 | 0 | 23926.15 | 1689 | 462.5
NHT-015301 - Lab Analysis | 26-PC-40590 | Completed |  |  | 276769 | 223656.68 | 223656.68 | 2163.11 | 20518.8 | 0 | 22681.91 | 2805 | 445
NHT-015304 - Monitoring | 26-PC-40590 | Completed |  |  | 315653 | 255079.29 | 255079.29 | 2915.47 | 27655.52 | 0 | 30570.99 | 2978 | 518.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40590 | Completed |  |  | 0 | 0 | 0 | 0 | 1776.79 | 0 | 1776.79 | 0 | 38.75
NHT-015313 - Project Management | 26-PC-40605 | Completed |  |  | 16108 | 11079.31 | 11079.31 | 1254.37 | 8248.42 | 0 | 9502.79 | 124 | 179.05
NHT-015315 - Fieldwork | 26-PC-40605 | Completed |  |  | 56184 | 38642.96 | 38642.96 | 4375.05 | 28769.27 | 0 | 33144.32 | 456 | 511.31
NHT-015322 - Lab Analysis | 26-PC-40605 | Completed |  |  | 20962 | 14417.63 | 14417.63 | 1632.32 | 10733.76 | 0 | 12366.08 | 189 | 218.63
NHT-015323 - Prefield | 26-PC-40605 | Completed |  |  | 11513 | 7918.57 | 7918.57 | 896.52 | 5895.28 | 0 | 6791.8 | 83 | 108.97
NHT-015327 - Survey | 26-PC-40605 | Completed |  |  | 33633 | 23133.05 | 23133.05 | 2619.06 | 17222.3 | 0 | 19841.36 | 201 | 361.93
NHT-015330 - Lab Analysis | 26-PC-40607 | On hold |  |  | 75100 | 36024 | 47821.37 | 0 | 0 | 0 | 0 | 738 | 0
NHT-015331 - Lab Analysis | 26-PC-40640 | Completed |  |  | 12900 | 7793.5 | 9127.87 | 1254.53 | 7642.81 | 0 | 8897.34 | 117 | 154.69
NHT-015334 - Site Recordation | 26-PC-40690 | In progress |  |  | 65447 | 44347.06 | 44347.06 | 1314.59 | 8481.99 | 0 | 9796.58 | 597 | 160.25
NHT-015339 - GIS & Mapping | 26-PC-40690 | In progress |  |  | 33444 | 22661.87 | 22661.87 | 2900.98 | 18717.78 | 0 | 21618.76 | 423 | 357.75
NHT-015346 - Final Report | 26-PC-40690 | In progress |  |  | 118290 | 80152.95 | 80152.95 | 2092.34 | 13500.21 | 0 | 15592.55 | 1488 | 246.75
NHT-015349 - Curation | 26-PC-40690 | In progress |  |  | 35319 | 23932.12 | 23932.12 | 2356.33 | 15203.53 | 0 | 17559.86 | 415 | 313.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40690 | In progress |  |  | 0 | 0 | 0 | 0 | 1070.45 | 0 | 1070.45 | 0 | 22.5
NHT-015359 - Fieldwork | 26-PC-40716 | Completed |  |  | 2479 | 1743.01 | 1743.01 | 331.3 | 1529.89 | 0 | 1861.19 | 27 | 29.5
NHT-015360 - Background Research | 26-PC-40716 | Completed |  |  | 491 | 345.32 | 345.32 | 65.63 | 303.1 | 0 | 368.73 | 5 | 7.06
NHT-015361 - Reporting | 26-PC-40716 | Completed |  |  | 1589 | 1117.44 | 1117.44 | 212.39 | 980.82 | 0 | 1193.21 | 18 | 18.51
NHT-015362 - Data Recovery Excavation | 26-PC-40716 | Completed |  |  | 2141 | 1505 | 1505 | 286.05 | 1320.99 | 0 | 1607.04 | 21 | 24.91
NHT-015363 - Lab Analysis | 26-PC-40729 | In progress |  |  | 46894 | 27113.25 | 29444.78 | 227.3 | 839.83 | 0 | 1067.13 | 0 | 17.25
NHT-015366 - Data Recovery Excavation | 26-PC-40729 | In progress |  |  | 45606 | 26368.84 | 28636.35 | 815.61 | 3013.53 | 0 | 3829.14 | 0 | 62
NHT-015371 - Final Report | 26-PC-40750 | In progress |  |  | 424755 | 210862.57 | 266671.78 | 2854.13 | 11665.16 | 0 | 14519.29 | 6047 | 280.75
NHT-015378 - Curation | 26-PC-40750 | In progress |  |  | 69845 | 34673.18 | 43850.16 | 457.47 | 1869.75 | 0 | 2327.22 | 1213 | 42
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40750 | In progress |  |  | 0 | 0 | 0 | 0 | 675.19 | 0 | 675.19 | 0 | 16.25
NHT-015386 - Desktop Review | 26-PC-40760 | Completed |  |  | 42954 | 25919.32 | 35412.37 | 560.22 | 4876.78 | 0 | 5437 | 0 | 99
NHT-015393 - Final Report | 26-PC-40760 | Completed |  |  | 34546 | 20846.12 | 28481.09 | 1295.25 | 11275.26 | 0 | 12570.51 | 0 | 229.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40760 | Completed |  |  | 0 | 0 | 0 | 0 | 183.34 | 0 | 183.34 | 0 | 3.75
NHT-015398 - Lab Analysis | 26-PC-40805 | Completed |  |  | 15100 | 11494.12 | 11494.12 | 2153.42 | 10897.62 | 0 | 13051.04 | 183 | 205.32
NHT-015405 - Curation | 26-PC-40860 | In progress |  |  | 40517 | 32437.82 | 32437.82 | 828.69 | 9088.99 | 0 | 9917.68 | 0 | 200
NHT-015412 - Reporting | 26-PC-40860 | In progress |  |  | 83155 | 66574.11 | 66574.11 | 640.44 | 7024.26 | 0 | 7664.7 | 0 | 160.75
NHT-015415 - Lab Analysis | 26-PC-40860 | In progress |  |  | 14889 | 11919.95 | 11919.95 | 265.47 | 2911.62 | 0 | 3177.09 | 0 | 71.75
NHT-015419 - Fieldwork | 26-PC-40860 | In progress |  |  | 24744 | 19809.74 | 19809.74 | 693.44 | 7605.51 | 0 | 8298.95 | 0 | 172.25
NHT-015424 - Data Recovery Excavation | 26-PC-40860 | In progress |  |  | 17995 | 14407.16 | 14407.16 | 294.71 | 3232.35 | 0 | 3527.06 | 0 | 66.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40860 | In progress |  |  | 0 | 0 | 0 | 0 | 618.85 | 0 | 618.85 | 0 | 15.25
NHT-015433 - Background Research | 26-PC-40902 | Completed |  |  | 11347 | 8594.01 | 8594.01 | 710.81 | 7651.69 | 0 | 8362.5 | 128 | 124.08
NHT-015439 - Desktop Review | 26-PC-40902 | Completed |  |  | 9311 | 7052.36 | 7052.36 | 583.3 | 6279.08 | 0 | 6862.38 | 111 | 117.54
NHT-015440 - Final Report | 26-PC-40902 | Completed |  |  | 14156 | 10721.59 | 10721.59 | 886.79 | 9545.99 | 0 | 10432.78 | 149 | 160.85
NHT-015443 - Curation | 26-PC-40902 | Completed |  |  | 7656 | 5798.35 | 5798.35 | 479.58 | 5162.57 | 0 | 5642.15 | 89 | 89.79
NHT-015445 - Fieldwork | 26-PC-40902 | Completed |  |  | 44230 | 33500.27 | 33500.27 | 2770.82 | 29827.02 | 0 | 32597.84 | 565 | 545.35
NHT-015452 - Desktop Review | 26-PC-40966 | Completed |  |  | 111763 | 72645.69 | 72645.69 | 1784.11 | 17017.49 | 0 | 18801.6 | 1323 | 383
NHT-015459 - Draft Report | 26-PC-40966 | Completed |  |  | 113337 | 73669.31 | 73669.31 | 1400.07 | 13354.43 | 0 | 14754.5 | 1063 | 297
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40966 | Completed |  |  | 0 | 0 | 0 | 0 | 1054.58 | 0 | 1054.58 | 0 | 23
NHT-015466 - Background Research | 26-PC-40983 | Completed |  |  | 7200 | 4906.72 | 6217.91 | 485.27 | 4333.42 | 0 | 4818.69 | 42 | 71.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-40983 | Completed |  |  | 0 | 0 | 0 | 0 | 33.98 | 0 | 33.98 | 0 | 0.5
NHT-015477 - GIS & Mapping | 26-PC-41005 | In progress |  |  | 650 | 422.07 | 422.07 | 0 | 0 | 0 | 0 | 7 | 0
NHT-015478 - Prefield | 26-PC-41005 | In progress |  |  | 47806 | 31021.14 | 31021.14 | 246.13 | 1420.7 | 0 | 1666.83 | 553 | 32.75
NHT-015483 - Draft Report | 26-PC-41005 | In progress |  |  | 11544 | 7490.79 | 7490.79 | 97.7 | 563.94 | 0 | 661.64 | 105 | 13
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41005 | In progress |  |  | 0 | 0 | 0 | 0 | 75.92 | 0 | 75.92 | 0 | 1.75
NHT-015493 - Lab Analysis | 26-PC-41046 | Completed |  |  | 20906 | 12241.86 | 16545.99 | 1720.88 | 18765.75 | 0 | 20486.63 | 311 | 378.11
NHT-015495 - Testing | 26-PC-41046 | Completed |  |  | 28881 | 16911.05 | 22856.83 | 2377.23 | 25923.24 | 0 | 28300.47 | 338 | 502.84
NHT-015497 - Final Report | 26-PC-41046 | Completed |  |  | 10413 | 6097.51 | 8241.34 | 857.15 | 9346.98 | 0 | 10204.13 | 123 | 178.07
NHT-015501 - Background Research | 26-PC-41048 | In progress |  |  | 458200 | 315149.96 | 315149.96 | 14631.76 | 71439.13 | 0 | 86070.89 | 3299 | 1366.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41048 | In progress |  |  | 0 | 0 | 0 | 0 | 2072.26 | 0 | 2072.26 | 0 | 48.25
NHT-015504 - Curation | 26-PC-41130 | Completed |  |  | 290300 | 219699.04 | 219699.04 | 14079.53 | 187056.65 | 0 | 201136.18 | 3721 | 3896.75
NHT-015505 - Curation | 26-PC-41176 | Completed |  |  | 23071 | 17201.69 | 17201.69 | 985.52 | 10882.36 | 0 | 11867.88 | 0 | 175.75
NHT-015512 - Project Management | 26-PC-41176 | Completed |  |  | 20725 | 15452.24 | 15452.24 | 756.37 | 8352.05 | 0 | 9108.42 | 0 | 152.5
NHT-015518 - Monitoring | 26-PC-41176 | Completed |  |  | 65604 | 48914.71 | 48914.71 | 728.52 | 8044.55 | 0 | 8773.07 | 0 | 148.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41176 | Completed |  |  | 0 | 0 | 0 | 0 | 377.58 | 0 | 377.58 | 0 | 5.75
NHT-015525 - Background Research | 26-PC-41202 | Completed |  |  | 41400 | 19877.52 | 27278.33 | 4383.76 | 25407.38 | 0 | 29791.14 | 392 | 483
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41202 | In progress |  |  | 0 | 0 | 0 | 0 | 441.69 | 0 | 441.69 | 0 | 7
NHT-015532 - Curation | 26-PC-41222 | In progress |  |  | 26000 | 18522.4 | 18522.4 | 356.92 | 2801.7 | 0 | 3158.62 | 433 | 65
NHT-015539 - Reporting | 26-PC-41229 | On hold |  |  | 86353 | 57951.12 | 57951.12 | 0 | 0 | 0 | 0 | 385 | 0
NHT-015542 - Curation | 26-PC-41229 | On hold |  |  | 20615 | 13834.87 | 13834.87 | 0 | 0 | 0 | 0 | 123 | 0
NHT-015546 - Prefield | 26-PC-41229 | On hold |  |  | 43310 | 29065.3 | 29065.3 | 0 | 0 | 0 | 0 | 204 | 0
NHT-015550 - GIS & Mapping | 26-PC-41229 | On hold |  |  | 63722 | 42764.11 | 42764.11 | 0 | 0 | 0 | 0 | 359 | 0
NHT-015554 - GIS & Mapping | 26-PC-41230 | In progress |  |  | 28100 | 21662.41 | 21662.41 | 702.94 | 3753.74 | 0 | 4456.68 | 435 | 80.25
NHT-015559 - Prefield | 26-PC-41230 | In progress |  |  | 18300 | 14107.35 | 14107.35 | 1284.91 | 6861.46 | 0 | 8146.37 | 249 | 145.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41230 | In progress |  |  | 0 | 0 | 0 | 0 | 58.41 | 0 | 58.41 | 0 | 1.25
NHT-015565 - Desktop Review | 26-PC-41302 | Completed |  |  | 7807 | 5021.18 | 5021.18 | 512.47 | 4716.84 | 0 | 5229.31 | 51 | 89.37
NHT-015567 - Background Research | 26-PC-41302 | Completed |  |  | 12493 | 8035.78 | 8035.78 | 820.15 | 7548.73 | 0 | 8368.88 | 96 | 168.38
NHT-015569 - Survey | 26-PC-41334 | Completed |  |  | 36971 | 21321.02 | 23814.98 | 1681.5 | 25589.05 | 0 | 27270.55 | 447 | 588
NHT-015572 - Data Recovery Excavation | 26-PC-41334 | In progress |  |  | 117029 | 67489.02 | 75383.34 | 2482.4 | 37777.27 | 0 | 40259.67 | 1112 | 860.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41334 | In progress |  |  | 0 | 0 | 0 | 0 | 730.41 | 0 | 730.41 | 0 | 16.75
NHT-015576 - Reporting | 26-PC-41386 | In progress |  |  | 302700 | 209680.29 | 209680.29 | 1200.49 | 6594.91 | 0 | 7795.4 | 3122 | 147.75
NHT-015581 - Final Report | 26-PC-41394 | Completed |  |  | 1561 | 1115.25 | 1115.25 | 197.99 | 796.94 | 0 | 994.93 | 0 | 13.1
NHT-015588 - Survey | 26-PC-41394 | Completed |  |  | 8141 | 5817.91 | 5817.91 | 1032.85 | 4157.39 | 0 | 5190.24 | 0 | 73.77
NHT-015595 - Site Recordation | 26-PC-41394 | Completed |  |  | 4329 | 3093.63 | 3093.63 | 549.22 | 2210.67 | 0 | 2759.89 | 0 | 36.7
NHT-015596 - Curation | 26-PC-41394 | Completed |  |  | 1669 | 1192.43 | 1192.43 | 211.7 | 852.1 | 0 | 1063.8 | 0 | 16.01
NHT-015602 - Reporting | 26-PC-41406 | In progress |  |  | 381600 | 187803.42 | 257192.06 | 20128.61 | 83605.33 | 0 | 103733.94 | 4207 | 1866
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41406 | In progress |  |  | 0 | 0 | 0 | 0 | 1102.55 | 0 | 1102.55 | 0 | 24.75
NHT-015610 - Fieldwork | 26-PC-41425 | Completed |  |  | 268700 | 183253.4 | 183253.4 | 10707.92 | 52486.36 | 0 | 63194.28 | 1669 | 852.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41425 | Completed |  |  | 0 | 0 | 0 | 0 | 543.34 | 0 | 543.34 | 0 | 8.25
NHT-015617 - Fieldwork | 26-PC-41446 | In progress |  |  | 206642 | 135371.4 | 135371.4 | 0 | 0 | 0 | 0 | 1995 | 0
NHT-015624 - GIS & Mapping | 26-PC-41446 | In progress |  |  | 56358 | 36919.9 | 36919.9 | 0 | 0 | 0 | 0 | 449 | 0
NHT-015626 - Testing | 26-PC-41453 | On hold |  |  | 20629 | 16361.04 | 16361.04 | 0 | 0 | 0 | 0 | 153 | 0
NHT-015629 - Prefield | 26-PC-41453 | On hold |  |  | 7471 | 5925.07 | 5925.07 | 0 | 0 | 0 | 0 | 53 | 0
NHT-015631 - Lab Analysis | 26-PC-41466 | Completed |  |  | 735215 | 543470.99 | 543470.99 | 19677.11 | 73980.82 | 0 | 93657.93 | 8067 | 1324.5
NHT-015637 - Curation | 26-PC-41466 | Completed |  |  | 122585 | 90614.77 | 90614.77 | 17125.03 | 64385.65 | 0 | 81510.68 | 1227 | 1146
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41466 | Completed |  |  | 0 | 0 | 0 | 0 | 3482.57 | 0 | 3482.57 | 0 | 59.25
NHT-015643 - Data Recovery Excavation | 26-PC-41575 | In progress |  |  | 96702 | 74286.74 | 74286.74 | 436.55 | 5584.5 | 0 | 6021.05 | 1459 | 129.5
NHT-015647 - Fieldwork | 26-PC-41575 | In progress |  |  | 34698 | 26654.74 | 26654.74 | 305.62 | 3909.54 | 0 | 4215.16 | 500 | 90.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41575 | In progress |  |  | 0 | 0 | 0 | 0 | 216.9 | 0 | 216.9 | 0 | 5
NHT-015654 - Curation | 26-PC-41578 | On hold |  |  | 52824 | 29177.88 | 37233.3 | 0 | 0 | 0 | 0 | 646 | 0
NHT-015661 - Draft Report | 26-PC-41578 | On hold |  |  | 124753 | 68909.09 | 87933.49 | 0 | 0 | 0 | 0 | 1687 | 0
NHT-015666 - Agency Consultation | 26-PC-41578 | On hold |  |  | 43739 | 24159.42 | 30829.35 | 0 | 0 | 0 | 0 | 451 | 0
NHT-015673 - Lab Analysis | 26-PC-41578 | On hold |  |  | 119584 | 66053.29 | 84289.28 | 0 | 0 | 0 | 0 | 1159 | 0
NHT-015674 - Curation | 26-PC-41623 | On hold |  |  | 14480 | 10130.43 | 10130.43 | 0 | 0 | 0 | 0 | 151 | 0
NHT-015677 - Agency Consultation | 26-PC-41623 | On hold |  |  | 17505 | 12246.74 | 12246.74 | 0 | 0 | 0 | 0 | 219 | 0
NHT-015680 - Testing | 26-PC-41623 | On hold |  |  | 50141 | 35078.5 | 35078.5 | 0 | 0 | 0 | 0 | 465 | 0
NHT-015681 - Prefield | 26-PC-41623 | On hold |  |  | 30974 | 21669.09 | 21669.09 | 0 | 0 | 0 | 0 | 320 | 0
NHT-015688 - Monitoring | 26-PC-41644 | Completed |  |  | 148933 | 116361.12 | 116361.12 | 2024.8 | 13205.54 | 0 | 15230.34 | 2520 | 250.5
NHT-015689 - Draft Report | 26-PC-41644 | Completed |  |  | 65714 | 51342.6 | 51342.6 | 2142.52 | 13973.22 | 0 | 16115.74 | 1054 | 275.75
NHT-015695 - GIS & Mapping | 26-PC-41644 | Completed |  |  | 50866 | 39741.3 | 39741.3 | 1324.17 | 8636.11 | 0 | 9960.28 | 828 | 132.5
NHT-015697 - Desktop Review | 26-PC-41644 | Completed |  |  | 65087 | 50852.76 | 50852.76 | 1097.05 | 7154.86 | 0 | 8251.91 | 916 | 145.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41644 | Completed |  |  | 0 | 0 | 0 | 0 | 2320.01 | 0 | 2320.01 | 0 | 32.75
NHT-015702 - Curation | 26-PC-41661 | In progress |  |  | 482 | 404.88 | 404.88 | 26.51 | 212.49 | 0 | 239 | 5 | 3.25
NHT-015703 - Testing | 26-PC-41661 | In progress |  |  | 333 | 279.3 | 279.3 | 18.09 | 144.99 | 0 | 163.08 | 3 | 2.75
NHT-015708 - Project Management | 26-PC-41661 | Completed |  |  | 2053 | 1722.34 | 1722.34 | 347.06 | 2781.84 | 0 | 3128.9 | 20 | 39
NHT-015709 - Draft Report | 26-PC-41661 | In progress |  |  | 1634 | 1371.41 | 1371.41 | 42.19 | 338.2 | 0 | 380.39 | 17 | 5.5
NHT-015712 - GIS & Mapping | 26-PC-41661 | Completed |  |  | 298 | 250.23 | 250.23 | 40.66 | 325.91 | 0 | 366.57 | 4 | 4.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41661 | In progress |  |  | 0 | 0 | 0 | 0 | 115.7 | 0 | 115.7 | 0 | 1.75
NHT-015717 - Survey | 26-PC-41663 | On hold |  |  | 221316 | 146290.05 | 146290.05 | 0 | 0 | 0 | 0 | 1939 | 0
NHT-015721 - Prefield | 26-PC-41663 | On hold |  |  | 73361 | 48491.62 | 48491.62 | 0 | 0 | 0 | 0 | 810 | 0
NHT-015724 - Testing | 26-PC-41663 | On hold |  |  | 216023 | 142791.03 | 142791.03 | 0 | 0 | 0 | 0 | 2478 | 0
NHT-015725 - Survey | 26-PC-41667 | In progress |  |  | 21341 | 13618.94 | 15974.93 | 2336.25 | 15996.99 | 0 | 18333.24 | 155 | 286
NHT-015727 - Desktop Review | 26-PC-41667 | In progress |  |  | 28257 | 18032.55 | 21152.07 | 1561.07 | 10689.14 | 0 | 12250.21 | 251 | 168.75
NHT-015728 - Curation | 26-PC-41667 | Completed |  |  | 6602 | 4213.26 | 4942.13 | 1725.69 | 11816.28 | 0 | 13541.97 | 43 | 206
NHT-015731 - Project Management | 26-PC-41667 | In progress |  |  | 5672 | 3619.84 | 4246.05 | 1369.89 | 9380.02 | 0 | 10749.91 | 44 | 150
NHT-015738 - Monitoring | 26-PC-41667 | In progress |  |  | 69928 | 44624.61 | 52344.36 | 3331.83 | 22814.07 | 0 | 26145.9 | 428 | 447.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41667 | In progress |  |  | 0 | 0 | 0 | 0 | 921.05 | 0 | 921.05 | 0 | 14.25
NHT-015745 - Monitoring | 26-PC-41671 | Completed |  |  | 87584 | 62403.16 | 62403.16 | 6408.8 | 74715.31 | 0 | 81124.11 | 1131 | 1266.69
NHT-015749 - Draft Report | 26-PC-41671 | Completed |  |  | 48823 | 34786.54 | 34786.54 | 3572.58 | 41649.92 | 0 | 45222.5 | 555 | 904.74
NHT-015755 - Fieldwork | 26-PC-41671 | Completed |  |  | 83620 | 59579.51 | 59579.51 | 6118.81 | 71334.55 | 0 | 77453.36 | 833 | 1395.68
NHT-015762 - GIS & Mapping | 26-PC-41671 | Completed |  |  | 36173 | 25773.29 | 25773.29 | 2646.92 | 30858.36 | 0 | 33505.28 | 426 | 624.83
NHT-015764 - Monitoring | 26-PC-41683 | In progress |  |  | 51114 | 34547.94 | 34547.94 | 64.08 | 478.98 | 0 | 543.06 | 732 | 12.25
NHT-015766 - Background Research | 26-PC-41683 | In progress |  |  | 198986 | 134494.65 | 134494.65 | 483.71 | 3615.57 | 0 | 4099.28 | 2989 | 69.75
NHT-015769 - Draft Report | 26-PC-41707 | Completed |  |  | 927 | 698.82 | 698.82 | 35.5 | 142 | 0 | 177.5 | 6 | 2.25
NHT-015770 - Curation | 26-PC-41707 | Completed |  |  | 2515 | 1895.95 | 1895.95 | 157.19 | 628.77 | 0 | 785.96 | 20 | 8.75
NHT-015777 - Testing | 26-PC-41707 | Completed |  |  | 18726 | 14119.83 | 14119.83 | 718.6 | 2874.4 | 0 | 3593 | 110 | 40
NHT-015781 - Agency Consultation | 26-PC-41707 | Completed |  |  | 4733 | 3568.39 | 3568.39 | 139.23 | 556.91 | 0 | 696.14 | 23 | 7.75
NHT-015783 - Background Research | 26-PC-41707 | Completed |  |  | 99 | 75.01 | 75.01 | 0 | 0 | 0 | 0 | 1 | 0
NHT-015784 - Monitoring | 26-PC-41721 | In progress |  |  | 29046 | 20033.13 | 20033.13 | 621.25 | 7084.96 | 0 | 7706.21 | 297 | 121
NHT-015790 - Final Report | 26-PC-41721 | In progress |  |  | 7583 | 5230 | 5230 | 352.81 | 4023.64 | 0 | 4376.45 | 77 | 50.5
NHT-015793 - Draft Report | 26-PC-41721 | In progress |  |  | 21982 | 15160.82 | 15160.82 | 560.26 | 6389.45 | 0 | 6949.71 | 205 | 88.5
NHT-015795 - Lab Analysis | 26-PC-41721 | In progress |  |  | 5320 | 3669.18 | 3669.18 | 193.34 | 2204.91 | 0 | 2398.25 | 52 | 30.5
NHT-015800 - Reporting | 26-PC-41721 | In progress |  |  | 3769 | 2599.56 | 2599.56 | 100.99 | 1151.7 | 0 | 1252.69 | 39 | 18.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41721 | In progress |  |  | 0 | 0 | 0 | 0 | 1065.39 | 0 | 1065.39 | 0 | 14.25
NHT-015810 - GIS & Mapping | 26-PC-41739 | In progress |  |  | 240100 | 163268 | 163268 | 2866.55 | 15630.18 | 0 | 18496.73 | 1802 | 251.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41739 | In progress |  |  | 0 | 0 | 0 | 0 | 362.15 | 0 | 362.15 | 0 | 6.75
NHT-015815 - GIS & Mapping | 26-PC-41750 | On hold |  |  | 84287 | 62533.66 | 67331.55 | 0 | 0 | 0 | 0 | 935 | 0
NHT-015818 - Final Report | 26-PC-41750 | On hold |  |  | 64929 | 48171.18 | 51867.1 | 0 | 0 | 0 | 0 | 663 | 0
NHT-015824 - Monitoring | 26-PC-41750 | On hold |  |  | 267581 | 198521.28 | 213752.79 | 0 | 0 | 0 | 0 | 2754 | 0
NHT-015827 - Reporting | 26-PC-41750 | On hold |  |  | 149837 | 111165.12 | 119694.24 | 0 | 0 | 0 | 0 | 1535 | 0
NHT-015831 - Data Recovery Excavation | 26-PC-41750 | On hold |  |  | 258566 | 191832.2 | 206550.48 | 0 | 0 | 0 | 0 | 2005 | 0
NHT-015836 - Site Recordation | 26-PC-41776 | Completed |  |  | 67586 | 45776.11 | 45776.11 | 595.37 | 3570.18 | 0 | 4165.55 | 725 | 71.5
NHT-015843 - Reporting | 26-PC-41776 | Completed |  |  | 120545 | 81645.18 | 81645.18 | 644.12 | 3862.47 | 0 | 4506.59 | 1264 | 79.25
NHT-015848 - Lab Analysis | 26-PC-41776 | Completed |  |  | 160620 | 108787.92 | 108787.92 | 862.78 | 5173.65 | 0 | 6036.43 | 1290 | 98.5
NHT-015851 - Curation | 26-PC-41776 | Completed |  |  | 109049 | 73858.73 | 73858.73 | 1439.32 | 8630.92 | 0 | 10070.24 | 871 | 163.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41776 | Completed |  |  | 0 | 0 | 0 | 0 | 700.26 | 0 | 700.26 | 0 | 13.75
NHT-015859 - Final Report | 26-PC-41803 | Completed |  |  | 277437 | 196036.9 | 196036.9 | 2858.97 | 15861.43 | 0 | 18720.4 | 4123 | 259.25
NHT-015862 - Curation | 26-PC-41803 | Completed |  |  | 204863 | 144756.55 | 144756.55 | 1887.24 | 10470.35 | 0 | 12357.59 | 3009 | 191.5
NHT-015863 - Draft Report | 26-PC-41803 | Completed |  |  | 72500 | 51228.23 | 51228.23 | 2419.19 | 13421.59 | 0 | 15840.78 | 786 | 228.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41803 | Completed |  |  | 0 | 0 | 0 | 0 | 534.2 | 0 | 534.2 | 0 | 11.25
NHT-015875 - Agency Consultation | 26-PC-41821 | In progress |  |  | 152400 | 98770.44 | 98770.44 | 4215.96 | 21487.13 | 0 | 25703.09 | 1738 | 387
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41821 | In progress |  |  | 0 | 0 | 0 | 0 | 161.69 | 0 | 161.69 | 0 | 2.25
NHT-015885 - Prefield | 26-PC-41863 | In progress |  |  | 54757 | 38110.56 | 38110.56 | 330.13 | 1600.2 | 0 | 1930.33 | 0 | 15.75
NHT-015887 - Survey | 26-PC-41863 | In progress |  |  | 267743 | 186349.44 | 186349.44 | 759.81 | 3683 | 0 | 4442.81 | 0 | 36.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41863 | In progress |  |  | 0 | 0 | 0 | 0 | 76.2 | 0 | 76.2 | 0 | 0.75
NHT-015893 - GIS & Mapping | 26-PC-41865 | In progress |  |  | 17868 | 12868.38 | 12868.38 | 0 | 0 | 0 | 0 | 329 | 0
NHT-015896 - Site Recordation | 26-PC-41865 | In progress |  |  | 16797 | 12096.89 | 12096.89 | 0 | 0 | 0 | 0 | 299 | 0
NHT-015897 - Survey | 26-PC-41865 | In progress |  |  | 32435 | 23360.15 | 23360.15 | 0 | 0 | 0 | 0 | 551 | 0
NHT-015902 - Survey | 26-PC-41884 | In progress |  |  | 1099300 | 550430.95 | 743556.08 | 12794.67 | 54935.66 | 0 | 67730.33 | 13210 | 1217.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41884 | In progress |  |  | 0 | 0 | 0 | 0 | 1805.93 | 0 | 1805.93 | 0 | 40.75
NHT-015910 - Background Research | 26-PC-41918 | In progress |  |  | 6540 | 4378.19 | 4378.19 | 21.62 | 97.67 | 0 | 119.29 | 68 | 2.25
NHT-015912 - Reporting | 26-PC-41918 | In progress |  |  | 8192 | 5483.69 | 5483.69 | 64.86 | 293.02 | 0 | 357.88 | 88 | 6.75
NHT-015914 - Project Management | 26-PC-41918 | In progress |  |  | 9063 | 6066.86 | 6066.86 | 163.36 | 737.97 | 0 | 901.33 | 109 | 17
NHT-015919 - Prefield | 26-PC-41918 | In progress |  |  | 54727 | 36633.95 | 36633.95 | 290.69 | 1313.15 | 0 | 1603.84 | 597 | 30.25
NHT-015925 - Monitoring | 26-PC-41918 | In progress |  |  | 42578 | 28501.65 | 28501.65 | 538.15 | 2430.95 | 0 | 2969.1 | 407 | 56
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41918 | In progress |  |  | 0 | 0 | 0 | 0 | 108.52 | 0 | 108.52 | 0 | 2.5
NHT-015935 - Lab Analysis | 26-PC-41947 | Completed |  |  | 17467 | 14124.17 | 14124.17 | 1107.36 | 8598.39 | 0 | 9705.75 | 257 | 196.75
NHT-015942 - Data Recovery Excavation | 26-PC-41947 | Completed |  |  | 10670 | 8627.75 | 8627.75 | 455.03 | 3533.23 | 0 | 3988.26 | 165 | 77.5
NHT-015945 - Survey | 26-PC-41947 | Completed |  |  | 1275 | 1031.24 | 1031.24 | 130.8 | 1015.67 | 0 | 1146.47 | 22 | 23.5
NHT-015950 - Reporting | 26-PC-41947 | Completed |  |  | 32070 | 25931.03 | 25931.03 | 1362.48 | 10579.34 | 0 | 11941.82 | 540 | 244
NHT-015952 - Desktop Review | 26-PC-41947 | Completed |  |  | 2918 | 2359.65 | 2359.65 | 371.39 | 2883.79 | 0 | 3255.18 | 47 | 65.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41947 | Completed |  |  | 0 | 0 | 0 | 0 | 24.41 | 0 | 24.41 | 0 | 0.5
NHT-015956 - Curation | 26-PC-41954 | Completed |  |  | 7399 | 5822.89 | 5822.89 | 633.56 | 6106.46 | 0 | 6740.02 | 67 | 128.93
NHT-015963 - Project Management | 26-PC-41954 | Completed |  |  | 12874 | 10131.67 | 10131.67 | 1102.38 | 10625.06 | 0 | 11727.44 | 102 | 205.18
NHT-015966 - Prefield | 26-PC-41954 | Completed |  |  | 4324 | 3402.67 | 3402.67 | 370.23 | 3568.37 | 0 | 3938.6 | 38 | 67.89
NHT-015971 - Data Recovery Excavation | 26-PC-41954 | Completed |  |  | 39732 | 31269.51 | 31269.51 | 3402.29 | 32792.29 | 0 | 36194.58 | 374 | 616.44
NHT-015975 - Survey | 26-PC-41954 | Completed |  |  | 34071 | 26814.06 | 26814.06 | 2917.52 | 28119.87 | 0 | 31037.39 | 378 | 489.65
NHT-015976 - Survey | 26-PC-41961 | In progress |  |  | 102271 | 81489.84 | 81489.84 | 4287.26 | 34636.61 | 0 | 38923.87 | 1078 | 575
NHT-015980 - Final Report | 26-PC-41961 | In progress |  |  | 179820 | 143280.6 | 143280.6 | 1719.56 | 13892.23 | 0 | 15611.79 | 1569 | 263.25
NHT-015986 - Lab Analysis | 26-PC-41961 | In progress |  |  | 181109 | 144307.32 | 144307.32 | 3095.28 | 25006.61 | 0 | 28101.89 | 1686 | 440.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41961 | In progress |  |  | 0 | 0 | 0 | 0 | 867.93 | 0 | 867.93 | 0 | 15.75
NHT-015993 - Testing | 26-PC-41970 | Completed |  |  | 36385 | 21448.48 | 26449.06 | 1630.46 | 11851.68 | 0 | 13482.14 | 614 | 274.25
NHT-015996 - Monitoring | 26-PC-41970 | Completed |  |  | 32126 | 18937.45 | 23352.6 | 1443.74 | 10494.42 | 0 | 11938.16 | 444 | 224.25
NHT-016001 - Background Research | 26-PC-41970 | Completed |  |  | 120220 | 70867.64 | 87390.01 | 1819.03 | 13222.4 | 0 | 15041.43 | 1660 | 294.75
NHT-016003 - GIS & Mapping | 26-PC-41970 | Completed |  |  | 103469 | 60993.47 | 75213.74 | 2277.99 | 16558.61 | 0 | 18836.6 | 1479 | 357.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-41970 | Completed |  |  | 0 | 0 | 0 | 0 | 964.01 | 0 | 964.01 | 0 | 21
NHT-016009 - Reporting | 26-PC-41987 | Completed |  |  | 88100 | 66383.35 | 66383.35 | 9524.38 | 39824.71 | 0 | 49349.09 | 735 | 701.02
NHT-016015 - GIS & Mapping | 26-PC-42007 | In progress |  |  | 151123 | 79573.6 | 95420.27 | 1293.62 | 6695.36 | 0 | 7988.98 | 1274 | 136.25
NHT-016021 - Site Recordation | 26-PC-42007 | In progress |  |  | 54990 | 28954.88 | 34721.09 | 1226.04 | 6345.58 | 0 | 7571.62 | 572 | 129.25
NHT-016022 - Survey | 26-PC-42007 | In progress |  |  | 69656 | 36677.43 | 43981.55 | 740.15 | 3830.79 | 0 | 4570.94 | 576 | 78
NHT-016023 - Agency Consultation | 26-PC-42007 | In progress |  |  | 65931 | 34716.09 | 41629.62 | 560.6 | 2901.51 | 0 | 3462.11 | 568 | 59.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42007 | In progress |  |  | 0 | 0 | 0 | 0 | 135.63 | 0 | 135.63 | 0 | 2.75
NHT-016030 - Lab Analysis | 26-PC-42008 | In progress |  |  | 18921 | 13057.46 | 13057.46 | 0 | 0 | 0 | 0 | 214 | 0
NHT-016036 - Draft Report | 26-PC-42008 | In progress |  |  | 17500 | 12076.95 | 12076.95 | 0 | 0 | 0 | 0 | 201 | 0
NHT-016039 - Fieldwork | 26-PC-42008 | In progress |  |  | 42979 | 29659.53 | 29659.53 | 0 | 0 | 0 | 0 | 618 | 0
NHT-016042 - Final Report | 26-PC-42023 | Completed |  |  | 20165 | 14361.41 | 14361.41 | 174.93 | 1370.64 | 0 | 1545.57 | 189 | 26.5
NHT-016044 - Agency Consultation | 26-PC-42023 | Completed |  |  | 90712 | 64605.28 | 64605.28 | 555.75 | 4354.57 | 0 | 4910.32 | 876 | 66.75
NHT-016045 - Site Recordation | 26-PC-42023 | Completed |  |  | 46123 | 32848.71 | 32848.71 | 647.01 | 5069.65 | 0 | 5716.66 | 457 | 87
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42023 | Completed |  |  | 0 | 0 | 0 | 0 | -295.92 | 0 | -295.92 | 0 | -6
NHT-016052 - Monitoring | 26-PC-42040 | In progress |  |  | 24047 | 16566.26 | 16566.26 | 218.77 | 1697.29 | 0 | 1916.06 | 153 | 30.75
NHT-016053 - GIS & Mapping | 26-PC-42040 | In progress |  |  | 8371 | 5766.94 | 5766.94 | 176.31 | 1367.91 | 0 | 1544.22 | 52 | 19
NHT-016058 - Prefield | 26-PC-42040 | In progress |  |  | 9616 | 6624.53 | 6624.53 | 122.06 | 947.03 | 0 | 1069.09 | 71 | 13.5
NHT-016061 - Desktop Review | 26-PC-42040 | In progress |  |  | 29109 | 20053.53 | 20053.53 | 210.56 | 1633.59 | 0 | 1844.15 | 243 | 21
NHT-016062 - Draft Report | 26-PC-42040 | In progress |  |  | 58557 | 40339.07 | 40339.07 | 298.62 | 2316.79 | 0 | 2615.41 | 343 | 32
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42040 | In progress |  |  | 0 | 0 | 0 | 0 | 602.87 | 0 | 602.87 | 0 | 7.75
NHT-016064 - GIS & Mapping | 26-PC-42099 | In progress |  |  | 661800 | 445656.12 | 445656.12 | 4872.76 | 67605.03 | 0 | 72477.79 | 0 | 1165
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42099 | In progress |  |  | 0 | 0 | 0 | 0 | 2487.67 | 0 | 2487.67 | 0 | 41
NHT-016074 - Curation | 26-PC-42105 | Completed |  |  | 49447 | 31968.81 | 35814.29 | 5946.77 | 37460.32 | 0 | 43407.09 | 408 | 750.35
NHT-016076 - Reporting | 26-PC-42105 | Completed |  |  | 136667 | 88358.32 | 98986.81 | 16436.23 | 103536.25 | 0 | 119972.48 | 976 | 1931.15
NHT-016080 - Survey | 26-PC-42105 | Completed |  |  | 232186 | 150113.78 | 168170.76 | 27923.85 | 175899.91 | 0 | 203823.76 | 1724 | 3184.86
NHT-016085 - Lab Analysis | 26-PC-42105 | Completed |  |  | 149750 | 96816.62 | 108462.55 | 18009.63 | 113447.5 | 0 | 131457.13 | 1226 | 1992
NHT-016091 - Prefield | 26-PC-42105 | Completed |  |  | 103850 | 67141.77 | 75218.15 | 12489.57 | 78675.18 | 0 | 91164.75 | 856 | 1496.43
NHT-016097 - Background Research | 26-PC-42108 | In progress |  |  | 190390 | 144848.48 | 144848.48 | 3878.46 | 14606.4 | 0 | 18484.86 | 2044 | 182.5
NHT-016104 - Survey | 26-PC-42108 | In progress |  |  | 219350 | 166881.8 | 166881.8 | 1787.32 | 6731.09 | 0 | 8518.41 | 2247 | 87.75
NHT-016110 - Draft Report | 26-PC-42108 | In progress |  |  | 590860 | 449526.2 | 449526.2 | 3478.7 | 13100.86 | 0 | 16579.56 | 6727 | 168.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42108 | In progress |  |  | 0 | 0 | 0 | 0 | 381 | 0 | 381 | 0 | 3.75
NHT-016123 - Lab Analysis | 26-PC-42222 | On hold |  |  | 3325 | 2351.46 | 2351.46 | 0 | 0 | 0 | 0 | 32 | 0
NHT-016126 - Project Management | 26-PC-42222 | On hold |  |  | 2338 | 1653.52 | 1653.52 | 0 | 0 | 0 | 0 | 22 | 0
NHT-016129 - Prefield | 26-PC-42222 | On hold |  |  | 2409 | 1703.7 | 1703.7 | 0 | 0 | 0 | 0 | 19 | 0
NHT-016132 - Monitoring | 26-PC-42222 | On hold |  |  | 10220 | 7226.56 | 7226.56 | 0 | 0 | 0 | 0 | 91 | 0
NHT-016137 - Fieldwork | 26-PC-42222 | On hold |  |  | 11708 | 8277.76 | 8277.76 | 0 | 0 | 0 | 0 | 106 | 0
NHT-016139 - Background Research | 26-PC-42293 | In progress |  |  | 54006 | 47525.34 | 47525.34 | 2372.86 | 8899.17 | 0 | 11272.03 | 717 | 208.5
NHT-016146 - Reporting | 26-PC-42293 | In progress |  |  | 46794 | 41178.66 | 41178.66 | 2102.44 | 7884.98 | 0 | 9987.42 | 527 | 178.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42293 | In progress |  |  | 0 | 0 | 0 | 0 | 465.3 | 0 | 465.3 | 0 | 11
NHT-016153 - Site Recordation | 26-PC-42406 | Completed |  |  | 32090 | 17579.86 | 22474.96 | 1458.75 | 17735.27 | 0 | 19194.02 | 390 | 354.17
NHT-016154 - Prefield | 26-PC-42406 | Completed |  |  | 15674 | 8586.45 | 10977.34 | 712.49 | 8662.35 | 0 | 9374.84 | 153 | 164.03
NHT-016158 - Project Management | 26-PC-42406 | Completed |  |  | 32116 | 17593.89 | 22492.91 | 1459.9 | 17749.43 | 0 | 19209.33 | 377 | 348.61
NHT-016159 - Desktop Review | 26-PC-42406 | Completed |  |  | 12720 | 6968.05 | 8908.31 | 578.2 | 7029.65 | 0 | 7607.85 | 159 | 135.08
NHT-016164 - Agency Consultation | 26-PC-42427 | In progress |  |  | 926100 | 644195.16 | 644195.16 | 25763.55 | 112266.02 | 0 | 138029.57 | 8174 | 2321.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42427 | In progress |  |  | 0 | 0 | 0 | 0 | 1989.73 | 0 | 1989.73 | 0 | 42.25
NHT-016171 - Curation | 26-PC-42428 | Completed |  |  | 474793 | 350587.35 | 350587.35 | 968.97 | 5983.32 | 0 | 6952.29 | 0 | 142.25
NHT-016175 - Monitoring | 26-PC-42428 | Completed |  |  | 69905 | 51617.52 | 51617.52 | 615.63 | 3801.52 | 0 | 4417.15 | 0 | 82.5
NHT-016181 - Desktop Review | 26-PC-42428 | Completed |  |  | 376502 | 278009.21 | 278009.21 | 785.47 | 4850.26 | 0 | 5635.73 | 0 | 112.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42428 | Completed |  |  | 0 | 0 | 0 | 0 | 169.25 | 0 | 169.25 | 0 | 4.5
NHT-016192 - Survey | 26-PC-42472 | In progress |  |  | 51039 | 37263.75 | 37263.75 | 208.45 | 656.7 | 0 | 865.15 | 893 | 15
NHT-016199 - Fieldwork | 26-PC-42472 | In progress |  |  | 66953 | 48881.78 | 48881.78 | 343.93 | 1083.56 | 0 | 1427.49 | 800 | 24.75
NHT-016200 - Site Recordation | 26-PC-42472 | In progress |  |  | 741 | 541.33 | 541.33 | 0 | 0 | 0 | 0 | 8 | 0
NHT-016205 - Final Report | 26-PC-42472 | In progress |  |  | 10096 | 7371.4 | 7371.4 | 91.82 | 289.27 | 0 | 381.09 | 130 | 7.25
NHT-016212 - Curation | 26-PC-42472 | In progress |  |  | 371 | 270.66 | 270.66 | 0 | 0 | 0 | 0 | 4 | 0
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42472 | In progress |  |  | 0 | 0 | 0 | 0 | 547.25 | 0 | 547.25 | 0 | 12.5
NHT-016216 - Lab Analysis | 26-PC-42492 | In progress |  |  | 4652 | 3067.24 | 3067.24 | 126.29 | 1127.41 | 0 | 1253.7 | 55 | 20
NHT-016223 - GIS & Mapping | 26-PC-42492 | In progress |  |  | 43066 | 28398.5 | 28398.5 | 601.19 | 5367.04 | 0 | 5968.23 | 428 | 102.25
NHT-016229 - Testing | 26-PC-42492 | In progress |  |  | 906 | 597.19 | 597.19 | 12.4 | 110.68 | 0 | 123.08 | 8 | 2.25
NHT-016233 - Project Management | 26-PC-42492 | In progress |  |  | 9749 | 6428.18 | 6428.18 | 150.8 | 1346.24 | 0 | 1497.04 | 104 | 30.75
NHT-016240 - Background Research | 26-PC-42492 | In progress |  |  | 1727 | 1138.83 | 1138.83 | 70.39 | 628.42 | 0 | 698.81 | 21 | 15.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42492 | In progress |  |  | 0 | 0 | 0 | 0 | 69.83 | 0 | 69.83 | 0 | 1.75
NHT-016246 - GIS & Mapping | 26-PC-42510 | In progress |  |  | 160359 | 116709.36 | 116709.36 | 3226.86 | 17177.57 | 0 | 20404.43 | 1770 | 415.75
NHT-016247 - Lab Analysis | 26-PC-42510 | In progress |  |  | 625188 | 455011.38 | 455011.38 | 4013.53 | 21365.21 | 0 | 25378.74 | 5437 | 518
NHT-016251 - Curation | 26-PC-42510 | In progress |  |  | 106801 | 77729.83 | 77729.83 | 1801.96 | 9592.39 | 0 | 11394.35 | 1105 | 228
NHT-016256 - Final Report | 26-PC-42510 | In progress |  |  | 88382 | 64324.5 | 64324.5 | 2447.93 | 13031.07 | 0 | 15479 | 944 | 320.5
NHT-016263 - Desktop Review | 26-PC-42510 | In progress |  |  | 323470 | 235421.69 | 235421.69 | 3435.01 | 18285.63 | 0 | 21720.64 | 3179 | 434
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42510 | In progress |  |  | 0 | 0 | 0 | 0 | 1915.02 | 0 | 1915.02 | 0 | 47
NHT-016273 - GIS & Mapping | 26-PC-42554 | In progress |  |  | 8774 | 6486.02 | 6486.02 | 289.74 | 2039.25 | 0 | 2328.99 | 0 | 18.5
NHT-016278 - Draft Report | 26-PC-42554 | In progress |  |  | 95689 | 70733.64 | 70733.64 | 254.67 | 1792.44 | 0 | 2047.11 | 0 | 41.75
NHT-016279 - Lab Analysis | 26-PC-42554 | In progress |  |  | 5220 | 3858.3 | 3858.3 | 49.6 | 349.13 | 0 | 398.73 | 0 | 8.75
NHT-016281 - Agency Consultation | 26-PC-42554 | In progress |  |  | 29217 | 21596.92 | 21596.92 | 278.57 | 1960.65 | 0 | 2239.22 | 0 | 45
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42554 | In progress |  |  | 0 | 0 | 0 | 0 | 197.37 | 0 | 197.37 | 0 | 3
NHT-016284 - Survey | 26-PC-42585 | Completed |  |  | 12267 | 8561.07 | 8561.07 | 813.13 | 5346.96 | 0 | 6160.09 | 129 | 101.97
NHT-016289 - Data Recovery Excavation | 26-PC-42585 | Completed |  |  | 17133 | 11957.19 | 11957.19 | 1135.7 | 7468.05 | 0 | 8603.75 | 162 | 161.44
NHT-016292 - Background Research | 26-PC-42598 | In progress |  |  | 30947 | 17376.5 | 23198.07 | 1009.73 | 7459.23 | 0 | 8468.96 | 276 | 105.25
NHT-016299 - Monitoring | 26-PC-42598 | In progress |  |  | 35917 | 20166.67 | 26923.03 | 647.64 | 4784.36 | 0 | 5432 | 276 | 68.75
NHT-016306 - Lab Analysis | 26-PC-42598 | In progress |  |  | 26611 | 14941.45 | 19947.21 | 1618.98 | 11959.97 | 0 | 13578.95 | 212 | 146.75
NHT-016312 - Prefield | 26-PC-42598 | In progress |  |  | 5925 | 3326.92 | 4441.52 | 440.82 | 3256.51 | 0 | 3697.33 | 42 | 43.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42598 | In progress |  |  | 0 | 0 | 0 | 0 | 593.44 | 0 | 593.44 | 0 | 8.75
NHT-016321 - Site Recordation | 26-PC-42616 | Completed |  |  | 4242 | 3485.07 | 3485.07 | 503.59 | 1941.02 | 0 | 2444.61 | 57 | 40.51
NHT-016326 - Prefield | 26-PC-42616 | Completed |  |  | 2541 | 2087.26 | 2087.26 | 301.61 | 1162.51 | 0 | 1464.12 | 30 | 21.71
NHT-016330 - Desktop Review | 26-PC-42616 | Completed |  |  | 2158 | 1772.71 | 1772.71 | 256.16 | 987.32 | 0 | 1243.48 | 23 | 17.32
NHT-016333 - Background Research | 26-PC-42616 | Completed |  |  | 1584 | 1300.95 | 1300.95 | 187.99 | 724.57 | 0 | 912.56 | 21 | 14.66
NHT-016336 - Draft Report | 26-PC-42616 | Completed |  |  | 4075 | 3347.91 | 3347.91 | 483.77 | 1864.64 | 0 | 2348.41 | 45 | 40.91
NHT-016337 - Site Recordation | 26-PC-42648 | Completed |  |  | 90891 | 57552.34 | 57552.34 | 5288.61 | 38060.68 | 0 | 43349.29 | 1352 | 781.03
NHT-016343 - Project Management | 26-PC-42648 | Completed |  |  | 57236 | 36241.57 | 36241.57 | 3330.32 | 23967.38 | 0 | 27297.7 | 762 | 472.8
NHT-016350 - Reporting | 26-PC-42648 | Completed |  |  | 107419 | 68017.94 | 68017.94 | 6250.33 | 44981.82 | 0 | 51232.15 | 1227 | 957.99
NHT-016352 - Prefield | 26-PC-42648 | Completed |  |  | 42606 | 26977.82 | 26977.82 | 2479.05 | 17841.05 | 0 | 20320.1 | 510 | 349.53
NHT-016354 - Background Research | 26-PC-42648 | Completed |  |  | 32148 | 20356.29 | 20356.29 | 1870.58 | 13462.08 | 0 | 15332.66 | 340 | 255.06
NHT-016357 - Survey | 26-PC-42664 | In progress |  |  | 36443 | 21230.25 | 23650.73 | 161.91 | 690.23 | 0 | 852.14 | 0 | 12.75
NHT-016358 - Lab Analysis | 26-PC-42664 | In progress |  |  | 7902 | 4603.6 | 5128.46 | 199.64 | 851.14 | 0 | 1050.78 | 0 | 10.75
NHT-016362 - GIS & Mapping | 26-PC-42664 | In progress |  |  | 356 | 207.24 | 230.87 | 0 | 0 | 0 | 0 | 0 | 0
NHT-016365 - Curation | 26-PC-42664 | In progress |  |  | 5722 | 3333.71 | 3713.79 | 32.76 | 139.65 | 0 | 172.41 | 0 | 3.5
NHT-016369 - Prefield | 26-PC-42664 | In progress |  |  | 277 | 161.19 | 179.56 | 0 | 0 | 0 | 0 | 0 | 0
NHT-016372 - Lab Analysis | 26-PC-42679 | Completed |  |  | 214600 | 144103.9 | 144103.9 | 13012.88 | 54215.18 | 0 | 67228.06 | 1148 | 737.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42679 | Completed |  |  | 0 | 0 | 0 | 0 | 1989.36 | 0 | 1989.36 | 0 | 27.75
NHT-016380 - Fieldwork | 26-PC-42692 | In progress |  |  | 100348 | 68086.05 | 68086.05 | 3926.28 | 14445.07 | 0 | 18371.35 | 513 | 208.25
NHT-016387 - Agency Consultation | 26-PC-42692 | In progress |  |  | 200152 | 135803.2 | 135803.2 | 1723.98 | 6342.66 | 0 | 8066.64 | 1058 | 86
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42692 | In progress |  |  | 0 | 0 | 0 | 0 | 468 | 0 | 468 | 0 | 4
NHT-016394 - GIS & Mapping | 26-PC-42734 | In progress |  |  | 5294 | 3525.94 | 3525.94 | 478.73 | 3268.22 | 0 | 3746.95 | 48 | 64.25
NHT-016399 - Reporting | 26-PC-42734 | In progress |  |  | 16670 | 11102.12 | 11102.12 | 562.05 | 3837 | 0 | 4399.05 | 160 | 81.5
NHT-016406 - Curation | 26-PC-42734 | In progress |  |  | 21635 | 14408.83 | 14408.83 | 506.02 | 3454.51 | 0 | 3960.53 | 194 | 77.25
NHT-016413 - Project Management | 26-PC-42734 | In progress |  |  | 33901 | 22578.11 | 22578.11 | 1697.06 | 11585.62 | 0 | 13282.68 | 302 | 237.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42734 | In progress |  |  | 0 | 0 | 0 | 0 | 561.7 | 0 | 561.7 | 0 | 7.75
NHT-016422 - GIS & Mapping | 26-PC-42757 | In progress |  |  | 149596 | 110521.97 | 110521.97 | 5130.33 | 34646.91 | 0 | 39777.24 | 1548 | 571.75
NHT-016426 - Draft Report | 26-PC-42757 | Completed |  |  | 86023 | 63553.59 | 63553.59 | 8403.45 | 56751.42 | 0 | 65154.87 | 919 | 1054.5
NHT-016429 - Data Recovery Excavation | 26-PC-42757 | In progress |  |  | 111381 | 82288.04 | 82288.04 | 9968.76 | 67322.54 | 0 | 77291.3 | 1248 | 1048.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42757 | In progress |  |  | 0 | 0 | 0 | 0 | 4304.67 | 0 | 4304.67 | 0 | 65.75
NHT-016437 - Background Research | 26-PC-42759 | Completed |  |  | 740600 | 515013.24 | 515013.24 | 56771.71 | 432639.6 | 0 | 489411.31 | 7530 | 7634.55
NHT-016440 - Reporting | 26-PC-42788 | Completed |  |  | 290805 | 190942.81 | 190942.81 | 29553.09 | 199540.64 | 0 | 229093.73 | 3776 | 3280.85
NHT-016445 - Data Recovery Excavation | 26-PC-42788 | Completed |  |  | 485252 | 318616.39 | 318616.39 | 49313.72 | 332963.16 | 0 | 382276.88 | 7135 | 5389.63
NHT-016447 - Fieldwork | 26-PC-42788 | Completed |  |  | 568177 | 373064.78 | 373064.78 | 57740.95 | 389863.29 | 0 | 447604.24 | 5931 | 6939.28
NHT-016453 - Background Research | 26-PC-42788 | Completed |  |  | 116803 | 76692.96 | 76692.96 | 11870.12 | 80146.31 | 0 | 92016.43 | 1517 | 1383.36
NHT-016457 - Prefield | 26-PC-42788 | Completed |  |  | 134863 | 88551 | 88551 | 13705.44 | 92538.3 | 0 | 106243.74 | 1947 | 1399.13
NHT-016461 - Site Recordation | 26-PC-42811 | Completed |  |  | 1252 | 787.83 | 787.83 | 210 | 748.9 | 0 | 958.9 | 7 | 14.56
NHT-016468 - Desktop Review | 26-PC-42811 | Completed |  |  | 838 | 527.14 | 527.14 | 140.51 | 501.09 | 0 | 641.6 | 5 | 7.97
NHT-016475 - Testing | 26-PC-42811 | Completed |  |  | 2399 | 1509.79 | 1509.79 | 402.44 | 1435.19 | 0 | 1837.63 | 14 | 21.6
NHT-016481 - Data Recovery Excavation | 26-PC-42811 | Completed |  |  | 3511 | 2209.64 | 2209.64 | 588.99 | 2100.46 | 0 | 2689.45 | 24 | 32.2
NHT-016487 - Testing | 26-PC-42832 | Completed |  |  | 5612 | 3970.26 | 3970.26 | 79.4 | 662.13 | 0 | 741.53 | 72 | 14.75
NHT-016488 - Survey | 26-PC-42832 | Completed |  |  | 53745 | 38024.93 | 38024.93 | 571.33 | 4764.66 | 0 | 5335.99 | 838 | 104.5
NHT-016492 - Fieldwork | 26-PC-42832 | Completed |  |  | 216542 | 153203.3 | 153203.3 | 915.8 | 7637.48 | 0 | 8553.28 | 3296 | 176
NHT-016497 - Draft Report | 26-PC-42832 | Completed |  |  | 28957 | 20486.91 | 20486.91 | 656.93 | 5478.49 | 0 | 6135.42 | 328 | 122.25
NHT-016501 - GIS & Mapping | 26-PC-42832 | Completed |  |  | 38744 | 27411.6 | 27411.6 | 274.28 | 2287.37 | 0 | 2561.65 | 460 | 53
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42832 | Completed |  |  | 0 | 0 | 0 | 0 | 235.67 | 0 | 235.67 | 0 | 5.25
NHT-016505 - Fieldwork | 26-PC-42838 | In progress |  |  | 12734 | 8549.51 | 8549.51 | 240.56 | 2179.21 | 0 | 2419.77 | 139 | 43.25
NHT-016510 - Project Management | 26-PC-42838 | In progress |  |  | 10904 | 7320.7 | 7320.7 | 433.15 | 3923.91 | 0 | 4357.06 | 165 | 65
NHT-016511 - Background Research | 26-PC-42838 | In progress |  |  | 19393 | 13020.52 | 13020.52 | 384.78 | 3485.65 | 0 | 3870.43 | 240 | 68.75
NHT-016516 - Final Report | 26-PC-42838 | In progress |  |  | 4369 | 2933.63 | 2933.63 | 248.62 | 2252.18 | 0 | 2500.8 | 52 | 39.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42838 | In progress |  |  | 0 | 0 | 0 | 0 | 189.77 | 0 | 189.77 | 0 | 4.5
NHT-016519 - Draft Report | 26-PC-42859 | On hold |  |  | 34400 | 26797.6 | 26797.6 | 0 | 0 | 0 | 0 | 267 | 0
NHT-016522 - Lab Analysis | 26-PC-42880 | In progress |  |  | 107200 | 87904 | 87904 | 905.98 | 9049.89 | 0 | 9955.87 | 1117 | 214
NHT-016525 - Background Research | 26-PC-42898 | Completed |  |  | 128946 | 61173.99 | 82216.45 | 10430.24 | 61502.47 | 0 | 71932.71 | 821 | 1031.89
NHT-016526 - Desktop Review | 26-PC-42898 | Completed |  |  | 48192 | 22863.21 | 30727.64 | 3898.21 | 22985.98 | 0 | 26884.19 | 349 | 408.73
NHT-016532 - Lab Analysis | 26-PC-42898 | Completed |  |  | 210962 | 100083.3 | 134509.68 | 17064.33 | 100620.7 | 0 | 117685.03 | 1314 | 1473.92
NHT-016535 - Agency Consultation | 26-PC-42926 | In progress |  |  | 10336 | 8020.97 | 8020.97 | 54.56 | 284.34 | 0 | 338.9 | 125 | 6
NHT-016539 - Curation | 26-PC-42926 | In progress |  |  | 29977 | 23262.3 | 23262.3 | 114.74 | 597.92 | 0 | 712.66 | 444 | 16
NHT-016545 - Lab Analysis | 26-PC-42926 | In progress |  |  | 2311 | 1793.1 | 1793.1 | 0 | 0 | 0 | 0 | 27 | 0
NHT-016546 - GIS & Mapping | 26-PC-42926 | In progress |  |  | 21861 | 16964.22 | 16964.22 | 195.41 | 1018.33 | 0 | 1213.74 | 227 | 27.25
NHT-016551 - Background Research | 26-PC-42926 | In progress |  |  | 23315 | 18092.21 | 18092.21 | 215.14 | 1121.1 | 0 | 1336.24 | 293 | 30
NHT-016552 - Draft Report | 26-PC-42940 | Completed |  |  | 5497 | 3719.42 | 3719.42 | 881.37 | 3908.67 | 0 | 4790.04 | 38 | 72.07
NHT-016553 - GIS & Mapping | 26-PC-42940 | Completed |  |  | 2427 | 1641.96 | 1641.96 | 389.08 | 1725.5 | 0 | 2114.58 | 21 | 29.62
NHT-016556 - Testing | 26-PC-42940 | Completed |  |  | 6917 | 4679.74 | 4679.74 | 1108.92 | 4917.84 | 0 | 6026.76 | 72 | 80.55
NHT-016559 - Prefield | 26-PC-42940 | Completed |  |  | 2759 | 1867.04 | 1867.04 | 442.42 | 1962.03 | 0 | 2404.45 | 26 | 38.14
NHT-016563 - Final Report | 26-PC-42951 | Completed |  |  | 27013 | 14685.72 | 18924.5 | 2170.85 | 18117.49 | 0 | 20288.34 | 301 | 308.98
NHT-016568 - Data Recovery Excavation | 26-PC-42951 | Completed |  |  | 113782 | 61859.59 | 79714.29 | 9144.12 | 76314.96 | 0 | 85459.08 | 1034 | 1362.83
NHT-016575 - Draft Report | 26-PC-42951 | Completed |  |  | 68505 | 37243.49 | 47993.18 | 5505.36 | 45946.56 | 0 | 51451.92 | 550 | 770.93
NHT-016576 - Agency Consultation | 26-PC-42962 | In progress |  |  | 52032 | 35178.89 | 35178.89 | 186.73 | 1608.75 | 0 | 1795.48 | 0 | 13.75
NHT-016582 - Monitoring | 26-PC-42962 | In progress |  |  | 83854 | 56693.56 | 56693.56 | 139.34 | 1200.45 | 0 | 1339.79 | 0 | 26.5
NHT-016583 - Survey | 26-PC-42962 | In progress |  |  | 12371 | 8363.83 | 8363.83 | 0 | 0 | 0 | 0 | 0 | 0
NHT-016589 - Final Report | 26-PC-42962 | In progress |  |  | 893443 | 604057.09 | 604057.09 | 502.32 | 4327.73 | 0 | 4830.05 | 0 | 74.25
NHT-016594 - Prefield | 26-PC-42989 | In progress |  |  | 17526 | 8743.25 | 11130.38 | 99.81 | 401.73 | 0 | 501.54 | 0 | 10.75
NHT-016601 - Reporting | 26-PC-42989 | In progress |  |  | 6474 | 3229.57 | 4111.33 | 81.24 | 326.99 | 0 | 408.23 | 0 | 8.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-42989 | In progress |  |  | 0 | 0 | 0 | 0 | 18.68 | 0 | 18.68 | 0 | 0.5
NHT-016609 - Curation | 26-PC-43000 | Completed |  |  | 150700 | 99296.23 | 99296.23 | 14649.18 | 86379.63 | 0 | 101028.81 | 1048 | 1763.22
NHT-016616 - Final Report | 26-PC-43026 | On hold |  |  | 6553 | 4177.22 | 4177.22 | 0 | 0 | 0 | 0 | 36 | 0
NHT-016618 - Monitoring | 26-PC-43026 | On hold |  |  | 30301 | 19317.59 | 19317.59 | 0 | 0 | 0 | 0 | 241 | 0
NHT-016620 - Curation | 26-PC-43026 | On hold |  |  | 4722 | 3010.08 | 3010.08 | 0 | 0 | 0 | 0 | 31 | 0
NHT-016622 - Lab Analysis | 26-PC-43026 | On hold |  |  | 8987 | 5728.92 | 5728.92 | 0 | 0 | 0 | 0 | 55 | 0
NHT-016629 - Draft Report | 26-PC-43026 | On hold |  |  | 16137 | 10287.44 | 10287.44 | 0 | 0 | 0 | 0 | 106 | 0
NHT-016635 - Project Management | 26-PC-43039 | Completed |  |  | 107600 | 68885.46 | 77827.43 | 6860.6 | 82118.48 | 0 | 88979.08 | 0 | 1360.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43039 | Completed |  |  | 0 | 0 | 0 | 0 | 119.67 | 0 | 119.67 | 0 | 3
NHT-016641 - Lab Analysis | 26-PC-43059 | Completed |  |  | 11374 | 7099.73 | 7099.73 | 690.12 | 8157.63 | 0 | 8847.75 | 117 | 146.61
NHT-016644 - Project Management | 26-PC-43059 | Completed |  |  | 7619 | 4755.73 | 4755.73 | 462.28 | 5464.36 | 0 | 5926.64 | 86 | 97.63
NHT-016647 - Prefield | 26-PC-43059 | Completed |  |  | 7371 | 4600.68 | 4600.68 | 447.21 | 5286.21 | 0 | 5733.42 | 84 | 88.56
NHT-016654 - Testing | 26-PC-43059 | Completed |  |  | 17736 | 11071.08 | 11071.08 | 1076.15 | 12720.71 | 0 | 13796.86 | 231 | 226.64
NHT-016660 - Desktop Review | 26-PC-43086 | In progress |  |  | 237199 | 160251.68 | 160251.68 | 0 | 0 | 0 | 0 | 1375 | 0
NHT-016661 - Fieldwork | 26-PC-43086 | In progress |  |  | 1055554 | 713132.02 | 713132.02 | 0 | 0 | 0 | 0 | 7924 | 0
NHT-016665 - Draft Report | 26-PC-43086 | In progress |  |  | 589927 | 398554.85 | 398554.85 | 0 | 0 | 0 | 0 | 3812 | 0
NHT-016670 - Curation | 26-PC-43086 | In progress |  |  | 236120 | 159522.73 | 159522.73 | 0 | 0 | 0 | 0 | 1384 | 0
NHT-016677 - Survey | 26-PC-43132 | Completed |  |  | 58886 | 47190.89 | 47190.89 | 1169.97 | 9657.13 | 0 | 10827.1 | 631 | 188.5
NHT-016680 - GIS & Mapping | 26-PC-43132 | Completed |  |  | 29445 | 23597.35 | 23597.35 | 651 | 5373.46 | 0 | 6024.46 | 388 | 94.75
NHT-016686 - Draft Report | 26-PC-43132 | Completed |  |  | 22153 | 17753.33 | 17753.33 | 988.41 | 8158.5 | 0 | 9146.91 | 199 | 174.25
NHT-016689 - Fieldwork | 26-PC-43132 | Completed |  |  | 8208 | 6577.82 | 6577.82 | 847.3 | 6993.78 | 0 | 7841.08 | 79 | 124
NHT-016692 - Monitoring | 26-PC-43132 | Completed |  |  | 22008 | 17637.59 | 17637.59 | 376.16 | 3104.89 | 0 | 3481.05 | 233 | 68.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43132 | Completed |  |  | 0 | 0 | 0 | 0 | 369.5 | 0 | 369.5 | 0 | 5.75
NHT-016706 - GIS & Mapping | 26-PC-43136 | In progress |  |  | 720819 | 482444.33 | 482444.33 | 9616.26 | 42398.34 | 0 | 52014.6 | 6767 | 674.75
NHT-016710 - Desktop Review | 26-PC-43136 | In progress |  |  | 3110981 | 2082179.41 | 2082179.41 | 12150.19 | 53570.5 | 0 | 65720.69 | 25658 | 807.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43136 | In progress |  |  | 0 | 0 | 0 | 0 | 2521.33 | 0 | 2521.33 | 0 | 44.25
NHT-016722 - Project Management | 26-PC-43168 | Completed |  |  | 281200 | 145548.52 | 164749.65 | 5612.96 | 42574.84 | 0 | 48187.8 | 2975 | 835.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43168 | Completed |  |  | 0 | 0 | 0 | 0 | 1048.69 | 0 | 1048.69 | 0 | 24.25
NHT-016730 - Fieldwork | 26-PC-43191 | Completed |  |  | 47200 | 27988.2 | 37639.5 | 3728.6 | 35519.77 | 0 | 39248.37 | 613 | 539.83
NHT-016737 - Testing | 26-PC-43199 | Completed |  |  | 42200 | 26341.24 | 26341.24 | 4715.28 | 19590.28 | 0 | 24305.56 | 249 | 336.58
NHT-016739 - Lab Analysis | 26-PC-43222 | On hold |  |  | 2268 | 1451.78 | 1451.78 | 0 | 0 | 0 | 0 | 22 | 0
NHT-016740 - Draft Report | 26-PC-43222 | On hold |  |  | 3212 | 2055.6 | 2055.6 | 0 | 0 | 0 | 0 | 28 | 0
NHT-016747 - Data Recovery Excavation | 26-PC-43222 | On hold |  |  | 6903 | 4418.05 | 4418.05 | 0 | 0 | 0 | 0 | 67 | 0
NHT-016750 - Prefield | 26-PC-43222 | On hold |  |  | 980 | 627.17 | 627.17 | 0 | 0 | 0 | 0 | 7 | 0
NHT-016753 - GIS & Mapping | 26-PC-43222 | On hold |  |  | 1737 | 1111.4 | 1111.4 | 0 | 0 | 0 | 0 | 14 | 0
NHT-016758 - Site Recordation | 26-PC-43266 | In progress |  |  | 363 | 225.67 | 225.67 | 0 | 0 | 0 | 0 | 3 | 0
NHT-016760 - Reporting | 26-PC-43266 | In progress |  |  | 545 | 338.51 | 338.51 | 0 | 0 | 0 | 0 | 5 | 0
NHT-016766 - Project Management | 26-PC-43266 | In progress |  |  | 20392 | 12663.12 | 12663.12 | 29.1 | 258.99 | 0 | 288.09 | 184 | 5.75
NHT-016769 - Lab Analysis | 26-PC-43307 | In progress |  |  | 186974 | 147840.58 | 147840.58 | 6192.05 | 26907.16 | 0 | 33099.21 | 3013 | 553.5
NHT-016772 - Prefield | 26-PC-43307 | In progress |  |  | 52626 | 41611.14 | 41611.14 | 3527.73 | 15329.56 | 0 | 18857.29 | 940 | 326
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43307 | In progress |  |  | 0 | 0 | 0 | 0 | 582.84 | 0 | 582.84 | 0 | 12
NHT-016781 - Draft Report | 26-PC-43329 | In progress |  |  | 16907 | 11255.24 | 11255.24 | 557.19 | 3365.97 | 0 | 3923.16 | 118 | 54.5
NHT-016787 - Survey | 26-PC-43329 | In progress |  |  | 14694 | 9781.74 | 9781.74 | 1000.49 | 6043.94 | 0 | 7044.43 | 162 | 88.5
NHT-016794 - Monitoring | 26-PC-43329 | Completed |  |  | 1532 | 1019.55 | 1019.55 | 150.68 | 910.23 | 0 | 1060.91 | 20 | 8.75
NHT-016795 - Curation | 26-PC-43329 | In progress |  |  | 8067 | 5370.31 | 5370.31 | 1134.37 | 6852.74 | 0 | 7987.11 | 99 | 107.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43329 | In progress |  |  | 0 | 0 | 0 | 0 | 583.85 | 0 | 583.85 | 0 | 7.5
NHT-016803 - Agency Consultation | 26-PC-43338 | In progress |  |  | 57899 | 37582.56 | 37582.56 | 0 | 0 | 0 | 0 | 528 | 0
NHT-016805 - Curation | 26-PC-43338 | In progress |  |  | 64001 | 41542.73 | 41542.73 | 0 | 0 | 0 | 0 | 630 | 0
NHT-016806 - Project Management | 26-PC-43341 | Completed |  |  | 12103 | 9734.29 | 9734.29 | 1164.97 | 6499.31 | 0 | 7664.28 | 112 | 95.91
NHT-016810 - Site Recordation | 26-PC-43341 | Completed |  |  | 28559 | 22970.4 | 22970.4 | 2749.03 | 15336.68 | 0 | 18085.71 | 254 | 252.17
NHT-016814 - GIS & Mapping | 26-PC-43341 | Completed |  |  | 11267 | 9062.11 | 9062.11 | 1084.52 | 6050.51 | 0 | 7135.03 | 88 | 105.91
NHT-016820 - Draft Report | 26-PC-43341 | Completed |  |  | 29677 | 23868.99 | 23868.99 | 2856.57 | 15936.64 | 0 | 18793.21 | 334 | 253.97
NHT-016823 - Agency Consultation | 26-PC-43341 | Completed |  |  | 5894 | 4740.46 | 4740.46 | 567.32 | 3165.07 | 0 | 3732.39 | 42 | 45.89
NHT-016830 - Desktop Review | 26-PC-43364 | Completed |  |  | 8606 | 5233.45 | 5745.54 | 805.75 | 6225.84 | 0 | 7031.59 | 66 | 97
NHT-016835 - Project Management | 26-PC-43364 | Completed |  |  | 12528 | 7618.91 | 8364.41 | 1223.43 | 9453.21 | 0 | 10676.64 | 98 | 155.25
NHT-016838 - Testing | 26-PC-43364 | Completed |  |  | 3766 | 2290.04 | 2514.12 | 527.33 | 4074.54 | 0 | 4601.87 | 27 | 94.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43364 | Completed |  |  | 0 | 0 | 0 | 0 | 515.86 | 0 | 515.86 | 0 | 9.75
NHT-016840 - Lab Analysis | 26-PC-43381 | In progress |  |  | 309600 | 249847.2 | 249847.2 | 3345.71 | 14708.7 | 0 | 18054.41 | 0 | 157
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43381 | In progress |  |  | 0 | 0 | 0 | 0 | 1063.92 | 0 | 1063.92 | 0 | 13
NHT-016849 - Monitoring | 26-PC-43404 | Completed |  |  | 66474 | 54369.07 | 54369.07 | 11450.13 | 59229.67 | 0 | 70679.8 | 650 | 1114.9
NHT-016853 - Draft Report | 26-PC-43404 | Completed |  |  | 46261 | 37837.14 | 37837.14 | 7968.5 | 41219.78 | 0 | 49188.28 | 424 | 665.81
NHT-016857 - Testing | 26-PC-43404 | Completed |  |  | 52790 | 43176.83 | 43176.83 | 9093.04 | 47036.83 | 0 | 56129.87 | 475 | 832.15
NHT-016859 - Final Report | 26-PC-43404 | Completed |  |  | 25175 | 20590.49 | 20590.49 | 4336.36 | 22431.28 | 0 | 26767.64 | 221 | 385.9
NHT-016862 - Reporting | 26-PC-43429 | Completed |  |  | 5929 | 3377.06 | 3377.06 | 83.75 | 345.76 | 0 | 429.51 | 0 | 8.25
NHT-016868 - Testing | 26-PC-43429 | Completed |  |  | 20884 | 11895.81 | 11895.81 | 317.25 | 1309.69 | 0 | 1626.94 | 0 | 31.25
NHT-016873 - GIS & Mapping | 26-PC-43429 | Completed |  |  | 175787 | 100128.09 | 100128.09 | 767.98 | 3170.34 | 0 | 3938.32 | 0 | 74.75
NHT-016879 - Lab Analysis | 26-PC-43478 | In progress |  |  | 390724 | 277804.83 | 277804.83 | 15452 | 56412.52 | 0 | 71864.52 | 2298 | 877.25
NHT-016885 - Reporting | 26-PC-43478 | In progress |  |  | 141076 | 100304.97 | 100304.97 | 9234.04 | 33711.85 | 0 | 42945.89 | 802 | 536.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43478 | In progress |  |  | 0 | 0 | 0 | 0 | 2742.19 | 0 | 2742.19 | 0 | 50
NHT-016895 - GIS & Mapping | 26-PC-43493 | In progress |  |  | 506403 | 315878.22 | 388453.47 | 4791.18 | 20311.91 | 0 | 25103.09 | 5584 | 404.75
NHT-016900 - Reporting | 26-PC-43493 | In progress |  |  | 554993 | 346187.74 | 425726.82 | 3682.84 | 15613.16 | 0 | 19296 | 4513 | 291
NHT-016904 - Final Report | 26-PC-43493 | In progress |  |  | 102904 | 64188.34 | 78936.06 | 3993.68 | 16930.96 | 0 | 20924.64 | 695 | 280.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43493 | In progress |  |  | 0 | 0 | 0 | 0 | 1348.45 | 0 | 1348.45 | 0 | 27.25
NHT-016912 - Monitoring | 26-PC-43519 | Completed |  |  | 21603 | 15362.49 | 15362.49 | 1463.39 | 13940.68 | 0 | 15404.07 | 0 | 218.45
NHT-016914 - Curation | 26-PC-43519 | Completed |  |  | 3285 | 2335.69 | 2335.69 | 222.49 | 2119.52 | 0 | 2342.01 | 0 | 31.68
NHT-016917 - Agency Consultation | 26-PC-43519 | Completed |  |  | 3212 | 2283.73 | 2283.73 | 217.54 | 2072.37 | 0 | 2289.91 | 0 | 29.4
NHT-016924 - GIS & Mapping | 26-PC-43527 | In progress |  |  | 24862 | 16739.72 | 16739.72 | 1331.01 | 6035.81 | 0 | 7366.82 | 142 | 91
NHT-016926 - Reporting | 26-PC-43527 | In progress |  |  | 116790 | 78634.15 | 78634.15 | 1492.99 | 6770.37 | 0 | 8263.36 | 723 | 82.5
NHT-016927 - Fieldwork | 26-PC-43527 | In progress |  |  | 36025 | 24255.87 | 24255.87 | 1814.08 | 8226.42 | 0 | 10040.5 | 195 | 113.5
NHT-016931 - Agency Consultation | 26-PC-43527 | In progress |  |  | 107315 | 72255.38 | 72255.38 | 2175.29 | 9864.46 | 0 | 12039.75 | 667 | 118.25
NHT-016935 - Desktop Review | 26-PC-43527 | In progress |  |  | 48708 | 32795.09 | 32795.09 | 2499.32 | 11333.85 | 0 | 13833.17 | 277 | 175
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43527 | In progress |  |  | 0 | 0 | 0 | 0 | 1977.61 | 0 | 1977.61 | 0 | 18.75
NHT-016944 - Reporting | 26-PC-43528 | Completed |  |  | 21800 | 14869.78 | 14869.78 | 1156.93 | 10447.97 | 0 | 11604.9 | 185 | 136.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43528 | Completed |  |  | 0 | 0 | 0 | 0 | 1108.65 | 0 | 1108.65 | 0 | 14.25
NHT-016950 - GIS & Mapping | 26-PC-43546 | Completed |  |  | 26321 | 20196.02 | 20196.02 | 8811.08 | 32421.3 | 0 | 41232.38 | 140 | 469.75
NHT-016957 - Testing | 26-PC-43546 | In progress |  |  | 42287 | 32446.45 | 32446.45 | 7644.49 | 28128.7 | 0 | 35773.19 | 306 | 485.25
NHT-016962 - Fieldwork | 26-PC-43546 | In progress |  |  | 68292 | 52400.9 | 52400.9 | 4958 | 18243.5 | 0 | 23201.5 | 485 | 303.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43546 | In progress |  |  | 0 | 0 | 0 | 0 | 326.14 | 0 | 326.14 | 0 | 6
NHT-016968 - Site Recordation | 26-PC-43563 | In progress |  |  | 34164 | 19408.02 | 22430.67 | 525.37 | 2687.83 | 0 | 3213.2 | 265 | 56.25
NHT-016972 - Draft Report | 26-PC-43563 | In progress |  |  | 45636 | 25924.98 | 29962.58 | 2139.38 | 10945.21 | 0 | 13084.59 | 375 | 175.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43563 | In progress |  |  | 0 | 0 | 0 | 0 | 461.62 | 0 | 461.62 | 0 | 6.25
NHT-016983 - Site Recordation | 26-PC-43575 | Completed |  |  | 113100 | 66733.2 | 87831.71 | 11441.92 | 47874.66 | 0 | 59316.58 | 0 | 743.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43575 | Completed |  |  | 0 | 0 | 0 | 0 | 2531.64 | 0 | 2531.64 | 0 | 44.75
NHT-016991 - Background Research | 26-PC-43584 | In progress |  |  | 42423 | 35185.72 | 35185.72 | 0 | 0 | 0 | 0 | 430 | 0
NHT-016994 - Agency Consultation | 26-PC-43584 | In progress |  |  | 29182 | 24203.79 | 24203.79 | 0 | 0 | 0 | 0 | 225 | 0
NHT-016997 - Curation | 26-PC-43584 | In progress |  |  | 48404 | 40146.45 | 40146.45 | 0 | 0 | 0 | 0 | 433 | 0
NHT-017001 - Draft Report | 26-PC-43584 | In progress |  |  | 103691 | 86000.82 | 86000.82 | 0 | 0 | 0 | 0 | 1016 | 0
NHT-017003 - Agency Consultation | 26-PC-43695 | In progress |  |  | 32699 | 23033.28 | 23033.28 | 1224.9 | 5410.99 | 0 | 6635.89 | 340 | 101
NHT-017007 - Prefield | 26-PC-43695 | In progress |  |  | 47256 | 33287.25 | 33287.25 | 1635.82 | 7226.16 | 0 | 8861.98 | 451 | 146
NHT-017014 - Survey | 26-PC-43695 | In progress |  |  | 20213 | 14237.95 | 14237.95 | 1173.07 | 5182.01 | 0 | 6355.08 | 213 | 112.75
NHT-017017 - Testing | 26-PC-43695 | In progress |  |  | 4532 | 3192.2 | 3192.2 | 533.96 | 2358.77 | 0 | 2892.73 | 48 | 34.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43695 | In progress |  |  | 0 | 0 | 0 | 0 | 630.69 | 0 | 630.69 | 0 | 14
NHT-017027 - Agency Consultation | 26-PC-43731 | In progress |  |  | 2012 | 1467.26 | 1467.26 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017028 - Final Report | 26-PC-43731 | In progress |  |  | 3115 | 2271.3 | 2271.3 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017032 - Project Management | 26-PC-43731 | In progress |  |  | 4910 | 3579.62 | 3579.62 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017035 - Desktop Review | 26-PC-43731 | In progress |  |  | 1351 | 984.93 | 984.93 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017038 - Testing | 26-PC-43731 | In progress |  |  | 6312 | 4601.96 | 4601.96 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017039 - Agency Consultation | 26-PC-43746 | On hold |  |  | 94200 | 53458.5 | 53458.5 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017046 - Draft Report | 26-PC-43762 | In progress |  |  | 10233 | 9005.3 | 9005.3 | 115.21 | 514.37 | 0 | 629.58 | 84 | 7.75
NHT-017053 - Fieldwork | 26-PC-43762 | In progress |  |  | 837 | 736.47 | 736.47 | 0 | 0 | 0 | 0 | 6 | 0
NHT-017056 - Desktop Review | 26-PC-43762 | In progress |  |  | 6235 | 5486.39 | 5486.39 | 37.17 | 165.93 | 0 | 203.1 | 35 | 2.5
NHT-017061 - Prefield | 26-PC-43762 | In progress |  |  | 195 | 171.84 | 171.84 | 0 | 0 | 0 | 0 | 1 | 0
NHT-017065 - Final Report | 26-PC-43818 | Completed |  |  | 100049 | 81769.56 | 81769.56 | 727.41 | 7179.18 | 0 | 7906.59 | 0 | 114
NHT-017068 - Curation | 26-PC-43818 | Completed |  |  | 29363 | 23998.23 | 23998.23 | 240.89 | 2377.5 | 0 | 2618.39 | 0 | 41.75
NHT-017075 - Site Recordation | 26-PC-43818 | Completed |  |  | 71913 | 58774.74 | 58774.74 | 541.34 | 5342.78 | 0 | 5884.12 | 0 | 80.5
NHT-017081 - Background Research | 26-PC-43818 | Completed |  |  | 26649 | 21780.43 | 21780.43 | 455.88 | 4499.37 | 0 | 4955.25 | 0 | 69.25
NHT-017083 - Desktop Review | 26-PC-43818 | Completed |  |  | 49626 | 40559.52 | 40559.52 | 445.24 | 4394.35 | 0 | 4839.59 | 0 | 70
NHT-017087 - Agency Consultation | 26-PC-43874 | Completed |  |  | 37536 | 27066.86 | 27066.86 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017088 - Prefield | 26-PC-43874 | Completed |  |  | 34564 | 24924.45 | 24924.45 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017094 - Lab Analysis | 26-PC-43899 | In progress |  |  | 125756 | 84407.67 | 84407.67 | 2184.66 | 8961.58 | 0 | 11146.24 | 0 | 100.5
NHT-017101 - Project Management | 26-PC-43899 | In progress |  |  | 873 | 585.77 | 585.77 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017106 - Desktop Review | 26-PC-43899 | In progress |  |  | 25547 | 17146.93 | 17146.93 | 279.77 | 1147.61 | 0 | 1427.38 | 0 | 25.25
NHT-017107 - Monitoring | 26-PC-43899 | In progress |  |  | 2424 | 1627.15 | 1627.15 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017111 - Agency Consultation | 26-PC-43915 | Completed |  |  | 468 | 411.89 | 411.89 | 0 | 0 | 0 | 0 | 5 | 0
NHT-017112 - Desktop Review | 26-PC-43915 | Completed |  |  | 468 | 411.89 | 411.89 | 0 | 0 | 0 | 0 | 5 | 0
NHT-017119 - Final Report | 26-PC-43915 | Completed |  |  | 749 | 659.02 | 659.02 | 0 | 0 | 0 | 0 | 8 | 0
NHT-017120 - Data Recovery Excavation | 26-PC-43915 | Completed |  |  | 200515 | 176453.2 | 176453.2 | 147.76 | 938.72 | 0 | 1086.48 | 2360 | 12.25
NHT-017121 - Draft Report | 26-PC-43927 | Completed |  |  | 560 | 335.02 | 367.12 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017128 - Lab Analysis | 26-PC-43927 | Completed |  |  | 47362 | 28334.84 | 31049.73 | 245.89 | 1655.74 | 0 | 1901.63 | 0 | 33
NHT-017130 - Survey | 26-PC-43927 | Completed |  |  | 12078 | 7225.49 | 7917.79 | 39.01 | 262.71 | 0 | 301.72 | 0 | 5.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43927 | Completed |  |  | 0 | 0 | 0 | 0 | 75.84 | 0 | 75.84 | 0 | 1.5
NHT-017138 - Fieldwork | 26-PC-43957 | Completed |  |  | 161833 | 120015.05 | 120015.05 | 14893.75 | 125613.35 | 0 | 140507.1 | 972 | 1750.78
NHT-017145 - Data Recovery Excavation | 26-PC-43957 | Completed |  |  | 132167 | 98015.35 | 98015.35 | 12163.61 | 102587.42 | 0 | 114751.03 | 1150 | 1377.87
NHT-017152 - Desktop Review | 26-PC-43961 | Completed |  |  | 23968 | 19170 | 19170 | 3839.75 | 17023.2 | 0 | 20862.95 | 295 | 302.5
NHT-017156 - Prefield | 26-PC-43961 | Completed |  |  | 76128 | 60887.51 | 60887.51 | 4732.05 | 20979.09 | 0 | 25711.14 | 867 | 384.75
NHT-017161 - Final Report | 26-PC-43961 | Completed |  |  | 80476 | 64364.12 | 64364.12 | 3723.81 | 16509.19 | 0 | 20233 | 754 | 307.75
NHT-017168 - Reporting | 26-PC-43961 | Completed |  |  | 61133 | 48894.34 | 48894.34 | 2185.02 | 9687.11 | 0 | 11872.13 | 822 | 170.25
NHT-017169 - Background Research | 26-PC-43961 | Completed |  |  | 22895 | 18311.11 | 18311.11 | 2714.1 | 12032.71 | 0 | 14746.81 | 254 | 210.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43961 | Completed |  |  | 0 | 0 | 0 | 0 | 1572.5 | 0 | 1572.5 | 0 | 27.75
NHT-017177 - Lab Analysis | 26-PC-43963 | In progress |  |  | 81265 | 51124.02 | 51124.02 | 2146.29 | 13920.08 | 0 | 16066.37 | 1265 | 261
NHT-017181 - Curation | 26-PC-43963 | In progress |  |  | 141209 | 88833.82 | 88833.82 | 2344.31 | 15204.36 | 0 | 17548.67 | 1533 | 294.25
NHT-017183 - Desktop Review | 26-PC-43963 | In progress |  |  | 116642 | 73379.79 | 73379.79 | 2121.32 | 13758.16 | 0 | 15879.48 | 1521 | 237.5
NHT-017189 - Final Report | 26-PC-43963 | In progress |  |  | 77852 | 48976.76 | 48976.76 | 2284.66 | 14817.48 | 0 | 17102.14 | 920 | 275
NHT-017193 - Testing | 26-PC-43963 | In progress |  |  | 115632 | 72744.27 | 72744.27 | 2132.01 | 13827.49 | 0 | 15959.5 | 1376 | 266.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43963 | In progress |  |  | 0 | 0 | 0 | 0 | 1631.56 | 0 | 1631.56 | 0 | 32.5
NHT-017205 - Lab Analysis | 26-PC-43979 | Completed |  |  | 29917 | 22093.92 | 22093.92 | 0 | 0 | 0 | 0 | 317 | 0
NHT-017207 - Curation | 26-PC-43979 | Completed |  |  | 13844 | 10223.95 | 10223.95 | 0 | 0 | 0 | 0 | 98 | 0
NHT-017212 - Fieldwork | 26-PC-43979 | Completed |  |  | 54739 | 40424.38 | 40424.38 | 0 | 0 | 0 | 0 | 475 | 0
NHT-017215 - Final Report | 26-PC-43986 | Completed |  |  | 33383 | 22179.65 | 22179.65 | 5578.26 | 32190.3 | 0 | 37768.56 | 263 | 429.25
NHT-017219 - Desktop Review | 26-PC-43986 | Completed |  |  | 32826 | 21809.77 | 21809.77 | 7907.27 | 45630.23 | 0 | 53537.5 | 285 | 660
NHT-017226 - Fieldwork | 26-PC-43986 | Completed |  |  | 154591 | 102710.1 | 102710.1 | 6494.44 | 37477.28 | 0 | 43971.72 | 1206 | 559.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43986 | Completed |  |  | 0 | 0 | 0 | 0 | 1571.3 | 0 | 1571.3 | 0 | 20
NHT-017235 - Final Report | 26-PC-43991 | In progress |  |  | 1557 | 721.76 | 922.55 | 62.91 | 448.95 | 0 | 511.86 | 6 | 3.75
NHT-017241 - Lab Analysis | 26-PC-43991 | In progress |  |  | 224 | 104.08 | 133.04 | 0 | 0 | 0 | 0 | 1 | 0
NHT-017245 - Project Management | 26-PC-43991 | Completed |  |  | 1425 | 660.8 | 844.64 | 117.42 | 838.04 | 0 | 955.46 | 4 | 7
NHT-017248 - Desktop Review | 26-PC-43991 | In progress |  |  | 4543 | 2106.55 | 2692.61 | 220.94 | 1576.79 | 0 | 1797.73 | 14 | 14
NHT-017249 - Agency Consultation | 26-PC-43991 | In progress |  |  | 14751 | 6840.09 | 8743.03 | 598.08 | 4268.41 | 0 | 4866.49 | 49 | 43.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-43991 | In progress |  |  | 0 | 0 | 0 | 0 | 59.86 | 0 | 59.86 | 0 | 0.5
NHT-017256 - Project Management | 26-PC-44007 | Completed |  |  | 226900 | 149799.38 | 149799.38 | 1251.47 | 7500.05 | 0 | 8751.52 | 2606 | 170
NHT-017257 - Desktop Review | 26-PC-44050 | Completed |  |  | 173767 | 123687.51 | 123687.51 | 496.28 | 3923.69 | 0 | 4419.97 | 1363 | 80.75
NHT-017260 - Final Report | 26-PC-44050 | Completed |  |  | 43541 | 30992.38 | 30992.38 | 362.8 | 2868.37 | 0 | 3231.17 | 398 | 59.5
NHT-017267 - Monitoring | 26-PC-44050 | Completed |  |  | 291217 | 207288.07 | 207288.07 | 1368.21 | 10817.2 | 0 | 12185.41 | 2125 | 224.25
NHT-017273 - Reporting | 26-PC-44050 | Completed |  |  | 109895 | 78223.23 | 78223.23 | 296.8 | 2346.5 | 0 | 2643.3 | 938 | 48.75
NHT-017276 - Site Recordation | 26-PC-44050 | Completed |  |  | 51980 | 36999.53 | 36999.53 | 345.4 | 2730.76 | 0 | 3076.16 | 399 | 54.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44050 | Completed |  |  | 0 | 0 | 0 | 0 | 1013.31 | 0 | 1013.31 | 0 | 20.25
NHT-017286 - Fieldwork | 26-PC-44072 | Completed |  |  | 106200 | 79469.46 | 79469.46 | 7592.57 | 32957.58 | 0 | 40550.15 | 0 | 391
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44072 | Completed |  |  | 0 | 0 | 0 | 0 | 939.31 | 0 | 939.31 | 0 | 12.5
NHT-017298 - Survey | 26-PC-44090 | Completed |  |  | 230 | 119.37 | 160.97 | 0 | 0 | 0 | 0 | 1 | 0
NHT-017301 - Background Research | 26-PC-44090 | Completed |  |  | 55 | 28.65 | 38.63 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017306 - Fieldwork | 26-PC-44090 | Completed |  |  | 276 | 143.25 | 193.16 | 0 | 0 | 0 | 0 | 2 | 0
NHT-017312 - GIS & Mapping | 26-PC-44090 | Completed |  |  | 5684 | 2946.11 | 3972.77 | 35.07 | 530.61 | 0 | 565.68 | 28 | 5.75
NHT-017314 - Curation | 26-PC-44090 | Completed |  |  | 55 | 28.65 | 38.63 | 0 | 0 | 0 | 0 | 0 | 0
NHT-017318 - GIS & Mapping | 26-PC-44129 | In progress |  |  | 7368 | 5530.59 | 5530.59 | 0 | 0 | 0 | 0 | 38 | 0
NHT-017319 - Survey | 26-PC-44129 | In progress |  |  | 21988 | 16503.99 | 16503.99 | 0 | 0 | 0 | 0 | 109 | 0
NHT-017322 - Curation | 26-PC-44129 | In progress |  |  | 3201 | 2402.5 | 2402.5 | 0 | 0 | 0 | 0 | 20 | 0
NHT-017325 - Site Recordation | 26-PC-44129 | In progress |  |  | 7843 | 5887.16 | 5887.16 | 0 | 0 | 0 | 0 | 45 | 0
NHT-017332 - Fieldwork | 26-PC-44173 | Completed |  |  | 25154 | 17391.42 | 17391.42 | 434.61 | 3574.07 | 0 | 4008.68 | 0 | 72
NHT-017333 - Reporting | 26-PC-44173 | Completed |  |  | 28736 | 19868.24 | 19868.24 | 388.36 | 3193.73 | 0 | 3582.09 | 0 | 63.5
NHT-017334 - Background Research | 26-PC-44173 | Completed |  |  | 106710 | 73779.18 | 73779.18 | 1276.18 | 10494.71 | 0 | 11770.89 | 0 | 213
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44173 | Completed |  |  | 0 | 0 | 0 | 0 | 822.44 | 0 | 822.44 | 0 | 16.5
NHT-017345 - Prefield | 26-PC-44201 | Completed |  |  | 165400 | 115267.26 | 115267.26 | 2412.66 | 35754.99 | 0 | 38167.65 | 1266 | 479
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44201 | Completed |  |  | 0 | 0 | 0 | 0 | 1384.2 | 0 | 1384.2 | 0 | 15
NHT-017353 - Monitoring | 26-PC-44220 | Completed |  |  | 25120 | 20042.93 | 20042.93 | 281.97 | 1431.95 | 0 | 1713.92 | 325 | 32.5
NHT-017357 - Testing | 26-PC-44220 | Completed |  |  | 34580 | 27591.7 | 27591.7 | 501.05 | 2544.47 | 0 | 3045.52 | 366 | 57.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44220 | Completed |  |  | 0 | 0 | 0 | 0 | 165.22 | 0 | 165.22 | 0 | 3.75
NHT-017365 - Testing | 26-PC-44256 | Completed |  |  | 566172 | 401472.5 | 401472.5 | 26673.86 | 104595.23 | 0 | 131269.09 | 0 | 1547.75
NHT-017368 - GIS & Mapping | 26-PC-44256 | Completed |  |  | 244528 | 173394.87 | 173394.87 | 18452.23 | 72356.02 | 0 | 90808.25 | 0 | 1094.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44256 | Completed |  |  | 0 | 0 | 0 | 0 | 5832.23 | 0 | 5832.23 | 0 | 84.25
NHT-017373 - Draft Report | 26-PC-44277 | In progress |  |  | 13705 | 11074.95 | 11074.95 | 1568.9 | 5777.31 | 0 | 7346.21 | 112 | 77
NHT-017378 - Desktop Review | 26-PC-44277 | In progress |  |  | 29413 | 23768.82 | 23768.82 | 2200.54 | 8103.24 | 0 | 10303.78 | 271 | 108
NHT-017382 - Monitoring | 26-PC-44277 | Completed |  |  | 5982 | 4833.94 | 4833.94 | 1110.46 | 4089.14 | 0 | 5199.6 | 44 | 54.5
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44277 | In progress |  |  | 0 | 0 | 0 | 0 | 168.82 | 0 | 168.82 | 0 | 2.25
NHT-017386 - Data Recovery Excavation | 26-PC-44290 | Completed |  |  | 45054 | 34993.54 | 34993.54 | 643.75 | 4365.52 | 0 | 5009.27 | 352 | 74
NHT-017393 - Curation | 26-PC-44290 | Completed |  |  | 7890 | 6128.49 | 6128.49 | 337.02 | 2285.49 | 0 | 2622.51 | 73 | 27.75
NHT-017394 - Project Management | 26-PC-44290 | Completed |  |  | 13422 | 10425.1 | 10425.1 | 519.81 | 3525.04 | 0 | 4044.85 | 106 | 48
NHT-017400 - Testing | 26-PC-44290 | Completed |  |  | 77903 | 60506.71 | 60506.71 | 1598.76 | 10841.73 | 0 | 12440.49 | 658 | 151.75
NHT-017403 - Lab Analysis | 26-PC-44290 | Completed |  |  | 61831 | 48024.03 | 48024.03 | 1138.6 | 7721.25 | 0 | 8859.85 | 544 | 93.75
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44290 | Completed |  |  | 0 | 0 | 0 | 0 | 926.55 | 0 | 926.55 | 0 | 11.25
NHT-017412 - Lab Analysis | 26-PC-44302 | Completed |  |  | 792 | 591.31 | 591.31 | 0 | 0 | 0 | 0 | 3 | 0
NHT-017414 - Desktop Review | 26-PC-44302 | Completed |  |  | 33534 | 25033.07 | 25033.07 | 2746.35 | 10595.21 | 0 | 13341.56 | 158 | 88.5
NHT-017418 - Testing | 26-PC-44302 | Completed |  |  | 43271 | 32301.37 | 32301.37 | 1721.36 | 6640.88 | 0 | 8362.24 | 165 | 64
NHT-017424 - Fieldwork | 26-PC-44302 | Completed |  |  | 8238 | 6149.84 | 6149.84 | 1039.58 | 4010.62 | 0 | 5050.2 | 39 | 33.5
NHT-017430 - Background Research | 26-PC-44302 | Completed |  |  | 4365 | 3258.71 | 3258.71 | 390.42 | 1506.21 | 0 | 1896.63 | 24 | 19.25
OVHD-Non-Posting - Overhead Non-Posting | 26-PC-44302 | Completed |  |  | 0 | 0 | 0 | 0 | 1286.99 | 0 | 1286.99 | 0 | 10.75
Total All |  |  |  |  | 270119100 | 182212286.83 | 190699414.58 | 15825569.98 | 99002825.19 | 0 | 114828395.17 | 2240294 | 1820252.95
Created on : 09/29/2026 06:42:18 AM

## OTC All reports keys account in
Northstar
OTC All reports keys account information (In USD)
Reporting Book: | ACCRUAL
As of Date: | 09/26/2026
Location: | Northstar
[8 empty] | Contract Value | Invoiced Amount | Total Revised Budget | Accounts Receivable | Cash and Cash Equivalents | Revenues | Cost of Sales | Wages | Total Delayed Revenue |  |  |  | OTC Cycle Walkforward Validation | Total Billable Hours | Total Non-Billable Hours | Budgeted Hours
[16 empty] | Unbilled Receivable | WIP | Deferred Revenue | Total Delayed Revenue
[8 empty] | ITD As of | ITD As of | ITD As of | ITD As of | Month To Date | ITD As of | ITD As of | Month To Date | ITD As of | ITD As of | ITD As of | ITD As of | ITD As of | Month Ending | Month Ending | Month Ending
[8 empty] | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/26/2026 | 09/30/2026 | 09/30/2026 | 09/30/2026
Project ID |  | Billing type | Project status | Location ID | Project manager ID | Customer Name | % Complete | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Project Customer ID | Salesforce ID | Auto Calculate % ...
| All Locations | [5 empty] | 0 | 270119100 | 133830111.46 | 190699414.58 | 3491807.91 | 1993227.52 | 137493343.96 | 15825569.98 | 1747151.56 | 0 | 3663449.46 | 216.96 | 3663666.42 | 0 | 30622.5 | 721.25 | 2240294
| All Customers | [5 empty] | 0 | 270119100 | 133830111.46 | 190699414.58 | 3491807.91 | 1993227.52 | 137493343.96 | 15825569.98 | 1747151.56 | 0 | 3663449.46 | 216.96 | 3663666.42 | 0 | 30622.5 | 721.25 | 2240294
All Projects
23-PC-30060 | Lone Pine Pipeline - Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | L8000 | E30904 | Prairie Wind Utilities | 100% | 397800 | 397800 | 312273 | 0 | 0 | 397800 | 38818.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3891 | 14159 | 006WVuysvol3h4Q4uF | FALSE
23-PC-30163 | Timber Gap Phase I Survey | Fixed fee | Completed | L8000 | E30907 | Ridgeline Energy Partners | 100% | 33300 | 33300 | 22510.8 | 0 | 0 | 33300 | 3716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299 | 14433 | 006rYkKN4PwXMZnzVG | TRUE
23-PC-30307 | Quail Run Wastewater Plant Cultural Resources Assessment | Fixed fee | Transferred Entity | L8000 | E30904 | Northfield Pipeline Company | 65.62% | 240100 | 157553.62 | 136256.75 | 0 | 0 | 157553.62 | 15736.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118 | 13520 | 006bdm5JCjrLeyabZy | FALSE
23-PC-30372 | Phase I: Lone Pine Reservoir Architectural History Survey | Time and material | In Progress | L8000 | E30907 | Coastal Rail Partners | 0% | 27100 | 18428 | 19864.3 | 0 | 0 | 18428 | 2029.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357 | 11259 | 0062RbxoranJO8AREt | FALSE
23-PC-30543 | Phase III: Riverbend Rail Siding Maritime Remote Sensing Survey | Fixed fee | In Progress | L8000 | E30904 | Prairie Wind Planning Associates | 70.42% | 320600 | 225766.52 | 255628.66 | 0 | 0 | 225766.52 | 26822.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538 | 14041 | 006pK09izpXDRPJEbp | TRUE
23-PC-30644 | Phase II: Millbrook Wastewater Plant Data Recovery | Time and material | In Progress | L8010 | E30916 | Summit Port Authority | 0% | 108100 | 73508 | 72102.7 | 0 | 0 | 73508 | 10123.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854 | 15239 | 00639aqzWOOcNrHbEe | FALSE
23-PC-30667 | North Fork Canal Lining Data Recovery | Time and material | Completed | L8010 | E30913 | Canyon Construction Co. | 100% | 210500 | 143140 | 144045.15 | 0 | 0 | 143140 | 23145.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 10448 | 006z8VeyjGLU2nTIhP | FALSE
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | Time and material | In Progress | L8010 | E30913 | Mesa Verde Pipeline Company | 0% | 49800 | 33864 | 34501.44 | 0 | 0 | 33864 | 5731.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399 | 13320 | 006DAsGlJO6HE9IzMT | FALSE
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Time and material | Cost Tracking on Closed Project | L8010 | E30916 | Westwind Energy Partners | 0% | 86200 | 58616 | 58650.48 | 0 | 0 | 58616 | 7848.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15833 | 006cCx5d0xrnSBZX4t | FALSE
23-PC-30933 | Lantern Bay Water Main - Phase I Survey | Time and material | On Hold | L8010 | E30913 | Lakecrest Planning Associates | 0% | 703200 | 478176 | 461299.2 | 0 | 0 | 478176 | 73095.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9230 | 13040 | 006tJK4o9It9TAincG | FALSE
23-PC-31003 | Windmill Flat Environmental Review Support | Fixed fee | In Progress | L8010 | E30913 | Timberline Telecom Holdings | 80.03% | 19300 | 15445.79 | 10568.68 | 0 | 0 | 15445.79 | 972.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15690 | 006S9hokBHCuhwLwNy | FALSE
23-PC-31042 | Stone Mill Historic Resources Evaluation | Time and material | In Progress | L8020 | E30925 | Ridgeline County | 0% | 299700 | 203796 | 202896.9 | 0 | 0 | 203796 | 22779.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2753 | 14393 | 006bbzKCJSsRPlc6re | FALSE
23-PC-31076 | Wildrye Rail Siding - Archaeological Testing | Time and material | Final Reporting/Review | L8020 | E30937 | Coastal County | 0% | 95100 | 64668 | 65561.94 | 0 | 0 | 64668 | 2865.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 11118 | 006KGNhCEvk1zIC4tD | FALSE
23-PC-31344 | Timber Gap Battery Storage Archaeological Testing | Fixed fee | In Progress | L8020 | E30937 | Blue Mesa Port Authority | 58.66% | 331600 | 194516.56 | 264351.52 | 0 | 0 | 194516.56 | 22948.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10214 | 006Hlhn5jmEwh6O9Rn | FALSE
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | Time and material | In Progress | L8020 | E30925 | Stonebridge Land Company | 0% | 255700 | 173876 | 168225.03 | 0 | 0 | 173876 | 34493.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342 | 14975 | 006TYP6GbCV7W4L0dv | FALSE
23-PC-31389 | Juniper Wash Highway Widening Archaeological Testing | Time and material | Final Billing/Invoice | L8020 | E30942 | Highland Construction Co. | 100% | 30700 | 20876 | 20958.95 | 0 | 0 | 20876 | 3351.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 12239 | 006IXggu8M935mgsE5 | FALSE
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | Fixed fee | In Progress | L8020 | E30935 | Pioneer County | 70.86% | 108000 | 76528.8 | 82404 | 0 | 0 | 76528.8 | 9167.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308 | 13727 | 006etavgHX7RIeFvXu | TRUE
23-PC-31604 | Timber Gap Pipeline - Cultural Resources Assessment | Time and material | Final Billing/Invoice | L8020 | E30937 | Brightwater Planning Associates | 100% | 180800 | 122944 | 124607.36 | 0 | 0 | 122944 | 11501.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897 | 10306 | 0065RbLT51keMjvpkP | FALSE
23-PC-31765 | Saltgrass Phase I Survey | Fixed fee | Final Reporting/Review | L8020 | E30923 | Redtail Engineering, Inc. | 57.21% | 32700 | 18707.67 | 27114.84 | 0 | 0 | 18707.67 | 1644.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14233 | 006UjKkWs17boPp95A | TRUE
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | Fixed fee | In Progress | L8020 | E30936 | Lakecrest Renewables LLC | 100% | 34800 | 34800 | 28779.6 | 0 | 0 | 34800 | 6875.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367 | 13164 | 006J1GoiwwkFGt4FUO | FALSE
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | Fixed fee | In Progress | L8020 | E30935 | Summit Port Authority | 75.7% | 460600 | 348674.2 | 390957.28 | 0 | 0 | 348674.2 | 54459.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6183 | 15239 | 006IAztFnvhMIuWTWL | FALSE
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | L8020 | E30935 | Prairie Wind Port Authority | 100% | 175300 | 175300 | 93481.01 | 0 | 0 | 175300 | 24581.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14077 | 006euuNzOkIRcXeIMg | TRUE
23-PC-31944 | Phase I: Goldfinch Airport Apron Class III Survey | Fixed fee | Final Billing/Invoice | L8020 | E30942 | Lakecrest Construction Co. | 100% | 76000 | 76000 | 54636.4 | 0 | 0 | 76000 | 6893.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 12952 | 006OGFKq0VThEAYXvl | FALSE
23-PC-31976 | Foxglove Cell Tower GIS Mapping | Time and material | Completed | L8030 | E30958 | Harborlight Transit Authority | 100% | 72100 | 49028 | 51263.1 | 0 | 0 | 49028 | 6425.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698 | 11703 | 006eYADDBmj9DKqf3l | FALSE
23-PC-32015 | Copper Flats Harbor Dredging - Class III Survey | Fixed fee | In Progress | L8030 | E30958 | Pioneer Development Group | 45.38% | 89300 | 40524.34 | 65024.25 | 0 | 0 | 40524.34 | 4898.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852 | 13750 | 0062bAYLbXD38NXx4F | FALSE
23-PC-32135 | Sage Flat Levee Repair Architectural History Survey | Fixed fee | Final Billing/Invoice | L8030 | E30947 | Blue Mesa Resources Corp. | 100% | 171600 | 171600 | 128744.02 | 0 | 0 | 171600 | 7840.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10225 | 006Ga5dwu9YfFl8az2 | FALSE
23-PC-32278 | Coyote Springs Highway Widening Paleontological Monitoring | Time and material | Lab/Curation | L8030 | E30950 | Silverline Port Authority | 0% | 3500 | 2380 | 2281.3 | 0 | 0 | 2380 | 340.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 14747 | 0065tdFuqJLFzrCSgh | FALSE
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | Fixed fee | In Progress | L8030 | E30957 | Clearwater Engineering, Inc. | 89.13% | 149100 | 132892.83 | 111109.32 | 0 | 0 | 132892.83 | 13567.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506 | 10896 | 0062NDiCxMTUJPgFuu | TRUE
23-PC-32443 | Tamarack Battery Storage - Cultural Resources Monitoring | Time and material | In Progress | L8030 | E30947 | Prairie Wind Transit Authority | 0% | 152600 | 117078.5 | 107415.14 | 0 | 0 | 117078.5 | 6033.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 14127 | 006VBhAAVSIH7pOa9c | FALSE
23-PC-32474 | Slate Ridge Cell Tower - Phase I Survey | Fixed fee | Completed | L8030 | E30950 | Timberline Planning Associates | 100% | 52900 | 52900 | 42882.38 | 0 | 0 | 52900 | 4160.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 745 | 15643 | 0063uaf2iwZcTqqOaN | TRUE
23-PC-32520 | Tamarack Battery Storage GIS Mapping | Time and material | Lab/Curation | L8030 | E30950 | Summit Transit Authority | 0% | 1116300 | 759084 | 767567.88 | 0 | 0 | 759084 | 127497.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8561 | 15291 | 0065qqE32LtgkG9t8H | FALSE
23-PC-32635 | Rushgrass Draw Curation | Time and material | Cost Tracking on Closed Project | L8030 | E30958 | Keystone Rail Partners | 0% | 36800 | 25024 | 24644.96 | 0 | 0 | 25024 | 5792.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 12893 | 006jITHjTMLF1xS2Y8 | FALSE
23-PC-33001 | Heron Marsh Environmental Review Support | Time and material | In Progress | L8040 | E30980 | Clearwater Resources Corp. | 0% | 356400 | 242352 | 221573.88 | 0 | 0 | 242352 | 17730.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3325 | 11004 | 006cPuVCYpUKSaYO7v | FALSE
23-PC-33043 | Phase II: Copper Flats Fiber Route Data Recovery | Fixed fee | Completed | L8040 | E30965 | Granite State Infrastructure Group | 100% | 508800 | 508800 | 282312.26 | 0 | 0 | 508800 | 37421.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4078 | 11510 | 006akXYYmTELQxjE7x | FALSE
23-PC-33070 | Meadowlark Curation | Fixed fee | In Progress | L8040 | E30965 | Clearwater Resources Corp. | 84.17% | 55100 | 46377.67 | 34299.75 | 0 | 0 | 46377.67 | 2194.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461 | 11004 | 00610X9RpRPpF4s0xW | FALSE
23-PC-33151 | Sandpiper Class III Survey | Fixed fee | In Progress | L8040 | E30967 | Clearwater Port Authority | 84.91% | 637100 | 540961.61 | 497638.81 | 0 | 0 | 540961.61 | 62114.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6012 | 10969 | 006NBK7QBqmCxqSSK0 | FALSE
23-PC-33193 | Falcon Mesa Transmission Line - Environmental Review Support | Fixed fee | On Hold | L8040 | E30972 | Blue Mesa Resources Corp. | 70.24% | 10900 | 7656.16 | 8531.43 | 0 | 0 | 7656.16 | 796.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 10225 | 006tVtKgw0jxdJXFC7 | FALSE
23-PC-33218 | Plover Cove Class III Survey | Time and material | On Hold | L8040 | E30971 | Ironbridge Construction Co. | 0% | 57000 | 38760 | 36256.05 | 0 | 0 | 38760 | 5604.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422 | 12523 | 006YuzP57DWHvqNnGL | FALSE
23-PC-33299 | Fern Valley Fiber Route - Curation | Fixed fee | On Hold | L8040 | E30965 | Cardinal Utilities | 78.44% | 71300 | 55927.72 | 47214.86 | 0 | 0 | 55927.72 | 6073.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408 | 10833 | 006JvmHiJU6bKmKIyc | FALSE
23-PC-33395 | Lone Pine Environmental Review Support | Time and material | Final Billing/Invoice | L8040 | E30971 | Pioneer County | 100% | 186900 | 127092 | 122438.19 | 0 | 0 | 127092 | 25944.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 13727 | 006iXYORAxWxQrTkzv | FALSE
23-PC-33428 | Hackberry Bend Archaeological Testing | Fixed fee | Final Billing/Invoice | L8040 | E30965 | Sunrise Development Group | 100% | 293900 | 293900 | 208874.73 | 0 | 0 | 293900 | 50234.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3332 | 15389 | 006s1jrW9vzw8rEv26 | FALSE
23-PC-33471 | Sandpiper Park Improvements - Environmental Review Support | Time and material | Lab/Curation | L8040 | E30972 | Clearwater Port Authority | 0% | 113200 | 76976 | 80813.48 | 0 | 0 | 76976 | 11700.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10969 | 006zkWAyNjKFVkRsfH | FALSE
23-PC-33551 | Heron Marsh Airport Apron GIS Mapping | Time and material | Final Reporting/Review | L8040 | E30965 | Ridgeline County | 0% | 95400 | 64872 | 62019.54 | 0 | 0 | 64872 | 5488.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14393 | 0064pdsntFy04Q1Ssi | FALSE
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | Fixed fee | In Progress | L8040 | E30967 | Coastal Development Group | 100% | 21600 | 21600 | 15245.28 | 0 | 0 | 21600 | 1886.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11160 | 006G8uaDYKYF1rHhik | TRUE
23-PC-33605 | Rushgrass Draw Highway Widening - Class III Survey | Fixed fee | Completed | L8040 | E30967 | Cardinal Port Authority | 100% | 309100 | 309100 | 188427.36 | 0 | 0 | 309100 | 27202.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3432 | 10753 | 006nuq7QRFE6v7dBSb | FALSE
23-PC-33695 | On-Call: Windmill Flat Highway Widening Phase I Survey | Fixed fee | On Hold | L8050 | E31001 | Cardinal Land Company | 55.75% | 42600 | 23749.5 | 34191.4 | 0 | 0 | 23749.5 | 3678.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408 | 10711 | 006GW9Tl4PgT8W5oX9 | FALSE
23-PC-33803 | Willow Springs Pipeline Cultural Resources Assessment | Time and material | On Hold | L8050 | E31000 | Westwind Infrastructure Group | 0% | 66400 | 45152 | 40244.88 | 0 | 0 | 45152 | 1692.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15890 | 006Ja7F74Al2nBNwuB | FALSE
23-PC-33858 | Phase II: Cedar Hollow Pipeline Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8050 | E31001 | Harborlight Transit Authority | 100% | 68500 | 68500 | 46737.55 | 0 | 0 | 68500 | 3169.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823 | 11703 | 006lglkb9N2VUWf8KX | TRUE
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | Time and material | In Progress | L8050 | E31001 | Coastal Land Company | 0% | 300600 | 204408 | 219257.64 | 0 | 0 | 204408 | 36571.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11195 | 006zR9jJWDn9qccc4D | FALSE
23-PC-33998 | Phase II: Granite Pass Reservoir Class III Survey | Time and material | In Progress | L8050 | E30995 | Clearwater Engineering, Inc. | 0% | 238800 | 162384 | 156891.6 | 0 | 0 | 162384 | 8408.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10896 | 0068RpGXRUQzwV2EMZ | FALSE
23-PC-34054 | Slate Ridge Wastewater Plant - Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | L8050 | E30984 | Ironbridge Infrastructure Group | 100% | 99000 | 67320 | 67052.7 | 0 | 0 | 67320 | 14629.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12667 | 006LrXktzScig1MtGd | FALSE
23-PC-34135 | Falcon Mesa Architectural History Survey | Fixed fee | Completed | L8050 | E30999 | Redtail Infrastructure Group | 100% | 108800 | 108800 | 84537.6 | 0 | 0 | 108800 | 7710.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14267 | 006RTGCX88kNs3bFh4 | TRUE
23-PC-34171 | Timber Gap Rail Siding - Built Environment Survey | Time and material | In Progress | L8050 | E31001 | Highland Construction Co. | 0% | 221100 | 150348 | 154858.44 | 0 | 0 | 150348 | 13480.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12239 | 006wrWLhKSypGq171G | FALSE
23-PC-34229 | Creosote Draw Mixed-Use Development Paleontological Monitoring | Time and material | In Progress | L8050 | E31001 | Ironbridge Engineering, Inc. | 0% | 48800 | 33184 | 34427.85 | 0 | 0 | 33184 | 2566.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 12649 | 006o5CdHI8kT4RLbPN | FALSE
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | Time and material | In Progress | L8050 | E30999 | Ironbridge County | 0% | 373100 | 253708 | 247626.47 | 0 | 0 | 253708 | 23821.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3361 | 12563 | 0065rd78yMWuLUbpoJ | FALSE
23-PC-34403 | Plover Cove Built Environment Survey | Time and material | In Progress | L8050 | E30999 | Lakecrest Pipeline Company | 0% | 46200 | 31416 | 30187.08 | 0 | 0 | 31416 | 3237.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397 | 13006 | 006TsrhGWOraGmrFDB | FALSE
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | Fixed fee | In Progress | L8050 | E30984 | Sunrise Rail Partners | 72.81% | 477000 | 347303.7 | 333756.9 | 0 | 0 | 347303.7 | 45444.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495 | 15467 | 006aE5diYNXLO4kcx1 | FALSE
23-PC-34473 | Aspen Ridge Cell Tower Phase I Survey | Time and material | In Progress | L8050 | E30992 | Blue Mesa Infrastructure Group | 0% | 52300 | 35564 | 36353.73 | 0 | 0 | 35564 | 4490.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 10139 | 006Bt4tnM2uCGD4FYl | FALSE
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Time and material | Final Reporting/Review | L8050 | E30986 | Blue Mesa Infrastructure Group | 0% | 70000 | 47600 | 50246 | 0 | 0 | 47600 | 10079.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 10139 | 006bTbYhJaHuE3MWsN | FALSE
23-PC-34522 | Foxglove GIS Mapping | Time and material | In Progress | L8050 | E31000 | Westwind Energy Partners | 0% | 192200 | 130696 | 131503.24 | 0 | 0 | 130696 | 9990.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192 | 15833 | 006PhF6EKvOVDSxhsh | FALSE
23-PC-34567 | Foxglove School Campus Phase II Testing | Fixed fee | On Hold | L8050 | E31000 | Lakecrest Telecom Holdings | 50.59% | 17900 | 9055.61 | 14103.41 | 0 | 0 | 9055.61 | 1341.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13182 | 006crZIETVTH7hhPhU | TRUE
23-PC-34745 | Slate Ridge Battery Storage Environmental Review Support | Fixed fee | In Progress | L8050 | E30985 | Lakecrest Development Group | 66.51% | 614200 | 408504.42 | 440258.56 | 0 | 0 | 408504.42 | 60024.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3354 | 12986 | 006iocbg0l9lqFjZGu | FALSE
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | Fixed fee | In Progress | L8060 | E31008 | Stonebridge Utilities | 70.44% | 46100 | 32472.84 | 31721.41 | 0 | 0 | 32472.84 | 3172.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 15036 | 006VsQSykMZtqRXs5S | TRUE
23-PC-34811 | Task Order 2: Saltgrass Airport Apron Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | L8060 | E31014 | Sunrise Telecom Holdings | 82.52% | 112600 | 92917.52 | 80883.68 | 0 | 0 | 92917.52 | 5072.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15492 | 0066zQY7X8sT9Mbrjh | FALSE
23-PC-34826 | Task Order 13: Foxglove Canal Lining Cultural Resources Monitoring | Time and material | In Progress | L8060 | E31018 | Granite State Development Group | 0% | 168500 | 114580 | 109642.95 | 0 | 0 | 114580 | 9943.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384 | 11469 | 006Eq72sHLpm6LrzmN | FALSE
23-PC-34891 | Saltgrass GIS Mapping | Fixed fee | Final Billing/Invoice | L8060 | E31018 | Blue Mesa Port Authority | 100% | 26600 | 26600 | 20891.64 | 0 | 0 | 26600 | 3062.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 10214 | 006HT9ZXmhpbvVLsnC | FALSE
23-PC-34902 | Sumac Ridge Built Environment Survey | Time and material | Final Reporting/Review | L8060 | E31008 | Lakecrest Renewables LLC | 0% | 37000 | 25160 | 26270 | 0 | 0 | 25160 | 3022.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 13164 | 006vnyPRbq3uSLDh9b | FALSE
23-PC-34939 | Maple Fork Maritime Remote Sensing Survey | Time and material | In Progress | L8060 | E31018 | Pioneer Transit Authority | 0% | 145800 | 99144 | 104172.04 | 0 | 0 | 99144 | 5603.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1587 | 13885 | 0061gGVdVbb17q8L5i | FALSE
23-PC-34947 | Aspen Ridge Cell Tower Architectural History Survey | Fixed fee | In Progress | L8060 | E31019 | Coastal Construction Co. | 67.42% | 285900 | 192753.78 | 199615.38 | 0 | 0 | 192753.78 | 17765.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2885 | 11092 | 006RGzoRLbTkCdpvi3 | TRUE
23-PC-35003 | Creosote Draw Archaeological Testing | Time and material | In Progress | L8060 | E31018 | Mesa Verde Telecom Holdings | 0% | 187900 | 127772 | 127170.72 | 0 | 0 | 127772 | 6082.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13431 | 006IrC2YMZz6jouPja | FALSE
23-PC-35098 | On-Call: Larkspur Reservoir Environmental Review Support | Fixed fee | Final Billing/Invoice | L8060 | E31008 | Ironbridge Development Group | 100% | 120000 | 120000 | 100560 | 0 | 0 | 120000 | 9576.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765 | 12618 | 006Nq2duhbinejdAYO | FALSE
23-PC-35126 | Falcon Mesa Rail Siding Built Environment Survey | Time and material | In Progress | L8060 | E31019 | Harborlight County | 0% | 273100 | 185708 | 197014.34 | 0 | 0 | 185708 | 21220.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1974 | 11648 | 006ZDmuT302tZ1unxa | FALSE
23-PC-35176 | Plover Cove Mine Expansion Section 106 Consultation | Fixed fee | In Progress | L8060 | E31018 | Westwind Energy Partners | 66.26% | 74700 | 49496.22 | 53388.09 | 0 | 0 | 49496.22 | 6367.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15833 | 0060RuUvc6qTDMfXNm | TRUE
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | Fixed fee | In Progress | L8060 | E31019 | Coastal Construction Co. | 74.37% | 407900 | 303355.23 | 321139.67 | 0 | 0 | 303355.23 | 27226.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4342 | 11092 | 006P0C3fbzokUH6pAA | FALSE
23-PC-35425 | Yarrow Point Trail - GIS Mapping | Time and material | Lab/Curation | L8070 | E31034 | Summit County | 0% | 24000 | 16320 | 15998.4 | 0 | 0 | 16320 | 2030.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15070 | 006Gq6SjuGMam5A8KQ | FALSE
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | Time and material | In Progress | L8070 | E31023 | Silverline Construction Co. | 0% | 116200 | 79016 | 87219.72 | 0 | 0 | 79016 | 9930.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 14700 | 0063ATSpm5OPtB7DTY | FALSE
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | Fixed fee | In Progress | L8070 | E31034 | Westwind Development Group | 76.15% | 11400 | 8681.1 | 8206.86 | 0 | 0 | 8681.1 | 462.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 15795 | 006m6EIJnH1tnOLKbp | FALSE
23-PC-35568 | Phase II: Coyote Springs Wind Farm Environmental Review Support | Fixed fee | In Progress | L8070 | E31029 | Pioneer Development Group | 56.93% | 253600 | 144374.48 | 168365.04 | 0 | 0 | 144374.48 | 6997.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504 | 13750 | 0061aZ5RsSNJv69E6g | TRUE
23-PC-35682 | Lantern Bay Class III Survey | Fixed fee | In Progress | L8070 | E31034 | Canyon Planning Associates | 95.51% | 290400 | 277361.04 | 252938.4 | 0 | 0 | 277361.04 | 39618.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10525 | 006eAc3wFgePDAYphw | TRUE
23-PC-35715 | Saltgrass Cell Tower Historic Resources Evaluation | Fixed fee | On Hold | L8070 | E31023 | Sunrise County | 83.3% | 44500 | 37068.5 | 33802.2 | 0 | 0 | 37068.5 | 5884.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 15336 | 006U2qsjiboXRYMGzt | FALSE
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | Fixed fee | In Progress | L8070 | E31032 | High Plains Renewables LLC | 91.51% | 114600 | 104870.46 | 77893.62 | 0 | 0 | 104870.46 | 9266.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 12128 | 0066kEUPGj9JLzlIZq | TRUE
23-PC-36108 | Pebble Beach Road Maritime Remote Sensing Survey | Fixed fee | On Hold | L8070 | E31023 | Sunrise Rail Partners | 65.62% | 50200 | 32941.24 | 40154.98 | 0 | 0 | 32941.24 | 3899.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555 | 15467 | 006Gz2AMNqrKZecOwS | FALSE
23-PC-36231 | Phase II: Rushgrass Draw Airport Apron GIS Mapping | Time and material | Final Billing/Invoice | L8080 | E31041 | Highland Telecom Holdings | 100% | 436500 | 296820 | 298453.59 | 0 | 0 | 296820 | 61521.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3577 | 12458 | 006NraJ66ELohnDJlY | FALSE
23-PC-36385 | On-Call: Cedar Hollow Transmission Line Paleontological Monitoring | Time and material | In Progress | L8080 | E31046 | Northfield Development Group | 0% | 392900 | 267172 | 262008.61 | 0 | 0 | 267172 | 17453.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2505 | 13499 | 006rD3TkDBKEsX8cHl | FALSE
23-PC-36422 | Hawk Point Phase I Survey | Time and material | In Progress | L8080 | E31043 | Mesa Verde Pipeline Company | 0% | 50700 | 34476 | 36579.06 | 0 | 0 | 34476 | 6845.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365 | 13320 | 006Q6S2YqktdDpMu4J | FALSE
23-PC-36426 | On-Call: Fern Valley Wastewater Plant Environmental Review Support | Fixed fee | Final Billing/Invoice | L8080 | E31046 | Brightwater Land Company | 100% | 76300 | 76300 | 52730.93 | 0 | 0 | 76300 | 10751.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585 | 10261 | 006YFxS3agSjcJAEjf | FALSE
23-PC-36530 | Lone Pine Architectural History Survey | Time and material | In Progress | L8080 | E31043 | Westwind Development Group | 0% | 141100 | 95948 | 102823.29 | 0 | 0 | 95948 | 6112.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480 | 15795 | 0060zOz6Vdk80c3fil | FALSE
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | Fixed fee | In Progress | L8090 | E31050 | Lakecrest Rail Partners | 84.69% | 201000 | 170226.9 | 151513.8 | 0 | 0 | 170226.9 | 24252.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290 | 13111 | 0064P5kJ03AE9KiISI | FALSE
23-PC-36734 | Raven Rock Curation | Fixed fee | In Progress | L8090 | E31052 | Coastal Rail Partners | 94% | 38600 | 36284 | 27753.4 | 0 | 0 | 36284 | 3574.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 11259 | 00605On4rbVk3sgGSc | FALSE
23-PC-36776 | On-Call: Twin Buttes Trail Phase I Survey | Time and material | In Progress | L8100 | E31059 | Pioneer Renewables LLC | 0% | 457300 | 310964 | 338564.86 | 0 | 0 | 310964 | 17836.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4554 | 13869 | 006wiM2i7w8lRgw5Uy | FALSE
23-PC-37105 | Foxglove Housing Development - Data Recovery | Fixed fee | In Progress | L8100 | E31061 | Pioneer Renewables LLC | 74.87% | 110800 | 82955.96 | 80165.21 | 0 | 0 | 82955.96 | 11163.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 13869 | 006MOgicEfQOCLBf0E | TRUE
23-PC-37245 | Rushgrass Draw Wind Farm Archaeological Testing | Fixed fee | In Progress | L8100 | E31063 | Cardinal Energy Partners | 56% | 425700 | 238392 | 306248.58 | 0 | 0 | 238392 | 37557.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2792 | 10648 | 006jZcoApjQle7Zwbj | FALSE
23-PC-37301 | Coyote Springs Highway Widening Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | L8100 | E31055 | Ridgeline Resources Corp. | 100% | 71900 | 71900 | 50775.78 | 0 | 0 | 71900 | 9859.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 | 14529 | 0063j5lW9tOc55ZQgB | FALSE
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | Fixed fee | In Progress | L8110 | E31074 | Lakecrest Planning Associates | 71.69% | 44500 | 31902.05 | 35070.45 | 0 | 0 | 31902.05 | 4022.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524 | 13040 | 006K9UkQvVdwDLCWS1 | FALSE
23-PC-37590 | On-Call: Rushgrass Draw Water Main Environmental Review Support | Fixed fee | In Progress | L8110 | E31073 | Stonebridge Utilities | 61.13% | 46500 | 28425.45 | 36232.8 | 0 | 0 | 28425.45 | 3765.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387 | 15036 | 006JdxoeRzZW0aHIgO | TRUE
23-PC-37642 | Quail Run Solar Curation | Fixed fee | Final Billing/Invoice | L8110 | E31068 | Harborlight Water District | 100% | 286500 | 286500 | 185422.8 | 0 | 0 | 286500 | 14817.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2263 | 11739 | 0068OGSlTI7jFpIy4o | FALSE
23-PC-37648 | Phase III: Thistle Down Mixed-Use Development Phase I Survey | Time and material | Final Billing/Invoice | L8110 | E31073 | Clearwater Resources Corp. | 100% | 49100 | 33388 | 32995.2 | 0 | 0 | 33388 | 2729.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389 | 11004 | 006bpXI8wJvnZ5hKLe | FALSE
23-PC-37740 | Sandpiper Trail Archaeological Testing | Fixed fee | Final Billing/Invoice | L8110 | E31068 | Brightwater Utilities | 100% | 33900 | 33900 | 20068.8 | 0 | 0 | 33900 | 1404.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 10408 | 006rpMvibYYfb3zTbq | FALSE
23-PC-37763 | Bramble Creek School Campus - Environmental Review Support | Time and material | In Progress | L8110 | E31068 | Mesa Verde Pipeline Company | 0% | 35000 | 23800 | 25056.5 | 0 | 0 | 23800 | 3180.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 13320 | 006q7AJxz40dtCz63W | FALSE
23-PC-38089 | Lone Pine Wastewater Plant - Phase I Survey | Fixed fee | In Progress | L8120 | E31079 | Stonebridge Land Company | 68.24% | 110100 | 75132.24 | 84001.75 | 0 | 0 | 75132.24 | 5560.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1984 | 14975 | 006pz6FAtRJye35Hse | TRUE
23-PC-38159 | Badger Hollow Data Recovery | Time and material | Completed | L8120 | E31079 | Northfield Telecom Holdings | 100% | 8000 | 5440 | 5319.2 | 0 | 0 | 5440 | 634.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13631 | 006KYFkeYxezr9cSnR | FALSE
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | Time and material | In Progress | L8120 | E31079 | Ridgeline Renewables LLC | 0% | 128200 | 87176 | 90073.32 | 0 | 0 | 87176 | 9289.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 14493 | 0066cdHD54E7fwXf5S | FALSE
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8120 | E31079 | Ironbridge Development Group | 72.58% | 79800 | 57918.84 | 53434.08 | 0 | 0 | 57918.84 | 5546.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 12618 | 006y8g0bwIVepmiZxP | FALSE
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | Fixed fee | In Progress | L8130 | E31110 | High Plains County | 83.54% | 67700 | 56556.58 | 44688.77 | 0 | 0 | 56556.58 | 5711.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682 | 11980 | 0069ElDmZQ6fmHUdcc | FALSE
23-PC-38520 | On-Call: Larkspur Park Improvements Built Environment Survey | Time and material | In Progress | L8130 | E31095 | High Plains Renewables LLC | 0% | 148500 | 100980 | 97074.45 | 0 | 0 | 100980 | 10005.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 12128 | 006IOzQXD6ghAAt5Ro | FALSE
23-PC-38666 | Tamarack Paleontological Monitoring | Fixed fee | In Progress | L8130 | E31088 | Coastal County | 54.44% | 390300 | 212479.32 | 243898.47 | 0 | 0 | 212479.32 | 10489.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3241 | 11118 | 006YjnIoGUp3PK8OpV | TRUE
23-PC-38759 | Saltgrass Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | L8130 | E31107 | Stonebridge Utilities | 0% | 52400 | 35632 | 36847.68 | 0 | 0 | 35632 | 6661.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 15036 | 006OwfACFmdUAoRc93 | FALSE
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | Fixed fee | In Progress | L8130 | E31107 | Prairie Wind County | 79.49% | 109400 | 86962.06 | 83089.3 | 0 | 0 | 86962.06 | 11954.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032 | 13978 | 006iGCOEiAXZ0Ve5XV | FALSE
23-PC-39011 | Fern Valley Solar Curation | Time and material | Final Billing/Invoice | L8130 | E31107 | Mesa Verde Port Authority | 100% | 189300 | 128724 | 142126.44 | 0 | 0 | 128724 | 20254.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303 | 13374 | 006UP4KFsH7WbFnAEc | FALSE
23-PC-39063 | Task Order 21: Badger Hollow Substation Historic Resources Evaluation | Time and material | Lab/Curation | L8130 | E31097 | Stonebridge Utilities | 0% | 24200 | 16456 | 17235.24 | 0 | 0 | 16456 | 1291.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15036 | 006uyCVGLReexmcIPI | FALSE
23-PC-39111 | On-Call: Sage Flat Housing Development Section 106 Consultation | Time and material | Final Billing/Invoice | L8130 | E31095 | Clearwater Builders | 100% | 414500 | 281860 | 281113.9 | 0 | 0 | 281860 | 42359.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2736 | 10855 | 006xEQVgbN87Mt0ivw | FALSE
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | Fixed fee | In Progress | L8130 | E31105 | Heartland Transit Authority | 74.74% | 27800 | 20777.72 | 18214.56 | 0 | 0 | 20777.72 | 1660.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 11878 | 006YiEl5GqXphTysOn | FALSE
23-PC-39280 | Eagle Bend Architectural History Survey | Fixed fee | Final Billing/Invoice | L8130 | E31092 | Clearwater Resources Corp. | 100% | 122700 | 122700 | 84258.09 | 0 | 0 | 122700 | 8709.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705 | 11004 | 006hAjQkxZuy2TzgVx | TRUE
23-PC-39323 | Silver Lake Battery Storage Class III Survey | Fixed fee | In Progress | L8130 | E31107 | Blue Mesa Environmental Consultants | 76.85% | 550600 | 423136.1 | 444994.92 | 0 | 0 | 423136.1 | 36935.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6352 | 10083 | 006dehZ6uO92lXQAPe | FALSE
23-PC-39502 | Ember Valley Housing Development - Phase II Testing | Time and material | Final Billing/Invoice | L8130 | E31095 | High Plains Engineering, Inc. | 100% | 352700 | 239836 | 238918.98 | 0 | 0 | 239836 | 21431.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3268 | 12054 | 006dEdggFBFSMg4R7L | FALSE
23-PC-39608 | Tansy Flat Historic Resources Evaluation | Time and material | Completed | L8130 | E31088 | Ridgeline Rail Partners | 100% | 166700 | 113356 | 118140.29 | 0 | 0 | 113356 | 20379.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14455 | 006CuYYQSgdrF48L1l | FALSE
23-PC-39840 | Kestrel Butte Cell Tower - Curation | Time and material | In Progress | L8130 | E31088 | Stonebridge Builders | 0% | 237700 | 164750.75 | 173575 | 0 | 0 | 164750.75 | 16597.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867 | 14860 | 006JLTprfNeGLNTm8B | FALSE
23-PC-39856 | Phase II: Thistle Down Transmission Line Historic Resources Evaluation | Fixed fee | Final Reporting/Review | L8130 | E31088 | Blue Mesa Resources Corp. | 51.17% | 91300 | 46718.21 | 72285.79 | 0 | 0 | 46718.21 | 3143.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1044 | 10225 | 006ICV4o7e2912dCLj | FALSE
23-PC-39857 | Copper Flats Highway Widening - Environmental Review Support | Fixed fee | In Progress | L8130 | E31088 | Ridgeline Renewables LLC | 58.49% | 69000 | 40358.1 | 58157.02 | 0 | 0 | 40358.1 | 2040.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14493 | 006IMsqqXcBpZGW7Fs | FALSE
23-PC-39918 | Elk Meadow Transmission Line - Data Recovery | Time and material | Completed | L8130 | E31092 | Canyon Rail Partners | 100% | 75300 | 51204 | 51437.43 | 0 | 0 | 51204 | 8406.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 10579 | 0065trwnD3tkYG1ENe | FALSE
23-PC-39996 | Plover Cove Trail - Data Recovery | Fixed fee | On Hold | L8130 | E31088 | Pioneer Power Cooperative | 64.88% | 611900 | 397000.72 | 419273.88 | 0 | 0 | 397000.72 | 34548.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6615 | 13831 | 006gscWNQAeSJOVF5F | FALSE
23-PC-40028 | Phase II: Sumac Ridge Mixed-Use Development Section 106 Consultation | Fixed fee | In Progress | L8130 | E31088 | Sunrise Planning Associates | 67.3% | 100900 | 67905.7 | 70256.67 | 0 | 0 | 67905.7 | 6430.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15406 | 006dM0j0j7cR3DZQOi | FALSE
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | Time and material | In Progress | L8130 | E31092 | Blue Mesa Port Authority | 0% | 119500 | 103480.5 | 80196.45 | 0 | 0 | 103480.5 | 15142.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374 | 10214 | 006ASFe25zqoi18y8L | FALSE
23-PC-40150 | Juniper Wash Curation | Time and material | In Progress | L8140 | E31122 | Timberline Telecom Holdings | 0% | 114700 | 90325.75 | 73316.24 | 0 | 0 | 90325.75 | 9572.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388 | 15690 | 006IGMrBucsb2covIy | FALSE
23-PC-40387 | Copper Flats Trail Paleontological Monitoring | Fixed fee | Lab/Curation | L8140 | E31121 | Redtail Engineering, Inc. | 56.72% | 145000 | 82244 | 97266 | 0 | 0 | 82244 | 6731.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547 | 14233 | 006mQq94BxjIo0yOyp | FALSE
23-PC-40402 | Pebble Beach Road Architectural History Survey | Fixed fee | In Progress | L8140 | E31121 | Blue Mesa Energy Partners | 80.95% | 411600 | 333190.2 | 302937.6 | 0 | 0 | 333190.2 | 53951.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3909 | 10054 | 006BZ9Pld3okdfEi8L | FALSE
23-PC-40406 | Maple Fork Airport Apron Environmental Review Support | Time and material | In Progress | L8140 | E31121 | Mesa Verde Planning Associates | 0% | 60100 | 40868 | 40631.14 | 0 | 0 | 40868 | 3635.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13344 | 006AanN5hrssoQpbOl | FALSE
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | Fixed fee | In Progress | L8140 | E31122 | Lakecrest Development Group | 71.46% | 53900 | 38516.94 | 40910.1 | 0 | 0 | 38516.94 | 6255.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 12986 | 006zVR6719PNcTetY3 | TRUE
23-PC-40493 | Phase III: Quail Run Rail Siding Phase I Survey | Fixed fee | In Progress | L8140 | E31122 | Sunrise Development Group | 63.18% | 84700 | 53513.46 | 57130.15 | 0 | 0 | 53513.46 | 5269.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681 | 15389 | 006kojvx7F611JkwBJ | FALSE
23-PC-40519 | Windmill Flat Mixed-Use Development - Class III Survey | Fixed fee | In Progress | L8140 | E31127 | Highland Builders | 72.01% | 194700 | 140203.47 | 157875.18 | 0 | 0 | 140203.47 | 17622.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257 | 12199 | 006c2W4f1m2EclcLdk | FALSE
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Fixed fee | Lab/Curation | L8140 | E31121 | Clearwater Builders | 100% | 76500 | 76500 | 58746.94 | 0 | 0 | 76500 | 9801.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 10855 | 006VxI1NNWowLCvQH6 | FALSE
23-PC-40627 | Ember Valley Solar - Phase I Survey | Fixed fee | In Progress | L8140 | E31121 | Canyon Utilities | 61.94% | 71300 | 44163.22 | 38273.84 | 0 | 0 | 44163.22 | 2512.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 0065xkGOtfhyF0sJjg | TRUE
23-PC-40688 | Sparrow Hill Historic Resources Evaluation | Time and material | On Hold | L8150 | E31150 | Harborlight Port Authority | 0% | 70500 | 47940 | 43731.15 | 0 | 0 | 47940 | 5856.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711 | 11691 | 0060saZY3sV00CaksP | FALSE
23-PC-40963 | Wildrye Archaeological Testing | Fixed fee | On Hold | L8150 | E31138 | Lakecrest Pipeline Company | 69.84% | 58000 | 40507.2 | 34689.8 | 0 | 0 | 40507.2 | 3706.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 13006 | 006zFh87B5vqf5KZ4A | FALSE
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | Time and material | In Progress | L8150 | E31141 | Mesa Verde County | 0% | 56300 | 38284 | 42714.81 | 0 | 0 | 38284 | 10261.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676 | 13234 | 006UixBQd9nGpYFVUm | FALSE
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | Fixed fee | In Progress | L8150 | E31150 | Canyon Utilities | 75.15% | 33100 | 24874.65 | 29128 | 0 | 0 | 24874.65 | 2364.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496 | 10611 | 006dRBeFoDBP5e0kJI | FALSE
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Fixed fee | Cost Tracking on Closed Project | L8150 | E31138 | Sunrise Water District | 100% | 349600 | 349600 | 221087.04 | 0 | 0 | 349600 | 20169.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4274 | 15575 | 006FTkkWhKlcjuHl9R | FALSE
23-PC-41314 | Raven Rock Transmission Line - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8150 | E31150 | Lakecrest Power Cooperative | 72.58% | 38800 | 28161.04 | 29503.45 | 0 | 0 | 28161.04 | 3789.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13081 | 0063tfeIi2YhqjEN5D | FALSE
23-PC-41361 | Juniper Wash Substation - Cultural Resources Assessment | Time and material | Final Billing/Invoice | L8150 | E31151 | Mesa Verde Pipeline Company | 100% | 240700 | 163676 | 180645.35 | 0 | 0 | 163676 | 19544.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2473 | 13320 | 0066vVHNA7TKX9vtEs | FALSE
23-PC-41378 | Thistle Down Cultural Resources Assessment | Fixed fee | In Progress | L8150 | E31137 | Granite State Resources Corp. | 55.92% | 170800 | 95511.36 | 91151.1 | 0 | 0 | 95511.36 | 8971.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11571 | 006WMaHVy3hUayB5pH | FALSE
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | Fixed fee | Transferred Entity | L8150 | E31137 | Riverstone Port Authority | 70.14% | 132000 | 92584.8 | 108108 | 0 | 0 | 92584.8 | 12739.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14640 | 0068vM3LQ1GwTodnFb | FALSE
23-PC-41429 | Meadowlark Housing Development - Phase II Testing | Time and material | In Progress | L8150 | E31137 | Lakecrest Power Cooperative | 0% | 1924200 | 1308456 | 1334625.12 | 0 | 0 | 1308456 | 112389.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18838 | 13081 | 0065lYiaN8LqVjLmQm | FALSE
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Fixed fee | Lab/Curation | L8150 | E31151 | Blue Mesa Infrastructure Group | 93.4% | 755000 | 705170 | 444695 | 0 | 0 | 705170 | 52746.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6838 | 10139 | 006yWwy45ejg9JH0bF | FALSE
23-PC-41613 | Tamarack School Campus Archaeological Testing | Fixed fee | In Progress | L8150 | E31141 | Highland Planning Associates | 84.7% | 151900 | 128659.3 | 105099.61 | 0 | 0 | 128659.3 | 14865.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394 | 12340 | 006FRKJjyhercNAkvH | FALSE
23-PC-41787 | Copper Flats Phase I Survey | Time and material | Completed | L8160 | E31170 | Canyon Planning Associates | 100% | 48000 | 32640 | 31929.6 | 0 | 0 | 32640 | 4917.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10525 | 0067k8xYFx9g0OHcNE | FALSE
23-PC-41802 | Plover Cove Paleontological Monitoring | Fixed fee | In Progress | L8160 | E31167 | Timberline Planning Associates | 65.48% | 102400 | 67051.52 | 66672.64 | 0 | 0 | 67051.52 | 9517.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017 | 15643 | 006XSbqUTib7UdPg6s | FALSE
23-PC-41827 | Task Order 9: Dove Canyon Bridge Replacement Section 106 Consultation | Fixed fee | In Progress | L8160 | E31170 | Highland Construction Co. | 58.16% | 646100 | 375771.76 | 414881.21 | 0 | 0 | 375771.76 | 47293.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4362 | 12239 | 006g4vZfo8dwcjc94n | FALSE
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | Time and material | In Progress | L8160 | E31173 | Ironbridge Construction Co. | 0% | 18800 | 12784 | 12705.04 | 0 | 0 | 12784 | 2216.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 12523 | 006wOIhPsklPxfoJi3 | FALSE
23-PC-41934 | Sea Oat Bridge Replacement - GIS Mapping | Fixed fee | Final Reporting/Review | L8160 | E31170 | Prairie Wind Transit Authority | 57.28% | 364700 | 208900.16 | 228812.78 | 0 | 0 | 208900.16 | 14548.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3661 | 14127 | 006np9DuKLVtwCWNoS | FALSE
23-PC-42054 | Task Order 25: Meadowlark Water Main Curation | Time and material | Completed | L8160 | E31170 | Westwind County | 100% | 35600 | 24208 | 24350.4 | 0 | 0 | 24208 | 2532.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 15753 | 006mzKkya0ofYZtcl5 | FALSE
23-PC-42154 | Task Order 25: Goldfinch School Campus Section 106 Consultation | Time and material | Final Reporting/Review | L8160 | E31170 | High Plains Environmental Consultants | 0% | 29200 | 19856 | 20127.56 | 0 | 0 | 19856 | 1843.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 12089 | 006LI7UUrwKCeM2XmH | FALSE
23-PC-42199 | Sandpiper Highway Widening GIS Mapping | Fixed fee | Completed | L8160 | E31170 | Blue Mesa Port Authority | 100% | 270200 | 270200 | 196621.63 | 0 | 0 | 270200 | 19919.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10214 | 006oWnjEwmbHGCS59t | FALSE
23-PC-42237 | Foxglove Historic Resources Evaluation | Time and material | In Progress | L8170 | E31175 | Keystone Energy Partners | 0% | 82300 | 55964 | 55519.51 | 0 | 0 | 55964 | 1848.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157 | 12804 | 006SAe8r5id2L6QDob | FALSE
23-PC-42377 | Sumac Ridge Curation | Fixed fee | In Progress | L8170 | E31179 | Blue Mesa Resources Corp. | 57.23% | 68300 | 39088.09 | 47215.79 | 0 | 0 | 39088.09 | 4134.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10225 | 006IBAmfV4JNBLSHen | TRUE
23-PC-42405 | Task Order 23: Silver Lake Levee Repair Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8170 | E31179 | Highland Infrastructure Group | 100% | 757500 | 757500 | 494268.75 | 0 | 0 | 757500 | 105699.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8170 | 12316 | 006kXKGOFkDAvJjlx3 | FALSE
23-PC-42451 | Phase I: Oak Terrace Cell Tower Data Recovery | Time and material | In Progress | L8170 | E31179 | High Plains Environmental Consultants | 0% | 101800 | 69224 | 72208.06 | 0 | 0 | 69224 | 9067.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847 | 12089 | 006VnQo9ImZoQmFFAZ | FALSE
23-PC-42496 | Silver Lake Paleontological Monitoring | Fixed fee | Completed | L8170 | E31179 | Evergreen Power Cooperative | 100% | 254000 | 254000 | 143230.6 | 0 | 0 | 254000 | 18998.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807 | 11431 | 006frEUJwXJvoYk7pE | FALSE
23-PC-42771 | Redbud Housing Development GIS Mapping | Fixed fee | In Progress | L8180 | E31185 | Coastal Planning Associates | 75.89% | 25200 | 19124.28 | 18799.2 | 0 | 0 | 19124.28 | 2254.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 11250 | 006ka4eO0ORA7qsiqC | TRUE
23-PC-42907 | Heron Marsh Historic Resources Evaluation | Fixed fee | In Progress | L8180 | E31188 | High Plains County | 64.58% | 1637200 | 1057303.76 | 977458.87 | 0 | 0 | 1057303.76 | 85213.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11980 | 006IuVIDm1MFGksLAE | TRUE
23-PC-42981 | Hawk Point Architectural History Survey | Fixed fee | In Progress | L8180 | E31185 | Pioneer County | 75.77% | 175800 | 133203.66 | 129494.28 | 0 | 0 | 133203.66 | 12069.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13727 | 006mZgfnvMAdd2X1cK | FALSE
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | Time and material | In Progress | L8180 | E31188 | Summit Infrastructure Group | 0% | 139700 | 94996 | 93543.12 | 0 | 0 | 94996 | 14683.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1018 | 15147 | 006FbdeMu0UxWmc7Jx | FALSE
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | Fixed fee | In Progress | L8190 | E31192 | Silverline Water District | 90.81% | 73300 | 66563.73 | 53362.4 | 0 | 0 | 66563.73 | 8141.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805 | 14839 | 006H46Q6Yd2sWlEHtW | FALSE
23-PC-43209 | Sea Oat Harbor Dredging Curation | Fixed fee | In Progress | L8200 | E31196 | Summit Transit Authority | 55.39% | 247500 | 137090.25 | 178398 | 0 | 0 | 137090.25 | 16401.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850 | 15291 | 0063yrfKAVpM8F6MRO | TRUE
23-PC-43238 | Thistle Down Fiber Route - Data Recovery | Fixed fee | In Progress | L8200 | E31200 | Clearwater Planning Associates | 62.3% | 454300 | 283028.9 | 287491.13 | 0 | 0 | 283028.9 | 25431.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10938 | 0066fKCH9weyPmhG9R | FALSE
23-PC-43356 | Granite Pass Wastewater Plant - Phase II Testing | Fixed fee | Final Billing/Invoice | L8200 | E31196 | Coastal Land Company | 100% | 66500 | 66500 | 43863.4 | 0 | 0 | 66500 | 7033.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 11195 | 006nAPlL18ahWyv1ei | FALSE
23-PC-43408 | Wildrye Solar - Built Environment Survey | Time and material | In Progress | L8200 | E31199 | Redtail Water District | 0% | 176300 | 119884 | 121964.34 | 0 | 0 | 119884 | 14353.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14359 | 006n8tn6KBbxkXY1fo | FALSE
23-PC-43477 | On-Call: Meadowlark Levee Repair Cultural Resources Monitoring | Time and material | Completed | L8200 | E31199 | Pioneer Power Cooperative | 100% | 69800 | 47464 | 51233.2 | 0 | 0 | 47464 | 10229.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13831 | 00656UXq8DAsiuvZzr | FALSE
23-PC-43564 | Willow Springs Levee Repair - Curation | Fixed fee | Final Billing/Invoice | L8200 | E31199 | Silverline Water District | 100% | 277000 | 277000 | 174842.4 | 0 | 0 | 277000 | 22570.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14839 | 006Hebc0iHKcRqsaB6 | FALSE
23-PC-43612 | Maple Fork Wind Farm Class III Survey | Time and material | In Progress | L8200 | E31196 | Granite State Development Group | 0% | 201800 | 137224 | 135120.77 | 0 | 0 | 137224 | 14133.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1451 | 11469 | 006vrMsWuwpzoEK1Zd | FALSE
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | Fixed fee | In Progress | L8210 | E31206 | Pioneer Renewables LLC | 81.15% | 112600 | 91374.9 | 77637.7 | 0 | 0 | 91374.9 | 7308.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872 | 13869 | 0064Trt20ptCVpE8jy | FALSE
23-PC-43788 | Sandpiper Cell Tower - GIS Mapping | Fixed fee | Final Billing/Invoice | L8210 | E31207 | Keystone Environmental Consultants | 100% | 57800 | 57800 | 39628.4 | 0 | 0 | 57800 | 3964.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 12815 | 006poXpAaMuk1VXmHQ | TRUE
23-PC-43811 | Phase I: Thistle Down Fiber Route Section 106 Consultation | Fixed fee | On Hold | L8210 | E31209 | Stonebridge County | 57.72% | 34600 | 19971.12 | 28596.9 | 0 | 0 | 19971.12 | 1650.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14884 | 006Xb5Qtpd1UEWLPZb | FALSE
23-PC-43829 | Task Order 34: Ember Valley Wastewater Plant Architectural History Survey | Fixed fee | In Progress | L8210 | E31205 | Sunrise Development Group | 60.07% | 166500 | 100016.55 | 125557.65 | 0 | 0 | 100016.55 | 11313.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154 | 15389 | 00612Dyy9gtDvn048W | TRUE
23-PC-44023 | Phase I: Sandpiper Pipeline Archaeological Testing | Time and material | Transferred Entity | L8220 | E31218 | Ridgeline Water District | 0% | 299200 | 203456 | 196796.95 | 0 | 0 | 203456 | 29329.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565 | 14577 | 006X3ySFE82yd256LB | FALSE
23-PC-44147 | Phase II: Wren Hollow Harbor Dredging Historic Resources Evaluation | Fixed fee | Transferred Entity | L8220 | E31218 | Evergreen Development Group | 100% | 138100 | 138100 | 115907.33 | 0 | 0 | 138100 | 13465.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11371 | 006mJM1OHTH5UU3zRS | FALSE
24-PC-30017 | Sparrow Hill Data Recovery | Time and material | Final Billing/Invoice | L8000 | E30900 | Cardinal Environmental Consultants | 100% | 24800 | 10788 | 17553.44 | 0 | 0 | 10788 | 1917.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678 | 006ckGsGZWP98jYiuX | FALSE
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | Fixed fee | In Progress | L8000 | E30904 | Summit Port Authority | 100% | 93300 | 90265.16 | 59544.06 | 5807.39 | 2355.2 | 93300 | 14618.6 | 1968.66 | 0 | 3034.84 | 0 | 3034.84 | 0 | 37.5 | 6 | 1332 | 15239 | 006hvBm3lIHHvPp2ry | FALSE
24-PC-30378 | Phase III: Eagle Bend Rail Siding Class III Survey | Fixed fee | Completed | L8000 | E30905 | Blue Mesa Infrastructure Group | 100% | 133000 | 133000 | 107304.4 | 0 | 0 | 133000 | 10816.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659 | 10139 | 006kq0MnWWvQY9Dbk4 | TRUE
24-PC-30448 | Maple Fork Substation - Data Recovery | Fixed fee | In Progress | L8000 | E30907 | Brightwater Rail Partners | 68.52% | 142600 | 97709.52 | 105894.76 | 0 | 0 | 97709.52 | 6747.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 10392 | 006jd7ZdsZzolDmBl3 | TRUE
24-PC-30509 | On-Call: Yarrow Point Mine Expansion Cultural Resources Monitoring | Fixed fee | Lab/Curation | L8000 | E30904 | High Plains Renewables LLC | 61.14% | 682700 | 417402.78 | 517281.79 | 0 | 0 | 417402.78 | 41749.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7437 | 12128 | 006TKgnPPlZkHfyS5S | FALSE
24-PC-30620 | Task Order 31: Sumac Ridge Trail GIS Mapping | Fixed fee | Lab/Curation | L8010 | E30913 | Redtail Water District | 84.99% | 104400 | 88729.56 | 78268.68 | 0 | 0 | 88729.56 | 9046.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14359 | 0062laoDK7wFHQNPs1 | FALSE
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | Fixed fee | In Progress | L8010 | E30913 | Cardinal Utilities | 100% | 60600 | 60600 | 45577.26 | 0 | 0 | 60600 | 3035.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 10833 | 006AKjQP47Yncfz9yo | FALSE
24-PC-30751 | Windmill Flat Section 106 Consultation | Fixed fee | In Progress | L8010 | E30913 | Silverline Water District | 69.73% | 90800 | 63314.84 | 72034.09 | 0 | 0 | 63314.84 | 5575.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1122 | 14839 | 006JU6Zo0ABmUjuRxc | FALSE
24-PC-30843 | North Fork Highway Widening - Built Environment Survey | Time and material | Final Billing/Invoice | L8010 | E30916 | Brightwater Utilities | 100% | 108600 | 73848 | 82210.2 | 0 | 0 | 73848 | 8663.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1541 | 10408 | 006xm8XfOQtYpjOnDJ | FALSE
24-PC-30850 | Tamarack Transmission Line - Data Recovery | Time and material | Final Reporting/Review | L8010 | E30916 | Redtail Infrastructure Group | 0% | 991800 | 674424 | 689995.26 | 0 | 0 | 674424 | 75842.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8332 | 14267 | 0069Xy9bgURx58mokY | FALSE
24-PC-31134 | Blue Heron Built Environment Survey | Time and material | On Hold | L8020 | E30935 | Stonebridge County | 0% | 59300 | 40324 | 41670.11 | 0 | 0 | 40324 | 4315.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502 | 14884 | 006Wm7fWjCvOQwBp3b | FALSE
24-PC-31224 | Quail Run Harbor Dredging - Architectural History Survey | Fixed fee | Final Billing/Invoice | L8020 | E30942 | Blue Mesa Port Authority | 100% | 64800 | 64800 | 37720.08 | 0 | 0 | 64800 | 8090.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478 | 10214 | 006K6CWkfvqXg4E8dX | FALSE
24-PC-31267 | Coyote Springs Built Environment Survey | Fixed fee | On Hold | L8020 | E30937 | Sunrise County | 63.27% | 97500 | 61688.25 | 73905 | 0 | 0 | 61688.25 | 3787.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492 | 15336 | 0061YIZHhmDKpzckOn | FALSE
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Time and material | Cost Tracking on Closed Project | L8020 | E30942 | Lakecrest Construction Co. | 0% | 94000 | 63920 | 65640.2 | 0 | 0 | 63920 | 8132.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164 | 12952 | 0069KzihqqS8gm2UQ1 | FALSE
24-PC-31358 | Dove Canyon Archaeological Testing | Fixed fee | Final Reporting/Review | L8020 | E30925 | Mesa Verde Planning Associates | 96.22% | 595100 | 572605.22 | 484590.9 | 0 | 0 | 572605.22 | 66673.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6789 | 13344 | 006Odg0ibc8yU4tE3o | FALSE
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | Fixed fee | In Progress | L8020 | E30923 | Cardinal Port Authority | 73.27% | 18200 | 13335.14 | 12417.86 | 0 | 0 | 13335.14 | 1464.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 10753 | 006R7vFizrwzemneiu | TRUE
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | Time and material | In Progress | L8020 | E30936 | Ironbridge Engineering, Inc. | 0% | 18300 | 12444 | 11931.6 | 0 | 0 | 12444 | 2004.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 12649 | 006nsXqg2BekOVVKzV | FALSE
24-PC-31503 | North Fork Wind Farm Curation | Time and material | Lab/Curation | L8020 | E30942 | Pioneer Power Cooperative | 0% | 129900 | 88332 | 87825.39 | 0 | 0 | 88332 | 18569.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1437 | 13831 | 006ZmLACK3MmRwZ2i6 | FALSE
24-PC-31514 | On-Call: Harbor View Highway Widening Curation | Fixed fee | Final Billing/Invoice | L8020 | E30936 | Stonebridge Land Company | 100% | 111700 | 111700 | 98296 | 0 | 0 | 111700 | 16946.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14975 | 00606N17qxmieTEmNc | TRUE
24-PC-31534 | Willow Springs Wastewater Plant - Architectural History Survey | Fixed fee | Completed | L8020 | E30925 | Clearwater Port Authority | 100% | 156900 | 156900 | 93967.41 | 0 | 0 | 156900 | 20937.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344 | 10969 | 006ktcYiuTbDm558SV | FALSE
24-PC-31663 | Fern Valley Section 106 Consultation | Fixed fee | In Progress | L8020 | E30923 | Evergreen Power Cooperative | 83.36% | 52600 | 43847.36 | 37714.2 | 0 | 0 | 43847.36 | 2609.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487 | 11431 | 006SQD3PNYdvFLiqNe | FALSE
24-PC-31750 | Kestrel Butte Park Improvements - Phase I Survey | Fixed fee | Final Reporting/Review | L8020 | E30937 | Highland Telecom Holdings | 84.56% | 257200 | 212721.72 | 200024.44 | 9912.79 | 3899 | 217488.32 | 19450.38 | 546.03 | 0 | 4766.6 | 0 | 4766.6 | 0 | 13.25 | 0 | 2056 | 12458 | 0069NnBKYWJWu1hGOB | TRUE
24-PC-31819 | Plover Cove Reservoir - Curation | Time and material | Final Reporting/Review | L8020 | E30936 | Summit Renewables LLC | 0% | 38600 | 26248 | 26703.48 | 0 | 0 | 26248 | 3057.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 15274 | 006XpS9E1UBbOJLcRl | FALSE
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | Time and material | In Progress | L8020 | E30936 | Sunrise Telecom Holdings | 0% | 15200 | 10871.15 | 10676.48 | 0 | 0 | 10871.15 | 1563.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 15492 | 006YiGrZ7huN8ZMlUP | FALSE
24-PC-31924 | Cedar Hollow Wind Farm - Cultural Resources Assessment | Fixed fee | In Progress | L8020 | E30936 | Harborlight Transit Authority | 66.28% | 186800 | 123811.04 | 147262.72 | 0 | 0 | 123811.04 | 12591.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2395 | 11703 | 00661IXfmkBDfguO1x | FALSE
24-PC-32088 | Elk Meadow Phase I Survey | Time and material | In Progress | L8030 | E30958 | Prairie Wind Utilities | 0% | 305100 | 207468 | 228062.25 | 0 | 0 | 207468 | 26055.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5158 | 14159 | 006Sdm3B9G4OkCV127 | FALSE
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | In Progress | L8030 | E30958 | Mesa Verde Planning Associates | 100% | 51800 | 50026.67 | 36731.38 | 2299.62 | 2026.07 | 51800 | 9108.2 | 0 | 0 | 1773.33 | 0 | 1773.33 | 0 | 0 | 0 | 697 | 13344 | 006AtliyhAXNytv0C0 | FALSE
24-PC-32209 | Saltgrass Wastewater Plant - Phase I Survey | Fixed fee | In Progress | L8030 | E30950 | Blue Mesa Pipeline Company | 98.35% | 13000 | 12785.5 | 9029.25 | 0 | 0 | 12785.5 | 1891.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 10171 | 006u5O8Mn2c0cnwhhh | FALSE
24-PC-32210 | Badger Hollow Transmission Line - Class III Survey | Fixed fee | In Progress | L8030 | E30948 | Redtail Infrastructure Group | 69.49% | 114400 | 79496.56 | 91211.12 | 0 | 0 | 79496.56 | 13311.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153 | 14267 | 006E3akpbqwpyrcTQg | FALSE
24-PC-32270 | Creosote Draw School Campus Data Recovery | Time and material | Final Billing/Invoice | L8030 | E30948 | Lakecrest Rail Partners | 100% | 42200 | 28696 | 29472.48 | 0 | 0 | 28696 | 4519.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13111 | 006HvBlLNogZTWPl0H | FALSE
24-PC-32479 | Riverbend Transmission Line Maritime Remote Sensing Survey | Fixed fee | In Progress | L8030 | E30948 | Ridgeline Energy Partners | 66.59% | 94000 | 62594.6 | 66890.4 | 0 | 0 | 62594.6 | 4142.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14433 | 006K0WcngV5doCbyYj | FALSE
24-PC-32591 | Larkspur Fiber Route - Cultural Resources Assessment | Time and material | Final Billing/Invoice | L8030 | E30957 | Summit County | 100% | 41000 | 27880 | 27478.2 | 0 | 0 | 27880 | 7309.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292 | 15070 | 006SYF8bxNGlj2gxxQ | FALSE
24-PC-32640 | Badger Hollow Harbor Dredging Architectural History Survey | Time and material | Transferred Entity | L8030 | E30948 | Canyon Planning Associates | 0% | 39000 | 26520 | 28130.47 | 0 | 0 | 26520 | 2009.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581 | 10525 | 006iuUJBy6CLvArCdM | FALSE
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | L8030 | E30948 | Lakecrest Telecom Holdings | 100% | 84000 | 83888.35 | 70198.8 | 69.79 | 95.2 | 84000 | 10158.04 | 91.8 | 0 | 111.65 | 0 | 111.65 | 0 | 1.75 | 0 | 938 | 13182 | 006qIUSJ1tEiCfX7O0 | FALSE
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | Fixed fee | In Progress | L8030 | E30950 | High Plains County | 86.52% | 51700 | 44730.84 | 45206.48 | 0 | 0 | 44730.84 | 5671.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588 | 11980 | 006b7x3PzEoyLx29bi | TRUE
24-PC-32954 | Redbud Substation - Historic Resources Evaluation | Time and material | In Progress | L8040 | E30967 | Blue Mesa Environmental Consultants | 0% | 331200 | 225216 | 217532.16 | 0 | 0 | 225216 | 14743.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2762 | 10083 | 006hQXzyCayL21L2Uf | FALSE
24-PC-33384 | Phase III: Pine Hollow Rail Siding Maritime Remote Sensing Survey | Time and material | In Progress | L8040 | E30980 | Cardinal Energy Partners | 0% | 288100 | 195908 | 207230.33 | 0 | 0 | 195908 | 18450.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094 | 10648 | 006epkMxwa94RNgmCp | FALSE
24-PC-33394 | Foxglove Park Improvements Cultural Resources Assessment | Time and material | In Progress | L8040 | E30976 | Canyon Construction Co. | 0% | 298200 | 202776 | 197617.14 | 0 | 0 | 202776 | 10237.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3027 | 10448 | 006jpnZEiowzm0xz4z | FALSE
24-PC-33448 | Ember Valley Solar Architectural History Survey | Fixed fee | In Progress | L8040 | E30972 | Mesa Verde Pipeline Company | 82.8% | 681000 | 560235.94 | 419972.7 | 3737.59 | 4888.18 | 563868 | 67464.58 | 2256.21 | 0 | 3632.06 | 0 | 3632.06 | 0 | 50.75 | 3.75 | 6739 | 13320 | 006X1UqT962DyRbvdd | FALSE
24-PC-33531 | North Fork Park Improvements - Curation | Fixed fee | Lab/Curation | L8040 | E30980 | Ironbridge County | 76.08% | 31500 | 23965.2 | 23760.45 | 0 | 0 | 23965.2 | 3308.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 12563 | 006SUSHvAugmAC92lu | FALSE
24-PC-33575 | On-Call: North Fork Trail Architectural History Survey | Time and material | Final Reporting/Review | L8040 | E30972 | Cardinal Utilities | 0% | 589600 | 369763.26 | 433356 | 7743.32 | 8136.96 | 384232.95 | 31872.16 | 4372.88 | 0 | 14469.69 | 0 | 14469.69 | 0 | 102.25 | 0 | 9742 | 10833 | 006tWIxXrmUAIpV8SB | FALSE
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | Fixed fee | In Progress | L8050 | E30987 | Blue Mesa Energy Partners | 92.01% | 64500 | 57224.04 | 49568.25 | 1677 | 867.58 | 59346.45 | 7753.04 | 1666.75 | 0 | 2122.41 | 0 | 2122.41 | 0 | 24.5 | 0 | 431 | 10054 | 0063k3CMx9d2DnyhJu | FALSE
24-PC-33927 | Aspen Ridge Solar Class III Survey | Fixed fee | Final Reporting/Review | L8050 | E30995 | Coastal County | 54.82% | 104000 | 57012.8 | 77001.6 | 0 | 0 | 57012.8 | 8821.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908 | 11118 | 006FfAOxCZ1AjBYxdN | FALSE
24-PC-33981 | Yarrow Point Airport Apron - Phase II Testing | Time and material | Lab/Curation | L8050 | E30995 | Blue Mesa Energy Partners | 0% | 47500 | 36664.5 | 29944 | 0 | 0 | 36664.5 | 5162.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10054 | 006vetSbBCZkCt83jk | FALSE
24-PC-33985 | Thistle Down Substation Curation | Time and material | In Progress | L8050 | E30984 | Ironbridge Telecom Holdings | 0% | 78300 | 53244 | 57863.7 | 0 | 0 | 53244 | 4911.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797 | 12740 | 006E1u51otMCFvk0uf | FALSE
24-PC-34015 | Sea Oat Mixed-Use Development Environmental Review Support | Fixed fee | Final Billing/Invoice | L8050 | E30987 | High Plains Water District | 100% | 16200 | 16200 | 10449 | 0 | 0 | 16200 | 1059.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 12150 | 0068wvNpoyYb8EGzyE | FALSE
24-PC-34211 | Quail Run Substation - Cultural Resources Monitoring | Time and material | On Hold | L8050 | E30998 | Riverstone Port Authority | 0% | 70900 | 48212 | 50537.52 | 0 | 0 | 48212 | 8218.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 14640 | 006M9fjzgO3PwUvnSs | FALSE
24-PC-34263 | Cedar Hollow Airport Apron Section 106 Consultation | Fixed fee | In Progress | L8050 | E30985 | Sunrise Rail Partners | 63.87% | 199300 | 127292.91 | 147800.88 | 0 | 0 | 127292.91 | 8874.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2016 | 15467 | 006x0kuxHYORFuBNxK | FALSE
24-PC-34274 | Lantern Bay Rail Siding - Environmental Review Support | Fixed fee | Completed | L8050 | E30984 | Sunrise Telecom Holdings | 100% | 61900 | 61900 | 48195.34 | 0 | 0 | 61900 | 3492.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 15492 | 006O5hxDZfz9i7xuwy | TRUE
24-PC-34320 | Sage Flat Canal Lining Curation | Fixed fee | In Progress | L8050 | E30995 | Redtail Infrastructure Group | 71.96% | 388400 | 279492.64 | 253927.23 | 0 | 0 | 279492.64 | 26130.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2815 | 14267 | 0067PlK7eUhEgX6CFF | FALSE
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | Time and material | In Progress | L8050 | E30987 | Summit Renewables LLC | 0% | 38700 | 26316 | 26644.95 | 0 | 0 | 26316 | 2366.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15274 | 006Cww504ABLRjBsgK | FALSE
24-PC-34422 | Silver Lake Historic Resources Evaluation | Fixed fee | Completed | L8050 | E30984 | Stonebridge Utilities | 100% | 183900 | 183900 | 106036.74 | 0 | 0 | 183900 | 19436.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15036 | 0066txdSHN48MxUTTG | TRUE
24-PC-34458 | Badger Hollow Built Environment Survey | Time and material | Completed | L8050 | E30992 | Blue Mesa Infrastructure Group | 100% | 78300 | 53244 | 57511.35 | 0 | 0 | 53244 | 6708.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 10139 | 006AtP5IajMKnmPZKV | FALSE
24-PC-34499 | Dove Canyon Trail - GIS Mapping | Time and material | In Progress | L8050 | E31000 | Highland Construction Co. | 0% | 104200 | 70856 | 76427.58 | 0 | 0 | 70856 | 15414.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568 | 12239 | 006jhvMUG2XYh2I6YH | FALSE
24-PC-34593 | Riverbend Park Improvements - Paleontological Monitoring | Fixed fee | In Progress | L8050 | E30992 | Blue Mesa Port Authority | 58.18% | 43500 | 25308.3 | 33447.15 | 0 | 0 | 25308.3 | 3599.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403 | 10214 | 006VzQVubmvlB6WWo7 | FALSE
24-PC-34654 | Timber Gap Phase II Testing | Time and material | Final Reporting/Review | L8050 | E31000 | Harborlight Port Authority | 0% | 115400 | 82899.95 | 87787.28 | 40.46 | 28.04 | 82959.15 | 4281.22 | 54.92 | 0 | 59.2 | 0 | 59.2 | 0 | 1.25 | 0 | 0 | 11691 | 006UxAo1UunvTl2Geq | FALSE
24-PC-34663 | Redbud Airport Apron - GIS Mapping | Time and material | In Progress | L8050 | E30999 | Mesa Verde Pipeline Company | 0% | 505100 | 343468 | 342760.86 | 0 | 0 | 343468 | 49488.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5130 | 13320 | 006HBVrMjtSff8SXo1 | FALSE
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | Time and material | In Progress | L8060 | E31014 | Lakecrest Rail Partners | 0% | 176500 | 120020 | 121414.35 | 0 | 0 | 120020 | 12696.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2269 | 13111 | 006Twfq0jaFZ7AMeok | FALSE
24-PC-34919 | Fern Valley Levee Repair Class III Survey | Fixed fee | Completed | L8060 | E31008 | Cardinal Rail Partners | 100% | 20000 | 20000 | 13582 | 0 | 0 | 20000 | 2269.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 10792 | 006fSQ7QEbJnd9YGj7 | FALSE
24-PC-34975 | Foxglove Fiber Route GIS Mapping | Fixed fee | In Progress | L8060 | E31018 | Ironbridge Telecom Holdings | 85.07% | 205900 | 175159.13 | 181192 | 0 | 0 | 175159.13 | 32521.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2902 | 12740 | 00673RftaVhnURPExm | FALSE
24-PC-35267 | Falcon Mesa Trail - Phase II Testing | Fixed fee | Final Reporting/Review | L8060 | E31008 | Northfield Builders | 58.6% | 56700 | 33226.2 | 42581.7 | 0 | 0 | 33226.2 | 3293.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 13460 | 006eojJHAu1r2MzKIx | FALSE
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | Time and material | In Progress | L8070 | E31032 | Blue Mesa Infrastructure Group | 0% | 301200 | 204816 | 217496.52 | 0 | 0 | 204816 | 19406.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10139 | 006KHge6nkYRIIXbtE | FALSE
24-PC-35419 | Yarrow Point Pipeline - Class III Survey | Time and material | Completed | L8070 | E31029 | Northfield Builders | 100% | 24800 | 16864 | 16359.63 | 0 | 0 | 16864 | 1241.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 13460 | 006tXn8E24AIZ2yoZS | FALSE
24-PC-35474 | Larkspur Curation | Fixed fee | In Progress | L8070 | E31034 | Redtail Water District | 76.88% | 369600 | 284148.48 | 278295.85 | 0 | 0 | 284148.48 | 22679.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6675 | 14359 | 006iiiq00OzZ2k7sVf | FALSE
24-PC-35559 | Phase III: Fern Valley Battery Storage Curation | Fixed fee | Final Reporting/Review | L8070 | E31034 | Ironbridge Port Authority | 85.15% | 218200 | 185797.3 | 144252.02 | 0 | 0 | 185797.3 | 11176.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2249 | 12704 | 006gIgu5SjEKzYF05p | FALSE
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | Fixed fee | In Progress | L8070 | E31034 | Coastal Builders | 75.63% | 119200 | 90150.96 | 88243.76 | 0 | 0 | 90150.96 | 4271.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11038 | 006MuR25IKqqTzFALN | FALSE
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | Time and material | In Progress | L8070 | E31032 | Heartland Power Cooperative | 0% | 69900 | 66597.48 | 49013.31 | 3645.38 | 2428.64 | 69900 | 3716.52 | 1086.03 | 0 | 3302.52 | 0 | 3302.52 | 0 | 22.5 | 0.75 | 1005 | 11841 | 0063aBRNbQIkoYvD6M | FALSE
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | Time and material | In Progress | L8070 | E31032 | Silverline Port Authority | 0% | 225100 | 200102.05 | 153743.3 | 0 | 0 | 200102.05 | 18595.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4322 | 14747 | 006D3EuRE62tD8KAxv | FALSE
24-PC-35881 | Wren Hollow Transmission Line - Architectural History Survey | Fixed fee | Final Billing/Invoice | L8070 | E31029 | Northfield Development Group | 100% | 154200 | 154200 | 112673.94 | 0 | 0 | 154200 | 7910.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704 | 13499 | 006iNPk6HRVJ284fXf | FALSE
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | Fixed fee | In Progress | L8070 | E31034 | Pioneer Transit Authority | 84.18% | 12900 | 10859.22 | 9094.5 | 0 | 0 | 10859.22 | 1064.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 13885 | 006qGZ7IkUyGM36LAh | FALSE
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Fixed fee | Cost Tracking on Closed Project | L8070 | E31032 | Coastal County | 100% | 58300 | 58300 | 39072.66 | 0 | 0 | 58300 | 7419.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662 | 11118 | 0066Hr7Syji3QEgnEY | FALSE
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | Time and material | In Progress | L8070 | E31032 | Heartland Port Authority | 0% | 5700 | 3876 | 4244.79 | 0 | 0 | 3876 | 214.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 11802 | 006PFS6URsM6FSHU4L | FALSE
24-PC-36184 | Juniper Wash Pipeline Maritime Remote Sensing Survey | Fixed fee | On Hold | L8070 | E31034 | Coastal Land Company | 66.56% | 3500 | 2329.6 | 2062.55 | 0 | 0 | 2329.6 | 296.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 11195 | 006lYwFF80qvRb5xla | TRUE
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Fixed fee | Cost Tracking on Closed Project | L8080 | E31044 | Coastal Construction Co. | 92.5% | 56300 | 52077.5 | 37721 | 0 | 0 | 52077.5 | 6280.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604 | 11092 | 006DgBZebjLcWJzuyE | TRUE
24-PC-36445 | Tamarack Archaeological Testing | Time and material | On Hold | L8080 | E31041 | Highland Construction Co. | 0% | 63600 | 43248 | 43330.68 | 0 | 0 | 43248 | 8543.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 12239 | 006FnOLuZoPD2tflT0 | FALSE
24-PC-36559 | Stone Mill Airport Apron - Class III Survey | Fixed fee | Completed | L8080 | E31047 | Brightwater Rail Partners | 100% | 11800 | 11800 | 8903.1 | 0 | 0 | 11800 | 999.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10392 | 0060kia1W37ZEmcaBu | FALSE
24-PC-36620 | Silver Lake Cultural Resources Assessment | Time and material | In Progress | L8090 | E31052 | Sunrise Rail Partners | 0% | 368100 | 290535 | 252295.74 | 0 | 0 | 290535 | 20057.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15467 | 006iy1VHxGNcRYj3kn | FALSE
24-PC-36676 | Task Order 38: Ember Valley Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | L8090 | E31051 | Highland Telecom Holdings | 100% | 93200 | 63376 | 62093.62 | 0 | 0 | 63376 | 7683.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 12458 | 006ceUerHwd0EQKxyg | FALSE
24-PC-36710 | Phase III: Twin Buttes Cell Tower Section 106 Consultation | Fixed fee | On Hold | L8090 | E31050 | Redtail Water District | 67.38% | 138500 | 93321.3 | 97600.95 | 0 | 0 | 93321.3 | 8089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211 | 14359 | 006ZkRRBqkOMbRoSNf | FALSE
24-PC-36932 | Badger Hollow Canal Lining - Section 106 Consultation | Time and material | Final Reporting/Review | L8100 | E31057 | Ridgeline Renewables LLC | 0% | 12200 | 9992.5 | 7733.58 | 0 | 0 | 9992.5 | 694.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 14493 | 006RYGuL6x0zoSRh2Q | FALSE
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | Fixed fee | In Progress | L8100 | E31055 | Clearwater Engineering, Inc. | 100% | 141000 | 141000 | 113970.3 | 0 | 0 | 141000 | 20718.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209 | 10896 | 006cyrS36zaBFjTqwM | TRUE
24-PC-37107 | Hawk Point Mixed-Use Development Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | L8100 | E31063 | Ridgeline Resources Corp. | 67.89% | 259400 | 176106.66 | 186117.89 | 0 | 0 | 176106.66 | 26027.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146 | 14529 | 006Ke1UIaWYPt6Wjo4 | FALSE
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | Fixed fee | In Progress | L8100 | E31063 | Summit Transit Authority | 73.76% | 1259200 | 928785.92 | 853989.44 | 0 | 0 | 928785.92 | 116535.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10052 | 15291 | 006QKUqeVpGMma3Gog | FALSE
24-PC-37167 | Saltgrass Curation | Time and material | Lab/Curation | L8100 | E31057 | Summit Planning Associates | 0% | 65600 | 44608 | 48603.04 | 0 | 0 | 44608 | 5847.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15198 | 006ADuYWsabLK1Pxtr | FALSE
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | Time and material | In Progress | L8100 | E31062 | Sunrise Water District | 0% | 67000 | 51564 | 40709.2 | 0 | 0 | 51564 | 4245.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316 | 15575 | 006G9jFOdVy6jjnfk9 | FALSE
24-PC-37266 | Granite Pass Cell Tower Phase I Survey | Time and material | In Progress | L8100 | E31057 | Lakecrest Power Cooperative | 0% | 41400 | 29169.9 | 24587.46 | 0 | 0 | 29169.9 | 3179.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 13081 | 006Cz1atsqrgNgblyk | FALSE
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | Fixed fee | In Progress | L8100 | E31061 | Redtail Infrastructure Group | 71.38% | 298500 | 213069.3 | 243904.35 | 0 | 0 | 213069.3 | 28377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14267 | 006lf3ChGCb0In9O9p | FALSE
24-PC-37372 | Harbor View Harbor Dredging Paleontological Monitoring | Fixed fee | Final Reporting/Review | L8110 | E31074 | High Plains Renewables LLC | 89.88% | 272100 | 237896.12 | 221924.76 | 5844.44 | 5985.41 | 244563.48 | 18350.25 | 2793.35 | 0 | 6667.36 | 0 | 6667.36 | 0 | 57.5 | 0.25 | 0 | 12128 | 006xfNJMQ9IjN4gZVC | TRUE
24-PC-37415 | Sage Flat Mine Expansion Maritime Remote Sensing Survey | Fixed fee | In Progress | L8110 | E31068 | Blue Mesa Port Authority | 60.73% | 191000 | 115994.3 | 147948.6 | 0 | 0 | 115994.3 | 10602.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10214 | 006nR1toNGg2g0uN9L | TRUE
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | Time and material | In Progress | L8110 | E31070 | Cardinal Environmental Consultants | 0% | 309400 | 210392 | 184093 | 0 | 0 | 210392 | 25851.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678 | 006GKKkM2e48hCocr5 | FALSE
24-PC-37686 | Twin Buttes Mixed-Use Development Paleontological Monitoring | Fixed fee | In Progress | L8110 | E31073 | Riverstone Resources Corp. | 81.79% | 50600 | 41385.74 | 39155.85 | 0 | 0 | 41385.74 | 4195.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490 | 14683 | 006yvWUQG9CbOSzHMT | TRUE
24-PC-37823 | Granite Pass Pipeline Cultural Resources Monitoring | Fixed fee | Lab/Curation | L8110 | E31070 | Blue Mesa Resources Corp. | 72.91% | 28900 | 21070.99 | 21651.88 | 0 | 0 | 21070.99 | 1199.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 10225 | 00691vgneQLfJvjfmT | FALSE
24-PC-37942 | Task Order 39: Meadowlark Mine Expansion Curation | Time and material | Final Reporting/Review | L8110 | E31073 | Redtail Infrastructure Group | 0% | 241400 | 199259.4 | 173542.46 | 0 | 0 | 199259.4 | 25610.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422 | 14267 | 006c10sPhFt0LetpM3 | FALSE
24-PC-38054 | On-Call: Willow Springs Highway Widening GIS Mapping | Fixed fee | Final Reporting/Review | L8120 | E31079 | Silverline Water District | 68.16% | 60700 | 41373.12 | 51516.09 | 0 | 0 | 41373.12 | 2493.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14839 | 006hf3f7YSPluZpAE1 | FALSE
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | Fixed fee | In Progress | L8120 | E31079 | Coastal Land Company | 92.03% | 132200 | 121663.66 | 95580.6 | 0 | 0 | 121663.66 | 10555.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704 | 11195 | 006JR7snX7jctOv3F8 | FALSE
24-PC-38374 | On-Call: Riverbend Highway Widening Archaeological Testing | Time and material | In Progress | L8120 | E31079 | Lakecrest Telecom Holdings | 0% | 481100 | 327148 | 330082.71 | 0 | 0 | 327148 | 25265.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6959 | 13182 | 006xEliYvLiOLuS3uX | FALSE
24-PC-38426 | Elk Meadow Mine Expansion Phase II Testing | Fixed fee | Final Billing/Invoice | L8120 | E31079 | Coastal Land Company | 100% | 203000 | 203000 | 167048.7 | 0 | 0 | 203000 | 35558.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11195 | 006JC2eU7CazqqDzBU | TRUE
24-PC-38469 | Falcon Mesa Harbor Dredging - Built Environment Survey | Fixed fee | In Progress | L8130 | E31105 | Redtail Builders | 80.35% | 656700 | 515845.1 | 435290.48 | 11935.02 | 6202.37 | 527658.45 | 70647.32 | 6209.99 | 0 | 11813.35 | 0 | 11813.35 | 0 | 125.75 | 5.75 | 7103 | 14184 | 006NOFhUFBDXq54R6m | FALSE
24-PC-38486 | Kestrel Butte Phase I Survey | Fixed fee | In Progress | L8130 | E31105 | Summit Engineering, Inc. | 100% | 153600 | 153600 | 105043.81 | 0 | 0 | 153600 | 11147.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1729 | 15125 | 006SGIIYHeyErwU8CW | FALSE
24-PC-38579 | Kestrel Butte Harbor Dredging - Data Recovery | Time and material | Final Billing/Invoice | L8130 | E31092 | Brightwater Power Cooperative | 100% | 59100 | 40188 | 39502.44 | 0 | 0 | 40188 | 2115.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 10363 | 006zmjB5EKheAbl9Nf | FALSE
24-PC-38687 | Lantern Bay GIS Mapping | Time and material | In Progress | L8130 | E31092 | High Plains Renewables LLC | 0% | 68600 | 46648 | 49542.92 | 0 | 0 | 46648 | 4912.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832 | 12128 | 006l9aCcY8m1hJ8bAt | FALSE
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | L8130 | E31095 | Lakecrest Planning Associates | 100% | 168200 | 168200 | 130489.56 | 0 | 0 | 168200 | 19437.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711 | 13040 | 006cB5QeqQbpWXrVdh | FALSE
24-PC-38795 | Meadowlark Class III Survey | Time and material | Final Billing/Invoice | L8130 | E31092 | Pioneer Renewables LLC | 100% | 684500 | 465460 | 462838.34 | 0 | 0 | 465460 | 35014.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8935 | 13869 | 006alqXcUj8KZKYnqD | FALSE
24-PC-38817 | Phase III: Wildrye Fiber Route Built Environment Survey | Fixed fee | Completed | L8130 | E31088 | Ironbridge County | 100% | 1966200 | 1966200 | 1268002.38 | 0 | 0 | 1966200 | 198219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14990 | 12563 | 006qLAaBknJj765n31 | FALSE
24-PC-38847 | Pine Hollow School Campus - Environmental Review Support | Fixed fee | On Hold | L8130 | E31107 | Highland Construction Co. | 65.77% | 118600 | 78003.22 | 93456.8 | 0 | 0 | 78003.22 | 6822.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770 | 12239 | 006DlnAULSExdhhewi | FALSE
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | Fixed fee | In Progress | L8130 | E31110 | Harborlight Water District | 100% | 100200 | 93737.19 | 72685.08 | 4074.09 | 3120.92 | 100200 | 20215.85 | 2655.21 | 0 | 6462.81 | 0 | 6462.81 | 0 | 67 | 0 | 1304 | 11739 | 006QrmIAk3FddHYunb | FALSE
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | Time and material | In Progress | L8130 | E31097 | Stonebridge Utilities | 0% | 126600 | 86088 | 82581.18 | 0 | 0 | 86088 | 3830.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15036 | 006aEFET908fx1kWDS | FALSE
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | Fixed fee | In Progress | L8130 | E31092 | Ironbridge Telecom Holdings | 76.78% | 597800 | 458990.84 | 435557.08 | 0 | 0 | 458990.84 | 21068.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5341 | 12740 | 006dnVSsRVoIDbStGW | FALSE
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Fixed fee | Cost Tracking on Closed Project | L8130 | E31110 | Keystone Energy Partners | 100% | 11000 | 11000 | 7227 | 0 | 0 | 11000 | 995.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 12804 | 006nFPiEydrXFlXv0P | TRUE
24-PC-39405 | Wren Hollow Harbor Dredging - Section 106 Consultation | Time and material | Final Billing/Invoice | L8130 | E31092 | Ridgeline County | 100% | 159700 | 70906.8 | 107248.85 | 0 | 0 | 70906.8 | 5052.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 14393 | 006hkKXfFRqiGW0o1E | FALSE
24-PC-39479 | Granite Pass Solar - Cultural Resources Assessment | Time and material | Final Reporting/Review | L8130 | E31092 | Mesa Verde Land Company | 0% | 233000 | 165185 | 164777.6 | 0 | 0 | 165185 | 10389.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3729 | 13275 | 006cU4i2GSLidbt7ta | FALSE
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | Time and material | In Progress | L8130 | E31107 | Timberline Telecom Holdings | 0% | 33000 | 29186 | 23227.58 | 0 | 0 | 29186 | 5274.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15690 | 006WbMNMeBVgk2MImC | FALSE
24-PC-39533 | Elk Meadow Architectural History Survey | Fixed fee | In Progress | L8130 | E31105 | Silverline Construction Co. | 94.83% | 67000 | 63536.1 | 52641.9 | 0 | 0 | 63536.1 | 3644.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14700 | 006SnrSkCv9h2dxtIs | FALSE
24-PC-39694 | Task Order 35: Sandpiper Trail Historic Resources Evaluation | Time and material | In Progress | L8130 | E31107 | Sunrise Transit Authority | 0% | 136500 | 92820 | 93075.52 | 0 | 0 | 92820 | 10588.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695 | 15537 | 006P4Nl8NhjfCC5phx | FALSE
24-PC-39789 | Meadowlark Airport Apron Archaeological Testing | Fixed fee | On Hold | L8130 | E31095 | Highland Engineering, Inc. | 49.57% | 126000 | 62458.2 | 101029.58 | 0 | 0 | 62458.2 | 4306.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12284 | 006JqT1OUe2JP99V8L | FALSE
24-PC-39822 | On-Call: Redbud Wind Farm Class III Survey | Fixed fee | Completed | L8130 | E31097 | Summit Renewables LLC | 100% | 109500 | 109500 | 87460.32 | 0 | 0 | 109500 | 7662.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225 | 15274 | 0062TCdIutelrfAMgJ | FALSE
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | Fixed fee | In Progress | L8130 | E31088 | Sunrise Transit Authority | 100% | 17800 | 17800 | 14308.95 | 0 | 0 | 17800 | 3019.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 15537 | 006e1Afo3za8B1kNLF | FALSE
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | Time and material | In Progress | L8130 | E31097 | Keystone Planning Associates | 0% | 414900 | 331243.28 | 270722.25 | 11307.29 | 7353.75 | 339174.65 | 17893.93 | 4306.75 | 0 | 7931.37 | 0 | 7931.37 | 0 | 97.5 | 4.25 | 4873 | 12859 | 006Wd4UPctyttQYW73 | FALSE
24-PC-39940 | Riverbend Levee Repair - Curation | Fixed fee | In Progress | L8130 | E31095 | Ironbridge Port Authority | 64.39% | 20400 | 13135.56 | 16397.52 | 0 | 0 | 13135.56 | 865.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 12704 | 006ylhUgybQLFfIZkU | FALSE
24-PC-40067 | Saltgrass Fiber Route Class III Survey | Time and material | In Progress | L8130 | E31095 | Ridgeline County | 0% | 218100 | 148308 | 163684.05 | 0 | 0 | 148308 | 17058.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738 | 14393 | 006L9HuwU6V9ovkBEF | FALSE
24-PC-40078 | Task Order 32: Heron Marsh Highway Widening Paleontological Monitoring | Time and material | Completed | L8140 | E31127 | Summit Engineering, Inc. | 100% | 1820100 | 1237668 | 1155945.51 | 0 | 0 | 1237668 | 156116.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16689 | 15125 | 006uflIIaxl6GD5c1U | FALSE
24-PC-40091 | Stone Mill Canal Lining Curation | Fixed fee | Completed | L8140 | E31128 | Evergreen County | 100% | 121900 | 121900 | 105126.56 | 0 | 0 | 121900 | 22204.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805 | 11354 | 006Qyhvba7La49pFla | FALSE
24-PC-40102 | Redbud Class III Survey | Fixed fee | Final Reporting/Review | L8140 | E31122 | Evergreen County | 100% | 453900 | 453900 | 322187.01 | 0 | 0 | 453900 | 55799.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5462 | 11354 | 006UsLWyEFMBIvWbou | FALSE
24-PC-40218 | North Fork Bridge Replacement - Built Environment Survey | Time and material | In Progress | L8140 | E31128 | Blue Mesa Energy Partners | 0% | 141000 | 95880 | 95626.2 | 0 | 0 | 95880 | 8647.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1169 | 10054 | 006mz8QLxPaEE77yFN | FALSE
24-PC-40271 | Millbrook Rail Siding Phase II Testing | Fixed fee | Final Billing/Invoice | L8140 | E31121 | Pioneer Renewables LLC | 100% | 1146200 | 1146200 | 757124.2 | 0 | 0 | 1146200 | 75644.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12512 | 13869 | 0066kQYfsCG4ynsbVT | FALSE
24-PC-40317 | Sumac Ridge Harbor Dredging Curation | Time and material | In Progress | L8140 | E31128 | Canyon Planning Associates | 0% | 225800 | 153544 | 153318.2 | 0 | 0 | 153544 | 16189.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177 | 10525 | 0069yfI4lfz4xuBMtu | FALSE
24-PC-40427 | On-Call: Harbor View Trail Built Environment Survey | Fixed fee | Completed | L8140 | E31121 | Evergreen Development Group | 100% | 121700 | 121700 | 90556.97 | 0 | 0 | 121700 | 15879.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11371 | 006AZ6vmpT3XEIVaqX | FALSE
24-PC-40479 | Quail Run Rail Siding - Built Environment Survey | Fixed fee | In Progress | L8140 | E31127 | Stonebridge Land Company | 63.78% | 139600 | 89036.88 | 110619.04 | 0 | 0 | 89036.88 | 5644.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 14975 | 006a8lWzz3BH9RFffR | TRUE
24-PC-40561 | Task Order 39: Aspen Ridge Housing Development GIS Mapping | Fixed fee | In Progress | L8140 | E31122 | Prairie Wind Port Authority | 71.34% | 2335800 | 1651216.14 | 1746045.15 | 13828.05 | 6330.56 | 1666359.72 | 119583.94 | 5264.39 | 0 | 15143.58 | 0 | 15143.58 | 0 | 70.75 | 0 | 28964 | 14077 | 006eVSaJW5c0VKOBYz | TRUE
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | Fixed fee | In Progress | L8140 | E31128 | Highland Resources Corp. | 70.91% | 460500 | 326540.55 | 381017.7 | 0 | 0 | 326540.55 | 34582.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12409 | 006iVLbS4abA7XowXz | FALSE
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Fixed fee | Cost Tracking on Closed Project | L8140 | E31121 | Westwind Development Group | 91.85% | 50300 | 46200.55 | 35350.84 | 0 | 0 | 46200.55 | 6331.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408 | 15795 | 006hOsVKzacGR9Q0dk | FALSE
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | L8140 | E31127 | Canyon Planning Associates | 100% | 22100 | 22100 | 17918.68 | 2310.39 | 1323.85 | 22100 | 2116.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 10525 | 006n0CE7SB3X6S8T0o | FALSE
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | Time and material | In Progress | L8150 | E31151 | Lakecrest Construction Co. | 0% | 48400 | 47376.63 | 37137.32 | 1542.91 | 717.73 | 48400 | 8288.42 | 567.31 | 0 | 1023.37 | 0 | 1023.37 | 0 | 13 | 0 | 0 | 12952 | 006L1FBi1R1PcKNoGY | FALSE
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | L8150 | E31137 | Redtail Engineering, Inc. | 100% | 31800 | 31800 | 20975.28 | 0 | 0 | 31800 | 2276.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253 | 14233 | 006Yc4ulSxREC9EZOi | TRUE
24-PC-40836 | Task Order 12: Saltgrass Highway Widening Curation | Fixed fee | On Hold | L8150 | E31151 | Sunrise Planning Associates | 87.46% | 17000 | 14868.2 | 11633.1 | 0 | 0 | 14868.2 | 1505.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 15406 | 0069YwnnUGwRfaHMKy | FALSE
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Fixed fee | Lab/Curation | L8150 | E31138 | Silverline Construction Co. | 100% | 579300 | 579300 | 392475.75 | 0 | 0 | 579300 | 74888.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4511 | 14700 | 006fpoxJsYCAvB5HE0 | TRUE
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8150 | E31138 | Clearwater Engineering, Inc. | 100% | 8800 | 8800 | 6914.16 | 0 | 0 | 8800 | 1555.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10896 | 006WiBK7eY6YqsI68D | TRUE
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | Time and material | In Progress | L8150 | E31151 | Westwind Engineering, Inc. | 0% | 60600 | 41208 | 39983.88 | 0 | 0 | 41208 | 6131.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 15856 | 006XJspjmjxe3wcTbP | FALSE
24-PC-41066 | Task Order 31: Yarrow Point Wind Farm Curation | Time and material | Final Billing/Invoice | L8150 | E31141 | Harborlight County | 100% | 30400 | 17571.2 | 19493.63 | 0 | 0 | 17571.2 | 3536.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 11648 | 006k3yRGjbK49tPBhD | FALSE
24-PC-41067 | On-Call: Goldfinch Wastewater Plant Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | L8150 | E31137 | Summit Transit Authority | 100% | 364100 | 364100 | 243619.31 | 0 | 0 | 364100 | 28130.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3387 | 15291 | 006HbULAveO8d6Dr99 | TRUE
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Fixed fee | Transferred Entity | L8150 | E31151 | Silverline Port Authority | 100% | 18000 | 15244.1 | 12312 | 2118.46 | 648.66 | 18000 | 1795.06 | 64.22 | 0 | 2755.9 | 0 | 2755.9 | 0 | 0.5 | 0 | 109 | 14747 | 006Vz2IQCRuOzCw5IU | FALSE
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | Fixed fee | In Progress | L8150 | E31151 | Brightwater Utilities | 96.25% | 194900 | 187591.25 | 131089.74 | 0 | 0 | 187591.25 | 9084.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 10408 | 00698IghSkK0XEOzs2 | FALSE
24-PC-41534 | Badger Hollow Architectural History Survey | Fixed fee | On Hold | L8150 | E31137 | Lakecrest Construction Co. | 58.82% | 795200 | 467736.64 | 579859.84 | 0 | 0 | 467736.64 | 54911.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12952 | 006zcV9yqzd9cwODb4 | FALSE
24-PC-41555 | Phase III: Pine Hollow Solar Built Environment Survey | Time and material | Final Billing/Invoice | L8150 | E31151 | Heartland Transit Authority | 100% | 38200 | 25976 | 27011.22 | 0 | 0 | 25976 | 3909.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 11878 | 006eZjy7QWfsa06JJu | FALSE
24-PC-41572 | Task Order 13: Plover Cove Water Main Architectural History Survey | Fixed fee | On Hold | L8150 | E31141 | Northfield Builders | 70.53% | 126800 | 89432.04 | 95391.63 | 0 | 0 | 89432.04 | 8140.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614 | 13460 | 006wJ1lhuRIj4U96d6 | TRUE
24-PC-41701 | Cedar Hollow Wastewater Plant - Data Recovery | Fixed fee | On Hold | L8160 | E31162 | Harborlight Builders | 85.52% | 189100 | 161718.32 | 119908.31 | 0 | 0 | 161718.32 | 20200.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1469 | 11612 | 0069VPKgbjcBJP6aNi | TRUE
24-PC-41886 | On-Call: Pebble Beach Road Canal Lining Section 106 Consultation | Time and material | Final Reporting/Review | L8160 | E31167 | Northfield Port Authority | 0% | 67500 | 43694 | 46824.75 | 0 | 0 | 43694 | 5509.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543 | 13558 | 006zOkTiOqa5tVcp0g | FALSE
24-PC-41904 | Falcon Mesa Battery Storage - Architectural History Survey | Fixed fee | Final Billing/Invoice | L8160 | E31173 | Summit Engineering, Inc. | 100% | 31500 | 31500 | 21889.35 | 0 | 0 | 31500 | 3805.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281 | 15125 | 006y3q7v5OjRbcAgXe | FALSE
24-PC-41969 | Windmill Flat Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | L8160 | E31167 | Ironbridge Development Group | 66.45% | 216500 | 143864.25 | 161335.8 | 0 | 0 | 143864.25 | 10506.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3849 | 12618 | 006Q4MxgmgYrivyc2D | TRUE
24-PC-42121 | Oak Terrace Substation Maritime Remote Sensing Survey | Fixed fee | In Progress | L8160 | E31162 | Mesa Verde Planning Associates | 90.05% | 267300 | 240703.65 | 208453.84 | 0 | 0 | 240703.65 | 35103.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2366 | 13344 | 006kmT1nX6vU7m53Vj | FALSE
24-PC-42174 | Thistle Down Section 106 Consultation | Time and material | On Hold | L8160 | E31170 | Coastal Builders | 0% | 20800 | 14144 | 14431.04 | 0 | 0 | 14144 | 947.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 11038 | 006Vi3yhDizs1irQLR | FALSE
24-PC-42184 | Phase II: Granite Pass Substation Environmental Review Support | Fixed fee | In Progress | L8160 | E31170 | Stonebridge Resources Corp. | 43.93% | 25600 | 11246.08 | 17986.56 | 0 | 0 | 11246.08 | 979.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 15001 | 0068nlsXeNedjmizPQ | TRUE
24-PC-42267 | Aspen Ridge Bridge Replacement Paleontological Monitoring | Fixed fee | On Hold | L8170 | E31175 | Brightwater Rail Partners | 39.44% | 49000 | 19325.6 | 32797.59 | 0 | 0 | 19325.6 | 2225.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422 | 10392 | 006fYai4s53SQKYSjk | FALSE
24-PC-42338 | Silver Lake Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | L8170 | E31179 | Blue Mesa Port Authority | 100% | 21700 | 14756 | 14751.66 | 0 | 0 | 14756 | 2489.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 10214 | 006MYCHZfeJpAJpdMd | FALSE
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | Time and material | In Progress | L8170 | E31175 | Lakecrest Power Cooperative | 0% | 263500 | 179180 | 173567.45 | 0 | 0 | 179180 | 16137.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3511 | 13081 | 006QakLhxIyBAnu2md | FALSE
24-PC-42495 | Kestrel Butte Battery Storage - Cultural Resources Monitoring | Fixed fee | Lab/Curation | L8170 | E31175 | Pioneer Renewables LLC | 62.91% | 45900 | 28875.69 | 35246.61 | 0 | 0 | 28875.69 | 4833.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 13869 | 006VykcgecVopyCsEb | FALSE
24-PC-42527 | Heron Marsh Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | L8170 | E31175 | Pioneer Renewables LLC | 100% | 31700 | 21556 | 20415.55 | 0 | 0 | 21556 | 3213.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 13869 | 006GqI6lmyPKWfC4H7 | FALSE
24-PC-42550 | Yarrow Point Paleontological Monitoring | Fixed fee | In Progress | L8170 | E31179 | Timberline Telecom Holdings | 66.98% | 301300 | 200636.36 | 216936 | 1829.3 | 2014.55 | 201810.74 | 25137.69 | 315.57 | 0 | 1174.38 | 0 | 1174.38 | 0 | 6.5 | 0 | 2420 | 15690 | 006LlhR0jXT299PrQo | TRUE
24-PC-42638 | Task Order 21: Plover Cove Transmission Line Maritime Remote Sensing Survey | Fixed fee | On Hold | L8170 | E31175 | Evergreen Development Group | 53.83% | 417200 | 224578.76 | 310521.96 | 0 | 0 | 224578.76 | 20559.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4299 | 11371 | 006Dt6qLGBDh3aTOXg | TRUE
24-PC-42674 | Foxglove Canal Lining Architectural History Survey | Time and material | Lab/Curation | L8180 | E31188 | Pioneer Renewables LLC | 0% | 156100 | 106148 | 111589.34 | 0 | 0 | 106148 | 7670.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241 | 13869 | 006r2AW3zgaTqG2KfZ | FALSE
24-PC-42697 | On-Call: Dove Canyon Airport Apron GIS Mapping | Time and material | Final Billing/Invoice | L8180 | E31188 | Coastal Planning Associates | 100% | 120000 | 81600 | 85241.3 | 0 | 0 | 81600 | 9684.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 006IVT7Z3OR3h48bJ7 | FALSE
24-PC-42846 | On-Call: Juniper Wash Airport Apron Historic Resources Evaluation | Fixed fee | Completed | L8180 | E31185 | Summit Engineering, Inc. | 100% | 161200 | 161200 | 115644.05 | 0 | 0 | 161200 | 14663.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15125 | 006MPGkOgKmaeLHojQ | FALSE
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | Fixed fee | In Progress | L8190 | E31193 | Lakecrest Pipeline Company | 70.61% | 639100 | 451268.51 | 498050.63 | 0 | 0 | 451268.51 | 56971.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9052 | 13006 | 006565G0lWswNmwnZA | FALSE
24-PC-43116 | On-Call: Larkspur Airport Apron Phase II Testing | Fixed fee | Final Reporting/Review | L8190 | E31193 | High Plains Environmental Consultants | 67.7% | 424400 | 287318.8 | 314395.52 | 0 | 0 | 287318.8 | 43632.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12089 | 006yLbyWY8EkboqD7L | FALSE
24-PC-43150 | Rushgrass Draw Architectural History Survey | Fixed fee | In Progress | L8190 | E31193 | Granite State Rail Partners | 81.21% | 301500 | 244848.15 | 222689.15 | 0 | 0 | 244848.15 | 15372.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4305 | 11524 | 006LhD3tAQdwNxhiTu | FALSE
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | Time and material | In Progress | L8190 | E31193 | Sunrise Planning Associates | 0% | 19700 | 13396 | 14170.21 | 0 | 0 | 13396 | 3386.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15406 | 006ny6vumoUrICP2Dw | FALSE
24-PC-43251 | Phase III: Maple Fork Fiber Route Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | L8200 | E31196 | Cardinal Land Company | 100% | 163100 | 110908 | 112751.03 | 0 | 0 | 110908 | 15707.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566 | 10711 | 006MHiJnIq4KUZI18e | FALSE
24-PC-43406 | Pine Hollow Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8200 | E31196 | High Plains Engineering, Inc. | 100% | 38700 | 38700 | 27987.84 | 0 | 0 | 38700 | 2071.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613 | 12054 | 006VUmDUNhP0M4JQDH | TRUE
24-PC-43670 | Granite Pass Archaeological Testing | Fixed fee | Final Reporting/Review | L8210 | E31206 | Lakecrest Pipeline Company | 70.56% | 220400 | 155514.24 | 168565.52 | 0 | 0 | 155514.24 | 18198.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13006 | 006xhXAttoEpVHgmjB | TRUE
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | Time and material | In Progress | L8210 | E31206 | Harborlight Builders | 0% | 1003600 | 682448 | 771166.24 | 0 | 0 | 682448 | 70094.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9084 | 11612 | 006XsP6hjZPVpwbesx | FALSE
24-PC-43719 | On-Call: Juniper Wash Wastewater Plant Historic Resources Evaluation | Time and material | Final Reporting/Review | L8210 | E31205 | Highland Resources Corp. | 0% | 382100 | 259828 | 239599.17 | 0 | 0 | 259828 | 14332.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3822 | 12409 | 006BfXpfO5k0J15VSD | FALSE
24-PC-43782 | Stone Mill Cultural Resources Assessment | Time and material | Completed | L8210 | E31205 | Mesa Verde Pipeline Company | 100% | 571500 | 388620 | 411773.03 | 0 | 0 | 388620 | 89496.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581 | 13320 | 006dnTaixD9E3wTfn7 | FALSE
24-PC-43786 | Task Order 3: Wren Hollow Canal Lining Architectural History Survey | Fixed fee | Lab/Curation | L8210 | E31209 | Cardinal Rail Partners | 65.36% | 220400 | 144053.44 | 123791.36 | 0 | 0 | 144053.44 | 12702.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10792 | 006FRdV1t4xJmdQjdF | FALSE
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | L8220 | E31220 | Redtail Infrastructure Group | 71.7% | 213100 | 152792.7 | 187528 | 0 | 0 | 152792.7 | 18151.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2321 | 14267 | 006F3OuaHMhN9nPt2i | FALSE
24-PC-44022 | Sea Oat Historic Resources Evaluation | Time and material | Transferred Entity | L8220 | E31220 | Evergreen County | 0% | 1072900 | 729572 | 625022.97 | 0 | 0 | 729572 | 44173.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | 11354 | 006bBzGvZKWnY8fhqm | FALSE
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Time and material | Transferred Entity | L8220 | E31213 | Coastal Builders | 0% | 264500 | 256769.18 | 194222.35 | 5056.54 | 4645.97 | 264500 | 29807.09 | 2903.54 | 0 | 7730.82 | 0 | 7730.82 | 0 | 37 | 0 | 1593 | 11038 | 0061BpFhaD8mPk62uB | FALSE
24-PC-44158 | Saltgrass Environmental Review Support | Fixed fee | Transferred Entity | L8220 | E31220 | Lakecrest Telecom Holdings | 100% | 23200 | 23148.01 | 15583.44 | 13.02 | 10.21 | 23200 | 2567.05 | 0 | 0 | 51.99 | 0 | 51.99 | 0 | 0 | 0 | 132 | 13182 | 0065wbeoaw92DghSJh | TRUE
25-PC-30034 | On-Call: Wren Hollow Wastewater Plant GIS Mapping | Fixed fee | Final Reporting/Review | L8000 | E30907 | Pioneer Transit Authority | 68.54% | 101900 | 69842.26 | 74162.82 | 0 | 0 | 69842.26 | 3761.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347 | 13885 | 006MAsvEKbGuN8VCHc | FALSE
25-PC-30077 | Phase II: Tamarack Housing Development Phase I Survey | Time and material | In Progress | L8000 | E30900 | Coastal Development Group | 0% | 103400 | 103400 | 71293.1 | 0 | 0 | 103400 | 10503.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 718 | 11160 | 006XVxzPUQbel5VgwP | FALSE
25-PC-30140 | Windmill Flat Cell Tower - GIS Mapping | Time and material | In Progress | L8000 | E30900 | Ridgeline Resources Corp. | 0% | 257200 | 121129.05 | 165353.88 | 0 | 0 | 121129.05 | 13467.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2437 | 14529 | 006d3YbYU6TuysMUYl | FALSE
25-PC-30204 | Maple Fork Phase I Survey | Time and material | Final Billing/Invoice | L8000 | E30905 | Summit Renewables LLC | 100% | 179400 | 121992 | 124220.26 | 0 | 0 | 121992 | 14905.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15274 | 006AjqZxQfosqw0dsl | FALSE
25-PC-30254 | Task Order 16: Coyote Springs Reservoir Class III Survey | Time and material | Final Reporting/Review | L8000 | E30905 | Cardinal Utilities | 0% | 77100 | 51372.6 | 49529.04 | 224.83 | 108.17 | 51372.6 | 2824.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 569 | 10833 | 006sOZ8AHbz4k1TfZh | FALSE
25-PC-30345 | Wildrye Phase II Testing | Fixed fee | In Progress | L8000 | E30905 | Canyon Rail Partners | 81.67% | 160400 | 130998.68 | 92631 | 0 | 0 | 130998.68 | 5447.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097 | 10579 | 0064WVxChDoJedYW4B | FALSE
25-PC-30348 | Phase II: Pine Hollow Wind Farm Environmental Review Support | Fixed fee | In Progress | L8000 | E30900 | Blue Mesa Port Authority | 64.16% | 20800 | 13345.28 | 15194.4 | 0 | 0 | 13345.28 | 1179.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 10214 | 0064nL4iiThnjYFSKS | FALSE
25-PC-30418 | Dove Canyon Wind Farm Class III Survey | Fixed fee | Final Reporting/Review | L8000 | E30905 | Westwind County | 72.28% | 344800 | 249221.44 | 233309.47 | 0 | 0 | 249221.44 | 30523.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3956 | 15753 | 006GL9Yi4XlMuNQqb4 | FALSE
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | Fixed fee | In Progress | L8010 | E30916 | Northfield Power Cooperative | 100% | 19700 | 17105.05 | 13027.61 | 3150.88 | 1751.65 | 19700 | 1847.28 | 2634.4 | 0 | 2594.95 | 0 | 2594.95 | 0 | 40 | 0 | 149 | 13614 | 006n23rJFDdw4hpsnp | FALSE
25-PC-30694 | Rushgrass Draw Class III Survey | Fixed fee | Completed | L8010 | E30913 | Granite State Resources Corp. | 100% | 358200 | 358200 | 267073.92 | 0 | 0 | 358200 | 22567.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3515 | 11571 | 006WXyG9BjsiG9GSvy | FALSE
25-PC-30717 | Phase II: Riverbend Cell Tower Built Environment Survey | Fixed fee | In Progress | L8010 | E30916 | Brightwater Land Company | 84.78% | 324100 | 255801.54 | 205678.64 | 22129.39 | 13410.59 | 274771.98 | 22842.88 | 7440.57 | 0 | 18970.44 | 0 | 18970.44 | 0 | 148.5 | 0 | 2658 | 10261 | 0066VAWkXAzKmTkGHi | FALSE
25-PC-30725 | Slate Ridge Paleontological Monitoring | Time and material | Completed | L8010 | E30913 | Sunrise Rail Partners | 100% | 7400 | 5032 | 4916.56 | 0 | 0 | 5032 | 1284.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 15467 | 006euiP7qynrVqf7Y4 | FALSE
25-PC-30739 | Saltgrass Solar Class III Survey | Fixed fee | Final Reporting/Review | L8010 | E30916 | Cardinal Environmental Consultants | 50.92% | 244200 | 124346.64 | 214896 | 0 | 0 | 124346.64 | 21667.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10678 | 006rtdo6eAtk6c41qW | FALSE
25-PC-30772 | Sea Oat Cultural Resources Assessment | Fixed fee | In Progress | L8010 | E30916 | High Plains Environmental Consultants | 100% | 63300 | 63300 | 43065.84 | 0 | 0 | 63300 | 5246.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 12089 | 0065R3z7bDuS8xdGLU | TRUE
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | Fixed fee | In Progress | L8010 | E30916 | Keystone Rail Partners | 100% | 131000 | 122522.64 | 85464.4 | 6029.67 | 2396.82 | 131000 | 17585.86 | 4839.96 | 0 | 8477.36 | 0 | 8477.36 | 0 | 83.25 | 4 | 713 | 12893 | 006p20BUkrrTSj8ZtT | FALSE
25-PC-30824 | Task Order 2: Lantern Bay Fiber Route Environmental Review Support | Fixed fee | In Progress | L8010 | E30916 | Mesa Verde Port Authority | 69.03% | 206400 | 142477.92 | 145641.07 | 0 | 0 | 142477.92 | 8043.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3572 | 13374 | 006movyu471Mc56Khp | FALSE
25-PC-30928 | Tansy Flat Bridge Replacement Cultural Resources Monitoring | Fixed fee | On Hold | L8010 | E30913 | Blue Mesa County | 80.33% | 71900 | 57757.27 | 53817.15 | 0 | 0 | 57757.27 | 6312.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114 | 10001 | 0066tVJDPSMX33s8ef | TRUE
25-PC-31024 | Rushgrass Draw Environmental Review Support | Fixed fee | On Hold | L8010 | E30916 | Clearwater Resources Corp. | 2.15% | 770600 | 16567.9 | 514826.47 | 0 | 0 | 16567.9 | 976.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5690 | 11004 | 006BpyfHurfSWH7hrg | TRUE
25-PC-31109 | Riverbend GIS Mapping | Time and material | In Progress | L8020 | E30937 | Lakecrest Power Cooperative | 0% | 174700 | 154905.3 | 109484.49 | 30821.83 | 16937.66 | 174700 | 23130.7 | 10420.13 | 0 | 19794.7 | 0 | 19794.7 | 0 | 107.25 | 0 | 785 | 13081 | 0067redjq8BNWSHYTt | FALSE
25-PC-31114 | Granite Pass Built Environment Survey | Time and material | In Progress | L8020 | E30923 | Coastal Builders | 0% | 229400 | 179308.8 | 157964.84 | 0 | 0 | 179308.8 | 25651.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257 | 11038 | 0060MoSzCJRPiu4cig | FALSE
25-PC-31144 | Heron Marsh Bridge Replacement Section 106 Consultation | Time and material | Completed | L8020 | E30935 | Coastal Development Group | 100% | 78700 | 53516 | 54208.56 | 0 | 0 | 53516 | 7747.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 | 11160 | 006Iiruj9CcsM3y2RG | FALSE
25-PC-31180 | Blue Heron Environmental Review Support | Fixed fee | In Progress | L8020 | E30942 | Prairie Wind Transit Authority | 100% | 80000 | 69747.43 | 60701.89 | 10384.42 | 4847.47 | 80000 | 7627.47 | 4001.9 | 0 | 10252.57 | 0 | 10252.57 | 0 | 31.5 | 0.75 | 0 | 14127 | 006SQw96FkcgLgjHjW | FALSE
25-PC-31242 | Sage Flat Fiber Route - Class III Survey | Fixed fee | In Progress | L8020 | E30936 | Keystone Rail Partners | 35.93% | 398600 | 139744.36 | 273446.93 | 4315.92 | 3383.35 | 143216.98 | 9726.35 | 1295.76 | 0 | 3472.62 | 0 | 3472.62 | 0 | 28.25 | 1.75 | 4289 | 12893 | 006aPDpnzc3HmxfnHM | FALSE
25-PC-31263 | Dove Canyon Water Main Phase I Survey | Time and material | Lab/Curation | L8020 | E30937 | Summit Engineering, Inc. | 0% | 203400 | 173315.81 | 139410.36 | 3992.54 | 3697.23 | 177142 | 11132.42 | 499.68 | 0 | 3826.19 | 0 | 3826.19 | 0 | 12 | 0 | 2275 | 15125 | 006syAZdcPJgOGqBSp | FALSE
25-PC-31275 | Sage Flat Highway Widening Environmental Review Support | Time and material | Final Billing/Invoice | L8020 | E30936 | Ridgeline Renewables LLC | 100% | 24900 | 7320.6 | 18435.96 | 0 | 0 | 7320.6 | 3050.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 14493 | 006sqrapOsmAJmj86Q | FALSE
25-PC-31298 | On-Call: Lone Pine Water Main Class III Survey | Fixed fee | In Progress | L8020 | E30937 | Cardinal Land Company | 86.27% | 48100 | 41495.87 | 35361.72 | 0 | 0 | 41495.87 | 3660.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 10711 | 006fCaooAfHg2Mewwk | FALSE
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Fixed fee | Lab/Curation | L8020 | E30925 | Harborlight County | 100% | 23500 | 23419.06 | 17263.1 | 330.9 | 162.09 | 23500 | 4247.64 | 77.19 | 0 | 80.94 | 0 | 80.94 | 0 | 1.75 | 0 | 289 | 11648 | 006JUC2OBoJQ3QUHBg | FALSE
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | Fixed fee | In Progress | L8020 | E30937 | Redtail Rail Partners | 100% | 52000 | 49983.77 | 38781.6 | 1966.69 | 1377.91 | 52000 | 7519.04 | 151.49 | 0 | 2016.23 | 0 | 2016.23 | 0 | 6 | -5.5 | 707 | 14317 | 006Nmks4BaTzLgO2Li | FALSE
25-PC-31420 | Cedar Hollow Wind Farm Archaeological Testing | Fixed fee | Final Reporting/Review | L8020 | E30935 | Mesa Verde Telecom Holdings | 54.12% | 102200 | 48011.31 | 68753.09 | 6267.18 | 2859.65 | 55310.64 | 7143.69 | 2202.84 | 0 | 7299.33 | 0 | 7299.33 | 0 | 57 | 0 | 1116 | 13431 | 006O6vfcTmyqKjFNQR | FALSE
25-PC-31555 | Wren Hollow Architectural History Survey | Fixed fee | In Progress | L8020 | E30936 | Stonebridge Engineering, Inc. | 95.84% | 69300 | 60877.3 | 53097.66 | 8460.35 | 5286.24 | 66417.12 | 3256.84 | 2561.65 | 0 | 5539.82 | 0 | 5539.82 | 0 | 38.5 | 0 | 641 | 14937 | 00696REimiPIsbxfsV | FALSE
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | Fixed fee | In Progress | L8020 | E30923 | Lakecrest Rail Partners | 100% | 16800 | 16756.9 | 11810.4 | 13.99 | 8.69 | 16800 | 1459.97 | 23.64 | 0 | 43.1 | 0 | 43.1 | 0 | 0.5 | 0 | 139 | 13111 | 006LGkpDYYEuJJ60rp | FALSE
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Time and material | Final Reporting/Review | L8020 | E30935 | Riverstone Resources Corp. | 0% | 30300 | 30300 | 22049.31 | 0 | 0 | 30300 | 3353.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14683 | 006amQUkjgoyfq59LG | FALSE
25-PC-31775 | Task Order 26: Pine Hollow Bridge Replacement Cultural Resources Monitoring | Time and material | In Progress | L8020 | E30937 | Prairie Wind Port Authority | 0% | 163200 | 89880 | 98279.04 | 0 | 0 | 89880 | 5268.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14077 | 006ZSo4xWGJMdDH029 | FALSE
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | Fixed fee | In Progress | L8020 | E30942 | Pioneer Utilities | 100% | 216800 | 202009.7 | 171337.04 | 8726.83 | 7781.78 | 216800 | 27849.54 | 5056.03 | 0 | 14790.3 | 0 | 14790.3 | 0 | 92.75 | 0 | 2601 | 13948 | 006jh2NyHSzVW7JFpg | TRUE
25-PC-31821 | Millbrook Environmental Review Support | Fixed fee | Final Reporting/Review | L8020 | E30942 | Summit Transit Authority | 81.19% | 211400 | 156607.64 | 183932.36 | 12125.94 | 12556.23 | 171635.66 | 32705.57 | 8861.76 | 0 | 15028.02 | 0 | 15028.02 | 0 | 198.5 | 7.25 | 2512 | 15291 | 0064ivDBPn0a1TXn68 | FALSE
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Time and material | Cost Tracking on Closed Project | L8020 | E30925 | Pioneer County | 0% | 40900 | 13987.8 | 28728.16 | 0 | 0 | 13987.8 | 2838.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13727 | 006yzS4fewM3Om8G84 | FALSE
25-PC-31905 | Raven Rock Mixed-Use Development Phase II Testing | Time and material | Final Reporting/Review | L8020 | E30937 | Stonebridge Builders | 0% | 331600 | 185324.62 | 228107.64 | 15252.8 | 4021.73 | 201880.85 | 22332.4 | 5257.22 | 0 | 16556.23 | 0 | 16556.23 | 0 | 119.25 | 0 | 3676 | 14860 | 006lJpMF5XuVUAsjhN | FALSE
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Time and material | Final Reporting/Review | L8030 | E30958 | Coastal Rail Partners | 0% | 35200 | 35200 | 24481.6 | 0 | 0 | 35200 | 6924.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 11259 | 006k29PsOLiuZLScNs | FALSE
25-PC-31983 | Task Order 29: Juniper Wash Housing Development Cultural Resources Assessment | Time and material | Final Billing/Invoice | L8030 | E30950 | Ridgeline County | 100% | 271500 | 152583 | 186004.65 | 0 | 0 | 152583 | 33386.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2553 | 14393 | 0065GNPcVxxYHoqbHk | FALSE
25-PC-32000 | Twin Buttes Built Environment Survey | Fixed fee | On Hold | L8030 | E30950 | Sunrise Telecom Holdings | 39.07% | 61200 | 23910.84 | 50312.52 | 0 | 0 | 23910.84 | 2948.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15492 | 006UCM8v9PoQVWs9iS | FALSE
25-PC-32021 | Oak Terrace Cultural Resources Monitoring | Time and material | In Progress | L8030 | E30948 | Harborlight Builders | 0% | 148200 | 95737.05 | 111253.74 | 1323.94 | 973.57 | 97677.05 | 7560.44 | 566.72 | 0 | 1940 | 0 | 1940 | 0 | 14.25 | 0 | 1469 | 11612 | 006QsQvHTD0RsRkZio | FALSE
25-PC-32024 | Pine Hollow Historic Resources Evaluation | Time and material | In Progress | L8030 | E30950 | Northfield Telecom Holdings | 0% | 79500 | 51094.33 | 57637.5 | 3078.85 | 1670.58 | 57058 | 6672.04 | 807.78 | 0 | 5963.67 | 0 | 5963.67 | 0 | 11 | 0 | 565 | 13631 | 006FlOpHmo7GqavjF0 | FALSE
25-PC-32112 | Foxglove School Campus Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8030 | E30958 | High Plains Engineering, Inc. | 100% | 37600 | 37600 | 26165.84 | 0 | 0 | 37600 | 3879.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553 | 12054 | 006zowNdzBujboKez0 | TRUE
25-PC-32144 | Ember Valley Archaeological Testing | Fixed fee | Completed | L8030 | E30948 | Coastal Planning Associates | 100% | 12100 | 12100 | 9169.38 | 0 | 0 | 12100 | 989.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 006kls8w4PQy6OZNnJ | FALSE
25-PC-32241 | Sumac Ridge Canal Lining Cultural Resources Monitoring | Time and material | Final Reporting/Review | L8030 | E30947 | Ironbridge Telecom Holdings | 0% | 331500 | 253304.76 | 231983.7 | 5934.64 | 5319.29 | 258073.5 | 35687.99 | 0 | 0 | 4768.74 | 0 | 4768.74 | 0 | 0 | 0 | 2426 | 12740 | 006mhvfvI5WTTd7slh | FALSE
25-PC-32264 | Tansy Flat Wastewater Plant Phase I Survey | Time and material | Final Reporting/Review | L8030 | E30957 | Canyon Rail Partners | 0% | 736000 | 500480 | 420550.4 | 0 | 0 | 500480 | 34470.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5939 | 10579 | 0062bOqawoawIIZUXW | FALSE
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | Time and material | In Progress | L8030 | E30950 | Prairie Wind Planning Associates | 0% | 201300 | 185059.24 | 150874.35 | 11966.94 | 6701.74 | 196916.6 | 19092.46 | 8932.84 | 0 | 11857.36 | 0 | 11857.36 | 0 | 119.5 | 0 | 1642 | 14041 | 006tZNDrCuTKrP9Nhq | FALSE
25-PC-32346 | Phase II: Aspen Ridge Mixed-Use Development Historic Resources Evaluation | Time and material | Final Billing/Invoice | L8030 | E30958 | Summit Port Authority | 100% | 40200 | 27336 | 29157.06 | 0 | 0 | 27336 | 4667.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 15239 | 006fFHDZQtnVEeUL6k | FALSE
25-PC-32402 | Hawk Point Highway Widening - Cultural Resources Monitoring | Fixed fee | Lab/Curation | L8030 | E30957 | Coastal Construction Co. | 59.08% | 401300 | 229423.8 | 353144 | 13200.79 | 7095.93 | 237088.04 | 40058.33 | 4332.79 | 0 | 7664.24 | 0 | 7664.24 | 0 | 104 | 0 | 5485 | 11092 | 006d48o2KErR5ujC4Y | FALSE
25-PC-32447 | Pebble Beach Road Archaeological Testing | Fixed fee | In Progress | L8030 | E30948 | Canyon Construction Co. | 100% | 88200 | 88200 | 61772.24 | 0 | 0 | 88200 | 9281.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 10448 | 006emdsYjd4mLN9kjU | FALSE
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | Time and material | In Progress | L8030 | E30957 | Ironbridge County | 0% | 118800 | 111029.5 | 85013.28 | 4898.44 | 5953.6 | 118800 | 24341.45 | 3463.05 | 0 | 7770.5 | 0 | 7770.5 | 0 | 52.5 | 0 | 651 | 12563 | 006W6tHOTkWKjn2qf6 | FALSE
25-PC-32500 | On-Call: Dove Canyon Cell Tower Environmental Review Support | Time and material | Final Billing/Invoice | L8030 | E30947 | Ironbridge Infrastructure Group | 100% | 95700 | 38567.1 | 67273.36 | 0 | 0 | 38567.1 | 11473.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813 | 12667 | 006Of52C4mgaWYHJQD | FALSE
25-PC-32630 | Wildrye Archaeological Testing | Fixed fee | On Hold | L8030 | E30957 | Mesa Verde Telecom Holdings | 52.95% | 865400 | 458229.3 | 644117.22 | 0 | 0 | 458229.3 | 49111.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9408 | 13431 | 006mybXLDQiArGWREW | FALSE
25-PC-32750 | Elk Meadow Fiber Route Paleontological Monitoring | Fixed fee | In Progress | L8030 | E30947 | Stonebridge Engineering, Inc. | 76.43% | 35500 | 27028.9 | 25187.75 | 104.36 | 69.24 | 27132.65 | 1655.58 | 91.92 | 0 | 103.75 | 0 | 103.75 | 0 | 2 | 0 | 440 | 14937 | 006xVhIBH3kIBPEkgg | FALSE
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | Time and material | In Progress | L8040 | E30971 | Coastal Utilities | 0% | 86500 | 75767.65 | 62245.4 | 7753.8 | 3939.57 | 83279.75 | 3400.08 | 7542.03 | 0 | 7512.1 | 0 | 7512.1 | 0 | 117.75 | 4.5 | 1283 | 11319 | 006Wwm5qKB0GgTbhts | FALSE
25-PC-32795 | North Fork Water Main Architectural History Survey | Time and material | In Progress | L8040 | E30965 | Coastal Construction Co. | 0% | 16900 | 16900 | 11650.86 | 0 | 0 | 16900 | 1030.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 11092 | 0064qo8tzwwfs9SmHe | FALSE
25-PC-32819 | Eagle Bend Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | L8040 | E30976 | Mesa Verde Land Company | 100% | 49800 | 49800 | 32021.4 | 0 | 0 | 49800 | 2122.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 13275 | 006u3mlYewJ0p6IJLG | FALSE
25-PC-32838 | Aspen Ridge Canal Lining - Curation | Fixed fee | In Progress | L8040 | E30971 | Pioneer Renewables LLC | 92.03% | 42600 | 39204.78 | 33543.24 | 0 | 0 | 39204.78 | 4815.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13869 | 006T25G604Al9FYOTF | FALSE
25-PC-32861 | Yarrow Point Architectural History Survey | Fixed fee | In Progress | L8040 | E30980 | Westwind Development Group | 100% | 59200 | 54224.79 | 41555.52 | 3120.85 | 2867.42 | 59200 | 10328.34 | 3682.7 | 0 | 4975.21 | 0 | 4975.21 | 0 | 57.25 | 0 | 0 | 15795 | 0066MgsSzaYBshY5DT | FALSE
25-PC-32867 | Larkspur Levee Repair Maritime Remote Sensing Survey | Fixed fee | In Progress | L8040 | E30972 | Ironbridge County | 61.03% | 144100 | 85641.73 | 82727.81 | 2126.54 | 2345.61 | 87944.23 | 10097.35 | 1767.25 | 0 | 2302.5 | 0 | 2302.5 | 0 | 38.5 | 0 | 1042 | 12563 | 006GKzkET4UAtXXml3 | FALSE
25-PC-32885 | Maple Fork Reservoir Historic Resources Evaluation | Fixed fee | In Progress | L8040 | E30967 | Evergreen County | 24.56% | 1706300 | 394166.15 | 1213962.27 | 20237.73 | 8534.84 | 419067.28 | 26234.13 | 7162.35 | 0 | 24901.13 | 0 | 24901.13 | 0 | 117 | 0 | 17831 | 11354 | 006hXNFP7tDbMlWYul | FALSE
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | Fixed fee | In Progress | L8040 | E30971 | High Plains Environmental Consultants | 100% | 59600 | 57228.13 | 51399.04 | 2238.32 | 1737.34 | 59600 | 13094.13 | 969.99 | 0 | 2371.87 | 0 | 2371.87 | 0 | 18.25 | 0 | 797 | 12089 | 006dP3qPnEc4RQTze0 | FALSE
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Time and material | Lab/Curation | L8040 | E30971 | Highland Infrastructure Group | 0% | 13300 | 13300 | 8727.43 | 0 | 0 | 13300 | 1728.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 12316 | 006yEsVz8Y7snSZC8e | FALSE
25-PC-32926 | Tamarack Pipeline - Cultural Resources Monitoring | Time and material | In Progress | L8040 | E30971 | Ridgeline Water District | 0% | 328400 | 68635.6 | 212343.44 | 0 | 0 | 68635.6 | 5269.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2847 | 14577 | 0061XnKF2izlUu1CPo | FALSE
25-PC-32952 | Eagle Bend Wastewater Plant - Data Recovery | Fixed fee | In Progress | L8040 | E30967 | Pioneer Engineering, Inc. | 50.05% | 299000 | 143659.49 | 202368.34 | 6267.47 | 3371.29 | 149649.5 | 7596.21 | 2797.22 | 0 | 5990.01 | 0 | 5990.01 | 0 | 38.75 | 0 | 0 | 13790 | 006y1eyNvpV9FYQ66B | FALSE
25-PC-33065 | Wren Hollow GIS Mapping | Fixed fee | In Progress | L8040 | E30980 | Blue Mesa Resources Corp. | 90.47% | 50400 | 45596.88 | 40748.4 | 0 | 0 | 45596.88 | 6893.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 10225 | 006B88BlMs1Q6eRu17 | TRUE
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | Fixed fee | In Progress | L8040 | E30965 | Heartland Water District | 78.65% | 767800 | 603874.7 | 553046.34 | 0 | 0 | 603874.7 | 82209.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10971 | 11891 | 006FKWq1s1FVhoia2y | TRUE
25-PC-33105 | Redbud Data Recovery | Fixed fee | In Progress | L8040 | E30967 | Mesa Verde Port Authority | 100% | 3500 | 0 | 2324 | 0 | 0 | 3500 | 846.58 | 2995.63 | 0 | 3500 | 0 | 3500 | 0 | 43 | 3.75 | 23 | 13374 | 006gAz05Wd6KWXVcc8 | FALSE
25-PC-33136 | North Fork Historic Resources Evaluation | Time and material | In Progress | L8040 | E30980 | Granite State Development Group | 0% | 33200 | 17533.17 | 22378.06 | 416.24 | 382.03 | 18065.15 | 2470.88 | 336.98 | 0 | 531.98 | 0 | 531.98 | 0 | 7.25 | 0 | 426 | 11469 | 006CdjZCth7CKNRDln | FALSE
25-PC-33183 | Saltgrass Architectural History Survey | Fixed fee | In Progress | L8040 | E30980 | Clearwater Builders | 96.66% | 104500 | 95400.33 | 79399.1 | 4561.9 | 3173.42 | 101009.7 | 7521.05 | 1577.71 | 0 | 5609.37 | 0 | 5609.37 | 0 | 31 | 0 | 1464 | 10855 | 006lH27hqcGZCeiZdC | FALSE
25-PC-33206 | Larkspur Water Main - Phase II Testing | Fixed fee | In Progress | L8040 | E30979 | Sunrise Development Group | 56.27% | 48800 | 25370.03 | 39449.92 | 2756.12 | 1934.2 | 27459.76 | 4039.81 | 2036.5 | 0 | 2089.73 | 0 | 2089.73 | 0 | 29.25 | 0 | 478 | 15389 | 006dSKACqCSFIznAya | FALSE
25-PC-33238 | Phase I: Foxglove Battery Storage Section 106 Consultation | Time and material | Final Billing/Invoice | L8040 | E30965 | Westwind Construction Co. | 100% | 949900 | 545242.6 | 642400.18 | 0 | 0 | 545242.6 | 121160.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9427 | 15724 | 006bMML1V1xGVafkZI | FALSE
25-PC-33294 | Fern Valley Substation - Built Environment Survey | Fixed fee | In Progress | L8040 | E30976 | Lakecrest Construction Co. | 61.04% | 137200 | 77650.18 | 91032.2 | 8833.61 | 2694.5 | 83746.88 | 11002.12 | 3696.42 | 0 | 6096.7 | 0 | 6096.7 | 0 | 83 | 0 | 984 | 12952 | 006SaTknQHTw7SAQhc | FALSE
25-PC-33321 | Hawk Point Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8040 | E30972 | Northfield Power Cooperative | 100% | 87200 | 87200 | 61258 | 0 | 0 | 87200 | 11017.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782 | 13614 | 0065tkIdqbDbibxLvX | TRUE
25-PC-33332 | Willow Springs Cultural Resources Assessment | Fixed fee | In Progress | L8040 | E30980 | Redtail Builders | 63.43% | 91000 | 54760.99 | 69587.7 | 4354.71 | 2467.8 | 57721.3 | 6488.85 | 3370.25 | 0 | 2960.31 | 0 | 2960.31 | 0 | 76.25 | 0 | 837 | 14184 | 006Y0BDLspLHlDdtGS | FALSE
25-PC-33348 | Dove Canyon Cell Tower Phase II Testing | Fixed fee | In Progress | L8040 | E30979 | Heartland Transit Authority | 55.89% | 161700 | 90374.13 | 117749.94 | 0 | 0 | 90374.13 | 10135.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194 | 11878 | 0064mGKCUHzkmrKsBU | TRUE
25-PC-33367 | Slate Ridge Rail Siding Archaeological Testing | Time and material | Lab/Curation | L8040 | E30980 | Brightwater Utilities | 0% | 150800 | 52242.62 | 100689.16 | 1367.66 | 1112 | 55445.9 | 4623 | 2115.98 | 0 | 3203.28 | 0 | 3203.28 | 0 | 46.75 | 0.75 | 3249 | 10408 | 0061ZmqGCnf8ElChc7 | FALSE
25-PC-33412 | Tansy Flat Bridge Replacement - GIS Mapping | Time and material | Final Billing/Invoice | L8040 | E30979 | Lakecrest Rail Partners | 100% | 1336200 | 428920.2 | 914495.28 | 0 | 0 | 428920.2 | 122458.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14331 | 13111 | 006opUkWD6Q1X9s12W | FALSE
25-PC-33414 | On-Call: Falcon Mesa Substation Historic Resources Evaluation | Fixed fee | Completed | L8040 | E30971 | Ridgeline County | 100% | 81800 | 81800 | 64082.12 | 0 | 0 | 81800 | 7006.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657 | 14393 | 006hAXDNjV4U1Bl0pO | FALSE
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | Fixed fee | In Progress | L8040 | E30972 | Blue Mesa Pipeline Company | 77.9% | 41600 | 32210.19 | 29136.64 | 134.72 | 124.19 | 32406.4 | 2042.78 | 0 | 0 | 196.21 | 0 | 196.21 | 0 | 0 | 0 | 333 | 10171 | 0060JBFeI4g5we9XXE | FALSE
25-PC-33522 | Yarrow Point Architectural History Survey | Time and material | Final Reporting/Review | L8040 | E30971 | Evergreen Development Group | 0% | 61800 | 50630.64 | 42270.22 | 3011.93 | 1875.16 | 52972.45 | 3029.81 | 0 | 0 | 2341.81 | 0 | 2341.81 | 0 | 0 | 0 | 0 | 11371 | 0065NYKiWouwYapCJl | FALSE
25-PC-33528 | Bramble Creek Wastewater Plant - Environmental Review Support | Time and material | Final Billing/Invoice | L8040 | E30976 | Prairie Wind County | 100% | 138500 | 9695 | 104844.5 | 0 | 0 | 9695 | 13313.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366 | 13978 | 0062bA3QqcNiuSmyWm | FALSE
25-PC-33535 | Sage Flat Data Recovery | Fixed fee | On Hold | L8040 | E30976 | Coastal Planning Associates | 65.43% | 120500 | 78843.15 | 91326.95 | 0 | 0 | 78843.15 | 4839.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783 | 11250 | 006ZpycfelNpoo4oj5 | FALSE
25-PC-33561 | Task Order 22: Badger Hollow Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | L8040 | E30979 | Keystone Energy Partners | 100% | 132200 | 44551.4 | 85348.32 | 0 | 0 | 44551.4 | 10692.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12804 | 006mcfdjwSpCUoC83h | FALSE
25-PC-33640 | Tamarack Canal Lining - Cultural Resources Assessment | Fixed fee | In Progress | L8040 | E30980 | Brightwater Power Cooperative | 29.91% | 1444500 | 417334.9 | 1192145.85 | 17104.89 | 8923.34 | 432049.95 | 71304.06 | 5863.41 | 0 | 14715.05 | 0 | 14715.05 | 0 | 94.5 | 0 | 0 | 10363 | 006ZemzVk1ciES7J4w | FALSE
25-PC-33680 | Quail Run School Campus Cultural Resources Monitoring | Fixed fee | In Progress | L8040 | E30967 | Blue Mesa Pipeline Company | 39.86% | 106800 | 37483.28 | 80014.56 | 6065.64 | 2112.33 | 42570.48 | 6187.37 | 3007.2 | 0 | 5087.2 | 0 | 5087.2 | 0 | 80 | 0 | 1057 | 10171 | 0062Jqst5WbLMH09zK | FALSE
25-PC-33744 | Blue Heron Canal Lining - Curation | Fixed fee | In Progress | L8050 | E30995 | Summit Infrastructure Group | 73.86% | 87100 | 64332.06 | 60133.84 | 0 | 0 | 64332.06 | 7106.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311 | 15147 | 006f1O6vXrs9rbAaFj | FALSE
25-PC-33750 | Kestrel Butte Archaeological Testing | Fixed fee | Transferred Entity | L8050 | E30999 | Silverline Port Authority | 100% | 69600 | 64460.42 | 51302.16 | 7977.68 | 5419.07 | 69600 | 3677.49 | 2378.75 | 0 | 5139.58 | 0 | 5139.58 | 0 | 55 | 0 | 0 | 14747 | 006RwnqD3RkclWJQGP | FALSE
25-PC-33795 | Phase I: Sage Flat Park Improvements Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | L8050 | E31001 | Harborlight County | 100% | 174500 | 174500 | 106392.65 | 0 | 0 | 174500 | 16523.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1406 | 11648 | 006IUk7ezVornvi7fp | FALSE
25-PC-33798 | On-Call: Harbor View Wind Farm Historic Resources Evaluation | Fixed fee | Final Reporting/Review | L8050 | E31000 | Blue Mesa Resources Corp. | 53.39% | 155300 | 80025.19 | 128215.68 | 2338.88 | 3415.39 | 82914.67 | 5544.42 | 1411.55 | 0 | 2889.48 | 0 | 2889.48 | 0 | 29.5 | 3.25 | 1954 | 10225 | 006TECzJ9xiobY7PSj | FALSE
25-PC-33827 | Millbrook Transmission Line - Built Environment Survey | Fixed fee | On Hold | L8050 | E30995 | Evergreen Development Group | 13.65% | 132500 | 18086.25 | 103820.06 | 0 | 0 | 18086.25 | 1247.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1660 | 11371 | 006bJl1rfSDQ2MfJz6 | FALSE
25-PC-33841 | Juniper Wash Built Environment Survey | Fixed fee | In Progress | L8050 | E30999 | Brightwater Utilities | 62.41% | 586500 | 366034.65 | 416356.35 | 0 | 0 | 366034.65 | 16111.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6037 | 10408 | 006XBWHp7SLKha1JXP | TRUE
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Fixed fee | Final Reporting/Review | L8050 | E30986 | Ridgeline Rail Partners | 100% | 15200 | 15200 | 11021.49 | 0 | 0 | 15200 | 1684.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 14455 | 006hCIQkquG4K7lsnt | FALSE
25-PC-33855 | Creosote Draw Rail Siding - Paleontological Monitoring | Time and material | Final Reporting/Review | L8050 | E30987 | Canyon Utilities | 0% | 34000 | 18919.13 | 23930.44 | 1730.26 | 784.87 | 19618 | 1404.95 | 202.38 | 0 | 698.87 | 0 | 698.87 | 0 | 4.25 | 0 | 451 | 10611 | 006ZjruuNcsJWftwuN | FALSE
25-PC-33915 | Sage Flat Archaeological Testing | Fixed fee | In Progress | L8050 | E30984 | Lakecrest Power Cooperative | 67.26% | 272400 | 176595.09 | 198225.48 | 7148.41 | 6800.22 | 183216.24 | 26399.94 | 962.62 | 0 | 6621.15 | 0 | 6621.15 | 0 | 20.25 | 0 | 0 | 13081 | 006fuL94t5HZh74MYY | FALSE
25-PC-33919 | Task Order 18: Coyote Springs Water Main Curation | Fixed fee | Completed | L8050 | E30999 | Summit Port Authority | 100% | 45500 | 45500 | 26949.65 | 0 | 0 | 45500 | 6626.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 15239 | 006z6sATIFOhlVXQjx | FALSE
25-PC-33922 | Slate Ridge Data Recovery | Fixed fee | In Progress | L8050 | E30995 | Coastal County | 100% | 22100 | 22100 | 16113.11 | 70.76 | 36.53 | 22100 | 2101.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 11118 | 006KdETLq85NrSzApP | FALSE
25-PC-33969 | Sumac Ridge Archaeological Testing | Fixed fee | In Progress | L8050 | E30992 | Ironbridge Infrastructure Group | 59.2% | 13200 | 7814.4 | 10134.96 | 0 | 0 | 7814.4 | 1043.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 12667 | 0065PmKmyI4mX2Qene | FALSE
25-PC-34036 | Kestrel Butte Battery Storage - Phase I Survey | Time and material | Lab/Curation | L8050 | E30998 | Coastal Planning Associates | 0% | 62300 | 47936.1 | 41495.74 | 6117.53 | 5585.3 | 54230.15 | 7155.3 | 2568.98 | 0 | 6294.05 | 0 | 6294.05 | 0 | 36.25 | 0 | 434 | 11250 | 006Wj4uoc2djUoCSGq | FALSE
25-PC-34077 | Sage Flat Levee Repair Class III Survey | Fixed fee | In Progress | L8050 | E30992 | Summit Port Authority | 49.93% | 580500 | 272107.91 | 459697.95 | 20123.72 | 21208.56 | 289843.65 | 19967.45 | 14693.5 | 0 | 17735.74 | 0 | 17735.74 | 0 | 159.5 | 6.25 | 4668 | 15239 | 006RX3mNdoz4ner7Ak | TRUE
25-PC-34088 | Timber Gap Harbor Dredging Cultural Resources Monitoring | Time and material | In Progress | L8050 | E30992 | Cardinal Environmental Consultants | 0% | 47300 | 32164 | 29041.82 | 0 | 0 | 32164 | 1979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 10678 | 006W8JqKdeI9Rc57L7 | FALSE
25-PC-34090 | Thistle Down Data Recovery | Time and material | In Progress | L8050 | E30986 | Pioneer Development Group | 0% | 66200 | 34066.3 | 46862.98 | 0 | 0 | 34066.3 | 4717.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744 | 13750 | 006hPaY7Nm1OIaNYLF | FALSE
25-PC-34144 | On-Call: Dove Canyon School Campus Phase II Testing | Fixed fee | Final Billing/Invoice | L8050 | E30987 | Brightwater Utilities | 100% | 23400 | 23400 | 16230.24 | 0 | 0 | 23400 | 1905.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10408 | 006cZ9nU7IcteoBd17 | TRUE
25-PC-34151 | Bramble Creek Fiber Route Cultural Resources Monitoring | Time and material | In Progress | L8050 | E30984 | Silverline Telecom Holdings | 0% | 505100 | 181895.54 | 334224.67 | 7495.57 | 4352.77 | 190049.9 | 10271.58 | 3306.45 | 0 | 8154.36 | 0 | 8154.36 | 0 | 48.75 | 0 | 0 | 14780 | 00679JxRXdy6lm6Nkn | FALSE
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | Time and material | In Progress | L8050 | E30986 | Coastal Rail Partners | 0% | 53000 | 53000 | 36718.4 | 0 | 0 | 53000 | 7801.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 11259 | 006v4EQIB1NedoOyRk | FALSE
25-PC-34374 | Tansy Flat Reservoir Cultural Resources Assessment | Time and material | In Progress | L8050 | E30998 | Silverline Water District | 0% | 14100 | 5160.6 | 9871.41 | 0 | 0 | 5160.6 | 604.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 14839 | 0060ElMdhykq23CuWr | FALSE
25-PC-34382 | Meadowlark Paleontological Monitoring | Time and material | Completed | L8050 | E30998 | Sunrise Transit Authority | 100% | 34600 | 415.2 | 26125.87 | 0 | 0 | 415.2 | 5773.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 15537 | 006yW0xqnMdJhS9SnJ | FALSE
25-PC-34451 | North Fork Curation | Time and material | In Progress | L8050 | E30985 | Harborlight Water District | 0% | 46400 | 46400 | 32526.4 | 0 | 0 | 46400 | 6294.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 11739 | 006yoAcQldhtD6hIql | FALSE
25-PC-34537 | Raven Rock Harbor Dredging - Paleontological Monitoring | Fixed fee | On Hold | L8050 | E31001 | Harborlight Builders | 44.09% | 78900 | 34787.01 | 63481.3 | 0 | 0 | 34787.01 | 3554.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682 | 11612 | 006YEZ5ath8UrNT7Fz | FALSE
25-PC-34652 | Coyote Springs Section 106 Consultation | Fixed fee | In Progress | L8050 | E30998 | Ridgeline County | 83.6% | 210700 | 157854.18 | 180928.09 | 14888.33 | 12564.62 | 176145.2 | 10587.98 | 7480.48 | 0 | 18291.02 | 0 | 18291.02 | 0 | 104.75 | 7.25 | 1733 | 14393 | 006r7mYIguwjyvzDUN | FALSE
25-PC-34681 | Hawk Point Pipeline Section 106 Consultation | Fixed fee | In Progress | L8050 | E31000 | Prairie Wind Pipeline Company | 37.01% | 715200 | 240939.56 | 430908 | 22967.5 | 18972.25 | 264695.52 | 34292.09 | 10403.15 | 0 | 23755.96 | 0 | 23755.96 | 0 | 193 | 0 | 5498 | 14024 | 006AOSckhVH1quob1L | FALSE
25-PC-34732 | Thistle Down Trail Architectural History Survey | Fixed fee | In Progress | L8050 | E30986 | Evergreen Development Group | 61.33% | 101800 | 62433.94 | 76441.62 | 0 | 0 | 62433.94 | 3937.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554 | 11371 | 0060unJ4BM3B1vkA7L | FALSE
25-PC-34768 | On-Call: Oak Terrace Wastewater Plant Section 106 Consultation | Time and material | Final Billing/Invoice | L8050 | E30984 | Evergreen County | 100% | 119400 | 29730.6 | 88654.5 | 0 | 0 | 29730.6 | 19597.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11354 | 006NbKTOVE4bEKCrTT | FALSE
25-PC-34772 | Windmill Flat Paleontological Monitoring | Time and material | Final Reporting/Review | L8050 | E31000 | High Plains Development Group | 0% | 186900 | 18840.73 | 126437.85 | 1838.13 | 542.1 | 20889.75 | 2110.75 | 1645.9 | 0 | 2049.02 | 0 | 2049.02 | 0 | 37.75 | 0 | 1386 | 12013 | 006uZVNRzRiYaDf7LO | FALSE
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | Time and material | In Progress | L8050 | E30998 | Timberline Environmental Consultants | 0% | 82200 | 65071.92 | 51638.04 | 15651.12 | 17226.7 | 82200 | 8154.02 | 11113.35 | 0 | 17128.08 | 0 | 17128.08 | 0 | 177.75 | 6 | 662 | 15591 | 0062ISoz8Qzg3v6sX7 | FALSE
25-PC-34843 | Elk Meadow Highway Widening Data Recovery | Fixed fee | Final Billing/Invoice | L8060 | E31018 | Evergreen Development Group | 100% | 188000 | 188000 | 136544.4 | 0 | 0 | 188000 | 14717.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753 | 11371 | 006X4UEWoYPvX3RQxA | FALSE
25-PC-34850 | Thistle Down Section 106 Consultation | Time and material | In Progress | L8060 | E31019 | Timberline Planning Associates | 0% | 201300 | 120850.25 | 117035.82 | 7413.53 | 10258.65 | 129963.25 | 18994.55 | 4905.81 | 0 | 9113 | 0 | 9113 | 0 | 79.5 | 0 | 1638 | 15643 | 0064W6noYNL76XRBj8 | FALSE
25-PC-34871 | Willow Springs GIS Mapping | Fixed fee | Lab/Curation | L8060 | E31008 | Timberline Telecom Holdings | 57.61% | 338100 | 173584.4 | 260979.39 | 24322.48 | 15103.72 | 194779.41 | 18795.22 | 10876.88 | 0 | 21195.01 | 0 | 21195.01 | 0 | 171.25 | 5.5 | 3386 | 15690 | 006Tm5LDKGukeYHuuW | FALSE
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | Fixed fee | In Progress | L8060 | E31019 | Highland Builders | 70.32% | 224400 | 157798.08 | 165046.2 | 0 | 0 | 157798.08 | 19035.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2686 | 12199 | 006PZ3nELeBHR7xRvE | FALSE
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | Time and material | In Progress | L8060 | E31018 | Highland Rail Partners | 0% | 71400 | 71400 | 48880.44 | 0 | 0 | 71400 | 8542.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799 | 12394 | 006fTEyYgiv70xKXt4 | FALSE
25-PC-35084 | On-Call: Fern Valley Wastewater Plant Class III Survey | Fixed fee | Final Reporting/Review | L8060 | E31018 | Pioneer County | 69.56% | 204900 | 137085.87 | 133588.01 | 3930.91 | 3150.09 | 142528.44 | 10965.08 | 1871.66 | 0 | 5442.57 | 0 | 5442.57 | 0 | 48 | 0 | 2566 | 13727 | 006WoZxZXO0Hz1OGQc | TRUE
25-PC-35131 | Tamarack Phase II Testing | Fixed fee | In Progress | L8060 | E31018 | Ridgeline Water District | 41.99% | 311900 | 130966.81 | 227562.24 | 0 | 0 | 130966.81 | 7166.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6216 | 14577 | 006Rs9xkE7MhA0BfQ2 | TRUE
25-PC-35138 | Foxglove Mixed-Use Development - Data Recovery | Time and material | In Progress | L8060 | E31008 | Ironbridge Telecom Holdings | 0% | 815000 | 590691.86 | 517757.75 | 8645.68 | 7900.96 | 593702.25 | 75268.72 | 0 | 0 | 3010.39 | 0 | 3010.39 | 0 | 0 | 0 | 8374 | 12740 | 006Qv4NfIFVJehQ3k7 | FALSE
25-PC-35168 | Quail Run Park Improvements - GIS Mapping | Time and material | Completed | L8060 | E31018 | Pioneer Power Cooperative | 100% | 330300 | 14202.9 | 212151.69 | 0 | 0 | 14202.9 | 13878.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4369 | 13831 | 006mrfn4XkhhvE4Zhr | FALSE
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | Time and material | In Progress | L8060 | E31019 | Coastal Planning Associates | 0% | 33200 | 31529.2 | 23495.64 | 1054.18 | 696.34 | 33200 | 5760.25 | 58.85 | 0 | 1670.8 | 0 | 1670.8 | 0 | 1.25 | 0 | 273 | 11250 | 006Og962DZPMnqkvhA | FALSE
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | Time and material | In Progress | L8060 | E31018 | Summit Transit Authority | 0% | 49900 | 47494.52 | 35982.89 | 3908.52 | 2743.19 | 49900 | 4549.58 | 1501.41 | 0 | 2405.48 | 0 | 2405.48 | 0 | 39.25 | 0 | 665 | 15291 | 006K8sEPJK5V1wUiPd | FALSE
25-PC-35295 | Copper Flats Architectural History Survey | Time and material | In Progress | L8060 | E31018 | Prairie Wind Pipeline Company | 0% | 80400 | 54672 | 54551.4 | 0 | 0 | 54672 | 2659.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 973 | 14024 | 006W4qO3aFuP9eUp4K | FALSE
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | Fixed fee | In Progress | L8060 | E31018 | Ironbridge Telecom Holdings | 100% | 19400 | 15409.48 | 13919.5 | 2336.1 | 1253.31 | 19400 | 7003.51 | 2749.58 | 0 | 3990.52 | 0 | 3990.52 | 0 | 70.25 | 0 | 148 | 12740 | 006arqW2TIUSs4UFyk | FALSE
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | Fixed fee | In Progress | L8060 | E31014 | Stonebridge Builders | 100% | 25100 | 24927.65 | 20032.31 | 340.19 | 239.52 | 25100 | 2829.52 | 0 | 0 | 172.35 | 0 | 172.35 | 0 | 0 | 0 | 321 | 14860 | 006W9VIXYAgfAUWNka | FALSE
25-PC-35431 | Task Order 26: Wildrye Mine Expansion Environmental Review Support | Fixed fee | On Hold | L8070 | E31034 | Blue Mesa Port Authority | 2.67% | 304700 | 8135.49 | 252565.83 | 0 | 0 | 8135.49 | 464.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4186 | 10214 | 006wp01Cen6G4P0BRU | TRUE
25-PC-35442 | Pebble Beach Road Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8070 | E31034 | Stonebridge Utilities | 100% | 86600 | 86600 | 65071.24 | 0 | 0 | 86600 | 15880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942 | 15036 | 0063AJfej436cd9hdP | FALSE
25-PC-35470 | Lantern Bay Reservoir Data Recovery | Time and material | Final Billing/Invoice | L8070 | E31023 | Ironbridge Port Authority | 100% | 484000 | 47916 | 325683.6 | 0 | 0 | 47916 | 35164.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4235 | 12704 | 006cqUKEHpAGV87lSP | FALSE
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | Time and material | In Progress | L8070 | E31032 | Ridgeline Rail Partners | 0% | 136900 | 132838.07 | 90994.45 | 3989.02 | 2973.56 | 136900 | 11784.26 | 1844.87 | 0 | 4061.93 | 0 | 4061.93 | 0 | 24 | 0 | 1344 | 14455 | 006e1BwuDuCdsjDDlb | FALSE
25-PC-35496 | Silver Lake Airport Apron Class III Survey | Time and material | In Progress | L8070 | E31032 | Lakecrest Pipeline Company | 0% | 15200 | 14910.4 | 10132.32 | 0 | 0 | 14910.4 | 1418.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 13006 | 0065RapQhAf46g6NdB | FALSE
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | Fixed fee | In Progress | L8070 | E31029 | Harborlight Port Authority | 78.31% | 98800 | 77370.28 | 78447.2 | 0 | 0 | 77370.28 | 12593.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707 | 11691 | 006VUaFglEFVHca12y | FALSE
25-PC-35553 | Rushgrass Draw Rail Siding - Data Recovery | Time and material | In Progress | L8070 | E31034 | Highland Builders | 0% | 589900 | 421582.2 | 444589.27 | 34140.9 | 25253.56 | 446922.5 | 39292.52 | 14187.02 | 0 | 25340.3 | 0 | 25340.3 | 0 | 262.5 | 0 | 8862 | 12199 | 006D8PslkkIkjLNFEj | FALSE
25-PC-35620 | Task Order 24: Hackberry Bend Solar Class III Survey | Time and material | Completed | L8070 | E31023 | Brightwater Power Cooperative | 100% | 2007200 | 1364896 | 1423506.24 | 0 | 0 | 1364896 | 252057.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10363 | 006VikVhnB7nYDqM1Z | FALSE
25-PC-35740 | Oak Terrace Transmission Line - Historic Resources Evaluation | Fixed fee | In Progress | L8070 | E31032 | Northfield Telecom Holdings | 2% | 28600 | 572 | 15121.1 | 0 | 0 | 572 | 19.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 13631 | 006YVPkU8UMdHkuweJ | FALSE
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | Fixed fee | In Progress | L8070 | E31032 | Highland Water District | 100% | 204800 | 187347.98 | 136396.8 | 20542.17 | 10066.4 | 204800 | 14147.85 | 8450.27 | 0 | 17452.02 | 0 | 17452.02 | 0 | 198.25 | 0 | 2527 | 12481 | 006Xl5XGsjmtkJRYT3 | FALSE
25-PC-35779 | Task Order 9: Juniper Wash Wastewater Plant Built Environment Survey | Fixed fee | In Progress | L8070 | E31029 | Keystone Energy Partners | 83% | 124800 | 101478.5 | 84973.75 | 1344.91 | 1274.18 | 103584 | 12976.8 | 923.32 | 0 | 2105.5 | 0 | 2105.5 | 0 | 12.25 | 0 | 746 | 12804 | 006uDvc6ydBmm9ZvVB | FALSE
25-PC-35850 | Pebble Beach Road Environmental Review Support | Time and material | Cost Tracking on Closed Project | L8070 | E31029 | Blue Mesa Port Authority | 0% | 53400 | 36312 | 37978.08 | 0 | 0 | 36312 | 3977.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 10214 | 006LsTOYFKRVTfgCIA | FALSE
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | Fixed fee | In Progress | L8070 | E31023 | Ridgeline Energy Partners | 91.71% | 83700 | 76761.27 | 61050.78 | 0 | 0 | 76761.27 | 4815.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872 | 14433 | 006ax95Hrd0Kwlv565 | FALSE
25-PC-35958 | Task Order 20: Pebble Beach Road Levee Repair Class III Survey | Fixed fee | Final Billing/Invoice | L8070 | E31023 | High Plains Construction Co. | 100% | 67300 | 67300 | 54896.61 | 0 | 0 | 67300 | 6313.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806 | 11951 | 0068KvhmWEnNyFSvOs | FALSE
25-PC-35963 | Quail Run Substation - Section 106 Consultation | Time and material | In Progress | L8070 | E31032 | Heartland Transit Authority | 0% | 320000 | 290771 | 216192 | 1525.35 | 858.11 | 290771 | 22628.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 11878 | 006rksaTKwza7JZyIC | FALSE
25-PC-35970 | Eagle Bend Wind Farm Phase II Testing | Fixed fee | In Progress | L8070 | E31029 | Sunrise Telecom Holdings | 30.75% | 53200 | 16359 | 38886.26 | 0 | 0 | 16359 | 2355.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15492 | 006U2XVtVDXe4FIOhX | FALSE
25-PC-36007 | Larkspur Rail Siding Phase II Testing | Fixed fee | On Hold | L8070 | E31034 | Lakecrest Power Cooperative | 0.98% | 21700 | 212.66 | 16244.62 | 0 | 0 | 212.66 | 28.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 13081 | 006IVORE4kUfGP5elJ | FALSE
25-PC-36030 | Stone Mill Solar Cultural Resources Monitoring | Time and material | Completed | L8070 | E31029 | Summit Transit Authority | 100% | 89200 | 46384 | 57064.52 | 0 | 0 | 46384 | 6387.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 963 | 15291 | 0065EPNLciZIqwcbKn | FALSE
25-PC-36051 | Riverbend Levee Repair Archaeological Testing | Fixed fee | In Progress | L8070 | E31029 | Ironbridge Engineering, Inc. | 67.74% | 405400 | 274617.96 | 250415.58 | 0 | 0 | 274617.96 | 16624.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3587 | 12649 | 006PZPqBh8X0LH1lF8 | FALSE
25-PC-36071 | Task Order 12: Foxglove Transmission Line Archaeological Testing | Fixed fee | Final Billing/Invoice | L8070 | E31034 | Westwind Development Group | 100% | 245200 | 245200 | 202167.4 | 0 | 0 | 245200 | 23198.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 15795 | 006eU0FMlp3n1SM7p1 | FALSE
25-PC-36093 | Pine Hollow Pipeline Cultural Resources Assessment | Fixed fee | Lab/Curation | L8070 | E31023 | High Plains Construction Co. | 70.61% | 213300 | 149533.07 | 157884.66 | 1257.73 | 408.99 | 150611.13 | 9698.44 | 180.93 | 0 | 1078.06 | 0 | 1078.06 | 0 | 4.75 | 0 | 2595 | 11951 | 006nUn2669tKiaO2Ur | TRUE
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | Time and material | In Progress | L8070 | E31032 | Sunrise Development Group | 0% | 114200 | 114200 | 78124.22 | 0 | 0 | 114200 | 9149.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1254 | 15389 | 006FIIwNuYqcigN22y | FALSE
25-PC-36197 | Windmill Flat Rail Siding - Historic Resources Evaluation | Fixed fee | On Hold | L8070 | E31034 | Westwind County | 80.16% | 35900 | 28777.44 | 26935.77 | 0 | 0 | 28777.44 | 1403.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15753 | 006iek5Tra5dggb2TW | FALSE
25-PC-36251 | Kestrel Butte Environmental Review Support | Fixed fee | Lab/Curation | L8080 | E31043 | Evergreen Power Cooperative | 100% | 39200 | 39200 | 30446.64 | 0 | 0 | 39200 | 7795.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 11431 | 0066H1ULeExjQzoJHi | TRUE
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | Time and material | In Progress | L8080 | E31043 | Lakecrest Development Group | 0% | 28100 | 24500.73 | 19141.72 | 68.79 | 39.28 | 24522.2 | 2800.86 | 24.43 | 0 | 21.47 | 0 | 21.47 | 0 | 0.5 | 0 | 0 | 12986 | 006WMAeLaGiHsxJSBV | FALSE
25-PC-36313 | Task Order 27: Coyote Springs Solar Historic Resources Evaluation | Time and material | Completed | L8080 | E31041 | Stonebridge Land Company | 100% | 135100 | 91868 | 94691.59 | 0 | 0 | 91868 | 26835.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932 | 14975 | 006eefNypxRqcASp9h | FALSE
25-PC-36332 | Goldfinch Data Recovery | Fixed fee | In Progress | L8080 | E31041 | Coastal Rail Partners | 54.3% | 871000 | 455814.95 | 618958.05 | 22798.08 | 16927.19 | 472953 | 36637.01 | 6945.41 | 0 | 17138.05 | 0 | 17138.05 | 0 | 135.25 | 0 | 11625 | 11259 | 006pdsDuiUffH76IR2 | FALSE
25-PC-36336 | Sea Oat Canal Lining Data Recovery | Fixed fee | In Progress | L8080 | E31041 | Sunrise County | 91.66% | 36400 | 29544.7 | 25854.92 | 2112.85 | 3414.86 | 33364.24 | 3910.36 | 2948.67 | 0 | 3819.54 | 0 | 3819.54 | 0 | 54.25 | 0 | 278 | 15336 | 006IAnaK2DWAJz3Fky | FALSE
25-PC-36352 | Phase I: Plover Cove Substation Paleontological Monitoring | Fixed fee | In Progress | L8080 | E31043 | Coastal Utilities | 13.84% | 3262900 | 413628.97 | 2263196.88 | 32159.93 | 24787.42 | 451585.36 | 44802 | 16634.52 | 0 | 37956.39 | 0 | 37956.39 | 0 | 212 | 5.75 | 15961 | 11319 | 006Hu9SIvEf4AL4mN8 | FALSE
25-PC-36366 | Lone Pine Solar Data Recovery | Fixed fee | In Progress | L8080 | E31041 | Pioneer County | 38.09% | 119500 | 41825.58 | 101598.9 | 3230.49 | 1963.91 | 45517.55 | 7817.66 | 1943.35 | 0 | 3691.97 | 0 | 3691.97 | 0 | 34.5 | 1.5 | 0 | 13727 | 0062LLgThrF43B2BNh | FALSE
25-PC-36464 | Larkspur Highway Widening Cultural Resources Assessment | Time and material | In Progress | L8080 | E31043 | Summit Port Authority | 0% | 102300 | 76761.1 | 72751.63 | 0 | 0 | 76761.1 | 3972.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15239 | 006JAVz55WfNKNivgl | FALSE
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | Fixed fee | In Progress | L8080 | E31047 | Silverline Port Authority | 100% | 33100 | 33100 | 25870.96 | 0 | 0 | 33100 | 2707.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 14747 | 006OoWKip6VHMRtk7K | FALSE
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | Fixed fee | In Progress | L8080 | E31043 | Summit Renewables LLC | 77.46% | 88300 | 67497.4 | 54269.18 | 1290.49 | 978.27 | 68397.18 | 5716.91 | 243.75 | 0 | 899.78 | 0 | 899.78 | 0 | 3.75 | 0 | 568 | 15274 | 0069yED79JsFQskmbp | FALSE
25-PC-36532 | Sparrow Hill Cell Tower - Architectural History Survey | Fixed fee | On Hold | L8080 | E31043 | Highland Construction Co. | 47.52% | 67300 | 31980.96 | 46773.5 | 0 | 0 | 31980.96 | 2911.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519 | 12239 | 006cDVnd3G3abo0SHQ | TRUE
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8080 | E31047 | Coastal Builders | 73.77% | 116000 | 85573.2 | 66050.4 | 0 | 0 | 85573.2 | 10037.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559 | 11038 | 006pn7Utp9SgqdraZp | FALSE
25-PC-36637 | Lantern Bay Fiber Route Environmental Review Support | Fixed fee | Final Billing/Invoice | L8090 | E31052 | Harborlight Builders | 100% | 44400 | 44400 | 36003.96 | 0 | 0 | 44400 | 5535.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 11612 | 006UwnhGl6YExEtOzc | FALSE
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | Time and material | In Progress | L8090 | E31051 | Pioneer Development Group | 0% | 181300 | 174825.53 | 117609.31 | 10696.27 | 9152.39 | 181300 | 28014.33 | 2394.85 | 0 | 6474.47 | 0 | 6474.47 | 0 | 34.75 | 0 | 1691 | 13750 | 0065jlE4jCgw2s6jW6 | FALSE
25-PC-36645 | Falcon Mesa Archaeological Testing | Fixed fee | In Progress | L8090 | E31050 | High Plains Renewables LLC | 100% | 25400 | 24158.24 | 20302.22 | 1769.21 | 1443.04 | 25400 | 2374.28 | 418.81 | 0 | 1241.76 | 0 | 1241.76 | 0 | 5.25 | 0 | 525 | 12128 | 006QXp63WLVBcUN9WR | FALSE
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | Time and material | In Progress | L8090 | E31051 | Ridgeline County | 0% | 137400 | 108023.85 | 99958.5 | 0 | 0 | 108023.85 | 6758.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489 | 14393 | 006HHTrtv757H0HVlu | FALSE
25-PC-36657 | Stone Mill Park Improvements Phase II Testing | Time and material | Final Reporting/Review | L8090 | E31050 | Timberline Planning Associates | 0% | 255700 | 121473 | 186833.25 | 7769.34 | 5778.47 | 128243.4 | 6584.56 | 3654.04 | 0 | 6770.4 | 0 | 6770.4 | 0 | 51.25 | 0 | 1796 | 15643 | 006CgebKKNTltl5iYZ | FALSE
25-PC-36697 | Phase III: Juniper Wash Solar Built Environment Survey | Fixed fee | Completed | L8090 | E31051 | Ironbridge County | 100% | 197400 | 197400 | 133797.72 | 0 | 0 | 197400 | 27752.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2124 | 12563 | 0061UFCuneX0z3U7NR | FALSE
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Fixed fee | Final Reporting/Review | L8090 | E31050 | Lakecrest Development Group | 100% | 74000 | 66065.35 | 56358.4 | 4540.43 | 4019.93 | 74000 | 10704.82 | 5800.69 | 0 | 7934.65 | 0 | 7934.65 | 0 | 90.25 | 0 | 393 | 12986 | 0064BpbEL5A5JfcKp1 | TRUE
25-PC-36799 | Meadowlark Substation Phase I Survey | Fixed fee | Final Reporting/Review | L8100 | E31063 | Ironbridge Infrastructure Group | 100% | 32900 | 30883.36 | 26389.09 | 1021.14 | 636.68 | 32900 | 2511.69 | 454.16 | 0 | 2016.64 | 0 | 2016.64 | 0 | 6 | 0 | 161 | 12667 | 006fbeauIaqrRSw9vG | FALSE
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | Fixed fee | In Progress | L8100 | E31062 | Prairie Wind Transit Authority | 100% | 24200 | 22550.8 | 16235.78 | 1188.16 | 889.71 | 24200 | 5363.38 | 190.12 | 0 | 1649.2 | 0 | 1649.2 | 0 | 2.5 | 0 | 182 | 14127 | 006EjMECyIvHI2WS1G | TRUE
25-PC-36832 | Stone Mill Phase I Survey | Fixed fee | In Progress | L8100 | E31061 | Canyon Construction Co. | 56.16% | 78400 | 44029.44 | 52449.6 | 0 | 0 | 44029.44 | 5773.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 565 | 10448 | 006ICDyFbaqwbGXaf3 | TRUE
25-PC-36838 | Phase II: Granite Pass Highway Widening Environmental Review Support | Time and material | Final Reporting/Review | L8100 | E31062 | Canyon Construction Co. | 0% | 216400 | 203236.1 | 160499.18 | 18636.57 | 15159.29 | 216400 | 30802.72 | 8818.99 | 0 | 13163.9 | 0 | 13163.9 | 0 | 114.75 | 10.25 | 1740 | 10448 | 006lRHOKpdcb4lp2o6 | FALSE
25-PC-36876 | Kestrel Butte Wastewater Plant - GIS Mapping | Fixed fee | Completed | L8100 | E31062 | Mesa Verde Land Company | 100% | 337000 | 337000 | 240685.4 | 0 | 0 | 337000 | 68836.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13275 | 006dqMwupohPxIwF9x | FALSE
25-PC-36896 | Slate Ridge Pipeline Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8100 | E31059 | Blue Mesa County | 100% | 184200 | 184200 | 117335.4 | 0 | 0 | 184200 | 27818.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761 | 10001 | 006Ud7L8J4BpdL07s2 | FALSE
25-PC-36909 | Aspen Ridge Water Main Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8100 | E31059 | High Plains Construction Co. | 100% | 41900 | 41900 | 30260.18 | 0 | 0 | 41900 | 3735.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 11951 | 006ZobbfEjeYNsfrUs | TRUE
25-PC-36971 | North Fork Historic Resources Evaluation | Fixed fee | Completed | L8100 | E31058 | High Plains Engineering, Inc. | 100% | 85100 | 85100 | 64888.75 | 0 | 0 | 85100 | 12315.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715 | 12054 | 006BR19loXYL852jNi | TRUE
25-PC-36988 | Cedar Hollow Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | L8100 | E31063 | Northfield Water District | 100% | 246000 | 51414 | 173331.6 | 0 | 0 | 51414 | 10419.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370 | 13685 | 006ZDVEhfaTuAztKPC | FALSE
25-PC-36993 | Sandpiper Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8100 | E31059 | Northfield Telecom Holdings | 100% | 702000 | 702000 | 446191.2 | 0 | 0 | 702000 | 52464.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6519 | 13631 | 006LDPL2PCS92gVcEe | FALSE
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | Time and material | In Progress | L8100 | E31055 | Brightwater Power Cooperative | 0% | 75400 | 71354.11 | 50299.34 | 4800.62 | 4700.18 | 75400 | 11090.03 | 816.92 | 0 | 4045.89 | 0 | 4045.89 | 0 | 10.5 | 0 | 503 | 10363 | 006Y1P33Aw9fdSaIWO | FALSE
25-PC-37188 | On-Call: Lone Pine Airport Apron Cultural Resources Assessment | Time and material | In Progress | L8100 | E31058 | Ironbridge Engineering, Inc. | 0% | 131600 | 103670.5 | 95554.76 | 0 | 0 | 103670.5 | 4363.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906 | 12649 | 006OOMuh7KfGVtJK0x | FALSE
25-PC-37359 | Bramble Creek Water Main Curation | Fixed fee | Completed | L8100 | E31059 | Ridgeline Rail Partners | 100% | 228400 | 228400 | 164950.48 | 0 | 0 | 228400 | 17989.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116 | 14455 | 006Xqr10RiX5iN20GW | TRUE
25-PC-37371 | Phase II: Ember Valley Water Main Class III Survey | Fixed fee | In Progress | L8110 | E31074 | Evergreen Power Cooperative | 43.16% | 292700 | 120692.53 | 199428.52 | 4989.63 | 5342.49 | 126329.32 | 18420.57 | 3309.39 | 0 | 5636.79 | 0 | 5636.79 | 0 | 55.75 | 0 | 1798 | 11431 | 006w9CV2vg1jFpmeAm | FALSE
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | Fixed fee | In Progress | L8110 | E31074 | Silverline Construction Co. | 92.76% | 59200 | 54913.92 | 50698.88 | 0 | 0 | 54913.92 | 4467.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595 | 14700 | 006Z9SGLwJvGoYzNYc | FALSE
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Time and material | Cost Tracking on Closed Project | L8110 | E31068 | Cardinal Rail Partners | 0% | 83200 | 22297.6 | 60186.88 | 0 | 0 | 22297.6 | 15100.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 10792 | 006zAAD71CtbVBLO5F | FALSE
25-PC-37487 | Sparrow Hill Airport Apron Environmental Review Support | Fixed fee | Final Billing/Invoice | L8110 | E31073 | Ironbridge Port Authority | 100% | 43400 | 43400 | 34525.12 | 0 | 0 | 43400 | 3533.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12704 | 006y7jz6fLEPYCo2JY | FALSE
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | Time and material | In Progress | L8110 | E31070 | Lakecrest Construction Co. | 0% | 458200 | 311576 | 301449.78 | 0 | 0 | 311576 | 23357.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5452 | 12952 | 006xBLNAJytvq9UZlu | FALSE
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Fixed fee | Lab/Curation | L8110 | E31070 | Canyon Energy Partners | 100% | 21500 | 20397.5 | 15617.6 | 1468.48 | 782.85 | 21500 | 3334.4 | 242.22 | 0 | 1102.5 | 0 | 1102.5 | 0 | 2.5 | 0 | 227 | 10492 | 0063uFHaPdaAI5gwj5 | FALSE
25-PC-37544 | Sparrow Hill Historic Resources Evaluation | Fixed fee | Final Reporting/Review | L8110 | E31074 | Harborlight Water District | 78.22% | 1009600 | 789709.12 | 644730.56 | 0 | 0 | 789709.12 | 36310.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7236 | 11739 | 0064MXdndCBWzNXssJ | FALSE
25-PC-37612 | Elk Meadow Solar Historic Resources Evaluation | Time and material | On Hold | L8110 | E31074 | Granite State Infrastructure Group | 0% | 134400 | 87628.8 | 94725.12 | 0 | 0 | 87628.8 | 4509.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489 | 11510 | 0069c85W5zr00YrPqw | FALSE
25-PC-37630 | Goldfinch Solar Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8110 | E31070 | Riverstone Construction Co. | 100% | 528200 | 528200 | 365998.97 | 0 | 0 | 528200 | 65660.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4239 | 14599 | 006uuxbp9bu3FbNjpi | FALSE
25-PC-37675 | Copper Flats Park Improvements - Phase I Survey | Fixed fee | Final Billing/Invoice | L8110 | E31068 | High Plains Water District | 100% | 129900 | 129900 | 96138.99 | 0 | 0 | 129900 | 7949.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740 | 12150 | 006Qtt49ITndgbzBko | FALSE
25-PC-37732 | Hawk Point Housing Development Class III Survey | Fixed fee | In Progress | L8110 | E31068 | Lakecrest Telecom Holdings | 87.93% | 72900 | 59413.97 | 45824.94 | 3672.15 | 2236.96 | 64100.97 | 8340.96 | 1152.55 | 0 | 4687 | 0 | 4687 | 0 | 17.5 | 0 | 436 | 13182 | 006tXacJZpPEQXcrl4 | FALSE
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Time and material | Final Reporting/Review | L8110 | E31074 | Blue Mesa Environmental Consultants | 0% | 72200 | 69466.7 | 44893.96 | 0 | 0 | 69466.7 | 10674.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 10083 | 006Xm6nLuctsLrdqtd | FALSE
25-PC-37841 | Coyote Springs Data Recovery | Fixed fee | On Hold | L8110 | E31073 | Granite State Resources Corp. | 24.52% | 243900 | 59804.28 | 144430.51 | 0 | 0 | 59804.28 | 5311.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1293 | 11571 | 006nZuoZlRVVxiuITB | FALSE
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | Fixed fee | In Progress | L8110 | E31068 | Highland Construction Co. | 100% | 7900 | 7900 | 6020.59 | 0 | 0 | 7900 | 576.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 12239 | 00687YwawEFFa6i5GB | FALSE
25-PC-37903 | Sandpiper Mine Expansion Curation | Fixed fee | Final Billing/Invoice | L8110 | E31070 | Harborlight Port Authority | 100% | 195600 | 195600 | 128411.4 | 0 | 0 | 195600 | 20366.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2171 | 11691 | 006qUqYfRlABubTXj1 | TRUE
25-PC-37920 | Heron Marsh Mine Expansion Class III Survey | Time and material | In Progress | L8110 | E31074 | Granite State Development Group | 0% | 138600 | 64957.08 | 92806.56 | 5630.62 | 4217.46 | 69844.2 | 5320.64 | 2658.44 | 0 | 4887.12 | 0 | 4887.12 | 0 | 62.5 | 0 | 2102 | 11469 | 006jtZQXAfoDM2e9fi | FALSE
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | Fixed fee | In Progress | L8120 | E31079 | Evergreen Development Group | 74.2% | 148100 | 107447.04 | 106809.72 | 3692.08 | 1971.76 | 109890.2 | 11412.65 | 1880.06 | 0 | 2443.16 | 0 | 2443.16 | 0 | 34.5 | 0 | 1080 | 11371 | 006VFeNW25Z1LVv8nr | FALSE
25-PC-37979 | Pine Hollow Wind Farm - Built Environment Survey | Fixed fee | Final Billing/Invoice | L8120 | E31079 | Sunrise Transit Authority | 100% | 230300 | 230300 | 172720.13 | 0 | 0 | 230300 | 39701.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635 | 15537 | 006TweF20mPYcm96pc | FALSE
25-PC-37994 | Blue Heron Harbor Dredging - Curation | Time and material | On Hold | L8120 | E31079 | Westwind Energy Partners | 0% | 326300 | 80269.8 | 217772.62 | 0 | 0 | 80269.8 | 4908.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15833 | 006FU0sn81hbZxEO0T | FALSE
25-PC-38006 | Timber Gap Wastewater Plant Archaeological Testing | Time and material | In Progress | L8120 | E31079 | Westwind Infrastructure Group | 0% | 112000 | 46616.5 | 75667.2 | 0 | 0 | 46616.5 | 5725.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505 | 15890 | 006IySCkX5gPhMOgqj | FALSE
25-PC-38036 | Elk Meadow Mixed-Use Development - Maritime Remote Sensing Survey | Fixed fee | Completed | L8120 | E31079 | Harborlight County | 100% | 27300 | 27300 | 23352.42 | 0 | 0 | 27300 | 2094.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 11648 | 006bdgViH3RUV4Glpd | FALSE
25-PC-38042 | Oak Terrace School Campus GIS Mapping | Fixed fee | In Progress | L8120 | E31079 | Westwind Engineering, Inc. | 82.9% | 24300 | 20144.7 | 19082.79 | 0 | 0 | 20144.7 | 1550.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 15856 | 006nVydGVlmBoFRc4D | FALSE
25-PC-38070 | Phase III: Willow Springs Wastewater Plant Historic Resources Evaluation | Fixed fee | In Progress | L8120 | E31079 | Silverline Construction Co. | 62.2% | 132800 | 82601.6 | 116864 | 0 | 0 | 82601.6 | 6178.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14700 | 006GQq4WONYJaj5Tjh | FALSE
25-PC-38107 | Task Order 13: Pebble Beach Road Substation Cultural Resources Monitoring | Fixed fee | In Progress | L8120 | E31079 | High Plains Renewables LLC | 33.23% | 234600 | 71933.85 | 208913.08 | 4090.82 | 4395.58 | 77957.58 | 9996.78 | 698.95 | 0 | 6023.73 | 0 | 6023.73 | 0 | 17.5 | 0 | 0 | 12128 | 0060FsgRVS2AZiIj49 | FALSE
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | Fixed fee | In Progress | L8120 | E31079 | Stonebridge Land Company | 82.14% | 25300 | 19246.71 | 16961.12 | 1558.13 | 1258.93 | 20781.42 | 1825.02 | 11.97 | 0 | 1534.71 | 0 | 1534.71 | 0 | 0.25 | 0 | 345 | 14975 | 006prj2RTzfVo5cpTj | FALSE
25-PC-38196 | Sea Oat Cell Tower Built Environment Survey | Fixed fee | In Progress | L8120 | E31079 | Heartland Transit Authority | 59.3% | 1160700 | 688295.1 | 717428.67 | 0 | 0 | 688295.1 | 29778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10395 | 11878 | 0067Jt6CgUkU5bT4Vs | TRUE
25-PC-38282 | Task Order 16: Fern Valley Reservoir Architectural History Survey | Time and material | In Progress | L8120 | E31079 | Pioneer County | 0% | 1334100 | 672386.4 | 876348.58 | 0 | 0 | 672386.4 | 60030.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17329 | 13727 | 006DAdBGxh2fQTsjKY | FALSE
25-PC-38296 | Ember Valley Pipeline - GIS Mapping | Fixed fee | In Progress | L8120 | E31079 | Ironbridge Infrastructure Group | 48.51% | 173000 | 73131.65 | 111169.8 | 6398.07 | 3714.42 | 83922.3 | 9760.12 | 4951.65 | 0 | 10790.65 | 0 | 10790.65 | 0 | 117.75 | 0 | 1482 | 12667 | 006ZLfK745GEwU001Z | TRUE
25-PC-38332 | Redbud GIS Mapping | Fixed fee | In Progress | L8120 | E31079 | Pioneer Power Cooperative | 78.52% | 899800 | 706522.96 | 754394.62 | 0 | 0 | 706522.96 | 82925.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13961 | 13831 | 006cnNhjkQz87YU4r8 | FALSE
25-PC-38333 | Pine Hollow Cell Tower Phase II Testing | Fixed fee | In Progress | L8120 | E31079 | High Plains Environmental Consultants | 72.62% | 78300 | 56861.46 | 51450.4 | 0 | 0 | 56861.46 | 2615.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 12089 | 006o2zFjqgNv2O22mW | FALSE
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | Fixed fee | In Progress | L8120 | E31079 | Canyon Energy Partners | 72.64% | 136400 | 99080.96 | 86736.76 | 0 | 0 | 99080.96 | 10080.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342 | 10492 | 0061RzEVawhKPu6gVb | FALSE
25-PC-38461 | Rushgrass Draw Substation Phase II Testing | Fixed fee | Final Billing/Invoice | L8130 | E31097 | Sunrise Water District | 100% | 187400 | 187400 | 143548.4 | 0 | 0 | 187400 | 16834.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15575 | 006HSdHLoEmIyRlPoC | FALSE
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | Time and material | In Progress | L8130 | E31105 | Northfield Port Authority | 0% | 496400 | 460087.32 | 357705.84 | 31289.55 | 11975.97 | 481730.55 | 28665.35 | 10973.75 | 0 | 21643.23 | 0 | 21643.23 | 0 | 208.5 | 0 | 5296 | 13558 | 006lIaF6xy4xFEnjHD | FALSE
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | Fixed fee | In Progress | L8130 | E31097 | Highland Rail Partners | 87.47% | 176400 | 154297.08 | 137697.84 | 0 | 0 | 154297.08 | 18547.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2964 | 12394 | 006kdkmYynn2v60Ahb | FALSE
25-PC-38596 | Tansy Flat Pipeline Data Recovery | Fixed fee | In Progress | L8130 | E31088 | Westwind Development Group | 51.6% | 178000 | 91848 | 148416.4 | 0 | 0 | 91848 | 13785.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15795 | 006fJ7QzLuL86QcgfF | FALSE
25-PC-38606 | Silver Lake School Campus - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8130 | E31105 | Sunrise Planning Associates | 58.5% | 34800 | 20358 | 26816.2 | 0 | 0 | 20358 | 3231.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 15406 | 006vvnLYkvetqurJ0n | FALSE
25-PC-38659 | On-Call: Elk Meadow School Campus Architectural History Survey | Time and material | Completed | L8130 | E31088 | Silverline Construction Co. | 100% | 3059900 | 927149.7 | 2017698.06 | 0 | 0 | 927149.7 | 295853.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14700 | 0065NpWfvS5HaSOmlQ | FALSE
25-PC-38701 | Slate Ridge Curation | Time and material | In Progress | L8130 | E31092 | Northfield Port Authority | 0% | 156400 | 102197.06 | 98735.32 | 7307.43 | 4245.44 | 109600.75 | 14986.1 | 1363.11 | 0 | 7403.69 | 0 | 7403.69 | 0 | 24.75 | 0 | 1417 | 13558 | 006oUV56BVdA29vlTC | FALSE
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | Fixed fee | In Progress | L8130 | E31092 | Sunrise Transit Authority | 100% | 63900 | 60446.65 | 41637.24 | 2768.29 | 1054.95 | 63900 | 8507.85 | 647.72 | 0 | 3453.35 | 0 | 3453.35 | 0 | 13.75 | 0 | 740 | 15537 | 0062tK1Axtbl1JscEt | FALSE
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Fixed fee | Final Reporting/Review | L8130 | E31088 | Sunrise Planning Associates | 100% | 10400 | 9781.64 | 5866.64 | 410.74 | 192.68 | 10400 | 3099.01 | 345.22 | 0 | 618.36 | 0 | 618.36 | 0 | 8 | 0 | 62 | 15406 | 006jCLaQQiIwcrLc6T | FALSE
25-PC-38879 | Kestrel Butte Built Environment Survey | Fixed fee | In Progress | L8130 | E31095 | Ridgeline County | 73.92% | 119700 | 88482.24 | 70323.75 | 0 | 0 | 88482.24 | 7381.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712 | 14393 | 006yElDE3RZU2yxGcN | TRUE
25-PC-38970 | Ember Valley Park Improvements Curation | Time and material | Final Billing/Invoice | L8130 | E31105 | Redtail Infrastructure Group | 100% | 160100 | 31539.7 | 117257.24 | 0 | 0 | 31539.7 | 10547.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2288 | 14267 | 006LRFS3wBaebszeXW | FALSE
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | Time and material | In Progress | L8130 | E31107 | Pioneer Transit Authority | 0% | 244000 | 201680 | 174704 | 0 | 0 | 201680 | 30391.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978 | 13885 | 006NVLrEhsoak6Qblm | FALSE
25-PC-39055 | Dove Canyon Transmission Line - Cultural Resources Assessment | Time and material | Final Billing/Invoice | L8130 | E31105 | Brightwater Land Company | 100% | 128700 | 79794 | 90984.64 | 0 | 0 | 79794 | 15728.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10261 | 006mQN63DTFyMOW7vs | FALSE
25-PC-39085 | Slate Ridge Environmental Review Support | Fixed fee | In Progress | L8130 | E31088 | Summit Renewables LLC | 99.26% | 120700 | 119806.82 | 69209.38 | 0 | 0 | 119806.82 | 8243.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216 | 15274 | 006IJQJkuEPTQ7ozkg | FALSE
25-PC-39093 | Goldfinch Canal Lining Phase I Survey | Fixed fee | In Progress | L8130 | E31107 | Highland Builders | 49.17% | 100100 | 45898.43 | 73673.6 | 2584.54 | 1137.59 | 49219.17 | 5034.85 | 928.86 | 0 | 3320.74 | 0 | 3320.74 | 0 | 22.25 | 0 | 0 | 12199 | 006c9hfd3YxIeG3i7f | FALSE
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | Fixed fee | In Progress | L8130 | E31110 | Lakecrest Telecom Holdings | 75.29% | 90300 | 62928.94 | 58198.35 | 2667.6 | 3907.66 | 67986.87 | 7274.12 | 2464.67 | 0 | 5057.93 | 0 | 5057.93 | 0 | 61 | 0 | 858 | 13182 | 006JFjnEluWRfuWkns | FALSE
25-PC-39187 | Windmill Flat Trail - Architectural History Survey | Fixed fee | Lab/Curation | L8130 | E31092 | Mesa Verde Planning Associates | 49.15% | 28100 | 13811.15 | 19470.49 | 0 | 0 | 13811.15 | 1617.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 13344 | 006XF1KFN7icaJfbap | FALSE
25-PC-39222 | Phase I: Badger Hollow Trail GIS Mapping | Fixed fee | Completed | L8130 | E31097 | Lakecrest Power Cooperative | 100% | 27000 | 27000 | 21648.6 | 0 | 0 | 27000 | 3418.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359 | 13081 | 0065aL3LLpQtFgrpcy | TRUE
25-PC-39318 | Lone Pine Fiber Route - Class III Survey | Fixed fee | In Progress | L8130 | E31095 | Canyon Utilities | 68.21% | 104300 | 70186.4 | 69818.42 | 424.17 | 523.58 | 71143.03 | 2905.2 | 0 | 0 | 956.63 | 0 | 956.63 | 0 | 0 | 0 | 810 | 10611 | 006jtbyCEaJeqI5IMv | TRUE
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Time and material | Final Reporting/Review | L8130 | E31107 | Northfield Builders | 0% | 55900 | 54034.56 | 39633.1 | 2227.13 | 698.28 | 55900 | 2613.17 | 975.76 | 0 | 1865.44 | 0 | 1865.44 | 0 | 23 | 0 | 529 | 13460 | 006I7ZzrhkUk19134A | FALSE
25-PC-39398 | Silver Lake Housing Development - Data Recovery | Fixed fee | Final Reporting/Review | L8130 | E31095 | Westwind Infrastructure Group | 64.65% | 103300 | 66783.45 | 81096.61 | 0 | 0 | 66783.45 | 3670.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428 | 15890 | 006VoMfaeOBRmrNV54 | FALSE
25-PC-39422 | Willow Springs Historic Resources Evaluation | Fixed fee | In Progress | L8130 | E31088 | Redtail Water District | 25.89% | 56900 | 14948.37 | 45036.35 | 0 | 0 | 14731.41 | 1515.57 | 0 | 0 | 0 | 216.96 | 216.96 | 0 | 0 | 0 | 628 | 14359 | 006W1pBDmTXNelhgvq | FALSE
25-PC-39424 | Tansy Flat Cultural Resources Assessment | Fixed fee | In Progress | L8130 | E31110 | Redtail Rail Partners | 100% | 19700 | 17614.13 | 13882.59 | 2236.2 | 780.83 | 19700 | 2830.6 | 1617.14 | 0 | 2085.87 | 0 | 2085.87 | 0 | 22.25 | 0 | 213 | 14317 | 006LJBUDBDhKfeHiOy | TRUE
25-PC-39458 | Larkspur Park Improvements Paleontological Monitoring | Time and material | In Progress | L8130 | E31088 | Summit County | 0% | 345000 | 222777.3 | 242983.5 | 4761.03 | 5001.64 | 230912.25 | 9333.11 | 4440.82 | 0 | 8134.95 | 0 | 8134.95 | 0 | 73.25 | 0.25 | 4713 | 15070 | 0061AczdFgtk48kDf3 | FALSE
25-PC-39489 | Phase II: Fern Valley Transmission Line Paleontological Monitoring | Fixed fee | Completed | L8130 | E31095 | Highland Infrastructure Group | 100% | 460000 | 460000 | 342148 | 0 | 0 | 460000 | 27441.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12316 | 006lVbWohwURT0aOxC | FALSE
25-PC-39554 | Thistle Down Archaeological Testing | Fixed fee | In Progress | L8130 | E31107 | Summit Port Authority | 87.23% | 86700 | 63747.46 | 63594.45 | 13034.06 | 6368.81 | 75628.41 | 10096.63 | 7755.93 | 0 | 11880.95 | 0 | 11880.95 | 0 | 166.5 | 0 | 889 | 15239 | 006blbvwq0bWemjwQn | TRUE
25-PC-39569 | Badger Hollow Park Improvements GIS Mapping | Fixed fee | Completed | L8130 | E31088 | Coastal Development Group | 100% | 304300 | 304300 | 191648.14 | 0 | 0 | 304300 | 18923.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3054 | 11160 | 0068Y9o7AC4XpgFEQS | TRUE
25-PC-39661 | Windmill Flat Cultural Resources Monitoring | Time and material | Completed | L8130 | E31088 | Prairie Wind Pipeline Company | 100% | 1468900 | 998852 | 1021032.39 | 0 | 0 | 998852 | 89672.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14024 | 006Uv4kQBvivuqM7DU | FALSE
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | Time and material | In Progress | L8130 | E31092 | Canyon Planning Associates | 0% | 51000 | 51000 | 36551.7 | 0 | 0 | 51000 | 14663.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 10525 | 006u0RWzvtldLbkLnV | FALSE
25-PC-39808 | On-Call: Pine Hollow Rail Siding Architectural History Survey | Fixed fee | In Progress | L8130 | E31095 | Highland Engineering, Inc. | 55.19% | 140600 | 77597.14 | 88846.16 | 3638.09 | 1461.56 | 77597.14 | 3530.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1463 | 12284 | 0062P1sNK8ggqWdD5B | TRUE
25-PC-39873 | On-Call: Eagle Bend Battery Storage Phase II Testing | Fixed fee | In Progress | L8130 | E31095 | Prairie Wind Pipeline Company | 47.55% | 93300 | 41424.71 | 70478.82 | 2880.52 | 1243.74 | 44364.15 | 6401.39 | 584.09 | 0 | 2939.44 | 0 | 2939.44 | 0 | 9.25 | 0 | 0 | 14024 | 006PWyNjRPBtZUgzyE | FALSE
25-PC-39885 | Bramble Creek Phase I Survey | Fixed fee | In Progress | L8130 | E31107 | Highland Builders | 64.67% | 85600 | 55221.19 | 54047.84 | 186.69 | 60.79 | 55357.52 | 5592.48 | 96.88 | 0 | 136.33 | 0 | 136.33 | 0 | 1.75 | 0 | 620 | 12199 | 006fsdQvuiubtc9833 | FALSE
25-PC-39896 | Task Order 8: Raven Rock Highway Widening Archaeological Testing | Fixed fee | In Progress | L8130 | E31097 | Timberline Telecom Holdings | 74.12% | 730900 | 541743.08 | 540257.83 | 0 | 0 | 541743.08 | 42046.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 15690 | 006x47En1Zzy7D9p75 | FALSE
25-PC-39951 | Falcon Mesa Reservoir - Phase II Testing | Fixed fee | Cost Tracking on Closed Project | L8130 | E31092 | Mesa Verde Telecom Holdings | 79.54% | 87200 | 69358.88 | 65277.92 | 0 | 0 | 69358.88 | 5503.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 13431 | 006Gym7MWIaaM56Snj | TRUE
25-PC-40020 | Wildrye Curation | Fixed fee | On Hold | L8130 | E31095 | Lakecrest Telecom Holdings | 30.26% | 186200 | 56344.12 | 128340.42 | 0 | 0 | 56344.12 | 8388.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445 | 13182 | 00632shiDclWGKNfXP | TRUE
25-PC-40099 | On-Call: Sparrow Hill Pipeline Phase II Testing | Time and material | Completed | L8140 | E31122 | Coastal Rail Partners | 100% | 665100 | 135680.4 | 460201.14 | 0 | 0 | 135680.4 | 41280.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7130 | 11259 | 006rrgnFh9ltNGiFc9 | FALSE
25-PC-40170 | Plover Cove Wastewater Plant Cultural Resources Assessment | Time and material | Final Billing/Invoice | L8140 | E31128 | Harborlight County | 100% | 260400 | 177072 | 190690.92 | 0 | 0 | 177072 | 22024.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2511 | 11648 | 006LWfNn3c57VBdtVh | FALSE
25-PC-40205 | Eagle Bend Cell Tower Paleontological Monitoring | Fixed fee | Completed | L8140 | E31127 | Coastal Development Group | 100% | 88100 | 88100 | 59027 | 0 | 0 | 88100 | 4138.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754 | 11160 | 006vdmaoDfhpWb7BLh | FALSE
25-PC-40231 | Goldfinch Pipeline - Section 106 Consultation | Time and material | In Progress | L8140 | E31127 | Sunrise County | 0% | 88300 | 60462.94 | 59478.88 | 6034.13 | 3543.4 | 65426.7 | 5310.99 | 2728.08 | 0 | 4963.76 | 0 | 4963.76 | 0 | 68 | 1 | 1290 | 15336 | 006AXemqbAaHmmmSet | FALSE
25-PC-40248 | Stone Mill Cultural Resources Monitoring | Time and material | Final Billing/Invoice | L8140 | E31121 | Silverline Water District | 100% | 164500 | 10692.5 | 111854.21 | 0 | 0 | 10692.5 | 20034.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505 | 14839 | 006wY9zCcPY24KgeHO | FALSE
25-PC-40383 | North Fork Archaeological Testing | Fixed fee | In Progress | L8140 | E31127 | Summit Renewables LLC | 83.41% | 193200 | 161148.12 | 144185.16 | 0 | 0 | 161148.12 | 9621.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888 | 15274 | 006gbya5gbVxqmv5qp | FALSE
25-PC-40465 | Task Order 32: Copper Flats Solar Historic Resources Evaluation | Fixed fee | In Progress | L8140 | E31122 | Stonebridge County | 63.37% | 127600 | 77042.86 | 94627.43 | 4639.33 | 2007.3 | 80860.12 | 8695.42 | 2130.58 | 0 | 3817.26 | 0 | 3817.26 | 0 | 50.5 | 0 | 2142 | 14884 | 006gvTwrj4LH5p4Sob | FALSE
25-PC-40482 | Task Order 33: Tamarack Cell Tower Cultural Resources Assessment | Fixed fee | In Progress | L8140 | E31121 | High Plains Renewables LLC | 44.68% | 73200 | 32090.81 | 60199.68 | 546.85 | 522.13 | 32705.76 | 4733.87 | 287.44 | 0 | 614.95 | 0 | 614.95 | 0 | 3.75 | 0 | 0 | 12128 | 006WWKDsE0RMSsquS3 | FALSE
25-PC-40501 | Aspen Ridge Archaeological Testing | Fixed fee | Completed | L8140 | E31122 | Summit Engineering, Inc. | 100% | 1246400 | 1246400 | 817638.4 | 0 | 0 | 1246400 | 131008.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9946 | 15125 | 006k6YIt7n0OtCJXmw | FALSE
25-PC-40503 | Copper Flats Phase I Survey | Time and material | Lab/Curation | L8140 | E31122 | Sunrise Telecom Holdings | 0% | 43400 | 43400 | 30119.6 | 0 | 0 | 43400 | 8388.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15492 | 00615eJ2wLFpexOcLw | FALSE
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | Time and material | In Progress | L8140 | E31127 | Sunrise Water District | 0% | 71000 | 67104.25 | 49579.3 | 4476.12 | 1502.66 | 71000 | 15738.32 | 2017.75 | 0 | 3895.75 | 0 | 3895.75 | 0 | 45.75 | 0 | 880 | 15575 | 006o7Cr4nNQoXhbkA1 | FALSE
25-PC-40541 | Eagle Bend Airport Apron - Archaeological Testing | Fixed fee | In Progress | L8140 | E31121 | Ironbridge Telecom Holdings | 66.38% | 25000 | 16595 | 16850 | 0 | 0 | 16595 | 1812.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12740 | 0066wbqpFtOdck6EBP | FALSE
25-PC-40572 | Maple Fork Cell Tower Environmental Review Support | Fixed fee | In Progress | L8140 | E31122 | High Plains Engineering, Inc. | 39.51% | 88300 | 34769.84 | 67293.43 | 72.85 | 71.82 | 34887.33 | 2499.41 | 0 | 0 | 117.49 | 0 | 117.49 | 0 | 0 | 0 | 1661 | 12054 | 006xG5lBsf4IxjqGec | TRUE
25-PC-40595 | Willow Springs Levee Repair - Built Environment Survey | Fixed fee | Final Reporting/Review | L8140 | E31128 | Clearwater Builders | 39.02% | 1568300 | 594232.15 | 1302159.49 | 20039.65 | 10537.86 | 611950.66 | 105170.21 | 7018.24 | 0 | 17718.51 | 0 | 17718.51 | 0 | 95.75 | 0 | 11931 | 10855 | 006zBNBVnD1autMtSS | FALSE
25-PC-40677 | Quail Run Paleontological Monitoring | Time and material | Transferred Entity | L8140 | E31121 | Mesa Verde County | 0% | 225000 | 192903.25 | 157612.5 | 0 | 0 | 192903.25 | 32737.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651 | 13234 | 006HWZn1fZntq5uorj | FALSE
25-PC-40680 | On-Call: Eagle Bend Battery Storage Cultural Resources Assessment | Time and material | Lab/Curation | L8140 | E31127 | Summit Port Authority | 0% | 10100 | 8386.75 | 6706.4 | 0 | 0 | 8386.75 | 804.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 15239 | 006UsHUlS7C6PMqVUd | FALSE
25-PC-40708 | Lantern Bay Built Environment Survey | Fixed fee | Final Billing/Invoice | L8150 | E31137 | Lakecrest Construction Co. | 100% | 50900 | 50900 | 31379.85 | 0 | 0 | 50900 | 4835.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 12952 | 006leXbFUFy32vhgf9 | FALSE
25-PC-40722 | Goldfinch Canal Lining - Archaeological Testing | Time and material | In Progress | L8150 | E31137 | Brightwater Rail Partners | 0% | 166600 | 128119.75 | 119491.23 | 0 | 0 | 128119.75 | 5710.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 10392 | 006Xw4cerlWWKe0UVh | FALSE
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Fixed fee | Transferred Entity | L8150 | E31137 | Canyon Utilities | 100% | 50100 | 47994.45 | 34844.55 | 1713.3 | 1776.85 | 50100 | 3793.18 | 961.18 | 0 | 2105.55 | 0 | 2105.55 | 0 | 22 | 0 | 706 | 10611 | 006hY2TySRTv4gDNGg | FALSE
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Fixed fee | Final Reporting/Review | L8150 | E31150 | Northfield Water District | 100% | 46800 | 46800 | 34243.56 | 0 | 0 | 46800 | 5436.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 13685 | 006Hg6PgXft7OiRK6G | TRUE
25-PC-40880 | Pebble Beach Road Bridge Replacement Cultural Resources Assessment | Time and material | In Progress | L8150 | E31138 | Westwind Development Group | 0% | 45800 | 26615.83 | 30347.08 | 2522.5 | 1551.64 | 28954.35 | 2723.88 | 171.59 | 0 | 2338.52 | 0 | 2338.52 | 0 | 4 | 0 | 0 | 15795 | 0068yPNRAW6xNOZdZU | FALSE
25-PC-40925 | Harbor View Airport Apron - Data Recovery | Time and material | Final Reporting/Review | L8150 | E31151 | Timberline Telecom Holdings | 0% | 35000 | 23800 | 23562 | 0 | 0 | 23800 | 2509.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 15690 | 006wsicjh623pJ8jHj | FALSE
25-PC-40944 | Maple Fork Archaeological Testing | Fixed fee | Final Billing/Invoice | L8150 | E31141 | Ironbridge Construction Co. | 100% | 101400 | 101400 | 73160.1 | 0 | 0 | 101400 | 13790.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12523 | 006hRTsVlfDsHgR6Ll | FALSE
25-PC-41075 | Phase I: Cedar Hollow Airport Apron Archaeological Testing | Fixed fee | In Progress | L8150 | E31137 | Cardinal Utilities | 56.68% | 82100 | 45582.42 | 61304.07 | 1262.28 | 959.07 | 46534.28 | 2571.31 | 602.5 | 0 | 951.86 | 0 | 951.86 | 0 | 10.25 | 0 | 880 | 10833 | 006nASVQEUHhYo6pno | FALSE
25-PC-41083 | On-Call: Hackberry Bend Rail Siding Class III Survey | Time and material | On Hold | L8150 | E31138 | Lakecrest Development Group | 0% | 193500 | 36958.5 | 140887.35 | 0 | 0 | 36958.5 | 5217.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762 | 12986 | 006lURsrFxw5NqUpIx | FALSE
25-PC-41097 | On-Call: Falcon Mesa Wastewater Plant Phase II Testing | Time and material | Final Reporting/Review | L8150 | E31137 | Ironbridge County | 0% | 197800 | 151428.7 | 128154.62 | 5747.94 | 2635.57 | 157477.05 | 15153.19 | 2193.91 | 0 | 6048.35 | 0 | 6048.35 | 0 | 47 | 0 | 1070 | 12563 | 006xS8VumT0PEfYAtn | FALSE
25-PC-41187 | Hackberry Bend Trail GIS Mapping | Fixed fee | In Progress | L8150 | E31138 | High Plains County | 76.35% | 98900 | 72782.09 | 55621.36 | 2103.37 | 695.42 | 75510.15 | 2675.59 | 135.03 | 0 | 2728.06 | 0 | 2728.06 | 0 | 2.5 | 0.25 | 0 | 11980 | 0069IGcuNAiNAjCdXq | FALSE
25-PC-41252 | Oak Terrace Wastewater Plant Curation | Fixed fee | Final Reporting/Review | L8150 | E31141 | Northfield Telecom Holdings | 93.14% | 33000 | 30524.42 | 25325 | 216.64 | 133.2 | 30736.2 | 4434.49 | 159.38 | 0 | 211.78 | 0 | 211.78 | 0 | 3.75 | 0 | 349 | 13631 | 006jrf8S0vkyTjjSmz | FALSE
25-PC-41265 | Larkspur Class III Survey | Fixed fee | Cost Tracking on Closed Project | L8150 | E31138 | Ironbridge County | 95.01% | 89800 | 85318.98 | 71911.84 | 0 | 0 | 85318.98 | 10726.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140 | 12563 | 006cdnJhW1L9c6aten | FALSE
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | Fixed fee | In Progress | L8150 | E31138 | Prairie Wind Pipeline Company | 79.68% | 167900 | 130782.09 | 131616.81 | 4196.03 | 2347.07 | 133782.72 | 20763.57 | 2411.07 | 0 | 3000.63 | 0 | 3000.63 | 0 | 44.25 | 0 | 1459 | 14024 | 006Vr8HgKsR0AUvO42 | TRUE
25-PC-41372 | Thistle Down Pipeline Curation | Fixed fee | Final Billing/Invoice | L8150 | E31137 | Clearwater Port Authority | 100% | 86100 | 86100 | 63016.59 | 0 | 0 | 86100 | 9497.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10969 | 006PI3zGahQcdP1g5h | FALSE
25-PC-41383 | Harbor View Reservoir - Cultural Resources Assessment | Fixed fee | In Progress | L8150 | E31141 | Stonebridge County | 77.11% | 342200 | 263870.42 | 223902.7 | 0 | 0 | 263870.42 | 25033.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14884 | 006ZZoRJUdVFhMp06o | FALSE
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | Fixed fee | In Progress | L8150 | E31138 | Pioneer Transit Authority | 100% | 179800 | 170811.36 | 119171.44 | 12268.2 | 10516.69 | 179800 | 22408.33 | 2724.28 | 0 | 8988.64 | 0 | 8988.64 | 0 | 21.5 | 0 | 819 | 13885 | 006Z4WNJzcdFP45wi6 | FALSE
25-PC-41476 | North Fork Mixed-Use Development Archaeological Testing | Time and material | Completed | L8150 | E31151 | Highland Builders | 100% | 211900 | 79674.4 | 146804.32 | 0 | 0 | 79674.4 | 38550.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1967 | 12199 | 006HtVOjbNDFvnkldb | FALSE
25-PC-41479 | Hawk Point Trail Maritime Remote Sensing Survey | Fixed fee | In Progress | L8150 | E31138 | High Plains Engineering, Inc. | 32.18% | 633600 | 200991.35 | 405123.84 | 1564.1 | 1013.16 | 203892.48 | 17598.02 | 2074.62 | 0 | 2901.13 | 0 | 2901.13 | 0 | 40.75 | 0 | 8732 | 12054 | 006587bIbEWVEUMHbb | FALSE
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | Time and material | In Progress | L8150 | E31150 | Harborlight Transit Authority | 0% | 130200 | 121022.45 | 94156.73 | 1015.29 | 719.56 | 121022.45 | 18893.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2339 | 11703 | 00679XcW16gT57BJ0K | FALSE
25-PC-41514 | Lantern Bay Levee Repair Historic Resources Evaluation | Fixed fee | Final Reporting/Review | L8150 | E31137 | Clearwater Planning Associates | 79.21% | 48700 | 38543.24 | 31123.36 | 19.17 | 21.94 | 38575.27 | 4733.49 | 0 | 0 | 32.03 | 0 | 32.03 | 0 | 0 | 0 | 556 | 10938 | 006VF2HNqtsC3j7Lex | FALSE
25-PC-41600 | Twin Buttes Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | L8150 | E31138 | Silverline Telecom Holdings | 100% | 647300 | 647300 | 488406.31 | 0 | 0 | 647300 | 101587.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8132 | 14780 | 006gLHU2gkk8Ulpf3T | FALSE
25-PC-41603 | Task Order 22: Wren Hollow Cell Tower Paleontological Monitoring | Time and material | Final Billing/Invoice | L8150 | E31151 | Redtail Infrastructure Group | 100% | 73800 | 1992.6 | 50808.19 | 0 | 0 | 1992.6 | 7265.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 819 | 14267 | 006ZBkfLDldRhsVlwU | FALSE
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | Time and material | In Progress | L8150 | E31150 | Stonebridge Engineering, Inc. | 0% | 412300 | 290386.6 | 281889.51 | 10900.13 | 5428.4 | 300806.95 | 32557.1 | 3223.42 | 0 | 10420.35 | 0 | 10420.35 | 0 | 68.75 | 3.25 | 3365 | 14937 | 0068hRYPLpKT2SBbrK | FALSE
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | Time and material | In Progress | L8160 | E31172 | Granite State Rail Partners | 0% | 152100 | 112187.4 | 108599.4 | 0 | 0 | 112187.4 | 10190.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2573 | 11524 | 006DAQNhOD2HuJ543O | FALSE
25-PC-41764 | Stone Mill Environmental Review Support | Time and material | In Progress | L8160 | E31172 | Harborlight Transit Authority | 0% | 20700 | 16684.25 | 15642.78 | 0 | 0 | 16684.25 | 1280.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 11703 | 0065Z6Yt4mibSuftjF | FALSE
25-PC-41834 | Pebble Beach Road Data Recovery | Fixed fee | In Progress | L8160 | E31170 | Highland Rail Partners | 37.47% | 170100 | 58480.85 | 145401.48 | 5449.76 | 2791.43 | 63736.47 | 4848.33 | 2166.33 | 0 | 5255.62 | 0 | 5255.62 | 0 | 49 | 0 | 2069 | 12394 | 006wN4qreCuzFpUZgA | TRUE
25-PC-41843 | Wren Hollow Rail Siding - Section 106 Consultation | Time and material | Final Reporting/Review | L8160 | E31173 | Mesa Verde Pipeline Company | 0% | 54000 | 36720 | 35988.02 | 0 | 0 | 36720 | 4991.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13320 | 006fcGsXhXMjUZ2Xvu | FALSE
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | Time and material | In Progress | L8160 | E31170 | Highland Infrastructure Group | 0% | 39700 | 38010.35 | 25920.13 | 1909.48 | 1540.73 | 39700 | 5050.21 | 1822.99 | 0 | 1689.65 | 0 | 1689.65 | 0 | 34.75 | 0 | 577 | 12316 | 006mohwIXkKiePt8Fr | FALSE
25-PC-41931 | Sandpiper Pipeline Curation | Fixed fee | Final Billing/Invoice | L8160 | E31173 | Lakecrest Rail Partners | 100% | 56200 | 56200 | 36698.6 | 0 | 0 | 56200 | 2768.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 | 13111 | 006QMRb33F1JKmD1Ch | FALSE
25-PC-41967 | On-Call: Redbud Pipeline Section 106 Consultation | Fixed fee | On Hold | L8160 | E31170 | Lakecrest Telecom Holdings | 28.15% | 37300 | 10499.95 | 28348 | 0 | 0 | 10499.95 | 638.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 13182 | 006p5fD0uUhLT5BL2h | FALSE
25-PC-42076 | Bramble Creek Highway Widening Curation | Time and material | In Progress | L8160 | E31173 | Timberline Telecom Holdings | 0% | 319600 | 147831.26 | 227746.96 | 7795.95 | 7402.99 | 155773.55 | 10889.12 | 4523.4 | 0 | 7942.29 | 0 | 7942.29 | 0 | 81 | 1.75 | 4605 | 15690 | 0063hhfHRzieC4jqCO | FALSE
25-PC-42078 | Sea Oat Paleontological Monitoring | Fixed fee | Completed | L8160 | E31172 | Highland Telecom Holdings | 100% | 433900 | 433900 | 316573.44 | 0 | 0 | 433900 | 38245.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12458 | 006gYia3mT1UPlhz8P | TRUE
25-PC-42084 | Foxglove Built Environment Survey | Time and material | In Progress | L8160 | E31162 | Keystone Planning Associates | 0% | 1294200 | 344257.2 | 847312.74 | 0 | 0 | 344257.2 | 40851.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10280 | 12859 | 0067WcRrOXWupsyKSO | FALSE
25-PC-42097 | Tansy Flat Solar Data Recovery | Fixed fee | In Progress | L8160 | E31172 | Brightwater Power Cooperative | 46.92% | 179700 | 72979.58 | 138548.7 | 17954.79 | 4913.2 | 84315.24 | 9490.12 | 7452.62 | 0 | 11335.66 | 0 | 11335.66 | 0 | 103.25 | 0 | 1033 | 10363 | 006aEhq0JBxTfs2nA3 | FALSE
25-PC-42115 | Hawk Point Reservoir Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | L8160 | E31173 | Brightwater Land Company | 63.89% | 110400 | 70534.56 | 90660.48 | 0 | 0 | 70534.56 | 7471.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078 | 10261 | 006HFV5FV9DanmYSev | TRUE
25-PC-42136 | Phase III: Granite Pass Mixed-Use Development Maritime Remote Sensing Survey | Fixed fee | In Progress | L8160 | E31173 | Sunrise Water District | 74.67% | 31700 | 20580.8 | 23936.32 | 1376.66 | 1311.22 | 23670.39 | 3807.07 | 125.5 | 0 | 3089.59 | 0 | 3089.59 | 0 | 1.75 | 0 | 224 | 15575 | 006f9ZSQccfxxQnEiL | FALSE
25-PC-42163 | Foxglove Historic Resources Evaluation | Time and material | Final Reporting/Review | L8160 | E31170 | Canyon Construction Co. | 0% | 50700 | 38724.35 | 34430.37 | 0 | 0 | 38724.35 | 2344.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507 | 10448 | 006wRUBj9buJIcVwDM | FALSE
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Time and material | Cost Tracking on Closed Project | L8160 | E31162 | Blue Mesa Energy Partners | 0% | 17900 | 161.1 | 12066.39 | 0 | 0 | 161.1 | 1533.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10054 | 006bjfF0P5ZU1cNxSb | FALSE
25-PC-42253 | On-Call: Plover Cove Substation Phase I Survey | Time and material | In Progress | L8170 | E31175 | Northfield Power Cooperative | 0% | 67000 | 47935 | 45781.1 | 0 | 0 | 47935 | 2230.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826 | 13614 | 006QDi9PTD2ctpS0cv | FALSE
25-PC-42282 | Dove Canyon Levee Repair - Phase I Survey | Fixed fee | In Progress | L8170 | E31175 | Sunrise Telecom Holdings | 60.96% | 33000 | 20116.8 | 19255.5 | 65.01 | 61.15 | 20116.8 | 2230.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417 | 15492 | 006MUszUd2BYPhLrTW | FALSE
25-PC-42303 | Copper Flats Cell Tower Environmental Review Support | Time and material | Completed | L8170 | E31179 | Highland Resources Corp. | 100% | 147500 | 46610 | 99769 | 0 | 0 | 46610 | 20881.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 916 | 12409 | 0069f1HT1r1E5WuOd1 | FALSE
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | Fixed fee | In Progress | L8170 | E31175 | Mesa Verde Planning Associates | 78.41% | 41200 | 29924.09 | 29239.64 | 4084.74 | 2327.36 | 32304.92 | 4378.75 | 1417.57 | 0 | 2380.83 | 0 | 2380.83 | 0 | 32 | 0 | 290 | 13344 | 006c3J2vR8o6PQOMZd | FALSE
25-PC-42323 | Millbrook Cultural Resources Monitoring | Fixed fee | In Progress | L8170 | E31179 | Cardinal Land Company | 58.09% | 79800 | 46355.82 | 58357.74 | 0 | 0 | 46355.82 | 3220.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10711 | 006Y3iRRmVUh4HL1ZB | FALSE
25-PC-42343 | Phase III: Coyote Springs Pipeline Phase II Testing | Fixed fee | In Progress | L8170 | E31179 | Keystone Planning Associates | 67.64% | 6100 | 4126.04 | 4038.38 | 0 | 0 | 4126.04 | 396.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 12859 | 006zzAdvQiZe4TnMiY | TRUE
25-PC-42364 | Sparrow Hill Fiber Route - Phase I Survey | Fixed fee | In Progress | L8170 | E31179 | Mesa Verde Telecom Holdings | 63.19% | 594900 | 375917.31 | 426353.2 | 0 | 0 | 375917.31 | 44723.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7627 | 13431 | 006JD3ZHKjiXRG38qb | FALSE
25-PC-42399 | Task Order 7: Aspen Ridge Housing Development Class III Survey | Fixed fee | In Progress | L8170 | E31175 | Mesa Verde Port Authority | 56.39% | 683800 | 364616.3 | 509225.86 | 23781.26 | 10548.48 | 385594.82 | 49104.7 | 8194.67 | 0 | 20978.52 | 0 | 20978.52 | 0 | 121.5 | 5 | 10389 | 13374 | 0060SqHkoXL9Wbl1tJ | FALSE
25-PC-42528 | Slate Ridge Park Improvements - Phase I Survey | Fixed fee | In Progress | L8170 | E31175 | Sunrise County | 28.14% | 132000 | 36898.14 | 93601.2 | 732.58 | 204.04 | 37144.8 | 3423.71 | 209.06 | 0 | 246.66 | 0 | 246.66 | 0 | 4.25 | 0 | 1161 | 15336 | 006jIxDAV0bXnJZ17X | FALSE
25-PC-42569 | Larkspur Phase I Survey | Fixed fee | Final Billing/Invoice | L8170 | E31175 | Lakecrest Construction Co. | 100% | 105700 | 105700 | 81219.88 | 0 | 0 | 105700 | 8559.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085 | 12952 | 006iLijqau1mCFuN5o | FALSE
25-PC-42601 | Lantern Bay Park Improvements - Cultural Resources Monitoring | Time and material | Transferred Entity | L8170 | E31175 | Northfield Development Group | 0% | 302100 | 100989.07 | 213521.46 | 4527.63 | 5914.54 | 108000.1 | 6601.68 | 2369.94 | 0 | 7011.03 | 0 | 7011.03 | 0 | 20.75 | 0.75 | 1670 | 13499 | 006WiNbNbvArzmlPD5 | FALSE
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | Time and material | In Progress | L8180 | E31185 | High Plains County | 0% | 130300 | 128601.35 | 95796.56 | 0 | 0 | 128601.35 | 7038.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 913 | 11980 | 006vV0vT8zumnsPhtZ | FALSE
25-PC-42747 | Yarrow Point Transmission Line - Historic Resources Evaluation | Fixed fee | On Hold | L8180 | E31188 | Stonebridge Utilities | 54.33% | 128900 | 70031.37 | 87896.91 | 0 | 0 | 70031.37 | 6924.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803 | 15036 | 006hIzy1pFtEaub7rQ | TRUE
25-PC-43037 | Cedar Hollow Section 106 Consultation | Fixed fee | Completed | L8180 | E31188 | Summit Renewables LLC | 100% | 250200 | 250200 | 196231.86 | 0 | 0 | 250200 | 41730.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 15274 | 0064IB6ugxO7YfHJgJ | FALSE
25-PC-43061 | Plover Cove Built Environment Survey | Fixed fee | Final Billing/Invoice | L8190 | E31192 | Harborlight Builders | 100% | 106500 | 106500 | 81184.95 | 0 | 0 | 106500 | 12605.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 11612 | 006tmgc6C0x3SyxL2t | FALSE
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Time and material | Transferred Entity | L8190 | E31193 | Highland Planning Associates | 0% | 62000 | 54684.75 | 44404.4 | 0 | 0 | 54684.75 | 5528.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 12340 | 006azCRvmmADgHBGUq | FALSE
25-PC-43075 | Coyote Springs Reservoir Cultural Resources Assessment | Time and material | On Hold | L8190 | E31193 | Prairie Wind County | 0% | 381100 | 124619.7 | 238416.16 | 0 | 0 | 124619.7 | 13607.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2548 | 13978 | 0060Uceq3Uv2Y4QnKw | FALSE
25-PC-43106 | Kestrel Butte Wastewater Plant - Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | L8190 | E31192 | Coastal Land Company | 100% | 63000 | 42840 | 41082.3 | 0 | 0 | 42840 | 3440.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677 | 11195 | 006heZccpHfPMc0QAi | FALSE
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | Fixed fee | In Progress | L8200 | E31196 | Ridgeline County | 100% | 128400 | 128209.36 | 106315.2 | 3160.93 | 1153.81 | 128400 | 37385.25 | 38.9 | 0 | 190.64 | 0 | 190.64 | 0 | 0.5 | 0 | 1431 | 14393 | 006baiJUIjxph20jIi | FALSE
25-PC-43244 | Windmill Flat Environmental Review Support | Fixed fee | Final Billing/Invoice | L8200 | E31200 | Mesa Verde Port Authority | 100% | 794900 | 794900 | 585516.71 | 0 | 0 | 794900 | 33762.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13374 | 0068gXhFD7hI1vX7yf | TRUE
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | Time and material | In Progress | L8200 | E31196 | Summit Infrastructure Group | 0% | 15700 | 11349.21 | 10903.65 | 6288.83 | 3577.68 | 15700 | 14803.02 | 0 | 0 | 4350.79 | 0 | 4350.79 | 0 | 0 | 0 | 146 | 15147 | 006VahUo876px0GpMb | FALSE
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Fixed fee | Cost Tracking on Closed Project | L8200 | E31200 | Ridgeline Resources Corp. | 90.96% | 715500 | 650818.8 | 625275.45 | 0 | 0 | 650818.8 | 39814.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7995 | 14529 | 006svep5uA2hmnut0R | FALSE
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Fixed fee | Cost Tracking on Closed Project | L8200 | E31196 | Pioneer Utilities | 100% | 551800 | 551800 | 378424.44 | 0 | 0 | 551800 | 28393.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4019 | 13948 | 006XZnfGsT1hzn1Prq | FALSE
25-PC-43455 | Kestrel Butte Maritime Remote Sensing Survey | Fixed fee | On Hold | L8200 | E31196 | Summit Engineering, Inc. | 9.96% | 116100 | 11563.56 | 84903.93 | 0 | 0 | 11563.56 | 702.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658 | 15125 | 006KMCYEU0f5oXmlQS | FALSE
25-PC-43511 | Wildrye Solar Phase II Testing | Time and material | Completed | L8200 | E31199 | Canyon Planning Associates | 100% | 1026200 | 607510.4 | 701711.56 | 0 | 0 | 607510.4 | 61119.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8612 | 10525 | 006dVegg9yS5IUVGjR | FALSE
25-PC-43566 | Copper Flats Solar - Phase II Testing | Fixed fee | In Progress | L8200 | E31199 | Evergreen Development Group | 100% | 114200 | 114200 | 73887.4 | 0 | 0 | 114200 | 13803.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11371 | 006Qmt6LN7Yw6ou8oa | FALSE
25-PC-43590 | Task Order 37: Elk Meadow Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | L8200 | E31199 | High Plains Engineering, Inc. | 68.46% | 24800 | 16978.08 | 16619.52 | 0 | 0 | 16978.08 | 1444.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218 | 12054 | 0062qtJpjNpvlFtqXR | FALSE
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | Fixed fee | In Progress | L8210 | E31209 | Lakecrest Pipeline Company | 100% | 52800 | 52800 | 37979.04 | 0 | 0 | 52800 | 6799.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13006 | 006TB3Z6pbUAOpbOCx | FALSE
25-PC-43639 | Windmill Flat Battery Storage Curation | Fixed fee | Final Reporting/Review | L8210 | E31205 | Blue Mesa Energy Partners | 100% | 137000 | 133193.26 | 91502.3 | 4747.28 | 3733.3 | 137000 | 19477.35 | 1566.4 | 0 | 3806.74 | 0 | 3806.74 | 0 | 28.5 | 0 | 1167 | 10054 | 0061Ez7uFxOnQe4CWR | FALSE
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Fixed fee | Lab/Curation | L8210 | E31207 | Canyon Rail Partners | 100% | 92800 | 80044.54 | 78211.84 | 14757.01 | 4061.82 | 92800 | 17345.17 | 5008.19 | 0 | 12755.46 | 0 | 12755.46 | 0 | 79.5 | 11 | 0 | 10579 | 006gdDnXbgLwFAuuyn | TRUE
25-PC-43752 | Bramble Creek Rail Siding - Environmental Review Support | Time and material | Final Billing/Invoice | L8210 | E31207 | Timberline Environmental Consultants | 100% | 49900 | 4391.2 | 36001.87 | 0 | 0 | 4391.2 | 8424.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15591 | 006oQSPyKvIkcct5Vb | FALSE
25-PC-43771 | Granite Pass Reservoir - Built Environment Survey | Time and material | Lab/Curation | L8210 | E31206 | Summit Planning Associates | 0% | 31500 | 15172.4 | 20147.4 | 399.49 | 320.95 | 15790.5 | 918.89 | 739.63 | 0 | 618.1 | 0 | 618.1 | 0 | 18.5 | 0 | 366 | 15198 | 006LGvxt1knEKGL6XE | FALSE
25-PC-43844 | Slate Ridge Battery Storage Class III Survey | Fixed fee | In Progress | L8210 | E31209 | High Plains Renewables LLC | 94.46% | 50700 | 43959.81 | 33907.9 | 6156.74 | 2128.08 | 47891.22 | 4964.81 | 3039.77 | 0 | 3931.41 | 0 | 3931.41 | 0 | 44.25 | 0 | 290 | 12128 | 0064NQ0NxF0NsG2sL6 | FALSE
25-PC-43853 | Heron Marsh Battery Storage - Phase II Testing | Time and material | Final Reporting/Review | L8210 | E31209 | Ridgeline Rail Partners | 0% | 162800 | 146251.97 | 115799.64 | 13534.88 | 10326.67 | 159982.25 | 10717.83 | 4641.64 | 0 | 13730.28 | 0 | 13730.28 | 0 | 75.5 | 0 | 1431 | 14455 | 0064vvySFl0J2sQnDp | FALSE
25-PC-43859 | On-Call: Juniper Wash Solar Architectural History Survey | Fixed fee | Completed | L8210 | E31209 | Ridgeline Renewables LLC | 100% | 1802800 | 1802800 | 1378420.88 | 0 | 0 | 1802800 | 130354.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21344 | 14493 | 0067CWBSiMUIIdrQbJ | FALSE
25-PC-43863 | Yarrow Point Cultural Resources Assessment | Fixed fee | In Progress | L8210 | E31207 | Ridgeline Renewables LLC | 18.58% | 545200 | 95002.43 | 450335.2 | 7924.31 | 7664.01 | 101298.16 | 9454.08 | 3377.63 | 0 | 6295.73 | 0 | 6295.73 | 0 | 25.75 | 0 | 0 | 14493 | 006oAI1xkIPblZsu3R | FALSE
25-PC-43932 | Blue Heron Built Environment Survey | Time and material | Transferred Entity | L8220 | E31213 | Ridgeline Resources Corp. | 0% | 35900 | 23610.32 | 24656.25 | 981.8 | 628.76 | 24136.55 | 1680.74 | 0 | 0 | 526.23 | 0 | 526.23 | 0 | 0 | 0 | 374 | 14529 | 006QpPMSOY8ql6DAKa | FALSE
25-PC-43944 | Elk Meadow Data Recovery | Fixed fee | In Progress | L8220 | E31220 | Clearwater Engineering, Inc. | 35.75% | 74800 | 26741 | 60460.84 | 0 | 0 | 26741 | 3890.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142 | 10896 | 006D5X4Yf5rCi5MNO3 | FALSE
25-PC-43966 | Silver Lake Rail Siding - Cultural Resources Monitoring | Fixed fee | Transferred Entity | L8220 | E31211 | Redtail Rail Partners | 79.18% | 47800 | 34241.7 | 34547.14 | 7071.95 | 4842.98 | 37848.04 | 5552.7 | 1668.06 | 0 | 3606.34 | 0 | 3606.34 | 0 | 18.5 | 0 | 217 | 14317 | 0062L0AQwLVvYr52A8 | TRUE
25-PC-43993 | Timber Gap GIS Mapping | Fixed fee | Transferred Entity | L8220 | E31221 | Blue Mesa Energy Partners | 73.22% | 27900 | 19158.53 | 19669.5 | 1250.78 | 657.3 | 20428.38 | 3053.17 | 0 | 0 | 1269.85 | 0 | 1269.85 | 0 | 0 | 0 | 136 | 10054 | 00610IqkQ2JjpV9nIc | TRUE
25-PC-44046 | Kestrel Butte Section 106 Consultation | Fixed fee | Transferred Entity | L8220 | E31218 | Clearwater Engineering, Inc. | 100% | 320300 | 320300 | 220526.55 | 0 | 0 | 320300 | 46752.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10896 | 006ThMYPTmM1HzxugB | FALSE
25-PC-44140 | Stone Mill Archaeological Testing | Fixed fee | In Progress | L8220 | E31211 | Clearwater Planning Associates | 99.74% | 149900 | 130809.05 | 100298.09 | 7552.3 | 7437.77 | 149510.26 | 12204.33 | 11014.59 | 0 | 18701.21 | 0 | 18701.21 | 0 | 132.25 | 9.25 | 1193 | 10938 | 006azlePBHzXnF5Kl8 | FALSE
25-PC-44186 | Falcon Mesa Section 106 Consultation | Fixed fee | Transferred Entity | L8220 | E31218 | Highland Telecom Holdings | 63.69% | 537000 | 342015.3 | 338148.9 | 856.44 | 800.97 | 342015.3 | 16152.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9096 | 12458 | 006TXGO2JduB3Jnbey | TRUE
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | Time and material | Transferred Entity | L8220 | E31213 | Silverline Port Authority | 0% | 31100 | 30922.86 | 17934.14 | 300.92 | 328.4 | 31100 | 2189.33 | 114.94 | 0 | 177.14 | 0 | 177.14 | 0 | 1.5 | 0 | 0 | 14747 | 006gPBVei3TK9C3hqe | FALSE
25-PC-44241 | On-Call: Timber Gap Reservoir Paleontological Monitoring | Time and material | Final Billing/Invoice | L8220 | E31222 | Coastal Planning Associates | 100% | 348700 | 164586.4 | 228712.33 | 0 | 0 | 164586.4 | 54707.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 006Npd0R2McK2omz80 | FALSE
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | Fixed fee | In Progress | L8220 | E31218 | Summit Port Authority | 100% | 97000 | 91499.34 | 71004 | 7202.87 | 4124.82 | 97000 | 15966.52 | 3305.66 | 0 | 5500.66 | 0 | 5500.66 | 0 | 29 | 1.5 | 322 | 15239 | 006z5mF4mnt7GFY92h | FALSE
26-PC-30013 | Windmill Flat Mine Expansion - Architectural History Survey | Time and material | Final Reporting/Review | L8000 | E30907 | Canyon Construction Co. | 0% | 62300 | 8607.19 | 43902.81 | 5302.79 | 2056.12 | 13942 | 1556.08 | 1853.9 | 0 | 5334.81 | 0 | 5334.81 | 0 | 22 | 2 | 685 | 10448 | 006wIxvhHKDW4lBVxw | FALSE
26-PC-30057 | Sparrow Hill Environmental Review Support | Time and material | In Progress | L8000 | E30905 | Canyon Construction Co. | 0% | 197500 | 81807.77 | 144017 | 20155.39 | 16169.38 | 104876.75 | 12956.55 | 9015.6 | 0 | 23068.98 | 0 | 23068.98 | 0 | 150.5 | 0 | 1736 | 10448 | 006Zbt2FcZN6GvCn9d | FALSE
26-PC-30065 | Granite Pass Water Main - Cultural Resources Assessment | Fixed fee | In Progress | L8000 | E30904 | Clearwater Port Authority | 19.96% | 132100 | 20607.73 | 104411.84 | 6050.94 | 3369.09 | 26367.16 | 1521.2 | 2479.2 | 0 | 5759.43 | 0 | 5759.43 | 0 | 30 | 0 | 879 | 10969 | 006E9nVtDYgdJhuQb7 | FALSE
26-PC-30094 | Sumac Ridge Wastewater Plant Paleontological Monitoring | Fixed fee | In Progress | L8000 | E30900 | Evergreen Development Group | 3.97% | 98400 | 1293.62 | 82193.52 | 1293.62 | 0 | 3906.48 | 195.99 | 1103.33 | 0 | 2612.86 | 0 | 2612.86 | 0 | 26.5 | 0 | 1481 | 11371 | 006NmvklnjTpkCJ65w | FALSE
26-PC-30115 | Quail Run Housing Development - Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8000 | E30907 | Mesa Verde Pipeline Company | 100% | 18600 | 18600 | 16368 | 0 | 0 | 18600 | 1937.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 13320 | 006wdAiK0XMrK2xvBT | FALSE
26-PC-30123 | Eagle Bend Park Improvements - Class III Survey | Fixed fee | In Progress | L8000 | E30907 | Summit County | 21.37% | 277200 | 45677.97 | 210477.96 | 9720.32 | 6255.09 | 59237.64 | 4227.26 | 8792.2 | 0 | 13559.67 | 0 | 13559.67 | 0 | 110.75 | 3.25 | 2614 | 15070 | 006JZ021WBYAGgTYct | TRUE
26-PC-30139 | Quail Run Canal Lining Phase I Survey | Fixed fee | In Progress | L8000 | E30904 | Ridgeline Resources Corp. | 8% | 239600 | 19168 | 198628.4 | 0 | 0 | 19168 | 2620.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2195 | 14529 | 006MwEsKP8zaGE9xgT | FALSE
26-PC-30180 | Willow Springs Architectural History Survey | Fixed fee | Lab/Curation | L8000 | E30900 | Clearwater Port Authority | 25.95% | 115700 | 24550.75 | 79798.29 | 5402.74 | 3398.04 | 30024.15 | 2671.01 | 4208.43 | 0 | 5473.4 | 0 | 5473.4 | 0 | 98.75 | 4.25 | 1880 | 10969 | 0060G4McD6Rwa7eemW | FALSE
26-PC-30185 | Task Order 40: Cedar Hollow Cell Tower Curation | Fixed fee | Final Reporting/Review | L8000 | E30904 | Brightwater Utilities | 5.81% | 53400 | 0 | 42447.66 | 0 | 0 | 3102.54 | 231.84 | 2234.58 | 0 | 3102.54 | 0 | 3102.54 | 0 | 41.25 | 0 | 711 | 10408 | 0064xNVGb3BeW199f6 | FALSE
26-PC-30203 | Millbrook Pipeline Data Recovery | Fixed fee | In Progress | L8000 | E30900 | Coastal Planning Associates | 6.47% | 134800 | 7426.17 | 102421.04 | 918.19 | 638.21 | 8721.56 | 1086.76 | 935.51 | 0 | 1295.39 | 0 | 1295.39 | 0 | 25.25 | 0 | 2925 | 11250 | 006GlS7Ke6zDF4L9ZN | FALSE
26-PC-30211 | Copper Flats Paleontological Monitoring | Fixed fee | Lab/Curation | L8000 | E30904 | Cardinal Energy Partners | 0% | 736100 | 0 | 498404.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10505 | 10648 | 006dEiAh7XQ0ZKySuV | FALSE
26-PC-30273 | Task Order 40: Copper Flats Trail Class III Survey | Fixed fee | Lab/Curation | L8000 | E30907 | Stonebridge Engineering, Inc. | 8.94% | 77200 | 6811.24 | 53522.76 | 209.53 | 62.2 | 6901.68 | 320.46 | 0 | 0 | 90.44 | 0 | 90.44 | 0 | 0 | 0 | 0 | 14937 | 006z3G4jjc7A55WHc6 | FALSE
26-PC-30287 | Task Order 40: Maple Fork Solar Historic Resources Evaluation | Fixed fee | In Progress | L8000 | E30904 | Granite State Infrastructure Group | 50.31% | 10100 | 5081.31 | 6193.32 | 0 | 0 | 5081.31 | 277.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11510 | 006mwixa9N1H6R2ZkE | FALSE
26-PC-30329 | Hackberry Bend Rail Siding Built Environment Survey | Fixed fee | In Progress | L8000 | E30904 | Keystone Energy Partners | 25.24% | 483600 | 103417.88 | 313904.76 | 27729.97 | 19643.58 | 122060.64 | 6338.97 | 10820.62 | 0 | 18642.76 | 0 | 18642.76 | 0 | 220.5 | 11.75 | 5312 | 12804 | 006FhL5KAWLonqhUr6 | FALSE
26-PC-30338 | On-Call: Saltgrass Mixed-Use Development Phase II Testing | Fixed fee | Lab/Curation | L8000 | E30905 | Lakecrest Renewables LLC | 0.57% | 268300 | 1529.31 | 189811.91 | 117 | 63.59 | 1529.31 | 184.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3414 | 13164 | 0065QNjiocj1Hd2Smp | TRUE
26-PC-30349 | Phase I: Copper Flats Rail Siding Cultural Resources Monitoring | Fixed fee | In Progress | L8000 | E30905 | High Plains Environmental Consultants | 16.75% | 184200 | 24917.81 | 105343.98 | 2778.38 | 3250.76 | 30853.5 | 2611.41 | 2496.25 | 0 | 5935.69 | 0 | 5935.69 | 0 | 57 | 0 | 2437 | 12089 | 006a45heLwfjCFH7GJ | FALSE
26-PC-30351 | Wildrye Architectural History Survey | Fixed fee | In Progress | L8000 | E30907 | Pioneer Renewables LLC | 33.7% | 393800 | 114207.61 | 262900.88 | 23899.68 | 10210.34 | 132710.6 | 16213.3 | 9357.21 | 0 | 18502.99 | 0 | 18502.99 | 0 | 162 | 0 | 4223 | 13869 | 006e8R5leamK7dehXz | FALSE
26-PC-30396 | Tamarack Historic Resources Evaluation | Fixed fee | In Progress | L8000 | E30905 | Canyon Energy Partners | 0% | 31300 | 0 | 23853.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 10492 | 006iQMiMXcDqRNSkBt | FALSE
26-PC-30402 | On-Call: Cedar Hollow Highway Widening Paleontological Monitoring | Time and material | Transferred Entity | L8000 | E30900 | Westwind County | 0% | 151000 | 0 | 118603.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142 | 15753 | 006SX93yZcqESL8sRm | FALSE
26-PC-30425 | Tamarack Water Main - Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8000 | E30907 | Summit County | 100% | 58100 | 58100 | 42076.02 | 0 | 0 | 58100 | 6576.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829 | 15070 | 006PNMPfWAlwH6Zo5C | FALSE
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | L8000 | E30904 | Summit Infrastructure Group | 0% | 93100 | 0 | 63801.43 | 0 | 0 | 0 | 8192.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659 | 15147 | 006kT3aIXNtm7kYlOd | FALSE
26-PC-30457 | Wren Hollow Transmission Line - Data Recovery | Fixed fee | Final Reporting/Review | L8000 | E30907 | Coastal Development Group | 16.72% | 719800 | 120350.56 | 547191.96 | 0 | 0 | 120350.56 | 14726.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6208 | 11160 | 006aeP2FG52N0E93cL | TRUE
26-PC-30480 | Tansy Flat Canal Lining Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8000 | E30904 | Silverline Construction Co. | 100% | 194300 | 194300 | 143375.92 | 0 | 0 | 194300 | 35401.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567 | 14700 | 0068BF2TFcYe49qIcg | FALSE
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | Fixed fee | In Progress | L8000 | E30905 | Heartland Power Cooperative | 100% | 19900 | 19400.11 | 14258.19 | 418.21 | 300 | 19900 | 1771.28 | 197.38 | 0 | 499.89 | 0 | 499.89 | 0 | 2 | 0 | 199 | 11841 | 0062e7PhvmTVfD5H0F | FALSE
26-PC-30528 | Plover Cove School Campus Architectural History Survey | Fixed fee | In Progress | L8000 | E30904 | Lakecrest Pipeline Company | 68.21% | 112900 | 71440.49 | 74017.24 | 6307.55 | 6163.03 | 77009.09 | 6311.35 | 3134.78 | 0 | 5568.6 | 0 | 5568.6 | 0 | 72.5 | 0 | 0 | 13006 | 006FFLvI2hkMPpAHqo | TRUE
26-PC-30554 | Thistle Down Airport Apron Curation | Fixed fee | In Progress | L8000 | E30907 | Coastal Rail Partners | 11.93% | 139800 | 9641.87 | 79741.92 | 6307.78 | 3334.09 | 16678.14 | 1626.54 | 3648.28 | 0 | 7036.27 | 0 | 7036.27 | 0 | 93.75 | 0 | 0 | 11259 | 006I7fRqxHYBxKVhM8 | FALSE
26-PC-30577 | Task Order 15: Wildrye Bridge Replacement Phase I Survey | Fixed fee | On Hold | L8000 | E30904 | Ridgeline Water District | 0% | 46800 | 0 | 36479.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 14577 | 006bRamH1nLHsGWKzw | FALSE
26-PC-30588 | Bramble Creek Fiber Route - Historic Resources Evaluation | Fixed fee | In Progress | L8010 | E30916 | Brightwater Power Cooperative | 12.16% | 97000 | 8704.54 | 75388.4 | 5258.52 | 1737.23 | 11795.2 | 834.35 | 1195.75 | 0 | 3090.66 | 0 | 3090.66 | 0 | 25 | 0 | 1668 | 10363 | 006DASN9sDdNN3v4oo | FALSE
26-PC-30589 | Aspen Ridge Trail Cultural Resources Assessment | Fixed fee | Completed | L8010 | E30913 | Canyon Utilities | 100% | 143200 | 143200 | 108502.64 | 0 | 0 | 143200 | 28210.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10611 | 006ANrSX65W59DkKMV | FALSE
26-PC-30602 | On-Call: Hawk Point Solar Cultural Resources Assessment | Time and material | In Progress | L8010 | E30913 | Coastal Planning Associates | 0% | 211900 | 46785.39 | 152752.98 | 5107.91 | 3492.59 | 55300 | 3849.61 | 4491.22 | 0 | 8514.61 | 0 | 8514.61 | 0 | 67.75 | 3.5 | 1755 | 11250 | 006PlsT6g1ujDSBKQn | FALSE
26-PC-30634 | Task Order 7: Blue Heron Canal Lining Historic Resources Evaluation | Time and material | Completed | L8010 | E30913 | Canyon Energy Partners | 100% | 21200 | 0 | 13865.34 | 0 | 0 | 0 | 1369.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 10492 | 006oeMpeZzcSccvHgL | FALSE
26-PC-30754 | On-Call: Kestrel Butte Highway Widening Archaeological Testing | Fixed fee | Final Reporting/Review | L8010 | E30916 | Summit Engineering, Inc. | 8.21% | 153300 | 3576.72 | 106834.77 | 3576.72 | 0 | 12585.93 | 1114.12 | 7354.22 | 0 | 9009.21 | 0 | 9009.21 | 0 | 167.5 | 0 | 2318 | 15125 | 006d2LOJRt1ZIBC79p | FALSE
26-PC-30781 | Cedar Hollow Trail - Architectural History Survey | Fixed fee | Final Billing/Invoice | L8010 | E30913 | Clearwater Resources Corp. | 100% | 113700 | 113700 | 71210.31 | 0 | 0 | 113700 | 10780.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933 | 11004 | 0063PrOWL7aVPPFdJ0 | TRUE
26-PC-30815 | Juniper Wash Water Main Archaeological Testing | Fixed fee | In Progress | L8010 | E30913 | Harborlight Water District | 17.39% | 236000 | 26899.17 | 177731.6 | 15600.53 | 8103.96 | 41040.4 | 2564.69 | 4034.65 | 0 | 14141.23 | 0 | 14141.23 | 0 | 74 | 0 | 1914 | 11739 | 006VN6glbcTCv2CIQ0 | FALSE
26-PC-30871 | Sea Oat Substation - Section 106 Consultation | Time and material | Final Billing/Invoice | L8010 | E30916 | Canyon Planning Associates | 100% | 205700 | 0 | 139834.86 | 0 | 0 | 0 | 21039.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082 | 10525 | 006kdt3m4Z5Zdg6199 | FALSE
26-PC-30896 | Phase III: Timber Gap Pipeline Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8010 | E30913 | Redtail Engineering, Inc. | 100% | 158100 | 158100 | 109547.49 | 0 | 0 | 158100 | 17378.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14233 | 006wmAfVib7adzDYaG | TRUE
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Time and material | Cost Tracking on Closed Project | L8010 | E30916 | Riverstone Construction Co. | 0% | 209800 | 0 | 135467.86 | 0 | 0 | 0 | 24784.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1355 | 14599 | 006RvEs9wBjvFkExlY | FALSE
26-PC-30945 | Wildrye Reservoir Architectural History Survey | Fixed fee | In Progress | L8010 | E30913 | Cardinal Port Authority | 46.67% | 179500 | 69601.09 | 120265 | 9353.24 | 10311.78 | 83772.65 | 6734.61 | 6141.8 | 0 | 14171.56 | 0 | 14171.56 | 0 | 124.5 | 0 | 0 | 10753 | 006jps2SJpmoOV8yhu | TRUE
26-PC-30967 | Timber Gap Pipeline - Built Environment Survey | Time and material | Final Reporting/Review | L8010 | E30916 | Evergreen Development Group | 0% | 173400 | 132862.73 | 108877.86 | 13061.2 | 4414.83 | 145618.75 | 11359.16 | 3248.42 | 0 | 12756.02 | 0 | 12756.02 | 0 | 73.25 | 0 | 1432 | 11371 | 006qmQx5Slved8BvXJ | FALSE
26-PC-30985 | On-Call: Maple Fork Wastewater Plant Built Environment Survey | Fixed fee | Final Billing/Invoice | L8010 | E30913 | High Plains County | 100% | 46500 | 46500 | 30100.87 | 0 | 0 | 46500 | 6819.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 11980 | 006hzaCVSvctrQNp4F | FALSE
26-PC-31002 | North Fork Harbor Dredging Data Recovery | Fixed fee | In Progress | L8010 | E30916 | Coastal Utilities | 13.78% | 211500 | 13311.23 | 164758.5 | 13311.23 | 0 | 29144.7 | 3835.57 | 8091.8 | 0 | 15833.47 | 0 | 15833.47 | 0 | 135 | 0 | 1533 | 11319 | 00605pNRYIZaDgXCQH | FALSE
26-PC-31037 | Cedar Hollow Cultural Resources Assessment | Fixed fee | In Progress | L8010 | E30916 | Ironbridge Construction Co. | 37.44% | 168500 | 52530.72 | 131345.75 | 12906.21 | 5697.94 | 63086.4 | 8016.59 | 5285.96 | 0 | 10555.68 | 0 | 10555.68 | 0 | 100.5 | 0 | 1730 | 12523 | 006esc1SQy5Z9SXURk | FALSE
26-PC-31064 | Quail Run Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | L8020 | E30936 | Brightwater Rail Partners | 100% | 74500 | 74500 | 60394.3 | 0 | 0 | 74500 | 12977.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 10392 | 006v83fJbJyPn1MvnP | FALSE
26-PC-31084 | Bramble Creek Park Improvements Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8020 | E30936 | Highland Water District | 100% | 28300 | 28300 | 14716 | 0 | 0 | 28300 | 2228.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 12481 | 006ln6zouys95yJKU4 | TRUE
26-PC-31098 | Millbrook School Campus - Environmental Review Support | Time and material | On Hold | L8020 | E30937 | Sunrise Rail Partners | 0% | 414100 | 0 | 297365.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2837 | 15467 | 006eqe7gBmoBgKjZIZ | FALSE
26-PC-31155 | Slate Ridge Cell Tower - Phase II Testing | Fixed fee | Final Billing/Invoice | L8020 | E30923 | Redtail Rail Partners | 100% | 56600 | 56600 | 35980.62 | 0 | 0 | 56600 | 3629.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449 | 14317 | 006cCRKIkpHJkWbLRq | FALSE
26-PC-31174 | Task Order 33: Tamarack Housing Development Data Recovery | Time and material | Cost Tracking on Closed Project | L8020 | E30925 | Ridgeline Renewables LLC | 0% | 4400 | 0 | 2984.25 | 0 | 0 | 0 | 276.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14493 | 006VdDolWvcVqBJMDS | FALSE
26-PC-31182 | Elk Meadow School Campus Curation | Fixed fee | In Progress | L8020 | E30935 | Pioneer Power Cooperative | 12.16% | 73400 | 5265.51 | 57596.98 | 4396.56 | 868.95 | 8925.44 | 1169.78 | 1697.92 | 0 | 3659.93 | 0 | 3659.93 | 0 | 39.5 | 0 | 1211 | 13831 | 006dLlQXaL8nP1rR1K | FALSE
26-PC-31186 | Task Order 14: Meadowlark Cell Tower Archaeological Testing | Time and material | Completed | L8020 | E30937 | Heartland Water District | 100% | 43100 | 0 | 31458.69 | 0 | 0 | 0 | 3618.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573 | 11891 | 006wUW4BNNezIE6jLW | FALSE
26-PC-31209 | Redbud Canal Lining - Built Environment Survey | Fixed fee | Final Billing/Invoice | L8020 | E30925 | Keystone Rail Partners | 100% | 960700 | 960700 | 765293.62 | 0 | 0 | 960700 | 116983.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14279 | 12893 | 0063EyMj7biNvYOw2f | FALSE
26-PC-31216 | On-Call: Saltgrass Fiber Route Environmental Review Support | Time and material | In Progress | L8020 | E30942 | Northfield Power Cooperative | 0% | 172400 | 6773.41 | 111025.6 | 6773.41 | 0 | 25313.25 | 1539.83 | 7003.94 | 0 | 18539.84 | 0 | 18539.84 | 0 | 99.75 | 12.5 | 1218 | 13614 | 006moWGcKR7OHjuf8E | FALSE
26-PC-31238 | Task Order 27: Wren Hollow Bridge Replacement Built Environment Survey | Time and material | In Progress | L8020 | E30942 | Cardinal Environmental Consultants | 0% | 832700 | 129716.05 | 533060.12 | 38727.26 | 25087.89 | 154708.25 | 6558.24 | 16503.67 | 0 | 24992.2 | 0 | 24992.2 | 0 | 386.75 | 18.5 | 11177 | 10678 | 0063cEV72wnhpjqDoE | FALSE
26-PC-31276 | Phase II: Sea Oat Solar Phase I Survey | Time and material | Final Billing/Invoice | L8020 | E30923 | Prairie Wind Pipeline Company | 100% | 132400 | 0 | 98558.56 | 0 | 0 | 0 | 16064.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157 | 14024 | 006265mux1eaS5N4gG | FALSE
26-PC-31316 | Sparrow Hill Trail Architectural History Survey | Fixed fee | Final Reporting/Review | L8020 | E30937 | Ironbridge Telecom Holdings | 25.72% | 148200 | 29984.37 | 109860.66 | 8434.61 | 7397.7 | 38117.04 | 2487.02 | 4167.39 | 0 | 8132.67 | 0 | 8132.67 | 0 | 41.75 | 0 | 912 | 12740 | 006SXhHFphR5EhMcOk | TRUE
26-PC-31421 | Task Order 30: Sage Flat Levee Repair Environmental Review Support | Fixed fee | Completed | L8020 | E30937 | Westwind County | 100% | 740400 | 740400 | 532717.8 | 0 | 0 | 740400 | 69253.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8491 | 15753 | 0069Tu7ssjWKN2rFA3 | FALSE
26-PC-31448 | Foxglove Class III Survey | Fixed fee | In Progress | L8020 | E30936 | Summit Port Authority | 27.97% | 25800 | 6639.74 | 20065.31 | 1018.86 | 647.67 | 7216.26 | 959.74 | 627.82 | 0 | 576.52 | 0 | 576.52 | 0 | 10.75 | 0 | 439 | 15239 | 006Ab0uiHfN2SJOb4c | FALSE
26-PC-31473 | Plover Cove Mixed-Use Development - Curation | Fixed fee | In Progress | L8020 | E30937 | Coastal Utilities | 6.15% | 180800 | 2976.07 | 112403.36 | 2976.07 | 0 | 11119.2 | 1167.52 | 5466.78 | 0 | 8143.13 | 0 | 8143.13 | 0 | 90.25 | 0 | 0 | 11319 | 006BF416nldusAXH6m | FALSE
26-PC-31484 | Maple Fork Wastewater Plant Data Recovery | Fixed fee | In Progress | L8020 | E30923 | Keystone Energy Partners | 25.86% | 31800 | 7336.57 | 23427.06 | 720.43 | 436.06 | 8223.48 | 1326.56 | 452.13 | 0 | 886.91 | 0 | 886.91 | 0 | 10.25 | 0 | 483 | 12804 | 006FsxaNyu0jjy4mxN | FALSE
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | Fixed fee | In Progress | L8020 | E30925 | Brightwater Land Company | 70.11% | 44400 | 30936.04 | 34032.6 | 800.34 | 225.38 | 31128.84 | 4414.31 | 142.87 | 0 | 192.8 | 0 | 192.8 | 0 | 3.25 | 0 | 394 | 10261 | 0061rcXchjn19eCWPs | FALSE
26-PC-31537 | Raven Rock Park Improvements - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8020 | E30942 | Northfield Telecom Holdings | 5.18% | 87300 | 3456.58 | 54449.01 | 2772.48 | 684.1 | 4522.14 | 386.77 | 1007.03 | 0 | 1065.56 | 0 | 1065.56 | 0 | 7.75 | 0 | 309 | 13631 | 006PyR9W5GkXTBHUnW | FALSE
26-PC-31568 | Sea Oat Housing Development - Section 106 Consultation | Fixed fee | In Progress | L8020 | E30925 | Sunrise Water District | 16.75% | 229100 | 31669.56 | 148678.02 | 9745.4 | 6233.12 | 38374.25 | 2340.36 | 5367.57 | 0 | 6704.69 | 0 | 6704.69 | 0 | 123.5 | 11.5 | 3286 | 15575 | 006wSgzeHx3Qb2YAd9 | TRUE
26-PC-31638 | Kestrel Butte Highway Widening - Cultural Resources Assessment | Fixed fee | In Progress | L8020 | E30936 | Cardinal Utilities | 12.69% | 170300 | 13959.16 | 108060.44 | 6710.39 | 2292.74 | 21611.07 | 1741.33 | 2981.88 | 0 | 7651.91 | 0 | 7651.91 | 0 | 67.25 | 0 | 1587 | 10833 | 006Bc5t8Cc7ckEqvUA | FALSE
26-PC-31648 | Rushgrass Draw Solar Data Recovery | Fixed fee | In Progress | L8020 | E30935 | Heartland Port Authority | 43.17% | 388400 | 138803.11 | 288425.84 | 23779.4 | 13406.37 | 167672.28 | 21667.82 | 11894.86 | 0 | 28869.17 | 0 | 28869.17 | 0 | 224.25 | 0 | 0 | 11802 | 006yg9BUSEx89Oh9Nb | FALSE
26-PC-31678 | Heron Marsh Wind Farm Phase I Survey | Fixed fee | In Progress | L8020 | E30942 | Cardinal Land Company | 33.3% | 892800 | 267319.35 | 641923.2 | 54334.76 | 39939.34 | 297302.4 | 41686.98 | 19628.25 | 0 | 29983.05 | 0 | 29983.05 | 0 | 366 | 6.25 | 0 | 10711 | 006QaFUtfBSBkVdeIu | FALSE
26-PC-31692 | Phase III: Meadowlark Reservoir Paleontological Monitoring | Fixed fee | In Progress | L8020 | E30942 | Lakecrest Pipeline Company | 5.97% | 615300 | 14836.74 | 423803.64 | 14836.74 | 0 | 36733.41 | 3416.73 | 10035.25 | 0 | 21896.67 | 0 | 21896.67 | 0 | 207 | 14 | 0 | 13006 | 0067xC7VE8U87sshKs | FALSE
26-PC-31700 | On-Call: Granite Pass Bridge Replacement Environmental Review Support | Time and material | Completed | L8020 | E30936 | Ironbridge Infrastructure Group | 100% | 49200 | 0 | 33923.4 | 0 | 0 | 0 | 2603.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338 | 12667 | 006USk4xudaDFJV4wF | FALSE
26-PC-31716 | Saltgrass Wind Farm Data Recovery | Fixed fee | In Progress | L8020 | E30925 | Ridgeline County | 26.45% | 13300 | 2027.4 | 9413.74 | 915.65 | 1111.75 | 3517.85 | 542.82 | 422.4 | 0 | 1490.45 | 0 | 1490.45 | 0 | 9 | 1.25 | 0 | 14393 | 006w8zGBVO8KwrFgFI | FALSE
26-PC-31728 | On-Call: Slate Ridge Housing Development Data Recovery | Fixed fee | In Progress | L8020 | E30935 | Stonebridge County | 5.1% | 38500 | 332.4 | 31042.55 | 332.4 | 0 | 1963.5 | 300.85 | 471.4 | 0 | 1631.1 | 0 | 1631.1 | 0 | 10.75 | 0 | 324 | 14884 | 0062TvwP2QQOEG0JfZ | TRUE
26-PC-31802 | Bramble Creek Environmental Review Support | Fixed fee | Lab/Curation | L8020 | E30923 | Ironbridge Port Authority | 57.08% | 53700 | 28674.1 | 41655.09 | 1070.88 | 730.17 | 30651.96 | 3756.43 | 1894.44 | 0 | 1977.86 | 0 | 1977.86 | 0 | 39 | 0 | 535 | 12704 | 006qyQ9P6SjU19r346 | FALSE
26-PC-31823 | Slate Ridge Phase II Testing | Fixed fee | Final Reporting/Review | L8020 | E30935 | Westwind Infrastructure Group | 9.24% | 173900 | 5114.84 | 122721.23 | 5114.84 | 0 | 16068.36 | 1077.77 | 9392.19 | 0 | 10953.52 | 0 | 10953.52 | 0 | 163 | 1 | 1756 | 15890 | 0067n9xIULdrt5yMeq | FALSE
26-PC-31830 | Ember Valley Archaeological Testing | Fixed fee | Transferred Entity | L8020 | E30937 | Heartland Port Authority | 46.38% | 86700 | 31491.18 | 59425.39 | 8682.49 | 9330.36 | 40211.46 | 2094.82 | 4829.14 | 0 | 8720.28 | 0 | 8720.28 | 0 | 69.25 | 0 | 1094 | 11802 | 006cs7uo6wxwhegBz1 | FALSE
26-PC-31872 | Sumac Ridge Water Main Archaeological Testing | Fixed fee | Lab/Curation | L8020 | E30925 | Harborlight Transit Authority | 52.58% | 63800 | 30533.41 | 45642.52 | 4891.72 | 2119.96 | 33546.04 | 1872.07 | 1273.48 | 0 | 3012.63 | 0 | 3012.63 | 0 | 24.25 | 1.25 | 622 | 11703 | 006Ibe4RhfKXJh9JVq | FALSE
26-PC-31881 | Fern Valley Rail Siding Cultural Resources Monitoring | Fixed fee | In Progress | L8020 | E30923 | Blue Mesa Environmental Consultants | 0% | 125300 | 0 | 94955.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10083 | 006rNRsltx1P8vkRik | FALSE
26-PC-32047 | On-Call: Sumac Ridge Mine Expansion Paleontological Monitoring | Fixed fee | In Progress | L8030 | E30950 | Summit Port Authority | 69.92% | 73200 | 43002 | 51825.6 | 8729.29 | 9953.18 | 51181.44 | 3660.09 | 3739.73 | 0 | 8179.44 | 0 | 8179.44 | 0 | 91.75 | 0 | 883 | 15239 | 006Y8u5CMHsmC6J09x | FALSE
26-PC-32069 | Task Order 25: Heron Marsh Wind Farm Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | L8030 | E30957 | Redtail Infrastructure Group | 7.79% | 844700 | 59477.56 | 646026.56 | 4715.5 | 4246.81 | 65802.13 | 4377.52 | 4191.32 | 0 | 6324.57 | 0 | 6324.57 | 0 | 101.25 | 0 | 0 | 14267 | 006vDxIvHL7pdQ37UK | FALSE
26-PC-32076 | Lone Pine Environmental Review Support | Fixed fee | Completed | L8030 | E30948 | Coastal Construction Co. | 100% | 165800 | 165800 | 125610.08 | 0 | 0 | 165800 | 8042.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2545 | 11092 | 006Apera1DxFu2iXpM | FALSE
26-PC-32094 | Maple Fork Trail - Phase II Testing | Time and material | In Progress | L8030 | E30947 | Canyon Energy Partners | 0% | 19000 | 8805.75 | 11274.6 | 3138.74 | 2043.5 | 8805.75 | 1030.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 10492 | 0063fh0o1zZFcUkNNG | FALSE
26-PC-32165 | Juniper Wash Park Improvements - Data Recovery | Time and material | In Progress | L8030 | E30958 | High Plains Renewables LLC | 0% | 501000 | 3832.67 | 394086.6 | 3832.67 | 0 | 13806 | 2229.56 | 2978.08 | 0 | 9973.33 | 0 | 9973.33 | 0 | 75.75 | 0 | 6396 | 12128 | 006oB03zsu7hMkencE | FALSE
26-PC-32188 | Creosote Draw Reservoir Curation | Fixed fee | In Progress | L8030 | E30950 | Silverline Water District | 0% | 91500 | 0 | 74856.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129 | 14839 | 006kQ7v5ZcPkYvjsXB | FALSE
26-PC-32227 | Foxglove Harbor Dredging Paleontological Monitoring | Time and material | Completed | L8030 | E30957 | Coastal Land Company | 100% | 32900 | 0 | 22437.8 | 0 | 0 | 0 | 4425.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316 | 11195 | 006nrFiP5plfHGoIz7 | FALSE
26-PC-32288 | Quail Run Solar - Architectural History Survey | Fixed fee | In Progress | L8030 | E30950 | Westwind County | 1.09% | 400500 | 2126.22 | 287318.7 | 1994.4 | 131.82 | 4365.45 | 508.71 | 2631.5 | 0 | 2239.23 | 0 | 2239.23 | 0 | 38 | 0 | 3493 | 15753 | 006AxCbDHdghXRUKji | FALSE
26-PC-32303 | Lone Pine Housing Development - Archaeological Testing | Time and material | In Progress | L8030 | E30950 | Coastal Planning Associates | 0% | 18700 | 277.36 | 13411.64 | 277.36 | 0 | 816 | 155.15 | 697.33 | 0 | 538.64 | 0 | 538.64 | 0 | 12.75 | 5.5 | 195 | 11250 | 0064MHIroqit01vucp | FALSE
26-PC-32322 | Foxglove Fiber Route - Curation | Fixed fee | In Progress | L8030 | E30957 | Coastal Rail Partners | 12.52% | 317500 | 37103.87 | 244665.5 | 1542.47 | 1506.73 | 39751 | 5789.05 | 0 | 0 | 2647.13 | 0 | 2647.13 | 0 | 0 | 0 | 1845 | 11259 | 006sSX9ltcAoyCOCt9 | TRUE
26-PC-32369 | Twin Buttes Water Main - Phase I Survey | Fixed fee | In Progress | L8030 | E30950 | Summit Renewables LLC | 9.75% | 730600 | 65269.21 | 470798.64 | 8223.04 | 7420.4 | 71233.5 | 5140.41 | 2626.13 | 0 | 5964.29 | 0 | 5964.29 | 0 | 49.5 | 13.5 | 9652 | 15274 | 0066sZT35QwJfjnAbl | FALSE
26-PC-32382 | Sea Oat Airport Apron Data Recovery | Fixed fee | Final Billing/Invoice | L8030 | E30950 | Highland Water District | 100% | 180500 | 180500 | 138172.75 | 0 | 0 | 180500 | 18764.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446 | 12481 | 006Fp8fOAlpGXs6RWV | FALSE
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | Time and material | In Progress | L8030 | E30947 | Highland Infrastructure Group | 0% | 13700 | 13641.82 | 9522.87 | 46.66 | 22.47 | 13700 | 5692 | 40.85 | 0 | 58.18 | 0 | 58.18 | 0 | 0.5 | 0 | 90 | 12316 | 006mSdxpBz4w4inUxE | FALSE
26-PC-32396 | On-Call: Copper Flats Mixed-Use Development Curation | Time and material | Final Reporting/Review | L8030 | E30957 | Heartland Transit Authority | 0% | 205600 | 2772.21 | 152123.45 | 2620.21 | 152 | 5224.75 | 615.08 | 1533.26 | 0 | 2452.54 | 0 | 2452.54 | 0 | 34 | 0 | 3197 | 11878 | 006v3VIpmAO2wGG2oN | FALSE
26-PC-32420 | Phase I: Copper Flats Water Main Architectural History Survey | Fixed fee | In Progress | L8030 | E30948 | Blue Mesa Environmental Consultants | 4.27% | 324200 | 4463.06 | 246926.01 | 4383.98 | 79.08 | 13843.34 | 2226.35 | 7151.88 | 0 | 9380.28 | 0 | 9380.28 | 0 | 96.75 | 9.75 | 0 | 10083 | 0067jUAUxs9DdwBkio | TRUE
26-PC-32442 | Sumac Ridge Airport Apron Cultural Resources Assessment | Fixed fee | In Progress | L8030 | E30957 | Ridgeline County | 32% | 53400 | 14860.55 | 33316.26 | 1608.21 | 831.5 | 17088 | 1162.08 | 585.2 | 0 | 2227.45 | 0 | 2227.45 | 0 | 9.75 | 4 | 621 | 14393 | 006KA10Np9IckPJ54V | FALSE
26-PC-32453 | Quail Run Housing Development Phase II Testing | Time and material | In Progress | L8030 | E30950 | Mesa Verde Pipeline Company | 0% | 103800 | 1853.51 | 74927.88 | 1853.51 | 0 | 6785.75 | 975.34 | 2412.29 | 0 | 4932.24 | 0 | 4932.24 | 0 | 59 | 0 | 1150 | 13320 | 006GIMbXFM6VMP2gxG | FALSE
26-PC-32540 | Task Order 36: Granite Pass Mixed-Use Development Phase II Testing | Time and material | Lab/Curation | L8030 | E30947 | Timberline Environmental Consultants | 0% | 846100 | 49253.92 | 625775.56 | 26800.72 | 22453.2 | 79570 | 10125.99 | 13381.58 | 0 | 30316.08 | 0 | 30316.08 | 0 | 166 | 0 | 5451 | 15591 | 006SlAGUDvZbRCLAUp | FALSE
26-PC-32556 | Maple Fork Cultural Resources Monitoring | Fixed fee | In Progress | L8030 | E30957 | Silverline Construction Co. | 34.51% | 45700 | 13650.9 | 32259.63 | 3076.5 | 1657.09 | 15771.07 | 1825.77 | 1022.88 | 0 | 2120.17 | 0 | 2120.17 | 0 | 24.5 | 0 | 0 | 14700 | 006YQR7TsIbAOgK3ln | FALSE
26-PC-32563 | On-Call: Creosote Draw Substation Phase I Survey | Fixed fee | Transferred Entity | L8030 | E30947 | Heartland Transit Authority | 24.89% | 534900 | 127694.45 | 344315.13 | 3083.48 | 4302.85 | 133136.61 | 13966.8 | 2730.66 | 0 | 5442.16 | 0 | 5442.16 | 0 | 60.25 | 0 | 7530 | 11878 | 006rahuFP4avMQnkVS | FALSE
26-PC-32569 | Hawk Point Data Recovery | Fixed fee | Completed | L8030 | E30947 | Brightwater Utilities | 100% | 191800 | 191800 | 155949 | 0 | 0 | 191800 | 11505.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2174 | 10408 | 006zYJYVRnvja62ZKC | FALSE
26-PC-32594 | On-Call: Tamarack Rail Siding Cultural Resources Monitoring | Fixed fee | In Progress | L8030 | E30958 | Cardinal Port Authority | 54.23% | 94400 | 38376.64 | 71536.32 | 9538.3 | 5625.93 | 51193.12 | 4305.76 | 8420.86 | 0 | 12816.48 | 0 | 12816.48 | 0 | 153.5 | 0 | 1184 | 10753 | 0068qJSzXj3ZP7Eqvr | FALSE
26-PC-32614 | Fern Valley Architectural History Survey | Time and material | In Progress | L8030 | E30950 | Mesa Verde County | 0% | 29700 | 0 | 20748.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 13234 | 006mjETQxbOVAJcC3j | FALSE
26-PC-32646 | Goldfinch Historic Resources Evaluation | Time and material | In Progress | L8030 | E30950 | Lakecrest Pipeline Company | 0% | 48600 | 19074.93 | 33922.8 | 6889.77 | 4586.79 | 24344.25 | 2042.16 | 3256.77 | 0 | 5269.32 | 0 | 5269.32 | 0 | 73 | 0 | 671 | 13006 | 006R21stZoUDGF6U8D | FALSE
26-PC-32668 | Millbrook Trail - Data Recovery | Time and material | Final Billing/Invoice | L8030 | E30948 | Heartland Port Authority | 100% | 300600 | 0 | 206151.48 | 0 | 0 | 0 | 24138.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747 | 11802 | 006wevnuzPWnlrjfYD | FALSE
26-PC-32707 | On-Call: Creosote Draw Transmission Line Cultural Resources Monitoring | Fixed fee | In Progress | L8030 | E30957 | Ironbridge Infrastructure Group | 46.52% | 327400 | 137397.62 | 229376.44 | 23897.76 | 10684.14 | 152306.48 | 8536.1 | 9603.51 | 0 | 14908.86 | 0 | 14908.86 | 0 | 166.75 | 7.75 | 0 | 12667 | 006arGJCXetedDWY76 | FALSE
26-PC-32711 | Creosote Draw Phase I Survey | Fixed fee | In Progress | L8030 | E30958 | Evergreen County | 20.93% | 62100 | 10647.65 | 44997.66 | 1903.03 | 2065.32 | 12997.53 | 1092.71 | 1520.22 | 0 | 2349.88 | 0 | 2349.88 | 0 | 23.25 | 0 | 597 | 11354 | 006tTdx1ODX04wPwJj | FALSE
26-PC-32725 | Willow Springs Wind Farm - GIS Mapping | Fixed fee | Final Reporting/Review | L8030 | E30947 | Highland Planning Associates | 61.14% | 26300 | 12170.12 | 18699.3 | 4715.32 | 2740.75 | 16079.82 | 1371.84 | 1353.65 | 0 | 3909.7 | 0 | 3909.7 | 0 | 32.5 | 0 | 271 | 12340 | 006xgqUjCvlSBVf5QR | FALSE
26-PC-32727 | North Fork Mine Expansion - Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | L8030 | E30948 | Granite State Infrastructure Group | 82.16% | 70100 | 57594.16 | 47310.49 | 0 | 0 | 57594.16 | 2487.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817 | 11510 | 006sxzqgtmJFzPDv9a | TRUE
26-PC-32731 | Wildrye Fiber Route Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8030 | E30947 | Clearwater Planning Associates | 100% | 26000 | 26000 | 20311.2 | 0 | 0 | 26000 | 1350.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10938 | 006UOfg9xScUFZVylG | TRUE
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Time and material | Cost Tracking on Closed Project | L8030 | E30957 | Brightwater Utilities | 0% | 137100 | 0 | 100617.66 | 0 | 0 | 0 | 22737.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063 | 10408 | 00697oQEng3cZHw164 | FALSE
26-PC-32745 | Task Order 37: Hawk Point Park Improvements Phase II Testing | Fixed fee | In Progress | L8030 | E30950 | Summit Renewables LLC | 41.5% | 135300 | 34745.99 | 89758.02 | 19071.94 | 12478.14 | 56149.5 | 3873.76 | 13126.84 | 0 | 21403.51 | 0 | 21403.51 | 0 | 189 | 0 | 0 | 15274 | 006B1b32FNyszyoQSf | TRUE
26-PC-32773 | Oak Terrace Paleontological Monitoring | Fixed fee | In Progress | L8040 | E30979 | Brightwater Power Cooperative | 44.15% | 48100 | 16486.92 | 32496.36 | 4831.09 | 4056.45 | 21236.15 | 1463.47 | 1690.65 | 0 | 4749.23 | 0 | 4749.23 | 0 | 35 | 0 | 0 | 10363 | 006Plru1O2ZZPGnO2d | FALSE
26-PC-32803 | Copper Flats Housing Development Archaeological Testing | Time and material | Final Billing/Invoice | L8040 | E30967 | Evergreen Power Cooperative | 100% | 198300 | 0 | 132700 | 0 | 0 | 0 | 17532.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1793 | 11431 | 006HPjJJ1J1rpYF3og | FALSE
26-PC-32852 | Task Order 39: Foxglove Highway Widening Data Recovery | Time and material | In Progress | L8040 | E30976 | Stonebridge County | 0% | 148800 | 18923.38 | 95395.68 | 14999.32 | 3549.56 | 31449.25 | 1403.6 | 2968.78 | 0 | 12525.87 | 0 | 12525.87 | 0 | 62 | 0 | 1154 | 14884 | 006hhfP63vhFgFjcOc | FALSE
26-PC-32946 | Phase I: Plover Cove Levee Repair GIS Mapping | Time and material | On Hold | L8040 | E30971 | Westwind Energy Partners | 0% | 151600 | 0 | 96190.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376 | 15833 | 006HNaJpo54GZ16WUA | FALSE
26-PC-32973 | Sage Flat GIS Mapping | Time and material | On Hold | L8040 | E30979 | Canyon Construction Co. | 0% | 203200 | 0 | 132028.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1423 | 10448 | 006LVL1wTqtiTWYOlt | FALSE
26-PC-32985 | Pine Hollow Built Environment Survey | Fixed fee | In Progress | L8040 | E30971 | Cardinal Rail Partners | 60.83% | 106500 | 55174.32 | 89214.38 | 15073.17 | 9268.44 | 64783.95 | 7651.66 | 6442.14 | 0 | 9609.63 | 0 | 9609.63 | 0 | 98.75 | 0 | 0 | 10792 | 006k6OB4fKJxGEl1l8 | FALSE
26-PC-33011 | Kestrel Butte Wastewater Plant Curation | Fixed fee | Completed | L8040 | E30972 | Redtail Infrastructure Group | 100% | 590600 | 590600 | 477965.46 | 0 | 0 | 590600 | 62049.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14267 | 0068lChk70yFamMjy2 | TRUE
26-PC-33017 | Redbud Battery Storage - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8040 | E30979 | Westwind Engineering, Inc. | 31.96% | 588600 | 188116.56 | 441413.1 | 0 | 0 | 188116.56 | 18338.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15856 | 006YinZHHg083MUfWy | TRUE
26-PC-33033 | Task Order 10: Pebble Beach Road Highway Widening Environmental Review Support | Fixed fee | On Hold | L8040 | E30976 | Northfield Pipeline Company | 0% | 121200 | 0 | 102111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062 | 13520 | 006t7Ifca7qlcCTTQe | FALSE
26-PC-33099 | Eagle Bend Maritime Remote Sensing Survey | Fixed fee | In Progress | L8040 | E30976 | Brightwater Rail Partners | 17.62% | 164900 | 16045.73 | 122091.96 | 13150.76 | 2894.97 | 29055.38 | 2581.28 | 7455.34 | 0 | 13009.65 | 0 | 13009.65 | 0 | 106 | 0 | 1628 | 10392 | 00685f2P83u3PbDx2t | FALSE
26-PC-33127 | Fern Valley Phase I Survey | Time and material | In Progress | L8040 | E30967 | Northfield Pipeline Company | 0% | 179500 | 39555.28 | 119968.02 | 10662.82 | 3523.06 | 46153.5 | 4563.81 | 3098.99 | 0 | 6598.22 | 0 | 6598.22 | 0 | 39.5 | 0 | 0 | 13520 | 006jHz2LiSoupds5bH | FALSE
26-PC-33162 | Phase III: Yarrow Point Airport Apron GIS Mapping | Time and material | In Progress | L8040 | E30980 | Silverline Telecom Holdings | 0% | 81900 | 8708.14 | 55036.8 | 3509.02 | 1222.86 | 9863.25 | 1157.55 | 0 | 0 | 1155.11 | 0 | 1155.11 | 0 | 0 | 0 | 0 | 14780 | 006Rv7jfkn1GkuXnTY | FALSE
26-PC-33217 | Larkspur Phase II Testing | Fixed fee | Final Billing/Invoice | L8040 | E30972 | Sunrise Planning Associates | 100% | 28700 | 28700 | 20572.16 | 0 | 0 | 28700 | 1529.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 15406 | 0066ZWOnWtWVLCrviC | FALSE
26-PC-33223 | Meadowlark Levee Repair - Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8040 | E30971 | High Plains County | 100% | 51600 | 51600 | 37858.92 | 0 | 0 | 51600 | 10778.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467 | 11980 | 006UDjBRxQVjH0s3PJ | FALSE
26-PC-33255 | Task Order 13: Pine Hollow Substation Maritime Remote Sensing Survey | Time and material | Final Billing/Invoice | L8040 | E30972 | Stonebridge Engineering, Inc. | 100% | 70300 | 0 | 51804.07 | 0 | 0 | 0 | 9620.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696 | 14937 | 006dUdGJMGn5oTnQY8 | FALSE
26-PC-33257 | Badger Hollow Levee Repair - Curation | Time and material | Completed | L8040 | E30976 | Pioneer Development Group | 100% | 60000 | 0 | 42360 | 0 | 0 | 0 | 8551.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 13750 | 006E2lbpQLgftH9iIx | FALSE
26-PC-33276 | Quail Run Housing Development Archaeological Testing | Time and material | In Progress | L8040 | E30971 | High Plains Renewables LLC | 0% | 64200 | 15096.5 | 42609.54 | 1085.15 | 690.72 | 15702.5 | 1306.06 | 92.06 | 0 | 606 | 0 | 606 | 0 | 2 | 0 | 778 | 12128 | 0066alvDRkW9ke4rzX | FALSE
26-PC-33413 | Hawk Point Bridge Replacement Cultural Resources Monitoring | Time and material | Final Billing/Invoice | L8040 | E30971 | Redtail Infrastructure Group | 100% | 484800 | 0 | 325106.88 | 0 | 0 | 0 | 31975.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6333 | 14267 | 0061zhS483DUGV7h58 | FALSE
26-PC-33485 | Sea Oat Harbor Dredging GIS Mapping | Time and material | In Progress | L8040 | E30980 | Summit County | 0% | 563800 | 22501.56 | 406950.84 | 20085.33 | 2416.23 | 45105.5 | 4945.12 | 11131.27 | 0 | 22603.94 | 0 | 22603.94 | 0 | 170.5 | 8 | 3726 | 15070 | 006Yc90rEiMRuCestg | FALSE
26-PC-33505 | Stone Mill Park Improvements - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8040 | E30979 | Heartland Water District | 1.42% | 105100 | 398.58 | 81200.26 | 398.58 | 0 | 1492.42 | 213.28 | 939.59 | 0 | 1093.84 | 0 | 1093.84 | 0 | 8.25 | 0 | 411 | 11891 | 006MAdeLq3TCI5EjsU | TRUE
26-PC-33533 | Harbor View Wastewater Plant Phase I Survey | Fixed fee | Final Billing/Invoice | L8040 | E30971 | Coastal Rail Partners | 100% | 37700 | 37700 | 27626.56 | 0 | 0 | 37700 | 4345.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427 | 11259 | 006Wiy8sEBto679uUD | TRUE
26-PC-33563 | Foxglove Phase I Survey | Fixed fee | In Progress | L8040 | E30972 | Cardinal Rail Partners | 0% | 61100 | 0 | 42098.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10792 | 006lrBNdWZkbdx6nKN | FALSE
26-PC-33588 | Fern Valley Trail - Cultural Resources Assessment | Time and material | Lab/Curation | L8040 | E30976 | Coastal Development Group | 0% | 207400 | 35440.47 | 141868.32 | 3627.42 | 3719.04 | 38333.25 | 1882.32 | 1712.95 | 0 | 2892.78 | 0 | 2892.78 | 0 | 35.25 | 0 | 1883 | 11160 | 006acdQREg84iREIQl | FALSE
26-PC-33624 | Stone Mill Airport Apron - Phase II Testing | Fixed fee | Final Billing/Invoice | L8040 | E30972 | Evergreen Development Group | 100% | 54500 | 54500 | 38509.7 | 0 | 0 | 54500 | 3254.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11371 | 006XNllq8niptzTA3v | FALSE
26-PC-33660 | Task Order 33: Fern Valley Water Main Section 106 Consultation | Fixed fee | In Progress | L8040 | E30980 | Northfield Water District | 22.34% | 108400 | 7479.68 | 94229.41 | 7479.68 | 0 | 24216.56 | 4294.76 | 6415.75 | 0 | 16736.88 | 0 | 16736.88 | 0 | 119.25 | 0 | 1375 | 13685 | 0064UBvoG7pefgDvZB | FALSE
26-PC-33684 | On-Call: Juniper Wash Airport Apron Paleontological Monitoring | Time and material | Final Reporting/Review | L8040 | E30967 | Summit Renewables LLC | 0% | 24000 | 1910.97 | 17450.4 | 1910.97 | 0 | 4253.75 | 265.06 | 1014.16 | 0 | 2342.78 | 0 | 2342.78 | 0 | 23.25 | 0 | 261 | 15274 | 006Tlnn0FZOE5gkwrK | FALSE
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Fixed fee | Final Reporting/Review | L8050 | E30987 | Granite State Resources Corp. | 100% | 21700 | 11375.68 | 18501.42 | 8954.09 | 2421.59 | 21700 | 3377.01 | 4120.22 | 0 | 10324.32 | 0 | 10324.32 | 0 | 63 | 1.5 | 197 | 11571 | 006Z5cqAzHxJxt6KM4 | FALSE
26-PC-33705 | Twin Buttes Phase I Survey | Fixed fee | In Progress | L8050 | E30987 | Summit Planning Associates | 48.12% | 211200 | 84698.25 | 166784.64 | 29054.66 | 13643.61 | 101629.44 | 7945.49 | 9415.48 | 0 | 16931.19 | 0 | 16931.19 | 0 | 149.25 | 10.75 | 0 | 15198 | 006SkmoLxhqEkaiea1 | TRUE
26-PC-33719 | Saltgrass GIS Mapping | Fixed fee | In Progress | L8050 | E30998 | Mesa Verde Planning Associates | 2.86% | 394200 | 4081.27 | 310235.4 | 4081.27 | 0 | 11274.12 | 1828.93 | 3051.43 | 0 | 7192.85 | 0 | 7192.85 | 0 | 73.5 | 0 | 8181 | 13344 | 006OonJV7oE8sCMdJN | FALSE
26-PC-33727 | Task Order 25: Badger Hollow Canal Lining Architectural History Survey | Fixed fee | Final Billing/Invoice | L8050 | E30984 | Summit Planning Associates | 100% | 185200 | 185200 | 146011.68 | 0 | 0 | 185200 | 12192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693 | 15198 | 006fI0UeXTgc3shxY0 | FALSE
26-PC-33743 | Raven Rock Canal Lining Architectural History Survey | Fixed fee | In Progress | L8050 | E31000 | Sunrise Telecom Holdings | 54.81% | 111800 | 58305.85 | 75766.86 | 3470.82 | 2902.49 | 61277.58 | 4401.83 | 3034.86 | 0 | 2971.73 | 0 | 2971.73 | 0 | 42.5 | 0 | 511 | 15492 | 006uG0UWfN03RlUwfY | FALSE
26-PC-33773 | Aspen Ridge Maritime Remote Sensing Survey | Fixed fee | On Hold | L8050 | E30986 | Northfield Water District | 0% | 41200 | 0 | 25469.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 13685 | 006nldGxR0xdUaGJGi | TRUE
26-PC-33834 | On-Call: Silver Lake Canal Lining Curation | Fixed fee | In Progress | L8050 | E30992 | Keystone Energy Partners | 23.87% | 204800 | 40950.62 | 158052.15 | 13185.81 | 6417.28 | 48885.76 | 6149.28 | 4712.56 | 0 | 7935.14 | 0 | 7935.14 | 0 | 105.75 | 0 | 3346 | 12804 | 00622TJV2ArJkBoF9Y | FALSE
26-PC-33896 | Maple Fork Trail Curation | Fixed fee | In Progress | L8050 | E30995 | Ironbridge Port Authority | 31.23% | 69800 | 14218.1 | 48734.36 | 7411.73 | 3467.92 | 21798.54 | 1902.77 | 1489.58 | 0 | 7580.44 | 0 | 7580.44 | 0 | 19.5 | 0 | 518 | 12704 | 006FtChxawexoZYQ7z | FALSE
26-PC-33903 | Task Order 3: Silver Lake Solar Cultural Resources Monitoring | Fixed fee | Final Billing/Invoice | L8050 | E30997 | Highland Telecom Holdings | 100% | 1201100 | 1201100 | 916078.97 | 0 | 0 | 1201100 | 155432.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12240 | 12458 | 0065QSZcUs0GVSnkeT | FALSE
26-PC-33913 | Windmill Flat Section 106 Consultation | Time and material | Final Reporting/Review | L8050 | E30984 | Sunrise County | 0% | 31100 | 828.06 | 20015.96 | 828.06 | 0 | 1702.75 | 200.81 | 0 | 0 | 874.69 | 0 | 874.69 | 0 | 0 | 0 | 278 | 15336 | 006nf17q6y3npev2Gl | FALSE
26-PC-33950 | Raven Rock Built Environment Survey | Fixed fee | Final Billing/Invoice | L8050 | E30985 | Stonebridge Engineering, Inc. | 100% | 483700 | 483700 | 372594.11 | 0 | 0 | 483700 | 43473.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3653 | 14937 | 006XbdpdR42SvK4PA6 | FALSE
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | Fixed fee | In Progress | L8050 | E30995 | Heartland Port Authority | 100% | 76400 | 70250.02 | 53087.85 | 9131.46 | 3759.36 | 76400 | 13033.14 | 4868.4 | 0 | 6149.98 | 0 | 6149.98 | 0 | 71.25 | 1.5 | 0 | 11802 | 006EAmyD3G114jRs8P | FALSE
26-PC-34114 | Granite Pass Canal Lining - Section 106 Consultation | Time and material | In Progress | L8050 | E31000 | Prairie Wind County | 0% | 216500 | 12093.51 | 145812.75 | 5032 | 1491.58 | 17201 | 582.9 | 2058.47 | 0 | 5107.49 | 0 | 5107.49 | 0 | 49.75 | 0 | 3895 | 13978 | 006MENkojOZtQZoBjk | FALSE
26-PC-34198 | Tansy Flat Pipeline - Historic Resources Evaluation | Time and material | In Progress | L8050 | E31000 | Evergreen Development Group | 0% | 65600 | 16223.25 | 47297.6 | 111.2 | 57.09 | 16223.25 | 783.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 11371 | 006n2NgTszkriE0Es4 | FALSE
26-PC-34247 | Harbor View Trail Phase I Survey | Fixed fee | Final Billing/Invoice | L8050 | E30985 | Keystone Energy Partners | 100% | 106200 | 106200 | 73362.96 | 0 | 0 | 106200 | 20028.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858 | 12804 | 006ffZN7pAxDJWq328 | FALSE
26-PC-34297 | Badger Hollow Historic Resources Evaluation | Fixed fee | In Progress | L8050 | E30997 | Canyon Construction Co. | 8.38% | 41700 | 3494.46 | 29306.76 | 0 | 0 | 3494.46 | 198.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611 | 10448 | 006G4gBDC5GmgpjWZ1 | TRUE
26-PC-34336 | Pine Hollow Solar Architectural History Survey | Fixed fee | In Progress | L8050 | E30985 | Blue Mesa Environmental Consultants | 30.37% | 56500 | 16619.72 | 40414.45 | 1471.79 | 726.35 | 17159.05 | 1485.03 | 429.12 | 0 | 539.33 | 0 | 539.33 | 0 | 10.5 | 0 | 772 | 10083 | 006vStMB2dVCAwaII7 | FALSE
26-PC-34394 | Ember Valley Battery Storage Maritime Remote Sensing Survey | Time and material | In Progress | L8050 | E30984 | Coastal County | 0% | 134200 | 0 | 94370.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 11118 | 006ustjku6C1KUkWYu | FALSE
26-PC-34400 | Wren Hollow Curation | Fixed fee | In Progress | L8050 | E30992 | Cardinal Port Authority | 6.06% | 34200 | 1844.21 | 23833.56 | 210.02 | 142.9 | 2072.52 | 280.2 | 0 | 0 | 228.31 | 0 | 228.31 | 0 | 0 | 0 | 158 | 10753 | 006738l6G83c9NxP3D | FALSE
26-PC-34432 | Stone Mill Bridge Replacement - GIS Mapping | Fixed fee | Final Reporting/Review | L8050 | E30997 | Riverstone Port Authority | 8.69% | 117900 | 6103.62 | 80620.02 | 3477.07 | 2626.55 | 10245.51 | 1429.27 | 1548.51 | 0 | 4141.89 | 0 | 4141.89 | 0 | 25.75 | 0 | 790 | 14640 | 006VRk6zp7d1kHNvcg | FALSE
26-PC-34472 | Eagle Bend Canal Lining Phase II Testing | Time and material | Completed | L8050 | E30998 | Sunrise County | 100% | 25400 | 0 | 16500.99 | 0 | 0 | 0 | 2180.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 15336 | 006cv1B4z3yLZDFlKm | FALSE
26-PC-34477 | Willow Springs Pipeline - Cultural Resources Monitoring | Fixed fee | In Progress | L8050 | E30986 | Keystone Energy Partners | 11.05% | 212500 | 15454.44 | 157143.75 | 13024.85 | 2429.59 | 23481.25 | 1476.32 | 5573.53 | 0 | 8026.81 | 0 | 8026.81 | 0 | 93.75 | 4.25 | 2598 | 12804 | 0060SByXKkqEklX7R9 | TRUE
26-PC-34487 | Quail Run Airport Apron - Phase I Survey | Time and material | In Progress | L8050 | E31001 | Highland Infrastructure Group | 0% | 488600 | 171542.56 | 348176.36 | 28209.68 | 27653.65 | 212913.75 | 11687.65 | 19087.47 | 0 | 41371.19 | 0 | 41371.19 | 0 | 326.5 | 15 | 7902 | 12316 | 006Q8F70YXGhjCCD4x | FALSE
26-PC-34552 | Blue Heron Mine Expansion Phase I Survey | Fixed fee | Lab/Curation | L8050 | E30986 | Heartland Transit Authority | 1.89% | 245500 | 2962.54 | 205115.25 | 2102.36 | 860.18 | 4639.95 | 539.55 | 231.75 | 0 | 1677.41 | 0 | 1677.41 | 0 | 4.75 | 0 | 4357 | 11878 | 006q28VefIRf0PtU54 | FALSE
26-PC-34574 | Elk Meadow Pipeline Paleontological Monitoring | Time and material | Completed | L8050 | E31000 | Heartland Power Cooperative | 100% | 1357400 | 0 | 944343.18 | 0 | 0 | 0 | 63243.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17017 | 11841 | 006QMP3g8Au5vy006D | FALSE
26-PC-34602 | Phase III: Sandpiper Park Improvements Historic Resources Evaluation | Fixed fee | In Progress | L8050 | E31000 | Highland Construction Co. | 87.83% | 36800 | 28986.41 | 26501.12 | 2430.07 | 1441.89 | 32321.44 | 2257.67 | 1574.36 | 0 | 3335.03 | 0 | 3335.03 | 0 | 28.25 | 2.25 | 239 | 12239 | 006zUcSh27zEIJwDpV | TRUE
26-PC-34611 | Wren Hollow Pipeline Environmental Review Support | Time and material | In Progress | L8050 | E30985 | Pioneer Renewables LLC | 0% | 365800 | 0 | 264180.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4543 | 13869 | 006IGoXcaCkv2WE3mL | FALSE
26-PC-34628 | Meadowlark Canal Lining Class III Survey | Fixed fee | Final Billing/Invoice | L8050 | E30992 | Cardinal Environmental Consultants | 100% | 121500 | 121500 | 80104.95 | 0 | 0 | 121500 | 12097.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 10678 | 0067DP6lzw8LEqjQjY | FALSE
26-PC-34631 | Tamarack Battery Storage - Phase I Survey | Fixed fee | Completed | L8050 | E31000 | Clearwater Planning Associates | 100% | 438600 | 438600 | 344257.14 | 0 | 0 | 438600 | 52560.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3690 | 10938 | 0065QJ19jO3czceeTJ | TRUE
26-PC-34701 | North Fork Paleontological Monitoring | Time and material | Final Billing/Invoice | L8050 | E30999 | Brightwater Power Cooperative | 100% | 248300 | 0 | 162629.9 | 0 | 0 | 0 | 36152.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594 | 10363 | 006K8q27utXrn63wZK | FALSE
26-PC-34711 | Hackberry Bend Section 106 Consultation | Fixed fee | Completed | L8050 | E30987 | Keystone Environmental Consultants | 100% | 34000 | 34000 | 25561.2 | 0 | 0 | 34000 | 3012.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12815 | 006dbGXVOyY8pkuRpP | TRUE
26-PC-34725 | Redbud Paleontological Monitoring | Fixed fee | In Progress | L8050 | E30999 | Blue Mesa Environmental Consultants | 11.23% | 107600 | 8872.18 | 89211.16 | 2061.16 | 1428.32 | 12083.48 | 681.13 | 0 | 0 | 3211.3 | 0 | 3211.3 | 0 | 0 | 0 | 1060 | 10083 | 006kytGP0DcUvZsgZA | TRUE
26-PC-34757 | Kestrel Butte Data Recovery | Time and material | In Progress | L8050 | E30984 | Harborlight Water District | 0% | 43800 | 29653.46 | 30230.76 | 9454.61 | 8831.1 | 43800 | 8218.37 | 7387.49 | 0 | 14146.54 | 0 | 14146.54 | 0 | 106.5 | 0 | 281 | 11739 | 006DXJeN9otL6tBS7E | FALSE
26-PC-34794 | On-Call: Kestrel Butte Reservoir Class III Survey | Fixed fee | Completed | L8060 | E31014 | Evergreen Power Cooperative | 100% | 40000 | 40000 | 25252 | 0 | 0 | 40000 | 4792.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407 | 11431 | 006Y12npipVgLlvJB4 | FALSE
26-PC-34906 | Cedar Hollow Harbor Dredging - Curation | Fixed fee | In Progress | L8060 | E31008 | Ridgeline Energy Partners | 51.74% | 81100 | 34013.4 | 60821.43 | 6050.36 | 2938.91 | 41961.14 | 2517.76 | 5172.92 | 0 | 7947.74 | 0 | 7947.74 | 0 | 102.75 | 4 | 1147 | 14433 | 006M2fIhIjQrusMTuF | TRUE
26-PC-34965 | On-Call: Pebble Beach Road Fiber Route Section 106 Consultation | Fixed fee | Final Reporting/Review | L8060 | E31019 | Stonebridge Utilities | 0% | 131600 | 0 | 95225.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 15036 | 0068UzUbjAT1jXA0Ny | FALSE
26-PC-34982 | Sandpiper Historic Resources Evaluation | Time and material | In Progress | L8060 | E31018 | Redtail Builders | 0% | 10600 | 7692.83 | 7895.94 | 3339.98 | 2689.08 | 10600 | 1580.72 | 74.26 | 0 | 2907.17 | 0 | 2907.17 | 0 | 0.75 | 0 | 110 | 14184 | 006JKheQe0zIJhAQL6 | FALSE
26-PC-35012 | Task Order 40: Granite Pass Harbor Dredging Archaeological Testing | Time and material | Final Billing/Invoice | L8060 | E31019 | Sunrise Planning Associates | 100% | 179700 | 0 | 130282.5 | 0 | 0 | 0 | 25973.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15406 | 006HQs3CUOtVRR9MwL | FALSE
26-PC-35056 | Yarrow Point Cell Tower - Section 106 Consultation | Fixed fee | Lab/Curation | L8060 | E31008 | Ironbridge Port Authority | 49.98% | 92800 | 43606.66 | 78555.2 | 1383.27 | 1150.69 | 46381.44 | 6949.24 | 858.78 | 0 | 2774.78 | 0 | 2774.78 | 0 | 18 | 0 | 1032 | 12704 | 0069JiqKuYKkOliL1S | FALSE
26-PC-35062 | Phase I: Falcon Mesa Park Improvements Data Recovery | Fixed fee | In Progress | L8060 | E31018 | Pioneer Engineering, Inc. | 11.47% | 267300 | 4507.74 | 207542.06 | 4507.74 | 0 | 30659.31 | 3785.43 | 12676.02 | 0 | 26151.57 | 0 | 26151.57 | 0 | 217.5 | 8.75 | 2128 | 13790 | 006oyzU0WPFkLyHozh | FALSE
26-PC-35063 | Meadowlark School Campus - Phase I Survey | Fixed fee | Final Reporting/Review | L8060 | E31018 | Timberline Planning Associates | 52.78% | 112100 | 53777.48 | 70129.76 | 5757.74 | 2399.41 | 59166.38 | 4367.95 | 1280.84 | 0 | 5388.9 | 0 | 5388.9 | 0 | 33.5 | 0 | 0 | 15643 | 006s5YFgmsqzTtRGry | FALSE
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | Fixed fee | In Progress | L8060 | E31014 | Summit Renewables LLC | 100% | 29600 | 22003.12 | 19287.36 | 10434.75 | 6747.14 | 29600 | 10919.73 | 1718.07 | 0 | 7596.88 | 0 | 7596.88 | 0 | 41.5 | 0 | 252 | 15274 | 006RzefXiCM7QS6udF | FALSE
26-PC-35111 | Fern Valley GIS Mapping | Fixed fee | Final Billing/Invoice | L8060 | E31018 | Coastal Rail Partners | 100% | 114800 | 114800 | 81129.16 | 0 | 0 | 114800 | 9285.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683 | 11259 | 006vVp9S2IhzKLHzuu | FALSE
26-PC-35158 | Sparrow Hill Trail Phase I Survey | Fixed fee | In Progress | L8060 | E31018 | Blue Mesa County | 30.36% | 41600 | 5669.01 | 27755.93 | 3025.5 | 2643.51 | 12629.76 | 1264.02 | 7162.76 | 0 | 6960.75 | 0 | 6960.75 | 0 | 83 | 6.25 | 309 | 10001 | 006iJ7V7j0o7GtNzDh | FALSE
26-PC-35193 | Heron Marsh Reservoir - Phase II Testing | Fixed fee | In Progress | L8060 | E31014 | Keystone Environmental Consultants | 80.42% | 102600 | 71608.18 | 74022.89 | 16483.75 | 6323.81 | 82510.92 | 6964.72 | 5868.1 | 0 | 10902.74 | 0 | 10902.74 | 0 | 122.5 | 0 | 1368 | 12815 | 006n397mHr9STvnPn6 | FALSE
26-PC-35201 | Plover Cove Transmission Line Data Recovery | Fixed fee | Lab/Curation | L8060 | E31008 | Stonebridge Utilities | 3.02% | 51600 | 145.25 | 40057.08 | 145.25 | 0 | 1558.32 | 111.46 | 1100.01 | 0 | 1413.07 | 0 | 1413.07 | 0 | 29.25 | 0 | 0 | 15036 | 0069xgEPTEjXSJRpgm | FALSE
26-PC-35220 | Badger Hollow Highway Widening GIS Mapping | Time and material | In Progress | L8060 | E31018 | Summit Port Authority | 0% | 109500 | 1288.42 | 69598.2 | 1288.42 | 0 | 4400.75 | 630.27 | 2444.21 | 0 | 3112.33 | 0 | 3112.33 | 0 | 50.25 | 4 | 989 | 15239 | 0062R9avmtpf4ItjXN | FALSE
26-PC-35245 | Stone Mill Cell Tower - Curation | Time and material | Completed | L8060 | E31019 | Riverstone Resources Corp. | 100% | 240900 | 0 | 162438.87 | 0 | 0 | 0 | 34270.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14683 | 006pgNJPF1Mq9gU86a | FALSE
26-PC-35248 | Granite Pass Levee Repair - Curation | Fixed fee | Final Billing/Invoice | L8060 | E31018 | Clearwater Builders | 100% | 107400 | 107400 | 75437.76 | 0 | 0 | 107400 | 7515.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855 | 10855 | 006r7ALS4qEJ7c1qMZ | TRUE
26-PC-35302 | Task Order 37: Hackberry Bend Battery Storage Cultural Resources Monitoring | Fixed fee | In Progress | L8060 | E31018 | High Plains County | 39.19% | 82400 | 21108.58 | 69199.52 | 9905.79 | 5520.54 | 32292.56 | 5450.74 | 2596.17 | 0 | 11183.98 | 0 | 11183.98 | 0 | 64.25 | 0 | 1094 | 11980 | 006F03Dx1zh6LgbPQw | FALSE
26-PC-35318 | Copper Flats Curation | Fixed fee | In Progress | L8060 | E31019 | Granite State Resources Corp. | 24.23% | 153900 | 27419.19 | 103851.72 | 15172.02 | 11639.48 | 37289.97 | 2465.9 | 3781.82 | 0 | 9870.78 | 0 | 9870.78 | 0 | 90 | 0 | 1934 | 11571 | 006R7BfN3xsl3nnwA7 | TRUE
26-PC-35381 | Badger Hollow Mine Expansion Archaeological Testing | Fixed fee | In Progress | L8070 | E31029 | Lakecrest Pipeline Company | 72.25% | 77800 | 45584.74 | 51064.93 | 15992.01 | 5215.34 | 56210.5 | 2435.19 | 2930.31 | 0 | 10625.76 | 0 | 10625.76 | 0 | 44.5 | 6.75 | 657 | 13006 | 006QdtRvCCCrsW28r3 | FALSE
26-PC-35401 | Raven Rock Phase II Testing | Time and material | In Progress | L8070 | E31029 | Northfield Telecom Holdings | 0% | 312900 | 8384.38 | 205376.26 | 8384.38 | 0 | 35485.5 | 2278.13 | 13606.52 | 0 | 27101.12 | 0 | 27101.12 | 0 | 250.25 | -0.5 | 1873 | 13631 | 0068lwwsZvrHj3K4ho | FALSE
26-PC-35449 | Saltgrass Cultural Resources Monitoring | Time and material | In Progress | L8070 | E31029 | Highland Infrastructure Group | 0% | 145800 | 7978.96 | 103226.4 | 7978.96 | 0 | 31446 | 4555.78 | 7656.11 | 0 | 23467.04 | 0 | 23467.04 | 0 | 119.25 | 1 | 900 | 12316 | 0069IUZ9JSbfQQqy2P | FALSE
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | Fixed fee | In Progress | L8070 | E31034 | Summit Engineering, Inc. | 86.4% | 68900 | 49947.75 | 53679.99 | 8320.71 | 6075.31 | 59529.6 | 3710.42 | 3771.39 | 0 | 9581.85 | 0 | 9581.85 | 0 | 65 | 4 | 746 | 15125 | 006H8d93IsaAemoLqN | FALSE
26-PC-35583 | On-Call: Eagle Bend Highway Widening Phase II Testing | Time and material | In Progress | L8070 | E31023 | Coastal Builders | 0% | 39700 | 721.99 | 28536.36 | 721.99 | 0 | 2479.5 | 239.66 | 1230.63 | 0 | 1757.51 | 0 | 1757.51 | 0 | 28.5 | 0 | 491 | 11038 | 006eYOmTUO1cRVDHJi | FALSE
26-PC-35588 | Fern Valley Wind Farm - Class III Survey | Fixed fee | Completed | L8070 | E31034 | Heartland Power Cooperative | 100% | 148800 | 148800 | 130289.28 | 0 | 0 | 148800 | 16090.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303 | 11841 | 006iqfiQ5Kdg7FpiWT | FALSE
26-PC-35596 | Millbrook Solar GIS Mapping | Fixed fee | Lab/Curation | L8070 | E31034 | Blue Mesa Pipeline Company | 21.37% | 197200 | 27554.12 | 149142.36 | 18587.1 | 5350.02 | 42141.64 | 3633.28 | 5909.5 | 0 | 14587.52 | 0 | 14587.52 | 0 | 136 | 0 | 3595 | 10171 | 006ojLltuItQzHw6Ye | TRUE
26-PC-35598 | Task Order 3: Raven Rock Rail Siding Built Environment Survey | Time and material | Final Billing/Invoice | L8070 | E31034 | Lakecrest Power Cooperative | 100% | 22100 | 0 | 15626.91 | 0 | 0 | 0 | 2092.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287 | 13081 | 0066pdzNC54pDBUgUu | FALSE
26-PC-35635 | Wren Hollow Architectural History Survey | Fixed fee | In Progress | L8070 | E31034 | Sunrise Planning Associates | 28.84% | 223600 | 42964.82 | 138900.32 | 27028.95 | 11204.25 | 64486.24 | 2964.42 | 7604.9 | 0 | 21521.42 | 0 | 21521.42 | 0 | 142.75 | 9.5 | 0 | 15406 | 006SpJC2mB4y1Na2n1 | FALSE
26-PC-35650 | Aspen Ridge Harbor Dredging - Maritime Remote Sensing Survey | Time and material | In Progress | L8070 | E31023 | Ironbridge Infrastructure Group | 0% | 155300 | 0 | 100626.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12667 | 006GPxCVB232QKpwhf | FALSE
26-PC-35698 | Silver Lake Class III Survey | Time and material | Completed | L8070 | E31029 | Lakecrest Telecom Holdings | 100% | 274000 | 0 | 188320.48 | 0 | 0 | 0 | 31826.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2258 | 13182 | 006BxkjKnwz2K1zA1j | FALSE
26-PC-35730 | Larkspur Solar Class III Survey | Fixed fee | In Progress | L8070 | E31034 | Blue Mesa Energy Partners | 4.25% | 74800 | 1495.98 | 50078.6 | 1252.73 | 243.25 | 3179 | 459.42 | 1667.54 | 0 | 1683.02 | 0 | 1683.02 | 0 | 43.75 | 0 | 852 | 10054 | 006F8in3leab5kevLy | TRUE
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Fixed fee | Cost Tracking on Closed Project | L8070 | E31023 | Harborlight Water District | 100% | 26300 | 26300 | 19575.09 | 0 | 0 | 26300 | 3167.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 11739 | 006cMkacIA1mqo4E2U | FALSE
26-PC-35789 | Cedar Hollow Environmental Review Support | Time and material | In Progress | L8070 | E31034 | Ridgeline Resources Corp. | 0% | 3800 | 27.38 | 2575.26 | 27.38 | 0 | 159.5 | 7.48 | 88.46 | 0 | 132.12 | 0 | 132.12 | 0 | 2 | 0.25 | 73 | 14529 | 006iXLjZ7hD9RVv2dY | FALSE
26-PC-35803 | Tamarack Airport Apron GIS Mapping | Time and material | In Progress | L8070 | E31023 | Silverline Water District | 0% | 82900 | 87.2 | 52144.1 | 87.2 | 0 | 217.5 | 15.85 | 107.95 | 0 | 130.3 | 0 | 130.3 | 0 | 2.5 | 0 | 758 | 14839 | 006lOMyv0JsnciFyI1 | FALSE
26-PC-35811 | Phase III: Wildrye Solar Architectural History Survey | Time and material | In Progress | L8070 | E31034 | Granite State Rail Partners | 0% | 19500 | 0 | 12897.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 11524 | 006CWQHrlXUZ5b5uPb | FALSE
26-PC-35828 | Aspen Ridge Park Improvements - Class III Survey | Time and material | In Progress | L8070 | E31023 | Ironbridge Construction Co. | 0% | 48300 | 23270.14 | 31733.1 | 5818.91 | 3999.88 | 27612.25 | 3746.68 | 1550.22 | 0 | 4342.11 | 0 | 4342.11 | 0 | 26.75 | 1.25 | 308 | 12523 | 006xc7DvkmBjYUCeBk | FALSE
26-PC-35920 | Phase I: Creosote Draw Park Improvements Historic Resources Evaluation | Time and material | In Progress | L8070 | E31034 | Lakecrest Planning Associates | 0% | 61600 | 0 | 42591.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672 | 13040 | 006Wl0i5ZpZTDyPo5n | FALSE
26-PC-35937 | Pebble Beach Road Built Environment Survey | Fixed fee | Transferred Entity | L8070 | E31032 | Ironbridge Infrastructure Group | 9.87% | 73700 | 1654.38 | 51155.17 | 1654.38 | 0 | 7274.19 | 813.2 | 2002.63 | 0 | 5619.81 | 0 | 5619.81 | 0 | 51.25 | 0 | 1539 | 12667 | 006GmiCUIUVVuoGAjQ | FALSE
26-PC-35984 | Timber Gap Bridge Replacement Archaeological Testing | Time and material | Final Reporting/Review | L8070 | E31029 | Coastal Planning Associates | 0% | 75200 | 7059.33 | 47215.34 | 5168.65 | 1890.68 | 13619.25 | 2143.69 | 2416.25 | 0 | 6559.92 | 0 | 6559.92 | 0 | 51.5 | 0 | 804 | 11250 | 006zP7ZUsCCdNxalq5 | FALSE
26-PC-36056 | Rushgrass Draw Historic Resources Evaluation | Fixed fee | Completed | L8070 | E31029 | Blue Mesa Pipeline Company | 100% | 559500 | 559500 | 461307.75 | 0 | 0 | 559500 | 88241.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7519 | 10171 | 006uXmEeP8koj8mLv0 | TRUE
26-PC-36110 | Blue Heron Canal Lining - Section 106 Consultation | Fixed fee | In Progress | L8070 | E31029 | Coastal County | 7.14% | 776100 | 49922.17 | 567018.66 | 11893.95 | 4511.15 | 55413.54 | 4048.11 | 2997.9 | 0 | 5491.37 | 0 | 5491.37 | 0 | 69.5 | 0 | 12606 | 11118 | 006zD97XH0mzbLaQtK | FALSE
26-PC-36112 | Task Order 31: Twin Buttes Housing Development Built Environment Survey | Fixed fee | Final Billing/Invoice | L8070 | E31032 | Sunrise Telecom Holdings | 100% | 39800 | 39800 | 29581.08 | 0 | 0 | 39800 | 2422.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 | 15492 | 0069TpVzhd5TnRcbtJ | FALSE
26-PC-36208 | Foxglove Fiber Route GIS Mapping | Time and material | Final Billing/Invoice | L8070 | E31023 | Heartland Transit Authority | 100% | 36600 | 0 | 24946.56 | 0 | 0 | 0 | 4908.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 11878 | 006R7ixOQXiocGDvHv | FALSE
26-PC-36247 | Harbor View Maritime Remote Sensing Survey | Fixed fee | In Progress | L8080 | E31046 | Northfield Pipeline Company | 1.18% | 44300 | 202 | 33455.36 | 140.72 | 61.28 | 522.74 | 34.73 | 179.96 | 0 | 320.74 | 0 | 320.74 | 0 | 4 | 0 | 418 | 13520 | 006tTrsuphqFpbdmet | TRUE
26-PC-36281 | Saltgrass Mixed-Use Development Architectural History Survey | Time and material | In Progress | L8080 | E31047 | Harborlight Builders | 0% | 25900 | 109.61 | 16954.14 | 109.61 | 0 | 202.5 | 26.38 | 112.48 | 0 | 92.89 | 0 | 92.89 | 0 | 2.5 | 0 | 0 | 11612 | 0065iYslwzxxPZ5kfF | FALSE
26-PC-36361 | Dove Canyon Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | L8080 | E31046 | Blue Mesa County | 100% | 343400 | 343400 | 282103.1 | 0 | 0 | 343400 | 44892.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581 | 10001 | 006yoVxj2nIX1DAIwh | FALSE
26-PC-36394 | Meadowlark Cultural Resources Monitoring | Fixed fee | In Progress | L8080 | E31041 | Summit Infrastructure Group | 5.23% | 61900 | 1344.78 | 39879.42 | 1128.79 | 215.99 | 3237.37 | 343.94 | 1069.09 | 0 | 1892.59 | 0 | 1892.59 | 0 | 16 | 0 | 610 | 15147 | 006BfTUEG8YnMpbTnL | FALSE
26-PC-36396 | Task Order 9: Twin Buttes Solar Architectural History Survey | Fixed fee | In Progress | L8080 | E31041 | Stonebridge Engineering, Inc. | 12.56% | 77700 | 7129.67 | 47283.31 | 4878.18 | 1893.81 | 9759.12 | 759.96 | 1147.65 | 0 | 2629.45 | 0 | 2629.45 | 0 | 15.5 | 0 | 467 | 14937 | 006oS5H12NXzt6QMZX | TRUE
26-PC-36416 | Task Order 2: Thistle Down Wind Farm Archaeological Testing | Fixed fee | Lab/Curation | L8080 | E31046 | Harborlight County | 45.9% | 589600 | 239675.91 | 462173.13 | 24068.45 | 25760.11 | 270626.4 | 46674.22 | 19698.53 | 0 | 30950.49 | 0 | 30950.49 | 0 | 278 | 0 | 3666 | 11648 | 0064eGGQi8ymZ1yZLq | FALSE
26-PC-36477 | Elk Meadow Pipeline - Environmental Review Support | Fixed fee | Final Billing/Invoice | L8080 | E31041 | Ironbridge Infrastructure Group | 100% | 70100 | 70100 | 51383.3 | 0 | 0 | 70100 | 4341.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587 | 12667 | 006FwGYZvs0ym0wvIs | FALSE
26-PC-36537 | Yarrow Point Park Improvements Built Environment Survey | Fixed fee | In Progress | L8080 | E31047 | Summit County | 31.56% | 125300 | 36421.55 | 86482.06 | 3069.89 | 2139.51 | 39544.68 | 4803.37 | 1781.4 | 0 | 3123.13 | 0 | 3123.13 | 0 | 29 | 1 | 988 | 15070 | 006Vph0PLFmfrh1UJ0 | TRUE
26-PC-36548 | Phase II: Granite Pass Levee Repair Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8080 | E31047 | Lakecrest Development Group | 100% | 59700 | 59700 | 35999.1 | 0 | 0 | 59700 | 6702.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395 | 12986 | 006RfCWgZHv4LL995F | FALSE
26-PC-36555 | Coyote Springs Pipeline Class III Survey | Time and material | On Hold | L8080 | E31043 | Brightwater Land Company | 0% | 206100 | 0 | 139514.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10261 | 006AWa5ZTqrf9JJHkh | FALSE
26-PC-36581 | Harbor View Maritime Remote Sensing Survey | Fixed fee | In Progress | L8080 | E31041 | Mesa Verde County | 38.21% | 127600 | 43545.62 | 76674.84 | 8698.16 | 5216.48 | 48755.96 | 2812.76 | 3818.4 | 0 | 5210.34 | 0 | 5210.34 | 0 | 53.75 | 0 | 831 | 13234 | 006BGxiSePcJJfMwPG | TRUE
26-PC-36595 | Blue Heron School Campus - Cultural Resources Monitoring | Time and material | Completed | L8090 | E31051 | Pioneer Development Group | 100% | 35700 | 0 | 26328.75 | 0 | 0 | 0 | 3430.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 13750 | 006q19tVGV1KfqyLdC | FALSE
26-PC-36602 | Sea Oat Airport Apron Cultural Resources Monitoring | Fixed fee | In Progress | L8090 | E31052 | Harborlight Water District | 14.44% | 396600 | 42958.07 | 288646.28 | 13640.97 | 9265.76 | 57269.04 | 8752.92 | 4067.62 | 0 | 14310.97 | 0 | 14310.97 | 0 | 57.25 | 1 | 3485 | 11739 | 006QTNI8bhRBvCf7TP | FALSE
26-PC-36616 | Lone Pine Harbor Dredging - Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8090 | E31052 | Canyon Planning Associates | 100% | 79100 | 79100 | 51885.54 | 0 | 0 | 79100 | 5712.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586 | 10525 | 006WlRI3Ya389CGFe2 | FALSE
26-PC-36726 | Willow Springs Cultural Resources Assessment | Fixed fee | In Progress | L8090 | E31051 | Stonebridge Engineering, Inc. | 10.88% | 153200 | 0 | 110288.68 | 0 | 0 | 16668.16 | 864.28 | 7969.29 | 0 | 16668.16 | 0 | 16668.16 | 0 | 99.5 | 0.75 | 1117 | 14937 | 006JcTaupI3WSddYZ4 | FALSE
26-PC-36749 | Windmill Flat Water Main - Cultural Resources Assessment | Fixed fee | In Progress | L8090 | E31051 | Evergreen County | 47.9% | 199000 | 85531.32 | 173567.8 | 15794.3 | 3896.39 | 95321 | 7731.46 | 5831.5 | 0 | 9789.68 | 0 | 9789.68 | 0 | 78.25 | 2.25 | 2352 | 11354 | 0065kCzIs0yDssCSDd | FALSE
26-PC-36750 | Task Order 15: North Fork Canal Lining Data Recovery | Time and material | In Progress | L8090 | E31052 | Blue Mesa Environmental Consultants | 0% | 121800 | 11545.83 | 80948.28 | 11545.83 | 0 | 24027.5 | 922.42 | 2803.39 | 0 | 12481.67 | 0 | 12481.67 | 0 | 40.75 | 0 | 1714 | 10083 | 006diWIWakE7ufizFY | FALSE
26-PC-36775 | Falcon Mesa Cultural Resources Monitoring | Fixed fee | Transferred Entity | L8100 | E31063 | Lakecrest Telecom Holdings | 0.21% | 90800 | 37.35 | 77565.54 | 37.35 | 0 | 190.68 | 27.61 | 132.89 | 0 | 153.33 | 0 | 153.33 | 0 | 3 | 0.5 | 1726 | 13182 | 006Oq3dpQG3NDbydNa | TRUE
26-PC-36802 | Thistle Down Canal Lining - Cultural Resources Assessment | Time and material | Final Reporting/Review | L8100 | E31063 | Granite State Resources Corp. | 0% | 71600 | 0 | 52303.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 11571 | 006mKIqdG4liaMFecq | FALSE
26-PC-36828 | Phase III: Rushgrass Draw Canal Lining GIS Mapping | Time and material | In Progress | L8100 | E31063 | Mesa Verde Pipeline Company | 0% | 28100 | 1198.92 | 19006.84 | 145.09 | 100.09 | 1368.5 | 105.55 | 0 | 0 | 169.58 | 0 | 169.58 | 0 | 0 | 0 | 193 | 13320 | 006vqStSsTxVKseITR | FALSE
26-PC-36861 | North Fork Park Improvements - Cultural Resources Assessment | Fixed fee | In Progress | L8100 | E31062 | Ironbridge Engineering, Inc. | 2.46% | 463900 | 8632.46 | 337255.3 | 4665.82 | 1582.06 | 11411.94 | 1565.98 | 1742.12 | 0 | 2779.48 | 0 | 2779.48 | 0 | 38.5 | 0 | 0 | 12649 | 006SyxGVgFbdvyLiYG | FALSE
26-PC-36944 | Copper Flats Levee Repair - Data Recovery | Fixed fee | Final Reporting/Review | L8100 | E31057 | Keystone Planning Associates | 17.92% | 102000 | 15058.85 | 68921.4 | 1746 | 1234.38 | 18278.4 | 2581.59 | 1311.94 | 0 | 3219.55 | 0 | 3219.55 | 0 | 25.5 | 0 | 851 | 12859 | 006qcgcJkuQXGzdl4S | FALSE
26-PC-36945 | Hawk Point Fiber Route - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8100 | E31063 | Stonebridge Resources Corp. | 42.54% | 496500 | 185861.75 | 329824.95 | 38549.16 | 18715.15 | 211211.1 | 17957.69 | 10309.92 | 0 | 25349.35 | 0 | 25349.35 | 0 | 127.5 | 0 | 3948 | 15001 | 0068W93cELXZLDKt3b | TRUE
26-PC-36949 | On-Call: Sandpiper Transmission Line Cultural Resources Monitoring | Time and material | Completed | L8100 | E31055 | Granite State Rail Partners | 100% | 100300 | 0 | 70075.49 | 0 | 0 | 0 | 7682.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895 | 11524 | 006OgBigIsnO2oKVPM | FALSE
26-PC-37015 | Phase III: Hawk Point Substation Phase II Testing | Fixed fee | On Hold | L8100 | E31058 | Cardinal Environmental Consultants | 0% | 40400 | 0 | 28833.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 10678 | 006KSxnCEwyb2C33Ck | FALSE
26-PC-37016 | Aspen Ridge Built Environment Survey | Time and material | Final Billing/Invoice | L8100 | E31058 | Pioneer Renewables LLC | 100% | 26000 | 0 | 19416.8 | 0 | 0 | 0 | 2636.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 13869 | 006YKNBnfMg8GDqACn | FALSE
26-PC-37024 | Hackberry Bend Mine Expansion - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8100 | E31059 | Heartland Power Cooperative | 16.45% | 78900 | 10889.26 | 63394.72 | 1999.38 | 2158.15 | 12979.05 | 1907.94 | 95.69 | 0 | 2089.79 | 0 | 2089.79 | 0 | 1.5 | 0 | 906 | 11841 | 006FauHboMZz08jaQ6 | FALSE
26-PC-37032 | Raven Rock Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8100 | E31063 | Cardinal Port Authority | 100% | 155000 | 155000 | 112060.12 | 0 | 0 | 155000 | 26659.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10753 | 0065HNrKHyERORWAMw | FALSE
26-PC-37051 | On-Call: Sandpiper Rail Siding Section 106 Consultation | Fixed fee | Lab/Curation | L8100 | E31061 | Highland Rail Partners | 2.98% | 365900 | 7006.96 | 243543.04 | 3392.07 | 1284.93 | 10903.82 | 499.96 | 3484.11 | 0 | 3896.86 | 0 | 3896.86 | 0 | 82.25 | 0 | 0 | 12394 | 006q18ePJ3Q8NA1s6H | TRUE
26-PC-37068 | Copper Flats Highway Widening - Data Recovery | Time and material | On Hold | L8100 | E31057 | Westwind Engineering, Inc. | 0% | 419100 | 0 | 298944.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361 | 15856 | 006UiEB2LNQjxANu0L | FALSE
26-PC-37073 | Kestrel Butte Pipeline Curation | Fixed fee | In Progress | L8100 | E31057 | Cardinal Port Authority | 2.54% | 441700 | 512.97 | 346822.84 | 512.97 | 0 | 11219.18 | 1570.88 | 7254.3 | 0 | 10706.21 | 0 | 10706.21 | 0 | 89.25 | 5 | 3380 | 10753 | 006bYpbUznvy8SmyI3 | FALSE
26-PC-37089 | Rushgrass Draw GIS Mapping | Time and material | In Progress | L8100 | E31063 | Coastal Rail Partners | 0% | 28900 | 1656.25 | 19054.14 | 0 | 0 | 1656.25 | 138.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 11259 | 006tBo2ct2rg3OEdBS | FALSE
26-PC-37136 | Yarrow Point Housing Development - Section 106 Consultation | Fixed fee | In Progress | L8100 | E31057 | Blue Mesa Port Authority | 35.31% | 153700 | 51231.02 | 109797.26 | 3745.94 | 2948.25 | 54271.47 | 6435.41 | 821.1 | 0 | 3040.45 | 0 | 3040.45 | 0 | 17 | 0 | 0 | 10214 | 006cWzWVYXey8Ingri | FALSE
26-PC-37137 | Sea Oat Archaeological Testing | Fixed fee | Final Billing/Invoice | L8100 | E31063 | Brightwater Utilities | 100% | 105600 | 105600 | 78492.48 | 0 | 0 | 105600 | 13901.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927 | 10408 | 006CrXd4XCZInxfgWE | FALSE
26-PC-37138 | Granite Pass Canal Lining - Environmental Review Support | Time and material | Final Reporting/Review | L8100 | E31063 | Sunrise Telecom Holdings | 0% | 315800 | 44944.82 | 223705.16 | 6507.71 | 5275.79 | 49327.5 | 6590.46 | 2680.27 | 0 | 4382.68 | 0 | 4382.68 | 0 | 28.75 | 0 | 1618 | 15492 | 006d4Z8ajUvPhm4HFJ | FALSE
26-PC-37139 | Goldfinch Reservoir Environmental Review Support | Time and material | In Progress | L8100 | E31061 | Silverline Construction Co. | 0% | 1070500 | 91019.47 | 734587.52 | 21249.7 | 8460.93 | 113864.25 | 7614.96 | 11961.22 | 0 | 22844.78 | 0 | 22844.78 | 0 | 160 | 7.25 | 9379 | 14700 | 006wI2TRPneFbXPl75 | FALSE
26-PC-37160 | Twin Buttes Environmental Review Support | Time and material | Completed | L8100 | E31062 | Lakecrest Power Cooperative | 100% | 733800 | 0 | 451360.38 | 0 | 0 | 0 | 78922.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7049 | 13081 | 006M8T7hzOTq8HiHtZ | FALSE
26-PC-37166 | Stone Mill Airport Apron - Section 106 Consultation | Time and material | Completed | L8100 | E31057 | Keystone Rail Partners | 100% | 252900 | 0 | 181708.65 | 0 | 0 | 0 | 29017.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3217 | 12893 | 006hn4zAoTzfxlSMJ9 | FALSE
26-PC-37196 | Sea Oat Built Environment Survey | Fixed fee | In Progress | L8100 | E31058 | Redtail Builders | 0% | 26900 | 0 | 22881.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 14184 | 00674npH3FhLOJvuoD | FALSE
26-PC-37204 | On-Call: Saltgrass Housing Development Built Environment Survey | Time and material | In Progress | L8100 | E31063 | Silverline Port Authority | 0% | 201900 | 69269.36 | 145630.47 | 2708.59 | 1870.81 | 73828.25 | 6490.48 | 0 | 0 | 4558.89 | 0 | 4558.89 | 0 | 0 | 0 | 2560 | 14747 | 0063cd2gWcvMTX5XpF | FALSE
26-PC-37224 | On-Call: Ember Valley Trail Class III Survey | Time and material | Final Billing/Invoice | L8100 | E31055 | Timberline Planning Associates | 100% | 168700 | 0 | 129802.56 | 0 | 0 | 0 | 12375.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1306 | 15643 | 0065x0m1q81n6YRKK8 | FALSE
26-PC-37271 | Maple Fork Wind Farm Built Environment Survey | Time and material | In Progress | L8100 | E31063 | Mesa Verde Planning Associates | 0% | 879900 | 204281.16 | 587259.92 | 32796.27 | 29710.64 | 258254.5 | 29765.38 | 22384.54 | 0 | 53973.34 | 0 | 53973.34 | 0 | 350.75 | 0 | 0 | 13344 | 00620CtxBWEDAKo7Cn | FALSE
26-PC-37282 | Windmill Flat Harbor Dredging GIS Mapping | Fixed fee | In Progress | L8100 | E31058 | Highland Telecom Holdings | 1.56% | 48800 | 644.79 | 41616.64 | 241.92 | 164.5 | 761.28 | 112.99 | 132.25 | 0 | 116.49 | 0 | 116.49 | 0 | 2.75 | 0 | 386 | 12458 | 006YFehL953EuckgiM | FALSE
26-PC-37311 | North Fork School Campus - Paleontological Monitoring | Time and material | On Hold | L8100 | E31057 | High Plains County | 0% | 49100 | 0 | 34527.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 11980 | 0064HUZYO54hADkOtr | FALSE
26-PC-37317 | Hackberry Bend Environmental Review Support | Time and material | In Progress | L8100 | E31059 | Brightwater Rail Partners | 0% | 348700 | 10796.07 | 224737.15 | 711.4 | 428.39 | 11592.75 | 1289.83 | 316.75 | 0 | 796.68 | 0 | 796.68 | 0 | 7 | 0 | 0 | 10392 | 006ci7RK2dV4ikSWLK | FALSE
26-PC-37322 | Maple Fork Canal Lining Built Environment Survey | Time and material | In Progress | L8100 | E31059 | Lakecrest Pipeline Company | 0% | 30900 | 1737.78 | 21095.43 | 1737.78 | 0 | 5098.25 | 187.77 | 2153.64 | 0 | 3360.47 | 0 | 3360.47 | 0 | 52.25 | 0 | 436 | 13006 | 006nPDn6G2mcnYhchp | FALSE
26-PC-37329 | Stone Mill Battery Storage Built Environment Survey | Fixed fee | Final Reporting/Review | L8100 | E31055 | Cardinal Rail Partners | 63.52% | 32600 | 14930.69 | 25463.86 | 3697.62 | 2176.01 | 20707.52 | 2377.83 | 5119.8 | 0 | 5776.83 | 0 | 5776.83 | 0 | 76.5 | 4 | 360 | 10792 | 006VHNB3NkGmTbzm2B | TRUE
26-PC-37367 | Millbrook Trail - Cultural Resources Assessment | Time and material | Completed | L8100 | E31061 | Sunrise Planning Associates | 100% | 196400 | 0 | 130802.4 | 0 | 0 | 0 | 22931.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 15406 | 006PpFtelhFTC3Sxes | FALSE
26-PC-37368 | Cedar Hollow Mine Expansion - Section 106 Consultation | Fixed fee | In Progress | L8110 | E31074 | Northfield Development Group | 4.51% | 201100 | 2512.18 | 123555.84 | 2512.18 | 0 | 9069.61 | 1152.76 | 4416.14 | 0 | 6557.43 | 0 | 6557.43 | 0 | 112.75 | 0 | 2280 | 13499 | 006puoktuVKfFMnI2u | FALSE
26-PC-37428 | Ember Valley Section 106 Consultation | Fixed fee | In Progress | L8110 | E31068 | Mesa Verde Planning Associates | 29.18% | 57900 | 2174.77 | 44206.65 | 2174.77 | 0 | 16895.22 | 1741.34 | 6677.57 | 0 | 14720.45 | 0 | 14720.45 | 0 | 129.75 | 3.5 | 523 | 13344 | 0068ly7i0n7KakUf0K | TRUE
26-PC-37441 | Juniper Wash Transmission Line Built Environment Survey | Time and material | Final Billing/Invoice | L8110 | E31068 | Coastal Rail Partners | 100% | 91500 | 0 | 66758.4 | 0 | 0 | 0 | 6224.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11259 | 0064pjfPI31UGSMpYi | FALSE
26-PC-37477 | Dove Canyon Data Recovery | Fixed fee | On Hold | L8110 | E31073 | Mesa Verde Pipeline Company | 0% | 41100 | 0 | 28424.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 13320 | 006XS4dJzaJJscCY70 | FALSE
26-PC-37511 | Badger Hollow Paleontological Monitoring | Time and material | Final Billing/Invoice | L8110 | E31070 | High Plains Development Group | 100% | 202900 | 0 | 142943.05 | 0 | 0 | 0 | 16055.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343 | 12013 | 0061mDsJMiXL5fTd1G | FALSE
26-PC-37513 | Harbor View Housing Development Paleontological Monitoring | Fixed fee | Final Reporting/Review | L8110 | E31070 | Northfield Builders | 0% | 34700 | 0 | 23634.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 13460 | 006mVQ8DKbv7RCFpyT | TRUE
26-PC-37520 | Elk Meadow Wastewater Plant Maritime Remote Sensing Survey | Fixed fee | Completed | L8110 | E31070 | Stonebridge Land Company | 100% | 59200 | 59200 | 43476.48 | 0 | 0 | 59200 | 9276.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 14975 | 006cRu4jPEfDbLggx5 | FALSE
26-PC-37543 | Pebble Beach Road Historic Resources Evaluation | Fixed fee | In Progress | L8110 | E31074 | Northfield Power Cooperative | 45.24% | 330200 | 133334.89 | 218394.28 | 9652.49 | 7475.03 | 149382.48 | 17387.23 | 5609.62 | 0 | 16047.59 | 0 | 16047.59 | 0 | 64 | 6 | 2677 | 13614 | 006Az9rTm7xXZJjQNZ | FALSE
26-PC-37559 | Badger Hollow Paleontological Monitoring | Time and material | In Progress | L8110 | E31070 | Westwind Infrastructure Group | 0% | 44300 | 33494.39 | 28024.18 | 9082.11 | 9548.67 | 44300 | 6921.95 | 4604.66 | 0 | 10805.61 | 0 | 10805.61 | 0 | 60.5 | 8 | 196 | 15890 | 0062T17OIN9shQJilW | FALSE
26-PC-37671 | Harbor View Mixed-Use Development Architectural History Survey | Time and material | In Progress | L8110 | E31073 | Coastal Rail Partners | 0% | 145900 | 9234.5 | 92486.01 | 0 | 0 | 9234.5 | 1245.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11259 | 006IjqOK0AaNhDefLx | FALSE
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | Fixed fee | In Progress | L8110 | E31070 | Riverstone Resources Corp. | 78.84% | 40300 | 24174.36 | 32312.54 | 5215.3 | 2471.51 | 31772.52 | 3897.7 | 1958.75 | 0 | 7598.16 | 0 | 7598.16 | 0 | 34.75 | 0 | 428 | 14683 | 006xUhQXGGrcsBpyGX | FALSE
26-PC-37709 | Sage Flat Phase I Survey | Fixed fee | Final Reporting/Review | L8110 | E31074 | Clearwater Engineering, Inc. | 100% | 31500 | 16533.22 | 21725.55 | 16533.22 | 0 | 31500 | 4422.21 | 4794.91 | 0 | 14966.78 | 0 | 14966.78 | 0 | 78.25 | 0 | 336 | 10896 | 006RnuA4C7pfhSxY2g | TRUE
26-PC-37788 | Sumac Ridge Cultural Resources Assessment | Fixed fee | In Progress | L8110 | E31070 | High Plains Environmental Consultants | 2.05% | 1112800 | 20528.14 | 826476.56 | 2925.28 | 2636.87 | 22812.4 | 3669.14 | 1331.45 | 0 | 2284.26 | 0 | 2284.26 | 0 | 31 | 0 | 11079 | 12089 | 006s2qtTaGnLC01iqA | TRUE
26-PC-37801 | Slate Ridge Section 106 Consultation | Time and material | Completed | L8110 | E31068 | Pioneer Power Cooperative | 100% | 72500 | 0 | 48408.25 | 0 | 0 | 0 | 8274.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 13831 | 006UqEuotG5gPjchfX | FALSE
26-PC-37860 | Slate Ridge Phase II Testing | Fixed fee | Final Billing/Invoice | L8110 | E31073 | Lakecrest Development Group | 100% | 27600 | 27600 | 19836.12 | 0 | 0 | 27600 | 3401.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 12986 | 006KDigN7kJcNJEmQk | FALSE
26-PC-37924 | Raven Rock Architectural History Survey | Time and material | Completed | L8110 | E31070 | Sunrise Telecom Holdings | 100% | 33600 | 0 | 23886.24 | 0 | 0 | 0 | 4409.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 15492 | 0062177kKizILpxY0s | FALSE
26-PC-37965 | Redbud Cultural Resources Assessment | Time and material | In Progress | L8110 | E31073 | Harborlight Transit Authority | 0% | 55400 | 31520.73 | 34625 | 23555.08 | 7965.65 | 50946.25 | 4943.2 | 7634.25 | 0 | 19425.52 | 0 | 19425.52 | 0 | 153 | 0 | 590 | 11703 | 006W8TjNemKGZiy19s | FALSE
26-PC-38019 | Phase II: Timber Gap Airport Apron Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8120 | E31079 | Cardinal Port Authority | 100% | 13700 | 13700 | 9151.6 | 0 | 0 | 13700 | 916.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 10753 | 006Vg1uTINoUVh2txK | TRUE
26-PC-38025 | Granite Pass Section 106 Consultation | Time and material | In Progress | L8120 | E31079 | Northfield Power Cooperative | 0% | 92200 | 10628.35 | 64982.56 | 1961.09 | 719.48 | 12549.75 | 1081.05 | 420.12 | 0 | 1921.4 | 0 | 1921.4 | 0 | 6.75 | 2.25 | 1167 | 13614 | 006RFTCXvS1HpMcTOf | FALSE
26-PC-38124 | Lantern Bay Architectural History Survey | Fixed fee | Final Billing/Invoice | L8120 | E31079 | Lakecrest Telecom Holdings | 100% | 48700 | 48700 | 38380.47 | 0 | 0 | 48700 | 5024.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 13182 | 006ZxGdHJTEuiS4DOU | FALSE
26-PC-38153 | Harbor View Reservoir Environmental Review Support | Fixed fee | In Progress | L8120 | E31079 | Cardinal Port Authority | 56.39% | 109100 | 54072.6 | 89766.43 | 9621.81 | 3957.7 | 61521.49 | 5416.26 | 4473.87 | 0 | 7448.89 | 0 | 7448.89 | 0 | 97.75 | 0 | 0 | 10753 | 006RyVITi4PsAOm0MJ | TRUE
26-PC-38215 | Phase I: Juniper Wash Cell Tower Historic Resources Evaluation | Fixed fee | In Progress | L8120 | E31079 | Ironbridge Construction Co. | 34.74% | 42800 | 8160.18 | 37664 | 3231.8 | 2730.58 | 14868.72 | 1962.5 | 2181.78 | 0 | 6708.54 | 0 | 6708.54 | 0 | 53.25 | 0 | 1259 | 12523 | 006NFKABKpeqlfLINS | FALSE
26-PC-38264 | On-Call: Coyote Springs Battery Storage Phase II Testing | Fixed fee | Final Reporting/Review | L8120 | E31079 | Mesa Verde Pipeline Company | 46.28% | 25500 | 4418.43 | 17926.43 | 4418.43 | 0 | 11801.4 | 1103.37 | 1974.61 | 0 | 7382.97 | 0 | 7382.97 | 0 | 42.25 | 0 | 281 | 13320 | 0065ky1zUjwcmfFrOz | FALSE
26-PC-38304 | Yarrow Point Cultural Resources Assessment | Time and material | In Progress | L8120 | E31079 | Ironbridge Construction Co. | 0% | 177100 | 0 | 125191.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349 | 12523 | 006IothTjyUjepaadl | FALSE
26-PC-38315 | Task Order 21: Larkspur Bridge Replacement Paleontological Monitoring | Fixed fee | Final Reporting/Review | L8120 | E31079 | Blue Mesa Resources Corp. | 5.66% | 735000 | 41601 | 578298 | 0 | 0 | 41601 | 4710.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8557 | 10225 | 0067cViAGXcUIb6vBZ | FALSE
26-PC-38367 | Stone Mill Architectural History Survey | Time and material | In Progress | L8120 | E31079 | Northfield Water District | 0% | 416500 | 73148.86 | 276097.85 | 46705.05 | 15791.68 | 110801 | 17329.26 | 19492.83 | 0 | 37652.14 | 0 | 37652.14 | 0 | 400 | 7 | 5434 | 13685 | 006J9Q8BtTRyiiLZcr | FALSE
26-PC-38379 | Sandpiper Levee Repair Historic Resources Evaluation | Time and material | On Hold | L8120 | E31079 | Keystone Rail Partners | 0% | 230500 | 0 | 167898.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663 | 12893 | 006krZ8zmzmMlWpSdt | FALSE
26-PC-38387 | Granite Pass Section 106 Consultation | Time and material | In Progress | L8120 | E31079 | Timberline Telecom Holdings | 0% | 182500 | 89223.77 | 120358.75 | 8554.03 | 2662.06 | 92777.25 | 4202.31 | 0 | 0 | 3553.48 | 0 | 3553.48 | 0 | 0 | 0 | 1643 | 15690 | 006SpG5qbIsMo3G08T | FALSE
26-PC-38390 | Redbud Curation | Fixed fee | Final Reporting/Review | L8120 | E31079 | Granite State Infrastructure Group | 2.47% | 85100 | 436.07 | 53630.02 | 436.07 | 0 | 2101.97 | 105.93 | 1218.17 | 0 | 1665.9 | 0 | 1665.9 | 0 | 22.75 | 7.75 | 1239 | 11510 | 006q6u5kDGkB0ZNREb | TRUE
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | Time and material | In Progress | L8120 | E31079 | Mesa Verde Planning Associates | 0% | 48300 | 38154.33 | 32887.47 | 180.23 | 60.91 | 38345.25 | 4071.46 | 0 | 0 | 190.92 | 0 | 190.92 | 0 | 0 | 0 | 395 | 13344 | 0067xR7aDS3ota2LJr | FALSE
26-PC-38431 | Silver Lake Levee Repair - Archaeological Testing | Fixed fee | Final Billing/Invoice | L8120 | E31079 | Highland Infrastructure Group | 100% | 254800 | 254800 | 143528.84 | 0 | 0 | 254800 | 38623.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754 | 12316 | 0065Rf6bRFEAmDXTYu | TRUE
26-PC-38438 | Slate Ridge Fiber Route Phase I Survey | Fixed fee | In Progress | L8120 | E31079 | Summit Planning Associates | 0% | 41000 | 0 | 32762.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388 | 15198 | 006XJCRNTZUzcFDjTV | TRUE
26-PC-38459 | Task Order 21: Sea Oat Highway Widening Cultural Resources Assessment | Fixed fee | Completed | L8130 | E31092 | Prairie Wind Pipeline Company | 100% | 96700 | 96700 | 76702.44 | 0 | 0 | 96700 | 7019.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14024 | 006o47V0CbFcdxJoHN | FALSE
26-PC-38532 | Tansy Flat Wind Farm - Paleontological Monitoring | Fixed fee | On Hold | L8130 | E31095 | Sunrise County | 0% | 46400 | 0 | 33663.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552 | 15336 | 006qpO0Y5j8fobb1rH | TRUE
26-PC-38546 | Sparrow Hill Reservoir Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8130 | E31105 | Blue Mesa Pipeline Company | 100% | 103300 | 103300 | 55430.78 | 0 | 0 | 103300 | 5939.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10171 | 006QF4QYnLuVb47NMq | FALSE
26-PC-38550 | On-Call: Sage Flat School Campus Class III Survey | Fixed fee | Completed | L8130 | E31105 | Ridgeline Water District | 100% | 385200 | 385200 | 289636.74 | 0 | 0 | 385200 | 21244.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4183 | 14577 | 006mt8t47AsoCzBuq0 | TRUE
26-PC-38571 | Stone Mill Transmission Line GIS Mapping | Fixed fee | Completed | L8130 | E31105 | Sunrise Planning Associates | 100% | 593600 | 593600 | 431665.92 | 0 | 0 | 593600 | 67706.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6438 | 15406 | 006BDawe6rCx1E6ZjX | FALSE
26-PC-38573 | Cedar Hollow School Campus - Class III Survey | Fixed fee | In Progress | L8130 | E31095 | Mesa Verde Planning Associates | 1.11% | 100100 | 405.7 | 74784.71 | 405.7 | 0 | 1111.11 | 102.49 | 730.75 | 0 | 705.41 | 0 | 705.41 | 0 | 10 | 0.25 | 706 | 13344 | 006qZJ8MNu9kgnKt2W | FALSE
26-PC-38624 | Juniper Wash Built Environment Survey | Fixed fee | Cost Tracking on Closed Project | L8130 | E31088 | Silverline Construction Co. | 100% | 77900 | 77900 | 56578.77 | 0 | 0 | 77900 | 4854.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 963 | 14700 | 006WMUJ8GI92Zveqjg | FALSE
26-PC-38647 | Meadowlark Cultural Resources Assessment | Time and material | In Progress | L8130 | E31088 | Northfield Telecom Holdings | 0% | 793800 | 232307.63 | 517795.74 | 49027.71 | 38265.23 | 281862.75 | 20944.8 | 20613.05 | 0 | 49555.12 | 0 | 49555.12 | 0 | 377 | 9.5 | 0 | 13631 | 006z26KfqLx4POii5s | FALSE
26-PC-38675 | On-Call: Lone Pine School Campus Data Recovery | Fixed fee | Final Reporting/Review | L8130 | E31105 | Cardinal Port Authority | 29.16% | 289700 | 82918.83 | 228167.72 | 4580.17 | 2858.24 | 84476.52 | 10511.13 | 0 | 0 | 1557.69 | 0 | 1557.69 | 0 | 0 | 0 | 3409 | 10753 | 006bBwkGjP498ETFSk | FALSE
26-PC-38691 | Elk Meadow Phase I Survey | Time and material | On Hold | L8130 | E31107 | Lakecrest Telecom Holdings | 0% | 1927200 | 0 | 1370431.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32342 | 13182 | 006vCmKMS01ITlCBr9 | FALSE
26-PC-38709 | Timber Gap Airport Apron Phase I Survey | Fixed fee | In Progress | L8130 | E31088 | Prairie Wind Planning Associates | 48.51% | 14100 | 6778.98 | 11415.36 | 44.3 | 23.17 | 6839.91 | 1196.16 | 34.48 | 0 | 60.93 | 0 | 60.93 | 0 | 0.5 | 0 | 243 | 14041 | 006NUGh81Ir2hezagv | FALSE
26-PC-38719 | Willow Springs Housing Development - Environmental Review Support | Fixed fee | In Progress | L8130 | E31092 | Prairie Wind Utilities | 0.52% | 298600 | 1508.75 | 193522.66 | 38.39 | 32.53 | 1552.72 | 123.81 | 0 | 0 | 43.97 | 0 | 43.97 | 0 | 0 | 0 | 2806 | 14159 | 006pdiTBfC2iYSRZbb | FALSE
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | Time and material | In Progress | L8130 | E31107 | Ironbridge Engineering, Inc. | 0% | 97700 | 80334.37 | 60828.02 | 25348.2 | 6667.43 | 97700 | 6821.13 | 10037.22 | 0 | 17365.63 | 0 | 17365.63 | 0 | 197.5 | 21 | 0 | 12649 | 006FYe2RmtTY3YS4Fp | FALSE
26-PC-38769 | On-Call: Elk Meadow Wastewater Plant Paleontological Monitoring | Time and material | Final Billing/Invoice | L8130 | E31095 | Stonebridge Utilities | 100% | 40500 | 0 | 25733.7 | 0 | 0 | 0 | 3872.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463 | 15036 | 006dCR7oT6uijMz4ra | FALSE
26-PC-38844 | Juniper Wash Cell Tower Phase II Testing | Fixed fee | Final Billing/Invoice | L8130 | E31105 | Harborlight Water District | 100% | 319700 | 319700 | 236322.24 | 0 | 0 | 319700 | 22734.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3530 | 11739 | 0064yPnQ2ho7xcsasl | FALSE
26-PC-38856 | Task Order 6: Maple Fork Trail Section 106 Consultation | Fixed fee | Completed | L8130 | E31107 | Coastal Planning Associates | 100% | 137600 | 137600 | 94200.96 | 0 | 0 | 137600 | 9674.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493 | 11250 | 0065ZRN3g3hOCF5zx1 | FALSE
26-PC-38880 | Wildrye Trail - Archaeological Testing | Fixed fee | Completed | L8130 | E31097 | Northfield Power Cooperative | 100% | 141200 | 141200 | 118636.24 | 0 | 0 | 141200 | 5622.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1615 | 13614 | 006neOqaVtB0DhA110 | FALSE
26-PC-38898 | Redbud Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | L8130 | E31088 | Lakecrest Rail Partners | 24.14% | 150100 | 19826.4 | 87478.28 | 12946.57 | 6879.83 | 36234.14 | 2576.37 | 6457.22 | 0 | 16407.74 | 0 | 16407.74 | 0 | 132.75 | 10 | 1519 | 13111 | 006TWrLyTqbmDFiNqd | FALSE
26-PC-38916 | Sparrow Hill Cultural Resources Assessment | Fixed fee | Final Billing/Invoice | L8130 | E31107 | Summit County | 100% | 54500 | 54500 | 42150.3 | 0 | 0 | 54500 | 4602.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632 | 15070 | 0062xlekuUkSbq72lm | TRUE
26-PC-38924 | Wildrye Harbor Dredging - Architectural History Survey | Time and material | In Progress | L8130 | E31110 | Northfield Builders | 0% | 117200 | 57207.78 | 83798 | 3979.35 | 3031 | 64940 | 3945.78 | 2572.14 | 0 | 7732.22 | 0 | 7732.22 | 0 | 65.75 | 0 | 1279 | 13460 | 006I1ei9iEmGOij6RA | FALSE
26-PC-38943 | Task Order 34: Fern Valley Wastewater Plant Archaeological Testing | Fixed fee | In Progress | L8130 | E31095 | Blue Mesa Infrastructure Group | 85.44% | 129100 | 95459.09 | 80272.12 | 16699.92 | 16485.78 | 110303.04 | 5280.96 | 9775.19 | 0 | 14843.95 | 0 | 14843.95 | 0 | 175 | 15.5 | 1494 | 10139 | 006314WqbgB8M2FUb9 | FALSE
26-PC-38966 | Task Order 12: Bramble Creek Battery Storage Cultural Resources Monitoring | Fixed fee | In Progress | L8130 | E31088 | Ridgeline Water District | 4.45% | 269400 | 7999.35 | 193052.04 | 3342.06 | 2540.8 | 11988.3 | 920.19 | 3271.28 | 0 | 3988.95 | 0 | 3988.95 | 0 | 78.75 | 0 | 2573 | 14577 | 006trxioLbwNjfdKYj | TRUE
26-PC-38993 | Willow Springs Airport Apron - Section 106 Consultation | Time and material | In Progress | L8130 | E31097 | Pioneer Engineering, Inc. | 0% | 201400 | 50428.33 | 131514.2 | 8658.52 | 2995.03 | 57707.5 | 3309.71 | 4470.35 | 0 | 7279.17 | 0 | 7279.17 | 0 | 59.75 | 5.75 | 1544 | 13790 | 006X3MQFFL5EkMyAuU | FALSE
26-PC-39024 | On-Call: Goldfinch Water Main Phase I Survey | Time and material | In Progress | L8130 | E31095 | Lakecrest Renewables LLC | 0% | 211800 | 1334.82 | 149416.47 | 1334.82 | 0 | 7879 | 932.46 | 4969.18 | 0 | 6544.18 | 0 | 6544.18 | 0 | 66 | 11 | 1801 | 13164 | 006QiN1X8oQfqDh612 | FALSE
26-PC-39043 | Twin Buttes Reservoir - Archaeological Testing | Fixed fee | In Progress | L8130 | E31088 | Prairie Wind Planning Associates | 16.02% | 123200 | 14790.45 | 96884.48 | 4363.38 | 4502.73 | 19736.64 | 1039.59 | 3475.55 | 0 | 4946.19 | 0 | 4946.19 | 0 | 77.5 | 0 | 2025 | 14041 | 006ukHi8Hg6iuWCpsq | TRUE
26-PC-39051 | Quail Run Fiber Route - Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8130 | E31097 | Stonebridge Builders | 100% | 510900 | 510900 | 377963.82 | 0 | 0 | 510900 | 39218.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5195 | 14860 | 0061gQIQA4QxzL6A7v | FALSE
26-PC-39143 | Meadowlark Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | In Progress | L8130 | E31088 | Summit Planning Associates | 1.08% | 500400 | 3639.56 | 366543 | 2173.17 | 729.24 | 5404.32 | 602.7 | 517.44 | 0 | 1764.76 | 0 | 1764.76 | 0 | 7.75 | 0 | 3404 | 15198 | 006ntNGVsK68NsPJRm | FALSE
26-PC-39165 | Pebble Beach Road Phase I Survey | Fixed fee | Final Reporting/Review | L8130 | E31107 | High Plains Engineering, Inc. | 92.76% | 94300 | 76455.85 | 63218.72 | 13169.33 | 11749.85 | 87472.68 | 12608.3 | 4277.21 | 0 | 11016.83 | 0 | 11016.83 | 0 | 50 | 3.25 | 395 | 12054 | 006sRiX2fc4GH74ZrN | TRUE
26-PC-39230 | Maple Fork Cultural Resources Assessment | Time and material | In Progress | L8130 | E31088 | Evergreen Development Group | 0% | 575400 | 42537.62 | 432643.26 | 39692.87 | 2844.75 | 64571.5 | 4482.16 | 12158.35 | 0 | 22033.88 | 0 | 22033.88 | 0 | 236.5 | 3.5 | 3831 | 11371 | 006OGM8BDzRQbi2xD2 | FALSE
26-PC-39232 | Plover Cove Canal Lining Archaeological Testing | Fixed fee | Final Billing/Invoice | L8130 | E31107 | Cardinal Port Authority | 100% | 11000 | 11000 | 8129 | 0 | 0 | 11000 | 696.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 10753 | 0067WXJ73rVoMCIWNw | FALSE
26-PC-39249 | On-Call: Millbrook Levee Repair Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | L8130 | E31107 | Cardinal Rail Partners | 0% | 126200 | 0 | 95785.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925 | 10792 | 006FDUc5MsuGwSQCWd | FALSE
26-PC-39264 | Hackberry Bend Housing Development - Architectural History Survey | Fixed fee | Final Billing/Invoice | L8130 | E31088 | Coastal Land Company | 100% | 37100 | 37100 | 30010.19 | 0 | 0 | 37100 | 6509.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 11195 | 006jTcLYVjPEHcnKHY | FALSE
26-PC-39277 | Larkspur Battery Storage Archaeological Testing | Fixed fee | Final Reporting/Review | L8130 | E31088 | Sunrise Planning Associates | 0.04% | 520900 | 42.86 | 341710.4 | 42.86 | 0 | 208.36 | 11.93 | 112.37 | 0 | 165.5 | 0 | 165.5 | 0 | 1.75 | 0 | 6464 | 15406 | 0065ULjh7pyWeVHIl5 | TRUE
26-PC-39303 | Maple Fork Wind Farm Historic Resources Evaluation | Fixed fee | Transferred Entity | L8130 | E31092 | Ironbridge Port Authority | 23.03% | 41200 | 5457.06 | 35687.44 | 5457.06 | 0 | 9488.36 | 1512.2 | 1063.38 | 0 | 4031.3 | 0 | 4031.3 | 0 | 15.5 | 0 | 496 | 12704 | 006FsO6RjmpiLFozrF | FALSE
26-PC-39335 | Windmill Flat Phase II Testing | Time and material | Completed | L8130 | E31092 | Stonebridge Builders | 100% | 78700 | 0 | 52791.96 | 0 | 0 | 0 | 5246.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722 | 14860 | 006YR4psnTIBOOGYQP | FALSE
26-PC-39372 | Tamarack Environmental Review Support | Time and material | Lab/Curation | L8130 | E31110 | Highland Telecom Holdings | 0% | 12300 | 6.19 | 7953.18 | 6.19 | 0 | 25.25 | 1.35 | 13.15 | 0 | 19.06 | 0 | 19.06 | 0 | 0.25 | 0 | 87 | 12458 | 006Z9UQIQuUIj9G9Xw | FALSE
26-PC-39390 | Juniper Wash Fiber Route Phase I Survey | Fixed fee | Final Reporting/Review | L8130 | E31092 | Summit Renewables LLC | 14.27% | 59600 | 7212.74 | 37810.24 | 515.38 | 689.59 | 8504.92 | 1095.42 | 453.54 | 0 | 1292.18 | 0 | 1292.18 | 0 | 8 | 0.75 | 530 | 15274 | 006qgGIj3VRPCRLnz6 | FALSE
26-PC-39408 | Meadowlark Class III Survey | Fixed fee | Final Billing/Invoice | L8130 | E31092 | Westwind Energy Partners | 100% | 103000 | 103000 | 73854.05 | 0 | 0 | 103000 | 9813.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 15833 | 006uO1rPJhF8QWoN6w | FALSE
26-PC-39446 | On-Call: Tamarack Bridge Replacement Architectural History Survey | Fixed fee | Transferred Entity | L8130 | E31105 | Ridgeline Water District | 27.97% | 131200 | 14737.81 | 102152.32 | 12639.29 | 2098.52 | 36696.64 | 3371.07 | 6471.61 | 0 | 21958.83 | 0 | 21958.83 | 0 | 101.25 | 16.25 | 0 | 14577 | 006wysWMKe3ilrGd1N | FALSE
26-PC-39534 | Aspen Ridge Park Improvements Maritime Remote Sensing Survey | Fixed fee | On Hold | L8130 | E31095 | Redtail Infrastructure Group | 0% | 551900 | 0 | 348248.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5966 | 14267 | 006JUWbdJzXdeB9vHZ | FALSE
26-PC-39537 | Badger Hollow Cultural Resources Monitoring | Fixed fee | In Progress | L8130 | E31107 | Prairie Wind Transit Authority | 8.33% | 82700 | 4164.55 | 63951.91 | 2062.55 | 1281.56 | 6888.91 | 410.21 | 974.11 | 0 | 2724.36 | 0 | 2724.36 | 0 | 23 | 0 | 868 | 14127 | 006Km01ZX3UX96S2c2 | TRUE
26-PC-39565 | On-Call: Aspen Ridge Battery Storage Maritime Remote Sensing Survey | Time and material | In Progress | L8130 | E31097 | Brightwater Rail Partners | 0% | 97600 | 27241.61 | 60541.28 | 5012.45 | 2621.11 | 32668 | 1471.42 | 3100.77 | 0 | 5426.39 | 0 | 5426.39 | 0 | 64.25 | 7.5 | 904 | 10392 | 006bEhvC2LR2MsMkS9 | FALSE
26-PC-39587 | Ember Valley Curation | Time and material | Cost Tracking on Closed Project | L8130 | E31092 | Sunrise County | 0% | 288900 | 0 | 211965.93 | 0 | 0 | 0 | 39915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2895 | 15336 | 00615JAzrrEfrMw14f | FALSE
26-PC-39595 | Plover Cove Archaeological Testing | Fixed fee | Completed | L8130 | E31092 | Blue Mesa Port Authority | 100% | 66700 | 66700 | 48564.27 | 0 | 0 | 66700 | 5739.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 10214 | 0066RRbsEsDUwicO41 | FALSE
26-PC-39619 | Hackberry Bend Transmission Line - Paleontological Monitoring | Fixed fee | In Progress | L8130 | E31097 | Ironbridge Telecom Holdings | 3.33% | 79000 | 609.56 | 54115 | 609.56 | 0 | 2630.7 | 246.82 | 1554.76 | 0 | 2021.14 | 0 | 2021.14 | 0 | 32 | 0 | 521 | 12740 | 006UhtOUDTcPtAPhvo | FALSE
26-PC-39638 | On-Call: North Fork Transmission Line Historic Resources Evaluation | Time and material | In Progress | L8130 | E31110 | Timberline Planning Associates | 0% | 131700 | 20382.48 | 85748.9 | 14191.99 | 5406.56 | 34411.5 | 4914.1 | 6143.58 | 0 | 14029.02 | 0 | 14029.02 | 0 | 64.5 | 0 | 763 | 15643 | 006IumgDJcmz4H8sxX | FALSE
26-PC-39644 | Ember Valley Reservoir - Section 106 Consultation | Time and material | Completed | L8130 | E31097 | Harborlight Port Authority | 100% | 100300 | 0 | 69527.96 | 0 | 0 | 0 | 7826.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221 | 11691 | 006JSiq4Wow0NZI6A8 | FALSE
26-PC-39671 | Phase I: Pebble Beach Road Solar Class III Survey | Fixed fee | Completed | L8130 | E31107 | Summit Planning Associates | 100% | 62500 | 62500 | 46625 | 0 | 0 | 62500 | 12789.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15198 | 006pMyq4kqoUbhwamw | FALSE
26-PC-39699 | Thistle Down Reservoir - Data Recovery | Fixed fee | In Progress | L8130 | E31105 | Granite State Development Group | 11.26% | 88200 | 5211.57 | 62269.2 | 4726.08 | 485.49 | 9931.32 | 567.98 | 2235.37 | 0 | 4719.75 | 0 | 4719.75 | 0 | 36.5 | 14.25 | 1628 | 11469 | 006QX0Ktx3t7VQyBLm | TRUE
26-PC-39711 | Sandpiper Canal Lining Phase II Testing | Fixed fee | Completed | L8130 | E31107 | Highland Infrastructure Group | 100% | 69600 | 69600 | 59125.2 | 0 | 0 | 69600 | 9064.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1264 | 12316 | 006ARWzPnEEEc5ZX2g | TRUE
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Fixed fee | Cost Tracking on Closed Project | L8130 | E31107 | Pioneer Transit Authority | 100% | 115900 | 115900 | 86530.94 | 0 | 0 | 115900 | 8374.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149 | 13885 | 006wFh7m1GnzbWF9ZY | FALSE
26-PC-39730 | Coyote Springs Water Main - Phase I Survey | Fixed fee | Completed | L8130 | E31092 | Sunrise County | 100% | 25600 | 25600 | 18618.88 | 0 | 0 | 25600 | 1830.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 15336 | 006WCtU3N5GHsJKeVP | TRUE
26-PC-39744 | Phase III: Sumac Ridge Wastewater Plant Archaeological Testing | Time and material | In Progress | L8130 | E31088 | Westwind County | 0% | 351100 | 16051.84 | 225441.31 | 9022.34 | 4811.48 | 25000.75 | 871.94 | 3895.61 | 0 | 8948.91 | 0 | 8948.91 | 0 | 85.75 | 0.5 | 4331 | 15753 | 006KvmaOdxqOOScB6L | FALSE
26-PC-39778 | Thistle Down Battery Storage - Architectural History Survey | Time and material | In Progress | L8130 | E31095 | Granite State Rail Partners | 0% | 35700 | 2429.52 | 26613.7 | 344.78 | 302.43 | 2505.25 | 135.21 | 40.51 | 0 | 75.73 | 0 | 75.73 | 0 | 0.75 | 0 | 515 | 11524 | 006tXAmWPJiq2rafW3 | FALSE
26-PC-39780 | Phase I: Rushgrass Draw Mine Expansion Maritime Remote Sensing Survey | Time and material | In Progress | L8130 | E31110 | Canyon Utilities | 0% | 113500 | 4440.96 | 76714.65 | 4440.96 | 0 | 9446.75 | 415.04 | 2442.03 | 0 | 5005.79 | 0 | 5005.79 | 0 | 54 | 0 | 1009 | 10611 | 0069ZRk1SFbZHARGke | FALSE
26-PC-39880 | Larkspur Section 106 Consultation | Time and material | In Progress | L8130 | E31105 | Stonebridge Utilities | 0% | 100200 | 16949.07 | 73772.32 | 14454.34 | 2494.73 | 37315.75 | 5935.17 | 6215.91 | 0 | 20366.68 | 0 | 20366.68 | 0 | 124.75 | 6.75 | 0 | 15036 | 006jj799gqN0d1ZKa3 | FALSE
26-PC-39913 | On-Call: Bramble Creek Rail Siding Cultural Resources Assessment | Fixed fee | On Hold | L8130 | E31092 | Highland Infrastructure Group | 0% | 119400 | 0 | 78314.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 12316 | 006jD6IbXYxEkNRQ6B | FALSE
26-PC-39971 | Pebble Beach Road Environmental Review Support | Time and material | Final Reporting/Review | L8130 | E31095 | Redtail Infrastructure Group | 0% | 114600 | 83845.05 | 79406.34 | 12972.68 | 13654.16 | 102477.5 | 7093.72 | 8775.03 | 0 | 18632.45 | 0 | 18632.45 | 0 | 135 | 12.5 | 780 | 14267 | 006EXkMfZl4awLxiY0 | FALSE
26-PC-39990 | Falcon Mesa Solar - Phase I Survey | Time and material | In Progress | L8130 | E31107 | Westwind County | 0% | 15600 | 363.28 | 10693.8 | 197.36 | 160.29 | 710.5 | 53.88 | 154.47 | 0 | 347.22 | 0 | 347.22 | 0 | 3.25 | 0 | 246 | 15753 | 006oLFqkcmQBnLzS5p | FALSE
26-PC-40009 | Oak Terrace Harbor Dredging Curation | Fixed fee | In Progress | L8130 | E31110 | Coastal Construction Co. | 36.46% | 63600 | 20141.14 | 43349.76 | 4171.76 | 2020.82 | 23188.56 | 1153.76 | 929.56 | 0 | 3047.42 | 0 | 3047.42 | 0 | 20.75 | 0 | 663 | 11092 | 006ikKYCigfDrNgFAT | FALSE
26-PC-40038 | Badger Hollow Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8130 | E31097 | Northfield Power Cooperative | 100% | 348700 | 348700 | 275403.26 | 0 | 0 | 348700 | 46576.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13614 | 006vHwZl8k6CEnVukv | FALSE
26-PC-40055 | Twin Buttes Pipeline Architectural History Survey | Time and material | In Progress | L8130 | E31110 | Redtail Water District | 0% | 22000 | 2605.35 | 14259.29 | 2605.35 | 0 | 8813.5 | 500.91 | 4409.96 | 0 | 6208.15 | 0 | 6208.15 | 0 | 79.25 | 0 | 219 | 14359 | 006rP5PWdJVEWBZXbU | FALSE
26-PC-40092 | Eagle Bend Environmental Review Support | Fixed fee | In Progress | L8140 | E31128 | Prairie Wind Transit Authority | 0.42% | 3672000 | 7215.21 | 2369908.8 | 7215.21 | 0 | 15422.4 | 884.26 | 3689.61 | 0 | 8207.19 | 0 | 8207.19 | 0 | 96.25 | 0 | 48889 | 14127 | 006FvQiKiOaRsnNWuy | FALSE
26-PC-40108 | Hackberry Bend Trail - Phase II Testing | Fixed fee | Final Billing/Invoice | L8140 | E31122 | Heartland Transit Authority | 100% | 138800 | 138800 | 89484.36 | 0 | 0 | 138800 | 13232.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912 | 11878 | 006zCt24WLvubRSbEW | FALSE
26-PC-40128 | Goldfinch Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | L8140 | E31127 | Harborlight County | 100% | 67100 | 67100 | 49016.55 | 0 | 0 | 67100 | 8759.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 | 11648 | 006oqXlnLAP5DfPUf4 | TRUE
26-PC-40176 | On-Call: Twin Buttes Harbor Dredging Phase I Survey | Time and material | Final Reporting/Review | L8140 | E31121 | Summit Engineering, Inc. | 0% | 143600 | 33027.78 | 93138.96 | 8154.56 | 3787.92 | 39852 | 1568.67 | 3066.21 | 0 | 6824.22 | 0 | 6824.22 | 0 | 78.5 | 0 | 1672 | 15125 | 006Oo4f6R0s3l5UhUn | FALSE
26-PC-40190 | Pebble Beach Road Trail - Section 106 Consultation | Fixed fee | On Hold | L8140 | E31122 | Mesa Verde Land Company | 0% | 113900 | 0 | 91485.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167 | 13275 | 006g8IEMloWtWYHlUH | FALSE
26-PC-40229 | Pine Hollow School Campus - Data Recovery | Time and material | Final Billing/Invoice | L8140 | E31128 | Evergreen Development Group | 100% | 370800 | 0 | 229525.2 | 0 | 0 | 0 | 30733.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4070 | 11371 | 006o0aPpTqdtGtrYtH | FALSE
26-PC-40289 | Windmill Flat Park Improvements Environmental Review Support | Fixed fee | Final Billing/Invoice | L8140 | E31128 | Keystone Rail Partners | 100% | 135800 | 135800 | 109481.96 | 0 | 0 | 135800 | 8540.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12893 | 00646Icp39n5tnBRyB | FALSE
26-PC-40296 | Twin Buttes Class III Survey | Fixed fee | In Progress | L8140 | E31127 | Stonebridge Resources Corp. | 17.01% | 6400 | 1006.05 | 4648.32 | 84.3 | 36.02 | 1088.64 | 126.53 | 0 | 0 | 82.59 | 0 | 82.59 | 0 | 0 | 0 | 28 | 15001 | 006dzEOTNriBADEBJv | TRUE
26-PC-40304 | Willow Springs Fiber Route Archaeological Testing | Fixed fee | In Progress | L8140 | E31127 | Ridgeline Renewables LLC | 13.62% | 132900 | 15168.63 | 101283.22 | 2411.19 | 2788.89 | 18100.98 | 1875.54 | 1534.51 | 0 | 2932.35 | 0 | 2932.35 | 0 | 34.5 | 0 | 2649 | 14493 | 006xurGYg7pyn1K1Sb | FALSE
26-PC-40329 | Yarrow Point Maritime Remote Sensing Survey | Fixed fee | Final Billing/Invoice | L8140 | E31127 | Blue Mesa Resources Corp. | 100% | 416100 | 416100 | 281325.21 | 0 | 0 | 416100 | 74607.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652 | 10225 | 006BUoExGGiX5khlPv | FALSE
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | Fixed fee | In Progress | L8140 | E31127 | Stonebridge Engineering, Inc. | 100% | 96900 | 90582.43 | 68401.71 | 6308.58 | 3662.38 | 96900 | 5183.86 | 2320.07 | 0 | 6317.57 | 0 | 6317.57 | 0 | 48.75 | 0 | 731 | 14937 | 006Fv8KTeKugziO1wb | TRUE
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Fixed fee | Final Reporting/Review | L8140 | E31121 | Ironbridge Engineering, Inc. | 100% | 19200 | 16759.26 | 14098.56 | 3547.79 | 1666.73 | 19200 | 3753.56 | 1203.62 | 0 | 2440.74 | 0 | 2440.74 | 0 | 30.75 | 1.25 | 0 | 12649 | 006lsv60hRd9hpn2PV | TRUE
26-PC-40361 | Sea Oat Cultural Resources Assessment | Fixed fee | In Progress | L8140 | E31127 | Sunrise Telecom Holdings | 75.43% | 156300 | 95830.05 | 102829.77 | 20868.19 | 15812.44 | 117897.09 | 7058.46 | 9001.46 | 0 | 22067.04 | 0 | 22067.04 | 0 | 148.5 | 1.75 | 950 | 15492 | 006LK3QJNBN8cv0KoY | TRUE
26-PC-40384 | Maple Fork Solar - Maritime Remote Sensing Survey | Time and material | In Progress | L8140 | E31127 | Sunrise County | 0% | 102900 | 47047.68 | 62220.33 | 4271.99 | 1775.14 | 49138.25 | 2731.72 | 1601.15 | 0 | 2090.57 | 0 | 2090.57 | 0 | 40.75 | 0 | 986 | 15336 | 006HpVMSuw7VlH8pDm | FALSE
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Fixed fee | Final Reporting/Review | L8140 | E31127 | High Plains Environmental Consultants | 100% | 5900 | 5708.22 | 4379.73 | 160.49 | 127.04 | 5900 | 1596.1 | 110.91 | 0 | 191.78 | 0 | 191.78 | 0 | 3 | 0 | 70 | 12089 | 006YXvwziZk9HlAXpL | TRUE
26-PC-40443 | Pine Hollow Wastewater Plant - Built Environment Survey | Fixed fee | In Progress | L8140 | E31127 | Coastal Utilities | 15.38% | 424500 | 27486.99 | 299781.9 | 27486.99 | 0 | 65288.1 | 5810.84 | 19223.41 | 0 | 37801.11 | 0 | 37801.11 | 0 | 302.5 | 5.25 | 3895 | 11319 | 006blf5j8JuKpVBI5B | FALSE
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | Fixed fee | In Progress | L8140 | E31127 | Northfield Water District | 100% | 7500 | 7376.17 | 5493 | 34.82 | 15.25 | 7500 | 633.81 | 0 | 0 | 123.83 | 0 | 123.83 | 0 | 0 | 0 | 70 | 13685 | 006f0kdWMEPCfmrs8G | FALSE
26-PC-40590 | Wildrye Highway Widening - Environmental Review Support | Fixed fee | Final Reporting/Review | L8140 | E31128 | Ridgeline Water District | 15.31% | 1002000 | 121067.73 | 809716.2 | 45485.72 | 30822.52 | 153406.2 | 11650.55 | 22904.23 | 0 | 32338.47 | 0 | 32338.47 | 0 | 444.75 | 0 | 9548 | 14577 | 006cHwztRh4sYCNij7 | TRUE
26-PC-40605 | Willow Springs Mixed-Use Development Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | L8140 | E31121 | Timberline Planning Associates | 0% | 138400 | 0 | 95191.52 | 0 | 0 | 0 | 10777.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053 | 15643 | 0063UFRkqvJ2oEbRLn | FALSE
26-PC-40607 | Task Order 35: Cedar Hollow Housing Development Archaeological Testing | Fixed fee | On Hold | L8140 | E31122 | Stonebridge Engineering, Inc. | 0% | 75100 | 0 | 47821.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738 | 14937 | 006JapY0hQLsklmLVM | FALSE
26-PC-40640 | Cedar Hollow Mine Expansion Cultural Resources Monitoring | Time and material | Final Billing/Invoice | L8140 | E31128 | Granite State Development Group | 100% | 12900 | 0 | 9127.87 | 0 | 0 | 0 | 1254.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 11469 | 0063lG4wF6Ey42yZMl | FALSE
26-PC-40690 | Pine Hollow Wastewater Plant - Paleontological Monitoring | Time and material | In Progress | L8150 | E31137 | Canyon Energy Partners | 0% | 252500 | 100069.43 | 171094 | 8765.96 | 4436.57 | 101574 | 8664.24 | 0 | 0 | 1504.57 | 0 | 1504.57 | 0 | 0 | 0 | 2923 | 10492 | 0065j7x4ClHxnzVRgu | FALSE
26-PC-40716 | Elk Meadow Architectural History Survey | Time and material | Final Billing/Invoice | L8150 | E31151 | Coastal Development Group | 100% | 6700 | 0 | 4710.77 | 0 | 0 | 0 | 895.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 11160 | 006bwhf8eIgKTYXeRA | FALSE
26-PC-40729 | On-Call: Dove Canyon Cell Tower Section 106 Consultation | Fixed fee | In Progress | L8150 | E31151 | Canyon Rail Partners | 8.43% | 92500 | 4889.9 | 58081.13 | 2895.56 | 1994.34 | 7797.75 | 1042.91 | 2285.76 | 0 | 2907.85 | 0 | 2907.85 | 0 | 46.75 | 0 | 0 | 10579 | 006peYyOa3xmtA5dVq | TRUE
26-PC-40750 | On-Call: Willow Springs Highway Widening Historic Resources Evaluation | Time and material | In Progress | L8150 | E31141 | Sunrise Rail Partners | 0% | 494600 | 9568.26 | 310521.94 | 9568.26 | 0 | 24206.25 | 3311.6 | 5609.25 | 0 | 14637.99 | 0 | 14637.99 | 0 | 135 | 0 | 7260 | 15467 | 006j9HvNuQz84ZjOsi | FALSE
26-PC-40760 | Foxglove Canal Lining - Archaeological Testing | Fixed fee | Final Reporting/Review | L8150 | E31150 | Canyon Utilities | 28.47% | 77500 | 19509.79 | 63893.46 | 2466.02 | 1695.08 | 22064.25 | 1855.47 | 1564.48 | 0 | 2554.46 | 0 | 2554.46 | 0 | 32 | 0 | 0 | 10611 | 006dSkQEanDPNQQesS | TRUE
26-PC-40805 | Willow Springs Battery Storage - Section 106 Consultation | Time and material | Completed | L8150 | E31150 | Lakecrest Telecom Holdings | 100% | 15100 | 0 | 11494.12 | 0 | 0 | 0 | 2153.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 13182 | 006FSJM4BTPVHGDeAD | FALSE
26-PC-40860 | Fern Valley Solar Data Recovery | Fixed fee | In Progress | L8150 | E31141 | Prairie Wind Pipeline Company | 22.88% | 181300 | 31148.81 | 145148.78 | 8408.99 | 7392.51 | 41481.44 | 2722.75 | 4238.72 | 0 | 10332.63 | 0 | 10332.63 | 0 | 89.5 | 4.25 | 0 | 14024 | 006vxpvxq3TzPRYCoi | FALSE
26-PC-40902 | Badger Hollow Solar Environmental Review Support | Fixed fee | Final Billing/Invoice | L8150 | E31150 | Granite State Rail Partners | 100% | 86700 | 86700 | 65666.58 | 0 | 0 | 86700 | 5431.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 11524 | 006n16vEIEltLlo8Qy | FALSE
26-PC-40966 | Harbor View Trail - GIS Mapping | Fixed fee | Final Reporting/Review | L8150 | E31137 | Ironbridge Construction Co. | 23.65% | 225100 | 41568.68 | 146315 | 6353.72 | 5212.68 | 53236.15 | 3184.18 | 5508.4 | 0 | 11667.47 | 0 | 11667.47 | 0 | 124.5 | 0 | 2386 | 12523 | 006AdNy8zvgHiPvu2C | FALSE
26-PC-40983 | Falcon Mesa Data Recovery | Fixed fee | Final Reporting/Review | L8150 | E31150 | Keystone Energy Partners | 78.04% | 7200 | 4989.63 | 6217.91 | 924.19 | 518.84 | 5618.88 | 485.27 | 302.06 | 0 | 629.25 | 0 | 629.25 | 0 | 5.25 | 0 | 42 | 12804 | 006p1HPaGjZ8lsYHOr | FALSE
26-PC-41005 | Juniper Wash Architectural History Survey | Time and material | In Progress | L8150 | E31137 | Brightwater Planning Associates | 0% | 60000 | 2895.23 | 38934 | 2149.63 | 745.6 | 4026 | 343.83 | 195.21 | 0 | 1130.77 | 0 | 1130.77 | 0 | 2.75 | 1.75 | 665 | 10306 | 006ccTfE3lSGGI60HJ | FALSE
26-PC-41046 | Wren Hollow Airport Apron - Data Recovery | Fixed fee | Final Billing/Invoice | L8150 | E31137 | Mesa Verde Planning Associates | 100% | 60200 | 60200 | 47644.16 | 0 | 0 | 60200 | 4955.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772 | 13344 | 006Wn98K6DIASRlAKF | TRUE
26-PC-41048 | Task Order 33: Granite Pass Battery Storage Phase I Survey | Time and material | In Progress | L8150 | E31150 | Coastal Planning Associates | 0% | 458200 | 82360.74 | 315149.96 | 20666.04 | 26901.94 | 126518.5 | 14631.76 | 20071.62 | 0 | 44157.76 | 0 | 44157.76 | 0 | 351.5 | 18.25 | 3299 | 11250 | 006jTB3WwxtURIHP39 | FALSE
26-PC-41130 | Harbor View Highway Widening Data Recovery | Time and material | Cost Tracking on Closed Project | L8150 | E31141 | Lakecrest Construction Co. | 0% | 290300 | 0 | 219699.04 | 0 | 0 | 0 | 14079.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3721 | 12952 | 006F10hONquFoITpjT | FALSE
26-PC-41176 | Wildrye Park Improvements - Environmental Review Support | Fixed fee | Final Reporting/Review | L8150 | E31141 | Keystone Energy Partners | 36.93% | 109400 | 34591.32 | 81568.64 | 5587 | 2925.15 | 40401.42 | 2470.41 | 2451.68 | 0 | 5810.1 | 0 | 5810.1 | 0 | 37.5 | 4.5 | 0 | 12804 | 006tF6YOVI4Td80C9h | FALSE
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | Fixed fee | In Progress | L8150 | E31150 | Stonebridge Utilities | 100% | 41400 | 41400 | 27278.33 | 0 | 0 | 41400 | 4383.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 15036 | 006TtnXZod2pbmMV3x | TRUE
26-PC-41222 | Sage Flat Transmission Line - Cultural Resources Assessment | Time and material | In Progress | L8150 | E31151 | High Plains Construction Co. | 0% | 26000 | 3035.93 | 18522.4 | 2610.15 | 425.78 | 5460 | 356.92 | 334.75 | 0 | 2424.07 | 0 | 2424.07 | 0 | 7.5 | 0 | 433 | 11951 | 0068lG9vEz9DqMTaZf | FALSE
26-PC-41229 | Windmill Flat Phase I Survey | Fixed fee | On Hold | L8150 | E31150 | Prairie Wind Pipeline Company | 0% | 214000 | 0 | 143615.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 14024 | 006koyfyo1DVtGEpKF | FALSE
26-PC-41230 | Phase I: Slate Ridge Battery Storage Phase I Survey | Fixed fee | In Progress | L8150 | E31151 | Stonebridge Builders | 35.4% | 46400 | 9235.19 | 35769.76 | 2946.48 | 2520.47 | 16425.6 | 1987.85 | 2638.99 | 0 | 7190.41 | 0 | 7190.41 | 0 | 53.25 | 1.25 | 684 | 14860 | 006qhKeEkEqM7o1bGN | FALSE
26-PC-41302 | Thistle Down Pipeline Architectural History Survey | Time and material | Completed | L8150 | E31137 | Lakecrest Telecom Holdings | 100% | 20300 | 0 | 13056.96 | 0 | 0 | 0 | 1332.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 13182 | 006XwO4jRl37aPKadB | FALSE
26-PC-41334 | Fern Valley Housing Development - Data Recovery | Fixed fee | In Progress | L8150 | E31137 | Canyon Utilities | 68.81% | 154000 | 97190.14 | 99198.32 | 6401.88 | 3661.37 | 105967.4 | 4163.9 | 4417.41 | 0 | 8777.26 | 0 | 8777.26 | 0 | 103.75 | 0 | 1559 | 10611 | 006290ZBq7su1Hken7 | FALSE
26-PC-41386 | Task Order 11: Slate Ridge Harbor Dredging Class III Survey | Fixed fee | In Progress | L8150 | E31151 | Coastal Land Company | 3.72% | 302700 | 5037.07 | 209680.29 | 5037.07 | 0 | 11260.44 | 1200.49 | 6594.91 | 0 | 6223.37 | 0 | 6223.37 | 0 | 147.75 | 0 | 3122 | 11195 | 006unTFqiEKSwvMB9P | FALSE
26-PC-41394 | Maple Fork Bridge Replacement - Class III Survey | Fixed fee | Cost Tracking on Closed Project | L8150 | E31137 | Stonebridge Land Company | 89.21% | 15700 | 14005.97 | 11219.22 | 0 | 0 | 14005.97 | 1991.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14975 | 006WXOyMj4kfptjSj6 | TRUE
26-PC-41406 | Task Order 27: Dove Canyon Battery Storage Section 106 Consultation | Fixed fee | In Progress | L8150 | E31151 | Harborlight Port Authority | 40.76% | 381600 | 139465.09 | 257192.06 | 22877.83 | 7925.54 | 155540.16 | 20128.61 | 9827.58 | 0 | 16075.07 | 0 | 16075.07 | 0 | 218 | 3 | 4207 | 11691 | 006qYS6YAbzAWxWz3Z | TRUE
26-PC-41425 | Pebble Beach Road GIS Mapping | Time and material | Transferred Entity | L8150 | E31141 | Heartland Power Cooperative | 0% | 268700 | 55597.03 | 183253.4 | 37377.63 | 18219.4 | 99208 | 10707.92 | 20058.8 | 0 | 43610.97 | 0 | 43610.97 | 0 | 268.5 | 2 | 1669 | 11841 | 0067PFqT2kGly4AiPo | FALSE
26-PC-41446 | Stone Mill Levee Repair Archaeological Testing | Time and material | In Progress | L8150 | E31150 | Granite State Development Group | 0% | 263000 | 0 | 172291.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2444 | 11469 | 006e8505dkMU1Z8deb | FALSE
26-PC-41453 | Pebble Beach Road Cell Tower Environmental Review Support | Fixed fee | On Hold | L8150 | E31151 | Riverstone Construction Co. | 0% | 28100 | 0 | 22286.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 14599 | 006NmED51wBV1qkqGo | FALSE
26-PC-41466 | Millbrook Cultural Resources Assessment | Time and material | Lab/Curation | L8150 | E31151 | Silverline Telecom Holdings | 0% | 857800 | 255216.5 | 634085.76 | 0 | 0 | 255216.5 | 36802.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9294 | 14780 | 006ZBAODZykRtlBfWu | FALSE
26-PC-41575 | Juniper Wash Highway Widening - Section 106 Consultation | Fixed fee | In Progress | L8150 | E31138 | Riverstone Port Authority | 10.36% | 131400 | 5545.27 | 100941.48 | 5545.27 | 0 | 13613.04 | 742.17 | 4198.68 | 0 | 8067.77 | 0 | 8067.77 | 0 | 95.75 | 1.5 | 1959 | 14640 | 006pGI67NybXfGganH | FALSE
26-PC-41578 | Task Order 2: Pebble Beach Road Transmission Line Paleontological Monitoring | Time and material | On Hold | L8150 | E31138 | Ironbridge County | 0% | 340900 | 0 | 240285.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3943 | 12563 | 006zJV61JVvCSgaEjP | FALSE
26-PC-41623 | Eagle Bend Bridge Replacement - GIS Mapping | Time and material | On Hold | L8150 | E31137 | Mesa Verde Telecom Holdings | 0% | 113100 | 0 | 79124.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 13431 | 006hniMGFs9NjY65Wy | FALSE
26-PC-41644 | Granite Pass Built Environment Survey | Fixed fee | Transferred Entity | L8150 | E31151 | Granite State Infrastructure Group | 20.08% | 330600 | 36012.37 | 258297.78 | 26083 | 9929.37 | 66384.48 | 6588.54 | 15228.4 | 0 | 30372.11 | 0 | 30372.11 | 0 | 278.75 | 11 | 5318 | 11510 | 006ch0J4MNqRZwBNjE | FALSE
26-PC-41661 | Ember Valley Levee Repair Data Recovery | Fixed fee | In Progress | L8150 | E31138 | Keystone Planning Associates | 100% | 4800 | 1827.9 | 4028.16 | 1827.9 | 0 | 4800 | 474.51 | 708.52 | 0 | 2972.1 | 0 | 2972.1 | 0 | 9.25 | 1 | 49 | 12859 | 006ylIaUBFLwQSjWQT | FALSE
26-PC-41663 | On-Call: Plover Cove Highway Widening Cultural Resources Assessment | Time and material | On Hold | L8150 | E31137 | Westwind Infrastructure Group | 0% | 510700 | 0 | 337572.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5227 | 15890 | 006Gtr0JJ2QWYY6CUS | FALSE
26-PC-41667 | Kestrel Butte Transmission Line - Historic Resources Evaluation | Time and material | In Progress | L8150 | E31137 | Coastal Builders | 0% | 131800 | 93060.18 | 98659.54 | 28847.35 | 19006.4 | 127576.25 | 10324.73 | 14240.93 | 0 | 34516.07 | 0 | 34516.07 | 0 | 249.5 | 5.75 | 921 | 11038 | 006fD1sHGfdQvWjkIq | FALSE
26-PC-41671 | Phase I: Slate Ridge Solar Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8150 | E31138 | Blue Mesa Infrastructure Group | 100% | 256200 | 256200 | 182542.5 | 0 | 0 | 256200 | 18747.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2945 | 10139 | 006uRucWO13LY2GFWi | FALSE
26-PC-41683 | On-Call: Slate Ridge Levee Repair Built Environment Survey | Fixed fee | In Progress | L8160 | E31173 | Ironbridge Telecom Holdings | 2.75% | 250100 | 1667.12 | 169042.59 | 1667.12 | 0 | 6877.75 | 547.79 | 3428.39 | 0 | 5210.63 | 0 | 5210.63 | 0 | 67.25 | 0 | 3721 | 12740 | 0066JNwBLwvR5IIhkO | FALSE
26-PC-41707 | Quail Run Solar Environmental Review Support | Fixed fee | Final Reporting/Review | L8160 | E31172 | Brightwater Planning Associates | 25.8% | 27000 | 3982.77 | 20358 | 2442.64 | 910.44 | 6966 | 1050.52 | 142 | 0 | 2983.23 | 0 | 2983.23 | 0 | 2.25 | 0 | 160 | 10306 | 006xLuy7ixuykT4QFY | TRUE
26-PC-41721 | Thistle Down Curation | Time and material | In Progress | L8160 | E31167 | Granite State Rail Partners | 0% | 67700 | 31888.77 | 46692.69 | 6298.96 | 3073.66 | 36183 | 1828.65 | 3379.97 | 0 | 4294.23 | 0 | 4294.23 | 0 | 60.5 | 0 | 670 | 11524 | 006yDQtw34qvzFNDNM | FALSE
26-PC-41739 | Slate Ridge Historic Resources Evaluation | Fixed fee | In Progress | L8160 | E31167 | Westwind County | 11.55% | 240100 | 23121.15 | 163268 | 10777.07 | 6832.35 | 27731.55 | 2866.55 | 3980.43 | 0 | 4610.4 | 0 | 4610.4 | 0 | 60.25 | 0.75 | 1802 | 15753 | 006Fqzi1jtX9Gzf76w | FALSE
26-PC-41750 | Task Order 6: Copper Flats Wind Farm Maritime Remote Sensing Survey | Fixed fee | On Hold | L8160 | E31162 | Northfield Telecom Holdings | 0% | 825200 | 0 | 659196.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7892 | 13631 | 006owvaMgB8sQUB9nr | FALSE
26-PC-41776 | Sandpiper Battery Storage GIS Mapping | Time and material | Lab/Curation | L8160 | E31172 | Lakecrest Construction Co. | 0% | 457800 | 36984.05 | 310067.94 | 5020.44 | 3957.47 | 40229.25 | 3541.59 | 2135.04 | 0 | 3245.2 | 0 | 3245.2 | 0 | 36.75 | 0 | 4150 | 12952 | 006PuVy4SQNiJvCYkG | FALSE
26-PC-41803 | Copper Flats Section 106 Consultation | Fixed fee | Lab/Curation | L8160 | E31172 | Ridgeline Water District | 12.1% | 554800 | 55086.8 | 392021.68 | 14973.55 | 4295.58 | 67130.8 | 7165.4 | 6309.99 | 0 | 12044 | 0 | 12044 | 0 | 95.75 | 2.5 | 7918 | 14577 | 006VfpjPgZtNDUMSLK | FALSE
26-PC-41821 | Blue Heron School Campus Curation | Time and material | In Progress | L8160 | E31172 | Timberline Telecom Holdings | 0% | 152400 | 35011.46 | 98770.44 | 4479.29 | 3391.11 | 38727 | 4215.96 | 1506.41 | 0 | 3715.54 | 0 | 3715.54 | 0 | 33.5 | 0 | 1738 | 15690 | 006Jl3tgIxRQjKXqUO | FALSE
26-PC-41863 | Silver Lake Canal Lining Cultural Resources Assessment | Fixed fee | In Progress | L8160 | E31172 | Silverline Construction Co. | 2.87% | 322500 | 8208.44 | 224460 | 1836.34 | 956.9 | 9255.75 | 1089.94 | 406.4 | 0 | 1047.31 | 0 | 1047.31 | 0 | 4 | 0 | 0 | 14700 | 006PGc4KlcN3UKiip2 | FALSE
26-PC-41865 | Phase II: Copper Flats Reservoir Class III Survey | Time and material | In Progress | L8160 | E31172 | Coastal Rail Partners | 0% | 67100 | 0 | 48325.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179 | 11259 | 006JBE9KQVz2ueaZU2 | FALSE
26-PC-41884 | Foxglove Trail - Curation | Time and material | In Progress | L8160 | E31167 | Pioneer Power Cooperative | 0% | 1099300 | 75305.17 | 743556.08 | 17401.15 | 16986.7 | 100170 | 12794.67 | 9325.45 | 0 | 24864.83 | 0 | 24864.83 | 0 | 203.75 | 5.25 | 13210 | 13831 | 006R8aYcQ2aK63K3kf | FALSE
26-PC-41918 | Plover Cove Data Recovery | Fixed fee | In Progress | L8160 | E31167 | Cardinal Environmental Consultants | 7.48% | 121100 | 7963.02 | 81064.34 | 793.63 | 677.42 | 9058.28 | 1078.68 | 868.2 | 0 | 1095.26 | 0 | 1095.26 | 0 | 20 | 0 | 1269 | 10678 | 006SjSfXhPFbNefy1V | FALSE
26-PC-41947 | Juniper Wash Trail - Cultural Resources Monitoring | Fixed fee | Lab/Curation | L8160 | E31170 | Mesa Verde Port Authority | 57.73% | 64400 | 30400.25 | 52073.84 | 6253.62 | 5513.84 | 37178.12 | 3427.06 | 3723.36 | 0 | 6777.87 | 0 | 6777.87 | 0 | 85.5 | 0 | 1031 | 13374 | 006ezsrKwvmKqO4pWQ | TRUE
26-PC-41954 | Creosote Draw Class III Survey | Fixed fee | Completed | L8160 | E31162 | Brightwater Rail Partners | 100% | 98400 | 98400 | 77440.8 | 0 | 0 | 98400 | 8425.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959 | 10392 | 006XsfJ7HDuBVEclBc | FALSE
26-PC-41961 | Eagle Bend Data Recovery | Fixed fee | In Progress | L8160 | E31167 | Sunrise Telecom Holdings | 22.63% | 463200 | 104822.16 | 369077.76 | 0 | 0 | 104822.16 | 9102.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4333 | 15492 | 006wEZOPanyq9SzdaP | FALSE
26-PC-41970 | North Fork School Campus - Cultural Resources Monitoring | Time and material | Final Reporting/Review | L8160 | E31167 | Brightwater Rail Partners | 0% | 292200 | 93249.75 | 212405.41 | 0 | 0 | 93249.75 | 7171.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197 | 10392 | 006OYTJxYgqAQi7DQj | FALSE
26-PC-41987 | Wildrye Cultural Resources Monitoring | Fixed fee | Completed | L8160 | E31170 | Keystone Planning Associates | 100% | 88100 | 88100 | 66383.35 | 0 | 0 | 88100 | 9524.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735 | 12859 | 00664IWb9HEa5n3pXq | FALSE
26-PC-42007 | On-Call: Wren Hollow Mixed-Use Development Architectural History Survey | Fixed fee | In Progress | L8160 | E31173 | Prairie Wind Planning Associates | 11% | 341700 | 31519.6 | 215752.53 | 9060.33 | 3904.5 | 37587 | 3820.41 | 3375.19 | 0 | 6067.4 | 0 | 6067.4 | 0 | 68.75 | 0 | 2990 | 14041 | 006ox93a6XC8ysqjol | FALSE
26-PC-42008 | Millbrook GIS Mapping | Time and material | In Progress | L8160 | E31162 | Canyon Utilities | 0% | 79400 | 0 | 54793.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033 | 10611 | 006EsLNtrnFn6E90iE | FALSE
26-PC-42023 | North Fork Historic Resources Evaluation | Fixed fee | Transferred Entity | L8160 | E31172 | Redtail Engineering, Inc. | 10.62% | 157000 | 14885.86 | 111815.4 | 2410.46 | 846.91 | 16673.4 | 1377.69 | 839.56 | 0 | 1787.54 | 0 | 1787.54 | 0 | 13.25 | 0 | 1522 | 14233 | 0068JJ9cULqmAkABC5 | FALSE
26-PC-42040 | Millbrook Phase II Testing | Time and material | In Progress | L8160 | E31172 | Coastal Rail Partners | 0% | 129700 | 9132.09 | 89350.33 | 2389.19 | 3205.89 | 14359.5 | 1026.32 | 2106.64 | 0 | 5227.41 | 0 | 5227.41 | 0 | 30.25 | 3 | 862 | 11259 | 006AZIe6Z9BLTgvbWs | FALSE
26-PC-42099 | Fern Valley Substation Cultural Resources Monitoring | Time and material | In Progress | L8160 | E31173 | Blue Mesa Environmental Consultants | 0% | 661800 | 110235.78 | 445656.12 | 11050.75 | 6060 | 124275.5 | 4872.76 | 5825.64 | 0 | 14039.72 | 0 | 14039.72 | 0 | 96.75 | 6.5 | 0 | 10083 | 006ismQgZVvkDUeuvO | FALSE
26-PC-42105 | Creosote Draw Archaeological Testing | Time and material | Completed | L8160 | E31173 | Blue Mesa Resources Corp. | 100% | 671900 | 0 | 486652.56 | 0 | 0 | 0 | 80806.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5190 | 10225 | 006krIUszui4zNHmXb | FALSE
26-PC-42108 | Sumac Ridge Mixed-Use Development Curation | Fixed fee | In Progress | L8160 | E31162 | Blue Mesa Port Authority | 5.78% | 1000600 | 51120.33 | 761256.48 | 10318.81 | 8298.01 | 57834.68 | 9144.48 | 4391.69 | 0 | 6714.35 | 0 | 6714.35 | 0 | 58 | 0 | 11018 | 10214 | 0064OdX83ejmpoVekO | FALSE
26-PC-42222 | On-Call: Stone Mill Fiber Route Cultural Resources Monitoring | Time and material | On Hold | L8160 | E31170 | High Plains Engineering, Inc. | 0% | 30000 | 0 | 21213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 12054 | 006wnte6qX4yH5S29d | FALSE
26-PC-42293 | Eagle Bend Water Main Phase II Testing | Fixed fee | In Progress | L8170 | E31175 | Pioneer Renewables LLC | 24.49% | 100800 | 22746.35 | 88704 | 3797.85 | 2480.15 | 24685.92 | 4475.3 | 232.65 | 0 | 1939.57 | 0 | 1939.57 | 0 | 5.5 | 0 | 1244 | 13869 | 006f7zUPOrcZNgQacB | FALSE
26-PC-42406 | Saltgrass Cell Tower - Section 106 Consultation | Time and material | Final Billing/Invoice | L8170 | E31175 | Ironbridge Telecom Holdings | 100% | 92600 | 0 | 64853.52 | 0 | 0 | 0 | 4209.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079 | 12740 | 006rxQX0fSGmAZSbRb | FALSE
26-PC-42427 | Phase II: Stone Mill Mine Expansion Section 106 Consultation | Time and material | In Progress | L8170 | E31179 | Redtail Engineering, Inc. | 0% | 926100 | 182757.68 | 644195.16 | 10555.9 | 8348.21 | 199575 | 25763.55 | 7780.88 | 0 | 16817.32 | 0 | 16817.32 | 0 | 149.5 | 8.5 | 8174 | 14233 | 006JroX5LJrErnOdq7 | FALSE
26-PC-42428 | Phase II: Yarrow Point Levee Repair Architectural History Survey | Fixed fee | Final Reporting/Review | L8170 | E31175 | Blue Mesa Port Authority | 2.52% | 921200 | 7402.27 | 680214.08 | 7402.27 | 0 | 23214.24 | 2370.07 | 10524.73 | 0 | 15811.97 | 0 | 15811.97 | 0 | 236 | 4.5 | 0 | 10214 | 006NPj3VPGmHYC0wLi | FALSE
26-PC-42472 | Kestrel Butte Cultural Resources Monitoring | Fixed fee | In Progress | L8170 | E31179 | Lakecrest Rail Partners | 3.41% | 129200 | 1825.8 | 94328.92 | 1499.04 | 326.76 | 4405.72 | 644.2 | 2576.78 | 0 | 2579.92 | 0 | 2579.92 | 0 | 47 | 12.5 | 1835 | 13111 | 006HnyoWPc7kCAgqiF | FALSE
26-PC-42492 | Tamarack Class III Survey | Time and material | In Progress | L8170 | E31175 | Riverstone Port Authority | 0% | 60100 | 14528.76 | 39629.94 | 2910.76 | 1203.37 | 15520.75 | 961.07 | 135.27 | 0 | 991.99 | 0 | 991.99 | 0 | 2.75 | 0 | 616 | 14640 | 006cfrECrRGSW1lQJM | FALSE
26-PC-42510 | Lantern Bay Data Recovery | Time and material | In Progress | L8170 | E31175 | Mesa Verde County | 0% | 1304200 | 138984.13 | 949196.76 | 9510.88 | 3830.28 | 147490.25 | 14925.29 | 952.22 | 0 | 8506.12 | 0 | 8506.12 | 0 | 21.75 | 0 | 12435 | 13234 | 006Qc0ciZG4W3DEpbk | FALSE
26-PC-42554 | Task Order 36: Larkspur Pipeline Class III Survey | Fixed fee | In Progress | L8170 | E31175 | Heartland Transit Authority | 7.02% | 138900 | 3241.35 | 102674.88 | 3241.35 | 0 | 9750.78 | 872.58 | 2511.91 | 0 | 6509.43 | 0 | 6509.43 | 0 | 59 | 0 | 0 | 11878 | 006W7Qi8nSpRcKDB0Y | FALSE
26-PC-42585 | On-Call: Eagle Bend Reservoir Class III Survey | Fixed fee | Completed | L8170 | E31175 | Prairie Wind Utilities | 100% | 29400 | 29400 | 20518.26 | 0 | 0 | 29400 | 1948.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 14159 | 006ARjZIBzLDyQKXtb | TRUE
26-PC-42598 | Badger Hollow Phase II Testing | Time and material | In Progress | L8170 | E31179 | Sunrise County | 0% | 99400 | 46544.43 | 74509.83 | 9188.21 | 3192.53 | 52925.75 | 3717.17 | 2733.75 | 0 | 6381.32 | 0 | 6381.32 | 0 | 38.5 | 0 | 806 | 15336 | 006ljtgUWn8jlujoZm | FALSE
26-PC-42616 | Goldfinch Section 106 Consultation | Fixed fee | Final Billing/Invoice | L8170 | E31175 | Heartland Transit Authority | 100% | 14600 | 14600 | 11993.9 | 0 | 0 | 14600 | 1733.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 11878 | 006CVBq86ImEv3788h | TRUE
26-PC-42648 | Plover Cove Highway Widening - Architectural History Survey | Fixed fee | Final Billing/Invoice | L8170 | E31175 | Ridgeline County | 100% | 330300 | 330300 | 209145.96 | 0 | 0 | 330300 | 19218.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4191 | 14393 | 006ExFiGnlbF09GtY9 | FALSE
26-PC-42664 | Foxglove Cell Tower GIS Mapping | Fixed fee | In Progress | L8170 | E31179 | Cardinal Environmental Consultants | 6.31% | 50700 | 1164.27 | 32903.41 | 1164.27 | 0 | 3199.17 | 394.31 | 1244.58 | 0 | 2034.9 | 0 | 2034.9 | 0 | 21.5 | 0 | 0 | 10678 | 006jziFzJdVgoiEjVm | TRUE
26-PC-42679 | Aspen Ridge Phase I Survey | Fixed fee | Final Reporting/Review | L8180 | E31185 | High Plains Renewables LLC | 48.03% | 214600 | 88132.28 | 144103.9 | 13424.31 | 6297.04 | 103072.38 | 13012.88 | 9479.56 | 0 | 14940.1 | 0 | 14940.1 | 0 | 122.5 | 3 | 1148 | 12128 | 006EgT6yYpO0mSH3d4 | TRUE
26-PC-42692 | Quail Run Curation | Fixed fee | In Progress | L8180 | E31188 | Mesa Verde Planning Associates | 13.2% | 300500 | 29809.72 | 203889.25 | 13282.59 | 14079.04 | 39666 | 5650.26 | 4667.55 | 0 | 9856.28 | 0 | 9856.28 | 0 | 60.5 | 0 | 1571 | 13344 | 006h2VUEpvMm974vzy | FALSE
26-PC-42734 | On-Call: Lantern Bay Reservoir Architectural History Survey | Time and material | In Progress | L8180 | E31188 | Coastal Construction Co. | 0% | 77500 | 38532.58 | 51615 | 5997.79 | 4820.43 | 41132.25 | 3243.86 | 1687.59 | 0 | 2599.67 | 0 | 2599.67 | 0 | 33.25 | 0 | 704 | 11092 | 006i7GsboTq9HXRsDo | FALSE
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | Fixed fee | In Progress | L8180 | E31185 | Blue Mesa Pipeline Company | 72.76% | 347000 | 226595.93 | 256363.6 | 25044.7 | 7632.25 | 252477.2 | 23502.54 | 9259.8 | 0 | 25881.27 | 0 | 25881.27 | 0 | 139 | 10.5 | 3715 | 10171 | 0068FKBi6MfB7xgYly | FALSE
26-PC-42759 | Cedar Hollow Pipeline - Section 106 Consultation | Time and material | Completed | L8180 | E31185 | Sunrise Telecom Holdings | 100% | 740600 | 0 | 515013.24 | 0 | 0 | 0 | 56771.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7530 | 15492 | 006aYWCIGLf9QaH7mJ | FALSE
26-PC-42788 | Riverbend Bridge Replacement Data Recovery | Fixed fee | Final Billing/Invoice | L8180 | E31185 | Brightwater Power Cooperative | 100% | 1595900 | 1595900 | 1047867.94 | 0 | 0 | 1595900 | 162183.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20306 | 10363 | 006TIX09qjFqBzV4BJ | TRUE
26-PC-42811 | On-Call: Yarrow Point Bridge Replacement Archaeological Testing | Time and material | Completed | L8180 | E31185 | Redtail Rail Partners | 100% | 8000 | 0 | 5034.4 | 0 | 0 | 0 | 1341.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 14317 | 006CvycXJKYTRyNemk | FALSE
26-PC-42832 | Task Order 39: Saltgrass Levee Repair Class III Survey | Time and material | Final Reporting/Review | L8180 | E31188 | Keystone Planning Associates | 0% | 343600 | 32806.18 | 243097 | 7152 | 6003.7 | 38736.25 | 2497.74 | 3688.83 | 0 | 5930.07 | 0 | 5930.07 | 0 | 83.75 | 0 | 4994 | 12859 | 006UPtFEfsCD5tz8Ue | FALSE
26-PC-42838 | Phase III: Oak Terrace Pipeline Phase II Testing | Fixed fee | In Progress | L8180 | E31188 | Granite State Infrastructure Group | 41.91% | 47400 | 19865.34 | 31824.36 | 0 | 0 | 19865.34 | 1307.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596 | 11510 | 006PLgn67SO2Q4rz3j | FALSE
26-PC-42859 | On-Call: Redbud Canal Lining Phase II Testing | Fixed fee | On Hold | L8180 | E31188 | Canyon Utilities | 0% | 34400 | 0 | 26797.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267 | 10611 | 006NREAvgxPuJpyyUS | FALSE
26-PC-42880 | Phase I: Quail Run Harbor Dredging Curation | Fixed fee | In Progress | L8180 | E31188 | Evergreen Development Group | 11.33% | 107200 | 7389.46 | 87904 | 4137.54 | 1783.38 | 12145.76 | 905.98 | 1691.93 | 0 | 4756.3 | 0 | 4756.3 | 0 | 38.75 | 0 | 1117 | 11371 | 006DIztTM5HgXTjEAN | FALSE
26-PC-42898 | Sumac Ridge Architectural History Survey | Fixed fee | Final Billing/Invoice | L8180 | E31185 | Summit Port Authority | 100% | 388100 | 388100 | 247453.77 | 0 | 0 | 388100 | 31392.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2484 | 15239 | 006TxliUPXx3nCwKO5 | TRUE
26-PC-42926 | Juniper Wash Transmission Line - Class III Survey | Fixed fee | In Progress | L8180 | E31188 | Northfield Telecom Holdings | 5.29% | 87800 | 1775.48 | 68132.8 | 1775.48 | 0 | 4644.62 | 579.85 | 1928.62 | 0 | 2869.14 | 0 | 2869.14 | 0 | 50 | 0 | 1116 | 13631 | 006o5l14QW0E9ND5Ef | FALSE
26-PC-42940 | North Fork Water Main GIS Mapping | Time and material | Completed | L8180 | E31185 | Coastal Development Group | 100% | 17600 | 0 | 11908.16 | 0 | 0 | 0 | 2821.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 11160 | 006NCBXzWKqYxE4vdi | FALSE
26-PC-42951 | Quail Run Solar - Paleontological Monitoring | Fixed fee | Final Billing/Invoice | L8180 | E31185 | Ridgeline Water District | 100% | 209300 | 209300 | 146631.97 | 0 | 0 | 209300 | 16820.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1885 | 14577 | 0066iUmXcqAtOXW6cR | FALSE
26-PC-42962 | Lone Pine Curation | Time and material | In Progress | L8180 | E31188 | Harborlight Port Authority | 0% | 1041700 | 4165.92 | 704293.37 | 4165.92 | 0 | 12393.75 | 828.39 | 4065.67 | 0 | 8227.83 | 0 | 8227.83 | 0 | 88.25 | 0 | 0 | 11691 | 006t2LDKg26Aqmhl5j | FALSE
26-PC-42989 | North Fork Cultural Resources Monitoring | Time and material | In Progress | L8180 | E31188 | Clearwater Planning Associates | 0% | 24000 | 1076.33 | 15241.71 | 619.36 | 442.01 | 1482 | 181.05 | 186.85 | 0 | 405.67 | 0 | 405.67 | 0 | 5 | 0 | 0 | 10938 | 006nP90Jpt5oxw2zA2 | FALSE
26-PC-43000 | Pebble Beach Road Park Improvements Curation | Fixed fee | Final Billing/Invoice | L8180 | E31188 | Cardinal Energy Partners | 100% | 150700 | 150700 | 99296.23 | 0 | 0 | 150700 | 14649.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048 | 10648 | 006Ddmr0JoqGZSqKbo | FALSE
26-PC-43026 | Fern Valley Phase I Survey | Fixed fee | On Hold | L8180 | E31188 | Granite State Rail Partners | 0% | 66700 | 0 | 42521.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 11524 | 006bs3LrLOlmRP8mKk | FALSE
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Time and material | Final Reporting/Review | L8190 | E31193 | Ironbridge Telecom Holdings | 0% | 107600 | 99262.67 | 77827.43 | 6238.81 | 3081.36 | 107600 | 6860.6 | 6541.71 | 0 | 8337.33 | 0 | 8337.33 | 0 | 109 | 0 | 0 | 12740 | 006dPP8syK9uLoL9DV | FALSE
26-PC-43059 | Kestrel Butte Battery Storage - Phase II Testing | Fixed fee | Final Billing/Invoice | L8190 | E31193 | Riverstone Construction Co. | 100% | 44100 | 44100 | 27527.22 | 0 | 0 | 44100 | 2675.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518 | 14599 | 006kHEjXnhT0qEoKai | FALSE
26-PC-43086 | On-Call: Silver Lake Transmission Line Archaeological Testing | Time and material | In Progress | L8190 | E31193 | Harborlight Transit Authority | 0% | 2118800 | 0 | 1431461.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14495 | 11703 | 006rhlj1wmqnZTqsw4 | FALSE
26-PC-43132 | Phase III: Ember Valley Highway Widening Phase II Testing | Fixed fee | Lab/Curation | L8190 | E31192 | Cardinal Environmental Consultants | 33.43% | 140700 | 43252.63 | 112756.98 | 5274.48 | 2071.31 | 47036.01 | 4032.84 | 144.59 | 0 | 3783.38 | 0 | 3783.38 | 0 | 2.25 | 0 | 1530 | 10678 | 006XXYSE7t4mFHhdJ6 | FALSE
26-PC-43136 | Phase III: Harbor View Highway Widening Section 106 Consultation | Time and material | In Progress | L8190 | E31192 | Granite State Resources Corp. | 0% | 3831800 | 138596.66 | 2564623.74 | 22155.74 | 12214.39 | 168416.5 | 21766.45 | 15391.05 | 0 | 29819.84 | 0 | 29819.84 | 0 | 205.5 | 13.5 | 32425 | 11571 | 006ctylPcfaWDOczZv | FALSE
26-PC-43168 | Task Order 35: Aspen Ridge Transmission Line Architectural History Survey | Fixed fee | Final Reporting/Review | L8190 | E31193 | Granite State Rail Partners | 29.89% | 281200 | 79022.62 | 164749.65 | 5106.49 | 6306.27 | 84050.68 | 5612.96 | 3924.8 | 0 | 5028.06 | 0 | 5028.06 | 0 | 87.25 | 0 | 2975 | 11524 | 0061g2DgUW70F1EkjO | FALSE
26-PC-43191 | Sandpiper Harbor Dredging - Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8200 | E31196 | Coastal Builders | 100% | 47200 | 47200 | 37639.5 | 0 | 0 | 47200 | 3728.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613 | 11038 | 0068IPoW0FuUeRMMVb | FALSE
26-PC-43199 | Thistle Down Airport Apron Phase I Survey | Fixed fee | Cost Tracking on Closed Project | L8200 | E31199 | Highland Water District | 92.27% | 42200 | 38937.94 | 26341.24 | 0 | 0 | 38937.94 | 4715.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 12481 | 00608NftAHbK5XuN8V | TRUE
26-PC-43222 | Blue Heron Highway Widening Phase II Testing | Time and material | On Hold | L8200 | E31202 | Coastal Construction Co. | 0% | 15100 | 0 | 9664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 11092 | 006MSvg749tzAHl2Fr | FALSE
26-PC-43266 | Silver Lake Curation | Fixed fee | In Progress | L8200 | E31199 | Northfield Pipeline Company | 2.18% | 21300 | 217.28 | 13227.3 | 217.28 | 0 | 464.34 | 29.1 | 258.99 | 0 | 247.06 | 0 | 247.06 | 0 | 5.75 | 0 | 192 | 13520 | 006QoKRCEolCYetvYi | FALSE
26-PC-43307 | Phase III: Aspen Ridge Mine Expansion Maritime Remote Sensing Survey | Time and material | In Progress | L8200 | E31202 | Clearwater Builders | 0% | 239600 | 71378.75 | 189451.72 | 0 | 0 | 71378.75 | 9719.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3953 | 10855 | 0068kvkKeFkM3r93AO | FALSE
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | Fixed fee | In Progress | L8200 | E31199 | Cardinal Environmental Consultants | 75.11% | 41200 | 29998.17 | 27426.84 | 801.45 | 866.58 | 30945.32 | 2842.73 | 914.02 | 0 | 947.15 | 0 | 947.15 | 0 | 24.25 | -1.25 | 399 | 10678 | 006nG3XZw8QCKK6AJj | FALSE
26-PC-43338 | Sparrow Hill Bridge Replacement Section 106 Consultation | Time and material | In Progress | L8200 | E31202 | Clearwater Resources Corp. | 0% | 121900 | 0 | 79125.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1158 | 11004 | 0067VVSANe64kfTAsg | FALSE
26-PC-43341 | Phase III: Twin Buttes Wastewater Plant Historic Resources Evaluation | Fixed fee | Final Billing/Invoice | L8200 | E31196 | Westwind Energy Partners | 100% | 87500 | 87500 | 70376.25 | 0 | 0 | 87500 | 8422.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 15833 | 006IO5coPyumrUj8FS | FALSE
26-PC-43364 | Goldfinch Class III Survey | Fixed fee | Transferred Entity | L8200 | E31202 | Westwind Infrastructure Group | 100% | 24900 | 23821.32 | 16624.07 | 2883.46 | 2415.01 | 24900 | 2556.51 | 161.4 | 0 | 1078.68 | 0 | 1078.68 | 0 | 2 | 1.75 | 191 | 15890 | 006ySmsw3MJfk8Q44V | FALSE
26-PC-43381 | Lantern Bay Canal Lining Archaeological Testing | Fixed fee | In Progress | L8200 | E31200 | Summit Port Authority | 7.65% | 309600 | 7401.4 | 249847.2 | 7401.4 | 0 | 23684.4 | 3345.71 | 7589.57 | 0 | 16283 | 0 | 16283 | 0 | 73 | 6.5 | 0 | 15239 | 006u4K0ssN1zW5sB6Y | FALSE
26-PC-43404 | On-Call: Timber Gap Transmission Line Built Environment Survey | Fixed fee | Final Billing/Invoice | L8200 | E31202 | Timberline Planning Associates | 100% | 190700 | 190700 | 155973.53 | 0 | 0 | 190700 | 32848.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770 | 15643 | 0064O3QnSps8Ipct0s | FALSE
26-PC-43429 | Stone Mill Highway Widening Curation | Fixed fee | Transferred Entity | L8200 | E31200 | Summit Infrastructure Group | 5.19% | 202600 | 5068.52 | 115400.96 | 5068.52 | 0 | 10514.94 | 1168.98 | 3458.65 | 0 | 5446.42 | 0 | 5446.42 | 0 | 82 | 0 | 0 | 15147 | 006loL9LLH28UnVWk6 | FALSE
26-PC-43478 | Tamarack Airport Apron Phase II Testing | Time and material | In Progress | L8200 | E31200 | Blue Mesa Environmental Consultants | 0% | 531800 | 118587.81 | 378109.8 | 40210.74 | 27647.64 | 167292.25 | 24686.04 | 26933.88 | 0 | 48704.44 | 0 | 48704.44 | 0 | 414.25 | 3.25 | 3100 | 10083 | 006KeRhjEmzf17MlsD | FALSE
26-PC-43493 | Millbrook Pipeline Cultural Resources Monitoring | Time and material | In Progress | L8200 | E31202 | Evergreen Development Group | 0% | 1164300 | 74613.99 | 893116.35 | 19838.99 | 13482.12 | 96389 | 12467.7 | 13975.81 | 0 | 21775.01 | 0 | 21775.01 | 0 | 248 | 19.75 | 10792 | 11371 | 006TF9MEhlUPd8Bsz7 | FALSE
26-PC-43519 | On-Call: Meadowlark Pipeline GIS Mapping | Fixed fee | Completed | L8200 | E31202 | Granite State Resources Corp. | 100% | 28100 | 28100 | 19981.91 | 0 | 0 | 28100 | 1903.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11571 | 006CoCNN9VeobiyjME | TRUE
26-PC-43527 | Maple Fork School Campus Phase II Testing | Time and material | In Progress | L8200 | E31202 | Lakecrest Planning Associates | 0% | 333700 | 72040.32 | 224680.21 | 3130.48 | 5025.46 | 77471 | 9312.69 | 1632.79 | 0 | 5430.68 | 0 | 5430.68 | 0 | 24.5 | 0 | 2004 | 13040 | 006MW93jHFVxLZC6ld | FALSE
26-PC-43528 | Quail Run Cell Tower GIS Mapping | Fixed fee | Final Reporting/Review | L8200 | E31199 | Stonebridge Engineering, Inc. | 85.5% | 21800 | 5521.71 | 14869.78 | 5521.71 | 0 | 18639 | 1156.93 | 8794.72 | 0 | 13117.29 | 0 | 13117.29 | 0 | 115.5 | 0 | 185 | 14937 | 006BuqdJQDxlAk3ayr | TRUE
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | Fixed fee | In Progress | L8200 | E31200 | Keystone Energy Partners | 95.71% | 136900 | 130552.64 | 105043.37 | 411.79 | 370.74 | 131026.99 | 21413.57 | 0 | 0 | 474.35 | 0 | 474.35 | 0 | 0 | 0 | 931 | 12804 | 006XjieQJaIndvvGka | FALSE
26-PC-43563 | Thistle Down Section 106 Consultation | Time and material | In Progress | L8200 | E31199 | Summit Planning Associates | 0% | 79800 | 19196.62 | 52393.25 | 5333.19 | 4471.34 | 25811.25 | 2664.75 | 2581.99 | 0 | 6614.63 | 0 | 6614.63 | 0 | 51.5 | 0 | 640 | 15198 | 006dghoFgrItCuok9u | FALSE
26-PC-43575 | On-Call: Fern Valley Substation Data Recovery | Fixed fee | Lab/Curation | L8200 | E31199 | Clearwater Planning Associates | 70.42% | 113100 | 74740.94 | 87831.71 | 5394.89 | 2359.41 | 79645.02 | 11441.92 | 460.16 | 0 | 4904.08 | 0 | 4904.08 | 0 | 3.75 | 0 | 0 | 10938 | 006eZLkaywu8noKb4E | TRUE
26-PC-43584 | On-Call: Wren Hollow Solar Architectural History Survey | Fixed fee | In Progress | L8200 | E31199 | Lakecrest Construction Co. | 0% | 223700 | 0 | 185536.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2104 | 12952 | 0060RZ0TxrhSii7XxV | FALSE
26-PC-43695 | Willow Springs Maritime Remote Sensing Survey | Fixed fee | In Progress | L8210 | E31209 | Summit Port Authority | 34.41% | 104700 | 27395.63 | 73750.68 | 7364.11 | 5629.08 | 36027.27 | 4567.75 | 4702.51 | 0 | 8631.64 | 0 | 8631.64 | 0 | 89.75 | 0 | 1052 | 15239 | 006mn5X4IDY38yytpD | FALSE
26-PC-43731 | Task Order 32: Dove Canyon Transmission Line Paleontological Monitoring | Time and material | In Progress | L8210 | E31209 | Ironbridge Port Authority | 0% | 17700 | 0 | 12905.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12704 | 006gMetRccsq8FeBBE | FALSE
26-PC-43746 | Cedar Hollow Wastewater Plant - Paleontological Monitoring | Fixed fee | On Hold | L8210 | E31209 | Westwind Infrastructure Group | 0% | 94200 | 0 | 53458.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15890 | 006cNNCVoMhb0rqj7d | TRUE
26-PC-43762 | Hawk Point Substation Paleontological Monitoring | Fixed fee | In Progress | L8210 | E31206 | Brightwater Rail Partners | 5.41% | 17500 | 335.45 | 15400 | 335.45 | 0 | 946.75 | 152.38 | 165.93 | 0 | 611.3 | 0 | 611.3 | 0 | 2.5 | 0 | 126 | 10392 | 006GsCwMJ2Ra1Cj5e0 | FALSE
26-PC-43818 | Plover Cove Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | L8210 | E31206 | Harborlight Water District | 11.55% | 277600 | 22111.94 | 226882.48 | 9412.92 | 4979.92 | 32062.8 | 2410.76 | 4927.97 | 0 | 9950.86 | 0 | 9950.86 | 0 | 74.25 | 0 | 0 | 11739 | 006Ck0lS1xaJMXTGGo | FALSE
26-PC-43874 | Oak Terrace Cell Tower - Class III Survey | Fixed fee | Transferred Entity | L8220 | E31222 | High Plains Water District | 0% | 72100 | 0 | 51991.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12150 | 006MMx5pa0AgakH7ou | FALSE
26-PC-43899 | On-Call: Foxglove Reservoir Cultural Resources Monitoring | Time and material | In Progress | L8220 | E31222 | Sunrise Planning Associates | 0% | 154600 | 9002.14 | 103767.52 | 8507.19 | 494.95 | 17698 | 2464.43 | 7018.13 | 0 | 8695.86 | 0 | 8695.86 | 0 | 82.75 | 0 | 0 | 15406 | 006yxdgFbaFuYz9yWS | FALSE
26-PC-43915 | Task Order 5: Twin Buttes Bridge Replacement Phase I Survey | Fixed fee | Transferred Entity | L8220 | E31221 | Keystone Rail Partners | 0.61% | 202200 | 311.59 | 177936 | 311.59 | 0 | 1233.42 | 147.76 | 938.72 | 0 | 921.83 | 0 | 921.83 | 0 | 12.25 | 0 | 2378 | 12893 | 006rXkAA2tO4sk6wBV | TRUE
26-PC-43927 | On-Call: Millbrook Cell Tower Architectural History Survey | Time and material | Transferred Entity | L8220 | E31213 | Lakecrest Pipeline Company | 0% | 60000 | 1412.87 | 39334.64 | 1412.87 | 0 | 3540.25 | 284.9 | 262.71 | 0 | 2127.38 | 0 | 2127.38 | 0 | 5.25 | 0 | 0 | 13006 | 006tg5LOmakDMuUMkQ | FALSE
26-PC-43957 | Meadowlark Rail Siding - GIS Mapping | Fixed fee | Completed | L8220 | E31220 | Coastal County | 100% | 294000 | 294000 | 218030.4 | 0 | 0 | 294000 | 27057.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 11118 | 006OtNxW1g63q7RvSK | TRUE
26-PC-43961 | On-Call: Sparrow Hill Fiber Route Architectural History Survey | Fixed fee | Transferred Entity | L8220 | E31220 | Ironbridge County | 44.89% | 264600 | 98585.19 | 211627.08 | 14176.83 | 8028.83 | 118778.94 | 17194.73 | 9861.43 | 0 | 20193.75 | 0 | 20193.75 | 0 | 172.75 | 3.5 | 2992 | 12563 | 006pkSygkwWQE0qQH2 | FALSE
26-PC-43963 | On-Call: Foxglove Trail Data Recovery | Fixed fee | In Progress | L8220 | E31221 | Sunrise Water District | 25.13% | 532600 | 117842.42 | 335058.66 | 13518.47 | 10885.05 | 133842.38 | 11028.59 | 6889.46 | 0 | 15999.96 | 0 | 15999.96 | 0 | 132 | 4.5 | 6615 | 15575 | 006FTWdqEPpVVDCHYA | TRUE
26-PC-43979 | Pine Hollow Harbor Dredging - Historic Resources Evaluation | Fixed fee | Transferred Entity | L8220 | E31222 | Highland Rail Partners | 0% | 98500 | 0 | 72742.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890 | 12394 | 006uE737ZDPRwsqCQr | TRUE
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Time and material | Transferred Entity | L8220 | E31222 | Coastal Development Group | 0% | 220800 | 195354 | 146699.52 | 17153.03 | 8639.37 | 218771.25 | 19979.97 | 8096.31 | 0 | 23417.25 | 0 | 23417.25 | 0 | 101.5 | 0 | 1754 | 11160 | 006j1vqsSzZ8427fUx | FALSE
26-PC-43991 | Saltgrass Water Main - Archaeological Testing | Fixed fee | In Progress | L8220 | E31211 | Redtail Water District | 61.42% | 22500 | 10534.3 | 13335.87 | 1932.07 | 1815.69 | 13819.5 | 999.35 | 1330.34 | 0 | 3285.2 | 0 | 3285.2 | 0 | 11.75 | 0 | 74 | 14359 | 006JAsvY8OxzGQVG0m | TRUE
26-PC-44007 | Goldfinch Battery Storage Architectural History Survey | Time and material | Transferred Entity | L8220 | E31218 | Prairie Wind Planning Associates | 0% | 226900 | 14790 | 149799.38 | 0 | 0 | 14790 | 1251.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2606 | 14041 | 006jFraTiQeaUmNIbM | FALSE
26-PC-44050 | On-Call: Hawk Point Canal Lining Archaeological Testing | Fixed fee | Transferred Entity | L8220 | E31220 | High Plains Engineering, Inc. | 5.57% | 670400 | 21973.44 | 477190.72 | 7780.7 | 11562.75 | 37341.28 | 2869.49 | 6125.92 | 0 | 15367.84 | 0 | 15367.84 | 0 | 126.25 | 0 | 5223 | 12054 | 006RhjB4twqrwJiAHx | FALSE
26-PC-44072 | Oak Terrace Water Main GIS Mapping | Fixed fee | Transferred Entity | L8220 | E31213 | Coastal Builders | 52.21% | 106200 | 48383.9 | 79469.46 | 6916.72 | 5521.28 | 55447.02 | 7592.57 | 838.04 | 0 | 7063.12 | 0 | 7063.12 | 0 | 7 | 0 | 0 | 11038 | 0063Wg4QPDyB6UolMs | FALSE
26-PC-44090 | Eagle Bend Phase I Survey | Time and material | Transferred Entity | L8220 | E31211 | Evergreen Development Group | 0% | 6300 | 227.3 | 4404.16 | 227.3 | 0 | 1040.75 | 35.07 | 0 | 0 | 813.45 | 0 | 813.45 | 0 | 0 | 0 | 31 | 11371 | 006Ds7d1hHotIb29gA | FALSE
26-PC-44129 | Tamarack Airport Apron - Section 106 Consultation | Fixed fee | In Progress | L8220 | E31221 | Coastal Rail Partners | 0% | 40400 | 0 | 30324.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 11259 | 006OZqRpO8mNOSn00q | TRUE
26-PC-44173 | Timber Gap Harbor Dredging - Section 106 Consultation | Fixed fee | Transferred Entity | L8220 | E31213 | Blue Mesa Pipeline Company | 18.18% | 160600 | 21934.33 | 111038.84 | 8498.32 | 7779.7 | 29197.08 | 2099.15 | 4047.13 | 0 | 7262.75 | 0 | 7262.75 | 0 | 68.25 | 13.25 | 0 | 10171 | 006JZczkdlhzUAJZke | FALSE
26-PC-44201 | Plover Cove Section 106 Consultation | Time and material | Transferred Entity | L8220 | E31221 | Keystone Environmental Consultants | 0% | 165400 | 60276.15 | 115267.26 | 10405.46 | 4629.23 | 67195 | 2412.66 | 3380.76 | 0 | 6918.85 | 0 | 6918.85 | 0 | 53 | 0 | 1266 | 12815 | 006Fj62VyGdHQwxNeh | FALSE
26-PC-44220 | Dove Canyon GIS Mapping | Time and material | Transferred Entity | L8220 | E31222 | Riverstone Port Authority | 0% | 59700 | 5425.72 | 47634.63 | 4627.44 | 798.28 | 7761.5 | 783.02 | 0 | 0 | 2335.78 | 0 | 2335.78 | 0 | 0 | 0 | 691 | 14640 | 006eay9MmFuiTECUXk | FALSE
26-PC-44256 | On-Call: Twin Buttes Rail Siding Environmental Review Support | Fixed fee | Transferred Entity | L8220 | E31213 | Granite State Rail Partners | 39.65% | 810700 | 283600.7 | 574867.37 | 30932.47 | 24935.87 | 321442.55 | 45126.09 | 16109.93 | 0 | 37841.85 | 0 | 37841.85 | 0 | 238.5 | 4.75 | 0 | 11524 | 00632jqOJ2EfxQChHs | TRUE
26-PC-44277 | Phase I: Sea Oat Harbor Dredging Architectural History Survey | Fixed fee | In Progress | L8220 | E31211 | Summit County | 58.01% | 49100 | 25401.55 | 39677.71 | 3729.13 | 1055.7 | 28482.91 | 4879.9 | 750.3 | 0 | 3081.36 | 0 | 3081.36 | 0 | 10 | 0 | 427 | 15070 | 006OT4npiwFnXxOcPY | FALSE
26-PC-44290 | On-Call: Larkspur Park Improvements GIS Mapping | Fixed fee | Transferred Entity | L8220 | E31222 | Prairie Wind Transit Authority | 21.18% | 206100 | 38613.69 | 160077.87 | 6068.39 | 3920.35 | 43651.98 | 4237.94 | 4818.06 | 0 | 5038.29 | 0 | 5038.29 | 0 | 58.5 | 0 | 1733 | 14127 | 006Jo7fwhZcYIfKSw2 | FALSE
26-PC-44302 | Dove Canyon Cell Tower - Built Environment Survey | Fixed fee | Transferred Entity | L8220 | E31220 | Prairie Wind Pipeline Company | 44.46% | 90200 | 28689.27 | 67334.3 | 7698.24 | 2937.45 | 40102.92 | 5897.71 | 2873.28 | 0 | 11413.65 | 0 | 11413.65 | 0 | 24 | 0 | 389 | 14024 | 006bxQHGED5uJS55G3 | TRUE
| Total All Projects | [5 empty] | 0 | 270119100 | 133830111.46 | 190699414.58 | 3491807.91 | 1993227.52 | 137493343.96 | 15825569.98 | 1747151.56 | 0 | 3663449.46 | 216.96 | 3663666.42 | 0 | 30622.5 | 721.25 | 2240294

## _Calc (hidden)
TaskProjectID | isFirst | idx | TaskOverrun$ | TaskOverrunHrs | 12 | T2 header row
| 0 |  |  |  | 11 | OTC header row
0
| 0 |  |  |  | 0 | T2 col B = Task Project ID
| 0 |  |  |  | 0 | T2 col G = Contract Value
| 0 |  |  |  | 0 | T2 col I = Revised Budget
| 0 |  |  |  | 0 | T2 col N = Total Costs
| 0 |  |  |  | 0 | T2 col O = Budgeted Hours
| 0 |  |  |  | 0 | T2 col P = Actual Hours
| 0 |  |  |  | 0 | OTC col A = Project ID
| 0 |  |  |  | 0 | OTC col C = Billing type
| 0 |  |  |  | 0 | OTC col D = Project status
| 0 |  |  |  | 0 | OTC col E = Location
23-PC-30060 | 1 | 1 | 64609.23 | 2047.27 | 0 | OTC col F = Project manager
23-PC-30163 | 1 | 2 | 44.16 | 7.91
23-PC-30163 | 0 |  | 242.61 | 121.09 | 0 | FAILED CHECKS
23-PC-30307 | 1 | 3 | 0 | 256.69 | 1219 | project count
23-PC-30307 | 0 |  | 0 | 129.31
23-PC-30372 | 1 | 4 | 0 | 0
23-PC-30372 | 0 |  | 0 | 0
23-PC-30372 | 0 |  | 0 | 0
23-PC-30372 | 0 |  | 0 | 0
23-PC-30372 | 0 |  | 0 | 0
23-PC-30543 | 1 | 5 | 0 | 240.79
23-PC-30543 | 0 |  | 0 | 0
23-PC-30644 | 1 | 6 | 0 | 0
23-PC-30644 | 0 |  | 0 | 0
23-PC-30667 | 1 | 7 | 3375.55 | 93.19
23-PC-30667 | 0 |  | 6883.89 | 603.22
23-PC-30869 | 1 | 8 | 0 | 89.25
23-PC-30881 | 1 | 9 | 2667.67 | 0
23-PC-30933 | 1 | 10 | 0 | 0
23-PC-30933 | 0 |  | 0 | 0
23-PC-30933 | 0 |  | 0 | 0
23-PC-30933 | 0 |  | 0 | 0
23-PC-31003 | 1 | 11 | 0 | 0
23-PC-31003 | 0 |  | 0 | 0
23-PC-31042 | 1 | 12 | 0 | 0
23-PC-31042 | 0 |  | 0 | 0
23-PC-31076 | 1 | 13 | 0 | 0
23-PC-31344 | 1 | 14 | 0 | 0
23-PC-31344 | 0 |  | 0 | 0
23-PC-31344 | 0 |  | 0 | 0
23-PC-31344 | 0 |  | 0 | 0
23-PC-31374 | 1 | 15 | 3532.77 | 85.77
23-PC-31374 | 0 |  | 24661.25 | 0
23-PC-31374 | 0 |  | 6484.4 | 0
23-PC-31389 | 1 | 16 | 942.29 | 5.71
23-PC-31389 | 0 |  | 672.59 | 0
23-PC-31389 | 0 |  | 4028.06 | 0
23-PC-31389 | 0 |  | 644.74 | 0
23-PC-31405 | 1 | 17 | 0 | 0
23-PC-31405 | 0 |  | 0 | 0
23-PC-31405 | 0 |  | 0 | 22.37
23-PC-31405 | 0 |  | 0 | 0
23-PC-31604 | 1 | 18 | 16454.83 | 453
23-PC-31604 | 0 |  | 4867.31 | 164.44
23-PC-31604 | 0 |  | 5596.73 | 164.46
23-PC-31604 | 0 |  | 10463.34 | 149.58
23-PC-31765 | 1 | 19 | 0 | 0
23-PC-31765 | 0 |  | 0 | 0
23-PC-31765 | 0 |  | 0 | 0
23-PC-31765 | 0 |  | 0 | 0
23-PC-31765 | 0 |  | 0 | 0
23-PC-31769 | 1 | 20 | 1661.77 | 40.38
23-PC-31769 | 0 |  | 610.26 | 42.05
23-PC-31769 | 0 |  | 489.13 | 15.16
23-PC-31812 | 1 | 21 | 0 | 0
23-PC-31812 | 0 |  | 0 | 0
23-PC-31812 | 0 |  | 0 | 0
23-PC-31812 | 0 |  | 0 | 0
23-PC-31844 | 1 | 22 | 9908.26 | 0
23-PC-31844 | 0 |  | 2750.98 | 0
23-PC-31844 | 0 |  | 5218.52 | 0
23-PC-31844 | 0 |  | 1400.4 | 0
23-PC-31944 | 1 | 23 | 2203.04 | 107.67
23-PC-31944 | 0 |  | 1721.89 | 80.15
23-PC-31944 | 0 |  | 6625.93 | 200.92
23-PC-31944 | 0 |  | 2397.95 | 74.44
23-PC-31976 | 1 | 24 | 0 | 0
23-PC-32015 | 1 | 25 | 0 | 0
23-PC-32015 | 0 |  | 0 | 0
23-PC-32015 | 0 |  | 0 | 0
23-PC-32015 | 0 |  | 0 | 0
23-PC-32015 | 0 |  | 0 | 0
23-PC-32135 | 1 | 26 | 0 | 0
23-PC-32135 | 0 |  | 0 | 0
23-PC-32135 | 0 |  | 0 | 0
23-PC-32135 | 0 |  | 0 | 0
23-PC-32135 | 0 |  | 0 | 0
23-PC-32278 | 1 | 27 | 0 | 0
23-PC-32329 | 1 | 28 | 0 | 818.85
23-PC-32443 | 1 | 29 | 0 | 0
23-PC-32443 | 0 |  | 0 | 76.84
23-PC-32443 | 0 |  | 173.12 | 2.5
23-PC-32474 | 1 | 30 | 222.5 | 0
23-PC-32474 | 0 |  | 686.49 | 20.63
23-PC-32474 | 0 |  | 758.95 | 0
23-PC-32474 | 0 |  | 191.02 | 9.03
23-PC-32520 | 1 | 31 | 0 | 59.42
23-PC-32520 | 0 |  | 0 | 0
23-PC-32520 | 0 |  | 0 | 0
23-PC-32635 | 1 | 32 | 574.25 | 0
23-PC-32635 | 0 |  | 495.87 | 0
23-PC-32635 | 0 |  | 765.62 | 0
23-PC-32635 | 0 |  | 521.83 | 8.95
23-PC-32635 | 0 |  | 321.42 | 0
23-PC-33001 | 1 | 33 | 0 | 0
23-PC-33001 | 0 |  | 0 | 0
23-PC-33043 | 1 | 34 | 7431.52 | 271.11
23-PC-33043 | 0 |  | 26421.53 | 271.21
23-PC-33043 | 0 |  | 9294.08 | 202.04
23-PC-33043 | 0 |  | 7280.18 | 192.25
23-PC-33043 | 0 |  | 7454.68 | 174.41
23-PC-33070 | 1 | 35 | 0 | 0
23-PC-33070 | 0 |  | 0 | 32.49
23-PC-33070 | 0 |  | 0 | 0
23-PC-33151 | 1 | 36 | 0 | 171.2
23-PC-33151 | 0 |  | 0 | 262.35
23-PC-33193 | 1 | 37 | 0 | 2.26
23-PC-33193 | 0 |  | 0 | 10.69
23-PC-33193 | 0 |  | 0 | 16.61
23-PC-33218 | 1 | 38 | 0 | 0
23-PC-33299 | 1 | 39 | 0 | 113.71
23-PC-33395 | 1 | 40 | 1988.14 | 53.68
23-PC-33395 | 0 |  | 7809.61 | 397.04
23-PC-33395 | 0 |  | 3197.37 | 147.85
23-PC-33395 | 0 |  | 16786.28 | 960.51
23-PC-33395 | 0 |  | 6950.06 | 314.49
23-PC-33428 | 1 | 41 | 11037.35 | 145.48
23-PC-33428 | 0 |  | 40382.47 | 570.02
23-PC-33428 | 0 |  | 11242.6 | 164.05
23-PC-33471 | 1 | 42 | 0 | 0
23-PC-33471 | 0 |  | 0 | 0
23-PC-33471 | 0 |  | 0 | 0
23-PC-33471 | 0 |  | 0 | 0
23-PC-33551 | 1 | 43 | 0 | 0
23-PC-33551 | 0 |  | 0 | 0
23-PC-33551 | 0 |  | 0 | 0
23-PC-33551 | 0 |  | 0 | 0
23-PC-33551 | 0 |  | 0 | 0
23-PC-33553 | 1 | 44 | 1306.51 | 0
23-PC-33605 | 1 | 45 | 0 | 0
23-PC-33605 | 0 |  | 0 | 0
23-PC-33695 | 1 | 46 | 0 | 0
23-PC-33803 | 1 | 47 | 0 | 0
23-PC-33803 | 0 |  | 0 | 0
23-PC-33803 | 0 |  | 0 | 0
23-PC-33803 | 0 |  | 0 | 0
23-PC-33803 | 0 |  | 0 | 0
23-PC-33858 | 1 | 48 | 0 | 0
23-PC-33858 | 0 |  | 0 | 0
23-PC-33858 | 0 |  | 0 | 0
23-PC-33858 | 0 |  | 0 | 0
23-PC-33879 | 1 | 49 | 0 | 0
23-PC-33879 | 0 |  | 0 | 0
23-PC-33879 | 0 |  | 0 | 0
23-PC-33879 | 0 |  | 0 | 0
23-PC-33998 | 1 | 50 | 0 | 0
23-PC-33998 | 0 |  | 0 | 0
23-PC-33998 | 0 |  | 0 | 0
23-PC-33998 | 0 |  | 0 | 0
23-PC-33998 | 0 |  | 0 | 0
23-PC-34054 | 1 | 51 | 0 | 0
23-PC-34054 | 0 |  | 0 | 0
23-PC-34054 | 0 |  | 0 | 0
23-PC-34135 | 1 | 52 | 13064.51 | 0
23-PC-34171 | 1 | 53 | 0 | 0
23-PC-34171 | 0 |  | 0 | 0
23-PC-34171 | 0 |  | 0 | 0
23-PC-34229 | 1 | 54 | 0 | 63.39
23-PC-34229 | 0 |  | 0 | 0
23-PC-34353 | 1 | 55 | 0 | 0
23-PC-34353 | 0 |  | 0 | 0
23-PC-34403 | 1 | 56 | 0 | 0
23-PC-34440 | 1 | 57 | 0 | 703.49
23-PC-34440 | 0 |  | 0 | 223.38
23-PC-34473 | 1 | 58 | 0 | 0
23-PC-34473 | 0 |  | 0 | 0
23-PC-34510 | 1 | 59 | 0 | 129.04
23-PC-34510 | 0 |  | 0 | 22.75
23-PC-34510 | 0 |  | 0 | 66.58
23-PC-34522 | 1 | 60 | 0 | 0
23-PC-34522 | 0 |  | 0 | 0
23-PC-34567 | 1 | 61 | 0 | 0
23-PC-34567 | 0 |  | 0 | 0
23-PC-34567 | 0 |  | 0 | 0
23-PC-34745 | 1 | 62 | 0 | 626.82
23-PC-34789 | 1 | 63 | 0 | 3.6
23-PC-34789 | 0 |  | 0 | 0
23-PC-34789 | 0 |  | 0 | 0
23-PC-34811 | 1 | 64 | 0 | 0
23-PC-34811 | 0 |  | 0 | 0
23-PC-34811 | 0 |  | 0 | 0
23-PC-34811 | 0 |  | 0 | 0
23-PC-34826 | 1 | 65 | 0 | 0
23-PC-34891 | 1 | 66 | 0 | 0.24
23-PC-34891 | 0 |  | 0 | 15.33
23-PC-34891 | 0 |  | 0 | 4.56
23-PC-34891 | 0 |  | 0 | 12.41
23-PC-34902 | 1 | 67 | 0 | 0
23-PC-34939 | 1 | 68 | 0 | 4.5
23-PC-34939 | 0 |  | 0 | 7.14
23-PC-34939 | 0 |  | 0 | 22.65
23-PC-34939 | 0 |  | 0 | 0
23-PC-34939 | 0 |  | 0 | 12.27
23-PC-34947 | 1 | 69 | 0 | 0
23-PC-35003 | 1 | 70 | 0 | 0
23-PC-35098 | 1 | 71 | 0 | 0
23-PC-35098 | 0 |  | 0 | 0
23-PC-35098 | 0 |  | 0 | 8.25
23-PC-35098 | 0 |  | 0 | 0
23-PC-35126 | 1 | 72 | 0 | 0
23-PC-35126 | 0 |  | 0 | 0
23-PC-35126 | 0 |  | 0 | 0
23-PC-35126 | 0 |  | 0 | 0
23-PC-35126 | 0 |  | 0 | 0
23-PC-35176 | 1 | 73 | 0 | 0
23-PC-35225 | 1 | 74 | 0 | 0
23-PC-35225 | 0 |  | 0 | 60.88
23-PC-35225 | 0 |  | 0 | 734.08
23-PC-35225 | 0 |  | 0 | 0
23-PC-35425 | 1 | 75 | 0 | 0
23-PC-35425 | 0 |  | 0 | 0
23-PC-35486 | 1 | 76 | 0 | 0
23-PC-35486 | 0 |  | 0 | 0
23-PC-35486 | 0 |  | 0 | 0
23-PC-35533 | 1 | 77 | 0 | 0
23-PC-35533 | 0 |  | 0 | 9.6
23-PC-35533 | 0 |  | 0 | 0
23-PC-35568 | 1 | 78 | 0 | 0
23-PC-35568 | 0 |  | 0 | 0
23-PC-35682 | 1 | 79 | 0 | 0
23-PC-35682 | 0 |  | 0 | 0
23-PC-35682 | 0 |  | 0 | 0
23-PC-35682 | 0 |  | 0 | 0
23-PC-35682 | 0 |  | 0 | 0
23-PC-35715 | 1 | 80 | 0 | 0
23-PC-35715 | 0 |  | 0 | 0
23-PC-35715 | 0 |  | 0 | 0
23-PC-36063 | 1 | 81 | 0 | 15.51
23-PC-36108 | 1 | 82 | 0 | 0
23-PC-36231 | 1 | 83 | 7023.19 | 182.8
23-PC-36231 | 0 |  | 13257.9 | 180.68
23-PC-36231 | 0 |  | 43480.69 | 519.32
23-PC-36231 | 0 |  | 10586.64 | 134.82
23-PC-36231 | 0 |  | 11706.61 | 257.89
23-PC-36385 | 1 | 84 | 0 | 23.95
23-PC-36385 | 0 |  | 0 | 11.46
23-PC-36385 | 0 |  | 0 | 10.46
23-PC-36385 | 0 |  | 0 | 220.87
23-PC-36422 | 1 | 85 | 115.14 | 33.09
23-PC-36422 | 0 |  | 283.77 | 54.46
23-PC-36422 | 0 |  | 194.77 | 20.07
23-PC-36422 | 0 |  | 236.85 | 50.97
23-PC-36426 | 1 | 86 | 0 | 0
23-PC-36426 | 0 |  | 0 | 92.1
23-PC-36530 | 1 | 87 | 0 | 0
23-PC-36530 | 0 |  | 0 | 4.27
23-PC-36530 | 0 |  | 0 | 9.66
23-PC-36530 | 0 |  | 0 | 0
23-PC-36530 | 0 |  | 0 | 30.53
23-PC-36687 | 1 | 88 | 0 | 82.3
23-PC-36687 | 0 |  | 0 | 209.18
23-PC-36687 | 0 |  | 0 | 93.03
23-PC-36687 | 0 |  | 0 | 54.6
23-PC-36734 | 1 | 89 | 0 | 136.27
23-PC-36734 | 0 |  | 9.9 | 0.25
23-PC-36776 | 1 | 90 | 0 | 0
23-PC-36776 | 0 |  | 0 | 0
23-PC-36776 | 0 |  | 0 | 0
23-PC-37105 | 1 | 91 | 0 | 0
23-PC-37105 | 0 |  | 607.19 | 26.38
23-PC-37105 | 0 |  | 1184.1 | 14.25
23-PC-37245 | 1 | 92 | 0 | 0
23-PC-37245 | 0 |  | 0 | 0
23-PC-37245 | 0 |  | 0 | 0
23-PC-37245 | 0 |  | 0 | 0
23-PC-37245 | 0 |  | 0 | 0
23-PC-37301 | 1 | 93 | 347.73 | 16.8
23-PC-37301 | 0 |  | 731 | 79.67
23-PC-37301 | 0 |  | 689.99 | 53.95
23-PC-37301 | 0 |  | 181.03 | 21.46
23-PC-37568 | 1 | 94 | 0 | 0
23-PC-37568 | 0 |  | 0 | 0
23-PC-37568 | 0 |  | 0 | 0
23-PC-37590 | 1 | 95 | 0 | 0
23-PC-37590 | 0 |  | 0 | 1.26
23-PC-37590 | 0 |  | 0 | 0
23-PC-37642 | 1 | 96 | 0 | 109.61
23-PC-37642 | 0 |  | 0 | 46.21
23-PC-37642 | 0 |  | 0 | 76.05
23-PC-37648 | 1 | 97 | 0 | 4.27
23-PC-37648 | 0 |  | 0 | 131.95
23-PC-37740 | 1 | 98 | 0 | 0
23-PC-37740 | 0 |  | 0 | 0
23-PC-37740 | 0 |  | 0 | 0
23-PC-37763 | 1 | 99 | 0 | 0
23-PC-37763 | 0 |  | 0 | 0
23-PC-38089 | 1 | 100 | 0 | 0
23-PC-38089 | 0 |  | 0 | 0
23-PC-38089 | 0 |  | 0 | 0
23-PC-38159 | 1 | 101 | 469.46 | 0
23-PC-38159 | 0 |  | 319.41 | 0
23-PC-38159 | 0 |  | 301.92 | 0
23-PC-38231 | 1 | 102 | 0 | 493.7
23-PC-38246 | 1 | 103 | 0 | 0
23-PC-38246 | 0 |  | 0 | 0
23-PC-38246 | 0 |  | 0 | 0
23-PC-38246 | 0 |  | 0 | 31.91
23-PC-38498 | 1 | 104 | 0 | 0
23-PC-38498 | 0 |  | 0 | 84.19
23-PC-38498 | 0 |  | 0 | 6.19
23-PC-38498 | 0 |  | 0 | 0
23-PC-38520 | 1 | 105 | 0 | 0
23-PC-38520 | 0 |  | 0 | 0
23-PC-38666 | 1 | 106 | 0 | 0
23-PC-38666 | 0 |  | 0 | 0
23-PC-38666 | 0 |  | 0 | 0
23-PC-38666 | 0 |  | 0 | 0
23-PC-38666 | 0 |  | 0 | 0
23-PC-38759 | 1 | 107 | 2894.15 | 105.16
23-PC-38759 | 0 |  | 630.61 | 26.71
23-PC-38849 | 1 | 108 | 0 | 0
23-PC-39011 | 1 | 109 | 0 | 0
23-PC-39011 | 0 |  | 0 | 71.63
23-PC-39063 | 1 | 110 | 0 | 0
23-PC-39111 | 1 | 111 | 4726.62 | 1076.57
23-PC-39111 | 0 |  | 6292.08 | 1765.35
23-PC-39135 | 1 | 112 | 0 | 7.51
23-PC-39135 | 0 |  | 0 | 0
23-PC-39280 | 1 | 113 | 0 | 0
23-PC-39280 | 0 |  | 0 | 0
23-PC-39323 | 1 | 114 | 0 | 0
23-PC-39323 | 0 |  | 0 | 0
23-PC-39323 | 0 |  | 0 | 334.16
23-PC-39323 | 0 |  | 0 | 0
23-PC-39502 | 1 | 115 | 71675.69 | 2797.13
23-PC-39608 | 1 | 116 | 0 | 0
23-PC-39608 | 0 |  | 0 | 0
23-PC-39608 | 0 |  | 0 | 0
23-PC-39608 | 0 |  | 0 | 0
23-PC-39608 | 0 |  | 0 | 0
23-PC-39840 | 1 | 117 | 0 | 0
23-PC-39856 | 1 | 118 | 0 | 0
23-PC-39857 | 1 | 119 | 0 | 0
23-PC-39857 | 0 |  | 0 | 0
23-PC-39857 | 0 |  | 0 | 0
23-PC-39918 | 1 | 120 | 0 | 25.55
23-PC-39918 | 0 |  | 0 | 0
23-PC-39918 | 0 |  | 0 | 1.26
23-PC-39918 | 0 |  | 0 | 52.6
23-PC-39918 | 0 |  | 0 | 29.74
23-PC-39996 | 1 | 121 | 0 | 0
23-PC-39996 | 0 |  | 0 | 0
23-PC-39996 | 0 |  | 0 | 0
23-PC-40028 | 1 | 122 | 0 | 0
23-PC-40028 | 0 |  | 0 | 0
23-PC-40028 | 0 |  | 0 | 0
23-PC-40028 | 0 |  | 0 | 0
23-PC-40052 | 1 | 123 | 0 | 1.76
23-PC-40052 | 0 |  | 0 | 30.54
23-PC-40052 | 0 |  | 0 | 0
23-PC-40052 | 0 |  | 0 | 0
23-PC-40052 | 0 |  | 0 | 58.91
23-PC-40052 | 0 |  | 316.41 | 8
23-PC-40150 | 1 | 124 | 0 | 0
23-PC-40150 | 0 |  | 0 | 0
23-PC-40150 | 0 |  | 0 | 0
23-PC-40150 | 0 |  | 0 | 0
23-PC-40150 | 0 |  | 0 | 0
23-PC-40150 | 0 |  | 98.28 | 2.5
23-PC-40387 | 1 | 125 | 0 | 0
23-PC-40387 | 0 |  | 0 | 0
23-PC-40387 | 0 |  | 0 | 0
23-PC-40402 | 1 | 126 | 0 | 0
23-PC-40402 | 0 |  | 0 | 0
23-PC-40406 | 1 | 127 | 0 | 0
23-PC-40406 | 0 |  | 0 | 0
23-PC-40406 | 0 |  | 0 | 0
23-PC-40406 | 0 |  | 0 | 0
23-PC-40406 | 0 |  | 0 | 0
23-PC-40469 | 1 | 128 | 0 | 0
23-PC-40469 | 0 |  | 0 | 0
23-PC-40469 | 0 |  | 0 | 0
23-PC-40469 | 0 |  | 0 | 0
23-PC-40469 | 0 |  | 0 | 0
23-PC-40493 | 1 | 129 | 0 | 0
23-PC-40519 | 1 | 130 | 0 | 440.63
23-PC-40537 | 1 | 131 | 936.13 | 87.52
23-PC-40537 | 0 |  | 2180.31 | 159.12
23-PC-40537 | 0 |  | 1373.18 | 79.25
23-PC-40627 | 1 | 132 | 0 | 0
23-PC-40627 | 0 |  | 0 | 0
23-PC-40627 | 0 |  | 0 | 0
23-PC-40627 | 0 |  | 0 | 0
23-PC-40627 | 0 |  | 0 | 0
23-PC-40688 | 1 | 133 | 0 | 0
23-PC-40688 | 0 |  | 0 | 0
23-PC-40688 | 0 |  | 0 | 0
23-PC-40688 | 0 |  | 0 | 0
23-PC-40688 | 0 |  | 0 | 0
23-PC-40963 | 1 | 134 | 0 | 22.4
23-PC-40963 | 0 |  | 0 | 95.43
23-PC-41134 | 1 | 135 | 887.88 | 30.76
23-PC-41134 | 0 |  | 604.01 | 0
23-PC-41134 | 0 |  | 1922.03 | 66.72
23-PC-41134 | 0 |  | 1820.16 | 0
23-PC-41207 | 1 | 136 | 0 | 0
23-PC-41207 | 0 |  | 0 | 0
23-PC-41285 | 1 | 137 | 4586.9 | 0
23-PC-41285 | 0 |  | 2667.48 | 0
23-PC-41285 | 0 |  | 862.93 | 198.94
23-PC-41314 | 1 | 138 | 0 | 0
23-PC-41361 | 1 | 139 | 7340.14 | 479.92
23-PC-41361 | 0 |  | 11006.48 | 340.81
23-PC-41361 | 0 |  | 2500.29 | 203.38
23-PC-41378 | 1 | 140 | 0 | 0
23-PC-41378 | 0 |  | 0 | 0
23-PC-41378 | 0 |  | 0 | 0
23-PC-41378 | 0 |  | 0 | 0
23-PC-41378 | 0 |  | 0 | 0
23-PC-41424 | 1 | 141 | 0 | 0
23-PC-41424 | 0 |  | 0 | 0
23-PC-41424 | 0 |  | 0 | 0
23-PC-41424 | 0 |  | 0 | 0
23-PC-41429 | 1 | 142 | 0 | 0
23-PC-41429 | 0 |  | 0 | 0
23-PC-41429 | 0 |  | 0 | 0
23-PC-41429 | 0 |  | 0 | 0
23-PC-41429 | 0 |  | 0 | 0
23-PC-41602 | 1 | 143 | 0 | 21.19
23-PC-41602 | 0 |  | 0 | 0
23-PC-41613 | 1 | 144 | 0 | 112.31
23-PC-41613 | 0 |  | 0 | 0
23-PC-41613 | 0 |  | 0 | 0
23-PC-41613 | 0 |  | 0 | 57.9
23-PC-41613 | 0 |  | 0 | 0
23-PC-41787 | 1 | 145 | 0 | 0
23-PC-41787 | 0 |  | 0 | 0
23-PC-41787 | 0 |  | 0 | 0
23-PC-41787 | 0 |  | 0 | 0
23-PC-41802 | 1 | 146 | 0 | 0
23-PC-41802 | 0 |  | 0 | 0
23-PC-41802 | 0 |  | 0 | 0
23-PC-41827 | 1 | 147 | 0 | 0
23-PC-41827 | 0 |  | 0 | 0
23-PC-41827 | 0 |  | 0 | 66.3
23-PC-41827 | 0 |  | 0 | 0
23-PC-41897 | 1 | 148 | 31.43 | 53.97
23-PC-41934 | 1 | 149 | 0 | 0
23-PC-41934 | 0 |  | 0 | 0
23-PC-41934 | 0 |  | 0 | 0
23-PC-41934 | 0 |  | 0 | 0
23-PC-41934 | 0 |  | 0 | 0
23-PC-42054 | 1 | 150 | 0 | 77.45
23-PC-42054 | 0 |  | 0 | 26.14
23-PC-42154 | 1 | 151 | 0 | 2.37
23-PC-42154 | 0 |  | 0 | 4.17
23-PC-42199 | 1 | 152 | 0 | 0
23-PC-42199 | 0 |  | 0 | 0
23-PC-42199 | 0 |  | 0 | 0
23-PC-42237 | 1 | 153 | 0 | 0
23-PC-42237 | 0 |  | 0 | 0
23-PC-42237 | 0 |  | 0 | 0
23-PC-42377 | 1 | 154 | 0 | 0
23-PC-42377 | 0 |  | 0 | 0
23-PC-42377 | 0 |  | 0 | 0
23-PC-42377 | 0 |  | 0 | 0
23-PC-42377 | 0 |  | 0 | 0
23-PC-42405 | 1 | 155 | 142473.1 | 4224.07
23-PC-42451 | 1 | 156 | 0 | 0
23-PC-42451 | 0 |  | 0 | 15
23-PC-42496 | 1 | 157 | 0 | 76.55
23-PC-42496 | 0 |  | 0 | 143.59
23-PC-42496 | 0 |  | 0 | 110.56
23-PC-42496 | 0 |  | 0 | 0
23-PC-42496 | 0 |  | 0 | 116.05
23-PC-42771 | 1 | 158 | 0 | 0
23-PC-42771 | 0 |  | 0 | 0
23-PC-42771 | 0 |  | 0 | 0
23-PC-42907 | 1 | 159 | 0 | 0
23-PC-42907 | 0 |  | 0 | 0
23-PC-42981 | 1 | 160 | 0 | 0
23-PC-43008 | 1 | 161 | 0 | 0
23-PC-43008 | 0 |  | 0 | 6.01
23-PC-43158 | 1 | 162 | 0 | 0
23-PC-43158 | 0 |  | 0 | 0
23-PC-43209 | 1 | 163 | 0 | 0
23-PC-43209 | 0 |  | 0 | 0
23-PC-43209 | 0 |  | 0 | 0
23-PC-43238 | 1 | 164 | 0 | 0
23-PC-43238 | 0 |  | 0 | 0
23-PC-43238 | 0 |  | 0 | 0
23-PC-43238 | 0 |  | 0 | 0
23-PC-43238 | 0 |  | 0 | 0
23-PC-43356 | 1 | 165 | 0 | 0
23-PC-43356 | 0 |  | 0 | 0
23-PC-43356 | 0 |  | 0 | 0
23-PC-43408 | 1 | 166 | 0 | 0
23-PC-43408 | 0 |  | 0 | 0
23-PC-43408 | 0 |  | 0 | 0
23-PC-43477 | 1 | 167 | 459.03 | 0
23-PC-43477 | 0 |  | 574.78 | 0
23-PC-43477 | 0 |  | 1203.83 | 0
23-PC-43477 | 0 |  | 1806.18 | 0
23-PC-43477 | 0 |  | 2514.35 | 0
23-PC-43564 | 1 | 168 | 0 | 0
23-PC-43564 | 0 |  | 0 | 0
23-PC-43564 | 0 |  | 0 | 0
23-PC-43564 | 0 |  | 0 | 0
23-PC-43564 | 0 |  | 0 | 0
23-PC-43612 | 1 | 169 | 0 | 0
23-PC-43612 | 0 |  | 0 | 0
23-PC-43612 | 0 |  | 0 | 0
23-PC-43692 | 1 | 170 | 0 | 228.93
23-PC-43788 | 1 | 171 | 0 | 81.14
23-PC-43811 | 1 | 172 | 0 | 0
23-PC-43829 | 1 | 173 | 0 | 0
23-PC-43829 | 0 |  | 0 | 30.48
23-PC-44023 | 1 | 174 | 0 | 115.44
23-PC-44023 | 0 |  | 0 | 201.23
23-PC-44023 | 0 |  | 0 | 3.16
23-PC-44147 | 1 | 175 | 7028.5 | 0
23-PC-44147 | 0 |  | 3212.45 | 0
23-PC-44147 | 0 |  | 6052.28 | 0
23-PC-44147 | 0 |  | 4625.83 | 0
23-PC-44147 | 0 |  | 1997.64 | 0
24-PC-30017 | 1 | 176 | 502.92 | 0
24-PC-30017 | 0 |  | 1132.32 | 0
24-PC-30017 | 0 |  | 961.47 | 0
24-PC-30017 | 0 |  | 1154.65 | 0
24-PC-30233 | 1 | 177 | 5538.75 | 67.37
24-PC-30233 | 0 |  | 7111.77 | 0
24-PC-30233 | 0 |  | 10841.95 | 146.64
24-PC-30233 | 0 |  | 8954.17 | 46.47
24-PC-30233 | 0 |  | 1718.26 | 33.5
24-PC-30378 | 1 | 178 | 0 | 0
24-PC-30448 | 1 | 179 | 0 | 0
24-PC-30448 | 0 |  | 0 | 0
24-PC-30509 | 1 | 180 | 0 | 0
24-PC-30620 | 1 | 181 | 0 | 0
24-PC-30620 | 0 |  | 0 | 0
24-PC-30620 | 0 |  | 0 | 0
24-PC-30620 | 0 |  | 0 | 0
24-PC-30679 | 1 | 182 | 3588.88 | 83.05
24-PC-30679 | 0 |  | 837.89 | 12.9
24-PC-30679 | 0 |  | 592.85 | 13.25
24-PC-30751 | 1 | 183 | 0 | 0
24-PC-30751 | 0 |  | 0 | 0
24-PC-30843 | 1 | 184 | 0 | 0
24-PC-30843 | 0 |  | 0 | 0
24-PC-30843 | 0 |  | 0 | 0
24-PC-30843 | 0 |  | 0 | 8.54
24-PC-30850 | 1 | 185 | 0 | 0
24-PC-30850 | 0 |  | 0 | 0
24-PC-30850 | 0 |  | 0 | 0
24-PC-31134 | 1 | 186 | 0 | 0
24-PC-31134 | 0 |  | 0 | 7.78
24-PC-31134 | 0 |  | 0 | 0
24-PC-31134 | 0 |  | 0 | 0
24-PC-31224 | 1 | 187 | 4958.7 | 170.48
24-PC-31224 | 0 |  | 1507.72 | 27.24
24-PC-31224 | 0 |  | 4849.6 | 161.59
24-PC-31267 | 1 | 188 | 0 | 0
24-PC-31267 | 0 |  | 0 | 0
24-PC-31267 | 0 |  | 0 | 0
24-PC-31267 | 0 |  | 0 | 0
24-PC-31282 | 1 | 189 | 7629.82 | 187.09
24-PC-31358 | 1 | 190 | 0 | 500.12
24-PC-31358 | 0 |  | 0 | 5.22
24-PC-31358 | 0 |  | 0 | 95.98
24-PC-31434 | 1 | 191 | 0 | 0.12
24-PC-31434 | 0 |  | 0 | 6.8
24-PC-31434 | 0 |  | 0 | 2.95
24-PC-31434 | 0 |  | 0 | 0.9
24-PC-31453 | 1 | 192 | 0 | 0
24-PC-31453 | 0 |  | 0 | 0
24-PC-31453 | 0 |  | 0 | 8.53
24-PC-31453 | 0 |  | 0 | 0
24-PC-31453 | 0 |  | 0 | 0
24-PC-31503 | 1 | 193 | 3305.01 | 7.13
24-PC-31503 | 0 |  | 4427.76 | 88.74
24-PC-31503 | 0 |  | 3215.1 | 6.77
24-PC-31514 | 1 | 194 | 812.83 | 0
24-PC-31514 | 0 |  | 2950.97 | 0
24-PC-31514 | 0 |  | 2234.93 | 0
24-PC-31514 | 0 |  | 3646.71 | 0
24-PC-31534 | 1 | 195 | 982.35 | 32.95
24-PC-31534 | 0 |  | 3477.77 | 154.81
24-PC-31534 | 0 |  | 6052.24 | 99.34
24-PC-31534 | 0 |  | 5861.69 | 172.33
24-PC-31534 | 0 |  | 2832 | 83.33
24-PC-31663 | 1 | 196 | 0 | 6.76
24-PC-31663 | 0 |  | 0 | 6.56
24-PC-31663 | 0 |  | 0 | 79.63
24-PC-31663 | 0 |  | 0 | 8.81
24-PC-31663 | 0 |  | 0 | 0
24-PC-31750 | 1 | 197 | 2599.99 | 0
24-PC-31750 | 0 |  | 0 | 37.83
24-PC-31750 | 0 |  | 0 | 0
24-PC-31750 | 0 |  | 0 | 3.49
24-PC-31750 | 0 |  | 0 | 0
24-PC-31750 | 0 |  | 2345.13 | 27.5
24-PC-31819 | 1 | 198 | 0 | 0
24-PC-31819 | 0 |  | 0 | 0
24-PC-31819 | 0 |  | 0 | 0
24-PC-31819 | 0 |  | 0 | 0
24-PC-31857 | 1 | 199 | 0 | 0
24-PC-31857 | 0 |  | 0 | 0
24-PC-31857 | 0 |  | 0 | 0
24-PC-31857 | 0 |  | 24.57 | 0.5
24-PC-31924 | 1 | 200 | 0 | 0
24-PC-32088 | 1 | 201 | 0 | 0
24-PC-32088 | 0 |  | 0 | 0
24-PC-32201 | 1 | 202 | 6831.69 | 37.93
24-PC-32201 | 0 |  | 1892.13 | 19.98
24-PC-32201 | 0 |  | 2809.42 | 57.49
24-PC-32201 | 0 |  | 3567.86 | 28.4
24-PC-32201 | 0 |  | 6267.49 | 114.51
24-PC-32201 | 0 |  | 1430.77 | 27.75
24-PC-32209 | 1 | 203 | 0 | 4.15
24-PC-32209 | 0 |  | 467.99 | 6.61
24-PC-32209 | 0 |  | 81.71 | 1
24-PC-32210 | 1 | 204 | 0 | 0
24-PC-32210 | 0 |  | 0 | 0
24-PC-32210 | 0 |  | 0 | 0
24-PC-32210 | 0 |  | 0 | 0
24-PC-32210 | 0 |  | 0 | 0
24-PC-32270 | 1 | 205 | 0 | 0
24-PC-32270 | 0 |  | 0 | 0
24-PC-32270 | 0 |  | 0 | 0
24-PC-32270 | 0 |  | 0 | 0
24-PC-32270 | 0 |  | 0 | 0
24-PC-32479 | 1 | 206 | 0 | 0
24-PC-32479 | 0 |  | 0 | 0
24-PC-32479 | 0 |  | 0 | 0
24-PC-32479 | 0 |  | 42.56 | 1
24-PC-32591 | 1 | 207 | 3895.35 | 126.14
24-PC-32591 | 0 |  | 1808.06 | 54.03
24-PC-32591 | 0 |  | 818.24 | 12.04
24-PC-32640 | 1 | 208 | 0 | 0
24-PC-32640 | 0 |  | 0 | 0
24-PC-32640 | 0 |  | 0 | 0
24-PC-32640 | 0 |  | 0 | 0
24-PC-32640 | 0 |  | 0 | 0
24-PC-32647 | 1 | 209 | 11622.81 | 101.9
24-PC-32647 | 0 |  | 8611 | 56.89
24-PC-32647 | 0 |  | 0 | 0
24-PC-32647 | 0 |  | 1082.66 | 13.25
24-PC-32688 | 1 | 210 | 0 | 22.15
24-PC-32688 | 0 |  | 0 | 0
24-PC-32688 | 0 |  | 0 | 0
24-PC-32688 | 0 |  | 0 | 65.98
24-PC-32954 | 1 | 211 | 0 | 0
24-PC-32954 | 0 |  | 0 | 0
24-PC-32954 | 0 |  | 0 | 0
24-PC-32954 | 0 |  | 0 | 0
24-PC-33384 | 1 | 212 | 0 | 72.28
24-PC-33384 | 0 |  | 0 | 167.36
24-PC-33384 | 0 |  | 0 | 0
24-PC-33394 | 1 | 213 | 0 | 0
24-PC-33394 | 0 |  | 0 | 0
24-PC-33394 | 0 |  | 0 | 0
24-PC-33394 | 0 |  | 0 | 0
24-PC-33394 | 0 |  | 0 | 0
24-PC-33448 | 1 | 214 | 0 | 0
24-PC-33448 | 0 |  | 0 | 62.63
24-PC-33448 | 0 |  | 0 | 282.98
24-PC-33448 | 0 |  | 0 | 241.76
24-PC-33448 | 0 |  | 0 | 85.32
24-PC-33448 | 0 |  | 279.17 | 6.75
24-PC-33531 | 1 | 215 | 0 | 0
24-PC-33531 | 0 |  | 0 | 0
24-PC-33531 | 0 |  | 0 | 0
24-PC-33531 | 0 |  | 0 | 0
24-PC-33531 | 0 |  | 0 | 0
24-PC-33575 | 1 | 216 | 0 | 0
24-PC-33575 | 0 |  | 0 | 0
24-PC-33575 | 0 |  | 1630.07 | 36.75
24-PC-33822 | 1 | 217 | 0 | 20.85
24-PC-33822 | 0 |  | 0 | 4.44
24-PC-33822 | 0 |  | 0 | 13.71
24-PC-33822 | 0 |  | 4982.02 | 89.14
24-PC-33822 | 0 |  | 0 | 5.16
24-PC-33822 | 0 |  | 76.81 | 1
24-PC-33927 | 1 | 218 | 0 | 0
24-PC-33927 | 0 |  | 114.33 | 1.5
24-PC-33981 | 1 | 219 | 0 | 0
24-PC-33981 | 0 |  | 0 | 0
24-PC-33981 | 0 |  | 0 | 0
24-PC-33981 | 0 |  | 0 | 0
24-PC-33981 | 0 |  | 19.41 | 0.25
24-PC-33985 | 1 | 220 | 0 | 0
24-PC-33985 | 0 |  | 0 | 11.03
24-PC-33985 | 0 |  | 0 | 19.26
24-PC-34015 | 1 | 221 | 0 | 0
24-PC-34015 | 0 |  | 0 | 0
24-PC-34015 | 0 |  | 0 | 0
24-PC-34211 | 1 | 222 | 0 | 0
24-PC-34211 | 0 |  | 0 | 0
24-PC-34211 | 0 |  | 0 | 15.67
24-PC-34211 | 0 |  | 0 | 2.16
24-PC-34211 | 0 |  | 0 | 8.15
24-PC-34263 | 1 | 223 | 0 | 0
24-PC-34263 | 0 |  | 0 | 23.28
24-PC-34263 | 0 |  | 0 | 0
24-PC-34263 | 0 |  | 0 | 0
24-PC-34263 | 0 |  | 0 | 0
24-PC-34274 | 1 | 224 | 4905.26 | 279.55
24-PC-34274 | 0 |  | 4156.65 | 168.2
24-PC-34320 | 1 | 225 | 0 | 1.56
24-PC-34320 | 0 |  | 0 | 0
24-PC-34320 | 0 |  | 0 | 37.32
24-PC-34320 | 0 |  | 0 | 0
24-PC-34320 | 0 |  | 0 | 114.08
24-PC-34330 | 1 | 226 | 0 | 0
24-PC-34330 | 0 |  | 0 | 0
24-PC-34330 | 0 |  | 0 | 0
24-PC-34330 | 0 |  | 0 | 0
24-PC-34330 | 0 |  | 0 | 0
24-PC-34422 | 1 | 227 | 21875.39 | 0
24-PC-34422 | 0 |  | 6359.24 | 0
24-PC-34422 | 0 |  | 3576.39 | 0
24-PC-34458 | 1 | 228 | 519.88 | 12.57
24-PC-34458 | 0 |  | 2668.13 | 15.2
24-PC-34458 | 0 |  | 3054.65 | 62.72
24-PC-34458 | 0 |  | 1379.45 | 13.97
24-PC-34499 | 1 | 229 | 0 | 52.67
24-PC-34499 | 0 |  | 0 | 150.58
24-PC-34499 | 0 |  | 0 | 50.21
24-PC-34499 | 0 |  | 0 | 32.67
24-PC-34499 | 0 |  | 0 | 118.91
24-PC-34593 | 1 | 230 | 0 | 0
24-PC-34593 | 0 |  | 0 | 0
24-PC-34593 | 0 |  | 0 | 0
24-PC-34593 | 0 |  | 0 | 0
24-PC-34593 | 0 |  | 0 | 0
24-PC-34654 | 1 | 231 | 0 | 0
24-PC-34654 | 0 |  | 0 | 0
24-PC-34654 | 0 |  | 1417.07 | 32.25
24-PC-34663 | 1 | 232 | 0 | 0
24-PC-34663 | 0 |  | 0 | 0
24-PC-34663 | 0 |  | 0 | 0
24-PC-34803 | 1 | 233 | 92.36 | 38.59
24-PC-34803 | 0 |  | 127.32 | 39.3
24-PC-34803 | 0 |  | 446.22 | 0
24-PC-34919 | 1 | 234 | 0 | 16.48
24-PC-34919 | 0 |  | 0 | 57.95
24-PC-34919 | 0 |  | 0 | 2.75
24-PC-34975 | 1 | 235 | 0 | 0
24-PC-34975 | 0 |  | 0 | 0
24-PC-34975 | 0 |  | 0 | 0
24-PC-35267 | 1 | 236 | 0 | 0
24-PC-35267 | 0 |  | 0 | 0
24-PC-35267 | 0 |  | 0 | 0
24-PC-35267 | 0 |  | 0 | 0
24-PC-35412 | 1 | 237 | 0 | 0
24-PC-35412 | 0 |  | 0 | 0
24-PC-35419 | 1 | 238 | 0 | 0
24-PC-35419 | 0 |  | 0 | 31.93
24-PC-35419 | 0 |  | 0 | 1.08
24-PC-35474 | 1 | 239 | 0 | 0
24-PC-35474 | 0 |  | 0 | 0
24-PC-35474 | 0 |  | 0 | 0
24-PC-35474 | 0 |  | 0 | 0
24-PC-35559 | 1 | 240 | 0 | 116.19
24-PC-35559 | 0 |  | 0 | 0
24-PC-35559 | 0 |  | 0 | 28.41
24-PC-35586 | 1 | 241 | 0 | 0
24-PC-35586 | 0 |  | 0 | 0
24-PC-35586 | 0 |  | 0 | 0
24-PC-35661 | 1 | 242 | 2929.37 | 96.07
24-PC-35661 | 0 |  | 3811.56 | 108.22
24-PC-35661 | 0 |  | 0 | 0
24-PC-35661 | 0 |  | 2612.16 | 96.76
24-PC-35661 | 0 |  | 552.97 | 14.5
24-PC-35872 | 1 | 243 | 0 | 0
24-PC-35872 | 0 |  | 5066.95 | 77.88
24-PC-35872 | 0 |  | 0 | 0
24-PC-35872 | 0 |  | 71.3 | 0
24-PC-35872 | 0 |  | 0 | 0
24-PC-35872 | 0 |  | 268.04 | 6.5
24-PC-35881 | 1 | 244 | 0 | 0
24-PC-35881 | 0 |  | 0 | 0
24-PC-36099 | 1 | 245 | 0 | 0
24-PC-36099 | 0 |  | 0 | 0
24-PC-36099 | 0 |  | 0 | 0
24-PC-36146 | 1 | 246 | 1339.34 | 0
24-PC-36146 | 0 |  | 1743.83 | 35.33
24-PC-36146 | 0 |  | 724.49 | 7.95
24-PC-36146 | 0 |  | 1158.88 | 4.18
24-PC-36146 | 0 |  | 1479.59 | 59.54
24-PC-36161 | 1 | 247 | 0 | 0
24-PC-36184 | 1 | 248 | 0 | 0
24-PC-36184 | 0 |  | 0 | 1.4
24-PC-36184 | 0 |  | 0 | 0.17
24-PC-36290 | 1 | 249 | 0 | 0
24-PC-36445 | 1 | 250 | 639.61 | 10.7
24-PC-36445 | 0 |  | 311.72 | 0
24-PC-36445 | 0 |  | 445.95 | 54.4
24-PC-36559 | 1 | 251 | 0 | 0
24-PC-36559 | 0 |  | 0 | 0
24-PC-36620 | 1 | 252 | 0 | 0
24-PC-36620 | 0 |  | 0 | 0
24-PC-36676 | 1 | 253 | 0 | 0
24-PC-36676 | 0 |  | 0 | 0
24-PC-36676 | 0 |  | 0 | 0
24-PC-36710 | 1 | 254 | 0 | 0
24-PC-36932 | 1 | 255 | 0 | 0.17
24-PC-36932 | 0 |  | 0 | 0
24-PC-36932 | 0 |  | 0 | 18.12
24-PC-36978 | 1 | 256 | 7231.97 | 69.68
24-PC-36978 | 0 |  | 4765.39 | 146.47
24-PC-36978 | 0 |  | 6011.77 | 261.22
24-PC-36978 | 0 |  | 1718.11 | 58.39
24-PC-36978 | 0 |  | 4426.52 | 45.96
24-PC-37107 | 1 | 257 | 0 | 0
24-PC-37107 | 0 |  | 0 | 0
24-PC-37125 | 1 | 258 | 0 | 0
24-PC-37125 | 0 |  | 0 | 0
24-PC-37125 | 0 |  | 0 | 0
24-PC-37167 | 1 | 259 | 0 | 0
24-PC-37235 | 1 | 260 | 0 | 47.22
24-PC-37235 | 0 |  | 0 | 64.79
24-PC-37235 | 0 |  | 215.52 | 3
24-PC-37266 | 1 | 261 | 0 | 0
24-PC-37266 | 0 |  | 0 | 0
24-PC-37266 | 0 |  | 0 | 0
24-PC-37336 | 1 | 262 | 0 | 0
24-PC-37336 | 0 |  | 0 | 0
24-PC-37336 | 0 |  | 0 | 0
24-PC-37336 | 0 |  | 0 | 0
24-PC-37336 | 0 |  | 0 | 0
24-PC-37336 | 0 |  | 2462.61 | 33.5
24-PC-37372 | 1 | 263 | 0 | 0
24-PC-37372 | 0 |  | 2585.3 | 53.25
24-PC-37415 | 1 | 264 | 0 | 0
24-PC-37415 | 0 |  | 0 | 0
24-PC-37415 | 0 |  | 0 | 0
24-PC-37415 | 0 |  | 0 | 0
24-PC-37415 | 0 |  | 0 | 0
24-PC-37442 | 1 | 265 | 0 | 0
24-PC-37442 | 0 |  | 0 | 0
24-PC-37686 | 1 | 266 | 0 | 29.5
24-PC-37823 | 1 | 267 | 0 | 0
24-PC-37823 | 0 |  | 0 | 0
24-PC-37823 | 0 |  | 0 | 0
24-PC-37823 | 0 |  | 0 | 0
24-PC-37823 | 0 |  | 0 | 1.24
24-PC-37942 | 1 | 268 | 0 | 0
24-PC-37942 | 0 |  | 0 | 0
24-PC-37942 | 0 |  | 0 | 0
24-PC-37942 | 0 |  | 411.62 | 6.25
24-PC-38054 | 1 | 269 | 0 | 0
24-PC-38054 | 0 |  | 0 | 0
24-PC-38054 | 0 |  | 0 | 0
24-PC-38054 | 0 |  | 0 | 0
24-PC-38141 | 1 | 270 | 0 | 0
24-PC-38141 | 0 |  | 0 | 42.57
24-PC-38141 | 0 |  | 0 | 0
24-PC-38141 | 0 |  | 0 | 0
24-PC-38374 | 1 | 271 | 0 | 0
24-PC-38426 | 1 | 272 | 1114.08 | 0
24-PC-38426 | 0 |  | 3279.1 | 0
24-PC-38426 | 0 |  | 3533.7 | 0
24-PC-38426 | 0 |  | 1058.7 | 0
24-PC-38469 | 1 | 273 | 0 | 0
24-PC-38469 | 0 |  | 0 | 0
24-PC-38469 | 0 |  | 0 | 0
24-PC-38469 | 0 |  | 0 | 0
24-PC-38469 | 0 |  | 0 | 0
24-PC-38469 | 0 |  | 470.36 | 9.75
24-PC-38486 | 1 | 274 | 2027.86 | 119.98
24-PC-38486 | 0 |  | 2697.05 | 90.31
24-PC-38486 | 0 |  | 10097.52 | 365.54
24-PC-38579 | 1 | 275 | 0 | 123.12
24-PC-38687 | 1 | 276 | 0 | 0
24-PC-38687 | 0 |  | 0 | 0
24-PC-38687 | 0 |  | 0 | 0
24-PC-38687 | 0 |  | 0 | 0
24-PC-38790 | 1 | 277 | 1741.11 | 501.09
24-PC-38795 | 1 | 278 | 0 | 245.46
24-PC-38795 | 0 |  | 0 | 0
24-PC-38795 | 0 |  | 0 | 0
24-PC-38817 | 1 | 279 | 53457.64 | 7166.26
24-PC-38847 | 1 | 280 | 0 | 0
24-PC-38847 | 0 |  | 0 | 0
24-PC-39091 | 1 | 281 | 29572.21 | 243.33
24-PC-39091 | 0 |  | 1413.71 | 20.75
24-PC-39206 | 1 | 282 | 0 | 0
24-PC-39206 | 0 |  | 0 | 0
24-PC-39206 | 0 |  | 0 | 0
24-PC-39213 | 1 | 283 | 0 | 81.97
24-PC-39213 | 0 |  | 2879.71 | 48.25
24-PC-39308 | 1 | 284 | 19.8 | 4.55
24-PC-39308 | 0 |  | 17.87 | 5.45
24-PC-39308 | 0 |  | 48.62 | 5.84
24-PC-39308 | 0 |  | 114.5 | 28.54
24-PC-39405 | 1 | 285 | 0 | 0
24-PC-39405 | 0 |  | 0 | 0
24-PC-39405 | 0 |  | 0 | 0
24-PC-39479 | 1 | 286 | 0 | 0
24-PC-39479 | 0 |  | 0 | 0
24-PC-39479 | 0 |  | 0 | 0
24-PC-39511 | 1 | 287 | 6388.61 | 0
24-PC-39511 | 0 |  | 17.34 | 0.25
24-PC-39533 | 1 | 288 | 0 | 0
24-PC-39533 | 0 |  | 0 | 0
24-PC-39694 | 1 | 289 | 0 | 0
24-PC-39789 | 1 | 290 | 0 | 0
24-PC-39789 | 0 |  | 0 | 0
24-PC-39789 | 0 |  | 0 | 0
24-PC-39789 | 0 |  | 0 | 0
24-PC-39789 | 0 |  | 0 | 0
24-PC-39822 | 1 | 291 | 0 | 34.2
24-PC-39822 | 0 |  | 0 | 14.28
24-PC-39822 | 0 |  | 0 | 250.34
24-PC-39822 | 0 |  | 0 | 23.24
24-PC-39825 | 1 | 292 | 53.02 | 5.01
24-PC-39825 | 0 |  | 74.85 | 2.13
24-PC-39825 | 0 |  | 59.61 | 6.49
24-PC-39825 | 0 |  | 106.36 | 0
24-PC-39825 | 0 |  | 56.37 | 0
24-PC-39923 | 1 | 293 | 0 | 0
24-PC-39923 | 0 |  | 0 | 294.06
24-PC-39923 | 0 |  | 0 | 0
24-PC-39923 | 0 |  | 1353.01 | 29.25
24-PC-39940 | 1 | 294 | 0 | 0
24-PC-40067 | 1 | 295 | 0 | 345.74
24-PC-40067 | 0 |  | 0 | 71.92
24-PC-40067 | 0 |  | 0 | 86.58
24-PC-40067 | 0 |  | 0 | 166.56
24-PC-40078 | 1 | 296 | 0 | 0
24-PC-40078 | 0 |  | 0 | 0
24-PC-40078 | 0 |  | 0 | 0
24-PC-40091 | 1 | 297 | 12359.91 | 0
24-PC-40102 | 1 | 298 | 14326.26 | 616.37
24-PC-40102 | 0 |  | 11506.7 | 830.96
24-PC-40102 | 0 |  | 5879.65 | 341.85
24-PC-40102 | 0 |  | 5363.88 | 128.93
24-PC-40102 | 0 |  | 731.1 | 14.5
24-PC-40218 | 1 | 299 | 0 | 0
24-PC-40218 | 0 |  | 0 | 0
24-PC-40218 | 0 |  | 0 | 0
24-PC-40218 | 0 |  | 0 | 0
24-PC-40218 | 0 |  | 0 | 0
24-PC-40271 | 1 | 300 | 72064.94 | 215.32
24-PC-40271 | 0 |  | 72014.66 | 2333.28
24-PC-40271 | 0 |  | 21293.17 | 526.47
24-PC-40317 | 1 | 301 | 0 | 0
24-PC-40317 | 0 |  | 0 | 0
24-PC-40317 | 0 |  | 0 | 0
24-PC-40427 | 1 | 302 | 12555.92 | 0
24-PC-40479 | 1 | 303 | 0 | 97.95
24-PC-40479 | 0 |  | 0 | 97.36
24-PC-40479 | 0 |  | 0 | 71.87
24-PC-40561 | 1 | 304 | 0 | 0
24-PC-40561 | 0 |  | 0 | 0
24-PC-40561 | 0 |  | 0 | 0
24-PC-40561 | 0 |  | 838.52 | 16.25
24-PC-40634 | 1 | 305 | 0 | 0
24-PC-40634 | 0 |  | 0 | 0
24-PC-40634 | 0 |  | 165.66 | 3.5
24-PC-40659 | 1 | 306 | 0 | 21.59
24-PC-40659 | 0 |  | 0 | 30.68
24-PC-40659 | 0 |  | 0 | 43.17
24-PC-40659 | 0 |  | 0 | 13.03
24-PC-40670 | 1 | 307 | 5770.69 | 133.07
24-PC-40670 | 0 |  | 1961.85 | 47.97
24-PC-40670 | 0 |  | 3179.07 | 67.45
24-PC-40670 | 0 |  | 3165.23 | 77.43
24-PC-40670 | 0 |  | 1120.34 | 18.74
24-PC-40670 | 0 |  | 486.24 | 11.25
24-PC-40782 | 1 | 308 | 9704.74 | 0
24-PC-40782 | 0 |  | 520.32 | 12
24-PC-40824 | 1 | 309 | 101.43 | 12.12
24-PC-40824 | 0 |  | 305.7 | 47.95
24-PC-40824 | 0 |  | 455.29 | 50.59
24-PC-40824 | 0 |  | 485.41 | 32.82
24-PC-40836 | 1 | 310 | 0 | 4.61
24-PC-40888 | 1 | 311 | 1860.51 | 91.27
24-PC-40888 | 0 |  | 1545.48 | 86.5
24-PC-40888 | 0 |  | 7187.47 | 964.68
24-PC-40888 | 0 |  | 1868.3 | 229.88
24-PC-40888 | 0 |  | 8813.23 | 315.85
24-PC-40956 | 1 | 312 | 162.05 | 0
24-PC-40956 | 0 |  | 193.69 | 0
24-PC-41023 | 1 | 313 | 0 | 0
24-PC-41023 | 0 |  | 0 | 35
24-PC-41023 | 0 |  | 0 | 11.86
24-PC-41066 | 1 | 314 | 0 | 8.33
24-PC-41066 | 0 |  | 0 | 0.63
24-PC-41066 | 0 |  | 0 | 0
24-PC-41066 | 0 |  | 0 | 12.04
24-PC-41066 | 0 |  | 0 | 19.53
24-PC-41067 | 1 | 315 | 22733.27 | 1249.78
24-PC-41067 | 0 |  | 2341.11 | 94.68
24-PC-41067 | 0 |  | 4416.12 | 138.07
24-PC-41119 | 1 | 316 | 4303.9 | 60.54
24-PC-41119 | 0 |  | 2152.66 | 15.04
24-PC-41119 | 0 |  | 1584.45 | 31.18
24-PC-41119 | 0 |  | 1214.06 | 14.89
24-PC-41119 | 0 |  | 845.67 | 11.15
24-PC-41119 | 0 |  | 309.49 | 3.75
24-PC-41154 | 1 | 317 | 0 | 1190.38
24-PC-41534 | 1 | 318 | 0 | 0
24-PC-41555 | 1 | 319 | 2328.56 | 59.66
24-PC-41555 | 0 |  | 4367.07 | 121.78
24-PC-41572 | 1 | 320 | 0 | 0
24-PC-41572 | 0 |  | 0 | 0
24-PC-41701 | 1 | 321 | 0 | 0
24-PC-41701 | 0 |  | 0 | 82.3
24-PC-41701 | 0 |  | 0 | 0
24-PC-41886 | 1 | 322 | 0 | 0
24-PC-41886 | 0 |  | 0 | 0
24-PC-41886 | 0 |  | 173.55 | 2.75
24-PC-41904 | 1 | 323 | 0 | 9.83
24-PC-41904 | 0 |  | 0 | 29.09
24-PC-41969 | 1 | 324 | 0 | 0
24-PC-41969 | 0 |  | 0 | 0
24-PC-41969 | 0 |  | 0 | 0
24-PC-41969 | 0 |  | 0 | 0
24-PC-42121 | 1 | 325 | 185.92 | 0
24-PC-42121 | 0 |  | 0 | 0
24-PC-42121 | 0 |  | 0 | 65.35
24-PC-42121 | 0 |  | 0 | 99.69
24-PC-42121 | 0 |  | 0 | 122.34
24-PC-42174 | 1 | 326 | 0 | 0
24-PC-42174 | 0 |  | 0 | 0
24-PC-42184 | 1 | 327 | 0 | 0
24-PC-42184 | 0 |  | 0 | 0
24-PC-42184 | 0 |  | 0 | 0
24-PC-42184 | 0 |  | 0 | 0
24-PC-42184 | 0 |  | 0 | 0
24-PC-42267 | 1 | 328 | 0 | 0
24-PC-42267 | 0 |  | 0 | 0
24-PC-42267 | 0 |  | 0 | 0
24-PC-42267 | 0 |  | 0 | 0
24-PC-42338 | 1 | 329 | 24.11 | 0
24-PC-42338 | 0 |  | 31.8 | 0
24-PC-42338 | 0 |  | 8.55 | 3.68
24-PC-42437 | 1 | 330 | 1629.9 | 0
24-PC-42437 | 0 |  | 1540.44 | 142.29
24-PC-42437 | 0 |  | 597.21 | 43.65
24-PC-42495 | 1 | 331 | 0 | 0
24-PC-42495 | 0 |  | 0 | 0
24-PC-42527 | 1 | 332 | 0 | 0
24-PC-42550 | 1 | 333 | 0 | 4.83
24-PC-42550 | 0 |  | 0 | 0
24-PC-42550 | 0 |  | 0 | 34.33
24-PC-42550 | 0 |  | 0 | 0
24-PC-42550 | 0 |  | 0 | 2.82
24-PC-42550 | 0 |  | 223.28 | 4
24-PC-42638 | 1 | 334 | 0 | 0
24-PC-42674 | 1 | 335 | 0 | 0
24-PC-42674 | 0 |  | 0 | 0
24-PC-42697 | 1 | 336 | 0 | 0
24-PC-42697 | 0 |  | 0 | 0
24-PC-42697 | 0 |  | 0 | 0
24-PC-42846 | 1 | 337 | 1310.9 | 0
24-PC-42846 | 0 |  | 313.04 | 0
24-PC-42846 | 0 |  | 1510.1 | 0
24-PC-42846 | 0 |  | 436.9 | 0
24-PC-43044 | 1 | 338 | 0 | 0
24-PC-43116 | 1 | 339 | 0 | 0
24-PC-43116 | 0 |  | 417.69 | 6.5
24-PC-43150 | 1 | 340 | 0 | 267.54
24-PC-43150 | 0 |  | 0 | 0
24-PC-43150 | 0 |  | 0 | 0
24-PC-43150 | 0 |  | 379.33 | 8.75
24-PC-43157 | 1 | 341 | 2442.72 | 0
24-PC-43157 | 0 |  | 947.12 | 0
24-PC-43157 | 0 |  | 587.83 | 0
24-PC-43157 | 0 |  | 251.6 | 0
24-PC-43157 | 0 |  | 519.8 | 0
24-PC-43251 | 1 | 342 | 0 | 0
24-PC-43251 | 0 |  | 0 | 0
24-PC-43251 | 0 |  | 0 | 0
24-PC-43251 | 0 |  | 0 | 0
24-PC-43406 | 1 | 343 | 0 | 0
24-PC-43406 | 0 |  | 0 | 0
24-PC-43406 | 0 |  | 0 | 0
24-PC-43670 | 1 | 344 | 0 | 0
24-PC-43670 | 0 |  | 0 | 0
24-PC-43670 | 0 |  | 0 | 0
24-PC-43670 | 0 |  | 0 | 0
24-PC-43670 | 0 |  | 0 | 0
24-PC-43715 | 1 | 345 | 0 | 226.61
24-PC-43715 | 0 |  | 0 | 224.45
24-PC-43715 | 0 |  | 0 | 0
24-PC-43715 | 0 |  | 0 | 0
24-PC-43719 | 1 | 346 | 0 | 0
24-PC-43719 | 0 |  | 0 | 0
24-PC-43719 | 0 |  | 0 | 0
24-PC-43782 | 1 | 347 | 2652.8 | 76.77
24-PC-43782 | 0 |  | 13571.35 | 353.47
24-PC-43782 | 0 |  | 11183.67 | 1039.54
24-PC-43782 | 0 |  | 3869.48 | 303.02
24-PC-43786 | 1 | 348 | 0 | 0
24-PC-43786 | 0 |  | 0 | 0
24-PC-43786 | 0 |  | 0 | 0
24-PC-43786 | 0 |  | 0 | 0
24-PC-43786 | 0 |  | 0 | 0
24-PC-43877 | 1 | 349 | 0 | 0
24-PC-43877 | 0 |  | 0 | 0
24-PC-43877 | 0 |  | 0 | 0
24-PC-43877 | 0 |  | 0 | 0
24-PC-43877 | 0 |  | 0 | 0
24-PC-44022 | 1 | 350 | 0 | 0
24-PC-44113 | 1 | 351 | 1929.24 | 302.97
24-PC-44113 | 0 |  | 7607.92 | 191.12
24-PC-44113 | 0 |  | 9840.11 | 227.22
24-PC-44113 | 0 |  | 23547.76 | 406.6
24-PC-44113 | 0 |  | 7603.01 | 137.3
24-PC-44113 | 0 |  | 1589.22 | 25
24-PC-44158 | 1 | 352 | 441.84 | 34.61
24-PC-44158 | 0 |  | 18.76 | 0.25
25-PC-30034 | 1 | 353 | 0 | 0
25-PC-30034 | 0 |  | 0 | 0
25-PC-30034 | 0 |  | 0 | 0
25-PC-30034 | 0 |  | 0 | 26.42
25-PC-30034 | 0 |  | 0 | 25.4
25-PC-30034 | 0 |  | 527.36 | 12.25
25-PC-30077 | 1 | 354 | 0 | 480.47
25-PC-30077 | 0 |  | 425.56 | 10
25-PC-30140 | 1 | 355 | 0 | 0
25-PC-30140 | 0 |  | 0 | 0
25-PC-30140 | 0 |  | 0 | 0
25-PC-30204 | 1 | 356 | 0 | 0
25-PC-30204 | 0 |  | 0 | 0
25-PC-30204 | 0 |  | 0 | 0
25-PC-30204 | 0 |  | 0 | 0
25-PC-30204 | 0 |  | 0 | 0
25-PC-30254 | 1 | 357 | 0 | 0
25-PC-30254 | 0 |  | 0 | 5.33
25-PC-30254 | 0 |  | 0 | 3.02
25-PC-30254 | 0 |  | 0 | 0
25-PC-30254 | 0 |  | 0 | 0
25-PC-30345 | 1 | 358 | 0 | 91.97
25-PC-30345 | 0 |  | 893.24 | 17.75
25-PC-30348 | 1 | 359 | 0 | 0
25-PC-30348 | 0 |  | 0 | 0
25-PC-30348 | 0 |  | 0 | 0
25-PC-30348 | 0 |  | 0 | 0
25-PC-30348 | 0 |  | 0 | 0
25-PC-30418 | 1 | 360 | 0 | 0
25-PC-30418 | 0 |  | 0 | 0
25-PC-30418 | 0 |  | 0 | 0
25-PC-30418 | 0 |  | 0 | 0
25-PC-30418 | 0 |  | 0 | 15.91
25-PC-30418 | 0 |  | 230.46 | 6
25-PC-30581 | 1 | 361 | 1219.87 | 46.31
25-PC-30581 | 0 |  | 0 | 14.56
25-PC-30581 | 0 |  | 65.86 | 1
25-PC-30694 | 1 | 362 | 15324.49 | 679.05
25-PC-30694 | 0 |  | 31014.16 | 670.48
25-PC-30694 | 0 |  | 9287.8 | 454.18
25-PC-30694 | 0 |  | 24495.73 | 1033.88
25-PC-30717 | 1 | 363 | 0 | 0
25-PC-30717 | 0 |  | 19314.76 | 431.87
25-PC-30717 | 0 |  | 2204.04 | 47
25-PC-30725 | 1 | 364 | 130.45 | 4.31
25-PC-30725 | 0 |  | 342.05 | 6.15
25-PC-30725 | 0 |  | 1002.47 | 39.82
25-PC-30739 | 1 | 365 | 0 | 0
25-PC-30739 | 0 |  | 0 | 0
25-PC-30739 | 0 |  | 0 | 0
25-PC-30739 | 0 |  | 0 | 0
25-PC-30739 | 0 |  | 0 | 0
25-PC-30739 | 0 |  | 958.39 | 22.25
25-PC-30772 | 1 | 366 | 2570.73 | 91.19
25-PC-30772 | 0 |  | 2615.09 | 167.54
25-PC-30772 | 0 |  | 500.07 | 41.48
25-PC-30772 | 0 |  | 7028.25 | 131.85
25-PC-30772 | 0 |  | 636.93 | 12.5
25-PC-30803 | 1 | 367 | 2208.27 | 195.79
25-PC-30803 | 0 |  | 1144.46 | 273.42
25-PC-30803 | 0 |  | 1366.77 | 24.5
25-PC-30824 | 1 | 368 | 0 | 0
25-PC-30824 | 0 |  | 0 | 0
25-PC-30824 | 0 |  | 0 | 0
25-PC-30824 | 0 |  | 0 | 0
25-PC-30928 | 1 | 369 | 0 | 0
25-PC-30928 | 0 |  | 0 | 0
25-PC-30928 | 0 |  | 0 | 1.84
25-PC-30928 | 0 |  | 0 | 0
25-PC-31024 | 1 | 370 | 0 | 0
25-PC-31024 | 0 |  | 0 | 0
25-PC-31024 | 0 |  | 0 | 0
25-PC-31024 | 0 |  | 0 | 0
25-PC-31024 | 0 |  | 0 | 0
25-PC-31109 | 1 | 371 | 49642.42 | 785.09
25-PC-31109 | 0 |  | 3765.35 | 39.5
25-PC-31114 | 1 | 372 | 0 | 87.44
25-PC-31114 | 0 |  | 415.64 | 10
25-PC-31144 | 1 | 373 | 0 | 228.99
25-PC-31180 | 1 | 374 | 2937.6 | 0
25-PC-31180 | 0 |  | 456.87 | 4
25-PC-31242 | 1 | 375 | 0 | 0
25-PC-31242 | 0 |  | 0 | 0
25-PC-31242 | 0 |  | 354.78 | 9
25-PC-31263 | 1 | 376 | 7112.16 | 140.06
25-PC-31263 | 0 |  | 0 | 25.87
25-PC-31263 | 0 |  | 0 | 28.23
25-PC-31263 | 0 |  | 0 | 0
25-PC-31263 | 0 |  | 1014.26 | 18.25
25-PC-31275 | 1 | 377 | 1455.85 | 50.47
25-PC-31275 | 0 |  | 394.78 | 12.93
25-PC-31275 | 0 |  | 369.08 | 8.8
25-PC-31275 | 0 |  | 2497.8 | 32.66
25-PC-31275 | 0 |  | 679.52 | 5.5
25-PC-31298 | 1 | 378 | 0 | 20.65
25-PC-31298 | 0 |  | 287.25 | 75.5
25-PC-31298 | 0 |  | 0 | 0
25-PC-31298 | 0 |  | 0 | 0
25-PC-31298 | 0 |  | 108.59 | 2.25
25-PC-31330 | 1 | 379 | 1271.74 | 16.24
25-PC-31330 | 0 |  | 3820.54 | 52.91
25-PC-31330 | 0 |  | -232.28 | -3.25
25-PC-31417 | 1 | 380 | 11850.13 | 62.84
25-PC-31417 | 0 |  | 868.56 | 12
25-PC-31420 | 1 | 381 | 1232.58 | 34.86
25-PC-31420 | 0 |  | 0 | 1.8
25-PC-31420 | 0 |  | 0 | 0
25-PC-31420 | 0 |  | 590.13 | 15
25-PC-31555 | 1 | 382 | 1936.92 | 81.39
25-PC-31555 | 0 |  | 0 | 0
25-PC-31555 | 0 |  | 1130.16 | 28.16
25-PC-31555 | 0 |  | 506.12 | 12.5
25-PC-31590 | 1 | 383 | 0 | 10.53
25-PC-31590 | 0 |  | 3858.35 | 95.73
25-PC-31590 | 0 |  | 47.27 | 1
25-PC-31616 | 1 | 384 | 4286 | 0
25-PC-31616 | 0 |  | 3402.63 | 0
25-PC-31616 | 0 |  | 4765.93 | 0
25-PC-31616 | 0 |  | 64.42 | 1.5
25-PC-31775 | 1 | 385 | 0 | 0
25-PC-31775 | 0 |  | 0 | 0
25-PC-31775 | 0 |  | 0 | 0
25-PC-31775 | 0 |  | 51.51 | 1.25
25-PC-31784 | 1 | 386 | 5182.25 | 179.07
25-PC-31784 | 0 |  | 13851.86 | 305.53
25-PC-31784 | 0 |  | 0 | 0
25-PC-31784 | 0 |  | 8769.11 | 118.29
25-PC-31784 | 0 |  | 7334.66 | 250.16
25-PC-31784 | 0 |  | 1860.7 | 31.75
25-PC-31821 | 1 | 387 | 0 | 0
25-PC-31821 | 0 |  | 0 | 167.52
25-PC-31821 | 0 |  | 2037.93 | 48
25-PC-31895 | 1 | 388 | 557.2 | 0
25-PC-31895 | 0 |  | 1359.13 | 0
25-PC-31895 | 0 |  | 2358.08 | 0
25-PC-31905 | 1 | 389 | 0 | 0
25-PC-31905 | 0 |  | 0 | 0
25-PC-31905 | 0 |  | 0 | 0
25-PC-31905 | 0 |  | 0 | 0
25-PC-31905 | 0 |  | 1470.66 | 34.25
25-PC-31961 | 1 | 390 | 5638.59 | 122.11
25-PC-31961 | 0 |  | 911.16 | 0
25-PC-31961 | 0 |  | 2176.64 | 50.67
25-PC-31961 | 0 |  | 966.84 | 22.22
25-PC-31961 | 0 |  | 5277.83 | 119.75
25-PC-31961 | 0 |  | 341.69 | 8.5
25-PC-31983 | 1 | 391 | 455.13 | 0
25-PC-31983 | 0 |  | 406.35 | 0
25-PC-31983 | 0 |  | 2316.36 | 613.26
25-PC-31983 | 0 |  | 515.68 | 154.16
25-PC-32000 | 1 | 392 | 0 | 0
25-PC-32000 | 0 |  | 0 | 0
25-PC-32000 | 0 |  | 0 | 0
25-PC-32021 | 1 | 393 | 0 | 0
25-PC-32021 | 0 |  | 442.17 | 9
25-PC-32024 | 1 | 394 | 0 | 0
25-PC-32024 | 0 |  | 0 | 15.21
25-PC-32024 | 0 |  | 682.45 | 15.75
25-PC-32112 | 1 | 395 | 0 | 0
25-PC-32112 | 0 |  | 0 | 0
25-PC-32144 | 1 | 396 | 246.81 | 0
25-PC-32144 | 0 |  | 760.6 | 0
25-PC-32144 | 0 |  | 574.28 | 0
25-PC-32144 | 0 |  | 232.27 | 0
25-PC-32144 | 0 |  | 936.85 | 0
25-PC-32241 | 1 | 397 | 0 | 15.1
25-PC-32241 | 0 |  | 0 | 19.53
25-PC-32241 | 0 |  | 0 | 0
25-PC-32241 | 0 |  | 0 | 0
25-PC-32241 | 0 |  | 0 | 0
25-PC-32241 | 0 |  | 1467.23 | 14.25
25-PC-32264 | 1 | 398 | 0 | 0
25-PC-32264 | 0 |  | 0 | 8.74
25-PC-32264 | 0 |  | 0 | 17.13
25-PC-32264 | 0 |  | 0 | 0
25-PC-32264 | 0 |  | 0 | 0
25-PC-32323 | 1 | 399 | 30007.34 | 472.08
25-PC-32323 | 0 |  | 0 | 0
25-PC-32323 | 0 |  | 0 | 267.88
25-PC-32323 | 0 |  | 4241.71 | 67.75
25-PC-32346 | 1 | 400 | 0 | 13.46
25-PC-32346 | 0 |  | 0 | 23.59
25-PC-32346 | 0 |  | 0 | 100.07
25-PC-32402 | 1 | 401 | 0 | 0
25-PC-32402 | 0 |  | 0 | 0
25-PC-32402 | 0 |  | 0 | 0
25-PC-32402 | 0 |  | 0 | 0
25-PC-32402 | 0 |  | 249.58 | 6
25-PC-32447 | 1 | 402 | 2661.98 | 55.97
25-PC-32447 | 0 |  | 844.96 | 77.9
25-PC-32447 | 0 |  | 6403.48 | 238.72
25-PC-32447 | 0 |  | 2389.29 | 110.67
25-PC-32447 | 0 |  | 2308.28 | 95.18
25-PC-32447 | 0 |  | 323.01 | 7.75
25-PC-32495 | 1 | 403 | 0 | 28.92
25-PC-32495 | 0 |  | 10980.75 | 225.62
25-PC-32495 | 0 |  | 30214.02 | 375.88
25-PC-32495 | 0 |  | 1376.65 | 17
25-PC-32500 | 1 | 404 | 979.2 | 170.93
25-PC-32500 | 0 |  | 1281.93 | 101.85
25-PC-32630 | 1 | 405 | 0 | 0
25-PC-32750 | 1 | 406 | 0 | 0
25-PC-32750 | 0 |  | 0 | 0
25-PC-32750 | 0 |  | 0 | 0
25-PC-32750 | 0 |  | 139.35 | 0
25-PC-32750 | 0 |  | 80.43 | 1.75
25-PC-32776 | 1 | 407 | 0 | 0
25-PC-32776 | 0 |  | 0 | 0
25-PC-32776 | 0 |  | 985 | 18.75
25-PC-32795 | 1 | 408 | 0 | 0
25-PC-32795 | 0 |  | 250.17 | 18.18
25-PC-32795 | 0 |  | 1006.06 | 21
25-PC-32819 | 1 | 409 | 0 | 44.91
25-PC-32819 | 0 |  | 0 | 160.79
25-PC-32838 | 1 | 410 | 0 | 0
25-PC-32838 | 0 |  | 371.71 | 0
25-PC-32838 | 0 |  | 182.67 | 0
25-PC-32838 | 0 |  | 0 | 0
25-PC-32838 | 0 |  | 1081.95 | 9.5
25-PC-32861 | 1 | 411 | 8050.85 | 0
25-PC-32861 | 0 |  | 288.99 | 4.5
25-PC-32867 | 1 | 412 | 0 | 0
25-PC-32867 | 0 |  | 2071.46 | 71.18
25-PC-32867 | 0 |  | 0 | 5.22
25-PC-32867 | 0 |  | 0 | 0
25-PC-32867 | 0 |  | 0 | 0
25-PC-32867 | 0 |  | 1575.32 | 30.75
25-PC-32885 | 1 | 413 | 0 | 0
25-PC-32885 | 0 |  | 2416.88 | 31.25
25-PC-32899 | 1 | 414 | 8767.07 | 10.29
25-PC-32899 | 0 |  | 14427.66 | 136.43
25-PC-32899 | 0 |  | 229.82 | 4
25-PC-32911 | 1 | 415 | 2794.55 | 56.27
25-PC-32911 | 0 |  | 3160.22 | 49.81
25-PC-32911 | 0 |  | 783.82 | 28.97
25-PC-32911 | 0 |  | 997.39 | 14.75
25-PC-32926 | 1 | 416 | 0 | 0
25-PC-32952 | 1 | 417 | 0 | 0
25-PC-32952 | 0 |  | 938.39 | 16.75
25-PC-33065 | 1 | 418 | 0 | 41.31
25-PC-33065 | 0 |  | 0 | 10.83
25-PC-33065 | 0 |  | 0 | 15.58
25-PC-33065 | 0 |  | 0 | 0.84
25-PC-33065 | 0 |  | 0 | 0
25-PC-33088 | 1 | 419 | 0 | 62.05
25-PC-33088 | 0 |  | 0 | 0
25-PC-33105 | 1 | 420 | 2764.24 | 44.62
25-PC-33105 | 0 |  | 1670.2 | 25.52
25-PC-33105 | 0 |  | 786.71 | 12.6
25-PC-33105 | 0 |  | 1107.84 | 17
25-PC-33105 | 0 |  | 353.21 | 5.5
25-PC-33136 | 1 | 421 | 0 | 0
25-PC-33136 | 0 |  | 0 | 0
25-PC-33136 | 0 |  | 0 | 0
25-PC-33136 | 0 |  | 0 | 0
25-PC-33136 | 0 |  | 0 | 0
25-PC-33136 | 0 |  | 615.86 | 13.25
25-PC-33183 | 1 | 422 | 8781.19 | 92.75
25-PC-33183 | 0 |  | 0 | 0
25-PC-33183 | 0 |  | 0 | 0
25-PC-33183 | 0 |  | 0 | 0
25-PC-33183 | 0 |  | 3285.3 | 68.76
25-PC-33183 | 0 |  | 1528.1 | 32
25-PC-33206 | 1 | 423 | 0 | 0
25-PC-33206 | 0 |  | 748.05 | 9.25
25-PC-33238 | 1 | 424 | 26994.17 | 0
25-PC-33294 | 1 | 425 | 0 | 53.69
25-PC-33294 | 0 |  | 0 | 0
25-PC-33294 | 0 |  | 0 | 70.74
25-PC-33294 | 0 |  | 757.29 | 16.25
25-PC-33321 | 1 | 426 | 0 | 5.54
25-PC-33321 | 0 |  | 0 | 10.34
25-PC-33321 | 0 |  | 0 | 10.42
25-PC-33321 | 0 |  | 0 | 16.54
25-PC-33321 | 0 |  | 0 | 5.84
25-PC-33332 | 1 | 427 | 0 | 0
25-PC-33332 | 0 |  | 0 | 73.86
25-PC-33332 | 0 |  | 449.31 | 9.75
25-PC-33348 | 1 | 428 | 0 | 0
25-PC-33348 | 0 |  | 0 | 0
25-PC-33348 | 0 |  | 0 | 0
25-PC-33348 | 0 |  | 192.66 | 3
25-PC-33367 | 1 | 429 | 0 | 0
25-PC-33367 | 0 |  | 371.02 | 9.25
25-PC-33412 | 1 | 430 | 0 | 200.73
25-PC-33412 | 0 |  | 0 | 0
25-PC-33412 | 0 |  | 0 | 0
25-PC-33412 | 0 |  | 0 | 0
25-PC-33414 | 1 | 431 | 7408.67 | 384.03
25-PC-33473 | 1 | 432 | 0 | 94.89
25-PC-33473 | 0 |  | 0 | 49.17
25-PC-33473 | 0 |  | 198.9 | 4.5
25-PC-33522 | 1 | 433 | 0 | 0
25-PC-33522 | 0 |  | 0 | 0
25-PC-33522 | 0 |  | 397.15 | 0
25-PC-33522 | 0 |  | 0 | 0
25-PC-33522 | 0 |  | 2426.11 | 0
25-PC-33522 | 0 |  | 627.45 | 13
25-PC-33528 | 1 | 434 | 0 | 0
25-PC-33528 | 0 |  | 0 | 11.11
25-PC-33528 | 0 |  | 0 | 17.32
25-PC-33528 | 0 |  | 0 | 0
25-PC-33535 | 1 | 435 | 0 | 0
25-PC-33535 | 0 |  | 0 | 0
25-PC-33535 | 0 |  | 0 | 0
25-PC-33535 | 0 |  | 0 | 0
25-PC-33561 | 1 | 436 | 0 | 0
25-PC-33561 | 0 |  | 0 | 0
25-PC-33561 | 0 |  | 0 | 0
25-PC-33561 | 0 |  | 0 | 0
25-PC-33640 | 1 | 437 | 0 | 0
25-PC-33640 | 0 |  | 2237.53 | 41
25-PC-33680 | 1 | 438 | 0 | 0
25-PC-33680 | 0 |  | 0 | 0
25-PC-33680 | 0 |  | 0 | 0
25-PC-33680 | 0 |  | 0 | 0
25-PC-33680 | 0 |  | 0 | 0
25-PC-33680 | 0 |  | 78.64 | 2
25-PC-33744 | 1 | 439 | 228.43 | 0
25-PC-33744 | 0 |  | 0 | 0
25-PC-33744 | 0 |  | 0 | 0
25-PC-33744 | 0 |  | 0 | 0
25-PC-33744 | 0 |  | 0 | 0
25-PC-33750 | 1 | 440 | 0 | 0
25-PC-33750 | 0 |  | 5969.04 | 0
25-PC-33750 | 0 |  | 8178.99 | 0
25-PC-33750 | 0 |  | 284.05 | 6.5
25-PC-33795 | 1 | 441 | 0 | 36.69
25-PC-33795 | 0 |  | 0 | 0
25-PC-33795 | 0 |  | 0 | 0
25-PC-33798 | 1 | 442 | 0 | 0
25-PC-33798 | 0 |  | 0 | 0
25-PC-33798 | 0 |  | 0 | 6.92
25-PC-33798 | 0 |  | 0 | 0
25-PC-33798 | 0 |  | 0 | 11.59
25-PC-33798 | 0 |  | 1440.22 | 28.25
25-PC-33827 | 1 | 443 | 0 | 0
25-PC-33827 | 0 |  | 0 | 0
25-PC-33827 | 0 |  | 0 | 0
25-PC-33827 | 0 |  | 0 | 0
25-PC-33841 | 1 | 444 | 0 | 0
25-PC-33841 | 0 |  | 439.4 | 10
25-PC-33846 | 1 | 445 | 23.16 | 2.44
25-PC-33846 | 0 |  | 0 | 0
25-PC-33846 | 0 |  | 463.05 | 19.88
25-PC-33846 | 0 |  | 117.73 | 3.69
25-PC-33846 | 0 |  | 130.27 | 4.47
25-PC-33846 | 0 |  | -233.63 | -3.5
25-PC-33855 | 1 | 446 | 0 | 0
25-PC-33855 | 0 |  | 0 | 1.09
25-PC-33855 | 0 |  | 0 | 0
25-PC-33855 | 0 |  | 0 | 0
25-PC-33855 | 0 |  | 0 | 0
25-PC-33915 | 1 | 447 | 0 | 0
25-PC-33915 | 0 |  | 700.59 | 11
25-PC-33919 | 1 | 448 | 680.72 | 43.5
25-PC-33919 | 0 |  | 258.76 | 12.26
25-PC-33919 | 0 |  | 2083.75 | 94.73
25-PC-33919 | 0 |  | 704.56 | 41.87
25-PC-33922 | 1 | 449 | 8577.24 | 111.67
25-PC-33922 | 0 |  | 0 | 0
25-PC-33922 | 0 |  | 10179.12 | 115.83
25-PC-33922 | 0 |  | 0 | 0
25-PC-33922 | 0 |  | 1461.14 | 19.5
25-PC-33969 | 1 | 450 | 0 | 0
25-PC-33969 | 0 |  | 0 | 0
25-PC-33969 | 0 |  | 0 | 0
25-PC-33969 | 0 |  | 0 | 0
25-PC-33969 | 0 |  | 0 | 0
25-PC-34036 | 1 | 451 | 351.8 | 28.01
25-PC-34036 | 0 |  | 0 | 0
25-PC-34036 | 0 |  | 0 | 1.34
25-PC-34036 | 0 |  | 0 | 25.49
25-PC-34036 | 0 |  | 2791.76 | 78.35
25-PC-34036 | 0 |  | 561.54 | 11.5
25-PC-34077 | 1 | 452 | 0 | 0
25-PC-34077 | 0 |  | 0 | 0
25-PC-34077 | 0 |  | 0 | 0
25-PC-34077 | 0 |  | 0 | 0
25-PC-34077 | 0 |  | 3014.41 | 36.75
25-PC-34088 | 1 | 453 | 0 | 12.95
25-PC-34088 | 0 |  | 0 | 0
25-PC-34090 | 1 | 454 | 0 | 0
25-PC-34090 | 0 |  | 0 | 0
25-PC-34090 | 0 |  | 35.61 | 0.75
25-PC-34144 | 1 | 455 | 3012.89 | 0
25-PC-34151 | 1 | 456 | 0 | 0
25-PC-34151 | 0 |  | 0 | 0
25-PC-34151 | 0 |  | 0 | 0
25-PC-34151 | 0 |  | 1192.28 | 15.25
25-PC-34176 | 1 | 457 | 3975.91 | 106.13
25-PC-34176 | 0 |  | 1556.41 | 110.28
25-PC-34176 | 0 |  | 0 | 5.57
25-PC-34176 | 0 |  | 456.61 | 7
25-PC-34374 | 1 | 458 | 0 | 0
25-PC-34374 | 0 |  | 0 | 0
25-PC-34374 | 0 |  | 0 | 0
25-PC-34374 | 0 |  | 0 | 0
25-PC-34374 | 0 |  | 0 | 0
25-PC-34382 | 1 | 459 | 1014.83 | 26.29
25-PC-34382 | 0 |  | 2004.39 | 62.23
25-PC-34382 | 0 |  | 1023.68 | 22.22
25-PC-34382 | 0 |  | 3794.86 | 125.39
25-PC-34451 | 1 | 460 | 624.37 | 18.28
25-PC-34451 | 0 |  | 0 | 36.29
25-PC-34451 | 0 |  | 0 | 20.47
25-PC-34451 | 0 |  | 3185.31 | 40.35
25-PC-34451 | 0 |  | 5164.09 | 75.92
25-PC-34451 | 0 |  | 1039.16 | 14.5
25-PC-34537 | 1 | 461 | 0 | 0
25-PC-34537 | 0 |  | 0 | 0
25-PC-34537 | 0 |  | 0 | 0
25-PC-34537 | 0 |  | 0 | 0
25-PC-34652 | 1 | 462 | 8670.12 | 296.46
25-PC-34652 | 0 |  | 15797.09 | 333.58
25-PC-34652 | 0 |  | 0 | 0
25-PC-34652 | 0 |  | 0 | 0
25-PC-34652 | 0 |  | 2125.49 | 36.5
25-PC-34681 | 1 | 463 | 0 | 0
25-PC-34681 | 0 |  | 0 | 0
25-PC-34681 | 0 |  | 0 | 0
25-PC-34681 | 0 |  | 2674.89 | 43.5
25-PC-34732 | 1 | 464 | 0 | 89.06
25-PC-34732 | 0 |  | 0 | 42.15
25-PC-34768 | 1 | 465 | 2034.64 | 0
25-PC-34768 | 0 |  | 13231.06 | 0
25-PC-34768 | 0 |  | 3164.68 | 0
25-PC-34768 | 0 |  | 2294.68 | 0
25-PC-34768 | 0 |  | 5223.64 | 0
25-PC-34772 | 1 | 466 | 0 | 0
25-PC-34772 | 0 |  | 0 | 0
25-PC-34772 | 0 |  | 0 | 0
25-PC-34772 | 0 |  | 0 | 0
25-PC-34780 | 1 | 467 | 8745.42 | 165.86
25-PC-34780 | 0 |  | 8310.72 | 174.57
25-PC-34780 | 0 |  | 1919.65 | 49.56
25-PC-34780 | 0 |  | 10215.67 | 143.59
25-PC-34780 | 0 |  | 1729.25 | 53.18
25-PC-34780 | 0 |  | 645.54 | 10.25
25-PC-34843 | 1 | 468 | 0 | 104.65
25-PC-34843 | 0 |  | 0 | 198.79
25-PC-34843 | 0 |  | 0 | 100.71
25-PC-34843 | 0 |  | 0 | 345.69
25-PC-34850 | 1 | 469 | 0 | 0
25-PC-34850 | 0 |  | 16973.12 | 275.87
25-PC-34850 | 0 |  | 0 | 0
25-PC-34850 | 0 |  | 1380.02 | 22.5
25-PC-34871 | 1 | 470 | 0 | 0
25-PC-34871 | 0 |  | 1770.83 | 27
25-PC-35024 | 1 | 471 | 0 | 0
25-PC-35024 | 0 |  | 0 | 0
25-PC-35024 | 0 |  | 0 | 0
25-PC-35024 | 0 |  | 0 | 0
25-PC-35024 | 0 |  | 0 | 0
25-PC-35040 | 1 | 472 | 3742.04 | 96.62
25-PC-35040 | 0 |  | 0 | 80.57
25-PC-35040 | 0 |  | 6337.38 | 94.52
25-PC-35040 | 0 |  | 12.33 | 0.25
25-PC-35084 | 1 | 473 | 0 | 47.94
25-PC-35084 | 0 |  | 0 | 0
25-PC-35084 | 0 |  | 0 | 0
25-PC-35084 | 0 |  | 1269.74 | 162.28
25-PC-35084 | 0 |  | 2841.72 | 108.25
25-PC-35084 | 0 |  | 348.69 | 8.75
25-PC-35131 | 1 | 474 | 0 | 0
25-PC-35138 | 1 | 475 | 0 | 0
25-PC-35138 | 0 |  | 2388.21 | 0
25-PC-35138 | 0 |  | 0 | 0
25-PC-35138 | 0 |  | 0 | 0
25-PC-35138 | 0 |  | 4473.89 | 82.75
25-PC-35168 | 1 | 476 | 0 | 0
25-PC-35182 | 1 | 477 | 0 | 47.96
25-PC-35182 | 0 |  | 1528.84 | 39.51
25-PC-35182 | 0 |  | 0 | 24.26
25-PC-35182 | 0 |  | 3363 | 79.83
25-PC-35182 | 0 |  | 733.72 | 60.74
25-PC-35182 | 0 |  | 335.79 | 7.5
25-PC-35272 | 1 | 478 | 0 | 0
25-PC-35272 | 0 |  | 2470.53 | 86.61
25-PC-35272 | 0 |  | 1393.53 | 42
25-PC-35272 | 0 |  | 1878.59 | 80.54
25-PC-35272 | 0 |  | 2782.67 | 83.05
25-PC-35272 | 0 |  | 367.99 | 9.25
25-PC-35295 | 1 | 479 | 0 | 0
25-PC-35340 | 1 | 480 | 13864.03 | 289.02
25-PC-35340 | 0 |  | 8135.42 | 242.71
25-PC-35340 | 0 |  | 368.68 | 7.5
25-PC-35361 | 1 | 481 | 144.8 | 92.91
25-PC-35361 | 0 |  | 3594.3 | 99.23
25-PC-35361 | 0 |  | 1576.27 | 40.43
25-PC-35361 | 0 |  | 1859.27 | 41.23
25-PC-35431 | 1 | 482 | 0 | 0
25-PC-35442 | 1 | 483 | 2901.2 | 111.77
25-PC-35442 | 0 |  | 2396.87 | 0
25-PC-35442 | 0 |  | 1812.5 | 49.65
25-PC-35470 | 1 | 484 | 11991.06 | 1022.04
25-PC-35470 | 0 |  | 10489.77 | 423.98
25-PC-35485 | 1 | 485 | 0 | 0
25-PC-35485 | 0 |  | 0 | 0
25-PC-35485 | 0 |  | 12379.37 | 166.73
25-PC-35485 | 0 |  | 14818.33 | 209.27
25-PC-35485 | 0 |  | 4355.03 | 55
25-PC-35496 | 1 | 486 | 1255.95 | 4.2
25-PC-35496 | 0 |  | 388.38 | 2.82
25-PC-35496 | 0 |  | 1452.08 | 9.76
25-PC-35496 | 0 |  | 0 | 0
25-PC-35496 | 0 |  | 534.21 | 5.75
25-PC-35525 | 1 | 487 | 0 | 0
25-PC-35525 | 0 |  | 1010.54 | 8.78
25-PC-35525 | 0 |  | 5881.43 | 106.63
25-PC-35525 | 0 |  | 3168.31 | 46.07
25-PC-35525 | 0 |  | 1245.65 | 15.5
25-PC-35553 | 1 | 488 | 0 | 0
25-PC-35553 | 0 |  | 0 | 0
25-PC-35553 | 0 |  | 0 | 0
25-PC-35553 | 0 |  | 0 | 0
25-PC-35553 | 0 |  | 7685.31 | 186.7
25-PC-35553 | 0 |  | 3461.14 | 62
25-PC-35620 | 1 | 489 | 0 | 0
25-PC-35620 | 0 |  | 0 | 0
25-PC-35620 | 0 |  | 0 | 0
25-PC-35620 | 0 |  | 0 | 0
25-PC-35620 | 0 |  | 0 | 0
25-PC-35740 | 1 | 490 | 0 | 0
25-PC-35740 | 0 |  | 0 | 0
25-PC-35740 | 0 |  | 0 | 0
25-PC-35740 | 0 |  | 0 | 0
25-PC-35740 | 0 |  | 0 | 0
25-PC-35761 | 1 | 491 | 188.56 | 399.42
25-PC-35761 | 0 |  | 3492.33 | 83
25-PC-35779 | 1 | 492 | 2559.1 | 69.66
25-PC-35779 | 0 |  | 3898.56 | 108.99
25-PC-35779 | 0 |  | 4019.77 | 84.86
25-PC-35779 | 0 |  | 0 | 72.23
25-PC-35779 | 0 |  | 0 | 0
25-PC-35779 | 0 |  | 1539.83 | 29
25-PC-35850 | 1 | 493 | 0 | 229.04
25-PC-35897 | 1 | 494 | 0 | 170.76
25-PC-35897 | 0 |  | 0 | 125.22
25-PC-35897 | 0 |  | 176.71 | 4.25
25-PC-35958 | 1 | 495 | 7005.09 | 296.39
25-PC-35963 | 1 | 496 | 0 | 649.74
25-PC-35963 | 0 |  | 23699.02 | 654.68
25-PC-35963 | 0 |  | 1621.72 | 30.5
25-PC-35970 | 1 | 497 | 0 | 0
25-PC-35970 | 0 |  | 0 | 0
25-PC-35970 | 0 |  | 0 | 0
25-PC-35970 | 0 |  | 0 | 0
25-PC-35970 | 0 |  | 115 | 2.75
25-PC-36007 | 1 | 498 | 0 | 0
25-PC-36007 | 0 |  | 0 | 0
25-PC-36007 | 0 |  | 0 | 0
25-PC-36007 | 0 |  | 0 | 0
25-PC-36030 | 1 | 499 | 3190.49 | 51.76
25-PC-36051 | 1 | 500 | 0 | 0
25-PC-36071 | 1 | 501 | 0 | 128.13
25-PC-36071 | 0 |  | 0 | 118.65
25-PC-36093 | 1 | 502 | 0 | 0
25-PC-36093 | 0 |  | 703.27 | 18
25-PC-36129 | 1 | 503 | 5347.9 | 37.74
25-PC-36129 | 0 |  | 3727.35 | 0
25-PC-36129 | 0 |  | 0 | 0
25-PC-36129 | 0 |  | 4659.08 | 33.81
25-PC-36129 | 0 |  | 1249.89 | 18.5
25-PC-36129 | 0 |  | 857.27 | 11.75
25-PC-36197 | 1 | 504 | 0 | 0
25-PC-36197 | 0 |  | 0 | 0
25-PC-36197 | 0 |  | 0 | 0
25-PC-36197 | 0 |  | 0 | 0
25-PC-36197 | 0 |  | 0 | 0
25-PC-36251 | 1 | 505 | 9136.32 | 127.27
25-PC-36251 | 0 |  | 3027.29 | 31.52
25-PC-36251 | 0 |  | 1212.98 | 12.46
25-PC-36251 | 0 |  | 2631.86 | 30.3
25-PC-36251 | 0 |  | 2631.06 | 39.82
25-PC-36251 | 0 |  | 249.4 | 3.25
25-PC-36263 | 1 | 506 | 0 | 0
25-PC-36263 | 0 |  | 247.45 | 5.5
25-PC-36313 | 1 | 507 | 19560.98 | 424.47
25-PC-36313 | 0 |  | 3698.05 | 61.87
25-PC-36313 | 0 |  | 5148.45 | 142.32
25-PC-36332 | 1 | 508 | 0 | 0
25-PC-36332 | 0 |  | 0 | 0
25-PC-36332 | 0 |  | 1497.11 | 31.5
25-PC-36336 | 1 | 509 | 548.4 | 10.61
25-PC-36336 | 0 |  | 0 | 2.39
25-PC-36336 | 0 |  | 0 | 27.54
25-PC-36336 | 0 |  | 1081.58 | 6.97
25-PC-36336 | 0 |  | 59.59 | 1.25
25-PC-36352 | 1 | 510 | 0 | 0
25-PC-36352 | 0 |  | 0 | 0
25-PC-36352 | 0 |  | 1935.75 | 31.5
25-PC-36366 | 1 | 511 | 0 | 0
25-PC-36366 | 0 |  | 0 | 0
25-PC-36366 | 0 |  | 156.71 | 3.25
25-PC-36464 | 1 | 512 | 0 | 0
25-PC-36464 | 0 |  | 0 | 0
25-PC-36464 | 0 |  | 0 | 0
25-PC-36464 | 0 |  | 0 | 0
25-PC-36464 | 0 |  | -605.25 | -5
25-PC-36485 | 1 | 513 | 851.53 | 12.05
25-PC-36485 | 0 |  | 2146.02 | 31.46
25-PC-36485 | 0 |  | 3436.57 | 72.53
25-PC-36485 | 0 |  | 1172.24 | 33.41
25-PC-36485 | 0 |  | 589.4 | 37.95
25-PC-36485 | 0 |  | 211.03 | 2.75
25-PC-36507 | 1 | 514 | 0 | 86.6
25-PC-36507 | 0 |  | 546.42 | 12
25-PC-36532 | 1 | 515 | 0 | 0
25-PC-36532 | 0 |  | 0 | 0
25-PC-36532 | 0 |  | 0 | 0
25-PC-36532 | 0 |  | 0 | 0
25-PC-36573 | 1 | 516 | 0 | 0
25-PC-36637 | 1 | 517 | 0 | 75.17
25-PC-36637 | 0 |  | 0 | 3.53
25-PC-36637 | 0 |  | 0 | 14.42
25-PC-36641 | 1 | 518 | 40288.97 | 548.01
25-PC-36641 | 0 |  | 5506.32 | 89.32
25-PC-36641 | 0 |  | 1385.58 | 22.5
25-PC-36645 | 1 | 519 | 7407.34 | 0
25-PC-36645 | 0 |  | 10246.12 | 90.96
25-PC-36645 | 0 |  | 966.92 | 20.25
25-PC-36646 | 1 | 520 | 0 | 0
25-PC-36646 | 0 |  | 0 | 0
25-PC-36646 | 0 |  | 0 | 0
25-PC-36646 | 0 |  | 0 | 0
25-PC-36646 | 0 |  | 538.19 | 6.75
25-PC-36657 | 1 | 521 | 0 | 0
25-PC-36657 | 0 |  | 549.98 | 9.5
25-PC-36697 | 1 | 522 | 0 | 0
25-PC-36697 | 0 |  | 0 | 0
25-PC-36697 | 0 |  | 0 | 0
25-PC-36697 | 0 |  | 0 | 0
25-PC-36697 | 0 |  | 0 | 0
25-PC-36761 | 1 | 523 | 9456.38 | 436.6
25-PC-36761 | 0 |  | 264.37 | 6.25
25-PC-36799 | 1 | 524 | 3625.62 | 174.77
25-PC-36799 | 0 |  | 2731.32 | 148.05
25-PC-36799 | 0 |  | 302.49 | 4
25-PC-36809 | 1 | 525 | 9926.74 | 114.08
25-PC-36809 | 0 |  | 258.05 | 6.75
25-PC-36832 | 1 | 526 | 0 | 0
25-PC-36832 | 0 |  | 0 | 0
25-PC-36838 | 1 | 527 | 0 | 50.53
25-PC-36838 | 0 |  | 5934.44 | 149.99
25-PC-36838 | 0 |  | 0 | 0
25-PC-36838 | 0 |  | 9999 | 150.08
25-PC-36838 | 0 |  | 2632.24 | 38.25
25-PC-36876 | 1 | 528 | 19249.08 | 0
25-PC-36876 | 0 |  | 9409.39 | 0
25-PC-36876 | 0 |  | 10473.51 | 0
25-PC-36876 | 0 |  | 33073.64 | 0
25-PC-36896 | 1 | 529 | 6237.91 | 208.72
25-PC-36896 | 0 |  | 9570.19 | 312.86
25-PC-36896 | 0 |  | 4602.76 | 183.77
25-PC-36896 | 0 |  | 2044.24 | 53.36
25-PC-36909 | 1 | 530 | 168.41 | 0
25-PC-36909 | 0 |  | 833.96 | 32.21
25-PC-36909 | 0 |  | 363.14 | 6.81
25-PC-36909 | 0 |  | 300.91 | 21.1
25-PC-36971 | 1 | 531 | 1778.96 | 44.38
25-PC-36971 | 0 |  | 5884.74 | 34.41
25-PC-36971 | 0 |  | 9347.77 | 180.79
25-PC-36971 | 0 |  | 2455.16 | 71.5
25-PC-36988 | 1 | 532 | 0 | 194.2
25-PC-36988 | 0 |  | 0 | 28.56
25-PC-36988 | 0 |  | 0 | 107.45
25-PC-36988 | 0 |  | 0 | 396.32
25-PC-36993 | 1 | 533 | 0 | 0
25-PC-36993 | 0 |  | 0 | 0
25-PC-36993 | 0 |  | 0 | 0
25-PC-37164 | 1 | 534 | 38823.21 | 500.96
25-PC-37164 | 0 |  | 1779.37 | 16.75
25-PC-37188 | 1 | 535 | 0 | 0
25-PC-37188 | 0 |  | 0 | 0
25-PC-37188 | 0 |  | 0 | 42.6
25-PC-37359 | 1 | 536 | 0 | 0
25-PC-37359 | 0 |  | 0 | 0
25-PC-37359 | 0 |  | 0 | 0
25-PC-37371 | 1 | 537 | 0 | 0
25-PC-37371 | 0 |  | 0 | 0
25-PC-37371 | 0 |  | 0 | 0
25-PC-37371 | 0 |  | 1510.29 | 26.5
25-PC-37392 | 1 | 538 | 4733.33 | 83.71
25-PC-37392 | 0 |  | 0 | 0
25-PC-37392 | 0 |  | 773.53 | 8.25
25-PC-37461 | 1 | 539 | 13467.57 | 499.33
25-PC-37461 | 0 |  | 4588.49 | 144.27
25-PC-37487 | 1 | 540 | 0 | 0
25-PC-37509 | 1 | 541 | 0 | 0
25-PC-37522 | 1 | 542 | 436.25 | 18.8
25-PC-37522 | 0 |  | 0 | 1.3
25-PC-37522 | 0 |  | 0 | 0
25-PC-37522 | 0 |  | 2228.3 | 29.13
25-PC-37522 | 0 |  | 3490.79 | 70.66
25-PC-37522 | 0 |  | 220.6 | 5.5
25-PC-37544 | 1 | 543 | 0 | 641.62
25-PC-37544 | 0 |  | 0 | 28.01
25-PC-37612 | 1 | 544 | 0 | 0
25-PC-37612 | 0 |  | 0 | 0
25-PC-37612 | 0 |  | 0 | 0
25-PC-37612 | 0 |  | 0 | 0
25-PC-37612 | 0 |  | 0 | 0
25-PC-37630 | 1 | 545 | 109799.69 | 2755.37
25-PC-37675 | 1 | 546 | 0 | 61.19
25-PC-37675 | 0 |  | 0 | 197.3
25-PC-37675 | 0 |  | 0 | 205.84
25-PC-37732 | 1 | 547 | 0 | 2.38
25-PC-37732 | 0 |  | 4827.5 | 67.87
25-PC-37732 | 0 |  | 1613.56 | 25.06
25-PC-37732 | 0 |  | 0 | 0
25-PC-37732 | 0 |  | 0 | 0.76
25-PC-37732 | 0 |  | 65.86 | 1
25-PC-37786 | 1 | 548 | 12474.43 | 73.39
25-PC-37786 | 0 |  | 22.13 | 0.5
25-PC-37841 | 1 | 549 | 0 | 0
25-PC-37841 | 0 |  | 0 | 0
25-PC-37841 | 0 |  | 0 | 0
25-PC-37841 | 0 |  | 0 | 0
25-PC-37881 | 1 | 550 | 236.02 | 0
25-PC-37881 | 0 |  | 372.69 | 8.03
25-PC-37903 | 1 | 551 | 38523.42 | 410.33
25-PC-37920 | 1 | 552 | 0 | 0
25-PC-37920 | 0 |  | 634.58 | 15
25-PC-37975 | 1 | 553 | 368.54 | 27.08
25-PC-37975 | 0 |  | 0 | 0
25-PC-37975 | 0 |  | 0 | 0
25-PC-37975 | 0 |  | 79.88 | 2
25-PC-37979 | 1 | 554 | 7869.39 | 524.24
25-PC-37979 | 0 |  | 2822.33 | 168.44
25-PC-37979 | 0 |  | 3157.5 | 146.42
25-PC-37979 | 0 |  | 4696.93 | 284.67
25-PC-37979 | 0 |  | 11292.82 | 892.56
25-PC-37994 | 1 | 555 | 0 | 0
25-PC-37994 | 0 |  | 0 | 0
25-PC-37994 | 0 |  | 0 | 0
25-PC-38006 | 1 | 556 | 0 | 0
25-PC-38006 | 0 |  | 0 | 0
25-PC-38006 | 0 |  | 0 | 0
25-PC-38006 | 0 |  | 537.19 | 12.25
25-PC-38036 | 1 | 557 | 2070.28 | 77.12
25-PC-38036 | 0 |  | 934.27 | 30.01
25-PC-38036 | 0 |  | 1112.35 | 44.87
25-PC-38036 | 0 |  | 2888.83 | 138.87
25-PC-38042 | 1 | 558 | 0 | 0.45
25-PC-38042 | 0 |  | 0 | 11.45
25-PC-38042 | 0 |  | 0 | 9.15
25-PC-38042 | 0 |  | 0 | 18.58
25-PC-38070 | 1 | 559 | 0 | 0
25-PC-38070 | 0 |  | 0 | 0
25-PC-38070 | 0 |  | 0 | 0
25-PC-38107 | 1 | 560 | 0 | 0
25-PC-38107 | 0 |  | 0 | 0
25-PC-38107 | 0 |  | 858.71 | 21.5
25-PC-38180 | 1 | 561 | 0 | 0
25-PC-38180 | 0 |  | 0 | 0
25-PC-38180 | 0 |  | 0 | 0
25-PC-38180 | 0 |  | 116.7 | 2.5
25-PC-38196 | 1 | 562 | 0 | 91.77
25-PC-38196 | 0 |  | 0 | 121.77
25-PC-38196 | 0 |  | 130.49 | 2.75
25-PC-38282 | 1 | 563 | 0 | 0
25-PC-38282 | 0 |  | 0 | 0
25-PC-38282 | 0 |  | 0 | 0
25-PC-38296 | 1 | 564 | 0 | 0
25-PC-38296 | 0 |  | 0 | 62.16
25-PC-38296 | 0 |  | 0 | 35.68
25-PC-38296 | 0 |  | 1231.77 | 29.25
25-PC-38332 | 1 | 565 | 0 | 0
25-PC-38332 | 0 |  | 0 | 0
25-PC-38332 | 0 |  | 0 | 182.87
25-PC-38332 | 0 |  | 167.65 | 3.5
25-PC-38333 | 1 | 566 | 0 | 0
25-PC-38333 | 0 |  | 0 | 47.89
25-PC-38352 | 1 | 567 | 0 | 0
25-PC-38461 | 1 | 568 | 0 | 0
25-PC-38461 | 0 |  | 0 | 0
25-PC-38461 | 0 |  | 0 | 0
25-PC-38461 | 0 |  | 0 | 0
25-PC-38540 | 1 | 569 | 0 | 143.75
25-PC-38540 | 0 |  | 0 | 0
25-PC-38540 | 0 |  | 30697.6 | 647.04
25-PC-38540 | 0 |  | 3988.28 | 68.75
25-PC-38563 | 1 | 570 | 0 | 0
25-PC-38563 | 0 |  | 2453.02 | 55.45
25-PC-38563 | 0 |  | 6268.71 | 71.43
25-PC-38563 | 0 |  | 0 | 0
25-PC-38563 | 0 |  | 0 | 82.41
25-PC-38563 | 0 |  | 767.64 | 18.25
25-PC-38596 | 1 | 571 | 0 | 0
25-PC-38596 | 0 |  | 0 | 0
25-PC-38596 | 0 |  | 0 | 0
25-PC-38596 | 0 |  | 0 | 0
25-PC-38596 | 0 |  | 0 | 0
25-PC-38606 | 1 | 572 | 0 | 0
25-PC-38606 | 0 |  | 0 | 0
25-PC-38606 | 0 |  | 0 | 0
25-PC-38659 | 1 | 573 | 0 | 0
25-PC-38701 | 1 | 574 | 0 | 0
25-PC-38701 | 0 |  | 0 | 0
25-PC-38701 | 0 |  | 900.4 | 20.75
25-PC-38754 | 1 | 575 | 8105.26 | 92.27
25-PC-38754 | 0 |  | 2155.44 | 9.95
25-PC-38754 | 0 |  | 4898.34 | 105.42
25-PC-38754 | 0 |  | 3252.07 | 71.87
25-PC-38754 | 0 |  | 722.04 | 13
25-PC-38835 | 1 | 576 | 12420.4 | 236.74
25-PC-38835 | 0 |  | -269.51 | -3.25
25-PC-38879 | 1 | 577 | 0 | 83.94
25-PC-38879 | 0 |  | 0 | 103.62
25-PC-38879 | 0 |  | 0 | 210.15
25-PC-38970 | 1 | 578 | 2404.06 | 0
25-PC-38970 | 0 |  | 1396.59 | 21.76
25-PC-38970 | 0 |  | 3484.49 | 6.08
25-PC-38970 | 0 |  | 5677.4 | 69.76
25-PC-39035 | 1 | 579 | 0 | 79.77
25-PC-39035 | 0 |  | 0 | 115.67
25-PC-39035 | 0 |  | 40.51 | 132.36
25-PC-39035 | 0 |  | 5245.44 | 146.09
25-PC-39035 | 0 |  | 0 | 168.22
25-PC-39035 | 0 |  | 2973.49 | 64.75
25-PC-39055 | 1 | 580 | 18239.01 | 0
25-PC-39085 | 1 | 581 | 0 | 0
25-PC-39085 | 0 |  | 402.51 | 8.5
25-PC-39093 | 1 | 582 | 0 | 0
25-PC-39093 | 0 |  | 0 | 0
25-PC-39093 | 0 |  | 782.06 | 18.75
25-PC-39118 | 1 | 583 | 0 | 7.03
25-PC-39118 | 0 |  | 308.89 | 7.75
25-PC-39187 | 1 | 584 | 0 | 0.54
25-PC-39187 | 0 |  | 0 | 4.92
25-PC-39187 | 0 |  | 0 | 0
25-PC-39222 | 1 | 585 | 0 | 0
25-PC-39222 | 0 |  | 0 | 0
25-PC-39222 | 0 |  | 0 | 0
25-PC-39222 | 0 |  | 0 | 0
25-PC-39318 | 1 | 586 | 0 | 0
25-PC-39318 | 0 |  | 0 | 0
25-PC-39318 | 0 |  | 145.5 | 3
25-PC-39358 | 1 | 587 | 3967.91 | 65.28
25-PC-39358 | 0 |  | 0 | 15.15
25-PC-39358 | 0 |  | 0 | 5.07
25-PC-39358 | 0 |  | 0 | 0
25-PC-39358 | 0 |  | 3653.62 | 79.4
25-PC-39358 | 0 |  | 555.69 | 12.75
25-PC-39398 | 1 | 588 | 0 | 0
25-PC-39398 | 0 |  | 0 | 0
25-PC-39398 | 0 |  | 0 | 0
25-PC-39398 | 0 |  | 0 | 0
25-PC-39398 | 0 |  | 0 | 0
25-PC-39422 | 1 | 589 | 0 | 0
25-PC-39422 | 0 |  | 0 | 0
25-PC-39422 | 0 |  | -154.89 | -3.25
25-PC-39424 | 1 | 590 | 2520.5 | 22.46
25-PC-39424 | 0 |  | -135.25 | -2.25
25-PC-39458 | 1 | 591 | 0 | 0
25-PC-39458 | 0 |  | 0 | 0
25-PC-39458 | 0 |  | 312.06 | 0
25-PC-39458 | 0 |  | 0 | 0
25-PC-39458 | 0 |  | 1001.38 | 16
25-PC-39489 | 1 | 592 | 0 | 0
25-PC-39489 | 0 |  | 0 | 0
25-PC-39489 | 0 |  | 0 | 0
25-PC-39489 | 0 |  | 0 | 0
25-PC-39554 | 1 | 593 | 0 | 75.62
25-PC-39554 | 0 |  | 218.82 | 4.75
25-PC-39569 | 1 | 594 | 0 | 0
25-PC-39569 | 0 |  | 0 | 0
25-PC-39569 | 0 |  | 0 | 89.69
25-PC-39569 | 0 |  | 0 | 9.49
25-PC-39661 | 1 | 595 | 0 | 0
25-PC-39765 | 1 | 596 | 15364 | 206.53
25-PC-39765 | 0 |  | 11491.48 | 161.17
25-PC-39765 | 0 |  | 2672.4 | 48.39
25-PC-39765 | 0 |  | 8304.34 | 109.26
25-PC-39765 | 0 |  | 813.12 | 14
25-PC-39808 | 1 | 597 | 0 | 0
25-PC-39808 | 0 |  | 0 | 0
25-PC-39808 | 0 |  | 1556.11 | 51.28
25-PC-39808 | 0 |  | 0 | 0
25-PC-39808 | 0 |  | 0 | 0
25-PC-39808 | 0 |  | 398.19 | 9
25-PC-39873 | 1 | 598 | 0 | 0
25-PC-39873 | 0 |  | 0 | 0
25-PC-39873 | 0 |  | 0 | 0
25-PC-39873 | 0 |  | 0 | 0
25-PC-39873 | 0 |  | 0 | 0
25-PC-39873 | 0 |  | 1017.05 | 15.75
25-PC-39885 | 1 | 599 | 0 | 0
25-PC-39885 | 0 |  | 0 | 4.92
25-PC-39885 | 0 |  | 238.66 | 3.5
25-PC-39896 | 1 | 600 | 0 | 457.43
25-PC-39896 | 0 |  | 0 | 0
25-PC-39896 | 0 |  | 0 | 50.1
25-PC-39896 | 0 |  | -2.6 | -0.25
25-PC-39951 | 1 | 601 | 0 | 0
25-PC-39951 | 0 |  | 0 | 0
25-PC-39951 | 0 |  | 0 | 0
25-PC-39951 | 0 |  | 0 | 0
25-PC-40020 | 1 | 602 | 0 | 0
25-PC-40020 | 0 |  | 0 | 0
25-PC-40020 | 0 |  | 0 | 0
25-PC-40020 | 0 |  | 0 | 0
25-PC-40020 | 0 |  | 0 | 0
25-PC-40099 | 1 | 603 | 138060.34 | 3917.87
25-PC-40170 | 1 | 604 | 0 | 0
25-PC-40205 | 1 | 605 | 0 | 11.13
25-PC-40205 | 0 |  | 0 | 39.76
25-PC-40205 | 0 |  | 0 | 114.42
25-PC-40205 | 0 |  | 0 | 56.22
25-PC-40205 | 0 |  | 0 | 0
25-PC-40231 | 1 | 606 | 0 | 0
25-PC-40231 | 0 |  | 0 | 0
25-PC-40231 | 0 |  | 842.98 | 19.75
25-PC-40248 | 1 | 607 | 2919.35 | 281.77
25-PC-40248 | 0 |  | 1800.68 | 104.55
25-PC-40248 | 0 |  | 450.24 | 11.55
25-PC-40248 | 0 |  | 824.19 | 0
25-PC-40383 | 1 | 608 | 0 | 192.15
25-PC-40383 | 0 |  | 0 | 71.29
25-PC-40383 | 0 |  | 808.96 | 18.75
25-PC-40465 | 1 | 609 | 0 | 0
25-PC-40465 | 0 |  | 914.13 | 20.75
25-PC-40482 | 1 | 610 | 0 | 0
25-PC-40482 | 0 |  | 929.83 | 0
25-PC-40482 | 0 |  | 0 | 0
25-PC-40482 | 0 |  | 0 | 0
25-PC-40482 | 0 |  | 0 | 0
25-PC-40482 | 0 |  | 364.48 | 7.75
25-PC-40501 | 1 | 611 | 0 | 2519.4
25-PC-40501 | 0 |  | 0 | 1602.4
25-PC-40503 | 1 | 612 | 11711.68 | 0
25-PC-40503 | 0 |  | 532.95 | 13
25-PC-40523 | 1 | 613 | 11592.59 | 150.6
25-PC-40523 | 0 |  | 14468.62 | 195.58
25-PC-40523 | 0 |  | 759.09 | 18.75
25-PC-40541 | 1 | 614 | 0 | 0
25-PC-40572 | 1 | 615 | 0 | 0
25-PC-40572 | 0 |  | 0 | 0
25-PC-40572 | 0 |  | 0 | 0
25-PC-40572 | 0 |  | 0 | 0
25-PC-40572 | 0 |  | 175.61 | 4.75
25-PC-40595 | 1 | 616 | 0 | 0
25-PC-40595 | 0 |  | 0 | 0
25-PC-40595 | 0 |  | 0 | 0
25-PC-40595 | 0 |  | 1793.94 | 30.75
25-PC-40677 | 1 | 617 | 1858.97 | 203.71
25-PC-40677 | 0 |  | 0 | 218.87
25-PC-40677 | 0 |  | 1184.64 | 122.38
25-PC-40677 | 0 |  | 260.21 | 74.46
25-PC-40677 | 0 |  | 0 | 8.28
25-PC-40677 | 0 |  | 290.24 | 7
25-PC-40680 | 1 | 618 | 0 | 35.42
25-PC-40680 | 0 |  | 0 | 0
25-PC-40680 | 0 |  | 166.85 | 4.25
25-PC-40708 | 1 | 619 | 0 | 68.03
25-PC-40708 | 0 |  | 0 | 24.68
25-PC-40722 | 1 | 620 | 0 | 84.62
25-PC-40722 | 0 |  | 0 | 46.43
25-PC-40722 | 0 |  | 0 | 11.48
25-PC-40722 | 0 |  | 0 | 99.42
25-PC-40810 | 1 | 621 | 128.29 | 0
25-PC-40810 | 0 |  | 0 | 0
25-PC-40810 | 0 |  | 3432.29 | 82.39
25-PC-40810 | 0 |  | 85.87 | 1.16
25-PC-40810 | 0 |  | 928.41 | 21.25
25-PC-40847 | 1 | 622 | 0 | 66.03
25-PC-40847 | 0 |  | 4241.92 | 137.34
25-PC-40847 | 0 |  | 233.89 | 5.25
25-PC-40880 | 1 | 623 | 0 | 0
25-PC-40880 | 0 |  | 0 | 0
25-PC-40880 | 0 |  | 0 | 0
25-PC-40880 | 0 |  | 282.79 | 6.75
25-PC-40925 | 1 | 624 | 0 | 0
25-PC-40925 | 0 |  | 0 | 0
25-PC-40925 | 0 |  | 0 | 0
25-PC-40925 | 0 |  | 0 | 0
25-PC-40944 | 1 | 625 | 21948.03 | 0
25-PC-41075 | 1 | 626 | 0 | 0
25-PC-41075 | 0 |  | 740.58 | 18.25
25-PC-41083 | 1 | 627 | 0 | 0
25-PC-41097 | 1 | 628 | 0 | 549
25-PC-41097 | 0 |  | 0 | 440.64
25-PC-41097 | 0 |  | 1793.09 | 39
25-PC-41187 | 1 | 629 | 0 | 0
25-PC-41187 | 0 |  | 0 | 0
25-PC-41187 | 0 |  | 502.25 | 10.75
25-PC-41252 | 1 | 630 | 0 | 52.39
25-PC-41252 | 0 |  | 138.12 | 3.25
25-PC-41265 | 1 | 631 | 0 | 0
25-PC-41265 | 0 |  | 0 | 177.88
25-PC-41341 | 1 | 632 | 0 | 117.42
25-PC-41372 | 1 | 633 | 0 | 0
25-PC-41372 | 0 |  | 0 | 0
25-PC-41383 | 1 | 634 | 0 | 0
25-PC-41383 | 0 |  | 0 | 0
25-PC-41383 | 0 |  | 0 | 0
25-PC-41383 | 0 |  | 63.75 | 1.5
25-PC-41385 | 1 | 635 | 19123.76 | 213.37
25-PC-41385 | 0 |  | 34820.51 | 373.79
25-PC-41385 | 0 |  | 686.88 | 92.09
25-PC-41385 | 0 |  | 0 | 178.54
25-PC-41385 | 0 |  | 2224.66 | 24
25-PC-41476 | 1 | 636 | 4544.04 | 61.45
25-PC-41476 | 0 |  | 14314.99 | 318.2
25-PC-41476 | 0 |  | 4668.08 | 49.62
25-PC-41476 | 0 |  | 14205.63 | 159.79
25-PC-41476 | 0 |  | 6308.56 | 212.65
25-PC-41479 | 1 | 637 | 0 | 0
25-PC-41479 | 0 |  | 0 | 0
25-PC-41479 | 0 |  | 0 | 0
25-PC-41479 | 0 |  | 0 | 0
25-PC-41479 | 0 |  | 0 | 0
25-PC-41479 | 0 |  | 652.02 | 13.75
25-PC-41500 | 1 | 638 | 7953.09 | 0
25-PC-41500 | 0 |  | 337.44 | 0
25-PC-41500 | 0 |  | 730.19 | 0
25-PC-41500 | 0 |  | 981.99 | 0
25-PC-41500 | 0 |  | 1388.68 | 33.25
25-PC-41514 | 1 | 639 | 0 | 0
25-PC-41514 | 0 |  | 0 | 0
25-PC-41514 | 0 |  | 714.91 | 31.36
25-PC-41514 | 0 |  | 0 | 0
25-PC-41514 | 0 |  | 83.1 | 2
25-PC-41600 | 1 | 640 | 0 | 340.13
25-PC-41603 | 1 | 641 | 4423.82 | 61.02
25-PC-41603 | 0 |  | 1089.13 | 28.87
25-PC-41603 | 0 |  | 3624.74 | 76.8
25-PC-41603 | 0 |  | 6104.77 | 113.35
25-PC-41635 | 1 | 642 | 0 | 191.76
25-PC-41635 | 0 |  | 10949.59 | 551.18
25-PC-41635 | 0 |  | 0 | 74.94
25-PC-41635 | 0 |  | 908.29 | 21
25-PC-41722 | 1 | 643 | 0 | 0
25-PC-41722 | 0 |  | 0 | 0
25-PC-41722 | 0 |  | 1015.62 | 22.5
25-PC-41764 | 1 | 644 | 0 | 61.8
25-PC-41834 | 1 | 645 | 0 | 0
25-PC-41834 | 0 |  | 0 | 0
25-PC-41834 | 0 |  | 0 | 0
25-PC-41834 | 0 |  | 0 | 0
25-PC-41834 | 0 |  | 306.45 | 6.75
25-PC-41843 | 1 | 646 | 0 | 0
25-PC-41854 | 1 | 647 | 3779.52 | 50.82
25-PC-41854 | 0 |  | 0 | 0
25-PC-41854 | 0 |  | 2883.19 | 26.54
25-PC-41931 | 1 | 648 | 0 | 20.59
25-PC-41931 | 0 |  | 0 | 67.79
25-PC-41931 | 0 |  | 0 | 104.12
25-PC-41967 | 1 | 649 | 0 | 0
25-PC-41967 | 0 |  | 0 | 0
25-PC-41967 | 0 |  | 0 | 0
25-PC-41967 | 0 |  | 0 | 0
25-PC-42076 | 1 | 650 | 0 | 0
25-PC-42076 | 0 |  | 0 | 0
25-PC-42076 | 0 |  | 0 | 0
25-PC-42076 | 0 |  | 1734.87 | 26.5
25-PC-42078 | 1 | 651 | 0 | 0
25-PC-42078 | 0 |  | 0 | 0
25-PC-42078 | 0 |  | 0 | 0
25-PC-42084 | 1 | 652 | 0 | 0
25-PC-42084 | 0 |  | 0 | 0
25-PC-42084 | 0 |  | 0 | 0
25-PC-42097 | 1 | 653 | 0 | 0
25-PC-42097 | 0 |  | 764.26 | 11.5
25-PC-42115 | 1 | 654 | 0 | 26.04
25-PC-42115 | 0 |  | 1755.29 | 32.5
25-PC-42136 | 1 | 655 | 0 | 0
25-PC-42163 | 1 | 656 | 0 | 0
25-PC-42163 | 0 |  | 0 | 37.17
25-PC-42163 | 0 |  | 0 | 0
25-PC-42163 | 0 |  | 34.77 | 0.75
25-PC-42227 | 1 | 657 | 2266.04 | 0
25-PC-42253 | 1 | 658 | 0 | 0
25-PC-42282 | 1 | 659 | 0 | 0
25-PC-42282 | 0 |  | 0 | 0
25-PC-42282 | 0 |  | 0 | 0
25-PC-42282 | 0 |  | 127.64 | 3
25-PC-42303 | 1 | 660 | 29930.7 | 1233.7
25-PC-42315 | 1 | 661 | 0 | 0
25-PC-42315 | 0 |  | 0 | 0
25-PC-42315 | 0 |  | 826.73 | 7.5
25-PC-42323 | 1 | 662 | 0 | 0
25-PC-42323 | 0 |  | 0 | 0
25-PC-42323 | 0 |  | 0 | 0
25-PC-42323 | 0 |  | 317.16 | 4
25-PC-42343 | 1 | 663 | 0 | 0
25-PC-42343 | 0 |  | 0 | 0
25-PC-42343 | 0 |  | 0 | 0
25-PC-42343 | 0 |  | 0 | 0
25-PC-42364 | 1 | 664 | 0 | 0
25-PC-42364 | 0 |  | 9.4 | 0.25
25-PC-42399 | 1 | 665 | 0 | 0
25-PC-42399 | 0 |  | 0 | 0
25-PC-42399 | 0 |  | 0 | 0
25-PC-42399 | 0 |  | 2743.58 | 55.25
25-PC-42528 | 1 | 666 | 0 | 0
25-PC-42528 | 0 |  | 0 | 0
25-PC-42528 | 0 |  | -145.47 | -3.5
25-PC-42569 | 1 | 667 | 0 | 22.11
25-PC-42569 | 0 |  | 0 | 26.58
25-PC-42569 | 0 |  | 0 | 0
25-PC-42569 | 0 |  | 0 | 6.5
25-PC-42601 | 1 | 668 | 0 | 0
25-PC-42601 | 0 |  | 661.38 | 6
25-PC-42717 | 1 | 669 | 0 | 21.34
25-PC-42717 | 0 |  | 0 | 73.52
25-PC-42717 | 0 |  | 932.92 | 63.72
25-PC-42717 | 0 |  | 0 | 168.59
25-PC-42717 | 0 |  | 0 | 33.85
25-PC-42717 | 0 |  | 389.14 | 10
25-PC-42747 | 1 | 670 | 0 | 0
25-PC-42747 | 0 |  | 0 | 0
25-PC-43037 | 1 | 671 | 4801.17 | 218.74
25-PC-43037 | 0 |  | 15166.52 | 691.83
25-PC-43037 | 0 |  | 13567.21 | 349.89
25-PC-43037 | 0 |  | 8693.59 | 464.39
25-PC-43061 | 1 | 672 | 0 | 0
25-PC-43061 | 0 |  | 0 | 0
25-PC-43061 | 0 |  | 0 | 0
25-PC-43073 | 1 | 673 | 2575.55 | 25.41
25-PC-43073 | 0 |  | 0 | 0
25-PC-43073 | 0 |  | 0 | 16.97
25-PC-43073 | 0 |  | 824.08 | 8
25-PC-43075 | 1 | 674 | 0 | 0
25-PC-43075 | 0 |  | 0 | 0
25-PC-43075 | 0 |  | 0 | 0
25-PC-43075 | 0 |  | 0 | 0
25-PC-43106 | 1 | 675 | 0 | 24.86
25-PC-43203 | 1 | 676 | 22639.02 | 272.13
25-PC-43203 | 0 |  | 40748.66 | 588.81
25-PC-43203 | 0 |  | 24088.64 | 355.14
25-PC-43203 | 0 |  | 1942.78 | 30
25-PC-43244 | 1 | 677 | 0 | 0
25-PC-43244 | 0 |  | 0 | 0
25-PC-43286 | 1 | 678 | 13296.33 | 161.11
25-PC-43286 | 0 |  | 25259.08 | 313.45
25-PC-43286 | 0 |  | 13386.94 | 160.48
25-PC-43286 | 0 |  | 6547.88 | 71.35
25-PC-43286 | 0 |  | 1774.48 | 24
25-PC-43315 | 1 | 679 | 0 | 1056.77
25-PC-43434 | 1 | 680 | 27201.92 | 2521.98
25-PC-43455 | 1 | 681 | 0 | 0
25-PC-43455 | 0 |  | 0 | 0
25-PC-43455 | 0 |  | 0 | 0
25-PC-43455 | 0 |  | 0 | 0
25-PC-43455 | 0 |  | 0 | 0
25-PC-43511 | 1 | 682 | 69576.67 | 1862.47
25-PC-43511 | 0 |  | 74217.49 | 597.51
25-PC-43511 | 0 |  | 66719.31 | 1985.49
25-PC-43566 | 1 | 683 | 13662.23 | 0
25-PC-43566 | 0 |  | 10283.73 | 0
25-PC-43566 | 0 |  | 11980.57 | 0
25-PC-43566 | 0 |  | 21045.67 | 0
25-PC-43566 | 0 |  | 598.43 | 7.5
25-PC-43590 | 1 | 684 | 0 | 0
25-PC-43621 | 1 | 685 | 0 | 0
25-PC-43621 | 0 |  | 1368.07 | 0
25-PC-43621 | 0 |  | 66.37 | 1
25-PC-43639 | 1 | 686 | 18492.73 | 275.24
25-PC-43639 | 0 |  | 0 | 0
25-PC-43639 | 0 |  | 1376.14 | 23.5
25-PC-43653 | 1 | 687 | 3190.38 | 0
25-PC-43653 | 0 |  | 19034.05 | 0
25-PC-43653 | 0 |  | 1205.16 | 0
25-PC-43653 | 0 |  | 1603.6 | 31.5
25-PC-43752 | 1 | 688 | 4474.22 | 0
25-PC-43752 | 0 |  | 1300.54 | 0
25-PC-43752 | 0 |  | 5025.8 | 0
25-PC-43771 | 1 | 689 | 0 | 0
25-PC-43771 | 0 |  | 561.48 | 12
25-PC-43844 | 1 | 690 | 1988.86 | 24.05
25-PC-43844 | 0 |  | 4762.48 | 68.17
25-PC-43844 | 0 |  | 0 | 0
25-PC-43844 | 0 |  | 1937.61 | 30.45
25-PC-43853 | 1 | 691 | 0 | 0
25-PC-43853 | 0 |  | 1607.71 | 62.28
25-PC-43853 | 0 |  | 1353.01 | 19.75
25-PC-43859 | 1 | 692 | 0 | 0
25-PC-43859 | 0 |  | 0 | 0
25-PC-43859 | 0 |  | 0 | 0
25-PC-43863 | 1 | 693 | 0 | 0
25-PC-43863 | 0 |  | 0 | 0
25-PC-43863 | 0 |  | 0 | 0
25-PC-43863 | 0 |  | 447.95 | 8.25
25-PC-43932 | 1 | 694 | 164.87 | 10.03
25-PC-43932 | 0 |  | 0 | 0
25-PC-43932 | 0 |  | 0 | 0
25-PC-43932 | 0 |  | 0 | 0
25-PC-43932 | 0 |  | 289.46 | 10.07
25-PC-43932 | 0 |  | 25.02 | 0.5
25-PC-43944 | 1 | 695 | 0 | 0
25-PC-43944 | 0 |  | 0 | 0
25-PC-43944 | 0 |  | 0 | 0
25-PC-43944 | 0 |  | 0 | 0
25-PC-43944 | 0 |  | 0 | 0
25-PC-43944 | 0 |  | 693.95 | 15.75
25-PC-43966 | 1 | 696 | 0 | 34.05
25-PC-43993 | 1 | 697 | 1852.86 | 26.27
25-PC-43993 | 0 |  | 0 | 0
25-PC-43993 | 0 |  | 0 | 0
25-PC-43993 | 0 |  | 2378.09 | 27.85
25-PC-43993 | 0 |  | 67.43 | 2.24
25-PC-43993 | 0 |  | 198.6 | 4
25-PC-44046 | 1 | 698 | 54805.73 | 0
25-PC-44046 | 0 |  | 1307.63 | 16.5
25-PC-44140 | 1 | 699 | 0 | 0
25-PC-44140 | 0 |  | 10429.35 | 144.12
25-PC-44140 | 0 |  | 7868.37 | 149.13
25-PC-44140 | 0 |  | 0 | 0
25-PC-44140 | 0 |  | 2381.53 | 39
25-PC-44186 | 1 | 700 | 0 | 0
25-PC-44186 | 0 |  | 0 | 0
25-PC-44186 | 0 |  | 0 | 0
25-PC-44186 | 0 |  | 693.06 | 16.25
25-PC-44198 | 1 | 701 | 7113.02 | 0
25-PC-44198 | 0 |  | 4906.6 | 0
25-PC-44198 | 0 |  | 0 | 0
25-PC-44198 | 0 |  | 1581.53 | 10.5
25-PC-44241 | 1 | 702 | 12314.75 | 0
25-PC-44241 | 0 |  | 30431.95 | 0
25-PC-44241 | 0 |  | 10873.4 | 0
25-PC-44241 | 0 |  | 14993.6 | 0
25-PC-44312 | 1 | 703 | 4296.35 | 302.61
25-PC-44312 | 0 |  | 2469.37 | 163.33
25-PC-44312 | 0 |  | 1272.45 | 15.25
26-PC-30013 | 1 | 704 | 0 | 0
26-PC-30013 | 0 |  | 410.1 | 6
26-PC-30057 | 1 | 705 | 0 | 0
26-PC-30057 | 0 |  | 665.35 | 9.25
26-PC-30065 | 1 | 706 | 0 | 0
26-PC-30065 | 0 |  | 0 | 0
26-PC-30065 | 0 |  | 0 | 0
26-PC-30065 | 0 |  | 0 | 0
26-PC-30065 | 0 |  | 723.1 | 8.75
26-PC-30094 | 1 | 707 | 0 | 0
26-PC-30094 | 0 |  | 0 | 0
26-PC-30115 | 1 | 708 | 134.83 | 56.79
26-PC-30115 | 0 |  | 55.21 | 0
26-PC-30123 | 1 | 709 | 0 | 0
26-PC-30123 | 0 |  | 0 | 0
26-PC-30123 | 0 |  | 0 | 0
26-PC-30123 | 0 |  | 1725.33 | 25.25
26-PC-30139 | 1 | 710 | 0 | 0
26-PC-30139 | 0 |  | 0 | 0
26-PC-30139 | 0 |  | 537.16 | 6.5
26-PC-30180 | 1 | 711 | 0 | 0
26-PC-30180 | 0 |  | 0 | 0
26-PC-30180 | 0 |  | 159.59 | 4.25
26-PC-30185 | 1 | 712 | 0 | 0
26-PC-30185 | 0 |  | 0 | 0
26-PC-30185 | 0 |  | 0 | 0
26-PC-30185 | 0 |  | 0 | 0
26-PC-30185 | 0 |  | 0 | 0
26-PC-30203 | 1 | 713 | 0 | 0
26-PC-30203 | 0 |  | 0 | 0
26-PC-30211 | 1 | 714 | 0 | 0
26-PC-30211 | 0 |  | 0 | 0
26-PC-30211 | 0 |  | 0 | 0
26-PC-30273 | 1 | 715 | 0 | 0
26-PC-30273 | 0 |  | 0 | 0
26-PC-30273 | 0 |  | 0 | 0
26-PC-30273 | 0 |  | 309.76 | 8
26-PC-30287 | 1 | 716 | 0 | 0
26-PC-30287 | 0 |  | 0 | 0
26-PC-30287 | 0 |  | 59.97 | 1.5
26-PC-30329 | 1 | 717 | 0 | 0
26-PC-30329 | 0 |  | 0 | 0
26-PC-30329 | 0 |  | 0 | 0
26-PC-30329 | 0 |  | 1101.92 | 25.5
26-PC-30338 | 1 | 718 | 0 | 0
26-PC-30338 | 0 |  | 0 | 0
26-PC-30338 | 0 |  | 0 | 0
26-PC-30338 | 0 |  | 0 | 0
26-PC-30349 | 1 | 719 | 0 | 0
26-PC-30349 | 0 |  | 0 | 0
26-PC-30349 | 0 |  | 0 | 0
26-PC-30349 | 0 |  | 0 | 0
26-PC-30349 | 0 |  | -32.21 | 1.5
26-PC-30351 | 1 | 720 | 0 | 0
26-PC-30351 | 0 |  | 0 | 0
26-PC-30351 | 0 |  | 0 | 0
26-PC-30351 | 0 |  | 0 | 0
26-PC-30351 | 0 |  | 425.94 | 6.5
26-PC-30396 | 1 | 721 | 0 | 0
26-PC-30396 | 0 |  | 0 | 0
26-PC-30396 | 0 |  | 0 | 0
26-PC-30396 | 0 |  | 0 | 0
26-PC-30402 | 1 | 722 | 0 | 0
26-PC-30402 | 0 |  | 0 | 0
26-PC-30402 | 0 |  | 0 | 0
26-PC-30402 | 0 |  | 0 | 0
26-PC-30425 | 1 | 723 | 0 | 0
26-PC-30425 | 0 |  | 0 | 0
26-PC-30425 | 0 |  | 0 | 1.82
26-PC-30425 | 0 |  | 0 | 0
26-PC-30432 | 1 | 724 | 101.75 | 31.73
26-PC-30432 | 0 |  | 94.47 | 20.84
26-PC-30432 | 0 |  | 167.92 | 59.52
26-PC-30432 | 0 |  | 566.13 | 281.82
26-PC-30432 | 0 |  | 289.77 | 84.49
26-PC-30457 | 1 | 725 | 0 | 0
26-PC-30457 | 0 |  | 0 | 0
26-PC-30457 | 0 |  | 1103.34 | 12.75
26-PC-30480 | 1 | 726 | 9344.91 | 319.39
26-PC-30480 | 0 |  | 5332.47 | 95.46
26-PC-30480 | 0 |  | 19131.76 | 651.72
26-PC-30480 | 0 |  | 4361.61 | 197.49
26-PC-30501 | 1 | 727 | 0 | 0
26-PC-30501 | 0 |  | 1251.18 | 51.75
26-PC-30501 | 0 |  | 1333.73 | 34.5
26-PC-30501 | 0 |  | 367.11 | 25
26-PC-30501 | 0 |  | 836.46 | 19
26-PC-30501 | 0 |  | 578.34 | 12.75
26-PC-30528 | 1 | 728 | 0 | 0
26-PC-30528 | 0 |  | 0 | 0
26-PC-30528 | 0 |  | 576.57 | 13.5
26-PC-30554 | 1 | 729 | 0 | 0
26-PC-30554 | 0 |  | 0 | 0
26-PC-30577 | 1 | 730 | 0 | 0
26-PC-30577 | 0 |  | 0 | 0
26-PC-30577 | 0 |  | 0 | 0
26-PC-30577 | 0 |  | 0 | 0
26-PC-30577 | 0 |  | 0 | 0
26-PC-30588 | 1 | 731 | 0 | 0
26-PC-30588 | 0 |  | 0 | 0
26-PC-30589 | 1 | 732 | 32550.79 | 0
26-PC-30602 | 1 | 733 | 0 | 0
26-PC-30602 | 0 |  | 0 | 0
26-PC-30602 | 0 |  | 1501.21 | 21.25
26-PC-30634 | 1 | 734 | 4159.6 | 135.02
26-PC-30754 | 1 | 735 | 0 | 0
26-PC-30754 | 0 |  | 0 | 0
26-PC-30754 | 0 |  | 0 | 0
26-PC-30754 | 0 |  | 0 | 0
26-PC-30781 | 1 | 736 | 7457.98 | 443.19
26-PC-30781 | 0 |  | 1827.78 | 75.62
26-PC-30781 | 0 |  | 1800.84 | 28.52
26-PC-30815 | 1 | 737 | 0 | 0
26-PC-30815 | 0 |  | 0 | 0
26-PC-30871 | 1 | 738 | 0 | 115.53
26-PC-30871 | 0 |  | 0 | 0
26-PC-30871 | 0 |  | 0 | 0
26-PC-30896 | 1 | 739 | 0 | 0
26-PC-30896 | 0 |  | 0 | 0
26-PC-30896 | 0 |  | 0 | 0
26-PC-30917 | 1 | 740 | 0 | 334.29
26-PC-30917 | 0 |  | 0 | 364.94
26-PC-30945 | 1 | 741 | 0 | 0
26-PC-30945 | 0 |  | 0 | 0
26-PC-30945 | 0 |  | 0 | 0
26-PC-30945 | 0 |  | 3105.34 | 0
26-PC-30945 | 0 |  | 0 | 0
26-PC-30945 | 0 |  | 1131.84 | 23.25
26-PC-30967 | 1 | 742 | 0 | 31
26-PC-30967 | 0 |  | 0 | 77
26-PC-30967 | 0 |  | 9677.6 | 212.75
26-PC-30967 | 0 |  | 0 | 0
26-PC-30967 | 0 |  | 0 | 0
26-PC-30967 | 0 |  | 1611.81 | 31.75
26-PC-30985 | 1 | 743 | 2699.17 | 105.6
26-PC-30985 | 0 |  | 5512.79 | 161.66
26-PC-31002 | 1 | 744 | 0 | 0
26-PC-31002 | 0 |  | 189.82 | 1.5
26-PC-31037 | 1 | 745 | 0 | 0
26-PC-31037 | 0 |  | 0 | 0
26-PC-31037 | 0 |  | 657.66 | 13.75
26-PC-31064 | 1 | 746 | 15946.53 | 0
26-PC-31084 | 1 | 747 | 0 | 63.08
26-PC-31084 | 0 |  | 0 | 5.53
26-PC-31084 | 0 |  | 0 | 15.12
26-PC-31098 | 1 | 748 | 0 | 0
26-PC-31155 | 1 | 749 | 1839.54 | 194.11
26-PC-31155 | 0 |  | 564.76 | 25.08
26-PC-31155 | 0 |  | 1570.72 | 42.56
26-PC-31155 | 0 |  | 377.55 | 27.65
26-PC-31174 | 1 | 750 | 0 | 0
26-PC-31174 | 0 |  | 0 | 10.42
26-PC-31182 | 1 | 751 | 0 | 0
26-PC-31182 | 0 |  | 0 | 0
26-PC-31182 | 0 |  | 0 | 0
26-PC-31182 | 0 |  | 0 | 0
26-PC-31182 | 0 |  | 0 | 0
26-PC-31182 | 0 |  | 408.02 | 9.25
26-PC-31186 | 1 | 752 | 0 | 0
26-PC-31186 | 0 |  | 0 | 0
26-PC-31186 | 0 |  | 0 | 0
26-PC-31186 | 0 |  | 0 | 0
26-PC-31209 | 1 | 753 | 46955.48 | 0
26-PC-31209 | 0 |  | 7621.91 | 125.43
26-PC-31209 | 0 |  | 38706.89 | 451.45
26-PC-31209 | 0 |  | 34427.3 | 1339.16
26-PC-31216 | 1 | 754 | 0 | 0
26-PC-31216 | 0 |  | 0 | 0
26-PC-31216 | 0 |  | 0 | 0
26-PC-31216 | 0 |  | 0 | 0
26-PC-31216 | 0 |  | 0 | 0
26-PC-31216 | 0 |  | 1439.96 | 23
26-PC-31238 | 1 | 755 | 0 | 0
26-PC-31238 | 0 |  | 0 | 0
26-PC-31238 | 0 |  | 0 | 0
26-PC-31238 | 0 |  | 1027.92 | 25.75
26-PC-31276 | 1 | 756 | 1193.9 | 209.34
26-PC-31276 | 0 |  | 698.82 | 90.57
26-PC-31276 | 0 |  | 1735.77 | 297.68
26-PC-31276 | 0 |  | 790.25 | 78.77
26-PC-31316 | 1 | 757 | 0 | 0
26-PC-31316 | 0 |  | 0 | 0
26-PC-31316 | 0 |  | 581.01 | 5.25
26-PC-31421 | 1 | 758 | 66410.26 | 1357.87
26-PC-31421 | 0 |  | 93405.08 | 1922.4
26-PC-31448 | 1 | 759 | 0 | 0
26-PC-31448 | 0 |  | 0 | 0
26-PC-31448 | 0 |  | 0 | 0
26-PC-31448 | 0 |  | 0 | 0
26-PC-31473 | 1 | 760 | 0 | 0
26-PC-31484 | 1 | 761 | 0 | 0
26-PC-31484 | 0 |  | 0 | 0
26-PC-31484 | 0 |  | 0 | 0
26-PC-31484 | 0 |  | 0 | 0
26-PC-31484 | 0 |  | 55.14 | 1.25
26-PC-31505 | 1 | 762 | 0 | 29
26-PC-31505 | 0 |  | 417.62 | 9.5
26-PC-31537 | 1 | 763 | 0 | 0
26-PC-31568 | 1 | 764 | 0 | 0
26-PC-31568 | 0 |  | 0 | 0
26-PC-31568 | 0 |  | 649.28 | 16.5
26-PC-31638 | 1 | 765 | 0 | 0
26-PC-31638 | 0 |  | 0 | 0
26-PC-31638 | 0 |  | 167.32 | 3.75
26-PC-31648 | 1 | 766 | 0 | 0
26-PC-31648 | 0 |  | 1341.46 | 21
26-PC-31678 | 1 | 767 | 0 | 0
26-PC-31678 | 0 |  | 2665.75 | 45
26-PC-31692 | 1 | 768 | 0 | 0
26-PC-31692 | 0 |  | 0 | 0
26-PC-31692 | 0 |  | 0 | 0
26-PC-31692 | 0 |  | 0 | 0
26-PC-31692 | 0 |  | 615.44 | 14
26-PC-31700 | 1 | 769 | 0 | 27.15
26-PC-31700 | 0 |  | 0 | 41.17
26-PC-31700 | 0 |  | 0 | 54.13
26-PC-31700 | 0 |  | 0 | 82.47
26-PC-31700 | 0 |  | 0 | 109.69
26-PC-31716 | 1 | 770 | 0 | 0
26-PC-31716 | 0 |  | 51.51 | 1.25
26-PC-31728 | 1 | 771 | 0 | 0
26-PC-31728 | 0 |  | 0 | 0
26-PC-31728 | 0 |  | 0 | 0
26-PC-31802 | 1 | 772 | 0 | 0
26-PC-31802 | 0 |  | 0 | 0
26-PC-31802 | 0 |  | 520.03 | 42
26-PC-31802 | 0 |  | 110.16 | 17.5
26-PC-31802 | 0 |  | 0 | 2.75
26-PC-31802 | 0 |  | 338.64 | 8
26-PC-31823 | 1 | 773 | 0 | 0
26-PC-31823 | 0 |  | 0 | 0
26-PC-31823 | 0 |  | 0 | 0
26-PC-31823 | 0 |  | 40.49 | 1
26-PC-31830 | 1 | 774 | 0 | 0
26-PC-31830 | 0 |  | 0 | 0
26-PC-31872 | 1 | 775 | 0 | 0
26-PC-31872 | 0 |  | 1681.43 | 55.75
26-PC-31872 | 0 |  | 0 | 30
26-PC-31872 | 0 |  | 0 | 0
26-PC-31872 | 0 |  | 1139.84 | 18
26-PC-31881 | 1 | 776 | 0 | 0
26-PC-32047 | 1 | 777 | 0 | 0
26-PC-32047 | 0 |  | 204.96 | 3
26-PC-32069 | 1 | 778 | 0 | 0
26-PC-32069 | 0 |  | 0 | 0
26-PC-32069 | 0 |  | 0 | 0
26-PC-32069 | 0 |  | 0 | 0
26-PC-32069 | 0 |  | 0 | 0
26-PC-32069 | 0 |  | 866.6 | 20
26-PC-32076 | 1 | 779 | 0 | 0
26-PC-32076 | 0 |  | 0 | 0
26-PC-32076 | 0 |  | 0 | 0
26-PC-32076 | 0 |  | 0 | 0
26-PC-32094 | 1 | 780 | 0 | 0
26-PC-32165 | 1 | 781 | 0 | 0
26-PC-32165 | 0 |  | 0 | 0
26-PC-32188 | 1 | 782 | 0 | 0
26-PC-32188 | 0 |  | 0 | 0
26-PC-32188 | 0 |  | 0 | 0
26-PC-32188 | 0 |  | 0 | 0
26-PC-32188 | 0 |  | 0 | 0
26-PC-32227 | 1 | 783 | 145.29 | 12.79
26-PC-32227 | 0 |  | 106.25 | 5.23
26-PC-32227 | 0 |  | 600.76 | 22.17
26-PC-32288 | 1 | 784 | 0 | 0
26-PC-32288 | 0 |  | 0 | 0
26-PC-32288 | 0 |  | 0 | 0
26-PC-32288 | 0 |  | 0 | 0
26-PC-32288 | 0 |  | 0 | 0
26-PC-32303 | 1 | 785 | 0 | 0
26-PC-32303 | 0 |  | 210.16 | 5.5
26-PC-32322 | 1 | 786 | 0 | 0
26-PC-32322 | 0 |  | 0 | 0
26-PC-32322 | 0 |  | 0 | 0
26-PC-32322 | 0 |  | 788.06 | 6.25
26-PC-32369 | 1 | 787 | 0 | 0
26-PC-32369 | 0 |  | 1060.88 | 26.25
26-PC-32382 | 1 | 788 | 1745.74 | 82.98
26-PC-32382 | 0 |  | 5441.23 | 281.67
26-PC-32382 | 0 |  | 6452.55 | 296.74
26-PC-32382 | 0 |  | 1778.68 | 93.14
26-PC-32382 | 0 |  | 6791.39 | 261.04
26-PC-32394 | 1 | 789 | 7221.33 | 71.75
26-PC-32394 | 0 |  | 6731.05 | 71.25
26-PC-32394 | 0 |  | 7424.28 | 75.5
26-PC-32394 | 0 |  | 204.27 | 2.5
26-PC-32396 | 1 | 790 | 0 | 0
26-PC-32396 | 0 |  | 0 | 0
26-PC-32396 | 0 |  | 0 | 0
26-PC-32396 | 0 |  | 0 | 0
26-PC-32396 | 0 |  | 0 | 0
26-PC-32420 | 1 | 791 | 0 | 0
26-PC-32420 | 0 |  | 0 | 0
26-PC-32420 | 0 |  | 0 | 0
26-PC-32420 | 0 |  | 0 | 0
26-PC-32420 | 0 |  | 0 | 0
26-PC-32420 | 0 |  | 380.64 | 9.75
26-PC-32442 | 1 | 792 | 0 | 0
26-PC-32442 | 0 |  | 0 | 0
26-PC-32442 | 0 |  | 170.24 | 4
26-PC-32453 | 1 | 793 | 0 | 0
26-PC-32540 | 1 | 794 | 0 | 0
26-PC-32540 | 0 |  | 0 | 0
26-PC-32540 | 0 |  | 1749.34 | 21.75
26-PC-32556 | 1 | 795 | 0 | 0
26-PC-32556 | 0 |  | 0 | 0
26-PC-32556 | 0 |  | 0 | 0
26-PC-32556 | 0 |  | -198.31 | -4.75
26-PC-32563 | 1 | 796 | 0 | 0
26-PC-32563 | 0 |  | 0 | 0
26-PC-32563 | 0 |  | 0 | 0
26-PC-32563 | 0 |  | 1802.81 | 45.75
26-PC-32569 | 1 | 797 | 0 | 89.96
26-PC-32594 | 1 | 798 | 0 | 0
26-PC-32594 | 0 |  | 0 | 0
26-PC-32594 | 0 |  | 608.97 | 13.25
26-PC-32614 | 1 | 799 | 0 | 0
26-PC-32614 | 0 |  | 0 | 0
26-PC-32614 | 0 |  | 0 | 0
26-PC-32614 | 0 |  | 0 | 0
26-PC-32614 | 0 |  | 0 | 0
26-PC-32646 | 1 | 800 | 0 | 0
26-PC-32646 | 0 |  | 0 | 0
26-PC-32668 | 1 | 801 | 1279.93 | 256.27
26-PC-32668 | 0 |  | 1159.74 | 172.77
26-PC-32668 | 0 |  | 1070.01 | 0
26-PC-32668 | 0 |  | 235.94 | 48.66
26-PC-32707 | 1 | 802 | 0 | 0
26-PC-32707 | 0 |  | 3687.23 | 0
26-PC-32707 | 0 |  | 0 | 0
26-PC-32707 | 0 |  | 197.08 | 0
26-PC-32707 | 0 |  | 0 | 0
26-PC-32707 | 0 |  | 2767.56 | 47.5
26-PC-32711 | 1 | 803 | 0 | 0
26-PC-32711 | 0 |  | 0 | 0
26-PC-32711 | 0 |  | 0 | 0
26-PC-32711 | 0 |  | 0 | 0
26-PC-32725 | 1 | 804 | 0 | 0
26-PC-32725 | 0 |  | 0 | 0
26-PC-32725 | 0 |  | 0 | 15
26-PC-32725 | 0 |  | 0 | 0
26-PC-32725 | 0 |  | 204.88 | 5
26-PC-32727 | 1 | 805 | 0 | 0
26-PC-32727 | 0 |  | 0 | 0
26-PC-32727 | 0 |  | 0 | 0
26-PC-32731 | 1 | 806 | 0 | 0
26-PC-32731 | 0 |  | 0 | 0
26-PC-32731 | 0 |  | 0 | 0
26-PC-32731 | 0 |  | 0 | 0
26-PC-32731 | 0 |  | 0 | 0
26-PC-32744 | 1 | 807 | 15476.83 | 613.01
26-PC-32744 | 0 |  | 3233.57 | 74.05
26-PC-32744 | 0 |  | 2917.23 | 48.38
26-PC-32745 | 1 | 808 | 0 | 0
26-PC-32745 | 0 |  | 0 | 0
26-PC-32745 | 0 |  | 0 | 0
26-PC-32745 | 0 |  | 0 | 0
26-PC-32773 | 1 | 809 | 0 | 0
26-PC-32773 | 0 |  | 0 | 0
26-PC-32773 | 0 |  | 0 | 0
26-PC-32773 | 0 |  | 0 | 0
26-PC-32773 | 0 |  | 0 | 0
26-PC-32803 | 1 | 810 | 14708.24 | 434.54
26-PC-32803 | 0 |  | 4491.73 | 90.35
26-PC-32803 | 0 |  | 5838.66 | 209.04
26-PC-32803 | 0 |  | 6120.33 | 185.77
26-PC-32852 | 1 | 811 | 0 | 0
26-PC-32852 | 0 |  | 57.77 | 0.75
26-PC-32946 | 1 | 812 | 0 | 0
26-PC-32973 | 1 | 813 | 0 | 0
26-PC-32973 | 0 |  | 0 | 0
26-PC-32973 | 0 |  | 0 | 0
26-PC-32973 | 0 |  | 0 | 0
26-PC-32973 | 0 |  | 0 | 0
26-PC-32985 | 1 | 814 | 0 | 0
26-PC-32985 | 0 |  | 0 | 0
26-PC-32985 | 0 |  | 1122.84 | 22.5
26-PC-33011 | 1 | 815 | 14539.03 | 0
26-PC-33011 | 0 |  | 7838.17 | 0
26-PC-33011 | 0 |  | 7323.76 | 0
26-PC-33011 | 0 |  | 15556.13 | 0
26-PC-33011 | 0 |  | 25892.06 | 0
26-PC-33017 | 1 | 816 | 0 | 0
26-PC-33017 | 0 |  | 0 | 0
26-PC-33017 | 0 |  | 0 | 0
26-PC-33017 | 0 |  | 3185.68 | 44
26-PC-33033 | 1 | 817 | 0 | 0
26-PC-33033 | 0 |  | 0 | 0
26-PC-33033 | 0 |  | 0 | 0
26-PC-33033 | 0 |  | 0 | 0
26-PC-33033 | 0 |  | 0 | 0
26-PC-33099 | 1 | 818 | 0 | 0
26-PC-33099 | 0 |  | 0 | 0
26-PC-33099 | 0 |  | 0 | 0
26-PC-33099 | 0 |  | 0 | 0
26-PC-33127 | 1 | 819 | 0 | 0
26-PC-33127 | 0 |  | 0 | 0
26-PC-33127 | 0 |  | 0 | 0
26-PC-33127 | 0 |  | 0 | 0
26-PC-33127 | 0 |  | 0 | 0
26-PC-33127 | 0 |  | 711.81 | 6.25
26-PC-33162 | 1 | 820 | 0 | 0
26-PC-33162 | 0 |  | 0 | 0
26-PC-33162 | 0 |  | 0 | 0
26-PC-33217 | 1 | 821 | 1239.66 | 24.55
26-PC-33217 | 0 |  | 2089.43 | 81.84
26-PC-33223 | 1 | 822 | 4620.39 | 89.85
26-PC-33223 | 0 |  | 2498.79 | 63.78
26-PC-33223 | 0 |  | 821.73 | 12.12
26-PC-33223 | 0 |  | 509.33 | 20.71
26-PC-33223 | 0 |  | 2907.44 | 42.29
26-PC-33255 | 1 | 823 | 12628.86 | 287.86
26-PC-33255 | 0 |  | 2377.49 | 33.79
26-PC-33257 | 1 | 824 | 24.11 | 26.25
26-PC-33257 | 0 |  | 45.71 | 41.74
26-PC-33257 | 0 |  | 29.91 | 72.19
26-PC-33257 | 0 |  | 53.85 | 56.48
26-PC-33257 | 0 |  | 32.32 | 46.23
26-PC-33276 | 1 | 825 | 0 | 0
26-PC-33276 | 0 |  | 0 | 0
26-PC-33276 | 0 |  | 0 | 0
26-PC-33276 | 0 |  | 0 | 0
26-PC-33276 | 0 |  | 597.9 | 14.25
26-PC-33413 | 1 | 826 | 15833.1 | 206.92
26-PC-33413 | 0 |  | 13379.29 | 9.54
26-PC-33413 | 0 |  | 38057.85 | 314.41
26-PC-33413 | 0 |  | 28355.58 | 0
26-PC-33485 | 1 | 827 | 0 | 0
26-PC-33485 | 0 |  | 0 | 0
26-PC-33485 | 0 |  | 0 | 0
26-PC-33485 | 0 |  | 0 | 0
26-PC-33485 | 0 |  | 0 | 0
26-PC-33485 | 0 |  | 657.93 | 8.75
26-PC-33505 | 1 | 828 | 0 | 0
26-PC-33505 | 0 |  | 0 | 0
26-PC-33505 | 0 |  | 0 | 0
26-PC-33533 | 1 | 829 | 4132.03 | 72.71
26-PC-33533 | 0 |  | 2425.23 | 47.15
26-PC-33533 | 0 |  | 1730.71 | 22.88
26-PC-33563 | 1 | 830 | 0 | 0
26-PC-33563 | 0 |  | 0 | 0
26-PC-33563 | 0 |  | 0 | 0
26-PC-33563 | 0 |  | 0 | 0
26-PC-33563 | 0 |  | 0 | 0
26-PC-33588 | 1 | 831 | 0 | 0
26-PC-33588 | 0 |  | 0 | 0
26-PC-33588 | 0 |  | 0 | 0
26-PC-33588 | 0 |  | 0 | 0
26-PC-33588 | 0 |  | 980.47 | 21.25
26-PC-33624 | 1 | 832 | 3848.45 | 0
26-PC-33624 | 0 |  | 1160.99 | 0
26-PC-33624 | 0 |  | 1039.27 | 0
26-PC-33624 | 0 |  | 2968.87 | 0
26-PC-33624 | 0 |  | 2535.33 | 0
26-PC-33660 | 1 | 833 | 0 | 0
26-PC-33660 | 0 |  | 0 | 0
26-PC-33660 | 0 |  | 0 | 0
26-PC-33660 | 0 |  | 0 | 0
26-PC-33660 | 0 |  | 113.22 | 3
26-PC-33684 | 1 | 834 | 0 | 0
26-PC-33684 | 0 |  | 0 | 0
26-PC-33703 | 1 | 835 | 0 | 0
26-PC-33703 | 0 |  | 328.71 | 12.25
26-PC-33703 | 0 |  | 2778.23 | 32.75
26-PC-33703 | 0 |  | 2913.5 | 37.75
26-PC-33703 | 0 |  | 346.9 | 5.25
26-PC-33705 | 1 | 836 | 0 | 0
26-PC-33705 | 0 |  | 0 | 0
26-PC-33705 | 0 |  | 0 | 0
26-PC-33705 | 0 |  | 0 | 0
26-PC-33705 | 0 |  | 1257.27 | 21.5
26-PC-33719 | 1 | 837 | 0 | 0
26-PC-33719 | 0 |  | 0 | 0
26-PC-33719 | 0 |  | 0 | 0
26-PC-33719 | 0 |  | 0 | 0
26-PC-33719 | 0 |  | 0 | 0
26-PC-33727 | 1 | 838 | 0 | 316.38
26-PC-33727 | 0 |  | 0 | 138.43
26-PC-33743 | 1 | 839 | 0 | 0
26-PC-33743 | 0 |  | 7536.58 | 165.25
26-PC-33743 | 0 |  | 2018.1 | 28.75
26-PC-33773 | 1 | 840 | 0 | 0
26-PC-33773 | 0 |  | 0 | 0
26-PC-33773 | 0 |  | 0 | 0
26-PC-33834 | 1 | 841 | 0 | 0
26-PC-33834 | 0 |  | 0 | 0
26-PC-33834 | 0 |  | 0 | 0
26-PC-33834 | 0 |  | 0 | 0
26-PC-33834 | 0 |  | 0 | 0
26-PC-33834 | 0 |  | 373.49 | 8.5
26-PC-33896 | 1 | 842 | 0 | 0
26-PC-33903 | 1 | 843 | 37165.12 | 772.66
26-PC-33903 | 0 |  | 49548.47 | 1691.91
26-PC-33913 | 1 | 844 | 0 | 0
26-PC-33913 | 0 |  | 0 | 0
26-PC-33913 | 0 |  | 0 | 0
26-PC-33913 | 0 |  | 0 | 0
26-PC-33913 | 0 |  | 0 | 0
26-PC-33950 | 1 | 845 | 0 | 250.74
26-PC-33950 | 0 |  | 0 | 166.95
26-PC-33950 | 0 |  | 0 | 16.16
26-PC-33950 | 0 |  | 0 | 0
26-PC-33950 | 0 |  | 0 | 69.04
26-PC-34101 | 1 | 846 | 5826.59 | 0
26-PC-34101 | 0 |  | 5781.99 | 0
26-PC-34101 | 0 |  | 13876.18 | 0
26-PC-34101 | 0 |  | 2378.57 | 35.5
26-PC-34114 | 1 | 847 | 0 | 0
26-PC-34114 | 0 |  | 0 | 0
26-PC-34114 | 0 |  | 0 | 0
26-PC-34114 | 0 |  | 0 | 0
26-PC-34114 | 0 |  | 0 | 0
26-PC-34114 | 0 |  | 142.13 | 3.5
26-PC-34198 | 1 | 848 | 0 | 0
26-PC-34198 | 0 |  | 60.99 | 1.25
26-PC-34247 | 1 | 849 | 2014.96 | 38.95
26-PC-34247 | 0 |  | 3646.85 | 118.81
26-PC-34247 | 0 |  | 2622.35 | 42.92
26-PC-34247 | 0 |  | 6382.8 | 20.96
26-PC-34247 | 0 |  | 7341.93 | 131.05
26-PC-34297 | 1 | 850 | 0 | 0
26-PC-34336 | 1 | 851 | 0 | 0
26-PC-34336 | 0 |  | 0 | 0
26-PC-34336 | 0 |  | 0 | 0
26-PC-34336 | 0 |  | 428.82 | 10.5
26-PC-34394 | 1 | 852 | 0 | 0
26-PC-34394 | 0 |  | 0 | 0
26-PC-34394 | 0 |  | 0 | 0
26-PC-34394 | 0 |  | 0 | 0
26-PC-34394 | 0 |  | 0 | 0
26-PC-34400 | 1 | 853 | 0 | 0
26-PC-34400 | 0 |  | 0 | 0
26-PC-34400 | 0 |  | 0 | 0
26-PC-34432 | 1 | 854 | 0 | 0
26-PC-34432 | 0 |  | 0 | 0
26-PC-34432 | 0 |  | 0 | 0
26-PC-34472 | 1 | 855 | 0 | 0
26-PC-34477 | 1 | 856 | 0 | 0
26-PC-34477 | 0 |  | 0 | 0
26-PC-34477 | 0 |  | 347.14 | 8.5
26-PC-34487 | 1 | 857 | 0 | 0
26-PC-34487 | 0 |  | 3978.79 | 67.75
26-PC-34552 | 1 | 858 | 0 | 0
26-PC-34552 | 0 |  | 0 | 0
26-PC-34552 | 0 |  | 256.15 | 5.25
26-PC-34574 | 1 | 859 | 18686.3 | 0
26-PC-34574 | 0 |  | 5329.42 | 5.5
26-PC-34574 | 0 |  | 12098.17 | 75.58
26-PC-34574 | 0 |  | 6595.36 | 0
26-PC-34574 | 0 |  | 33004.83 | 0
26-PC-34602 | 1 | 860 | 0 | 122
26-PC-34602 | 0 |  | 301.19 | 5.25
26-PC-34611 | 1 | 861 | 0 | 0
26-PC-34611 | 0 |  | 0 | 0
26-PC-34611 | 0 |  | 0 | 0
26-PC-34611 | 0 |  | 0 | 0
26-PC-34611 | 0 |  | 0 | 0
26-PC-34628 | 1 | 862 | 0 | 107.17
26-PC-34628 | 0 |  | 0 | 28.37
26-PC-34628 | 0 |  | 0 | 72.77
26-PC-34628 | 0 |  | 0 | 62.62
26-PC-34628 | 0 |  | 0 | 27.47
26-PC-34631 | 1 | 863 | 0 | 1063.55
26-PC-34701 | 1 | 864 | 48788.97 | 1388.55
26-PC-34711 | 1 | 865 | 0 | 0
26-PC-34711 | 0 |  | 0 | 0
26-PC-34711 | 0 |  | 0 | 0
26-PC-34711 | 0 |  | 0 | 0
26-PC-34711 | 0 |  | 0 | 0
26-PC-34725 | 1 | 866 | 0 | 0
26-PC-34725 | 0 |  | 979.69 | 13.5
26-PC-34757 | 1 | 867 | 7966.24 | 102.5
26-PC-34757 | 0 |  | 1063.41 | 23.75
26-PC-34757 | 0 |  | 1621.7 | 15.25
26-PC-34757 | 0 |  | 0 | 27.25
26-PC-34757 | 0 |  | 11708.54 | 147.25
26-PC-34794 | 1 | 868 | 7575.6 | 117.71
26-PC-34906 | 1 | 869 | 0 | 0
26-PC-34906 | 0 |  | 1023.99 | 21.75
26-PC-34965 | 1 | 870 | 0 | 0
26-PC-34982 | 1 | 871 | 9848.59 | 125.5
26-PC-34982 | 0 |  | 1073.56 | 11.75
26-PC-35012 | 1 | 872 | 10103.38 | 0
26-PC-35012 | 0 |  | 3706.59 | 0
26-PC-35012 | 0 |  | 7174.05 | 0
26-PC-35012 | 0 |  | 4261.21 | 0
26-PC-35056 | 1 | 873 | 0 | 0
26-PC-35056 | 0 |  | 5615.97 | 198.25
26-PC-35056 | 0 |  | 166.99 | 3.5
26-PC-35062 | 1 | 874 | 0 | 0
26-PC-35062 | 0 |  | 0 | 0
26-PC-35062 | 0 |  | 0 | 0
26-PC-35062 | 0 |  | 0 | 0
26-PC-35062 | 0 |  | 0 | 0
26-PC-35062 | 0 |  | 754.86 | 12.25
26-PC-35063 | 1 | 875 | 1132.54 | 0
26-PC-35063 | 0 |  | 139.55 | 0
26-PC-35063 | 0 |  | 1415.82 | 0
26-PC-35063 | 0 |  | 0 | 0
26-PC-35063 | 0 |  | 0 | 0
26-PC-35063 | 0 |  | 249.91 | 6.25
26-PC-35103 | 1 | 876 | 18339.04 | 244.75
26-PC-35103 | 0 |  | 9347.45 | 131.5
26-PC-35103 | 0 |  | 7604.42 | 85.5
26-PC-35103 | 0 |  | 1709.01 | 23.75
26-PC-35111 | 1 | 877 | 0 | 567.58
26-PC-35158 | 1 | 878 | 0 | 0
26-PC-35158 | 0 |  | 0 | 0
26-PC-35158 | 0 |  | 0 | 0
26-PC-35158 | 0 |  | 0 | 0
26-PC-35158 | 0 |  | 470.69 | 6.25
26-PC-35193 | 1 | 879 | 0 | 0
26-PC-35193 | 0 |  | 576.26 | 14
26-PC-35201 | 1 | 880 | 0 | 0
26-PC-35201 | 0 |  | 0 | 0
26-PC-35220 | 1 | 881 | 0 | 0
26-PC-35220 | 0 |  | 0 | 0
26-PC-35220 | 0 |  | 0 | 0
26-PC-35220 | 0 |  | 0 | 0
26-PC-35220 | 0 |  | 0 | 0
26-PC-35220 | 0 |  | 163.16 | 4
26-PC-35245 | 1 | 882 | 0 | 0
26-PC-35245 | 0 |  | 0 | 0
26-PC-35245 | 0 |  | 0 | 0
26-PC-35245 | 0 |  | 0 | 0
26-PC-35248 | 1 | 883 | 0 | 182.73
26-PC-35302 | 1 | 884 | 0 | 0
26-PC-35302 | 0 |  | 0 | 0
26-PC-35302 | 0 |  | 0 | 0
26-PC-35302 | 0 |  | 0 | 0
26-PC-35302 | 0 |  | 199.2 | 4.25
26-PC-35318 | 1 | 885 | 0 | 0
26-PC-35318 | 0 |  | 0 | 0
26-PC-35318 | 0 |  | 135.63 | 2.75
26-PC-35381 | 1 | 886 | 0 | 0
26-PC-35381 | 0 |  | 3340.19 | 102
26-PC-35381 | 0 |  | 0 | 0
26-PC-35381 | 0 |  | 280.66 | 6.75
26-PC-35401 | 1 | 887 | 0 | 0
26-PC-35401 | 0 |  | -215.94 | -0.5
26-PC-35449 | 1 | 888 | 0 | 0
26-PC-35449 | 0 |  | 0 | 0
26-PC-35449 | 0 |  | 113.47 | 1
26-PC-35510 | 1 | 889 | 0 | 0
26-PC-35510 | 0 |  | 3770.2 | 162.25
26-PC-35510 | 0 |  | 543.23 | 125.25
26-PC-35510 | 0 |  | 0 | 0
26-PC-35510 | 0 |  | 836.44 | 18.5
26-PC-35583 | 1 | 890 | 0 | 0
26-PC-35583 | 0 |  | 0 | 0
26-PC-35583 | 0 |  | 0 | 0
26-PC-35588 | 1 | 891 | 29495.51 | 1442.92
26-PC-35588 | 0 |  | 9591.27 | 390.39
26-PC-35596 | 1 | 892 | 0 | 0
26-PC-35596 | 0 |  | 0 | 0
26-PC-35598 | 1 | 893 | 1147.5 | 24.98
26-PC-35598 | 0 |  | 3540.57 | 22.33
26-PC-35635 | 1 | 894 | 0 | 0
26-PC-35635 | 0 |  | 0 | 0
26-PC-35635 | 0 |  | 0 | 0
26-PC-35635 | 0 |  | 0 | 0
26-PC-35635 | 0 |  | 1810.57 | 37.75
26-PC-35650 | 1 | 895 | 0 | 0
26-PC-35650 | 0 |  | 0 | 0
26-PC-35650 | 0 |  | 0 | 0
26-PC-35698 | 1 | 896 | 26759.29 | 553.64
26-PC-35698 | 0 |  | 10085.02 | 326.77
26-PC-35698 | 0 |  | 19651.83 | 846.71
26-PC-35730 | 1 | 897 | 0 | 0
26-PC-35730 | 0 |  | 0 | 0
26-PC-35730 | 0 |  | 0 | 0
26-PC-35730 | 0 |  | 0 | 0
26-PC-35730 | 0 |  | 0 | 0
26-PC-35766 | 1 | 898 | 420.44 | 16.58
26-PC-35766 | 0 |  | 1545.44 | 35.06
26-PC-35766 | 0 |  | 1246.98 | 0
26-PC-35789 | 1 | 899 | 0 | 0
26-PC-35789 | 0 |  | 0 | 0
26-PC-35789 | 0 |  | 9.39 | 0.25
26-PC-35803 | 1 | 900 | 0 | 0
26-PC-35803 | 0 |  | 0 | 0
26-PC-35811 | 1 | 901 | 0 | 0
26-PC-35811 | 0 |  | 0 | 0
26-PC-35828 | 1 | 902 | 386.42 | 4
26-PC-35828 | 0 |  | 0 | 0
26-PC-35828 | 0 |  | 0 | 0
26-PC-35828 | 0 |  | 52.27 | 1.25
26-PC-35920 | 1 | 903 | 0 | 0
26-PC-35920 | 0 |  | 0 | 0
26-PC-35920 | 0 |  | 0 | 0
26-PC-35920 | 0 |  | 0 | 0
26-PC-35920 | 0 |  | 0 | 0
26-PC-35937 | 1 | 904 | 0 | 0
26-PC-35937 | 0 |  | 0 | 0
26-PC-35937 | 0 |  | 0 | 0
26-PC-35984 | 1 | 905 | 0 | 0
26-PC-35984 | 0 |  | 0 | 0
26-PC-35984 | 0 |  | 0 | 0
26-PC-35984 | 0 |  | 606.39 | 14.5
26-PC-36056 | 1 | 906 | 13109.68 | 361.12
26-PC-36110 | 1 | 907 | 0 | 0
26-PC-36110 | 0 |  | 0 | 0
26-PC-36110 | 0 |  | 0 | 0
26-PC-36110 | 0 |  | 667.12 | 15.5
26-PC-36112 | 1 | 908 | 3147.26 | 88.93
26-PC-36112 | 0 |  | 1730.59 | 71.64
26-PC-36112 | 0 |  | 3598.92 | 81.84
26-PC-36112 | 0 |  | 397.55 | 15.77
26-PC-36208 | 1 | 909 | 530.03 | 0
26-PC-36208 | 0 |  | 444.67 | 11.13
26-PC-36208 | 0 |  | 188.55 | 0
26-PC-36247 | 1 | 910 | 0 | 0
26-PC-36247 | 0 |  | 0 | 0
26-PC-36247 | 0 |  | 0 | 0
26-PC-36247 | 0 |  | 0 | 0
26-PC-36247 | 0 |  | 56.24 | 1.25
26-PC-36281 | 1 | 911 | 0 | 0
26-PC-36281 | 0 |  | 0 | 0
26-PC-36281 | 0 |  | 0 | 0
26-PC-36281 | 0 |  | 0 | 0
26-PC-36281 | 0 |  | 0 | 0
26-PC-36361 | 1 | 912 | 6649.33 | 1015.36
26-PC-36361 | 0 |  | 1118.27 | 83.64
26-PC-36361 | 0 |  | 1286.59 | 12.61
26-PC-36361 | 0 |  | 4185.34 | 368.99
26-PC-36394 | 1 | 913 | 0 | 0
26-PC-36394 | 0 |  | 0 | 0
26-PC-36396 | 1 | 914 | 0 | 0
26-PC-36396 | 0 |  | 76.74 | 1
26-PC-36416 | 1 | 915 | 0 | 0
26-PC-36416 | 0 |  | 0 | 0
26-PC-36416 | 0 |  | 0 | 0
26-PC-36416 | 0 |  | 2001.46 | 30
26-PC-36477 | 1 | 916 | 7484.05 | 282.05
26-PC-36477 | 0 |  | 7930.94 | 144.92
26-PC-36537 | 1 | 917 | 0 | 0
26-PC-36537 | 0 |  | 0 | 17
26-PC-36537 | 0 |  | 0 | 0
26-PC-36537 | 0 |  | 0 | 0
26-PC-36537 | 0 |  | 515.57 | 9.75
26-PC-36548 | 1 | 918 | 2171.23 | 65.34
26-PC-36548 | 0 |  | 2946.77 | 0
26-PC-36555 | 1 | 919 | 0 | 0
26-PC-36555 | 0 |  | 0 | 0
26-PC-36555 | 0 |  | 0 | 0
26-PC-36555 | 0 |  | 0 | 0
26-PC-36555 | 0 |  | 0 | 0
26-PC-36581 | 1 | 920 | 0 | 0
26-PC-36581 | 0 |  | 506.84 | 9.25
26-PC-36595 | 1 | 921 | 1863.05 | 56.19
26-PC-36595 | 0 |  | 2691.46 | 92.77
26-PC-36595 | 0 |  | 879.23 | 44.67
26-PC-36602 | 1 | 922 | 0 | 0
26-PC-36602 | 0 |  | 0 | 0
26-PC-36602 | 0 |  | 0 | 0
26-PC-36602 | 0 |  | 372.63 | 4.25
26-PC-36616 | 1 | 923 | 0 | 0
26-PC-36616 | 0 |  | 0 | 0
26-PC-36616 | 0 |  | 0 | 8.51
26-PC-36616 | 0 |  | 0 | 0
26-PC-36726 | 1 | 924 | 0 | 0
26-PC-36726 | 0 |  | 79.11 | 0.75
26-PC-36749 | 1 | 925 | 0 | 0
26-PC-36749 | 0 |  | 0 | 0
26-PC-36749 | 0 |  | 1008.6 | 10.5
26-PC-36750 | 1 | 926 | 0 | 0
26-PC-36750 | 0 |  | 175.91 | 4.25
26-PC-36775 | 1 | 927 | 0 | 0
26-PC-36775 | 0 |  | 0 | 0
26-PC-36775 | 0 |  | 18.98 | 0.5
26-PC-36802 | 1 | 928 | 0 | 0
26-PC-36802 | 0 |  | 0 | 0
26-PC-36828 | 1 | 929 | 0 | 0
26-PC-36828 | 0 |  | 0 | 0
26-PC-36828 | 0 |  | 0 | 0
26-PC-36828 | 0 |  | 0 | 0
26-PC-36861 | 1 | 930 | 0 | 0
26-PC-36861 | 0 |  | 0 | 0
26-PC-36861 | 0 |  | 0 | 0
26-PC-36861 | 0 |  | 0 | 0
26-PC-36861 | 0 |  | 0 | 0
26-PC-36861 | 0 |  | 271.5 | 6
26-PC-36944 | 1 | 931 | 0 | 0
26-PC-36945 | 1 | 932 | 0 | 0
26-PC-36945 | 0 |  | 2795.55 | 38
26-PC-36949 | 1 | 933 | 7292.18 | 369.04
26-PC-36949 | 0 |  | 2378.14 | 23.03
26-PC-36949 | 0 |  | 1123.35 | 31.79
26-PC-37015 | 1 | 934 | 0 | 0
26-PC-37015 | 0 |  | 0 | 0
26-PC-37016 | 1 | 935 | 0 | 0
26-PC-37016 | 0 |  | 0 | 0
26-PC-37024 | 1 | 936 | 0 | 0
26-PC-37024 | 0 |  | 0 | 0
26-PC-37024 | 0 |  | 0 | 0
26-PC-37024 | 0 |  | 0 | 0
26-PC-37024 | 0 |  | 0 | 0
26-PC-37024 | 0 |  | 15.95 | 0.25
26-PC-37032 | 1 | 937 | 17724.39 | 0
26-PC-37032 | 0 |  | 15893.65 | 0
26-PC-37051 | 1 | 938 | 0 | 0
26-PC-37051 | 0 |  | 0 | 0
26-PC-37068 | 1 | 939 | 0 | 0
26-PC-37068 | 0 |  | 0 | 0
26-PC-37073 | 1 | 940 | 0 | 0
26-PC-37073 | 0 |  | 0 | 0
26-PC-37073 | 0 |  | 493.92 | 5
26-PC-37089 | 1 | 941 | 0 | 0
26-PC-37089 | 0 |  | 0 | 0
26-PC-37089 | 0 |  | 0 | 0
26-PC-37089 | 0 |  | 79.74 | 1.25
26-PC-37136 | 1 | 942 | 0 | 0
26-PC-37136 | 0 |  | 0 | 0
26-PC-37136 | 0 |  | 573.38 | 12.25
26-PC-37137 | 1 | 943 | 0 | 0
26-PC-37137 | 0 |  | 0 | 0
26-PC-37137 | 0 |  | 0 | 0
26-PC-37138 | 1 | 944 | 0 | 0
26-PC-37138 | 0 |  | 0 | 0
26-PC-37138 | 0 |  | 0 | 0
26-PC-37138 | 0 |  | 0 | 0
26-PC-37138 | 0 |  | 0 | 0
26-PC-37138 | 0 |  | 302.07 | 2.5
26-PC-37139 | 1 | 945 | 0 | 0
26-PC-37139 | 0 |  | 999.48 | 15.5
26-PC-37160 | 1 | 946 | 7487.05 | 0
26-PC-37160 | 0 |  | 3840.15 | 0
26-PC-37160 | 0 |  | 5180.07 | 0
26-PC-37160 | 0 |  | 20411.32 | 0
26-PC-37160 | 0 |  | 8086.46 | 0
26-PC-37166 | 1 | 947 | 7253.96 | 0
26-PC-37166 | 0 |  | 3057.84 | 94.4
26-PC-37166 | 0 |  | 1515.62 | 0
26-PC-37166 | 0 |  | 7975.52 | 0
26-PC-37196 | 1 | 948 | 0 | 0
26-PC-37196 | 0 |  | 0 | 0
26-PC-37196 | 0 |  | 0 | 0
26-PC-37196 | 0 |  | 0 | 0
26-PC-37196 | 0 |  | 0 | 0
26-PC-37204 | 1 | 949 | 0 | 0
26-PC-37204 | 0 |  | 0 | 0
26-PC-37204 | 0 |  | 573.45 | 15
26-PC-37224 | 1 | 950 | 0 | 0
26-PC-37224 | 0 |  | 0 | 193.72
26-PC-37224 | 0 |  | 0 | 15.26
26-PC-37271 | 1 | 951 | 0 | 0
26-PC-37271 | 0 |  | 0 | 0
26-PC-37271 | 0 |  | 0 | 0
26-PC-37271 | 0 |  | 0 | 0
26-PC-37271 | 0 |  | 893.06 | 14
26-PC-37282 | 1 | 952 | 0 | 0
26-PC-37282 | 0 |  | 0 | 0
26-PC-37282 | 0 |  | 0 | 0
26-PC-37311 | 1 | 953 | 0 | 0
26-PC-37311 | 0 |  | 0 | 0
26-PC-37317 | 1 | 954 | 0 | 0
26-PC-37317 | 0 |  | 0 | 0
26-PC-37317 | 0 |  | 0 | 0
26-PC-37317 | 0 |  | 0 | 0
26-PC-37317 | 0 |  | 0 | 0
26-PC-37317 | 0 |  | 497.75 | 11
26-PC-37322 | 1 | 955 | 0 | 0
26-PC-37329 | 1 | 956 | 0 | 0
26-PC-37329 | 0 |  | 570.78 | 8.5
26-PC-37367 | 1 | 957 | 0 | 0
26-PC-37367 | 0 |  | 0 | 173
26-PC-37367 | 0 |  | 0 | 27.15
26-PC-37367 | 0 |  | 0 | 202.21
26-PC-37368 | 1 | 958 | 0 | 0
26-PC-37368 | 0 |  | 0 | 0
26-PC-37368 | 0 |  | 0 | 0
26-PC-37428 | 1 | 959 | 457.06 | 7.75
26-PC-37428 | 0 |  | 0 | 0
26-PC-37428 | 0 |  | 0 | 0
26-PC-37428 | 0 |  | 140.38 | 3.5
26-PC-37441 | 1 | 960 | 0 | 0
26-PC-37441 | 0 |  | 0 | 0
26-PC-37441 | 0 |  | 0 | 0
26-PC-37477 | 1 | 961 | 0 | 0
26-PC-37511 | 1 | 962 | 14721.84 | 0
26-PC-37511 | 0 |  | 16856.71 | 384.31
26-PC-37513 | 1 | 963 | 0 | 0
26-PC-37513 | 0 |  | 0 | 0
26-PC-37513 | 0 |  | 0 | 0
26-PC-37520 | 1 | 964 | 1148.34 | 68.14
26-PC-37520 | 0 |  | 2514.25 | 49.7
26-PC-37520 | 0 |  | 1946.08 | 88.38
26-PC-37520 | 0 |  | 2164.81 | 66.63
26-PC-37543 | 1 | 965 | 0 | 0
26-PC-37543 | 0 |  | 0 | 0
26-PC-37543 | 0 |  | 0 | 0
26-PC-37543 | 0 |  | 0 | 0
26-PC-37543 | 0 |  | 0 | 0
26-PC-37543 | 0 |  | 1217.56 | 14.75
26-PC-37559 | 1 | 966 | 2250.7 | 32
26-PC-37559 | 0 |  | 10131.15 | 141.75
26-PC-37559 | 0 |  | 6062.39 | 91.5
26-PC-37559 | 0 |  | 0 | 48.25
26-PC-37559 | 0 |  | 708.63 | 10.25
26-PC-37671 | 1 | 967 | 0 | 0
26-PC-37671 | 0 |  | 0 | 0
26-PC-37671 | 0 |  | 0 | 0
26-PC-37705 | 1 | 968 | 2980.35 | 61
26-PC-37705 | 0 |  | 0 | 0
26-PC-37705 | 0 |  | 0 | 0
26-PC-37705 | 0 |  | 0 | 0
26-PC-37705 | 0 |  | 0 | 0
26-PC-37705 | 0 |  | 277.03 | 4.5
26-PC-37709 | 1 | 969 | 3849.61 | 36.25
26-PC-37709 | 0 |  | 0 | 0
26-PC-37709 | 0 |  | 4014.83 | 58.5
26-PC-37709 | 0 |  | 0 | 0
26-PC-37709 | 0 |  | 2831.93 | 44.5
26-PC-37709 | 0 |  | 1172.27 | 17.75
26-PC-37788 | 1 | 970 | 0 | 0
26-PC-37788 | 0 |  | 0 | 0
26-PC-37788 | 0 |  | 257.7 | 6
26-PC-37801 | 1 | 971 | 3331.22 | 131.52
26-PC-37801 | 0 |  | 2698.87 | 78.84
26-PC-37860 | 1 | 972 | 1361.17 | 0.64
26-PC-37860 | 0 |  | 1477.72 | 0
26-PC-37924 | 1 | 973 | 3100.13 | 81.97
26-PC-37924 | 0 |  | 4065.74 | 76.88
26-PC-37965 | 1 | 974 | 0 | 0
26-PC-37965 | 0 |  | 194.2 | 4.5
26-PC-38019 | 1 | 975 | 139.92 | 12.85
26-PC-38019 | 0 |  | 147.76 | 6.49
26-PC-38019 | 0 |  | 492.82 | 23.85
26-PC-38019 | 0 |  | 106.7 | 5.53
26-PC-38019 | 0 |  | 619.11 | 13.83
26-PC-38025 | 1 | 976 | 0 | 0
26-PC-38025 | 0 |  | 0 | 0
26-PC-38025 | 0 |  | 0 | 0
26-PC-38025 | 0 |  | 0 | 0
26-PC-38025 | 0 |  | 0 | 0
26-PC-38025 | 0 |  | 245.07 | 5.25
26-PC-38124 | 1 | 977 | 1253 | 46.77
26-PC-38124 | 0 |  | 1188 | 62.55
26-PC-38124 | 0 |  | 4036.23 | 58.08
26-PC-38153 | 1 | 978 | 1878.19 | 0
26-PC-38153 | 0 |  | 0 | 0
26-PC-38153 | 0 |  | 0 | 0
26-PC-38153 | 0 |  | 0 | 0
26-PC-38153 | 0 |  | 462.48 | 10.25
26-PC-38215 | 1 | 979 | 0 | 0
26-PC-38215 | 0 |  | 506.11 | 11.5
26-PC-38264 | 1 | 980 | 0 | 0
26-PC-38264 | 0 |  | 0 | 0
26-PC-38264 | 0 |  | 0 | 4.5
26-PC-38264 | 0 |  | 0 | 0
26-PC-38264 | 0 |  | 195.31 | 7.25
26-PC-38264 | 0 |  | 434.07 | 10
26-PC-38304 | 1 | 981 | 0 | 0
26-PC-38304 | 0 |  | 0 | 0
26-PC-38304 | 0 |  | 0 | 0
26-PC-38304 | 0 |  | 0 | 0
26-PC-38315 | 1 | 982 | 0 | 0
26-PC-38315 | 0 |  | 0 | 0
26-PC-38315 | 0 |  | 708.11 | 15.25
26-PC-38367 | 1 | 983 | 0 | 0
26-PC-38367 | 0 |  | 0 | 0
26-PC-38367 | 0 |  | 0 | 0
26-PC-38367 | 0 |  | 0 | 0
26-PC-38367 | 0 |  | 1075.39 | 24.5
26-PC-38379 | 1 | 984 | 0 | 0
26-PC-38387 | 1 | 985 | 0 | 0
26-PC-38387 | 0 |  | 0 | 0
26-PC-38387 | 0 |  | 6708.54 | 55.5
26-PC-38387 | 0 |  | 702.98 | 13
26-PC-38390 | 1 | 986 | 0 | 0
26-PC-38390 | 0 |  | 309.53 | 7.75
26-PC-38410 | 1 | 987 | 0 | 45.75
26-PC-38431 | 1 | 988 | 17825.35 | 413.19
26-PC-38431 | 0 |  | 11702.27 | 358.12
26-PC-38431 | 0 |  | 13531.03 | 581.58
26-PC-38438 | 1 | 989 | 0 | 0
26-PC-38438 | 0 |  | 0 | 0
26-PC-38438 | 0 |  | 0 | 0
26-PC-38438 | 0 |  | 0 | 0
26-PC-38459 | 1 | 990 | 0 | 0
26-PC-38532 | 1 | 991 | 0 | 0
26-PC-38532 | 0 |  | 0 | 0
26-PC-38532 | 0 |  | 0 | 0
26-PC-38532 | 0 |  | 0 | 0
26-PC-38532 | 0 |  | 0 | 0
26-PC-38546 | 1 | 992 | 449.32 | 0
26-PC-38546 | 0 |  | 3515.06 | 0
26-PC-38550 | 1 | 993 | 0 | 267.34
26-PC-38550 | 0 |  | 0 | 0
26-PC-38550 | 0 |  | 0 | 241
26-PC-38550 | 0 |  | 0 | 158.08
26-PC-38550 | 0 |  | 0 | 131.35
26-PC-38571 | 1 | 994 | 0 | 0
26-PC-38571 | 0 |  | 0 | 0
26-PC-38571 | 0 |  | 0 | 0
26-PC-38573 | 1 | 995 | 0 | 0
26-PC-38573 | 0 |  | 0 | 0
26-PC-38573 | 0 |  | 0 | 0
26-PC-38573 | 0 |  | 0 | 0
26-PC-38573 | 0 |  | 0 | 0
26-PC-38573 | 0 |  | 15.69 | 0.25
26-PC-38624 | 1 | 996 | 11956.71 | 218.05
26-PC-38624 | 0 |  | 5016.92 | 130.45
26-PC-38647 | 1 | 997 | 0 | 0
26-PC-38647 | 0 |  | 0 | 0
26-PC-38647 | 0 |  | 0 | 0
26-PC-38647 | 0 |  | 3923.39 | 69.25
26-PC-38675 | 1 | 998 | 0 | 0
26-PC-38675 | 0 |  | 0 | 0
26-PC-38675 | 0 |  | 0 | 0
26-PC-38675 | 0 |  | 0 | 0
26-PC-38675 | 0 |  | 571.18 | 12
26-PC-38691 | 1 | 999 | 0 | 0
26-PC-38691 | 0 |  | 0 | 0
26-PC-38691 | 0 |  | 0 | 0
26-PC-38691 | 0 |  | 0 | 0
26-PC-38709 | 1 | 1000 | 0 | 0
26-PC-38709 | 0 |  | 0 | 0
26-PC-38709 | 0 |  | 3.99 | 1
26-PC-38709 | 0 |  | 0 | 0
26-PC-38709 | 0 |  | 0 | 0
26-PC-38709 | 0 |  | 267.83 | 6.75
26-PC-38719 | 1 | 1001 | 0 | 0
26-PC-38719 | 0 |  | 0 | 0
26-PC-38719 | 0 |  | 0 | 0
26-PC-38719 | 0 |  | 0 | 0
26-PC-38719 | 0 |  | 0 | 0
26-PC-38737 | 1 | 1002 | 26235.98 | 0
26-PC-38737 | 0 |  | 0 | 0
26-PC-38737 | 0 |  | 3888.1 | 85.5
26-PC-38769 | 1 | 1003 | 0 | 0
26-PC-38769 | 0 |  | 0 | 0
26-PC-38844 | 1 | 1004 | 70896.67 | 1572.86
26-PC-38856 | 1 | 1005 | 9469.55 | 178.84
26-PC-38856 | 0 |  | 18790.74 | 488.31
26-PC-38880 | 1 | 1006 | 0 | 2.38
26-PC-38880 | 0 |  | 0 | 180.5
26-PC-38880 | 0 |  | 0 | 0
26-PC-38898 | 1 | 1007 | 0 | 0
26-PC-38898 | 0 |  | 462.96 | 10
26-PC-38916 | 1 | 1008 | 7800.93 | 208.68
26-PC-38916 | 0 |  | 4844.16 | 117.52
26-PC-38924 | 1 | 1009 | 0 | 0
26-PC-38924 | 0 |  | 0 | 2.75
26-PC-38924 | 0 |  | 3034.3 | 69.5
26-PC-38924 | 0 |  | 0 | 0
26-PC-38924 | 0 |  | 0 | 0
26-PC-38924 | 0 |  | 1249.13 | 24.75
26-PC-38943 | 1 | 1010 | 0 | 0
26-PC-38943 | 0 |  | 0 | 0
26-PC-38943 | 0 |  | 0 | 0
26-PC-38943 | 0 |  | 10105.53 | 179.25
26-PC-38943 | 0 |  | 1827.12 | 44.25
26-PC-38966 | 1 | 1011 | 0 | 0
26-PC-38966 | 0 |  | 0 | 0
26-PC-38966 | 0 |  | 0 | 0
26-PC-38993 | 1 | 1012 | 0 | 0
26-PC-38993 | 0 |  | 0 | 0
26-PC-38993 | 0 |  | 0 | 0
26-PC-38993 | 0 |  | 1101.25 | 16.25
26-PC-39024 | 1 | 1013 | 0 | 0
26-PC-39024 | 0 |  | 0 | 0
26-PC-39024 | 0 |  | 783.44 | 11
26-PC-39043 | 1 | 1014 | 0 | 0
26-PC-39043 | 0 |  | 0 | 0
26-PC-39043 | 0 |  | 0 | 0
26-PC-39043 | 0 |  | 0 | 0
26-PC-39043 | 0 |  | 0 | 0
26-PC-39043 | 0 |  | 736.17 | 17
26-PC-39051 | 1 | 1015 | 0 | 201.54
26-PC-39051 | 0 |  | 0 | 0
26-PC-39143 | 1 | 1016 | 0 | 0
26-PC-39143 | 0 |  | 0 | 0
26-PC-39143 | 0 |  | 0 | 0
26-PC-39143 | 0 |  | 129.16 | 2
26-PC-39165 | 1 | 1017 | 2228.65 | 90.25
26-PC-39165 | 0 |  | 12812.78 | 95.5
26-PC-39165 | 0 |  | 0 | 0
26-PC-39165 | 0 |  | 532.8 | 6.75
26-PC-39230 | 1 | 1018 | 0 | 0
26-PC-39230 | 0 |  | 0 | 0
26-PC-39230 | 0 |  | 513.92 | 11
26-PC-39232 | 1 | 1019 | 1261.79 | 41.79
26-PC-39232 | 0 |  | 999.01 | 29.27
26-PC-39249 | 1 | 1020 | 0 | 0
26-PC-39249 | 0 |  | 0 | 0
26-PC-39249 | 0 |  | 0 | 0
26-PC-39264 | 1 | 1021 | 0 | 47.82
26-PC-39264 | 0 |  | 0 | 118.71
26-PC-39277 | 1 | 1022 | 0 | 0
26-PC-39277 | 0 |  | 0 | 0
26-PC-39277 | 0 |  | 0 | 0
26-PC-39277 | 0 |  | 0 | 0
26-PC-39303 | 1 | 1023 | 0 | 0
26-PC-39303 | 0 |  | 0 | 0
26-PC-39335 | 1 | 1024 | 0 | 64.7
26-PC-39335 | 0 |  | 0 | 64.92
26-PC-39335 | 0 |  | 0 | 8.63
26-PC-39335 | 0 |  | 0 | 12.68
26-PC-39372 | 1 | 1025 | 0 | 0
26-PC-39372 | 0 |  | 0 | 0
26-PC-39372 | 0 |  | 0 | 0
26-PC-39390 | 1 | 1026 | 0 | 0
26-PC-39390 | 0 |  | 0 | 0
26-PC-39390 | 0 |  | 0 | 0
26-PC-39390 | 0 |  | 0 | 0
26-PC-39390 | 0 |  | 0 | 0
26-PC-39390 | 0 |  | 199.31 | 3.5
26-PC-39408 | 1 | 1027 | 0 | 6.54
26-PC-39408 | 0 |  | 0 | 0
26-PC-39446 | 1 | 1028 | 0 | 0
26-PC-39446 | 0 |  | 0 | 0
26-PC-39446 | 0 |  | 0 | 0
26-PC-39446 | 0 |  | 2132.08 | 47
26-PC-39534 | 1 | 1029 | 0 | 0
26-PC-39537 | 1 | 1030 | 0 | 0
26-PC-39537 | 0 |  | 45.34 | 0.75
26-PC-39565 | 1 | 1031 | 0 | 0
26-PC-39565 | 0 |  | 0 | 0
26-PC-39565 | 0 |  | 0 | 4.75
26-PC-39565 | 0 |  | 0 | 0
26-PC-39565 | 0 |  | 318.52 | 7.5
26-PC-39587 | 1 | 1032 | 1273.57 | 401.36
26-PC-39587 | 0 |  | 209.72 | 119.25
26-PC-39595 | 1 | 1033 | 0 | 0
26-PC-39595 | 0 |  | 0 | 0
26-PC-39619 | 1 | 1034 | 0 | 0
26-PC-39619 | 0 |  | 0 | 0
26-PC-39619 | 0 |  | 0 | 0
26-PC-39638 | 1 | 1035 | 0 | 0
26-PC-39638 | 0 |  | 0 | 0
26-PC-39638 | 0 |  | 0 | 0
26-PC-39638 | 0 |  | 0 | 0
26-PC-39638 | 0 |  | 0 | 0
26-PC-39638 | 0 |  | 554.19 | 10.75
26-PC-39644 | 1 | 1036 | 0 | 8.94
26-PC-39644 | 0 |  | 0 | 92.92
26-PC-39671 | 1 | 1037 | 1461.93 | 0
26-PC-39671 | 0 |  | 6390.37 | 0
26-PC-39671 | 0 |  | 2502.19 | 0
26-PC-39671 | 0 |  | 1524.35 | 0
26-PC-39671 | 0 |  | 2108.66 | 0
26-PC-39699 | 1 | 1038 | 0 | 0
26-PC-39699 | 0 |  | 0 | 0
26-PC-39699 | 0 |  | 0 | 0
26-PC-39699 | 0 |  | 0 | 0
26-PC-39699 | 0 |  | 0 | 0
26-PC-39699 | 0 |  | 587.24 | 14.25
26-PC-39711 | 1 | 1039 | 1494.01 | 0
26-PC-39711 | 0 |  | 5545.87 | 0
26-PC-39711 | 0 |  | 982.07 | 0
26-PC-39725 | 1 | 1040 | 2175.18 | 72.12
26-PC-39725 | 0 |  | 10988.85 | 223.87
26-PC-39730 | 1 | 1041 | 0 | 0
26-PC-39730 | 0 |  | 0 | 0
26-PC-39744 | 1 | 1042 | 0 | 0
26-PC-39744 | 0 |  | 0 | 0
26-PC-39744 | 0 |  | 0 | 0
26-PC-39744 | 0 |  | 100.62 | 2.25
26-PC-39778 | 1 | 1043 | 0 | 0
26-PC-39778 | 0 |  | 0 | 0
26-PC-39778 | 0 |  | 0 | 0
26-PC-39778 | 0 |  | 0 | 0
26-PC-39778 | 0 |  | 0 | 0
26-PC-39780 | 1 | 1044 | 0 | 0
26-PC-39880 | 1 | 1045 | 0 | 0
26-PC-39880 | 0 |  | 0 | 0
26-PC-39880 | 0 |  | 1557.02 | 32.75
26-PC-39913 | 1 | 1046 | 0 | 0
26-PC-39913 | 0 |  | 0 | 0
26-PC-39913 | 0 |  | 0 | 0
26-PC-39913 | 0 |  | 0 | 0
26-PC-39913 | 0 |  | 0 | 0
26-PC-39971 | 1 | 1047 | 0 | 76.25
26-PC-39971 | 0 |  | 5658.79 | 234.25
26-PC-39971 | 0 |  | 0 | 0
26-PC-39971 | 0 |  | 0 | 88.25
26-PC-39971 | 0 |  | 190.87 | 59.25
26-PC-39971 | 0 |  | 2112.76 | 39.75
26-PC-39990 | 1 | 1048 | 0 | 0
26-PC-39990 | 0 |  | 0 | 0
26-PC-40009 | 1 | 1049 | 0 | 0
26-PC-40009 | 0 |  | 0 | 0
26-PC-40009 | 0 |  | 503.4 | 36.5
26-PC-40009 | 0 |  | -227.06 | -3.5
26-PC-40038 | 1 | 1050 | 0 | 0
26-PC-40038 | 0 |  | 0 | 0
26-PC-40038 | 0 |  | 0 | 0
26-PC-40055 | 1 | 1051 | 0 | 0
26-PC-40055 | 0 |  | 0 | 0
26-PC-40092 | 1 | 1052 | 0 | 0
26-PC-40092 | 0 |  | 0 | 0
26-PC-40108 | 1 | 1053 | 1147.91 | 580.31
26-PC-40128 | 1 | 1054 | 234.45 | 44.2
26-PC-40128 | 0 |  | 331.65 | 127.09
26-PC-40128 | 0 |  | 258.53 | 60.92
26-PC-40128 | 0 |  | 83.98 | 45.06
26-PC-40128 | 0 |  | 127.03 | 35.67
26-PC-40176 | 1 | 1055 | 0 | 0
26-PC-40176 | 0 |  | 0 | 0
26-PC-40176 | 0 |  | 0 | 0
26-PC-40176 | 0 |  | 0 | 0
26-PC-40176 | 0 |  | 0 | 0
26-PC-40176 | 0 |  | 87.89 | 2.25
26-PC-40190 | 1 | 1056 | 0 | 0
26-PC-40190 | 0 |  | 0 | 0
26-PC-40229 | 1 | 1057 | 21956.2 | 23.57
26-PC-40229 | 0 |  | 5788.1 | 220.73
26-PC-40229 | 0 |  | 16701.76 | 284.93
26-PC-40229 | 0 |  | 18246.92 | 210
26-PC-40229 | 0 |  | 6164.58 | 45.19
26-PC-40289 | 1 | 1058 | 0 | 0
26-PC-40289 | 0 |  | 0 | 0
26-PC-40289 | 0 |  | 0 | 0
26-PC-40289 | 0 |  | 0 | 0
26-PC-40296 | 1 | 1059 | 0 | 0
26-PC-40296 | 0 |  | 0 | 0
26-PC-40296 | 0 |  | 0 | 0
26-PC-40296 | 0 |  | 0 | 0
26-PC-40296 | 0 |  | 39.08 | 0.5
26-PC-40304 | 1 | 1060 | 0 | 0
26-PC-40329 | 1 | 1061 | 37749.08 | 985.87
26-PC-40329 | 0 |  | 14827.39 | 509.02
26-PC-40329 | 0 |  | 31821.09 | 837.35
26-PC-40334 | 1 | 1062 | 2006.14 | 152.5
26-PC-40334 | 0 |  | 2410.58 | 134
26-PC-40334 | 0 |  | 0 | 87.75
26-PC-40334 | 0 |  | 7296.1 | 62.25
26-PC-40334 | 0 |  | 0 | 67.25
26-PC-40334 | 0 |  | 1543.29 | 28
26-PC-40344 | 1 | 1063 | 3582.04 | 0
26-PC-40344 | 0 |  | 719.22 | 17
26-PC-40361 | 1 | 1064 | 2859.75 | 135.25
26-PC-40361 | 0 |  | 0 | 0
26-PC-40361 | 0 |  | 5702.27 | 117
26-PC-40361 | 0 |  | 1345.56 | 15.25
26-PC-40384 | 1 | 1065 | 0 | 0
26-PC-40384 | 0 |  | 0 | 0
26-PC-40384 | 0 |  | 0 | 26
26-PC-40384 | 0 |  | 0 | 0
26-PC-40384 | 0 |  | 395.13 | 10.25
26-PC-40422 | 1 | 1066 | 2695.86 | 58
26-PC-40422 | 0 |  | 1331.23 | 31.25
26-PC-40422 | 0 |  | 83.08 | 1.75
26-PC-40443 | 1 | 1067 | 0 | 0
26-PC-40443 | 0 |  | 0 | 0
26-PC-40443 | 0 |  | 0 | 0
26-PC-40443 | 0 |  | 531.76 | 6.5
26-PC-40464 | 1 | 1068 | 2179.58 | 59.25
26-PC-40464 | 0 |  | 716.15 | 17.5
26-PC-40464 | 0 |  | 0 | 14.25
26-PC-40464 | 0 |  | 54.7 | 0.75
26-PC-40590 | 1 | 1069 | 0 | 0
26-PC-40590 | 0 |  | 0 | 0
26-PC-40590 | 0 |  | 0 | 0
26-PC-40590 | 0 |  | 0 | 0
26-PC-40590 | 0 |  | 0 | 0
26-PC-40590 | 0 |  | 1776.79 | 38.75
26-PC-40605 | 1 | 1070 | 0 | 55.05
26-PC-40605 | 0 |  | 0 | 55.31
26-PC-40605 | 0 |  | 0 | 29.63
26-PC-40605 | 0 |  | 0 | 25.97
26-PC-40605 | 0 |  | 0 | 160.93
26-PC-40607 | 1 | 1071 | 0 | 0
26-PC-40640 | 1 | 1072 | 0 | 37.69
26-PC-40690 | 1 | 1073 | 0 | 0
26-PC-40690 | 0 |  | 0 | 0
26-PC-40690 | 0 |  | 0 | 0
26-PC-40690 | 0 |  | 0 | 0
26-PC-40690 | 0 |  | 1070.45 | 22.5
26-PC-40716 | 1 | 1074 | 118.18 | 2.5
26-PC-40716 | 0 |  | 23.41 | 2.06
26-PC-40716 | 0 |  | 75.77 | 0.51
26-PC-40716 | 0 |  | 102.04 | 3.91
26-PC-40729 | 1 | 1075 | 0 | 0
26-PC-40729 | 0 |  | 0 | 0
26-PC-40750 | 1 | 1076 | 0 | 0
26-PC-40750 | 0 |  | 0 | 0
26-PC-40750 | 0 |  | 675.19 | 16.25
26-PC-40760 | 1 | 1077 | 0 | 0
26-PC-40760 | 0 |  | 0 | 0
26-PC-40760 | 0 |  | 183.34 | 3.75
26-PC-40805 | 1 | 1078 | 1556.92 | 22.32
26-PC-40860 | 1 | 1079 | 0 | 0
26-PC-40860 | 0 |  | 0 | 0
26-PC-40860 | 0 |  | 0 | 0
26-PC-40860 | 0 |  | 0 | 0
26-PC-40860 | 0 |  | 0 | 0
26-PC-40860 | 0 |  | 618.85 | 15.25
26-PC-40902 | 1 | 1080 | 0 | 0
26-PC-40902 | 0 |  | 0 | 6.54
26-PC-40902 | 0 |  | 0 | 11.85
26-PC-40902 | 0 |  | 0 | 0.79
26-PC-40902 | 0 |  | 0 | 0
26-PC-40966 | 1 | 1081 | 0 | 0
26-PC-40966 | 0 |  | 0 | 0
26-PC-40966 | 0 |  | 1054.58 | 23
26-PC-40983 | 1 | 1082 | 0 | 29.25
26-PC-40983 | 0 |  | 33.98 | 0.5
26-PC-41005 | 1 | 1083 | 0 | 0
26-PC-41005 | 0 |  | 0 | 0
26-PC-41005 | 0 |  | 0 | 0
26-PC-41005 | 0 |  | 75.92 | 1.75
26-PC-41046 | 1 | 1084 | 3940.64 | 67.11
26-PC-41046 | 0 |  | 5443.64 | 164.84
26-PC-41046 | 0 |  | 1962.79 | 55.07
26-PC-41048 | 1 | 1085 | 0 | 0
26-PC-41048 | 0 |  | 2072.26 | 48.25
26-PC-41130 | 1 | 1086 | 0 | 175.75
26-PC-41176 | 1 | 1087 | 0 | 0
26-PC-41176 | 0 |  | 0 | 0
26-PC-41176 | 0 |  | 0 | 0
26-PC-41176 | 0 |  | 377.58 | 5.75
26-PC-41202 | 1 | 1088 | 2512.81 | 91
26-PC-41202 | 0 |  | 441.69 | 7
26-PC-41222 | 1 | 1089 | 0 | 0
26-PC-41229 | 1 | 1090 | 0 | 0
26-PC-41229 | 0 |  | 0 | 0
26-PC-41229 | 0 |  | 0 | 0
26-PC-41229 | 0 |  | 0 | 0
26-PC-41230 | 1 | 1091 | 0 | 0
26-PC-41230 | 0 |  | 0 | 0
26-PC-41230 | 0 |  | 58.41 | 1.25
26-PC-41302 | 1 | 1092 | 208.13 | 38.37
26-PC-41302 | 0 |  | 333.1 | 72.38
26-PC-41334 | 1 | 1093 | 3455.57 | 141
26-PC-41334 | 0 |  | 0 | 0
26-PC-41334 | 0 |  | 730.41 | 16.75
26-PC-41386 | 1 | 1094 | 0 | 0
26-PC-41394 | 1 | 1095 | 0 | 0
26-PC-41394 | 0 |  | 0 | 0
26-PC-41394 | 0 |  | 0 | 0
26-PC-41394 | 0 |  | 0 | 0
26-PC-41406 | 1 | 1096 | 0 | 0
26-PC-41406 | 0 |  | 1102.55 | 24.75
26-PC-41425 | 1 | 1097 | 0 | 0
26-PC-41425 | 0 |  | 543.34 | 8.25
26-PC-41446 | 1 | 1098 | 0 | 0
26-PC-41446 | 0 |  | 0 | 0
26-PC-41453 | 1 | 1099 | 0 | 0
26-PC-41453 | 0 |  | 0 | 0
26-PC-41466 | 1 | 1100 | 0 | 0
26-PC-41466 | 0 |  | 0 | 0
26-PC-41466 | 0 |  | 3482.57 | 59.25
26-PC-41575 | 1 | 1101 | 0 | 0
26-PC-41575 | 0 |  | 0 | 0
26-PC-41575 | 0 |  | 216.9 | 5
26-PC-41578 | 1 | 1102 | 0 | 0
26-PC-41578 | 0 |  | 0 | 0
26-PC-41578 | 0 |  | 0 | 0
26-PC-41578 | 0 |  | 0 | 0
26-PC-41623 | 1 | 1103 | 0 | 0
26-PC-41623 | 0 |  | 0 | 0
26-PC-41623 | 0 |  | 0 | 0
26-PC-41623 | 0 |  | 0 | 0
26-PC-41644 | 1 | 1104 | 0 | 0
26-PC-41644 | 0 |  | 0 | 0
26-PC-41644 | 0 |  | 0 | 0
26-PC-41644 | 0 |  | 0 | 0
26-PC-41644 | 0 |  | 2320.01 | 32.75
26-PC-41661 | 1 | 1105 | 0 | 0
26-PC-41661 | 0 |  | 0 | 0
26-PC-41661 | 0 |  | 1406.56 | 19
26-PC-41661 | 0 |  | 0 | 0
26-PC-41661 | 0 |  | 116.34 | 0.75
26-PC-41661 | 0 |  | 115.7 | 1.75
26-PC-41663 | 1 | 1106 | 0 | 0
26-PC-41663 | 0 |  | 0 | 0
26-PC-41663 | 0 |  | 0 | 0
26-PC-41667 | 1 | 1107 | 2358.31 | 131
26-PC-41667 | 0 |  | 0 | 0
26-PC-41667 | 0 |  | 8599.84 | 163
26-PC-41667 | 0 |  | 6503.86 | 106
26-PC-41667 | 0 |  | 0 | 19.25
26-PC-41667 | 0 |  | 921.05 | 14.25
26-PC-41671 | 1 | 1108 | 18720.95 | 135.69
26-PC-41671 | 0 |  | 10435.96 | 349.74
26-PC-41671 | 0 |  | 17873.85 | 562.68
26-PC-41671 | 0 |  | 7731.99 | 198.83
26-PC-41683 | 1 | 1109 | 0 | 0
26-PC-41683 | 0 |  | 0 | 0
26-PC-41707 | 1 | 1110 | 0 | 0
26-PC-41707 | 0 |  | 0 | 0
26-PC-41707 | 0 |  | 0 | 0
26-PC-41707 | 0 |  | 0 | 0
26-PC-41707 | 0 |  | 0 | 0
26-PC-41721 | 1 | 1111 | 0 | 0
26-PC-41721 | 0 |  | 0 | 0
26-PC-41721 | 0 |  | 0 | 0
26-PC-41721 | 0 |  | 0 | 0
26-PC-41721 | 0 |  | 0 | 0
26-PC-41721 | 0 |  | 1065.39 | 14.25
26-PC-41739 | 1 | 1112 | 0 | 0
26-PC-41739 | 0 |  | 362.15 | 6.75
26-PC-41750 | 1 | 1113 | 0 | 0
26-PC-41750 | 0 |  | 0 | 0
26-PC-41750 | 0 |  | 0 | 0
26-PC-41750 | 0 |  | 0 | 0
26-PC-41750 | 0 |  | 0 | 0
26-PC-41776 | 1 | 1114 | 0 | 0
26-PC-41776 | 0 |  | 0 | 0
26-PC-41776 | 0 |  | 0 | 0
26-PC-41776 | 0 |  | 0 | 0
26-PC-41776 | 0 |  | 700.26 | 13.75
26-PC-41803 | 1 | 1115 | 0 | 0
26-PC-41803 | 0 |  | 0 | 0
26-PC-41803 | 0 |  | 0 | 0
26-PC-41803 | 0 |  | 534.2 | 11.25
26-PC-41821 | 1 | 1116 | 0 | 0
26-PC-41821 | 0 |  | 161.69 | 2.25
26-PC-41863 | 1 | 1117 | 0 | 0
26-PC-41863 | 0 |  | 0 | 0
26-PC-41863 | 0 |  | 76.2 | 0.75
26-PC-41865 | 1 | 1118 | 0 | 0
26-PC-41865 | 0 |  | 0 | 0
26-PC-41865 | 0 |  | 0 | 0
26-PC-41884 | 1 | 1119 | 0 | 0
26-PC-41884 | 0 |  | 1805.93 | 40.75
26-PC-41918 | 1 | 1120 | 0 | 0
26-PC-41918 | 0 |  | 0 | 0
26-PC-41918 | 0 |  | 0 | 0
26-PC-41918 | 0 |  | 0 | 0
26-PC-41918 | 0 |  | 0 | 0
26-PC-41918 | 0 |  | 108.52 | 2.5
26-PC-41947 | 1 | 1121 | 0 | 0
26-PC-41947 | 0 |  | 0 | 0
26-PC-41947 | 0 |  | 115.23 | 1.5
26-PC-41947 | 0 |  | 0 | 0
26-PC-41947 | 0 |  | 895.53 | 18.75
26-PC-41947 | 0 |  | 24.41 | 0.5
26-PC-41954 | 1 | 1122 | 917.13 | 61.93
26-PC-41954 | 0 |  | 1595.77 | 103.18
26-PC-41954 | 0 |  | 535.93 | 29.89
26-PC-41954 | 0 |  | 4925.07 | 242.44
26-PC-41954 | 0 |  | 4223.33 | 111.65
26-PC-41961 | 1 | 1123 | 0 | 0
26-PC-41961 | 0 |  | 0 | 0
26-PC-41961 | 0 |  | 0 | 0
26-PC-41961 | 0 |  | 867.93 | 15.75
26-PC-41970 | 1 | 1124 | 0 | 0
26-PC-41970 | 0 |  | 0 | 0
26-PC-41970 | 0 |  | 0 | 0
26-PC-41970 | 0 |  | 0 | 0
26-PC-41970 | 0 |  | 964.01 | 21
26-PC-41987 | 1 | 1125 | 0 | 0
26-PC-42007 | 1 | 1126 | 0 | 0
26-PC-42007 | 0 |  | 0 | 0
26-PC-42007 | 0 |  | 0 | 0
26-PC-42007 | 0 |  | 0 | 0
26-PC-42007 | 0 |  | 135.63 | 2.75
26-PC-42008 | 1 | 1127 | 0 | 0
26-PC-42008 | 0 |  | 0 | 0
26-PC-42008 | 0 |  | 0 | 0
26-PC-42023 | 1 | 1128 | 0 | 0
26-PC-42023 | 0 |  | 0 | 0
26-PC-42023 | 0 |  | 0 | 0
26-PC-42023 | 0 |  | -295.92 | -6
26-PC-42040 | 1 | 1129 | 0 | 0
26-PC-42040 | 0 |  | 0 | 0
26-PC-42040 | 0 |  | 0 | 0
26-PC-42040 | 0 |  | 0 | 0
26-PC-42040 | 0 |  | 0 | 0
26-PC-42040 | 0 |  | 602.87 | 7.75
26-PC-42099 | 1 | 1130 | 0 | 0
26-PC-42099 | 0 |  | 2487.67 | 41
26-PC-42105 | 1 | 1131 | 7592.8 | 342.35
26-PC-42105 | 0 |  | 20985.67 | 955.15
26-PC-42105 | 0 |  | 35653 | 1460.86
26-PC-42105 | 0 |  | 22994.58 | 766
26-PC-42105 | 0 |  | 15946.6 | 640.43
26-PC-42108 | 1 | 1132 | 0 | 0
26-PC-42108 | 0 |  | 0 | 0
26-PC-42108 | 0 |  | 0 | 0
26-PC-42108 | 0 |  | 381 | 3.75
26-PC-42222 | 1 | 1133 | 0 | 0
26-PC-42222 | 0 |  | 0 | 0
26-PC-42222 | 0 |  | 0 | 0
26-PC-42222 | 0 |  | 0 | 0
26-PC-42222 | 0 |  | 0 | 0
26-PC-42293 | 1 | 1134 | 0 | 0
26-PC-42293 | 0 |  | 0 | 0
26-PC-42293 | 0 |  | 465.3 | 11
26-PC-42406 | 1 | 1135 | 0 | 0
26-PC-42406 | 0 |  | 0 | 11.03
26-PC-42406 | 0 |  | 0 | 0
26-PC-42406 | 0 |  | 0 | 0
26-PC-42427 | 1 | 1136 | 0 | 0
26-PC-42427 | 0 |  | 1989.73 | 42.25
26-PC-42428 | 1 | 1137 | 0 | 0
26-PC-42428 | 0 |  | 0 | 0
26-PC-42428 | 0 |  | 0 | 0
26-PC-42428 | 0 |  | 169.25 | 4.5
26-PC-42472 | 1 | 1138 | 0 | 0
26-PC-42472 | 0 |  | 0 | 0
26-PC-42472 | 0 |  | 0 | 0
26-PC-42472 | 0 |  | 0 | 0
26-PC-42472 | 0 |  | 0 | 0
26-PC-42472 | 0 |  | 547.25 | 12.5
26-PC-42492 | 1 | 1139 | 0 | 0
26-PC-42492 | 0 |  | 0 | 0
26-PC-42492 | 0 |  | 0 | 0
26-PC-42492 | 0 |  | 0 | 0
26-PC-42492 | 0 |  | 0 | 0
26-PC-42492 | 0 |  | 69.83 | 1.75
26-PC-42510 | 1 | 1140 | 0 | 0
26-PC-42510 | 0 |  | 0 | 0
26-PC-42510 | 0 |  | 0 | 0
26-PC-42510 | 0 |  | 0 | 0
26-PC-42510 | 0 |  | 0 | 0
26-PC-42510 | 0 |  | 1915.02 | 47
26-PC-42554 | 1 | 1141 | 0 | 0
26-PC-42554 | 0 |  | 0 | 0
26-PC-42554 | 0 |  | 0 | 0
26-PC-42554 | 0 |  | 0 | 0
26-PC-42554 | 0 |  | 197.37 | 3
26-PC-42585 | 1 | 1142 | 0 | 0
26-PC-42585 | 0 |  | 0 | 0
26-PC-42598 | 1 | 1143 | 0 | 0
26-PC-42598 | 0 |  | 0 | 0
26-PC-42598 | 0 |  | 0 | 0
26-PC-42598 | 0 |  | 0 | 1.25
26-PC-42598 | 0 |  | 593.44 | 8.75
26-PC-42616 | 1 | 1144 | 0 | 0
26-PC-42616 | 0 |  | 0 | 0
26-PC-42616 | 0 |  | 0 | 0
26-PC-42616 | 0 |  | 0 | 0
26-PC-42616 | 0 |  | 0 | 0
26-PC-42648 | 1 | 1145 | 0 | 0
26-PC-42648 | 0 |  | 0 | 0
26-PC-42648 | 0 |  | 0 | 0
26-PC-42648 | 0 |  | 0 | 0
26-PC-42648 | 0 |  | 0 | 0
26-PC-42664 | 1 | 1146 | 0 | 0
26-PC-42664 | 0 |  | 0 | 0
26-PC-42664 | 0 |  | 0 | 0
26-PC-42664 | 0 |  | 0 | 0
26-PC-42664 | 0 |  | 0 | 0
26-PC-42679 | 1 | 1147 | 0 | 0
26-PC-42679 | 0 |  | 1989.36 | 27.75
26-PC-42692 | 1 | 1148 | 0 | 0
26-PC-42692 | 0 |  | 0 | 0
26-PC-42692 | 0 |  | 468 | 4
26-PC-42734 | 1 | 1149 | 221.01 | 16.25
26-PC-42734 | 0 |  | 0 | 0
26-PC-42734 | 0 |  | 0 | 0
26-PC-42734 | 0 |  | 0 | 0
26-PC-42734 | 0 |  | 561.7 | 7.75
26-PC-42757 | 1 | 1150 | 0 | 0
26-PC-42757 | 0 |  | 1601.28 | 135.5
26-PC-42757 | 0 |  | 0 | 0
26-PC-42757 | 0 |  | 4304.67 | 65.75
26-PC-42759 | 1 | 1151 | 0 | 104.55
26-PC-42788 | 1 | 1152 | 38150.92 | 0
26-PC-42788 | 0 |  | 63660.49 | 0
26-PC-42788 | 0 |  | 74539.46 | 1008.28
26-PC-42788 | 0 |  | 15323.47 | 0
26-PC-42788 | 0 |  | 17692.74 | 0
26-PC-42811 | 1 | 1153 | 171.07 | 7.56
26-PC-42811 | 0 |  | 114.46 | 2.97
26-PC-42811 | 0 |  | 327.84 | 7.6
26-PC-42811 | 0 |  | 479.81 | 8.2
26-PC-42832 | 1 | 1154 | 0 | 0
26-PC-42832 | 0 |  | 0 | 0
26-PC-42832 | 0 |  | 0 | 0
26-PC-42832 | 0 |  | 0 | 0
26-PC-42832 | 0 |  | 0 | 0
26-PC-42832 | 0 |  | 235.67 | 5.25
26-PC-42838 | 1 | 1155 | 0 | 0
26-PC-42838 | 0 |  | 0 | 0
26-PC-42838 | 0 |  | 0 | 0
26-PC-42838 | 0 |  | 0 | 0
26-PC-42838 | 0 |  | 189.77 | 4.5
26-PC-42859 | 1 | 1156 | 0 | 0
26-PC-42880 | 1 | 1157 | 0 | 0
26-PC-42898 | 1 | 1158 | 0 | 210.89
26-PC-42898 | 0 |  | 0 | 59.73
26-PC-42898 | 0 |  | 0 | 159.92
26-PC-42926 | 1 | 1159 | 0 | 0
26-PC-42926 | 0 |  | 0 | 0
26-PC-42926 | 0 |  | 0 | 0
26-PC-42926 | 0 |  | 0 | 0
26-PC-42926 | 0 |  | 0 | 0
26-PC-42940 | 1 | 1160 | 1070.62 | 34.07
26-PC-42940 | 0 |  | 472.62 | 8.62
26-PC-42940 | 0 |  | 1347.02 | 8.55
26-PC-42940 | 0 |  | 537.41 | 12.14
26-PC-42951 | 1 | 1161 | 1363.84 | 7.98
26-PC-42951 | 0 |  | 5744.79 | 328.83
26-PC-42951 | 0 |  | 3458.74 | 220.93
26-PC-42962 | 1 | 1162 | 0 | 0
26-PC-42962 | 0 |  | 0 | 0
26-PC-42962 | 0 |  | 0 | 0
26-PC-42962 | 0 |  | 0 | 0
26-PC-42989 | 1 | 1163 | 0 | 0
26-PC-42989 | 0 |  | 0 | 0
26-PC-42989 | 0 |  | 18.68 | 0.5
26-PC-43000 | 1 | 1164 | 1732.58 | 715.22
26-PC-43026 | 1 | 1165 | 0 | 0
26-PC-43026 | 0 |  | 0 | 0
26-PC-43026 | 0 |  | 0 | 0
26-PC-43026 | 0 |  | 0 | 0
26-PC-43026 | 0 |  | 0 | 0
26-PC-43039 | 1 | 1166 | 11151.65 | 0
26-PC-43039 | 0 |  | 119.67 | 3
26-PC-43059 | 1 | 1167 | 1748.02 | 29.61
26-PC-43059 | 0 |  | 1170.91 | 11.63
26-PC-43059 | 0 |  | 1132.74 | 4.56
26-PC-43059 | 0 |  | 2725.78 | 0
26-PC-43086 | 1 | 1168 | 0 | 0
26-PC-43086 | 0 |  | 0 | 0
26-PC-43086 | 0 |  | 0 | 0
26-PC-43086 | 0 |  | 0 | 0
26-PC-43132 | 1 | 1169 | 0 | 0
26-PC-43132 | 0 |  | 0 | 0
26-PC-43132 | 0 |  | 0 | 0
26-PC-43132 | 0 |  | 1263.26 | 45
26-PC-43132 | 0 |  | 0 | 0
26-PC-43132 | 0 |  | 369.5 | 5.75
26-PC-43136 | 1 | 1170 | 0 | 0
26-PC-43136 | 0 |  | 0 | 0
26-PC-43136 | 0 |  | 2521.33 | 44.25
26-PC-43168 | 1 | 1171 | 0 | 0
26-PC-43168 | 0 |  | 1048.69 | 24.25
26-PC-43191 | 1 | 1172 | 1608.87 | 0
26-PC-43199 | 1 | 1173 | 0 | 87.58
26-PC-43222 | 1 | 1174 | 0 | 0
26-PC-43222 | 0 |  | 0 | 0
26-PC-43222 | 0 |  | 0 | 0
26-PC-43222 | 0 |  | 0 | 0
26-PC-43222 | 0 |  | 0 | 0
26-PC-43266 | 1 | 1175 | 0 | 0
26-PC-43266 | 0 |  | 0 | 0
26-PC-43266 | 0 |  | 0 | 0
26-PC-43307 | 1 | 1176 | 0 | 0
26-PC-43307 | 0 |  | 0 | 0
26-PC-43307 | 0 |  | 582.84 | 12
26-PC-43329 | 1 | 1177 | 0 | 0
26-PC-43329 | 0 |  | 0 | 0
26-PC-43329 | 0 |  | 41.36 | 0
26-PC-43329 | 0 |  | 2616.8 | 8.75
26-PC-43329 | 0 |  | 583.85 | 7.5
26-PC-43338 | 1 | 1178 | 0 | 0
26-PC-43338 | 0 |  | 0 | 0
26-PC-43341 | 1 | 1179 | 0 | 0
26-PC-43341 | 0 |  | 0 | 0
26-PC-43341 | 0 |  | 0 | 17.91
26-PC-43341 | 0 |  | 0 | 0
26-PC-43341 | 0 |  | 0 | 3.89
26-PC-43364 | 1 | 1180 | 1286.05 | 31
26-PC-43364 | 0 |  | 2312.23 | 57.25
26-PC-43364 | 0 |  | 2087.75 | 67.5
26-PC-43364 | 0 |  | 515.86 | 9.75
26-PC-43381 | 1 | 1181 | 0 | 0
26-PC-43381 | 0 |  | 1063.92 | 13
26-PC-43404 | 1 | 1182 | 16310.73 | 464.9
26-PC-43404 | 0 |  | 11351.14 | 241.81
26-PC-43404 | 0 |  | 12953.04 | 357.15
26-PC-43404 | 0 |  | 6177.15 | 164.9
26-PC-43429 | 1 | 1183 | 0 | 0
26-PC-43429 | 0 |  | 0 | 0
26-PC-43429 | 0 |  | 0 | 0
26-PC-43478 | 1 | 1184 | 0 | 0
26-PC-43478 | 0 |  | 0 | 0
26-PC-43478 | 0 |  | 2742.19 | 50
26-PC-43493 | 1 | 1185 | 0 | 0
26-PC-43493 | 0 |  | 0 | 0
26-PC-43493 | 0 |  | 0 | 0
26-PC-43493 | 0 |  | 1348.45 | 27.25
26-PC-43519 | 1 | 1186 | 41.58 | 0
26-PC-43519 | 0 |  | 6.32 | 0
26-PC-43519 | 0 |  | 6.18 | 0
26-PC-43527 | 1 | 1187 | 0 | 0
26-PC-43527 | 0 |  | 0 | 0
26-PC-43527 | 0 |  | 0 | 0
26-PC-43527 | 0 |  | 0 | 0
26-PC-43527 | 0 |  | 0 | 0
26-PC-43527 | 0 |  | 1977.61 | 18.75
26-PC-43528 | 1 | 1188 | 0 | 0
26-PC-43528 | 0 |  | 1108.65 | 14.25
26-PC-43546 | 1 | 1189 | 21036.36 | 329.75
26-PC-43546 | 0 |  | 3326.74 | 179.25
26-PC-43546 | 0 |  | 0 | 0
26-PC-43546 | 0 |  | 326.14 | 6
26-PC-43563 | 1 | 1190 | 0 | 0
26-PC-43563 | 0 |  | 0 | 0
26-PC-43563 | 0 |  | 461.62 | 6.25
26-PC-43575 | 1 | 1191 | 0 | 0
26-PC-43575 | 0 |  | 2531.64 | 44.75
26-PC-43584 | 1 | 1192 | 0 | 0
26-PC-43584 | 0 |  | 0 | 0
26-PC-43584 | 0 |  | 0 | 0
26-PC-43584 | 0 |  | 0 | 0
26-PC-43695 | 1 | 1193 | 0 | 0
26-PC-43695 | 0 |  | 0 | 0
26-PC-43695 | 0 |  | 0 | 0
26-PC-43695 | 0 |  | 0 | 0
26-PC-43695 | 0 |  | 630.69 | 14
26-PC-43731 | 1 | 1194 | 0 | 0
26-PC-43731 | 0 |  | 0 | 0
26-PC-43731 | 0 |  | 0 | 0
26-PC-43731 | 0 |  | 0 | 0
26-PC-43731 | 0 |  | 0 | 0
26-PC-43746 | 1 | 1195 | 0 | 0
26-PC-43762 | 1 | 1196 | 0 | 0
26-PC-43762 | 0 |  | 0 | 0
26-PC-43762 | 0 |  | 0 | 0
26-PC-43762 | 0 |  | 0 | 0
26-PC-43818 | 1 | 1197 | 0 | 0
26-PC-43818 | 0 |  | 0 | 0
26-PC-43818 | 0 |  | 0 | 0
26-PC-43818 | 0 |  | 0 | 0
26-PC-43818 | 0 |  | 0 | 0
26-PC-43874 | 1 | 1198 | 0 | 0
26-PC-43874 | 0 |  | 0 | 0
26-PC-43899 | 1 | 1199 | 0 | 0
26-PC-43899 | 0 |  | 0 | 0
26-PC-43899 | 0 |  | 0 | 0
26-PC-43899 | 0 |  | 0 | 0
26-PC-43915 | 1 | 1200 | 0 | 0
26-PC-43915 | 0 |  | 0 | 0
26-PC-43915 | 0 |  | 0 | 0
26-PC-43915 | 0 |  | 0 | 0
26-PC-43927 | 1 | 1201 | 0 | 0
26-PC-43927 | 0 |  | 0 | 0
26-PC-43927 | 0 |  | 0 | 0
26-PC-43927 | 0 |  | 75.84 | 1.5
26-PC-43957 | 1 | 1202 | 20492.05 | 778.78
26-PC-43957 | 0 |  | 16735.68 | 227.87
26-PC-43961 | 1 | 1203 | 1692.95 | 7.5
26-PC-43961 | 0 |  | 0 | 0
26-PC-43961 | 0 |  | 0 | 0
26-PC-43961 | 0 |  | 0 | 0
26-PC-43961 | 0 |  | 0 | 0
26-PC-43961 | 0 |  | 1572.5 | 27.75
26-PC-43963 | 1 | 1204 | 0 | 0
26-PC-43963 | 0 |  | 0 | 0
26-PC-43963 | 0 |  | 0 | 0
26-PC-43963 | 0 |  | 0 | 0
26-PC-43963 | 0 |  | 0 | 0
26-PC-43963 | 0 |  | 1631.56 | 32.5
26-PC-43979 | 1 | 1205 | 0 | 0
26-PC-43979 | 0 |  | 0 | 0
26-PC-43979 | 0 |  | 0 | 0
26-PC-43986 | 1 | 1206 | 15588.91 | 166.25
26-PC-43986 | 0 |  | 31727.73 | 375
26-PC-43986 | 0 |  | 0 | 0
26-PC-43986 | 0 |  | 1571.3 | 20
26-PC-43991 | 1 | 1207 | 0 | 0
26-PC-43991 | 0 |  | 0 | 0
26-PC-43991 | 0 |  | 110.82 | 3
26-PC-43991 | 0 |  | 0 | 0
26-PC-43991 | 0 |  | 0 | 0
26-PC-43991 | 0 |  | 59.86 | 0.5
26-PC-44007 | 1 | 1208 | 0 | 0
26-PC-44050 | 1 | 1209 | 0 | 0
26-PC-44050 | 0 |  | 0 | 0
26-PC-44050 | 0 |  | 0 | 0
26-PC-44050 | 0 |  | 0 | 0
26-PC-44050 | 0 |  | 0 | 0
26-PC-44050 | 0 |  | 1013.31 | 20.25
26-PC-44072 | 1 | 1210 | 0 | 0
26-PC-44072 | 0 |  | 939.31 | 12.5
26-PC-44090 | 1 | 1211 | 0 | 0
26-PC-44090 | 0 |  | 0 | 0
26-PC-44090 | 0 |  | 0 | 0
26-PC-44090 | 0 |  | 0 | 0
26-PC-44090 | 0 |  | 0 | 0
26-PC-44129 | 1 | 1212 | 0 | 0
26-PC-44129 | 0 |  | 0 | 0
26-PC-44129 | 0 |  | 0 | 0
26-PC-44129 | 0 |  | 0 | 0
26-PC-44173 | 1 | 1213 | 0 | 0
26-PC-44173 | 0 |  | 0 | 0
26-PC-44173 | 0 |  | 0 | 0
26-PC-44173 | 0 |  | 822.44 | 16.5
26-PC-44201 | 1 | 1214 | 0 | 0
26-PC-44201 | 0 |  | 1384.2 | 15
26-PC-44220 | 1 | 1215 | 0 | 0
26-PC-44220 | 0 |  | 0 | 0
26-PC-44220 | 0 |  | 165.22 | 3.75
26-PC-44256 | 1 | 1216 | 0 | 0
26-PC-44256 | 0 |  | 0 | 0
26-PC-44256 | 0 |  | 5832.23 | 84.25
26-PC-44277 | 1 | 1217 | 0 | 0
26-PC-44277 | 0 |  | 0 | 0
26-PC-44277 | 0 |  | 365.66 | 10.5
26-PC-44277 | 0 |  | 168.82 | 2.25
26-PC-44290 | 1 | 1218 | 0 | 0
26-PC-44290 | 0 |  | 0 | 0
26-PC-44290 | 0 |  | 0 | 0
26-PC-44290 | 0 |  | 0 | 0
26-PC-44290 | 0 |  | 0 | 0
26-PC-44290 | 0 |  | 926.55 | 11.25
26-PC-44302 | 1 | 1219 | 0 | 0
26-PC-44302 | 0 |  | 0 | 0
26-PC-44302 | 0 |  | 0 | 0
26-PC-44302 | 0 |  | 0 | 0
26-PC-44302 | 0 |  | 0 | 0
26-PC-44302 | 0 |  | 1286.99 | 10.75
0
0
0
0

## How to Refresh
Weekly Refresh — How It Works
Project Details is driven entirely by formulas: refresh it by pasting the two new ERP exports into their tabs; nothing is typed by hand.
Steps each week
1. Run the "Budget to Actual Costs by Task" report in the ERP and copy the whole sheet.
2. Paste it at cell A1 of this workbook's tab of the same name. Always paste into the existing tab; replacing the tab renames it and breaks every reference to it.
3. Repeat with the "OTC All reports keys account in" report and its tab.
4. Go to Project Details (press F9 if the numbers have not updated) and read the status line in A3 before using anything.
The status line (Project Details cell A3)
When the layout checks in _Calc all pass, A3 shows "Layout check OK" with the project count and the number of projects over 5%. If the ERP moves a column, A3 switches to "EXPORT LAYOUT CHANGED" with the number of failed checks: stop and fix the column mapping instead of using the figures.
How this file handles the current export layout
• Header and data rows sit below a report banner on both tabs, and subtotal rows ("All Tasks", "All Locations", "All Customers", "All Projects") appear. The formulas find the header row by name and ignore label and total lines, so row drift is harmless.
• A spacer column sits before the money columns on the Budget-to-Actual tab (Contract Value G, Revised Budget I, Total Costs N, Budgeted Hours O, Actual Hours P).
• The export does not supply "Task Overrun $" or "Task Overrun Hours". Both are calculated per task in the hidden _Calc tab: when a task has a revised budget, overrun = Total Cost minus Revised Budget, floored at zero; when it has no revised budget the overrun is zero, except on "OVHD-Non-Posting - Overhead Non-Posting" lines, where the full cost carries as overrun (including credits, which carry as negatives). This export has 1,422 task lines with a non-zero overrun.
• The OTC export returns Location ID and Project Manager ID instead of names. A hidden "_Lookup" tab translates them back to names (26 locations, 104 managers). Any ID not in that list displays as the raw ID — add a row to _Lookup to name it.
Housekeeping
• When a new export is shorter than the last one, clear the old rows left below the pasted data on both tabs.
• Project Details is all formulas — never overwrite a cell with a typed value. Filtering the sheet is fine; sorting it is not.
• The report depends on the hidden _Calc (per-task overrun) and _Lookup (ID to name) tabs — do not delete or rename them.
• Capacity: ~16,000 task rows and ~6,000 projects. Current data is 4,130 task rows and 1,219 projects.
What each computed column does
Contract Value, Revised Budget, Total Cost ITD, Budgeted Hours and Actual Hours are summed across the project’s task lines. Total Task Overrun and Task Overrun Hours are summed from the per-task overrun rule above. Task Overrun % = Overrun ÷ Revised Budget. "> 5%" = 1 when that is above 5%. Cost % Complete = (Total Cost − Overrun) ÷ Revised Budget. Hours Overrun % = Overrun Hours ÷ Budgeted Hours.

## _Lookup (hidden)
Location ID | Location Name | PM ID | Project Manager Name | Built from the 9.26.26 export (ID -> name). Add rows here for any new location or manager ID; unmapped IDs display as the raw ID on Project Details.
L8000 | Big Sky | E30900 | Carl Barajas
L8010 | Bluegrass | E30904 | Javier Estrada
L8020 | Cascade | E30905 | Brendan Melton
L8030 | Chesapeake | E30907 | Bob Frye
L8040 | Front Range | E30913 | Kiara Gillespie
L8050 | Great Lakes | E30916 | Alice Galloway
L8060 | Gulf Coast | E30923 | Jean Cooke
L8070 | High Desert | E30925 | Donald Lutz
L8080 | Island | E30935 | Jeff Spence
L8090 | Lakeshore | E30936 | Gene Nixon
L8100 | Hill Country | E30937 | Cassidy Gay
L8110 | Piedmont | E30942 | Preston Duarte
L8120 | Prairie | E30947 | Bryan Mann
L8130 | Red Rock | E30948 | Alexandria Wilkinson
L8140 | Sierra | E30950 | Ian Maddox
L8150 | Coastal Bend | E30957 | Sandy Kerr
L8160 | Built Environment | E30958 | Jason Oconnor
L8170 | Paleontology | E30965 | Reginald Vargas
L8180 | Maritime | E30967 | Kimberly Daugherty
L8190 | Geospatial | E30971 | Jeremy Tran
L8200 | Meridian Central | E30972 | Devon Pitts
L8210 | Meridian Southwest | E30976 | Joanna Herrera
L8220 | NH Gulf (USD) | E30979 | Mindy Galvan
L8230 | Corporate | E30980 | Dean Velazquez
L8240 | Sales and Marketing | E30984 | Angelica Cervantes
L8250 | Archive Services | E30985 | Robin Mercado
|  | E30986 | Geoffrey Fernandez
|  | E30987 | Karl Valenzuela
|  | E30992 | Leonard Mejia
|  | E30995 | Nathan Lambert
|  | E30997 | Reginald Koch
|  | E30998 | Gina Beltran
|  | E30999 | Kathleen Galvan
|  | E31000 | Brendan Padilla
|  | E31001 | Jeff Pugh
|  | E31008 | Sean Jennings
|  | E31014 | Courtney Daugherty
|  | E31018 | Bernard Erickson
|  | E31019 | Wyatt Erickson
|  | E31023 | Jody Wang
|  | E31029 | Bridget Maddox
|  | E31032 | Kathy Hurley
|  | E31034 | Eileen Poole
|  | E31041 | Briana Melton
|  | E31043 | Joan Mathis
|  | E31044 | Rodney Mcguire
|  | E31046 | Maurice Dodson
|  | E31047 | Becky Velazquez
|  | E31050 | Jeanette Riddle
|  | E31051 | Lucas Benson
|  | E31052 | Terrence Gillespie
|  | E31055 | Glen Delacruz
|  | E31057 | Marcus Shea
|  | E31058 | Suzanne Mcmillan
|  | E31059 | Danielle Villanueva
|  | E31061 | Theresa Fernandez
|  | E31062 | Samuel Wilkerson
|  | E31063 | Gail Meza
|  | E31068 | Megan Pineda
|  | E31070 | Jody Chung
|  | E31073 | Annette Vaughan
|  | E31074 | Maria Parrish
|  | E31079 | Sherry Lloyd
|  | E31088 | Bruce Suarez
|  | E31092 | Javier Newman
|  | E31095 | Marisa Odom
|  | E31097 | Lydia Cisneros
|  | E31105 | Jeanette Chung
|  | E31107 | Tina Aguirre
|  | E31110 | Shelia Horne
|  | E31121 | Louis Huff
|  | E31122 | Benjamin Mathis
|  | E31127 | Donna Herring
|  | E31128 | Angelica Poole
|  | E31137 | Duane Ballard
|  | E31138 | Diane Daniels
|  | E31141 | Steve Rubio
|  | E31150 | Jared Choi
|  | E31151 | Alexis Nixon
|  | E31162 | Kathleen Cabrera
|  | E31167 | Melody Holloway
|  | E31170 | Rickey Salas
|  | E31172 | Jenny Wilkinson
|  | E31173 | Jesse Maynard
|  | E31175 | Charlene Sparks
|  | E31179 | Travis Delgado
|  | E31185 | Kyle Maynard
|  | E31188 | Rita Ayala
|  | E31192 | Priscilla Pennington
|  | E31193 | Sylvia Callahan
|  | E31196 | Seth Zavala
|  | E31199 | Mathew Shea
|  | E31200 | Clinton Solis
|  | E31202 | Raymond Hensley
|  | E31205 | Harold Chaney
|  | E31206 | Lynn Tran
|  | E31207 | Reginald Kerr
|  | E31209 | Alan Gay
|  | E31211 | Tonya Spence
|  | E31213 | Susan Wilkins
|  | E31218 | Randy Cantu
|  | E31220 | Vanessa Duarte
|  | E31221 | Javier Rangel
|  | E31222 | Justin Mejia