## All Active Projects
Northstar Heritage, LLC
FP&A & QC Project Report
As of June 16, 2026
[6 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Total Budget | Total Budget Adjustment | Total Costs |  |  |  | Recognized %
[6 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Remaining Budget | Orig Budget Remaining |  | REV REC % | Budget Spent %
[6 empty] | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026 | 06/16/2026
Project ID | Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Original Budget Remaining | teamwork Status | Actual | Summary
23-PC-30307 | Quail Run Wastewater Plant Cultural Resources Assessment | In Progress | Fixed fee | Big Sky | Javier Estrada | 240100 | 157553.62 | 157553.62 | 136256.75 | 136256.75 | 0 | 89412.87 | 46843.88 | 46843.88 |  | 65.6% | 65.62%
23-PC-30372 | Phase I: Lone Pine Reservoir Architectural History Survey | In Progress | Time and material | Big Sky | Bob Frye | 27100 | 18428 | 18428 | 19864.3 | 19864.3 | 0 | 11402.28 | 8462.02 | 8462.02 |  | 68% | 57.4%
23-PC-30543 | Phase III: Riverbend Rail Siding Maritime Remote Sensing Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 320600 | 225766.52 | 225766.52 | 255628.66 | 192683.15 | 62945.51 | 180013.95 | 75614.71 | 12669.2 |  | 70.4% | 70.42%
23-PC-30644 | Phase II: Millbrook Wastewater Plant Data Recovery | In Progress | Time and material | Bluegrass | Alice Galloway | 108100 | 73508 | 73508 | 72102.7 | 72102.7 | 0 | 46653.03 | 25449.67 | 25449.67 |  | 68% | 64.7%
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | In Progress | Time and material | Bluegrass | Kiara Gillespie | 49800 | 33864 | 33864 | 34501.44 | 34501.44 | 0 | 28656.36 | 5845.08 | 5845.08 |  | 68% | 83.06%
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 86200 | 58616 | 58616 | 58650.48 | 58650.48 | 0 | 61318.15 | -2667.67 | -2667.67 |  | 68% | 104.6%
23-PC-31003 | Windmill Flat Environmental Review Support | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 19300 | 15445.79 | 15445.79 | 10568.68 | 10568.68 | 0 | 8458.51 | 2110.17 | 2110.17 |  | 80% | 80.03%
23-PC-31042 | Stone Mill Historic Resources Evaluation | In Progress | Time and material | Cascade | Donald Lutz | 299700 | 203796 | 203796 | 202896.9 | 202896.9 | 0 | 147919.88 | 54977.02 | 54977.02 |  | 68% | 72.9%
23-PC-31076 | Wildrye Rail Siding - Archaeological Testing | Final Reporting/Review | Time and material | Cascade | Cassidy Gay | 95100 | 64668 | 64668 | 65561.94 | 65561.94 | 0 | 41531.43 | 24030.51 | 24030.51 |  | 68% | 63.35%
23-PC-31344 | Timber Gap Battery Storage Archaeological Testing | In Progress | Fixed fee | Cascade | Cassidy Gay | 331600 | 194516.56 | 194516.56 | 264351.52 | 264351.52 | 0 | 155057.32 | 109294.2 | 109294.2 |  | 58.7% | 58.66%
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | In Progress | Time and material | Cascade | Donald Lutz | 255700 | 173876 | 173876 | 168225.03 | 168225.03 | 0 | 202903.45 | -34678.42 | -34678.42 |  | 68% | 120.6%
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | In Progress | Fixed fee | Cascade | Jeff Spence | 108000 | 76528.8 | 76528.8 | 82404 | 82404 | 0 | 58391.35 | 24012.65 | 24012.65 |  | 70.9% | 70.86%
23-PC-31765 | Saltgrass Phase I Survey | Final Reporting/Review | Fixed fee | Cascade | Jean Cooke | 32700 | 18707.67 | 18707.67 | 27114.84 | 27114.84 | 0 | 15513.28 | 11601.56 | 11601.56 |  | 57.2% | 57.21%
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | In Progress | Fixed fee | Cascade | Gene Nixon | 34800 | 34800 | 34800 | 28779.6 | 28779.6 | 0 | 31540.76 | -2761.16 | -2761.16 |  | 100% | 109.6%
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | In Progress | Fixed fee | Cascade | Jeff Spence | 460600 | 348674.2 | 348674.2 | 390957.28 | 390957.28 | 0 | 295973.9 | 94983.38 | 94983.38 |  | 75.7% | 75.7%
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Jeff Spence | 175300 | 175300 | 175300 | 93481.01 | 71376.84 | 22104.17 | 112759.17 | -19278.16 | -41382.33 |  | 100% | 120.6%
23-PC-32015 | Copper Flats Harbor Dredging - Class III Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 89300 | 40524.34 | 40524.34 | 65024.25 | 59234.48 | 5789.77 | 29508.22 | 35516.03 | 29726.26 |  | 45.4% | 45.38%
23-PC-32278 | Coyote Springs Highway Widening Paleontological Monitoring | Lab/Curation | Time and material | Chesapeake | Ian Maddox | 3500 | 2380 | 2380 | 2281.3 | 2281.3 | 0 | 1738.97 | 542.33 | 542.33 |  | 68% | 76.23%
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 149100 | 132892.83 | 132892.83 | 111109.32 | 111109.32 | 0 | 99032.78 | 12076.54 | 12076.54 |  | 89.1% | 89.13%
23-PC-32443 | Tamarack Battery Storage - Cultural Resources Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann | 152600 | 117078.5 | 117078.5 | 107415.14 | 107415.14 | 0 | 63511.77 | 43903.37 | 43903.37 |  | 76.7% | 59.13%
23-PC-32520 | Tamarack Battery Storage GIS Mapping | Lab/Curation | Time and material | Chesapeake | Ian Maddox | 1116300 | 759084 | 759084 | 767567.88 | 767567.88 | 0 | 601405.25 | 166162.63 | 166162.63 |  | 68% | 78.35%
23-PC-32635 | Rushgrass Draw Curation | Cost Tracking on Closed Project | Time and material | Chesapeake | Jason Oconnor | 36800 | 25024 | 25024 | 24644.96 | 24644.96 | 0 | 27323.95 | -2678.99 | -2678.99 |  | 68% | 110.9%
23-PC-33001 | Heron Marsh Environmental Review Support | In Progress | Time and material | Front Range | Dean Velazquez | 356400 | 242352 | 242352 | 221573.88 | 221573.88 | 0 | 127558.9 | 94014.98 | 94014.98 |  | 68% | 57.57%
23-PC-33070 | Meadowlark Curation | In Progress | Fixed fee | Front Range | Reginald Vargas | 55100 | 46377.67 | 46377.67 | 34299.75 | 34299.75 | 0 | 28871.53 | 5428.22 | 5428.22 |  | 84.2% | 84.17%
23-PC-33151 | Sandpiper Class III Survey | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 637100 | 540961.61 | 540961.61 | 497638.81 | 497638.81 | 0 | 422546.87 | 75091.94 | 75091.94 |  | 84.9% | 84.91%
23-PC-33471 | Sandpiper Park Improvements - Environmental Review Support | Lab/Curation | Time and material | Front Range | Devon Pitts | 113200 | 76976 | 76976 | 80813.48 | 80813.48 | 0 | 61581.06 | 19232.42 | 19232.42 |  | 68% | 76.2%
23-PC-33551 | Heron Marsh Airport Apron GIS Mapping | Final Reporting/Review | Time and material | Front Range | Reginald Vargas | 95400 | 64872 | 64872 | 62019.54 | 62019.54 | 0 | 47726 | 14293.54 | 14293.54 |  | 68% | 76.95%
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 21600 | 21600 | 21600 | 15245.28 | 15245.28 | 0 | 16551.79 | -1306.51 | -1306.51 |  | 100% | 108.6%
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | In Progress | Time and material | Great Lakes | Jeff Pugh | 300600 | 204408 | 204408 | 219257.64 | 219257.64 | 0 | 176674.59 | 42583.05 | 42583.05 |  | 68% | 80.58%
23-PC-33998 | Phase II: Granite Pass Reservoir Class III Survey | In Progress | Time and material | Great Lakes | Nathan Lambert | 238800 | 162384 | 162384 | 156891.6 | 156891.6 | 0 | 95556.7 | 61334.9 | 61334.9 |  | 68% | 60.91%
23-PC-34171 | Timber Gap Rail Siding - Built Environment Survey | In Progress | Time and material | Great Lakes | Jeff Pugh | 221100 | 150348 | 150348 | 154858.44 | 154858.44 | 0 | 75735.59 | 79122.85 | 79122.85 |  | 68% | 48.91%
23-PC-34229 | Creosote Draw Mixed-Use Development Paleontological Monitoring | In Progress | Time and material | Great Lakes | Jeff Pugh | 48800 | 33184 | 33184 | 34427.85 | 31880.18 | 2547.67 | 25157.23 | 9270.62 | 6722.95 |  | 68% | 73.07%
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | In Progress | Time and material | Great Lakes | Kathleen Galvan | 373100 | 253708 | 253708 | 247626.47 | 247626.47 | 0 | 184659.6 | 62966.87 | 62966.87 |  | 68% | 74.57%
23-PC-34403 | Plover Cove Built Environment Survey | In Progress | Time and material | Great Lakes | Kathleen Galvan | 46200 | 31416 | 31416 | 30187.08 | 30187.08 | 0 | 23628.2 | 6558.88 | 6558.88 |  | 68% | 78.27%
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes | 477000 | 347303.7 | 347303.7 | 333756.9 | 333756.9 | 0 | 243019.93 | 90736.97 | 90736.97 |  | 72.8% | 72.81%
23-PC-34473 | Aspen Ridge Cell Tower Phase I Survey | In Progress | Time and material | Great Lakes | Leonard Mejia | 52300 | 35564 | 35564 | 36353.73 | 36353.73 | 0 | 23508.92 | 12844.81 | 12844.81 |  | 68% | 64.67%
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Final Reporting/Review | Time and material | Great Lakes | Geoffrey Fernandez | 70000 | 47600 | 47600 | 50246 | 50246 | 0 | 45814.41 | 4431.59 | 4431.59 |  | 68% | 91.18%
23-PC-34522 | Foxglove GIS Mapping | In Progress | Time and material | Great Lakes | Brendan Padilla | 192200 | 130696 | 130696 | 131503.24 | 131503.24 | 0 | 75113.75 | 56389.49 | 56389.49 |  | 68% | 57.12%
23-PC-34745 | Slate Ridge Battery Storage Environmental Review Support | In Progress | Fixed fee | Great Lakes | Robin Mercado | 614200 | 408504.42 | 408504.42 | 440258.56 | 440258.56 | 0 | 292800.8 | 147457.76 | 147457.76 |  | 66.5% | 66.51%
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Sean Jennings | 46100 | 32472.84 | 32472.84 | 31721.41 | 31721.41 | 0 | 22343.25 | 9378.16 | 9378.16 |  | 70.4% | 70.44%
23-PC-34811 | Task Order 2: Saltgrass Airport Apron Maritime Remote Sensing Survey | In Progress | Fixed fee | Gulf Coast West | Courtney Daugherty | 112600 | 92917.52 | 92917.52 | 80883.68 | 67188.42 | 13695.26 | 66744.54 | 14139.14 | 443.88 |  | 82.5% | 82.52%
23-PC-34826 | Task Order 13: Foxglove Canal Lining Cultural Resources Monitoring | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 168500 | 114580 | 114580 | 109642.95 | 109642.95 | 0 | 61763.3 | 47879.65 | 47879.65 |  | 68% | 56.33%
23-PC-34902 | Sumac Ridge Built Environment Survey | Final Reporting/Review | Time and material | Gulf Coast | Sean Jennings | 37000 | 25160 | 25160 | 26270 | 26270 | 0 | 17779.33 | 8490.67 | 8490.67 |  | 68% | 67.68%
23-PC-34939 | Maple Fork Maritime Remote Sensing Survey | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 145800 | 99144 | 99144 | 104172.04 | 89950 | 14222.04 | 74711.94 | 29460.1 | 15238.06 |  | 68% | 71.72%
23-PC-34947 | Aspen Ridge Cell Tower Architectural History Survey | In Progress | Fixed fee | Gulf Coast West | Wyatt Erickson | 285900 | 192753.78 | 192753.78 | 199615.38 | 199615.38 | 0 | 134588.76 | 65026.62 | 65026.62 |  | 67.4% | 67.42%
23-PC-35003 | Creosote Draw Archaeological Testing | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 187900 | 127772 | 127772 | 127170.72 | 127170.72 | 0 | 85671.58 | 41499.14 | 41499.14 |  | 68% | 67.37%
23-PC-35126 | Falcon Mesa Rail Siding Built Environment Survey | In Progress | Time and material | Gulf Coast West | Wyatt Erickson | 273100 | 185708 | 185708 | 197014.34 | 197014.34 | 0 | 105573.3 | 91441.04 | 91441.04 |  | 68% | 53.59%
23-PC-35176 | Plover Cove Mine Expansion Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Bernard Erickson | 74700 | 49496.22 | 49496.22 | 53388.09 | 53388.09 | 0 | 35373.34 | 18014.75 | 18014.75 |  | 66.3% | 66.26%
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | In Progress | Fixed fee | Gulf Coast East | Wyatt Erickson | 407900 | 303355.23 | 303355.23 | 321139.67 | 321139.67 | 0 | 238828.33 | 82311.34 | 82311.34 |  | 74.4% | 74.37%
23-PC-35425 | Yarrow Point Trail - GIS Mapping | Lab/Curation | Time and material | High Desert | Eileen Poole | 24000 | 16320 | 16320 | 15998.4 | 15998.4 | 0 | 13187.18 | 2811.22 | 2811.22 |  | 68% | 82.43%
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | In Progress | Time and material | High Desert | Jody Wang | 116200 | 79016 | 79016 | 87219.72 | 87219.72 | 0 | 78190.34 | 9029.38 | 9029.38 |  | 68% | 89.65%
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | In Progress | Fixed fee | High Desert | Eileen Poole | 11400 | 8681.1 | 8681.1 | 8206.86 | 8206.86 | 0 | 6249.46 | 1957.4 | 1957.4 |  | 76.2% | 76.15%
23-PC-35568 | Phase II: Coyote Springs Wind Farm Environmental Review Support | In Progress | Fixed fee | High Desert | Bridget Maddox | 253600 | 144374.48 | 144374.48 | 168365.04 | 168365.04 | 0 | 95853.64 | 72511.4 | 72511.4 |  | 56.9% | 56.93%
23-PC-35682 | Lantern Bay Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 290400 | 277361.04 | 277361.04 | 252938.4 | 252938.4 | 0 | 241578.4 | 11360 | 11360 |  | 95.5% | 95.51%
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 114600 | 104870.46 | 104870.46 | 77893.62 | 77893.62 | 0 | 71277.07 | 6616.55 | 6616.55 |  | 91.5% | 91.51%
23-PC-36385 | On-Call: Cedar Hollow Transmission Line Paleontological Monitoring | In Progress | Time and material | Island | Maurice Dodson | 392900 | 267172 | 267172 | 262008.61 | 207890.28 | 54118.33 | 185677.7 | 76330.91 | 22212.58 |  | 68% | 70.87%
23-PC-36422 | Hawk Point Phase I Survey | In Progress | Time and material | Island | Joan Mathis | 50700 | 34476 | 34476 | 36579.06 | 32790.93 | 3788.13 | 37409.59 | -830.53 | -4618.66 |  | 68% | 102.3%
23-PC-36530 | Lone Pine Architectural History Survey | In Progress | Time and material | Island | Joan Mathis | 141100 | 95948 | 95948 | 102823.29 | 89657.45 | 13165.84 | 97024.26 | 5799.03 | -7366.81 |  | 68% | 94.36%
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 201000 | 170226.9 | 170226.9 | 151513.8 | 151513.8 | 0 | 128322.24 | 23191.56 | 23191.56 |  | 84.7% | 84.69%
23-PC-36734 | Raven Rock Curation | In Progress | Fixed fee | Lakeshore | Terrence Gillespie | 38600 | 36284 | 36284 | 27753.4 | 27753.4 | 0 | 26089.14 | 1664.26 | 1664.26 |  | 94% | 94%
23-PC-36776 | On-Call: Twin Buttes Trail Phase I Survey | In Progress | Time and material | Hill Country | Danielle Villanueva | 457300 | 310964 | 310964 | 338564.86 | 268622.72 | 69942.14 | 214892.1 | 123672.76 | 53730.62 |  | 68% | 63.47%
23-PC-37105 | Foxglove Housing Development - Data Recovery | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 110800 | 82955.96 | 82955.96 | 80165.21 | 73023.16 | 7142.05 | 60019.34 | 20145.87 | 13003.82 |  | 74.9% | 74.87%
23-PC-37245 | Rushgrass Draw Wind Farm Archaeological Testing | In Progress | Fixed fee | Hill Country | Gail Meza | 425700 | 238392 | 238392 | 306248.58 | 306248.58 | 0 | 171495.1 | 134753.48 | 134753.48 |  | 56% | 56%
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | In Progress | Fixed fee | Piedmont - Inactive | Maria Parrish | 44500 | 31902.05 | 31902.05 | 35070.45 | 35070.45 | 0 | 25141.75 | 9928.7 | 9928.7 |  | 71.7% | 71.69%
23-PC-37590 | On-Call: Rushgrass Draw Water Main Environmental Review Support | In Progress | Fixed fee | PIEDMONT - INACTIVE | Annette Vaughan | 46500 | 28425.45 | 28425.45 | 36232.8 | 36232.8 | 0 | 22148.93 | 14083.87 | 14083.87 |  | 61.1% | 61.13%
23-PC-37763 | Bramble Creek School Campus - Environmental Review Support | In Progress | Time and material | PIEDMONT - INACTIVE | Megan Pineda | 35000 | 23800 | 23800 | 25056.5 | 25056.5 | 0 | 15144.42 | 9912.08 | 9912.08 |  | 68% | 60.44%
23-PC-38089 | Lone Pine Wastewater Plant - Phase I Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 110100 | 75132.24 | 75132.24 | 84001.75 | 72763.92 | 11237.83 | 57321.44 | 26680.31 | 15442.48 |  | 68.2% | 68.24%
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | In Progress | Time and material | Prairie | Sherry Lloyd | 128200 | 87176 | 87176 | 90073.32 | 90073.32 | 0 | 73724.08 | 16349.24 | 16349.24 |  | 68% | 81.85%
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 79800 | 57918.84 | 57918.84 | 53434.08 | 53434.08 | 0 | 38783.48 | 14650.6 | 14650.6 |  | 72.6% | 72.58%
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 67700 | 56556.58 | 56556.58 | 44688.77 | 44688.77 | 0 | 37332.05 | 7356.72 | 7356.72 |  | 83.5% | 83.54%
23-PC-38520 | On-Call: Larkspur Park Improvements Built Environment Survey | In Progress | Time and material | Red Rock | Marisa Odom | 148500 | 100980 | 100980 | 97074.45 | 97074.45 | 0 | 56211.48 | 40862.97 | 40862.97 |  | 68% | 57.91%
23-PC-38666 | Tamarack Paleontological Monitoring | In Progress | Fixed fee | Red Rock | Bruce Suarez | 390300 | 212479.32 | 212479.32 | 243898.47 | 243898.47 | 0 | 132781.77 | 111116.7 | 111116.7 |  | 54.4% | 54.44%
23-PC-38759 | Saltgrass Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Red Rock | Tina Aguirre | 52400 | 35632 | 35632 | 36847.68 | 36847.68 | 0 | 40372.44 | -3524.76 | -3524.76 |  | 68% | 109.6%
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | In Progress | Fixed fee | Red Rock | Tina Aguirre | 109400 | 86962.06 | 86962.06 | 83089.3 | 83089.3 | 0 | 66048.24 | 17041.06 | 17041.06 |  | 79.5% | 79.49%
23-PC-39063 | Task Order 21: Badger Hollow Substation Historic Resources Evaluation | Lab/Curation | Time and material | Red Rock | Lydia Cisneros | 24200 | 16456 | 16456 | 17235.24 | 17235.24 | 0 | 12296.83 | 4938.41 | 4938.41 |  | 68% | 71.35%
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | In Progress | Fixed fee | Red Rock | Jeanette Chung | 27800 | 20777.72 | 20777.72 | 18214.56 | 18214.56 | 0 | 13614.39 | 4600.17 | 4600.17 |  | 74.7% | 74.74%
23-PC-39323 | Silver Lake Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 550600 | 423136.1 | 423136.1 | 444994.92 | 444994.92 | 0 | 341994.21 | 103000.71 | 103000.71 |  | 76.8% | 76.85%
23-PC-39840 | Kestrel Butte Cell Tower - Curation | In Progress | Time and material | Red Rock | Bruce Suarez | 237700 | 164750.75 | 164750.75 | 173575 | 132634.88 | 40940.12 | 88754.16 | 84820.84 | 43880.72 |  | 69.3% | 51.13%
23-PC-39856 | Phase II: Thistle Down Transmission Line Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 91300 | 46718.21 | 46718.21 | 72285.79 | 62922.2 | 9363.59 | 36987.95 | 35297.84 | 25934.25 |  | 51.2% | 51.17%
23-PC-39857 | Copper Flats Highway Widening - Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez | 69000 | 40358.1 | 40358.1 | 58157.02 | 42210.52 | 15946.5 | 34016 | 24141.02 | 8194.52 |  | 58.5% | 58.49%
23-PC-40028 | Phase II: Sumac Ridge Mixed-Use Development Section 106 Consultation | In Progress | Fixed fee | Red Rock | Bruce Suarez | 100900 | 67905.7 | 67905.7 | 70256.67 | 70256.67 | 0 | 47284.49 | 22972.18 | 22972.18 |  | 67.3% | 67.3%
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | In Progress | Time and material | Red Rock | Javier Newman | 119500 | 103480.5 | 103480.5 | 80196.45 | 80196.45 | 0 | 70430.41 | 9766.04 | 9766.04 |  | 86.6% | 87.82%
23-PC-40150 | Juniper Wash Curation | In Progress | Time and material | Sierra North | Benjamin Mathis | 114700 | 90325.75 | 90325.75 | 73316.24 | 73316.24 | 0 | 47860.76 | 25455.48 | 25455.48 |  | 78.7% | 65.28%
23-PC-40387 | Copper Flats Trail Paleontological Monitoring | Lab/Curation | Fixed fee | Sierra North | Louis Huff | 145000 | 82244 | 82244 | 97266 | 97266 | 0 | 55173.29 | 42092.71 | 42092.71 |  | 56.7% | 56.72%
23-PC-40402 | Pebble Beach Road Architectural History Survey | In Progress | Fixed fee | Sierra North | Louis Huff | 411600 | 333190.2 | 333190.2 | 302937.6 | 302937.6 | 0 | 245232.54 | 57705.06 | 57705.06 |  | 80.9% | 80.95%
23-PC-40406 | Maple Fork Airport Apron Environmental Review Support | In Progress | Time and material | Sierra | Louis Huff | 60100 | 40868 | 40868 | 40631.14 | 34425.27 | 6205.87 | 33352.18 | 7278.96 | 1073.09 |  | 68% | 82.09%
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | In Progress | Fixed fee | Sierra South | Benjamin Mathis | 53900 | 38516.94 | 38516.94 | 40910.1 | 40910.1 | 0 | 29233.55 | 11676.55 | 11676.55 |  | 71.5% | 71.46%
23-PC-40493 | Phase III: Quail Run Rail Siding Phase I Survey | In Progress | Fixed fee | Sierra | Benjamin Mathis | 84700 | 53513.46 | 53513.46 | 57130.15 | 57130.15 | 0 | 36092.25 | 21037.9 | 21037.9 |  | 63.2% | 63.18%
23-PC-40519 | Windmill Flat Mixed-Use Development - Class III Survey | In Progress | Fixed fee | Sierra South | Donna Herring | 194700 | 140203.47 | 140203.47 | 157875.18 | 136847.52 | 21027.66 | 113693.31 | 44181.87 | 23154.21 |  | 72% | 72.01%
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Lab/Curation | Fixed fee | Sierra | Louis Huff | 76500 | 76500 | 76500 | 58746.94 | 55119.6 | 3627.34 | 63236.56 | -4489.62 | -8116.96 |  | 100% | 107.6%
23-PC-40627 | Ember Valley Solar - Phase I Survey | In Progress | Fixed fee | Sierra | Louis Huff | 71300 | 44163.22 | 44163.22 | 38273.84 | 38273.84 | 0 | 23707.44 | 14566.4 | 14566.4 |  | 61.9% | 61.94%
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | In Progress | Time and material | Coastal Bend | Steve Rubio | 56300 | 38284 | 38284 | 42714.81 | 42714.81 | 0 | 47948.89 | -5234.08 | -5234.08 |  | 68% | 112.2%
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 33100 | 24874.65 | 24874.65 | 29128 | 29128 | 0 | 21890.46 | 7237.54 | 7237.54 |  | 75.1% | 75.15%
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 349600 | 349600 | 349600 | 221087.04 | 221087.04 | 0 | 229204.35 | -8117.31 | -8117.31 |  | 100% | 103.7%
23-PC-41314 | Raven Rock Transmission Line - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 38800 | 28161.04 | 28161.04 | 29503.45 | 22168.08 | 7335.37 | 21412.36 | 8091.09 | 755.72 |  | 72.6% | 72.58%
23-PC-41378 | Thistle Down Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 170800 | 95511.36 | 95511.36 | 91151.1 | 67330.2 | 23820.9 | 50973.67 | 40177.43 | 16356.53 |  | 55.9% | 55.92%
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 132000 | 92584.8 | 92584.8 | 108108 | 108108 | 0 | 75830.35 | 32277.65 | 32277.65 |  | 70.1% | 70.14%
23-PC-41429 | Meadowlark Housing Development - Phase II Testing | In Progress | Time and material | Coastal Bend | Duane Ballard | 1924200 | 1308456 | 1308456 | 1334625.12 | 1334625.12 | 0 | 884955.35 | 449669.77 | 449669.77 |  | 68% | 66.31%
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Lab/Curation | Fixed fee | Coastal Bend | Alexis Nixon | 755000 | 705170 | 705170 | 444695 | 444695 | 0 | 415325.46 | 29369.54 | 29369.54 |  | 93.4% | 93.4%
23-PC-41613 | Tamarack School Campus Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 151900 | 128659.3 | 128659.3 | 105099.61 | 105099.61 | 0 | 89014.21 | 16085.4 | 16085.4 |  | 84.7% | 84.7%
23-PC-41802 | Plover Cove Paleontological Monitoring | In Progress | Fixed fee | Built Environment | Melody Holloway | 102400 | 67051.52 | 67051.52 | 66672.64 | 66672.64 | 0 | 43658.58 | 23014.06 | 23014.06 |  | 65.5% | 65.48%
23-PC-41827 | Task Order 9: Dove Canyon Bridge Replacement Section 106 Consultation | In Progress | Fixed fee | Built Environment | Rickey Salas | 646100 | 375771.76 | 375771.76 | 414881.21 | 355093.99 | 59787.22 | 241290.96 | 173590.25 | 113803.03 |  | 58.2% | 58.16%
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | In Progress | Time and material | Built Environment | Jesse Maynard | 18800 | 12784 | 12784 | 12705.04 | 12705.04 | 0 | 12736.47 | -31.43 | -31.43 |  | 68% | 100.2%
23-PC-41934 | Sea Oat Bridge Replacement - GIS Mapping | Final Reporting/Review | Fixed fee | Built Environment | Rickey Salas | 364700 | 208900.16 | 208900.16 | 228812.78 | 228812.78 | 0 | 131064.99 | 97747.79 | 97747.79 |  | 57.3% | 57.28%
23-PC-42154 | Task Order 25: Goldfinch School Campus Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Rickey Salas | 29200 | 19856 | 19856 | 20127.56 | 20127.56 | 0 | 12454.55 | 7673.01 | 7673.01 |  | 68% | 61.88%
23-PC-42237 | Foxglove Historic Resources Evaluation | In Progress | Time and material | Paleontology | Charlene Sparks | 82300 | 55964 | 55964 | 55519.51 | 46719.77 | 8799.74 | 30299.65 | 25219.86 | 16420.12 |  | 68% | 54.57%
23-PC-42377 | Sumac Ridge Curation | In Progress | Fixed fee | Paleontology | Travis Delgado | 68300 | 39088.09 | 39088.09 | 47215.79 | 47215.79 | 0 | 27022.26 | 20193.53 | 20193.53 |  | 57.2% | 57.23%
23-PC-42451 | Phase I: Oak Terrace Cell Tower Data Recovery | In Progress | Time and material | Paleontology | Travis Delgado | 101800 | 69224 | 69224 | 72208.06 | 64989 | 7219.06 | 49547.32 | 22660.74 | 15441.68 |  | 68% | 68.62%
23-PC-42771 | Redbud Housing Development GIS Mapping | In Progress | Fixed fee | Maritime | Kyle Maynard | 25200 | 19124.28 | 19124.28 | 18799.2 | 18799.2 | 0 | 14265.92 | 4533.28 | 4533.28 |  | 75.9% | 75.89%
23-PC-42907 | Heron Marsh Historic Resources Evaluation | In Progress | Fixed fee | Maritime | Rita Ayala | 1637200 | 1057303.76 | 1057303.76 | 977458.87 | 712768.92 | 264689.95 | 631212.64 | 346246.23 | 81556.28 |  | 64.6% | 64.58%
23-PC-42981 | Hawk Point Architectural History Survey | In Progress | Fixed fee | Maritime | Kyle Maynard | 175800 | 133203.66 | 133203.66 | 129494.28 | 129494.28 | 0 | 98123.54 | 31370.74 | 31370.74 |  | 75.8% | 75.77%
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | In Progress | Time and material | Maritime | Rita Ayala | 139700 | 94996 | 94996 | 93543.12 | 93543.12 | 0 | 67047.93 | 26495.19 | 26495.19 |  | 68% | 71.68%
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | In Progress | Fixed fee | Geospatial | Priscilla Pennington | 73300 | 66563.73 | 66563.73 | 53362.4 | 53362.4 | 0 | 48458.95 | 4903.45 | 4903.45 |  | 90.8% | 90.81%
23-PC-43209 | Sea Oat Harbor Dredging Curation | In Progress | Fixed fee | Meridian | Seth Zavala | 247500 | 137090.25 | 137090.25 | 178398 | 178398 | 0 | 98806.54 | 79591.46 | 79591.46 |  | 55.4% | 55.39%
23-PC-43238 | Thistle Down Fiber Route - Data Recovery | In Progress | Fixed fee | Meridian | Clinton Solis | 454300 | 283028.9 | 283028.9 | 287491.13 | 227977.2 | 59513.93 | 179098.38 | 108392.75 | 48878.82 |  | 62.3% | 62.3%
23-PC-43408 | Wildrye Solar - Built Environment Survey | In Progress | Time and material | Meridian | Mathew Shea | 176300 | 119884 | 119884 | 121964.34 | 121964.34 | 0 | 65842.99 | 56121.35 | 56121.35 |  | 68% | 53.99%
23-PC-43612 | Maple Fork Wind Farm Class III Survey | In Progress | Time and material | Meridian | Seth Zavala | 201800 | 137224 | 137224 | 135120.77 | 112489.92 | 22630.85 | 73233.08 | 61887.69 | 39256.84 |  | 68% | 54.2%
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran | 112600 | 91374.9 | 91374.9 | 77637.7 | 77637.7 | 0 | 63002.79 | 14634.91 | 14634.91 |  | 81.1% | 81.15%
23-PC-43829 | Task Order 34: Ember Valley Wastewater Plant Architectural History Survey | In Progress | Fixed fee | Meridian Southwest | Harold Chaney | 166500 | 100016.55 | 100016.55 | 125557.65 | 125557.65 | 0 | 75422.97 | 50134.68 | 50134.68 |  | 60.1% | 60.07%
23-PC-44023 | Phase I: Sandpiper Pipeline Archaeological Testing | In Progress | Time and material | Global LLC International | Randy Cantu | 299200 | 203456 | 203456 | 196796.95 | 179738.24 | 17058.71 | 154364.16 | 42432.79 | 25374.08 |  | 68% | 78.44%
23-PC-44147 | Phase II: Wren Hollow Harbor Dredging Historic Resources Evaluation | In Progress | Fixed fee | Global LLC International | Randy Cantu | 138100 | 138100 | 138100 | 115907.33 | 115907.33 | 0 | 138824.03 | -22916.7 | -22916.7 |  | 100% | 119.8%
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 93300 | 93300 | 90265.16 | 59544.06 | 59544.06 | 0 | 84322.02 | -24777.96 | -24777.96 |  | 100% | 141.6%
24-PC-30448 | Maple Fork Substation - Data Recovery | In Progress | Fixed fee | Big Sky | Bob Frye | 142600 | 97709.52 | 97709.52 | 105894.76 | 105894.76 | 0 | 72554.14 | 33340.62 | 33340.62 |  | 68.5% | 68.52%
24-PC-30509 | On-Call: Yarrow Point Mine Expansion Cultural Resources Monitoring | Lab/Curation | Fixed fee | Big Sky | Javier Estrada | 682700 | 417402.78 | 417402.78 | 517281.79 | 517281.79 | 0 | 316284.4 | 200997.39 | 200997.39 |  | 61.1% | 61.14%
24-PC-30620 | Task Order 31: Sumac Ridge Trail GIS Mapping | Lab/Curation | Fixed fee | Bluegrass | Kiara Gillespie | 104400 | 88729.56 | 88729.56 | 78268.68 | 78268.68 | 0 | 66519.65 | 11749.03 | 11749.03 |  | 85% | 84.99%
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 60600 | 60600 | 60600 | 45577.26 | 45577.26 | 0 | 47566.17 | -1988.91 | -1988.91 |  | 100% | 104.4%
24-PC-30751 | Windmill Flat Section 106 Consultation | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 90800 | 63314.84 | 63314.84 | 72034.09 | 57699.75 | 14334.34 | 50229.44 | 21804.65 | 7470.31 |  | 69.7% | 69.73%
24-PC-30850 | Tamarack Transmission Line - Data Recovery | Final Reporting/Review | Time and material | Bluegrass | Alice Galloway | 991800 | 674424 | 674424 | 689995.26 | 689995.26 | 0 | 423701.35 | 266293.91 | 266293.91 |  | 68% | 61.41%
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Cost Tracking on Closed Project | Time and material | Cascade | Preston Duarte | 94000 | 63920 | 63920 | 65640.2 | 65640.2 | 0 | 73270.02 | -7629.82 | -7629.82 |  | 68% | 111.6%
24-PC-31358 | Dove Canyon Archaeological Testing | Final Reporting/Review | Fixed fee | Cascade | Donald Lutz | 595100 | 572605.22 | 572605.22 | 484590.9 | 358002.83 | 126588.07 | 466249.95 | 18340.95 | -108247.12 |  | 96.2% | 96.22%
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Jean Cooke | 18200 | 13335.14 | 13335.14 | 12417.86 | 12417.86 | 0 | 9098.08 | 3319.78 | 3319.78 |  | 73.3% | 73.27%
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | In Progress | Time and material | Cascade | Gene Nixon | 18300 | 12444 | 12444 | 11931.6 | 11931.6 | 0 | 9112.04 | 2819.56 | 2819.56 |  | 68% | 76.37%
24-PC-31503 | North Fork Wind Farm Curation | Lab/Curation | Time and material | Cascade | Preston Duarte | 129900 | 88332 | 88332 | 87825.39 | 87825.39 | 0 | 98773.26 | -10947.87 | -10947.87 |  | 68% | 112.5%
24-PC-31663 | Fern Valley Section 106 Consultation | In Progress | Fixed fee | Cascade | Jean Cooke | 52600 | 43847.36 | 43847.36 | 37714.2 | 37714.2 | 0 | 31436.99 | 6277.21 | 6277.21 |  | 83.4% | 83.36%
24-PC-31750 | Kestrel Butte Park Improvements - Phase I Survey | Final Reporting/Review | Fixed fee | Cascade | Cassidy Gay | 257200 | 198969.92 | 194203.32 | 200024.44 | 200024.44 | 0 | 154744.71 | 45279.73 | 45279.73 |  | 77.4% | 77.36%
24-PC-31819 | Plover Cove Reservoir - Curation | Final Reporting/Review | Time and material | Cascade | Gene Nixon | 38600 | 26248 | 26248 | 26703.48 | 26703.48 | 0 | 15843.15 | 10860.33 | 10860.33 |  | 68% | 59.33%
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | In Progress | Time and material | Cascade | Gene Nixon | 15200 | 10646.15 | 10646.15 | 10676.48 | 10676.48 | 0 | 7480.05 | 3196.43 | 3196.43 |  | 70% | 70.06%
24-PC-31924 | Cedar Hollow Wind Farm - Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Gene Nixon | 186800 | 123811.04 | 123811.04 | 147262.72 | 122646.08 | 24616.64 | 97605.67 | 49657.05 | 25040.41 |  | 66.3% | 66.28%
24-PC-32088 | Elk Meadow Phase I Survey | In Progress | Time and material | Chesapeake | Jason Oconnor | 305100 | 207468 | 207468 | 228062.25 | 228062.25 | 0 | 135703.34 | 92358.91 | 92358.91 |  | 68% | 59.5%
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 51800 | 51800 | 50026.67 | 36731.38 | 36731.38 | 0 | 54746.36 | -18014.98 | -18014.98 |  | 100% | 149%
24-PC-32209 | Saltgrass Wastewater Plant - Phase I Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox | 13000 | 12785.5 | 12785.5 | 9029.25 | 7229.76 | 1799.49 | 8880.11 | 149.14 | -1650.35 |  | 98.4% | 98.35%
24-PC-32210 | Badger Hollow Transmission Line - Class III Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 114400 | 79496.56 | 79496.56 | 91211.12 | 91211.12 | 0 | 63386.97 | 27824.15 | 27824.15 |  | 69.5% | 69.49%
24-PC-32479 | Riverbend Transmission Line Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 94000 | 62594.6 | 62594.6 | 66890.4 | 66890.4 | 0 | 44542.3 | 22348.1 | 22348.1 |  | 66.6% | 66.59%
24-PC-32640 | Badger Hollow Harbor Dredging Architectural History Survey | In Progress | Time and material | Chesapeake | Alexandria Wilkinson | 39000 | 26520 | 26520 | 28130.47 | 21303 | 6827.47 | 22328.99 | 5801.48 | -1025.99 |  | 68% | 79.38%
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Chesapeake | Alexandria Wilkinson | 84000 | 84000 | 83888.35 | 70198.8 | 70198.8 | 0 | 76493.04 | -6294.24 | -6294.24 |  | 100% | 109%
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox | 51700 | 44730.84 | 44730.84 | 45206.48 | 45206.48 | 0 | 39111.36 | 6095.12 | 6095.12 |  | 86.5% | 86.52%
24-PC-32954 | Redbud Substation - Historic Resources Evaluation | In Progress | Time and material | Front Range | Kimberly Daugherty | 331200 | 225216 | 225216 | 217532.16 | 217532.16 | 0 | 114290.35 | 103241.81 | 103241.81 |  | 68% | 52.54%
24-PC-33384 | Phase III: Pine Hollow Rail Siding Maritime Remote Sensing Survey | In Progress | Time and material | Front Range | Dean Velazquez | 288100 | 195908 | 195908 | 207230.33 | 207230.33 | 0 | 139777.64 | 67452.69 | 67452.69 |  | 68% | 67.45%
24-PC-33394 | Foxglove Park Improvements Cultural Resources Assessment | In Progress | Time and material | Front Range | Joanna Herrera | 298200 | 202776 | 202776 | 197617.14 | 197617.14 | 0 | 102377.3 | 95239.84 | 95239.84 |  | 68% | 51.81%
24-PC-33448 | Ember Valley Solar Architectural History Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 681000 | 537036.6 | 533404.54 | 419972.7 | 419972.7 | 0 | 331170.91 | 88801.79 | 88801.79 |  | 78.9% | 78.86%
24-PC-33531 | North Fork Park Improvements - Curation | Lab/Curation | Fixed fee | Front Range | Dean Velazquez | 31500 | 23965.2 | 23965.2 | 23760.45 | 23760.45 | 0 | 18077.06 | 5683.39 | 5683.39 |  | 76.1% | 76.08%
24-PC-33575 | On-Call: North Fork Trail Architectural History Survey | Final Reporting/Review | Time and material | Front Range | Devon Pitts | 589600 | 334942.45 | 320472.76 | 433356 | 433356 | 0 | 279646.21 | 153709.79 | 153709.79 |  | 56.8% | 64.53%
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Karl Valenzuela | 64500 | 51748.35 | 49625.94 | 49568.25 | 49568.25 | 0 | 39767.41 | 9800.84 | 9800.84 |  | 80.2% | 80.23%
24-PC-33927 | Aspen Ridge Solar Class III Survey | Final Reporting/Review | Fixed fee | Great Lakes | Nathan Lambert | 104000 | 57012.8 | 57012.8 | 77001.6 | 77001.6 | 0 | 42209.16 | 34792.44 | 34792.44 |  | 54.8% | 54.82%
24-PC-33981 | Yarrow Point Airport Apron - Phase II Testing | Lab/Curation | Time and material | Great Lakes | Nathan Lambert | 47500 | 36664.5 | 36664.5 | 29944 | 29944 | 0 | 26339.43 | 3604.57 | 3604.57 |  | 77.2% | 87.96%
24-PC-33985 | Thistle Down Substation Curation | In Progress | Time and material | Great Lakes | Angelica Cervantes | 78300 | 53244 | 53244 | 57863.7 | 57863.7 | 0 | 50630.38 | 7233.32 | 7233.32 |  | 68% | 87.5%
24-PC-34263 | Cedar Hollow Airport Apron Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Robin Mercado | 199300 | 127292.91 | 127292.91 | 147800.88 | 147800.88 | 0 | 94406.95 | 53393.93 | 53393.93 |  | 63.9% | 63.87%
24-PC-34320 | Sage Flat Canal Lining Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 388400 | 279492.64 | 279492.64 | 253927.23 | 209652.52 | 44274.71 | 182728.59 | 71198.64 | 26923.93 |  | 72% | 71.96%
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Karl Valenzuela | 38700 | 26316 | 26316 | 26644.95 | 26644.95 | 0 | 19241.81 | 7403.14 | 7403.14 |  | 68% | 72.22%
24-PC-34499 | Dove Canyon Trail - GIS Mapping | In Progress | Time and material | Great Lakes | Brendan Padilla | 104200 | 70856 | 70856 | 76427.58 | 70842.85 | 5584.73 | 75193.06 | 1234.52 | -4350.21 |  | 68% | 98.38%
24-PC-34593 | Riverbend Park Improvements - Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 43500 | 25308.3 | 25308.3 | 33447.15 | 33447.15 | 0 | 19459.27 | 13987.88 | 13987.88 |  | 58.2% | 58.18%
24-PC-34654 | Timber Gap Phase II Testing | Final Reporting/Review | Time and material | Great Lakes | Brendan Padilla | 115400 | 82357.15 | 82297.95 | 87787.28 | 70825.08 | 16962.2 | 46707.98 | 41079.3 | 24117.1 |  | 71.4% | 53.21%
24-PC-34663 | Redbud Airport Apron - GIS Mapping | In Progress | Time and material | Great Lakes | Kathleen Galvan | 505100 | 343468 | 343468 | 342760.86 | 342760.86 | 0 | 286062.16 | 56698.7 | 56698.7 |  | 68% | 83.46%
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | In Progress | Time and material | Gulf Coast | Courtney Daugherty | 176500 | 120020 | 120020 | 121414.35 | 121414.35 | 0 | 122080.25 | -665.9 | -665.9 |  | 68% | 100.6%
24-PC-34975 | Foxglove Fiber Route GIS Mapping | In Progress | Fixed fee | Gulf Coast West | Bernard Erickson | 205900 | 175159.13 | 175159.13 | 181192 | 181192 | 0 | 154132.44 | 27059.56 | 27059.56 |  | 85.1% | 85.07%
24-PC-35267 | Falcon Mesa Trail - Phase II Testing | Final Reporting/Review | Fixed fee | Gulf Coast | Sean Jennings | 56700 | 33226.2 | 33226.2 | 42581.7 | 42581.7 | 0 | 24952.14 | 17629.56 | 17629.56 |  | 58.6% | 58.6%
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | In Progress | Time and material | High Desert | Kathy Hurley | 301200 | 204816 | 204816 | 217496.52 | 217496.52 | 0 | 196030.1 | 21466.42 | 21466.42 |  | 68% | 90.13%
24-PC-35474 | Larkspur Curation | In Progress | Fixed fee | High Desert | Eileen Poole | 369600 | 284148.48 | 284148.48 | 278295.85 | 215699.64 | 62596.21 | 213962.17 | 64333.68 | 1737.47 |  | 76.9% | 76.88%
24-PC-35559 | Phase III: Fern Valley Battery Storage Curation | Final Reporting/Review | Fixed fee | High Desert | Eileen Poole | 218200 | 185797.3 | 185797.3 | 144252.02 | 144252.02 | 0 | 122823.72 | 21428.3 | 21428.3 |  | 85.2% | 85.15%
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | In Progress | Fixed fee | High Desert | Eileen Poole | 119200 | 90150.96 | 90150.96 | 88243.76 | 88243.76 | 0 | 66735.14 | 21508.62 | 21508.62 |  | 75.6% | 75.63%
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | In Progress | Time and material | High Desert | Kathy Hurley | 69900 | 66440.45 | 63137.93 | 49013.31 | 40696.6 | 8316.71 | 46336.36 | 2676.95 | -5639.76 |  | 95.1% | 94.54%
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | In Progress | Time and material | High Desert | Kathy Hurley | 225100 | 200102.05 | 200102.05 | 153743.3 | 153743.3 | 0 | 140872.8 | 12870.5 | 12870.5 |  | 88.9% | 91.63%
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 12900 | 10859.22 | 10859.22 | 9094.5 | 9094.5 | 0 | 7655.43 | 1439.07 | 1439.07 |  | 84.2% | 84.18%
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Cost Tracking on Closed Project | Fixed fee | High Desert | Kathy Hurley | 58300 | 58300 | 58300 | 39072.66 | 39072.66 | 0 | 45518.79 | -6446.13 | -6446.13 |  | 100% | 116.5%
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | In Progress | Time and material | High Desert | Kathy Hurley | 5700 | 3876 | 3876 | 4244.79 | 4244.79 | 0 | 3255.04 | 989.75 | 989.75 |  | 68% | 76.68%
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Island | Rodney Mcguire | 56300 | 52077.5 | 52077.5 | 37721 | 37721 | 0 | 34891.33 | 2829.67 | 2829.67 |  | 92.5% | 92.5%
24-PC-36620 | Silver Lake Cultural Resources Assessment | In Progress | Time and material | Lakeshore | Terrence Gillespie | 368100 | 290535 | 290535 | 252295.74 | 252295.74 | 0 | 163066.37 | 89229.37 | 89229.37 |  | 78.9% | 64.63%
24-PC-36932 | Badger Hollow Canal Lining - Section 106 Consultation | Final Reporting/Review | Time and material | Hill Country | Marcus Shea | 12200 | 9992.5 | 9992.5 | 7733.58 | 7733.58 | 0 | 6430.16 | 1303.42 | 1303.42 |  | 81.9% | 83.15%
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | In Progress | Fixed fee | Hill Country | Glen Delacruz | 141000 | 141000 | 141000 | 113970.3 | 113970.3 | 0 | 138124.06 | -24153.76 | -24153.76 |  | 100% | 121.2%
24-PC-37107 | Hawk Point Mixed-Use Development Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 259400 | 176106.66 | 176106.66 | 186117.89 | 175095.48 | 11022.41 | 126346.85 | 59771.04 | 48748.63 |  | 67.9% | 67.89%
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | In Progress | Fixed fee | Hill Country | Gail Meza | 1259200 | 928785.92 | 928785.92 | 853989.44 | 853989.44 | 0 | 629919.62 | 224069.82 | 224069.82 |  | 73.8% | 73.76%
24-PC-37167 | Saltgrass Curation | Lab/Curation | Time and material | Hill Country | Marcus Shea | 65600 | 44608 | 44608 | 48603.04 | 48603.04 | 0 | 33605.6 | 14997.44 | 14997.44 |  | 68% | 69.14%
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | In Progress | Time and material | Hill Country | Samuel Wilkerson | 67000 | 51564 | 51564 | 40709.2 | 40709.2 | 0 | 34240.46 | 6468.74 | 6468.74 |  | 77% | 84.11%
24-PC-37266 | Granite Pass Cell Tower Phase I Survey | In Progress | Time and material | Hill Country | Marcus Shea | 41400 | 29169.9 | 29169.9 | 24587.46 | 24587.46 | 0 | 17096.42 | 7491.04 | 7491.04 |  | 70.5% | 69.53%
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 298500 | 213069.3 | 213069.3 | 243904.35 | 243904.35 | 0 | 174092.01 | 69812.34 | 69812.34 |  | 71.4% | 71.38%
24-PC-37372 | Harbor View Harbor Dredging Paleontological Monitoring | Final Reporting/Review | Fixed fee | Piedmont - Inactive | Maria Parrish | 272100 | 216918.12 | 210250.76 | 221924.76 | 221924.76 | 0 | 176913.5 | 45011.26 | 45011.26 |  | 79.7% | 79.72%
24-PC-37415 | Sage Flat Mine Expansion Maritime Remote Sensing Survey | In Progress | Fixed fee | PIEDMONT - INACTIVE | Megan Pineda | 191000 | 115994.3 | 115994.3 | 147948.6 | 147948.6 | 0 | 89853.11 | 58095.49 | 58095.49 |  | 60.7% | 60.73%
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | In Progress | Time and material | PIEDMONT - INACTIVE | Jody Chung | 309400 | 210392 | 210392 | 184093 | 184093 | 0 | 149432.06 | 34660.94 | 34660.94 |  | 68% | 81.17%
24-PC-37686 | Twin Buttes Mixed-Use Development Paleontological Monitoring | In Progress | Fixed fee | Piedmont - Inactive | Annette Vaughan | 50600 | 41385.74 | 41385.74 | 39155.85 | 28376.76 | 10779.09 | 32027.2 | 7128.65 | -3650.44 |  | 81.8% | 81.79%
24-PC-37823 | Granite Pass Pipeline Cultural Resources Monitoring | Lab/Curation | Fixed fee | Piedmont - Inactive | Jody Chung | 28900 | 21070.99 | 21070.99 | 21651.88 | 21651.88 | 0 | 15787.12 | 5864.76 | 5864.76 |  | 72.9% | 72.91%
24-PC-37942 | Task Order 39: Meadowlark Mine Expansion Curation | Final Reporting/Review | Time and material | Piedmont - Inactive | Annette Vaughan | 241400 | 199259.4 | 199259.4 | 173542.46 | 173542.46 | 0 | 141494.45 | 32048.01 | 32048.01 |  | 82.5% | 81.53%
24-PC-38054 | On-Call: Willow Springs Highway Widening GIS Mapping | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd | 60700 | 41373.12 | 41373.12 | 51516.09 | 51516.09 | 0 | 35113.87 | 16402.22 | 16402.22 |  | 68.2% | 68.16%
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Prairie | Sherry Lloyd | 132200 | 121663.66 | 121663.66 | 95580.6 | 95580.6 | 0 | 87961.2 | 7619.4 | 7619.4 |  | 92% | 92.03%
24-PC-38374 | On-Call: Riverbend Highway Widening Archaeological Testing | In Progress | Time and material | Prairie | Sherry Lloyd | 481100 | 327148 | 327148 | 330082.71 | 330082.71 | 0 | 229684.73 | 100397.98 | 100397.98 |  | 68% | 69.58%
24-PC-38469 | Falcon Mesa Harbor Dredging - Built Environment Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 656700 | 492196.65 | 480383.3 | 435290.48 | 364918.68 | 70371.8 | 326242.9 | 109047.58 | 38675.78 |  | 75% | 74.95%
24-PC-38486 | Kestrel Butte Phase I Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 153600 | 153600 | 153600 | 105043.81 | 77500.98 | 27542.83 | 119866.24 | -14822.43 | -42365.26 |  | 100% | 114.1%
24-PC-38687 | Lantern Bay GIS Mapping | In Progress | Time and material | Red Rock | Javier Newman | 68600 | 46648 | 46648 | 49542.92 | 49542.92 | 0 | 28559.72 | 20983.2 | 20983.2 |  | 68% | 57.65%
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 168200 | 168200 | 168200 | 130489.56 | 130489.56 | 0 | 132230.67 | -1741.11 | -1741.11 |  | 100% | 101.3%
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 100200 | 100200 | 93737.19 | 72685.08 | 72685.08 | 0 | 88959.55 | -16274.47 | -16274.47 |  | 100% | 122.4%
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | In Progress | Time and material | Red Rock | Lydia Cisneros | 126600 | 86088 | 86088 | 82581.18 | 82581.18 | 0 | 59856.61 | 22724.57 | 22724.57 |  | 68% | 72.48%
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Javier Newman | 597800 | 448290.22 | 448290.22 | 435557.08 | 435557.08 | 0 | 326614.02 | 108943.06 | 108943.06 |  | 75% | 74.99%
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Red Rock | Shelia Horne | 11000 | 11000 | 11000 | 7227 | 7227 | 0 | 7427.79 | -200.79 | -200.79 |  | 100% | 102.8%
24-PC-39479 | Granite Pass Solar - Cultural Resources Assessment | Final Reporting/Review | Time and material | Red Rock | Javier Newman | 233000 | 165185 | 165185 | 164777.6 | 164777.6 | 0 | 116733.87 | 48043.73 | 48043.73 |  | 70.9% | 70.84%
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | In Progress | Time and material | Red Rock | Tina Aguirre | 33000 | 28973 | 28973 | 23227.58 | 20462.4 | 2765.18 | 29485.89 | -6258.31 | -9023.49 |  | 87.8% | 126.9%
24-PC-39533 | Elk Meadow Architectural History Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 67000 | 63536.1 | 63536.1 | 52641.9 | 52641.9 | 0 | 49919.2 | 2722.7 | 2722.7 |  | 94.8% | 94.83%
24-PC-39694 | Task Order 35: Sandpiper Trail Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 136500 | 92820 | 92820 | 93075.52 | 70843.68 | 22231.84 | 77289.3 | 15786.22 | -6445.62 |  | 68% | 83.04%
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | In Progress | Fixed fee | Red Rock | Bruce Suarez | 17800 | 17800 | 17800 | 14308.95 | 10538.95 | 3770 | 14659.16 | -350.21 | -4120.21 |  | 100% | 102.5%
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | In Progress | Time and material | Red Rock | Lydia Cisneros | 414900 | 304714.4 | 296783.03 | 270722.25 | 270722.25 | 0 | 194484.62 | 76237.63 | 76237.63 |  | 73.4% | 71.84%
24-PC-39940 | Riverbend Levee Repair - Curation | In Progress | Fixed fee | Red Rock | Marisa Odom | 20400 | 13135.56 | 13135.56 | 16397.52 | 16397.52 | 0 | 10559.17 | 5838.35 | 5838.35 |  | 64.4% | 64.39%
24-PC-40067 | Saltgrass Fiber Route Class III Survey | In Progress | Time and material | Red Rock | Marisa Odom | 218100 | 148308 | 148308 | 163684.05 | 163684.05 | 0 | 137568.33 | 26115.72 | 26115.72 |  | 68% | 84.05%
24-PC-40102 | Redbud Class III Survey | Final Reporting/Review | Fixed fee | Sierra | Benjamin Mathis | 453900 | 453900 | 453900 | 322187.01 | 278794.4 | 43392.61 | 359994.61 | -37807.6 | -81200.21 |  | 100% | 111.7%
24-PC-40218 | North Fork Bridge Replacement - Built Environment Survey | In Progress | Time and material | Sierra North | Angelica Poole | 141000 | 95880 | 95880 | 95626.2 | 95626.2 | 0 | 51169.2 | 44457 | 44457 |  | 68% | 53.51%
24-PC-40317 | Sumac Ridge Harbor Dredging Curation | In Progress | Time and material | Sierra | Angelica Poole | 225800 | 153544 | 153544 | 153318.2 | 153318.2 | 0 | 86572.73 | 66745.47 | 66745.47 |  | 68% | 56.47%
24-PC-40479 | Quail Run Rail Siding - Built Environment Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 139600 | 89036.88 | 89036.88 | 110619.04 | 110619.04 | 0 | 70556.04 | 40063 | 40063 |  | 63.8% | 63.78%
24-PC-40561 | Task Order 39: Aspen Ridge Housing Development GIS Mapping | In Progress | Fixed fee | Sierra | Benjamin Mathis | 2335800 | 1620344.46 | 1605200.88 | 1746045.15 | 1301909.91 | 444135.24 | 1211215.33 | 534829.82 | 90694.58 |  | 69.4% | 69.37%
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Angelica Poole | 460500 | 326540.55 | 326540.55 | 381017.7 | 381017.7 | 0 | 270177.47 | 110840.23 | 110840.23 |  | 70.9% | 70.91%
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Sierra North | Louis Huff | 50300 | 46200.55 | 46200.55 | 35350.84 | 35350.84 | 0 | 32471.24 | 2879.6 | 2879.6 |  | 91.8% | 91.85%
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Sierra North | Donna Herring | 22100 | 22100 | 22100 | 17918.68 | 17918.68 | 0 | 26916.31 | -8997.63 | -8997.63 |  | 100% | 150.2%
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Alexis Nixon | 48400 | 48400 | 47376.63 | 37137.32 | 37137.32 | 0 | 43947.42 | -6810.1 | -6810.1 |  | 100% | 118.3%
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 31800 | 31800 | 31800 | 20975.28 | 20975.28 | 0 | 22323.11 | -1347.83 | -1347.83 |  | 100% | 106.4%
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Lab/Curation | Fixed fee | Coastal Bend | Diane Daniels | 579300 | 579300 | 579300 | 392475.75 | 392475.75 | 0 | 413750.74 | -21274.99 | -21274.99 |  | 100% | 105.4%
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 8800 | 8800 | 8800 | 6914.16 | 6914.16 | 0 | 7269.9 | -355.74 | -355.74 |  | 100% | 105.2%
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | In Progress | Time and material | Coastal Bend | Alexis Nixon | 60600 | 41208 | 41208 | 39983.88 | 39983.88 | 0 | 31771.04 | 8212.84 | 8212.84 |  | 68% | 79.46%
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 18000 | 18000 | 15244.1 | 12312 | 12312 | 0 | 19340.19 | -7028.19 | -7028.19 |  | 100% | 157.1%
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 194900 | 187591.25 | 187591.25 | 131089.74 | 131089.74 | 0 | 126178.41 | 4911.33 | 4911.33 |  | 96.3% | 96.25%
24-PC-41886 | On-Call: Pebble Beach Road Canal Lining Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Melody Holloway | 67500 | 43694 | 43694 | 46824.75 | 46824.75 | 0 | 29307.2 | 17517.55 | 17517.55 |  | 64.7% | 62.59%
24-PC-41969 | Windmill Flat Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Built Environment | Melody Holloway | 216500 | 143864.25 | 143864.25 | 161335.8 | 161335.8 | 0 | 107206.67 | 54129.13 | 54129.13 |  | 66.4% | 66.45%
24-PC-42121 | Oak Terrace Substation Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Kathleen Cabrera | 267300 | 240703.65 | 240703.65 | 208453.84 | 189453.96 | 18999.88 | 187719.43 | 20734.41 | 1734.53 |  | 90% | 90.05%
24-PC-42184 | Phase II: Granite Pass Substation Environmental Review Support | In Progress | Fixed fee | Built Environment | Rickey Salas | 25600 | 11246.08 | 11246.08 | 17986.56 | 17986.56 | 0 | 7901.19 | 10085.37 | 10085.37 |  | 43.9% | 43.93%
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 263500 | 179180 | 179180 | 173567.45 | 173567.45 | 0 | 177335 | -3767.55 | -3767.55 |  | 68% | 102.2%
24-PC-42495 | Kestrel Butte Battery Storage - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Paleontology | Charlene Sparks | 45900 | 28875.69 | 28875.69 | 35246.61 | 35246.61 | 0 | 22172.99 | 13073.62 | 13073.62 |  | 62.9% | 62.91%
24-PC-42550 | Yarrow Point Paleontological Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado | 301300 | 188945.23 | 187770.85 | 216936 | 216936 | 0 | 136041.09 | 80894.91 | 80894.91 |  | 62.7% | 62.71%
24-PC-42674 | Foxglove Canal Lining Architectural History Survey | Lab/Curation | Time and material | Maritime | Rita Ayala | 156100 | 106148 | 106148 | 111589.34 | 92586.34 | 19003 | 57675.71 | 53913.63 | 34910.63 |  | 68% | 51.69%
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 639100 | 451268.51 | 451268.51 | 498050.63 | 498050.63 | 0 | 351673.07 | 146377.56 | 146377.56 |  | 70.6% | 70.61%
24-PC-43116 | On-Call: Larkspur Airport Apron Phase II Testing | Final Reporting/Review | Fixed fee | Geospatial | Sylvia Callahan | 424400 | 287318.8 | 287318.8 | 314395.52 | 314395.52 | 0 | 212843.45 | 101552.07 | 101552.07 |  | 67.7% | 67.7%
24-PC-43150 | Rushgrass Draw Architectural History Survey | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 301500 | 244848.15 | 244848.15 | 222689.15 | 196120.08 | 26569.07 | 180855.17 | 41833.98 | 15264.91 |  | 81.2% | 81.21%
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Geospatial | Sylvia Callahan | 19700 | 13396 | 13396 | 14170.21 | 14170.21 | 0 | 18919.28 | -4749.07 | -4749.07 |  | 68% | 133.5%
24-PC-43670 | Granite Pass Archaeological Testing | Final Reporting/Review | Fixed fee | Meridian Southwest | Lynn Tran | 220400 | 155514.24 | 155514.24 | 168565.52 | 153066.64 | 15498.88 | 118945.86 | 49619.66 | 34120.78 |  | 70.6% | 70.56%
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | In Progress | Time and material | Meridian Southwest | Lynn Tran | 1003600 | 682448 | 682448 | 771166.24 | 771166.24 | 0 | 614867.84 | 156298.4 | 156298.4 |  | 68% | 79.73%
24-PC-43719 | On-Call: Juniper Wash Wastewater Plant Historic Resources Evaluation | Final Reporting/Review | Time and material | Meridian Southwest | Harold Chaney | 382100 | 259828 | 259828 | 239599.17 | 197376 | 42223.17 | 170624.75 | 68974.42 | 26751.25 |  | 68% | 71.21%
24-PC-43786 | Task Order 3: Wren Hollow Canal Lining Architectural History Survey | Lab/Curation | Fixed fee | Meridian Southwest | Alan Gay | 220400 | 144053.44 | 144053.44 | 123791.36 | 113687.28 | 10104.08 | 80906.2 | 42885.16 | 32781.08 |  | 65.4% | 65.36%
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 213100 | 152792.7 | 152792.7 | 187528 | 187528 | 0 | 134454.77 | 53073.23 | 53073.23 |  | 71.7% | 71.7%
24-PC-44022 | Sea Oat Historic Resources Evaluation | In Progress | Time and material | NH Gulf (USD) | Vanessa Duarte | 1072900 | 729572 | 729572 | 625022.97 | 541701.35 | 83321.62 | 345106.15 | 279916.82 | 196595.2 |  | 68% | 55.21%
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | In Progress | Time and material | NH Gulf (USD) | Susan Wilkins | 264500 | 249828.25 | 242097.43 | 194222.35 | 194222.35 | 0 | 223711.55 | -29489.2 | -29489.2 |  | 94.5% | 115.2%
24-PC-44158 | Saltgrass Environmental Review Support | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 23200 | 23200 | 23148.01 | 15583.44 | 15583.44 | 0 | 15910.06 | -326.62 | -326.62 |  | 100% | 102.1%
25-PC-30034 | On-Call: Wren Hollow Wastewater Plant GIS Mapping | Final Reporting/Review | Fixed fee | Big Sky | Bob Frye | 101900 | 67824.64 | 67824.64 | 74162.82 | 74162.82 | 0 | 49365.02 | 24797.8 | 24797.8 |  | 66.6% | 66.56%
25-PC-30077 | Phase II: Tamarack Housing Development Phase I Survey | In Progress | Time and material | Big Sky | Carl Barajas | 103400 | 103400 | 103400 | 71293.1 | 51740.95 | 19552.15 | 65644.01 | 5649.09 | -13903.06 |  | 100% | 92.08%
25-PC-30140 | Windmill Flat Cell Tower - GIS Mapping | In Progress | Time and material | Big Sky | Carl Barajas | 257200 | 121129.05 | 121129.05 | 165353.88 | 165353.88 | 0 | 95517.33 | 69836.55 | 69836.55 |  | 47.1% | 57.77%
25-PC-30254 | Task Order 16: Coyote Springs Reservoir Class III Survey | Final Reporting/Review | Time and material | Big Sky | Brendan Melton | 77100 | 47116.6 | 47116.6 | 49529.04 | 49529.04 | 0 | 32838.69 | 16690.35 | 16690.35 |  | 61.1% | 66.3%
25-PC-30345 | Wildrye Phase II Testing | In Progress | Fixed fee | Big Sky | Brendan Melton | 160400 | 130998.68 | 130998.68 | 92631 | 92631 | 0 | 75656.14 | 16974.86 | 16974.86 |  | 81.7% | 81.67%
25-PC-30348 | Phase II: Pine Hollow Wind Farm Environmental Review Support | In Progress | Fixed fee | Big Sky | Carl Barajas | 20800 | 13345.28 | 13345.28 | 15194.4 | 15194.4 | 0 | 9749.45 | 5444.95 | 5444.95 |  | 64.2% | 64.16%
25-PC-30418 | Dove Canyon Wind Farm Class III Survey | Final Reporting/Review | Fixed fee | Big Sky | Brendan Melton | 344800 | 249221.44 | 249221.44 | 233309.47 | 170518.18 | 62791.29 | 168637.5 | 64671.97 | 1880.68 |  | 72.3% | 72.28%
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway | 19700 | 16087.02 | 13492.07 | 13027.61 | 13027.61 | 0 | 10637.97 | 2389.64 | 2389.64 |  | 81.7% | 81.66%
25-PC-30717 | Phase II: Riverbend Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 324100 | 198738.12 | 179767.68 | 205678.64 | 166411.98 | 39266.66 | 126121.45 | 79557.19 | 40290.53 |  | 61.3% | 61.32%
25-PC-30739 | Saltgrass Solar Class III Survey | Final Reporting/Review | Fixed fee | Bluegrass | Alice Galloway | 244200 | 124346.64 | 124346.64 | 214896 | 214896 | 0 | 109432.28 | 105463.72 | 105463.72 |  | 50.9% | 50.92%
25-PC-30772 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 63300 | 63300 | 63300 | 43065.84 | 35870.85 | 7194.99 | 55788.54 | -12722.7 | -19917.69 |  | 100% | 129.5%
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 131000 | 118699.1 | 110221.74 | 85464.4 | 85464.4 | 0 | 77435.6 | 8028.8 | 8028.8 |  | 90.6% | 90.61%
25-PC-30824 | Task Order 2: Lantern Bay Fiber Route Environmental Review Support | In Progress | Fixed fee | Bluegrass | Alice Galloway | 206400 | 142477.92 | 142477.92 | 145641.07 | 109553 | 36088.07 | 100541.75 | 45099.32 | 9011.25 |  | 69% | 69.03%
25-PC-31109 | Riverbend GIS Mapping | In Progress | Time and material | Cascade | Cassidy Gay | 174700 | 160586.5 | 140791.8 | 109484.49 | 109484.49 | 0 | 106927.18 | 2557.31 | 2557.31 |  | 91.9% | 97.66%
25-PC-31114 | Granite Pass Built Environment Survey | In Progress | Time and material | Cascade | Jean Cooke | 229400 | 179308.8 | 179308.8 | 157964.84 | 157964.84 | 0 | 127618.8 | 30346.04 | 30346.04 |  | 78.2% | 80.79%
25-PC-31180 | Blue Heron Environmental Review Support | In Progress | Fixed fee | Cascade | Preston Duarte | 80000 | 59688 | 49435.43 | 60701.89 | 45712.3 | 14989.59 | 45287.24 | 15414.65 | 425.06 |  | 74.6% | 74.61%
25-PC-31242 | Sage Flat Fiber Route - Class III Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 398600 | 111647.86 | 108175.24 | 273446.93 | 244020.48 | 29426.45 | 76580.63 | 196866.3 | 167439.85 |  | 28% | 28.01%
25-PC-31263 | Dove Canyon Water Main Phase I Survey | Lab/Curation | Time and material | Cascade | Cassidy Gay | 203400 | 151454.75 | 147628.56 | 139410.36 | 139410.36 | 0 | 106760.7 | 32649.66 | 32649.66 |  | 74.5% | 76.58%
25-PC-31298 | On-Call: Lone Pine Water Main Class III Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 48100 | 41495.87 | 41495.87 | 35361.72 | 33111 | 2250.72 | 30507.93 | 4853.79 | 2603.07 |  | 86.3% | 86.27%
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 23500 | 23500 | 23419.06 | 17263.1 | 17263.1 | 0 | 21125.07 | -3861.97 | -3861.97 |  | 100% | 122.4%
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 52000 | 52000 | 49983.77 | 38781.6 | 38781.6 | 0 | 46810.89 | -8029.29 | -8029.29 |  | 100% | 120.7%
25-PC-31420 | Cedar Hollow Wind Farm Archaeological Testing | Final Reporting/Review | Fixed fee | Cascade | Jeff Spence | 102200 | 38468.08 | 31168.75 | 68753.09 | 50928.84 | 17824.25 | 25877.03 | 42876.06 | 25051.81 |  | 37.6% | 37.64%
25-PC-31555 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 69300 | 55363.77 | 49823.95 | 53097.66 | 53097.66 | 0 | 42420.69 | 10676.97 | 10676.97 |  | 79.9% | 79.89%
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 16800 | 16800 | 16756.9 | 11810.4 | 11810.4 | 0 | 15492.46 | -3682.06 | -3682.06 |  | 100% | 131.2%
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Final Reporting/Review | Time and material | Cascade | Jeff Spence | 30300 | 30300 | 30300 | 22049.31 | 22049.31 | 0 | 34568.28 | -12518.97 | -12518.97 |  | 100% | 156.8%
25-PC-31775 | Task Order 26: Pine Hollow Bridge Replacement Cultural Resources Monitoring | In Progress | Time and material | Cascade | Cassidy Gay | 163200 | 88840 | 88840 | 98279.04 | 98279.04 | 0 | 44426.27 | 53852.77 | 53852.77 |  | 54.4% | 45.2%
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | In Progress | Fixed fee | Cascade | Preston Duarte | 216800 | 185125.52 | 170335.22 | 171337.04 | 171337.04 | 0 | 146297.54 | 25039.5 | 25039.5 |  | 85.4% | 85.39%
25-PC-31821 | Millbrook Environmental Review Support | Final Reporting/Review | Fixed fee | Cascade | Preston Duarte | 211400 | 117813.22 | 102785.2 | 183932.36 | 145726.92 | 38205.44 | 102510.95 | 81421.41 | 43215.97 |  | 55.7% | 55.73%
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 40900 | 13987.8 | 13987.8 | 28728.16 | 28728.16 | 0 | 33002.57 | -4274.41 | -4274.41 |  | 34.2% | 114.9%
25-PC-31905 | Raven Rock Mixed-Use Development Phase II Testing | Final Reporting/Review | Time and material | Cascade | Cassidy Gay | 331600 | 153513.85 | 136957.62 | 228107.64 | 228107.64 | 0 | 102066.07 | 126041.57 | 126041.57 |  | 46.3% | 44.74%
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Jason Oconnor | 35200 | 35200 | 35200 | 24481.6 | 24481.6 | 0 | 39543.74 | -15062.14 | -15062.14 |  | 100% | 161.5%
25-PC-32021 | Oak Terrace Cultural Resources Monitoring | In Progress | Time and material | Chesapeake | Alexandria Wilkinson | 148200 | 88329.8 | 86389.8 | 111253.74 | 111253.74 | 0 | 52005.21 | 59248.53 | 59248.53 |  | 59.6% | 46.74%
25-PC-32024 | Pine Hollow Historic Resources Evaluation | In Progress | Time and material | Chesapeake | Ian Maddox | 79500 | 42562.75 | 36599.08 | 57637.5 | 57637.5 | 0 | 31705.22 | 25932.28 | 25932.28 |  | 53.5% | 55.01%
25-PC-32241 | Sumac Ridge Canal Lining Cultural Resources Monitoring | Final Reporting/Review | Time and material | Chesapeake | Bryan Mann | 331500 | 218836 | 214067.26 | 231983.7 | 231983.7 | 0 | 145011.57 | 86972.13 | 86972.13 |  | 66% | 62.51%
25-PC-32264 | Tansy Flat Wastewater Plant Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Sandy Kerr | 736000 | 500480 | 500480 | 420550.4 | 420550.4 | 0 | 341293.64 | 79256.76 | 79256.76 |  | 68% | 81.15%
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | In Progress | Time and material | Chesapeake | Ian Maddox | 201300 | 142188.6 | 130331.24 | 150874.35 | 150874.35 | 0 | 123300.5 | 27573.85 | 27573.85 |  | 70.6% | 81.72%
25-PC-32402 | Hawk Point Highway Widening - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Chesapeake | Sandy Kerr | 401300 | 211645.62 | 203981.38 | 353144 | 353144 | 0 | 186255.56 | 166888.44 | 166888.44 |  | 52.7% | 52.74%
25-PC-32447 | Pebble Beach Road Archaeological Testing | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 88200 | 88200 | 88200 | 61772.24 | 55626.38 | 6145.86 | 76703.23 | -14930.99 | -21076.85 |  | 100% | 124.2%
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | In Progress | Time and material | Chesapeake | Sandy Kerr | 118800 | 117294.6 | 109524.1 | 85013.28 | 85013.28 | 0 | 86666.19 | -1652.91 | -1652.91 |  | 98.7% | 101.9%
25-PC-32750 | Elk Meadow Fiber Route Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Bryan Mann | 35500 | 26884.15 | 26780.4 | 25187.75 | 22000.77 | 3186.98 | 19074.92 | 6112.83 | 2925.85 |  | 75.7% | 75.73%
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran | 86500 | 56266.5 | 48754.4 | 62245.4 | 62245.4 | 0 | 33373.56 | 28871.84 | 28871.84 |  | 65% | 53.62%
25-PC-32795 | North Fork Water Main Architectural History Survey | In Progress | Time and material | Front Range | Reginald Vargas | 16900 | 16900 | 16900 | 11650.86 | 11650.86 | 0 | 12884.7 | -1233.84 | -1233.84 |  | 100% | 110.6%
25-PC-32838 | Aspen Ridge Canal Lining - Curation | In Progress | Fixed fee | Front Range | Jeremy Tran | 42600 | 39204.78 | 39204.78 | 33543.24 | 33543.24 | 0 | 30870.45 | 2672.79 | 2672.79 |  | 92% | 92.03%
25-PC-32861 | Yarrow Point Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 59200 | 58353.44 | 53378.23 | 41555.52 | 31694.67 | 9860.85 | 40962.76 | 592.76 | -9268.09 |  | 98.6% | 98.57%
25-PC-32867 | Larkspur Levee Repair Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 144100 | 70882.79 | 68580.29 | 82727.81 | 82727.81 | 0 | 40695.2 | 42032.61 | 42032.61 |  | 49.2% | 49.19%
25-PC-32885 | Maple Fork Reservoir Historic Resources Evaluation | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 1706300 | 361394.34 | 336493.21 | 1213962.27 | 1090543.53 | 123418.74 | 257177.64 | 956784.63 | 833365.89 |  | 21.2% | 21.18%
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 59600 | 59600 | 57228.13 | 51399.04 | 51399.04 | 0 | 66929.55 | -15530.51 | -15530.51 |  | 100% | 130.2%
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Lab/Curation | Time and material | Front Range | Jeremy Tran | 13300 | 13300 | 13300 | 8727.43 | 6386.48 | 2340.95 | 16463.41 | -7735.98 | -10076.93 |  | 100% | 188.6%
25-PC-32926 | Tamarack Pipeline - Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran | 328400 | 68635.6 | 68635.6 | 212343.44 | 212343.44 | 0 | 61274.18 | 151069.26 | 151069.26 |  | 20.9% | 28.86%
25-PC-32952 | Eagle Bend Wastewater Plant - Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 299000 | 125968.7 | 119978.69 | 202368.34 | 160514.68 | 41853.66 | 85261.26 | 117107.08 | 75253.42 |  | 42.1% | 42.13%
25-PC-33065 | Wren Hollow GIS Mapping | In Progress | Fixed fee | Front Range | Dean Velazquez | 50400 | 45596.88 | 45596.88 | 40748.4 | 40748.4 | 0 | 36866.22 | 3882.18 | 3882.18 |  | 90.5% | 90.47%
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | In Progress | Fixed fee | Front Range | Reginald Vargas | 767800 | 603874.7 | 603874.7 | 553046.34 | 553046.34 | 0 | 434972.87 | 118073.47 | 118073.47 |  | 78.6% | 78.65%
25-PC-33105 | Redbud Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 3500 | 3219.65 | 0 | 2324 | 2324 | 0 | 2137.9 | 186.1 | 186.1 |  | 92% | 91.99%
25-PC-33136 | North Fork Historic Resources Evaluation | In Progress | Time and material | Front Range | Dean Velazquez | 33200 | 10696.15 | 10164.17 | 22378.06 | 19895.67 | 2482.39 | 7748.92 | 14629.14 | 12146.75 |  | 32.2% | 34.63%
25-PC-33183 | Saltgrass Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 104500 | 75386.3 | 69776.93 | 79399.1 | 79399.1 | 0 | 57275.72 | 22123.38 | 22123.38 |  | 72.1% | 72.14%
25-PC-33206 | Larkspur Water Main - Phase II Testing | In Progress | Fixed fee | Front Range | Mindy Galvan | 48800 | 16987.28 | 14897.55 | 39449.92 | 39449.92 | 0 | 13733.3 | 25716.62 | 25716.62 |  | 34.8% | 34.81%
25-PC-33294 | Fern Valley Substation - Built Environment Survey | In Progress | Fixed fee | Front Range | Joanna Herrera | 137200 | 62769 | 56672.3 | 91032.2 | 91032.2 | 0 | 41643.48 | 49388.72 | 49388.72 |  | 45.8% | 45.75%
25-PC-33332 | Willow Springs Cultural Resources Assessment | In Progress | Fixed fee | Front Range | Dean Velazquez | 91000 | 44844.8 | 41884.49 | 69587.7 | 69587.7 | 0 | 34294.19 | 35293.51 | 35293.51 |  | 49.3% | 49.28%
25-PC-33348 | Dove Canyon Cell Tower Phase II Testing | In Progress | Fixed fee | Front Range | Mindy Galvan | 161700 | 90374.13 | 90374.13 | 117749.94 | 117749.94 | 0 | 65815.88 | 51934.06 | 51934.06 |  | 55.9% | 55.89%
25-PC-33367 | Slate Ridge Rail Siding Archaeological Testing | Lab/Curation | Time and material | Front Range | Dean Velazquez | 150800 | 45583.65 | 42380.37 | 100689.16 | 100689.16 | 0 | 26591.04 | 74098.12 | 74098.12 |  | 30.2% | 26.41%
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Front Range | Devon Pitts | 41600 | 30792.32 | 30596.11 | 29136.64 | 29136.64 | 0 | 21568.22 | 7568.42 | 7568.42 |  | 74% | 74.02%
25-PC-33522 | Yarrow Point Architectural History Survey | Final Reporting/Review | Time and material | Front Range | Jeremy Tran | 61800 | 43109.2 | 40767.39 | 42270.22 | 36352.08 | 5918.14 | 28142.51 | 14127.71 | 8209.57 |  | 69.8% | 66.58%
25-PC-33640 | Tamarack Canal Lining - Cultural Resources Assessment | In Progress | Fixed fee | Front Range | Dean Velazquez | 1444500 | 389870.55 | 375155.5 | 1192145.85 | 1192145.85 | 0 | 321702.64 | 870443.21 | 870443.21 |  | 27% | 26.99%
25-PC-33680 | Quail Run School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 106800 | 31805.04 | 26717.84 | 80014.56 | 80014.56 | 0 | 23825.22 | 56189.34 | 56189.34 |  | 29.8% | 29.78%
25-PC-33744 | Blue Heron Canal Lining - Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 87100 | 56736.94 | 56736.94 | 60133.84 | 60133.84 | 0 | 39171.57 | 20962.27 | 20962.27 |  | 65.1% | 65.14%
25-PC-33750 | Kestrel Butte Archaeological Testing | In Progress | Fixed fee | Great Lakes | Kathleen Galvan | 69600 | 60614.64 | 55475.06 | 51302.16 | 51302.16 | 0 | 44676.73 | 6625.43 | 6625.43 |  | 87.1% | 87.09%
25-PC-33798 | On-Call: Harbor View Wind Farm Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Great Lakes | Brendan Padilla | 155300 | 68596.01 | 65706.53 | 128215.68 | 128215.68 | 0 | 56636.22 | 71579.46 | 71579.46 |  | 44.2% | 44.17%
25-PC-33841 | Juniper Wash Built Environment Survey | In Progress | Fixed fee | Great Lakes | Kathleen Galvan | 586500 | 366034.65 | 366034.65 | 416356.35 | 416356.35 | 0 | 259867.95 | 156488.4 | 156488.4 |  | 62.4% | 62.41%
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Final Reporting/Review | Fixed fee | Great Lakes | Geoffrey Fernandez | 15200 | 15200 | 15200 | 11021.49 | 9579.99 | 1441.5 | 11383.28 | -361.79 | -1803.29 |  | 100% | 103.3%
25-PC-33855 | Creosote Draw Rail Siding - Paleontological Monitoring | Final Reporting/Review | Time and material | Great Lakes | Karl Valenzuela | 34000 | 16697 | 15998.13 | 23930.44 | 21188.35 | 2742.09 | 11954.76 | 11975.68 | 9233.59 |  | 49.1% | 49.96%
25-PC-33915 | Sage Flat Archaeological Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes | 272400 | 145924.68 | 139303.53 | 198225.48 | 198225.48 | 0 | 106194.6 | 92030.88 | 92030.88 |  | 53.6% | 53.57%
25-PC-33922 | Slate Ridge Data Recovery | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 22100 | 22100 | 22100 | 16113.11 | 16113.11 | 0 | 31034.28 | -14921.17 | -14921.17 |  | 100% | 192.6%
25-PC-33969 | Sumac Ridge Archaeological Testing | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 13200 | 7814.4 | 7814.4 | 10134.96 | 10134.96 | 0 | 5999.73 | 4135.23 | 4135.23 |  | 59.2% | 59.2%
25-PC-34036 | Kestrel Butte Battery Storage - Phase I Survey | Lab/Curation | Time and material | Great Lakes | Gina Beltran | 62300 | 28401.9 | 22107.85 | 41495.74 | 36709.53 | 4786.21 | 20235.46 | 21260.28 | 16474.07 |  | 45.6% | 48.77%
25-PC-34077 | Sage Flat Levee Repair Class III Survey | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 580500 | 208805.85 | 191070.11 | 459697.95 | 459697.95 | 0 | 165339.47 | 294358.48 | 294358.48 |  | 36% | 35.97%
25-PC-34088 | Timber Gap Harbor Dredging Cultural Resources Monitoring | In Progress | Time and material | Great Lakes | Leonard Mejia | 47300 | 32164 | 32164 | 29041.82 | 26577.06 | 2464.76 | 17359.62 | 11682.2 | 9217.44 |  | 68% | 59.77%
25-PC-34090 | Thistle Down Data Recovery | In Progress | Time and material | Great Lakes | Geoffrey Fernandez | 66200 | 28489.3 | 28489.3 | 46862.98 | 46862.98 | 0 | 19845.59 | 27017.39 | 27017.39 |  | 43% | 42.35%
25-PC-34151 | Bramble Creek Fiber Route Cultural Resources Monitoring | In Progress | Time and material | Great Lakes | Angelica Cervantes | 505100 | 158849.4 | 150695.04 | 334224.67 | 334224.67 | 0 | 107068.4 | 227156.27 | 227156.27 |  | 31.4% | 32.03%
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Geoffrey Fernandez | 53000 | 53000 | 53000 | 36718.4 | 36718.4 | 0 | 38337.84 | -1619.44 | -1619.44 |  | 100% | 104.4%
25-PC-34374 | Tansy Flat Reservoir Cultural Resources Assessment | In Progress | Time and material | Great Lakes | Gina Beltran | 14100 | 5160.6 | 5160.6 | 9871.41 | 9871.41 | 0 | 3661.74 | 6209.67 | 6209.67 |  | 36.6% | 37.09%
25-PC-34451 | North Fork Curation | In Progress | Time and material | Great Lakes | Robin Mercado | 46400 | 46400 | 46400 | 32526.4 | 32526.4 | 0 | 41685.4 | -9159 | -9159 |  | 100% | 128.2%
25-PC-34652 | Coyote Springs Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Gina Beltran | 210700 | 127557.78 | 109266.76 | 180928.09 | 180928.09 | 0 | 109531.96 | 71396.13 | 71396.13 |  | 60.5% | 60.54%
25-PC-34681 | Hawk Point Pipeline Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Brendan Padilla | 715200 | 180444.96 | 156689 | 430908 | 430908 | 0 | 108698.3 | 322209.7 | 322209.7 |  | 25.2% | 25.23%
25-PC-34732 | Thistle Down Trail Architectural History Survey | In Progress | Fixed fee | Great Lakes | Geoffrey Fernandez | 101800 | 62433.94 | 62433.94 | 76441.62 | 76441.62 | 0 | 46880.67 | 29560.95 | 29560.95 |  | 61.3% | 61.33%
25-PC-34772 | Windmill Flat Paleontological Monitoring | Final Reporting/Review | Time and material | Great Lakes | Brendan Padilla | 186900 | 16821 | 14771.98 | 126437.85 | 126437.85 | 0 | 9051.13 | 117386.72 | 117386.72 |  | 9% | 7.16%
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | In Progress | Time and material | Great Lakes | Gina Beltran | 82200 | 72235 | 55106.92 | 51638.04 | 51638.04 | 0 | 47023.17 | 4614.87 | 4614.87 |  | 87.9% | 91.06%
25-PC-34850 | Thistle Down Section 106 Consultation | In Progress | Time and material | Gulf Coast East | Wyatt Erickson | 201300 | 100383.5 | 91270.5 | 117035.82 | 117035.82 | 0 | 72108.79 | 44927.03 | 44927.03 |  | 49.9% | 61.61%
25-PC-34871 | Willow Springs GIS Mapping | Lab/Curation | Fixed fee | Gulf Coast East | Sean Jennings | 338100 | 119383.11 | 98188.1 | 260979.39 | 260979.39 | 0 | 92146.31 | 168833.08 | 168833.08 |  | 35.3% | 35.31%
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Wyatt Erickson | 224400 | 157798.08 | 157798.08 | 165046.2 | 165046.2 | 0 | 116067.93 | 48978.27 | 48978.27 |  | 70.3% | 70.32%
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 71400 | 71400 | 71400 | 48880.44 | 48880.44 | 0 | 56947.79 | -8067.35 | -8067.35 |  | 100% | 116.5%
25-PC-35084 | On-Call: Fern Valley Wastewater Plant Class III Survey | Final Reporting/Review | Fixed fee | Gulf Coast East | Bernard Erickson | 204900 | 119968.95 | 114526.38 | 133588.01 | 98343.72 | 35244.29 | 78216.34 | 55371.67 | 20127.38 |  | 58.6% | 58.55%
25-PC-35131 | Tamarack Phase II Testing | In Progress | Fixed fee | Gulf Coast | Bernard Erickson | 311900 | 130966.81 | 130966.81 | 227562.24 | 227562.24 | 0 | 95549.55 | 132012.69 | 132012.69 |  | 42% | 41.99%
25-PC-35138 | Foxglove Mixed-Use Development - Data Recovery | In Progress | Time and material | Gulf Coast East | Sean Jennings | 815000 | 520809.25 | 517798.86 | 517757.75 | 477272.64 | 40485.11 | 376872.02 | 140885.73 | 100400.62 |  | 63.9% | 72.79%
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | In Progress | Time and material | Gulf Coast | Wyatt Erickson | 33200 | 30795.6 | 29124.8 | 23495.64 | 23495.64 | 0 | 24936.59 | -1440.95 | -1440.95 |  | 92.8% | 106.1%
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 49900 | 49900 | 47494.52 | 35982.89 | 35982.89 | 0 | 32404.14 | 3578.75 | 3578.75 |  | 100% | 90.05%
25-PC-35295 | Copper Flats Architectural History Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 80400 | 54672 | 54672 | 54551.4 | 54551.4 | 0 | 39686.68 | 14864.72 | 14864.72 |  | 68% | 72.75%
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 19400 | 19400 | 15409.48 | 13919.5 | 13919.5 | 0 | 28280.1 | -14360.6 | -14360.6 |  | 100% | 203.2%
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Courtney Daugherty | 25100 | 25100 | 24927.65 | 20032.31 | 20032.31 | 0 | 25937.98 | -5905.67 | -5905.67 |  | 100% | 129.5%
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | In Progress | Time and material | High Desert | Kathy Hurley | 136900 | 136900 | 132838.07 | 90994.45 | 78522.66 | 12471.79 | 99844.69 | -8850.24 | -21322.03 |  | 100% | 109.7%
25-PC-35496 | Silver Lake Airport Apron Class III Survey | In Progress | Time and material | High Desert | Kathy Hurley | 15200 | 11677.4 | 11677.4 | 10132.32 | 10132.32 | 0 | 8385.01 | 1747.31 | 1747.31 |  | 76.8% | 82.76%
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox | 98800 | 72578.48 | 72578.48 | 78447.2 | 78447.2 | 0 | 57628.94 | 20818.26 | 20818.26 |  | 73.5% | 73.46%
25-PC-35553 | Rushgrass Draw Rail Siding - Data Recovery | In Progress | Time and material | High Desert | Eileen Poole | 589900 | 335611 | 310270.7 | 444589.27 | 356163.6 | 88425.67 | 245050.65 | 199538.62 | 111112.95 |  | 56.9% | 55.12%
25-PC-35740 | Oak Terrace Transmission Line - Historic Resources Evaluation | In Progress | Fixed fee | High Desert | Kathy Hurley | 28600 | 572 | 572 | 15121.1 | 12638.3 | 2482.8 | 303.1 | 14818 | 12335.2 |  | 2% | 2%
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 204800 | 153825.28 | 136373.26 | 136396.8 | 136396.8 | 0 | 102448.83 | 33947.97 | 33947.97 |  | 75.1% | 75.11%
25-PC-35779 | Task Order 9: Juniper Wash Wastewater Plant Built Environment Survey | In Progress | Fixed fee | High Desert | Bridget Maddox | 124800 | 87672 | 85566.5 | 84973.75 | 63196.65 | 21777.1 | 59692.64 | 25281.11 | 3504.01 |  | 70.3% | 70.25%
25-PC-35850 | Pebble Beach Road Environmental Review Support | Cost Tracking on Closed Project | Time and material | High Desert | Bridget Maddox | 53400 | 36312 | 36312 | 37978.08 | 37978.08 | 0 | 32074.27 | 5903.81 | 5903.81 |  | 68% | 84.45%
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | In Progress | Fixed fee | High Desert | Jody Wang | 83700 | 76761.27 | 76761.27 | 61050.78 | 61050.78 | 0 | 55992.16 | 5058.62 | 5058.62 |  | 91.7% | 91.71%
25-PC-35963 | Quail Run Substation - Section 106 Consultation | In Progress | Time and material | High Desert | Kathy Hurley | 320000 | 267094.25 | 267094.25 | 216192 | 216192 | 0 | 187290.43 | 28901.57 | 28901.57 |  | 83.5% | 86.63%
25-PC-35970 | Eagle Bend Wind Farm Phase II Testing | In Progress | Fixed fee | High Desert | Bridget Maddox | 53200 | 15023.68 | 15023.68 | 38886.26 | 35417.28 | 3468.98 | 10981.21 | 27905.05 | 24436.07 |  | 28.2% | 28.24%
25-PC-36051 | Riverbend Levee Repair Archaeological Testing | In Progress | Fixed fee | High Desert | Bridget Maddox | 405400 | 274617.96 | 274617.96 | 250415.58 | 250415.58 | 0 | 169641.96 | 80773.62 | 80773.62 |  | 67.7% | 67.74%
25-PC-36093 | Pine Hollow Pipeline Cultural Resources Assessment | Lab/Curation | Fixed fee | High Desert | Jody Wang | 213300 | 140159.43 | 139081.37 | 157884.66 | 157884.66 | 0 | 103743.23 | 54141.43 | 54141.43 |  | 65.7% | 65.71%
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | In Progress | Time and material | High Desert | Kathy Hurley | 114200 | 114200 | 114200 | 78124.22 | 78124.22 | 0 | 74195.39 | 3928.83 | 3928.83 |  | 100% | 94.97%
25-PC-36251 | Kestrel Butte Environmental Review Support | Lab/Curation | Fixed fee | Island | Joan Mathis | 39200 | 39200 | 39200 | 30446.64 | 30446.64 | 0 | 49335.55 | -18888.91 | -18888.91 |  | 100% | 162%
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | In Progress | Time and material | Island | Joan Mathis | 28100 | 24249.95 | 24228.48 | 19141.72 | 19141.72 | 0 | 16390.17 | 2751.55 | 2751.55 |  | 86.3% | 85.63%
25-PC-36332 | Goldfinch Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 871000 | 421041.4 | 403903.35 | 618958.05 | 566005.77 | 52952.28 | 299209.24 | 319748.81 | 266796.53 |  | 48.3% | 48.34%
25-PC-36336 | Sea Oat Canal Lining Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 36400 | 24693.76 | 20874.22 | 25854.92 | 25854.92 | 0 | 17541.09 | 8313.83 | 8313.83 |  | 67.8% | 67.84%
25-PC-36352 | Phase I: Plover Cove Substation Paleontological Monitoring | In Progress | Fixed fee | Island | Joan Mathis | 3262900 | 350109.17 | 312152.78 | 2263196.88 | 1903101.18 | 360095.7 | 242935.53 | 2020261.35 | 1660165.65 |  | 10.7% | 10.73%
25-PC-36366 | Lone Pine Solar Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 119500 | 36829.9 | 33137.93 | 101598.9 | 101598.9 | 0 | 31308.09 | 70290.81 | 70290.81 |  | 30.8% | 30.82%
25-PC-36464 | Larkspur Highway Widening Cultural Resources Assessment | In Progress | Time and material | Island | Joan Mathis | 102300 | 76761.1 | 76761.1 | 72751.63 | 53089.29 | 19662.34 | 60185.29 | 12566.34 | -7096 |  | 75% | 82.73%
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | In Progress | Fixed fee | Island | Becky Velazquez | 33100 | 33100 | 33100 | 25870.96 | 25870.96 | 0 | 34277.75 | -8406.79 | -8406.79 |  | 100% | 132.5%
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | In Progress | Fixed fee | Island | Joan Mathis | 88300 | 62013.09 | 61113.31 | 54269.18 | 54269.18 | 0 | 38112.57 | 16156.61 | 16156.61 |  | 70.2% | 70.23%
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Becky Velazquez | 116000 | 85573.2 | 85573.2 | 66050.4 | 66050.4 | 0 | 48723.63 | 17326.77 | 17326.77 |  | 73.8% | 73.77%
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | In Progress | Time and material | Lakeshore | Lucas Benson | 181300 | 181300 | 174825.53 | 117609.31 | 117609.31 | 0 | 127344.66 | -9735.35 | -9735.35 |  | 100% | 108.3%
25-PC-36645 | Falcon Mesa Archaeological Testing | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 25400 | 25400 | 24158.24 | 20302.22 | 20302.22 | 0 | 30595.4 | -10293.18 | -10293.18 |  | 100% | 150.7%
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | In Progress | Time and material | Lakeshore | Lucas Benson | 137400 | 108023.85 | 108023.85 | 99958.5 | 99958.5 | 0 | 83440.54 | 16517.96 | 16517.96 |  | 78.6% | 83.48%
25-PC-36657 | Stone Mill Park Improvements Phase II Testing | Final Reporting/Review | Time and material | Lakeshore | Jeanette Riddle | 255700 | 97365.65 | 90595.25 | 186833.25 | 150017.49 | 36815.76 | 70646.69 | 116186.56 | 79370.8 |  | 38.1% | 37.81%
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Final Reporting/Review | Fixed fee | Lakeshore | Jeanette Riddle | 74000 | 63921.2 | 55986.55 | 56358.4 | 56358.4 | 0 | 48683.55 | 7674.85 | 7674.85 |  | 86.4% | 86.38%
25-PC-36799 | Meadowlark Substation Phase I Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 32900 | 32900 | 30883.36 | 26389.09 | 26389.09 | 0 | 28421.17 | -2032.08 | -2032.08 |  | 100% | 107.7%
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 24200 | 24200 | 22550.8 | 16235.78 | 16235.78 | 0 | 23585.68 | -7349.9 | -7349.9 |  | 100% | 145.3%
25-PC-36832 | Stone Mill Phase I Survey | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 78400 | 44029.44 | 44029.44 | 52449.6 | 52449.6 | 0 | 29456.38 | 22993.22 | 22993.22 |  | 56.2% | 56.16%
25-PC-36838 | Phase II: Granite Pass Highway Widening Environmental Review Support | Final Reporting/Review | Time and material | Hill Country | Samuel Wilkerson | 216400 | 147645.15 | 134481.25 | 160499.18 | 119267.1 | 41232.08 | 105308.54 | 55190.64 | 13958.56 |  | 68.2% | 65.61%
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | In Progress | Time and material | Hill Country | Glen Delacruz | 75400 | 75400 | 71354.11 | 50299.34 | 50299.34 | 0 | 81278.45 | -30979.11 | -30979.11 |  | 100% | 161.6%
25-PC-37188 | On-Call: Lone Pine Airport Apron Cultural Resources Assessment | In Progress | Time and material | Hill Country | Suzanne Mcmillan | 131600 | 103670.5 | 103670.5 | 95554.76 | 95554.76 | 0 | 53871.13 | 41683.63 | 41683.63 |  | 78.8% | 56.38%
25-PC-37371 | Phase II: Ember Valley Water Main Class III Survey | In Progress | Fixed fee | Piedmont | Maria Parrish | 292700 | 95859.25 | 90222.46 | 199428.52 | 154432.08 | 44996.44 | 65319.77 | 134108.75 | 89112.31 |  | 32.8% | 32.75%
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | In Progress | Fixed fee | Piedmont | Maria Parrish | 59200 | 54913.92 | 54913.92 | 50698.88 | 50698.88 | 0 | 47030.53 | 3668.35 | 3668.35 |  | 92.8% | 92.76%
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Cost Tracking on Closed Project | Time and material | Piedmont | Megan Pineda | 83200 | 22297.6 | 22297.6 | 60186.88 | 60186.88 | 0 | 78242.94 | -18056.06 | -18056.06 |  | 26.8% | 130%
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | In Progress | Time and material | Piedmont | Jody Chung | 458200 | 311576 | 311576 | 301449.78 | 301449.78 | 0 | 240796.49 | 60653.29 | 60653.29 |  | 68% | 79.88%
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Lab/Curation | Fixed fee | Piedmont | Jody Chung | 21500 | 18275 | 17172.5 | 15617.6 | 15617.6 | 0 | 13275.67 | 2341.93 | 2341.93 |  | 85% | 85%
25-PC-37544 | Sparrow Hill Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 1009600 | 789709.12 | 789709.12 | 644730.56 | 644730.56 | 0 | 504318.97 | 140411.59 | 140411.59 |  | 78.2% | 78.22%
25-PC-37732 | Hawk Point Housing Development Class III Survey | In Progress | Fixed fee | Piedmont | Megan Pineda | 72900 | 47895.3 | 43208.3 | 45824.94 | 45824.94 | 0 | 30107.77 | 15717.17 | 15717.17 |  | 65.7% | 65.7%
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Final Reporting/Review | Time and material | Piedmont | Maria Parrish | 72200 | 69466.7 | 69466.7 | 44893.96 | 44893.96 | 0 | 57390.52 | -12496.56 | -12496.56 |  | 96.2% | 127.8%
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Megan Pineda | 7900 | 7900 | 7900 | 6020.59 | 6020.59 | 0 | 6629.3 | -608.71 | -608.71 |  | 100% | 110.1%
25-PC-37920 | Heron Marsh Mine Expansion Class III Survey | In Progress | Time and material | Piedmont | Maria Parrish | 138600 | 41003.7 | 36116.58 | 92806.56 | 92806.56 | 0 | 27302.55 | 65504.01 | 65504.01 |  | 29.6% | 29.42%
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd | 148100 | 98767.89 | 96324.73 | 106809.72 | 106809.72 | 0 | 71233.44 | 35576.28 | 35576.28 |  | 66.7% | 66.69%
25-PC-38006 | Timber Gap Wastewater Plant Archaeological Testing | In Progress | Time and material | Prairie | Sherry Lloyd | 112000 | 46616.5 | 46616.5 | 75667.2 | 75667.2 | 0 | 36469.16 | 39198.04 | 39198.04 |  | 41.6% | 48.2%
25-PC-38042 | Oak Terrace School Campus GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 24300 | 20144.7 | 20144.7 | 19082.79 | 19082.79 | 0 | 15820.03 | 3262.76 | 3262.76 |  | 82.9% | 82.9%
25-PC-38070 | Phase III: Willow Springs Wastewater Plant Historic Resources Evaluation | In Progress | Fixed fee | Prairie | Sherry Lloyd | 132800 | 82601.6 | 82601.6 | 116864 | 116864 | 0 | 72689.82 | 44174.18 | 44174.18 |  | 62.2% | 62.2%
25-PC-38107 | Task Order 13: Pebble Beach Road Substation Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd | 234600 | 59283.42 | 53259.69 | 208913.08 | 154792 | 54121.08 | 52782.34 | 156130.74 | 102009.66 |  | 25.3% | 25.27%
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | In Progress | Fixed fee | Prairie | Sherry Lloyd | 25300 | 17937.7 | 16402.99 | 16961.12 | 16961.12 | 0 | 12025.12 | 4936 | 4936 |  | 70.9% | 70.9%
25-PC-38196 | Sea Oat Cell Tower Built Environment Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 1160700 | 688295.1 | 688295.1 | 717428.67 | 717428.67 | 0 | 425399.95 | 292028.72 | 292028.72 |  | 59.3% | 59.3%
25-PC-38282 | Task Order 16: Fern Valley Reservoir Architectural History Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 1334100 | 672386.4 | 672386.4 | 876348.58 | 703000.66 | 173347.92 | 522008.11 | 354340.47 | 180992.55 |  | 50.4% | 59.57%
25-PC-38296 | Ember Valley Pipeline - GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 173000 | 56882.4 | 46091.75 | 111169.8 | 111169.8 | 0 | 36547.9 | 74621.9 | 74621.9 |  | 32.9% | 32.88%
25-PC-38332 | Redbud GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 899800 | 706522.96 | 706522.96 | 754394.62 | 682213.35 | 72181.27 | 592323.19 | 162071.43 | 89890.16 |  | 78.5% | 78.52%
25-PC-38333 | Pine Hollow Cell Tower Phase II Testing | In Progress | Fixed fee | Prairie | Sherry Lloyd | 78300 | 56861.46 | 56861.46 | 51450.4 | 46958.73 | 4491.67 | 37360.87 | 14089.53 | 9597.86 |  | 72.6% | 72.62%
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd | 136400 | 99080.96 | 99080.96 | 86736.76 | 86736.76 | 0 | 63001.3 | 23735.46 | 23735.46 |  | 72.6% | 72.64%
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | In Progress | Time and material | Red Rock | Jeanette Chung | 496400 | 361231.05 | 339587.82 | 357705.84 | 357705.84 | 0 | 242460.88 | 115244.96 | 115244.96 |  | 72.8% | 67.78%
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 176400 | 144700.92 | 144700.92 | 137697.84 | 137697.84 | 0 | 112949.48 | 24748.36 | 24748.36 |  | 82% | 82.03%
25-PC-38596 | Tansy Flat Pipeline Data Recovery | In Progress | Fixed fee | Red Rock | Bruce Suarez | 178000 | 91848 | 91848 | 148416.4 | 148416.4 | 0 | 76585.73 | 71830.67 | 71830.67 |  | 51.6% | 51.6%
25-PC-38606 | Silver Lake School Campus - Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 34800 | 20358 | 20358 | 26816.2 | 23301.12 | 3515.08 | 15688.36 | 11127.84 | 7612.76 |  | 58.5% | 58.5%
25-PC-38701 | Slate Ridge Curation | In Progress | Time and material | Red Rock | Javier Newman | 156400 | 85366.5 | 77962.81 | 98735.32 | 98735.32 | 0 | 54980.84 | 43754.48 | 43754.48 |  | 54.6% | 55.69%
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | In Progress | Fixed fee | Red Rock | Javier Newman | 63900 | 63900 | 60446.65 | 41637.24 | 41637.24 | 0 | 46667.52 | -5030.28 | -5030.28 |  | 100% | 112.1%
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 10400 | 10400 | 9781.64 | 5866.64 | 5866.64 | 0 | 14952.41 | -9085.77 | -9085.77 |  | 100% | 254.9%
25-PC-38879 | Kestrel Butte Built Environment Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 119700 | 88482.24 | 88482.24 | 70323.75 | 70323.75 | 0 | 51984.23 | 18339.52 | 18339.52 |  | 73.9% | 73.92%
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | In Progress | Time and material | Red Rock | Tina Aguirre | 244000 | 179182 | 179182 | 174704 | 174704 | 0 | 141963.7 | 32740.3 | 32740.3 |  | 73.4% | 81.26%
25-PC-39085 | Slate Ridge Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez | 120700 | 105479.73 | 105479.73 | 69209.38 | 69209.38 | 0 | 60479.76 | 8729.62 | 8729.62 |  | 87.4% | 87.39%
25-PC-39093 | Goldfinch Canal Lining Phase I Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 100100 | 40990.95 | 37670.21 | 73673.6 | 73673.6 | 0 | 30167.05 | 43506.55 | 43506.55 |  | 40.9% | 40.95%
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Shelia Horne | 90300 | 56916.09 | 51858.16 | 58198.35 | 58198.35 | 0 | 36682.35 | 21516 | 21516 |  | 63% | 63.03%
25-PC-39187 | Windmill Flat Trail - Architectural History Survey | Lab/Curation | Fixed fee | Red Rock | Javier Newman | 28100 | 13811.15 | 13811.15 | 19470.49 | 19470.49 | 0 | 9569.28 | 9901.21 | 9901.21 |  | 49.1% | 49.15%
25-PC-39318 | Lone Pine Fiber Route - Class III Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 104300 | 63696.01 | 62739.38 | 69818.42 | 69818.42 | 0 | 42636.06 | 27182.36 | 27182.36 |  | 61.1% | 61.07%
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Final Reporting/Review | Time and material | Red Rock | Tina Aguirre | 55900 | 55838.85 | 53973.41 | 39633.1 | 39633.1 | 0 | 33287.69 | 6345.41 | 6345.41 |  | 99.9% | 83.99%
25-PC-39398 | Silver Lake Housing Development - Data Recovery | Final Reporting/Review | Fixed fee | Red Rock | Marisa Odom | 103300 | 66783.45 | 66783.45 | 81096.61 | 66453.3 | 14643.31 | 52431.07 | 28665.54 | 14022.23 |  | 64.6% | 64.65%
25-PC-39422 | Willow Springs Historic Resources Evaluation | In Progress | Fixed fee | Red Rock | Bruce Suarez | 56900 | 14953.32 | 15170.28 | 45036.35 | 45036.35 | 0 | 11836.29 | 33200.06 | 33200.06 |  | 26.3% | 26.28%
25-PC-39424 | Tansy Flat Cultural Resources Assessment | In Progress | Fixed fee | Red Rock | Shelia Horne | 19700 | 19700 | 17614.13 | 13882.59 | 13882.59 | 0 | 14155.07 | -272.48 | -272.48 |  | 100% | 102%
25-PC-39458 | Larkspur Park Improvements Paleontological Monitoring | In Progress | Time and material | Red Rock | Bruce Suarez | 345000 | 195602.25 | 187467.3 | 242983.5 | 242983.5 | 0 | 120714.28 | 122269.22 | 122269.22 |  | 56.7% | 49.68%
25-PC-39554 | Thistle Down Archaeological Testing | In Progress | Fixed fee | Red Rock | Tina Aguirre | 86700 | 35555.67 | 23674.72 | 63594.45 | 63594.45 | 0 | 26077.83 | 37516.62 | 37516.62 |  | 41% | 41.01%
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | In Progress | Time and material | Red Rock | Javier Newman | 51000 | 51000 | 51000 | 36551.7 | 36551.7 | 0 | 67180.53 | -30628.83 | -30628.83 |  | 100% | 183.8%
25-PC-39808 | On-Call: Pine Hollow Rail Siding Architectural History Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 140600 | 66827.18 | 66827.18 | 88846.16 | 68571.9 | 20274.26 | 42231.81 | 46614.35 | 26340.09 |  | 47.5% | 47.53%
25-PC-39873 | On-Call: Eagle Bend Battery Storage Phase II Testing | In Progress | Fixed fee | Red Rock | Marisa Odom | 93300 | 36051.12 | 33111.68 | 70478.82 | 70478.82 | 0 | 27233.7 | 43245.12 | 43245.12 |  | 38.6% | 38.64%
25-PC-39885 | Bramble Creek Phase I Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 85600 | 51368.56 | 51232.23 | 54047.84 | 54047.84 | 0 | 32436.64 | 21611.2 | 21611.2 |  | 60% | 60.01%
25-PC-39896 | Task Order 8: Raven Rock Highway Widening Archaeological Testing | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 730900 | 541743.08 | 541743.08 | 540257.83 | 458118.4 | 82139.43 | 400441.47 | 139816.36 | 57676.93 |  | 74.1% | 74.12%
25-PC-39951 | Falcon Mesa Reservoir - Phase II Testing | Cost Tracking on Closed Project | Fixed fee | Red Rock | Javier Newman | 87200 | 69358.88 | 69358.88 | 65277.92 | 65277.92 | 0 | 51921.91 | 13356.01 | 13356.01 |  | 79.5% | 79.54%
25-PC-40231 | Goldfinch Pipeline - Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring | 88300 | 43555.7 | 38591.94 | 59478.88 | 59478.88 | 0 | 26711.41 | 32767.47 | 32767.47 |  | 49.3% | 44.91%
25-PC-40383 | North Fork Archaeological Testing | In Progress | Fixed fee | Sierra | Donna Herring | 193200 | 161148.12 | 161148.12 | 144185.16 | 144185.16 | 0 | 120262.61 | 23922.55 | 23922.55 |  | 83.4% | 83.41%
25-PC-40465 | Task Order 32: Copper Flats Solar Historic Resources Evaluation | In Progress | Fixed fee | Sierra | Benjamin Mathis | 127600 | 66058.52 | 62241.26 | 94627.43 | 86041.09 | 8586.34 | 48993.04 | 45634.39 | 37048.05 |  | 51.8% | 51.77%
25-PC-40482 | Task Order 33: Tamarack Cell Tower Cultural Resources Assessment | In Progress | Fixed fee | Sierra South | Louis Huff | 73200 | 29184.84 | 28569.89 | 60199.68 | 60199.68 | 0 | 24003.99 | 36195.69 | 36195.69 |  | 39.9% | 39.87%
25-PC-40503 | Copper Flats Phase I Survey | Lab/Curation | Time and material | Sierra | Benjamin Mathis | 43400 | 43400 | 43400 | 30119.6 | 30119.6 | 0 | 42364.23 | -12244.63 | -12244.63 |  | 100% | 140.7%
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring | 71000 | 71000 | 67104.25 | 49579.3 | 49579.3 | 0 | 67225.72 | -17646.42 | -17646.42 |  | 100% | 135.6%
25-PC-40541 | Eagle Bend Airport Apron - Archaeological Testing | In Progress | Fixed fee | Sierra | Louis Huff | 25000 | 16595 | 16595 | 16850 | 16850 | 0 | 11185.54 | 5664.46 | 5664.46 |  | 66.4% | 66.38%
25-PC-40572 | Maple Fork Cell Tower Environmental Review Support | In Progress | Fixed fee | Sierra | Benjamin Mathis | 88300 | 33094.84 | 32977.35 | 67293.43 | 67293.43 | 0 | 25222.43 | 42071 | 42071 |  | 37.5% | 37.48%
25-PC-40595 | Willow Springs Levee Repair - Built Environment Survey | Final Reporting/Review | Fixed fee | Sierra South | Angelica Poole | 1568300 | 557530.65 | 539812.14 | 1302159.49 | 1302159.49 | 0 | 462868.69 | 839290.8 | 839290.8 |  | 35.6% | 35.55%
25-PC-40677 | Quail Run Paleontological Monitoring | In Progress | Time and material | Sierra South | Louis Huff | 225000 | 192903.25 | 192903.25 | 157612.5 | 157612.5 | 0 | 153698.04 | 3914.46 | 3914.46 |  | 85.7% | 97.52%
25-PC-40680 | On-Call: Eagle Bend Battery Storage Cultural Resources Assessment | Lab/Curation | Time and material | Sierra | Donna Herring | 10100 | 8386.75 | 8386.75 | 6706.4 | 6706.4 | 0 | 5628.16 | 1078.24 | 1078.24 |  | 83% | 83.92%
25-PC-40722 | Goldfinch Canal Lining - Archaeological Testing | In Progress | Time and material | Coastal Bend | Duane Ballard | 166600 | 128119.75 | 128119.75 | 119491.23 | 103318.2 | 16173.03 | 80423 | 39068.23 | 22895.2 |  | 76.9% | 67.3%
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 50100 | 44012.85 | 41907.3 | 34844.55 | 34844.55 | 0 | 30609.86 | 4234.69 | 4234.69 |  | 87.8% | 87.85%
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 46800 | 46800 | 46800 | 34243.56 | 34243.56 | 0 | 37327.45 | -3083.89 | -3083.89 |  | 100% | 109%
25-PC-40880 | Pebble Beach Road Bridge Replacement Cultural Resources Assessment | In Progress | Time and material | Coastal Bend | Diane Daniels | 45800 | 23601.35 | 21262.83 | 30347.08 | 30347.08 | 0 | 14800 | 15547.08 | 15547.08 |  | 51.5% | 48.77%
25-PC-40925 | Harbor View Airport Apron - Data Recovery | Final Reporting/Review | Time and material | Coastal Bend | Alexis Nixon | 35000 | 23800 | 23800 | 23562 | 23562 | 0 | 20240.75 | 3321.25 | 3321.25 |  | 68% | 85.9%
25-PC-41075 | Phase I: Cedar Hollow Airport Apron Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 82100 | 44448.94 | 43497.08 | 61304.07 | 61304.07 | 0 | 33188.18 | 28115.89 | 28115.89 |  | 54.1% | 54.14%
25-PC-41097 | On-Call: Falcon Mesa Wastewater Plant Phase II Testing | Final Reporting/Review | Time and material | Coastal Bend | Duane Ballard | 197800 | 130637.05 | 124588.7 | 128154.62 | 128154.62 | 0 | 87950.93 | 40203.69 | 40203.69 |  | 66% | 68.63%
25-PC-41187 | Hackberry Bend Trail GIS Mapping | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 98900 | 71524.48 | 68796.42 | 55621.36 | 55621.36 | 0 | 40227 | 15394.36 | 15394.36 |  | 72.3% | 72.32%
25-PC-41252 | Oak Terrace Wastewater Plant Curation | Final Reporting/Review | Fixed fee | Coastal Bend | Steve Rubio | 33000 | 27690.3 | 27478.52 | 25325 | 22089.27 | 3235.73 | 21249.95 | 4075.05 | 839.32 |  | 83.9% | 83.91%
25-PC-41265 | Larkspur Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 89800 | 85318.98 | 85318.98 | 71911.84 | 71911.84 | 0 | 68323.14 | 3588.7 | 3588.7 |  | 95% | 95.01%
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 167900 | 127117.09 | 124116.46 | 131616.81 | 131616.81 | 0 | 99649.4 | 31967.41 | 31967.41 |  | 75.7% | 75.71%
25-PC-41383 | Harbor View Reservoir - Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 342200 | 263870.42 | 263870.42 | 223902.7 | 185978.46 | 37924.24 | 172645.04 | 51257.66 | 13333.42 |  | 77.1% | 77.11%
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 179800 | 179800 | 170811.36 | 119171.44 | 119171.44 | 0 | 138577.96 | -19406.52 | -19406.52 |  | 100% | 116.3%
25-PC-41479 | Hawk Point Trail Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 633600 | 187989.12 | 185087.99 | 405123.84 | 405123.84 | 0 | 120193.33 | 284930.51 | 284930.51 |  | 29.7% | 29.67%
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Jared Choi | 130200 | 112124.2 | 112124.2 | 94156.73 | 81265.42 | 12891.31 | 99461.24 | -5304.51 | -18195.82 |  | 86.1% | 105.6%
25-PC-41514 | Lantern Bay Levee Repair Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 48700 | 38516.83 | 38484.8 | 31123.36 | 29237.6 | 1885.76 | 24615.03 | 6508.33 | 4622.57 |  | 79.1% | 79.09%
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | In Progress | Time and material | Coastal Bend | Jared Choi | 412300 | 260814.45 | 250394.1 | 281889.51 | 281889.51 | 0 | 197623.07 | 84266.44 | 84266.44 |  | 63.3% | 70.11%
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | In Progress | Time and material | Built Environment | Jenny Wilkinson | 152100 | 112187.4 | 112187.4 | 108599.4 | 108599.4 | 0 | 90984.66 | 17614.74 | 17614.74 |  | 73.8% | 83.78%
25-PC-41764 | Stone Mill Environmental Review Support | In Progress | Time and material | Built Environment | Jenny Wilkinson | 20700 | 16684.25 | 16684.25 | 15642.78 | 13328.34 | 2314.44 | 14549.83 | 1092.95 | -1221.49 |  | 80.6% | 93.01%
25-PC-41834 | Pebble Beach Road Data Recovery | In Progress | Fixed fee | Built Environment | Rickey Salas | 170100 | 52526.88 | 47271.26 | 145401.48 | 145401.48 | 0 | 44903.16 | 100498.32 | 100498.32 |  | 30.9% | 30.88%
25-PC-41843 | Wren Hollow Rail Siding - Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Jesse Maynard | 54000 | 36720 | 36720 | 35988.02 | 26607.55 | 9380.47 | 23655.15 | 12332.87 | 2952.4 |  | 68% | 65.73%
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | In Progress | Time and material | Built Environment | Rickey Salas | 39700 | 33696.1 | 32006.45 | 25920.13 | 25920.13 | 0 | 23960.47 | 1959.66 | 1959.66 |  | 84.9% | 92.44%
25-PC-42076 | Bramble Creek Highway Widening Curation | In Progress | Time and material | Built Environment | Jesse Maynard | 319600 | 118519.05 | 110576.76 | 227746.96 | 227746.96 | 0 | 75255.72 | 152491.24 | 152491.24 |  | 37.1% | 33.04%
25-PC-42084 | Foxglove Built Environment Survey | In Progress | Time and material | Built Environment | Kathleen Cabrera | 1294200 | 344257.2 | 344257.2 | 847312.74 | 847312.74 | 0 | 296024.06 | 551288.68 | 551288.68 |  | 26.6% | 34.94%
25-PC-42097 | Tansy Flat Solar Data Recovery | In Progress | Fixed fee | Built Environment | Jenny Wilkinson | 179700 | 47800.2 | 36464.54 | 138548.7 | 138548.7 | 0 | 36854.88 | 101693.82 | 101693.82 |  | 26.6% | 26.6%
25-PC-42115 | Hawk Point Reservoir Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 110400 | 70181.28 | 70181.28 | 90660.48 | 90660.48 | 0 | 57630.35 | 33030.13 | 33030.13 |  | 63.6% | 63.57%
25-PC-42136 | Phase III: Granite Pass Mixed-Use Development Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 31700 | 19688.87 | 16599.28 | 23936.32 | 17555.9 | 6380.42 | 14865.84 | 9070.48 | 2690.06 |  | 62.1% | 62.11%
25-PC-42163 | Foxglove Historic Resources Evaluation | Final Reporting/Review | Time and material | Built Environment | Rickey Salas | 50700 | 38724.35 | 38724.35 | 34430.37 | 34430.37 | 0 | 27262.05 | 7168.32 | 7168.32 |  | 76.4% | 79.18%
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Cost Tracking on Closed Project | Time and material | Built Environment | Kathleen Cabrera | 17900 | 161.1 | 161.1 | 12066.39 | 12066.39 | 0 | 14332.43 | -2266.04 | -2266.04 |  | 0.9% | 118.8%
25-PC-42253 | On-Call: Plover Cove Substation Phase I Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 67000 | 47935 | 47935 | 45781.1 | 45781.1 | 0 | 27198.17 | 18582.93 | 18582.93 |  | 71.5% | 59.41%
25-PC-42282 | Dove Canyon Levee Repair - Phase I Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 33000 | 18668.1 | 18668.1 | 19255.5 | 19255.5 | 0 | 10892.49 | 8363.01 | 8363.01 |  | 56.6% | 56.57%
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 41200 | 26400.96 | 24020.13 | 29239.64 | 29239.64 | 0 | 18737.92 | 10501.72 | 10501.72 |  | 64.1% | 64.08%
25-PC-42323 | Millbrook Cultural Resources Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado | 79800 | 44791.74 | 44791.74 | 58357.74 | 58357.74 | 0 | 32754.67 | 25603.07 | 25603.07 |  | 56.1% | 56.13%
25-PC-42343 | Phase III: Coyote Springs Pipeline Phase II Testing | In Progress | Fixed fee | Paleontology | Travis Delgado | 6100 | 4126.04 | 4126.04 | 4038.38 | 3787.65 | 250.73 | 2731.5 | 1306.88 | 1056.15 |  | 67.6% | 67.64%
25-PC-42364 | Sparrow Hill Fiber Route - Phase I Survey | In Progress | Fixed fee | Paleontology | Travis Delgado | 594900 | 375917.31 | 375917.31 | 426353.2 | 400715.25 | 25637.95 | 269416.69 | 156936.51 | 131298.56 |  | 63.2% | 63.19%
25-PC-42399 | Task Order 7: Aspen Ridge Housing Development Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 683800 | 319061.08 | 298082.56 | 509225.86 | 509225.86 | 0 | 237582.18 | 271643.68 | 271643.68 |  | 46.7% | 46.66%
25-PC-42528 | Slate Ridge Park Improvements - Phase I Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 132000 | 36141.6 | 35894.94 | 93601.2 | 93601.2 | 0 | 25632.68 | 67968.52 | 67968.52 |  | 27.4% | 27.38%
25-PC-42601 | Lantern Bay Park Improvements - Cultural Resources Monitoring | In Progress | Time and material | Paleontology | Charlene Sparks | 302100 | 82510.1 | 75499.07 | 213521.46 | 177364.48 | 36156.98 | 47392.28 | 166129.18 | 129972.2 |  | 27.3% | 22.2%
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | In Progress | Time and material | Maritime | Kyle Maynard | 130300 | 127336.35 | 127336.35 | 95796.56 | 95796.56 | 0 | 79248.02 | 16548.54 | 16548.54 |  | 97.7% | 82.73%
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | In Progress | Time and material | Geospatial | Sylvia Callahan | 62000 | 54684.75 | 54684.75 | 44404.4 | 44404.4 | 0 | 44584.79 | -180.39 | -180.39 |  | 88.2% | 100.4%
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | In Progress | Fixed fee | Meridian Central | Seth Zavala | 128400 | 128400 | 128209.36 | 106315.2 | 106315.2 | 0 | 183432.15 | -77116.95 | -77116.95 |  | 100% | 172.5%
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | In Progress | Time and material | Meridian Central | Seth Zavala | 15700 | 15700 | 11349.21 | 10903.65 | 10903.65 | 0 | 59799.88 | -48896.23 | -48896.23 |  | 100% | 548.4%
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Clinton Solis | 715500 | 650818.8 | 650818.8 | 625275.45 | 625275.45 | 0 | 568777.84 | 56497.61 | 56497.61 |  | 91% | 90.96%
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Seth Zavala | 551800 | 551800 | 551800 | 378424.44 | 378424.44 | 0 | 405626.36 | -27201.92 | -27201.92 |  | 100% | 107.2%
25-PC-43566 | Copper Flats Solar - Phase II Testing | In Progress | Fixed fee | Meridian Central | Mathew Shea | 114200 | 114200 | 114200 | 73887.4 | 73887.4 | 0 | 129635.19 | -55747.79 | -55747.79 |  | 100% | 175.4%
25-PC-43590 | Task Order 37: Elk Meadow Harbor Dredging Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Meridian Central | Mathew Shea | 24800 | 16978.08 | 16978.08 | 16619.52 | 14642.64 | 1976.88 | 11377.59 | 5241.93 | 3265.05 |  | 68.5% | 68.46%
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 52800 | 52800 | 52800 | 37979.04 | 37979.04 | 0 | 37986.88 | -7.84 | -7.84 |  | 100% | 100%
25-PC-43639 | Windmill Flat Battery Storage Curation | Final Reporting/Review | Fixed fee | Meridian Southwest | Harold Chaney | 137000 | 129355.4 | 125548.66 | 91502.3 | 91502.3 | 0 | 86400.21 | 5102.09 | 5102.09 |  | 94.4% | 94.42%
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Lab/Curation | Fixed fee | Meridian Southwest | Reginald Kerr | 92800 | 75743.36 | 62987.9 | 78211.84 | 78211.84 | 0 | 63834.31 | 14377.53 | 14377.53 |  | 81.6% | 81.62%
25-PC-43771 | Granite Pass Reservoir - Built Environment Survey | Lab/Curation | Time and material | Meridian Southwest | Lynn Tran | 31500 | 12067.5 | 11449.4 | 20147.4 | 20147.4 | 0 | 8962.54 | 11184.86 | 11184.86 |  | 38.3% | 44.48%
25-PC-43844 | Slate Ridge Battery Storage Class III Survey | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 50700 | 30840.81 | 26909.4 | 33907.9 | 26087.6 | 7820.3 | 20626.7 | 13281.2 | 5460.9 |  | 60.8% | 60.83%
25-PC-43853 | Heron Marsh Battery Storage - Phase II Testing | Final Reporting/Review | Time and material | Meridian Southwest | Alan Gay | 162800 | 111170 | 97439.72 | 115799.64 | 115799.64 | 0 | 68136.28 | 47663.36 | 47663.36 |  | 68.3% | 58.84%
25-PC-43863 | Yarrow Point Cultural Resources Assessment | In Progress | Fixed fee | Meridian Southwest | Reginald Kerr | 545200 | 72184.48 | 65888.75 | 450335.2 | 450335.2 | 0 | 59625.96 | 390709.24 | 390709.24 |  | 13.2% | 13.24%
25-PC-43932 | Blue Heron Built Environment Survey | In Progress | Time and material | NH Gulf (USD) | Susan Wilkins | 35900 | 22556.3 | 22030.07 | 24656.25 | 18135 | 6521.25 | 13902.3 | 10753.95 | 4232.7 |  | 62.8% | 56.38%
25-PC-43944 | Elk Meadow Data Recovery | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 74800 | 26741 | 26741 | 60460.84 | 60460.84 | 0 | 21611.75 | 38849.09 | 38849.09 |  | 35.7% | 35.75%
25-PC-43966 | Silver Lake Rail Siding - Cultural Resources Monitoring | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence | 47800 | 22217.44 | 18611.1 | 34547.14 | 30211.65 | 4335.49 | 16057.32 | 18489.82 | 14154.33 |  | 46.5% | 46.48%
25-PC-43993 | Timber Gap GIS Mapping | In Progress | Fixed fee | NH Gulf (USD) | Javier Rangel | 27900 | 18020.61 | 16750.76 | 19669.5 | 19669.5 | 0 | 12704.35 | 6965.15 | 6965.15 |  | 64.6% | 64.59%
25-PC-44046 | Kestrel Butte Section 106 Consultation | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 320300 | 320300 | 320300 | 220526.55 | 220526.55 | 0 | 276639.9 | -56113.35 | -56113.35 |  | 100% | 125.4%
25-PC-44140 | Stone Mill Archaeological Testing | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence | 149900 | 111000.95 | 92299.74 | 100298.09 | 100298.09 | 0 | 74266.59 | 26031.5 | 26031.5 |  | 74.1% | 74.05%
25-PC-44186 | Falcon Mesa Section 106 Consultation | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 537000 | 331866 | 331866 | 338148.9 | 338148.9 | 0 | 208989.93 | 129158.97 | 129158.97 |  | 61.8% | 61.8%
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | In Progress | Time and material | NH Gulf (USD) | Susan Wilkins | 31100 | 31100 | 30922.86 | 17934.14 | 13115.76 | 4818.38 | 29471.61 | -11537.47 | -16355.85 |  | 100% | 164.3%
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 97000 | 86766.5 | 81265.84 | 71004 | 71004 | 0 | 63511.55 | 7492.45 | 7492.45 |  | 89.4% | 89.45%
26-PC-30057 | Sparrow Hill Environmental Review Support | In Progress | Time and material | Big Sky | Brendan Melton | 197500 | 29231 | 6162.02 | 144017 | 144017 | 0 | 19087.96 | 124929.04 | 124929.04 |  | 14.8% | 13.25%
26-PC-30065 | Granite Pass Water Main - Cultural Resources Assessment | In Progress | Fixed fee | Big Sky | Javier Estrada | 132100 | 6829.57 | 1070.14 | 104411.84 | 104411.84 | 0 | 5393.44 | 99018.4 | 99018.4 |  | 5.2% | 5.17%
26-PC-30123 | Eagle Bend Park Improvements - Class III Survey | In Progress | Fixed fee | Big Sky | Bob Frye | 277200 | 28440.72 | 14881.05 | 210477.96 | 210477.96 | 0 | 21593.07 | 188884.89 | 188884.89 |  | 10.3% | 10.26%
26-PC-30139 | Quail Run Canal Lining Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 239600 | 7810.96 | 7810.96 | 198628.4 | 198628.4 | 0 | 6482.54 | 192145.86 | 192145.86 |  | 3.3% | 3.26%
26-PC-30180 | Willow Springs Architectural History Survey | Lab/Curation | Fixed fee | Big Sky | Carl Barajas | 115700 | 0 | 0 | 79798.29 | 79798.29 | 0 | 0 | 79798.29 | 79798.29 |  | 0% | 0%
26-PC-30203 | Millbrook Pipeline Data Recovery | In Progress | Fixed fee | Big Sky | Carl Barajas | 134800 | 1995.04 | 699.65 | 102421.04 | 102421.04 | 0 | 1513.57 | 100907.47 | 100907.47 |  | 1.5% | 1.48%
26-PC-30211 | Copper Flats Paleontological Monitoring | Lab/Curation | Fixed fee | Big Sky | Javier Estrada | 736100 | 0 | 0 | 498404.34 | 394730.97 | 103673.37 | 0 | 498404.34 | 394730.97 |  | 0% | 0%
26-PC-30273 | Task Order 40: Copper Flats Trail Class III Survey | Lab/Curation | Fixed fee | Big Sky | Bob Frye | 77200 | 5705.08 | 5614.64 | 53522.76 | 53522.76 | 0 | 3952.93 | 49569.83 | 49569.83 |  | 7.4% | 7.39%
26-PC-30287 | Task Order 40: Maple Fork Solar Historic Resources Evaluation | In Progress | Fixed fee | Big Sky | Javier Estrada | 10100 | 5081.31 | 5081.31 | 6193.32 | 6193.32 | 0 | 3115.89 | 3077.43 | 3077.43 |  | 50.3% | 50.31%
26-PC-30329 | Hackberry Bend Rail Siding Built Environment Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 483600 | 26646.36 | 8003.6 | 313904.76 | 313904.76 | 0 | 17308.9 | 296595.86 | 296595.86 |  | 5.5% | 5.51%
26-PC-30338 | On-Call: Saltgrass Mixed-Use Development Phase II Testing | Lab/Curation | Fixed fee | Big Sky | Brendan Melton | 268300 | 0 | 0 | 189811.91 | 146074.38 | 43737.53 | 0 | 189811.91 | 146074.38 |  | 0% | 0%
26-PC-30349 | Phase I: Copper Flats Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Big Sky | Brendan Melton | 184200 | 19654.14 | 13718.45 | 105343.98 | 105343.98 | 0 | 11245.27 | 94098.71 | 94098.71 |  | 10.7% | 10.67%
26-PC-30351 | Wildrye Architectural History Survey | In Progress | Fixed fee | Big Sky | Bob Frye | 393800 | 74073.78 | 55570.79 | 262900.88 | 262900.88 | 0 | 49439.04 | 213461.84 | 213461.84 |  | 18.8% | 18.81%
26-PC-30457 | Wren Hollow Transmission Line - Data Recovery | Final Reporting/Review | Fixed fee | Big Sky | Bob Frye | 719800 | 119126.9 | 119126.9 | 547191.96 | 547191.96 | 0 | 90552.84 | 456639.12 | 456639.12 |  | 16.6% | 16.55%
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | In Progress | Fixed fee | Big Sky | Brendan Melton | 19900 | 19900 | 19400.11 | 14258.19 | 12707.2 | 1550.99 | 17540.74 | -3282.55 | -4833.54 |  | 100% | 123%
26-PC-30528 | Plover Cove School Campus Architectural History Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 112900 | 48501.84 | 42933.24 | 74017.24 | 74017.24 | 0 | 31796.1 | 42221.14 | 42221.14 |  | 43% | 42.96%
26-PC-30602 | On-Call: Hawk Point Solar Cultural Resources Assessment | In Progress | Time and material | Bluegrass | Kiara Gillespie | 211900 | 7021.5 | 0 | 152752.98 | 141361.45 | 11391.53 | 4049.91 | 148703.07 | 137311.54 |  | 3.3% | 2.65%
26-PC-30815 | Juniper Wash Water Main Archaeological Testing | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 236000 | 2525.2 | 0 | 177731.6 | 177731.6 | 0 | 1903.26 | 175828.34 | 175828.34 |  | 1.1% | 1.07%
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 209800 | 0 | 0 | 135467.86 | 135467.86 | 0 | 134699.95 | 767.91 | 767.91 |  | 0% | 99.43%
26-PC-30945 | Wildrye Reservoir Architectural History Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 179500 | 36079.5 | 21907.94 | 120265 | 120265 | 0 | 24171.47 | 96093.53 | 96093.53 |  | 20.1% | 20.1%
26-PC-30967 | Timber Gap Pipeline - Built Environment Survey | Final Reporting/Review | Time and material | Bluegrass | Alice Galloway | 173400 | 76649.75 | 63893.73 | 108877.86 | 108877.86 | 0 | 48040.32 | 60837.54 | 60837.54 |  | 44.2% | 44.12%
26-PC-31037 | Cedar Hollow Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 168500 | 30296.3 | 19740.62 | 131345.75 | 131345.75 | 0 | 23622.42 | 107723.33 | 107723.33 |  | 18% | 17.98%
26-PC-31174 | Task Order 33: Tamarack Housing Development Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 4400 | 0 | 0 | 2984.25 | 2426.55 | 557.7 | 2714.71 | 269.54 | -288.16 |  | 0% | 90.97%
26-PC-31238 | Task Order 27: Wren Hollow Bridge Replacement Built Environment Survey | In Progress | Time and material | Cascade | Preston Duarte | 832700 | 45671.75 | 20679.55 | 533060.12 | 386912.7 | 146147.42 | 26558.57 | 506501.55 | 360354.13 |  | 5.5% | 4.98%
26-PC-31316 | Sparrow Hill Trail Architectural History Survey | Final Reporting/Review | Fixed fee | Cascade | Cassidy Gay | 148200 | 0 | 0 | 109860.66 | 109860.66 | 0 | 0 | 109860.66 | 109860.66 |  | 0% | 0%
26-PC-31448 | Foxglove Class III Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 25800 | 990.72 | 414.2 | 20065.31 | 16136.4 | 3928.91 | 770.98 | 19294.33 | 15365.42 |  | 3.8% | 3.84%
26-PC-31484 | Maple Fork Wastewater Plant Data Recovery | In Progress | Fixed fee | Cascade | Jean Cooke | 31800 | 4445.64 | 3558.73 | 23427.06 | 23427.06 | 0 | 3275.77 | 20151.29 | 20151.29 |  | 14% | 13.98%
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | In Progress | Fixed fee | Cascade | Donald Lutz | 44400 | 20916.84 | 20724.04 | 34032.6 | 34032.6 | 0 | 16033.26 | 17999.34 | 17999.34 |  | 47.1% | 47.11%
26-PC-31568 | Sea Oat Housing Development - Section 106 Consultation | In Progress | Fixed fee | Cascade | Donald Lutz | 229100 | 7949.77 | 1245.08 | 148678.02 | 119301 | 29377.02 | 5152.38 | 143525.64 | 114148.62 |  | 3.5% | 3.47%
26-PC-31648 | Rushgrass Draw Solar Data Recovery | In Progress | Fixed fee | Cascade | Jeff Spence | 388400 | 73640.64 | 44771.47 | 288425.84 | 288425.84 | 0 | 54694.47 | 233731.37 | 233731.37 |  | 19% | 18.96%
26-PC-31678 | Heron Marsh Wind Farm Phase I Survey | In Progress | Fixed fee | Cascade | Preston Duarte | 892800 | 161150.4 | 131167.35 | 641923.2 | 641923.2 | 0 | 115882.12 | 526041.08 | 526041.08 |  | 18% | 18.05%
26-PC-31716 | Saltgrass Wind Farm Data Recovery | In Progress | Fixed fee | Cascade | Donald Lutz | 13300 | 130.34 | 0 | 9413.74 | 9413.74 | 0 | 92.22 | 9321.52 | 9321.52 |  | 1% | 0.98%
26-PC-31802 | Bramble Creek Environmental Review Support | Lab/Curation | Fixed fee | Cascade | Jean Cooke | 53700 | 24718.11 | 22740.25 | 41655.09 | 41655.09 | 0 | 19175.38 | 22479.71 | 22479.71 |  | 46% | 46.03%
26-PC-31830 | Ember Valley Archaeological Testing | In Progress | Fixed fee | Cascade | Cassidy Gay | 86700 | 1560.6 | 0 | 59425.39 | 54460.35 | 4965.04 | 1070.38 | 58355.01 | 53389.97 |  | 1.8% | 1.8%
26-PC-31872 | Sumac Ridge Water Main Archaeological Testing | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 63800 | 12402.72 | 9390.09 | 45642.52 | 45642.52 | 0 | 8874.85 | 36767.67 | 36767.67 |  | 19.4% | 19.44%
26-PC-31881 | Fern Valley Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 125300 | 0 | 0 | 94955.6 | 80579.84 | 14375.76 | 0 | 94955.6 | 80579.84 |  | 0% | 0%
26-PC-32047 | On-Call: Sumac Ridge Mine Expansion Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox | 73200 | 12473.28 | 4293.84 | 51825.6 | 51825.6 | 0 | 8831.67 | 42993.93 | 42993.93 |  | 17% | 17.04%
26-PC-32069 | Task Order 25: Heron Marsh Wind Farm Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 844700 | 38687.26 | 32362.69 | 646026.56 | 646026.56 | 0 | 29618.9 | 616407.66 | 616407.66 |  | 4.6% | 4.58%
26-PC-32094 | Maple Fork Trail - Phase II Testing | In Progress | Time and material | Chesapeake | Bryan Mann | 19000 | 721.5 | 721.5 | 11274.6 | 11274.6 | 0 | 494.92 | 10779.68 | 10779.68 |  | 3.8% | 4.39%
26-PC-32322 | Foxglove Fiber Route - Curation | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 317500 | 7112 | 4464.87 | 244665.5 | 244665.5 | 0 | 5476.66 | 239188.84 | 239188.84 |  | 2.2% | 2.24%
26-PC-32369 | Twin Buttes Water Main - Phase I Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox | 730600 | 25278.76 | 19314.47 | 470798.64 | 470798.64 | 0 | 16303.4 | 454495.24 | 454495.24 |  | 3.5% | 3.46%
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann | 13700 | 13700 | 13641.82 | 9522.87 | 9522.87 | 0 | 21427.62 | -11904.75 | -11904.75 |  | 100% | 225%
26-PC-32442 | Sumac Ridge Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 53400 | 8538.66 | 6311.21 | 33316.26 | 33316.26 | 0 | 5328.47 | 27987.79 | 27987.79 |  | 16% | 15.99%
26-PC-32556 | Maple Fork Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 45700 | 7705.02 | 5584.85 | 32259.63 | 32259.63 | 0 | 5439.59 | 26820.04 | 26820.04 |  | 16.9% | 16.86%
26-PC-32563 | On-Call: Creosote Draw Substation Phase I Survey | In Progress | Fixed fee | Chesapeake | Bryan Mann | 534900 | 98261.13 | 92818.97 | 344315.13 | 344315.13 | 0 | 63247.77 | 281067.36 | 281067.36 |  | 18.4% | 18.37%
26-PC-32594 | On-Call: Tamarack Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 94400 | 28556 | 15739.52 | 71536.32 | 71536.32 | 0 | 21640.12 | 49896.2 | 49896.2 |  | 30.2% | 30.25%
26-PC-32707 | On-Call: Creosote Draw Transmission Line Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 327400 | 71635.12 | 56726.26 | 229376.44 | 229376.44 | 0 | 50182.56 | 179193.88 | 179193.88 |  | 21.9% | 21.88%
26-PC-32711 | Creosote Draw Phase I Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 62100 | 7532.73 | 5182.85 | 44997.66 | 44997.66 | 0 | 5460.14 | 39537.52 | 39537.52 |  | 12.1% | 12.13%
26-PC-32725 | Willow Springs Wind Farm - GIS Mapping | Final Reporting/Review | Fixed fee | Chesapeake | Bryan Mann | 26300 | 7066.81 | 3157.11 | 18699.3 | 18699.3 | 0 | 5025.08 | 13674.22 | 13674.22 |  | 26.9% | 26.87%
26-PC-32727 | North Fork Mine Expansion - Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Chesapeake | Alexandria Wilkinson | 70100 | 57594.16 | 57594.16 | 47310.49 | 47310.49 | 0 | 38868.52 | 8441.97 | 8441.97 |  | 82.2% | 82.16%
26-PC-32773 | Oak Terrace Paleontological Monitoring | In Progress | Fixed fee | Front Range | Mindy Galvan | 48100 | 5228.47 | 479.24 | 32496.36 | 32496.36 | 0 | 3531.57 | 28964.79 | 28964.79 |  | 10.9% | 10.87%
26-PC-32985 | Pine Hollow Built Environment Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 106500 | 30959.55 | 21349.92 | 89214.38 | 75741.38 | 13473 | 25933.59 | 63280.79 | 49807.79 |  | 29.1% | 29.07%
26-PC-33017 | Redbud Battery Storage - Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Mindy Galvan | 588600 | 142970.94 | 142970.94 | 441413.1 | 336449.96 | 104963.14 | 107200.4 | 334212.7 | 229249.56 |  | 24.3% | 24.29%
26-PC-33127 | Fern Valley Phase I Survey | In Progress | Time and material | Front Range | Kimberly Daugherty | 179500 | 4609.25 | 0 | 119968.02 | 92441.25 | 27526.77 | 3126.71 | 116841.31 | 89314.54 |  | 2.6% | 2.61%
26-PC-33162 | Phase III: Yarrow Point Airport Apron GIS Mapping | In Progress | Time and material | Front Range | Dean Velazquez | 81900 | 0 | 0 | 55036.8 | 55036.8 | 0 | 0 | 55036.8 | 55036.8 |  | 0% | 0%
26-PC-33276 | Quail Run Housing Development Archaeological Testing | In Progress | Time and material | Front Range | Jeremy Tran | 64200 | 9830.25 | 9224.25 | 42609.54 | 42609.54 | 0 | 6623.64 | 35985.9 | 35985.9 |  | 15.3% | 15.54%
26-PC-33588 | Fern Valley Trail - Cultural Resources Assessment | Lab/Curation | Time and material | Front Range | Joanna Herrera | 207400 | 21809.25 | 18916.47 | 141868.32 | 122263.6 | 19604.72 | 14499.72 | 127368.6 | 107763.88 |  | 10.5% | 10.22%
26-PC-33684 | On-Call: Juniper Wash Airport Apron Paleontological Monitoring | Final Reporting/Review | Time and material | Front Range | Kimberly Daugherty | 24000 | 0 | 0 | 17450.4 | 17450.4 | 0 | 0 | 17450.4 | 17450.4 |  | 0% | 0%
26-PC-33705 | Twin Buttes Phase I Survey | In Progress | Fixed fee | Great Lakes | Karl Valenzuela | 211200 | 40001.28 | 23070.09 | 166784.64 | 166784.64 | 0 | 31592.64 | 135192 | 135192 |  | 18.9% | 18.94%
26-PC-33743 | Raven Rock Canal Lining Architectural History Survey | In Progress | Fixed fee | Great Lakes | Brendan Padilla | 111800 | 46821.84 | 43850.11 | 75766.86 | 75766.86 | 0 | 31734.61 | 44032.25 | 44032.25 |  | 41.9% | 41.88%
26-PC-33834 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 204800 | 16793.6 | 8858.46 | 158052.15 | 136321.79 | 21730.36 | 12966.76 | 145085.39 | 123355.03 |  | 8.2% | 8.2%
26-PC-33896 | Maple Fork Trail Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 69800 | 6191.26 | 0 | 48734.36 | 48734.36 | 0 | 4323.5 | 44410.86 | 44410.86 |  | 8.9% | 8.87%
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 76400 | 76400 | 70250.02 | 53087.85 | 46646.64 | 6441.21 | 53650.35 | -562.5 | -7003.71 |  | 100% | 101.1%
26-PC-34114 | Granite Pass Canal Lining - Section 106 Consultation | In Progress | Time and material | Great Lakes | Brendan Padilla | 216500 | 2603.5 | 0 | 145812.75 | 145812.75 | 0 | 1371.67 | 144441.08 | 144441.08 |  | 1.2% | 0.94%
26-PC-34198 | Tansy Flat Pipeline - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Brendan Padilla | 65600 | 15665.5 | 15665.5 | 47297.6 | 47297.6 | 0 | 8630.43 | 38667.17 | 38667.17 |  | 23.9% | 18.25%
26-PC-34297 | Badger Hollow Historic Resources Evaluation | In Progress | Fixed fee | Great Lakes | Reginald Koch | 41700 | 0 | 0 | 29306.76 | 29306.76 | 0 | 0 | 29306.76 | 29306.76 |  | 0% | 0%
26-PC-34336 | Pine Hollow Solar Architectural History Survey | In Progress | Fixed fee | Great Lakes | Robin Mercado | 56500 | 6966.45 | 6427.12 | 40414.45 | 40414.45 | 0 | 4983.79 | 35430.66 | 35430.66 |  | 12.3% | 12.33%
26-PC-34394 | Ember Valley Battery Storage Maritime Remote Sensing Survey | In Progress | Time and material | Great Lakes | Angelica Cervantes | 134200 | 0 | 0 | 94370.11 | 80628.03 | 13742.08 | 0 | 94370.11 | 80628.03 |  | 0% | 0%
26-PC-34400 | Wren Hollow Curation | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 34200 | 478.8 | 250.49 | 23833.56 | 20735.65 | 3097.91 | 333.31 | 23500.25 | 20402.34 |  | 1.4% | 1.4%
26-PC-34487 | Quail Run Airport Apron - Phase I Survey | In Progress | Time and material | Great Lakes | Jeff Pugh | 488600 | 87171 | 45799.81 | 348176.36 | 348176.36 | 0 | 55843.39 | 292332.97 | 292332.97 |  | 17.8% | 16.04%
26-PC-34552 | Blue Heron Mine Expansion Phase I Survey | Lab/Curation | Fixed fee | Great Lakes | Geoffrey Fernandez | 245500 | 0 | 0 | 205115.25 | 205115.25 | 0 | 0 | 205115.25 | 205115.25 |  | 0% | 0%
26-PC-34602 | Phase III: Sandpiper Park Improvements Historic Resources Evaluation | In Progress | Fixed fee | Great Lakes | Brendan Padilla | 36800 | 12063.04 | 8728.01 | 26501.12 | 21328.5 | 5172.62 | 8686.82 | 17814.3 | 12641.68 |  | 32.8% | 32.78%
26-PC-34725 | Redbud Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Kathleen Galvan | 107600 | 2108.96 | 0 | 89211.16 | 89211.16 | 0 | 1751.96 | 87459.2 | 87459.2 |  | 2% | 1.96%
26-PC-34757 | Kestrel Butte Data Recovery | In Progress | Time and material | Great Lakes | Angelica Cervantes | 43800 | 13612 | 0 | 30230.76 | 30230.76 | 0 | 9482.37 | 20748.39 | 20748.39 |  | 31.1% | 31.37%
26-PC-34906 | Cedar Hollow Harbor Dredging - Curation | In Progress | Fixed fee | Gulf Coast | Sean Jennings | 81100 | 13032.77 | 5085.03 | 60821.43 | 44369.15 | 16452.28 | 9774.22 | 51047.21 | 34594.93 |  | 16.1% | 16.07%
26-PC-34982 | Sandpiper Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 10600 | 10600 | 7692.83 | 7895.94 | 7895.94 | 0 | 10265.05 | -2369.11 | -2369.11 |  | 100% | 130%
26-PC-35056 | Yarrow Point Cell Tower - Section 106 Consultation | Lab/Curation | Fixed fee | Gulf Coast West | Sean Jennings | 92800 | 39356.48 | 36581.7 | 78555.2 | 78555.2 | 0 | 33318.32 | 45236.88 | 45236.88 |  | 42.4% | 42.41%
26-PC-35063 | Meadowlark School Campus - Phase I Survey | Final Reporting/Review | Fixed fee | Gulf Coast East | Bernard Erickson | 112100 | 38629.66 | 33240.76 | 70129.76 | 70129.76 | 0 | 24165.68 | 45964.08 | 45964.08 |  | 34.5% | 34.46%
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 29600 | 29600 | 22003.12 | 19287.36 | 19287.36 | 0 | 26315.99 | -7028.63 | -7028.63 |  | 100% | 136.4%
26-PC-35193 | Heron Marsh Reservoir - Phase II Testing | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 102600 | 34299.18 | 23396.44 | 74022.89 | 54115.25 | 19907.64 | 24742.94 | 49279.95 | 29372.31 |  | 33.4% | 33.43%
26-PC-35381 | Badger Hollow Mine Expansion Archaeological Testing | In Progress | Fixed fee | High Desert | Bridget Maddox | 77800 | 3796.64 | 0 | 51064.93 | 45374 | 5690.93 | 2491.45 | 48573.48 | 42882.55 |  | 4.9% | 4.88%
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 68900 | 17872.66 | 8290.81 | 53679.99 | 53679.99 | 0 | 13926.1 | 39753.89 | 39753.89 |  | 25.9% | 25.94%
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | High Desert | Jody Wang | 26300 | 26300 | 26300 | 19575.09 | 19575.09 | 0 | 22787.95 | -3212.86 | -3212.86 |  | 100% | 116.4%
26-PC-36110 | Blue Heron Canal Lining - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox | 776100 | 25300.86 | 19809.49 | 567018.66 | 567018.66 | 0 | 18501.22 | 548517.44 | 548517.44 |  | 3.3% | 3.26%
26-PC-36416 | Task Order 2: Thistle Down Wind Farm Archaeological Testing | Lab/Curation | Fixed fee | Island | Maurice Dodson | 589600 | 138379.12 | 107428.63 | 462173.13 | 351925 | 110248.13 | 108468.91 | 353704.22 | 243456.09 |  | 23.5% | 23.47%
26-PC-36537 | Yarrow Point Park Improvements Built Environment Survey | In Progress | Fixed fee | Island | Becky Velazquez | 125300 | 14835.52 | 11712.39 | 86482.06 | 86482.06 | 0 | 10238.63 | 76243.43 | 76243.43 |  | 11.8% | 11.84%
26-PC-36581 | Harbor View Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Briana Melton | 127600 | 20033.2 | 14822.86 | 76674.84 | 76674.84 | 0 | 12040.19 | 64634.65 | 64634.65 |  | 15.7% | 15.7%
26-PC-36749 | Windmill Flat Water Main - Cultural Resources Assessment | In Progress | Fixed fee | Lakeshore | Lucas Benson | 199000 | 62207.4 | 52417.72 | 173567.8 | 173567.8 | 0 | 54260.12 | 119307.68 | 119307.68 |  | 31.3% | 31.26%
26-PC-36802 | Thistle Down Canal Lining - Cultural Resources Assessment | Final Reporting/Review | Time and material | Hill Country | Gail Meza | 71600 | 0 | 0 | 52303.8 | 52303.8 | 0 | 0 | 52303.8 | 52303.8 |  | 0% | 0%
26-PC-36828 | Phase III: Rushgrass Draw Canal Lining GIS Mapping | In Progress | Time and material | Hill Country | Gail Meza | 28100 | 476 | 306.42 | 19006.84 | 19006.84 | 0 | 293.71 | 18713.13 | 18713.13 |  | 1.7% | 1.55%
26-PC-36861 | North Fork Park Improvements - Cultural Resources Assessment | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 463900 | 0 | 0 | 337255.3 | 337255.3 | 0 | 0 | 337255.3 | 337255.3 |  | 0% | 0%
26-PC-36944 | Copper Flats Levee Repair - Data Recovery | Final Reporting/Review | Fixed fee | Hill Country | Marcus Shea | 102000 | 1938 | 0 | 68921.4 | 68921.4 | 0 | 1306.35 | 67615.05 | 67615.05 |  | 1.9% | 1.9%
26-PC-36945 | Hawk Point Fiber Route - Maritime Remote Sensing Survey | In Progress | Fixed fee | Hill Country | Gail Meza | 496500 | 111464.25 | 86114.9 | 329824.95 | 329824.95 | 0 | 74051.4 | 255773.55 | 255773.55 |  | 22.5% | 22.45%
26-PC-37024 | Hackberry Bend Mine Expansion - Maritime Remote Sensing Survey | In Progress | Fixed fee | Hill Country | Danielle Villanueva | 78900 | 3424.26 | 1334.47 | 63394.72 | 59087.34 | 4307.38 | 2752.6 | 60642.12 | 56334.74 |  | 4.3% | 4.34%
26-PC-37089 | Rushgrass Draw GIS Mapping | In Progress | Time and material | Hill Country | Gail Meza | 28900 | 500 | 500 | 19054.14 | 14854.2 | 4199.94 | 293.29 | 18760.85 | 14560.91 |  | 1.7% | 1.54%
26-PC-37136 | Yarrow Point Housing Development - Section 106 Consultation | In Progress | Fixed fee | Hill Country | Marcus Shea | 153700 | 37287.62 | 34247.17 | 109797.26 | 86150.47 | 23646.79 | 26631.99 | 83165.27 | 59518.48 |  | 24.3% | 24.26%
26-PC-37138 | Granite Pass Canal Lining - Environmental Review Support | Final Reporting/Review | Time and material | Hill Country | Gail Meza | 315800 | 23165.25 | 18782.57 | 223705.16 | 164829.33 | 58875.83 | 16101.29 | 207603.87 | 148728.04 |  | 7.3% | 7.2%
26-PC-37139 | Goldfinch Reservoir Environmental Review Support | In Progress | Time and material | Hill Country | Theresa Fernandez | 1070500 | 28754.75 | 5909.97 | 734587.52 | 579542.04 | 155045.48 | 16574.77 | 718012.75 | 562967.27 |  | 2.7% | 2.26%
26-PC-37196 | Sea Oat Built Environment Survey | In Progress | Fixed fee | Hill Country | Suzanne Mcmillan | 26900 | 0 | 0 | 22881.14 | 22881.14 | 0 | 0 | 22881.14 | 22881.14 |  | 0% | 0%
26-PC-37204 | On-Call: Saltgrass Housing Development Built Environment Survey | In Progress | Time and material | Hill Country | Gail Meza | 201900 | 45291.25 | 40732.36 | 145630.47 | 145630.47 | 0 | 28002.37 | 117628.1 | 117628.1 |  | 22.4% | 19.23%
26-PC-37271 | Maple Fork Wind Farm Built Environment Survey | In Progress | Time and material | Hill Country | Gail Meza | 879900 | 97121.25 | 43147.91 | 587259.92 | 482467.22 | 104792.7 | 64523.24 | 522736.68 | 417943.98 |  | 11% | 10.99%
26-PC-37317 | Hackberry Bend Environmental Review Support | In Progress | Time and material | Hill Country | Danielle Villanueva | 348700 | 8417.25 | 7620.57 | 224737.15 | 224737.15 | 0 | 5446.26 | 219290.89 | 219290.89 |  | 2.4% | 2.42%
26-PC-37329 | Stone Mill Battery Storage Built Environment Survey | Final Reporting/Review | Fixed fee | Hill Country | Glen Delacruz | 32600 | 1541.98 | 0 | 25463.86 | 25463.86 | 0 | 1204.09 | 24259.77 | 24259.77 |  | 4.7% | 4.73%
26-PC-37543 | Pebble Beach Road Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Maria Parrish | 330200 | 86941.66 | 70894.07 | 218394.28 | 218394.28 | 0 | 57512.7 | 160881.58 | 160881.58 |  | 26.3% | 26.33%
26-PC-37559 | Badger Hollow Paleontological Monitoring | In Progress | Time and material | Piedmont | Jody Chung | 44300 | 25525.5 | 14719.89 | 28024.18 | 28024.18 | 0 | 15789.25 | 12234.93 | 12234.93 |  | 57.6% | 56.34%
26-PC-37671 | Harbor View Mixed-Use Development Architectural History Survey | In Progress | Time and material | Piedmont | Annette Vaughan | 145900 | 9234.5 | 9234.5 | 92486.01 | 92486.01 | 0 | 6017.12 | 86468.89 | 86468.89 |  | 6.3% | 6.51%
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Piedmont | Jody Chung | 40300 | 12948.39 | 5350.23 | 32312.54 | 32312.54 | 0 | 10383.09 | 21929.45 | 21929.45 |  | 32.1% | 32.13%
26-PC-37709 | Sage Flat Phase I Survey | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 31500 | 0 | 0 | 21725.55 | 21725.55 | 0 | 0 | 21725.55 | 21725.55 |  | 0% | 0%
26-PC-37788 | Sumac Ridge Cultural Resources Assessment | In Progress | Fixed fee | Piedmont | Jody Chung | 1112800 | 11461.84 | 9177.58 | 826476.56 | 826476.56 | 0 | 8474.81 | 818001.75 | 818001.75 |  | 1% | 1.03%
26-PC-37965 | Redbud Cultural Resources Assessment | In Progress | Time and material | Piedmont | Annette Vaughan | 55400 | 0 | 0 | 34625 | 34625 | 0 | 0 | 34625 | 34625 |  | 0% | 0%
26-PC-38025 | Granite Pass Section 106 Consultation | In Progress | Time and material | Prairie | Sherry Lloyd | 92200 | 5568 | 3646.6 | 64982.56 | 64982.56 | 0 | 3659.46 | 61323.1 | 61323.1 |  | 6% | 5.63%
26-PC-38153 | Harbor View Reservoir Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd | 109100 | 39625.12 | 32176.23 | 89766.43 | 69277.74 | 20488.69 | 32603.05 | 57163.38 | 36674.69 |  | 36.3% | 36.32%
26-PC-38215 | Phase I: Juniper Wash Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Prairie | Sherry Lloyd | 42800 | 6206 | 0 | 37664 | 37664 | 0 | 5460.72 | 32203.28 | 32203.28 |  | 14.5% | 14.5%
26-PC-38304 | Yarrow Point Cultural Resources Assessment | In Progress | Time and material | Prairie | Sherry Lloyd | 177100 | 0 | 0 | 125191.99 | 125191.99 | 0 | 0 | 125191.99 | 125191.99 |  | 0% | 0%
26-PC-38315 | Task Order 21: Larkspur Bridge Replacement Paleontological Monitoring | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd | 735000 | 36456 | 36456 | 578298 | 578298 | 0 | 28684.76 | 549613.24 | 549613.24 |  | 5% | 4.96%
26-PC-38367 | Stone Mill Architectural History Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 416500 | 7592.5 | 0 | 276097.85 | 276097.85 | 0 | 6041.59 | 270056.26 | 270056.26 |  | 1.8% | 2.19%
26-PC-38387 | Granite Pass Section 106 Consultation | In Progress | Time and material | Prairie | Sherry Lloyd | 182500 | 45632 | 42078.52 | 120358.75 | 120358.75 | 0 | 25501.8 | 94856.95 | 94856.95 |  | 25% | 21.19%
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 48300 | 36540 | 36349.08 | 32887.47 | 32887.47 | 0 | 23821.02 | 9066.45 | 9066.45 |  | 75.7% | 72.43%
26-PC-38624 | Juniper Wash Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Red Rock | Bruce Suarez | 77900 | 77900 | 77900 | 56578.77 | 56578.77 | 0 | 73552.4 | -16973.63 | -16973.63 |  | 100% | 130%
26-PC-38647 | Meadowlark Cultural Resources Assessment | In Progress | Time and material | Red Rock | Bruce Suarez | 793800 | 137660.5 | 88105.38 | 517795.74 | 517795.74 | 0 | 87463.44 | 430332.3 | 430332.3 |  | 17.3% | 16.89%
26-PC-38675 | On-Call: Lone Pine School Campus Data Recovery | Final Reporting/Review | Fixed fee | Red Rock | Jeanette Chung | 289700 | 57621.33 | 56063.64 | 228167.72 | 228167.72 | 0 | 45390.52 | 182777.2 | 182777.2 |  | 19.9% | 19.89%
26-PC-38709 | Timber Gap Airport Apron Phase I Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez | 14100 | 2340.6 | 2279.67 | 11415.36 | 11415.36 | 0 | 1894.55 | 9520.81 | 9520.81 |  | 16.6% | 16.6%
26-PC-38719 | Willow Springs Housing Development - Environmental Review Support | In Progress | Fixed fee | Red Rock | Javier Newman | 298600 | 1403.42 | 1359.45 | 193522.66 | 193522.66 | 0 | 909.85 | 192612.81 | 192612.81 |  | 0.5% | 0.47%
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 97700 | 53916.75 | 36551.12 | 60828.02 | 60828.02 | 0 | 33113.22 | 27714.8 | 27714.8 |  | 55.2% | 54.44%
26-PC-38924 | Wildrye Harbor Dredging - Architectural History Survey | In Progress | Time and material | Red Rock | Shelia Horne | 117200 | 40441 | 32708.78 | 83798 | 83798 | 0 | 27104.24 | 56693.76 | 56693.76 |  | 34.5% | 32.34%
26-PC-38943 | Task Order 34: Fern Valley Wastewater Plant Archaeological Testing | In Progress | Fixed fee | Red Rock | Marisa Odom | 129100 | 46630.92 | 31786.97 | 80272.12 | 59881.52 | 20390.6 | 28992.02 | 51280.1 | 30889.5 |  | 36.1% | 36.12%
26-PC-38966 | Task Order 12: Bramble Creek Battery Storage Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Bruce Suarez | 269400 | 0 | 0 | 193052.04 | 193052.04 | 0 | 0 | 193052.04 | 193052.04 |  | 0% | 0%
26-PC-38993 | Willow Springs Airport Apron - Section 106 Consultation | In Progress | Time and material | Red Rock | Lydia Cisneros | 201400 | 39428.5 | 32149.33 | 131514.2 | 131514.2 | 0 | 25643.17 | 105871.03 | 105871.03 |  | 19.6% | 19.5%
26-PC-39043 | Twin Buttes Reservoir - Archaeological Testing | In Progress | Fixed fee | Red Rock | Bruce Suarez | 123200 | 3412.64 | 0 | 96884.48 | 96884.48 | 0 | 2687.18 | 94197.3 | 94197.3 |  | 2.8% | 2.77%
26-PC-39165 | Pebble Beach Road Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre | 94300 | 34127.17 | 23110.34 | 63218.72 | 63218.72 | 0 | 22877.18 | 40341.54 | 40341.54 |  | 36.2% | 36.19%
26-PC-39390 | Juniper Wash Fiber Route Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Javier Newman | 59600 | 4249.48 | 2957.3 | 37810.24 | 37810.24 | 0 | 2695.33 | 35114.91 | 35114.91 |  | 7.1% | 7.13%
26-PC-39565 | On-Call: Aspen Ridge Battery Storage Maritime Remote Sensing Survey | In Progress | Time and material | Red Rock | Lydia Cisneros | 97600 | 3266.75 | 0 | 60541.28 | 60541.28 | 0 | 2175.89 | 58365.39 | 58365.39 |  | 3.3% | 3.59%
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Cost Tracking on Closed Project | Fixed fee | Red Rock | Tina Aguirre | 115900 | 115900 | 115900 | 86530.94 | 86530.94 | 0 | 99694.97 | -13164.03 | -13164.03 |  | 100% | 115.2%
26-PC-39778 | Thistle Down Battery Storage - Architectural History Survey | In Progress | Time and material | Red Rock | Marisa Odom | 35700 | 434.25 | 358.52 | 26613.7 | 20089.92 | 6523.78 | 266.4 | 26347.3 | 19823.52 |  | 1.2% | 1%
26-PC-39971 | Pebble Beach Road Environmental Review Support | Final Reporting/Review | Time and material | Red Rock | Marisa Odom | 114600 | 37757 | 19124.55 | 79406.34 | 79406.34 | 0 | 24091.48 | 55314.86 | 55314.86 |  | 32.9% | 30.34%
26-PC-40009 | Oak Terrace Harbor Dredging Curation | In Progress | Fixed fee | Red Rock | Shelia Horne | 63600 | 14303.64 | 11256.22 | 43349.76 | 43349.76 | 0 | 9747.86 | 33601.9 | 33601.9 |  | 22.5% | 22.49%
26-PC-40176 | On-Call: Twin Buttes Harbor Dredging Phase I Survey | Final Reporting/Review | Time and material | Sierra South | Louis Huff | 143600 | 17244 | 10419.78 | 93138.96 | 93138.96 | 0 | 10173.18 | 82965.78 | 82965.78 |  | 12% | 10.92%
26-PC-40296 | Twin Buttes Class III Survey | In Progress | Fixed fee | Sierra South | Donna Herring | 6400 | 800.64 | 718.05 | 4648.32 | 4648.32 | 0 | 581.47 | 4066.85 | 4066.85 |  | 12.5% | 12.51%
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 96900 | 73866.87 | 67549.3 | 68401.71 | 68401.71 | 0 | 52140.44 | 16261.27 | 16261.27 |  | 76.2% | 76.23%
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Final Reporting/Review | Fixed fee | Sierra | Louis Huff | 19200 | 10874.88 | 8434.14 | 14098.56 | 14098.56 | 0 | 7985.86 | 6112.7 | 6112.7 |  | 56.6% | 56.64%
26-PC-40361 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Donna Herring | 156300 | 45889.68 | 23822.64 | 102829.77 | 102829.77 | 0 | 30190.41 | 72639.36 | 72639.36 |  | 29.4% | 29.36%
26-PC-40384 | Maple Fork Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Sierra North | Donna Herring | 102900 | 31087.5 | 28996.93 | 62220.33 | 48730.76 | 13489.57 | 19741.77 | 42478.56 | 28988.99 |  | 30.2% | 31.73%
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Final Reporting/Review | Fixed fee | Sierra South | Donna Herring | 5900 | 5900 | 5708.22 | 4379.73 | 3449.54 | 930.19 | 8243.77 | -3864.04 | -4794.23 |  | 100% | 188.2%
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | In Progress | Fixed fee | Sierra North | Donna Herring | 7500 | 3924.75 | 3800.92 | 5493 | 5493 | 0 | 2874.63 | 2618.37 | 2618.37 |  | 52.3% | 52.33%
26-PC-40590 | Wildrye Highway Widening - Environmental Review Support | Final Reporting/Review | Fixed fee | Sierra North | Angelica Poole | 1002000 | 46192.2 | 13853.73 | 809716.2 | 809716.2 | 0 | 37294.92 | 772421.28 | 772421.28 |  | 4.6% | 4.61%
26-PC-40690 | Pine Hollow Wastewater Plant - Paleontological Monitoring | In Progress | Time and material | Coastal Bend | Duane Ballard | 252500 | 64316 | 62811.43 | 171094 | 171094 | 0 | 41284.76 | 129809.24 | 129809.24 |  | 25.5% | 24.13%
26-PC-40760 | Foxglove Canal Lining - Archaeological Testing | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 77500 | 17840.5 | 15286.04 | 63893.46 | 46765.44 | 17128.02 | 14706.47 | 49186.99 | 32058.97 |  | 23% | 23.02%
26-PC-40860 | Fern Valley Solar Data Recovery | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 181300 | 18329.43 | 7996.8 | 145148.78 | 145148.78 | 0 | 14678.37 | 130470.41 | 130470.41 |  | 10.1% | 10.11%
26-PC-40966 | Harbor View Trail - GIS Mapping | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 225100 | 19403.62 | 7736.15 | 146315 | 146315 | 0 | 12605.23 | 133709.77 | 133709.77 |  | 8.6% | 8.62%
26-PC-40983 | Falcon Mesa Data Recovery | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 7200 | 3980.88 | 3351.63 | 6217.91 | 4906.72 | 1311.19 | 3437.93 | 2779.98 | 1468.79 |  | 55.3% | 55.29%
26-PC-41048 | Task Order 33: Granite Pass Battery Storage Phase I Survey | In Progress | Time and material | Coastal Bend | Jared Choi | 458200 | 16741.75 | 0 | 315149.96 | 315149.96 | 0 | 12012.81 | 303137.15 | 303137.15 |  | 3.7% | 3.81%
26-PC-41176 | Wildrye Park Improvements - Environmental Review Support | Final Reporting/Review | Fixed fee | Coastal Bend | Steve Rubio | 109400 | 24374.32 | 18564.22 | 81568.64 | 81568.64 | 0 | 18177.41 | 63391.23 | 63391.23 |  | 22.3% | 22.28%
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 41400 | 41400 | 41400 | 27278.33 | 19877.52 | 7400.81 | 30232.83 | -2954.5 | -10355.31 |  | 100% | 110.8%
26-PC-41222 | Sage Flat Transmission Line - Cultural Resources Assessment | In Progress | Time and material | Coastal Bend | Alexis Nixon | 26000 | 0 | 0 | 18522.4 | 18522.4 | 0 | 0 | 18522.4 | 18522.4 |  | 0% | 0%
26-PC-41230 | Phase I: Slate Ridge Battery Storage Phase I Survey | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 46400 | 213.44 | 0 | 35769.76 | 35769.76 | 0 | 163.97 | 35605.79 | 35605.79 |  | 0.5% | 0.46%
26-PC-41334 | Fern Valley Housing Development - Data Recovery | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 154000 | 66420.2 | 57642.94 | 99198.32 | 88810.04 | 10388.28 | 42784.72 | 56413.6 | 46025.32 |  | 43.1% | 43.13%
26-PC-41394 | Maple Fork Bridge Replacement - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Duane Ballard | 15700 | 14005.97 | 14005.97 | 11219.22 | 11219.22 | 0 | 10008.86 | 1210.36 | 1210.36 |  | 89.2% | 89.21%
26-PC-41406 | Task Order 27: Dove Canyon Battery Storage Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 381600 | 84638.88 | 68563.81 | 257192.06 | 187803.42 | 69388.64 | 57039.75 | 200152.31 | 130763.67 |  | 22.2% | 22.18%
26-PC-41425 | Pebble Beach Road GIS Mapping | In Progress | Time and material | Coastal Bend | Steve Rubio | 268700 | 7336.25 | 0 | 183253.4 | 183253.4 | 0 | 4858.46 | 178394.94 | 178394.94 |  | 2.7% | 2.65%
26-PC-41446 | Stone Mill Levee Repair Archaeological Testing | In Progress | Time and material | Coastal Bend | Jared Choi | 263000 | 0 | 0 | 172291.3 | 172291.3 | 0 | 0 | 172291.3 | 172291.3 |  | 0% | 0%
26-PC-41466 | Millbrook Cultural Resources Assessment | Lab/Curation | Time and material | Coastal Bend | Alexis Nixon | 857800 | 161726 | 161726 | 634085.76 | 634085.76 | 0 | 112101.34 | 521984.42 | 521984.42 |  | 18.9% | 17.68%
26-PC-41661 | Ember Valley Levee Repair Data Recovery | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 4800 | 273.6 | 0 | 4028.16 | 4028.16 | 0 | 229.67 | 3798.49 | 3798.49 |  | 5.7% | 5.7%
26-PC-41667 | Kestrel Butte Transmission Line - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Duane Ballard | 131800 | 31644.25 | 0 | 98659.54 | 84109.2 | 14550.34 | 20603.2 | 78056.34 | 63506 |  | 24% | 20.88%
26-PC-41707 | Quail Run Solar Environmental Review Support | Final Reporting/Review | Fixed fee | Built Environment | Jenny Wilkinson | 27000 | 0 | 0 | 20358 | 20358 | 0 | 0 | 20358 | 20358 |  | 0% | 0%
26-PC-41721 | Thistle Down Curation | In Progress | Time and material | Built Environment | Melody Holloway | 67700 | 18897 | 14602.77 | 46692.69 | 46692.69 | 0 | 11695.38 | 34997.31 | 34997.31 |  | 27.9% | 25.05%
26-PC-41776 | Sandpiper Battery Storage GIS Mapping | Lab/Curation | Time and material | Built Environment | Jenny Wilkinson | 457800 | 13941.25 | 10696.05 | 310067.94 | 310067.94 | 0 | 9328.98 | 300738.96 | 300738.96 |  | 3% | 3.01%
26-PC-41803 | Copper Flats Section 106 Consultation | Lab/Curation | Fixed fee | Built Environment | Jenny Wilkinson | 554800 | 24744.08 | 12700.08 | 392021.68 | 392021.68 | 0 | 17473.69 | 374547.99 | 374547.99 |  | 4.5% | 4.46%
26-PC-41821 | Blue Heron School Campus Curation | In Progress | Time and material | Built Environment | Jenny Wilkinson | 152400 | 21666.25 | 17950.71 | 98770.44 | 98770.44 | 0 | 14677.9 | 84092.54 | 84092.54 |  | 14.2% | 14.86%
26-PC-41863 | Silver Lake Canal Lining Cultural Resources Assessment | In Progress | Fixed fee | Built Environment | Jenny Wilkinson | 322500 | 5482.5 | 4435.19 | 224460 | 224460 | 0 | 3820.7 | 220639.3 | 220639.3 |  | 1.7% | 1.7%
26-PC-41884 | Foxglove Trail - Curation | In Progress | Time and material | Built Environment | Melody Holloway | 1099300 | 35169 | 10304.17 | 743556.08 | 550430.95 | 193125.13 | 23657.5 | 719898.58 | 526773.45 |  | 3.2% | 3.18%
26-PC-41918 | Plover Cove Data Recovery | In Progress | Fixed fee | Built Environment | Melody Holloway | 121100 | 7193.34 | 6098.08 | 81064.34 | 81064.34 | 0 | 4818.93 | 76245.41 | 76245.41 |  | 5.9% | 5.94%
26-PC-41947 | Juniper Wash Trail - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Built Environment | Rickey Salas | 64400 | 13994.12 | 7216.25 | 52073.84 | 52073.84 | 0 | 11317.02 | 40756.82 | 40756.82 |  | 21.7% | 21.73%
26-PC-41961 | Eagle Bend Data Recovery | In Progress | Fixed fee | Built Environment | Melody Holloway | 463200 | 82681.2 | 82681.2 | 369077.76 | 369077.76 | 0 | 65880.19 | 303197.57 | 303197.57 |  | 17.8% | 17.85%
26-PC-41970 | North Fork School Campus - Cultural Resources Monitoring | Final Reporting/Review | Time and material | Built Environment | Melody Holloway | 292200 | 93249.75 | 93249.75 | 212405.41 | 172247.04 | 40158.37 | 60262.35 | 152143.06 | 111984.69 |  | 31.9% | 28.37%
26-PC-42007 | On-Call: Wren Hollow Mixed-Use Development Architectural History Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 341700 | 9157.56 | 3090.16 | 215752.53 | 179922 | 35830.53 | 5771.8 | 209980.73 | 174150.2 |  | 2.7% | 2.68%
26-PC-42008 | Millbrook GIS Mapping | In Progress | Time and material | Built Environment | Kathleen Cabrera | 79400 | 0 | 0 | 54793.94 | 54793.94 | 0 | 0 | 54793.94 | 54793.94 |  | 0% | 0%
26-PC-42023 | North Fork Historic Resources Evaluation | In Progress | Fixed fee | Built Environment | Jenny Wilkinson | 157000 | 5950.3 | 4162.76 | 111815.4 | 111815.4 | 0 | 4240.16 | 107575.24 | 107575.24 |  | 3.8% | 3.79%
26-PC-42040 | Millbrook Phase II Testing | In Progress | Time and material | Built Environment | Jenny Wilkinson | 129700 | 2576.5 | 0 | 89350.33 | 89350.33 | 0 | 1568.76 | 87781.57 | 87781.57 |  | 2% | 1.76%
26-PC-42099 | Fern Valley Substation Cultural Resources Monitoring | In Progress | Time and material | Built Environment | Jesse Maynard | 661800 | 91692.75 | 77653.03 | 445656.12 | 445656.12 | 0 | 55459.17 | 390196.95 | 390196.95 |  | 13.9% | 12.44%
26-PC-42108 | Sumac Ridge Mixed-Use Development Curation | In Progress | Fixed fee | Built Environment | Kathleen Cabrera | 1000600 | 25215.12 | 18500.77 | 761256.48 | 761256.48 | 0 | 19160.02 | 742096.46 | 742096.46 |  | 2.5% | 2.52%
26-PC-42293 | Eagle Bend Water Main Phase II Testing | In Progress | Fixed fee | Paleontology | Charlene Sparks | 100800 | 12045.6 | 10106.03 | 88704 | 88704 | 0 | 10598.7 | 78105.3 | 78105.3 |  | 12% | 11.95%
26-PC-42427 | Phase II: Stone Mill Mine Expansion Section 106 Consultation | In Progress | Time and material | Paleontology | Travis Delgado | 926100 | 129604.5 | 112787.18 | 644195.16 | 644195.16 | 0 | 91235.31 | 552959.85 | 552959.85 |  | 14% | 14.16%
26-PC-42510 | Lantern Bay Data Recovery | In Progress | Time and material | Paleontology | Charlene Sparks | 1304200 | 103072.75 | 94566.63 | 949196.76 | 949196.76 | 0 | 67175.36 | 882021.4 | 882021.4 |  | 7.9% | 7.08%
26-PC-42598 | Badger Hollow Phase II Testing | In Progress | Time and material | Paleontology | Travis Delgado | 99400 | 9383 | 3001.68 | 74509.83 | 55811.54 | 18698.29 | 5754.31 | 68755.52 | 50057.23 |  | 9.4% | 7.72%
26-PC-42679 | Aspen Ridge Phase I Survey | Final Reporting/Review | Fixed fee | Maritime | Kyle Maynard | 214600 | 49594.06 | 34653.96 | 144103.9 | 144103.9 | 0 | 33305.96 | 110797.94 | 110797.94 |  | 23.1% | 23.11%
26-PC-42734 | On-Call: Lantern Bay Reservoir Architectural History Survey | In Progress | Time and material | Maritime | Rita Ayala | 77500 | 11190.25 | 8590.58 | 51615 | 51615 | 0 | 6901.55 | 44713.45 | 44713.45 |  | 14.4% | 13.37%
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | In Progress | Fixed fee | Maritime | Kyle Maynard | 347000 | 187345.3 | 161464.03 | 256363.6 | 256363.6 | 0 | 138412.07 | 117951.53 | 117951.53 |  | 54% | 53.99%
26-PC-42832 | Task Order 39: Saltgrass Levee Repair Class III Survey | Final Reporting/Review | Time and material | Maritime | Rita Ayala | 343600 | 7476.25 | 1546.18 | 243097 | 243097 | 0 | 4412.27 | 238684.73 | 238684.73 |  | 2.2% | 1.82%
26-PC-42838 | Phase III: Oak Terrace Pipeline Phase II Testing | In Progress | Fixed fee | Maritime | Rita Ayala | 47400 | 19865.34 | 19865.34 | 31824.36 | 31824.36 | 0 | 13337.82 | 18486.54 | 18486.54 |  | 41.9% | 41.91%
26-PC-42880 | Phase I: Quail Run Harbor Dredging Curation | In Progress | Fixed fee | Maritime | Rita Ayala | 107200 | 2004.64 | 0 | 87904 | 87904 | 0 | 1644.55 | 86259.45 | 86259.45 |  | 1.9% | 1.87%
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Final Reporting/Review | Time and material | Geospatial | Sylvia Callahan | 107600 | 107600 | 99262.67 | 77827.43 | 68885.46 | 8941.97 | 75050.79 | 2776.64 | -6165.33 |  | 100% | 96.43%
26-PC-43086 | On-Call: Silver Lake Transmission Line Archaeological Testing | In Progress | Time and material | Geospatial | Sylvia Callahan | 2118800 | 0 | 0 | 1431461.28 | 1431461.28 | 0 | 0 | 1431461.28 | 1431461.28 |  | 0% | 0%
26-PC-43132 | Phase III: Ember Valley Highway Widening Phase II Testing | Lab/Curation | Fixed fee | Geospatial | Priscilla Pennington | 140700 | 33824.28 | 30040.9 | 112756.98 | 112756.98 | 0 | 27102.82 | 85654.16 | 85654.16 |  | 24% | 24.04%
26-PC-43136 | Phase III: Harbor View Highway Widening Section 106 Consultation | In Progress | Time and material | Geospatial | Priscilla Pennington | 3831800 | 62087.5 | 32267.66 | 2564623.74 | 2564623.74 | 0 | 43973.89 | 2520649.85 | 2520649.85 |  | 1.6% | 1.71%
26-PC-43168 | Task Order 35: Aspen Ridge Transmission Line Architectural History Survey | Final Reporting/Review | Fixed fee | Geospatial | Sylvia Callahan | 281200 | 52893.72 | 47865.66 | 164749.65 | 145548.52 | 19201.13 | 30992.8 | 133756.85 | 114555.72 |  | 18.8% | 18.81%
26-PC-43307 | Phase III: Aspen Ridge Mine Expansion Maritime Remote Sensing Survey | In Progress | Time and material | Meridian Central | Raymond Hensley | 239600 | 63937.25 | 63937.25 | 189451.72 | 189451.72 | 0 | 47026.78 | 142424.94 | 142424.94 |  | 26.7% | 24.82%
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | In Progress | Fixed fee | Meridian Central | Mathew Shea | 41200 | 13328.2 | 12381.05 | 27426.84 | 27426.84 | 0 | 8871.32 | 18555.52 | 18555.52 |  | 32.4% | 32.35%
26-PC-43364 | Goldfinch Class III Survey | In Progress | Fixed fee | Meridian Central | Raymond Hensley | 24900 | 7305.66 | 6226.98 | 16624.07 | 15142.4 | 1481.67 | 4877.27 | 11746.8 | 10265.13 |  | 29.3% | 29.34%
26-PC-43527 | Maple Fork School Campus Phase II Testing | In Progress | Time and material | Meridian Central | Raymond Hensley | 333700 | 43556 | 38125.32 | 224680.21 | 224680.21 | 0 | 30018.6 | 194661.61 | 194661.61 |  | 13.1% | 13.36%
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | In Progress | Fixed fee | Meridian Central | Clinton Solis | 136900 | 123374.28 | 122899.93 | 105043.37 | 105043.37 | 0 | 94665.18 | 10378.19 | 10378.19 |  | 90.1% | 90.12%
26-PC-43575 | On-Call: Fern Valley Substation Data Recovery | Lab/Curation | Fixed fee | Meridian Central | Mathew Shea | 113100 | 65439.66 | 60535.58 | 87831.71 | 66733.2 | 21098.51 | 50820.34 | 37011.37 | 15912.86 |  | 57.9% | 57.86%
26-PC-43695 | Willow Springs Maritime Remote Sensing Survey | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 104700 | 14658 | 6026.36 | 73750.68 | 73750.68 | 0 | 10328.77 | 63421.91 | 63421.91 |  | 14% | 14%
26-PC-43731 | Task Order 32: Dove Canyon Transmission Line Paleontological Monitoring | In Progress | Time and material | Meridian Southwest | Alan Gay | 17700 | 0 | 0 | 12905.07 | 12905.07 | 0 | 0 | 12905.07 | 12905.07 |  | 0% | 0%
26-PC-43762 | Hawk Point Substation Paleontological Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran | 17500 | 0 | 0 | 15400 | 15400 | 0 | 0 | 15400 | 15400 |  | 0% | 0%
26-PC-43818 | Plover Cove Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Meridian Southwest | Lynn Tran | 277600 | 2914.8 | 0 | 226882.48 | 226882.48 | 0 | 2372.65 | 224509.83 | 224509.83 |  | 1.1% | 1.05%
26-PC-43874 | Oak Terrace Cell Tower - Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Justin Mejia | 72100 | 0 | 0 | 51991.31 | 51991.31 | 0 | 0 | 51991.31 | 51991.31 |  | 0% | 0%
26-PC-43961 | On-Call: Sparrow Hill Fiber Route Architectural History Survey | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 264600 | 63980.28 | 43786.53 | 211627.08 | 211627.08 | 0 | 51174.81 | 160452.27 | 160452.27 |  | 24.2% | 24.18%
26-PC-43963 | On-Call: Foxglove Trail Data Recovery | In Progress | Fixed fee | NH Gulf (USD) | Javier Rangel | 532600 | 85961.64 | 69961.68 | 335058.66 | 335058.66 | 0 | 54094.4 | 280964.26 | 280964.26 |  | 16.1% | 16.14%
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | In Progress | Time and material | NH Gulf (USD) | Justin Mejia | 220800 | 114316.5 | 90899.25 | 146699.52 | 146699.52 | 0 | 71602.23 | 75097.29 | 75097.29 |  | 51.8% | 48.81%
26-PC-43991 | Saltgrass Water Main - Archaeological Testing | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence | 22500 | 2542.5 | 0 | 13335.87 | 10433.28 | 2902.59 | 1506.49 | 11829.38 | 8926.79 |  | 11.3% | 11.3%
26-PC-44007 | Goldfinch Battery Storage Architectural History Survey | In Progress | Time and material | NH Gulf (USD) | Randy Cantu | 226900 | 9613.5 | 9613.5 | 149799.38 | 149799.38 | 0 | 5790.41 | 144008.97 | 144008.97 |  | 4.2% | 3.87%
26-PC-44050 | On-Call: Hawk Point Canal Lining Archaeological Testing | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 670400 | 5765.44 | 0 | 477190.72 | 477190.72 | 0 | 4109.23 | 473081.49 | 473081.49 |  | 0.9% | 0.86%
26-PC-44072 | Oak Terrace Water Main GIS Mapping | In Progress | Fixed fee | NH Gulf (USD) | Susan Wilkins | 106200 | 24362.28 | 17299.16 | 79469.46 | 79469.46 | 0 | 18232.82 | 61236.64 | 61236.64 |  | 22.9% | 22.94%
26-PC-44201 | Plover Cove Section 106 Consultation | In Progress | Time and material | NH Gulf (USD) | Javier Rangel | 165400 | 33887 | 26968.15 | 115267.26 | 115267.26 | 0 | 20345.64 | 94921.62 | 94921.62 |  | 20.5% | 17.65%
26-PC-44256 | On-Call: Twin Buttes Rail Siding Environmental Review Support | In Progress | Fixed fee | NH Gulf (USD) | Susan Wilkins | 810700 | 196513.68 | 158671.83 | 574867.37 | 574867.37 | 0 | 139337.92 | 435529.45 | 435529.45 |  | 24.2% | 24.24%
26-PC-44277 | Phase I: Sea Oat Harbor Dredging Architectural History Survey | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence | 49100 | 16350.3 | 13268.94 | 39677.71 | 39677.71 | 0 | 13211.18 | 26466.53 | 26466.53 |  | 33.3% | 33.3%
26-PC-44290 | On-Call: Larkspur Park Improvements GIS Mapping | In Progress | Fixed fee | NH Gulf (USD) | Justin Mejia | 206100 | 23351.13 | 18312.84 | 160077.87 | 160077.87 | 0 | 18144.13 | 141933.74 | 141933.74 |  | 11.3% | 11.33%
26-PC-44302 | Dove Canyon Cell Tower - Built Environment Survey | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 90200 | 10436.14 | 0 | 67334.3 | 67334.3 | 0 | 7790 | 59544.3 | 59544.3 |  | 11.6% | 11.57%