## All Active Projects
Northstar Heritage, LLC
FP&A & QC Project Report
As of September 29, 2026
[6 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Total Budget | Total Budget Adjustment | Total Costs |  |  |  | Recognized %
[6 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Remaining Budget | Orig Budget Remaining |  | REV REC % | Budget Spent %
Project ID | Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Original Budget Remaining | teamwork Status | Actual | Summary
23-PC-30307 | Quail Run Wastewater Plant Cultural Resources Assessment | Transferred Entity | Fixed fee | Big Sky | Javier Estrada | 240100 | 157553.62 | 157553.62 | 136256.75 | 136256.75 | 0 | 89412.87 | 46843.88 | 46843.88 |  | 65.6% | 65.62%
23-PC-30372 | Phase I: Lone Pine Reservoir Architectural History Survey | In Progress | Time and material | Big Sky | Bob Frye | 27100 | 18428 | 18428 | 19864.3 | 19864.3 | 0 | 11402.28 | 8462.02 | 8462.02 |  | 68% | 57.4%
23-PC-30543 | Phase III: Riverbend Rail Siding Maritime Remote Sensing Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 320600 | 225766.52 | 225766.52 | 255628.66 | 192683.15 | 62945.51 | 180013.95 | 75614.71 | 12669.2 |  | 70.4% | 70.42%
23-PC-30644 | Phase II: Millbrook Wastewater Plant Data Recovery | In Progress | Time and material | Bluegrass | Alice Galloway | 108100 | 73508 | 73508 | 72102.7 | 72102.7 | 0 | 46653.03 | 25449.67 | 25449.67 |  | 68% | 64.7%
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | In Progress | Time and material | Bluegrass | Kiara Gillespie | 49800 | 33864 | 33864 | 34501.44 | 34501.44 | 0 | 28656.36 | 5845.08 | 5845.08 |  | 68% | 83.06%
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 86200 | 58616 | 58616 | 58650.48 | 58650.48 | 0 | 61318.15 | -2667.67 | -2667.67 |  | 68% | 104.6%
23-PC-31003 | Windmill Flat Environmental Review Support | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 19300 | 15445.79 | 15445.79 | 10568.68 | 10568.68 | 0 | 8458.51 | 2110.17 | 2110.17 |  | 80% | 80.03%
23-PC-31042 | Stone Mill Historic Resources Evaluation | In Progress | Time and material | Cascade | Donald Lutz | 299700 | 203796 | 203796 | 202896.9 | 202896.9 | 0 | 147919.88 | 54977.02 | 54977.02 |  | 68% | 72.9%
23-PC-31076 | Wildrye Rail Siding - Archaeological Testing | Final Reporting/Review | Time and material | Cascade | Cassidy Gay | 95100 | 64668 | 64668 | 65561.94 | 65561.94 | 0 | 41531.43 | 24030.51 | 24030.51 |  | 68% | 63.35%
23-PC-31344 | Timber Gap Battery Storage Archaeological Testing | In Progress | Fixed fee | Cascade | Cassidy Gay | 331600 | 194516.56 | 194516.56 | 264351.52 | 264351.52 | 0 | 155057.32 | 109294.2 | 109294.2 |  | 58.7% | 58.66%
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | In Progress | Time and material | Cascade | Donald Lutz | 255700 | 173876 | 173876 | 168225.03 | 168225.03 | 0 | 202903.45 | -34678.42 | -34678.42 |  | 68% | 120.6%
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | In Progress | Fixed fee | Cascade | Jeff Spence | 108000 | 76528.8 | 76528.8 | 82404 | 82404 | 0 | 58391.35 | 24012.65 | 24012.65 |  | 70.9% | 70.86%
23-PC-31765 | Saltgrass Phase I Survey | Final Reporting/Review | Fixed fee | Cascade | Jean Cooke | 32700 | 18707.67 | 18707.67 | 27114.84 | 27114.84 | 0 | 15513.28 | 11601.56 | 11601.56 |  | 57.2% | 57.21%
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | In Progress | Fixed fee | Cascade | Gene Nixon | 34800 | 34800 | 34800 | 28779.6 | 28779.6 | 0 | 31540.76 | -2761.16 | -2761.16 |  | 100% | 109.6%
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | In Progress | Fixed fee | Cascade | Jeff Spence | 460600 | 348674.2 | 348674.2 | 390957.28 | 390957.28 | 0 | 295973.9 | 94983.38 | 94983.38 |  | 75.7% | 75.7%
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Jeff Spence | 175300 | 175300 | 175300 | 93481.01 | 71376.84 | 22104.17 | 112759.17 | -19278.16 | -41382.33 |  | 100% | 120.6%
23-PC-32015 | Copper Flats Harbor Dredging - Class III Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 89300 | 40524.34 | 40524.34 | 65024.25 | 59234.48 | 5789.77 | 29508.22 | 35516.03 | 29726.26 |  | 45.4% | 45.38%
23-PC-32278 | Coyote Springs Highway Widening Paleontological Monitoring | Lab/Curation | Time and material | Chesapeake | Ian Maddox | 3500 | 2380 | 2380 | 2281.3 | 2281.3 | 0 | 1738.97 | 542.33 | 542.33 |  | 68% | 76.23%
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 149100 | 132892.83 | 132892.83 | 111109.32 | 111109.32 | 0 | 99032.78 | 12076.54 | 12076.54 |  | 89.1% | 89.13%
23-PC-32443 | Tamarack Battery Storage - Cultural Resources Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann | 152600 | 117078.5 | 117078.5 | 107415.14 | 107415.14 | 0 | 63511.77 | 43903.37 | 43903.37 |  | 76.7% | 59.13%
23-PC-32520 | Tamarack Battery Storage GIS Mapping | Lab/Curation | Time and material | Chesapeake | Ian Maddox | 1116300 | 759084 | 759084 | 767567.88 | 767567.88 | 0 | 601405.25 | 166162.63 | 166162.63 |  | 68% | 78.35%
23-PC-32635 | Rushgrass Draw Curation | Cost Tracking on Closed Project | Time and material | Chesapeake | Jason Oconnor | 36800 | 25024 | 25024 | 24644.96 | 24644.96 | 0 | 27323.95 | -2678.99 | -2678.99 |  | 68% | 110.9%
23-PC-33001 | Heron Marsh Environmental Review Support | In Progress | Time and material | Front Range | Dean Velazquez | 356400 | 242352 | 242352 | 221573.88 | 221573.88 | 0 | 127558.9 | 94014.98 | 94014.98 |  | 68% | 57.57%
23-PC-33070 | Meadowlark Curation | In Progress | Fixed fee | Front Range | Reginald Vargas | 55100 | 46377.67 | 46377.67 | 34299.75 | 34299.75 | 0 | 28871.53 | 5428.22 | 5428.22 |  | 84.2% | 84.17%
23-PC-33151 | Sandpiper Class III Survey | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 637100 | 540961.61 | 540961.61 | 497638.81 | 497638.81 | 0 | 422546.87 | 75091.94 | 75091.94 |  | 84.9% | 84.91%
23-PC-33471 | Sandpiper Park Improvements - Environmental Review Support | Lab/Curation | Time and material | Front Range | Devon Pitts | 113200 | 76976 | 76976 | 80813.48 | 80813.48 | 0 | 61581.06 | 19232.42 | 19232.42 |  | 68% | 76.2%
23-PC-33551 | Heron Marsh Airport Apron GIS Mapping | Final Reporting/Review | Time and material | Front Range | Reginald Vargas | 95400 | 64872 | 64872 | 62019.54 | 62019.54 | 0 | 47726 | 14293.54 | 14293.54 |  | 68% | 76.95%
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 21600 | 21600 | 21600 | 15245.28 | 15245.28 | 0 | 16551.79 | -1306.51 | -1306.51 |  | 100% | 108.6%
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | In Progress | Time and material | Great Lakes | Jeff Pugh | 300600 | 204408 | 204408 | 219257.64 | 219257.64 | 0 | 176674.59 | 42583.05 | 42583.05 |  | 68% | 80.58%
23-PC-33998 | Phase II: Granite Pass Reservoir Class III Survey | In Progress | Time and material | Great Lakes | Nathan Lambert | 238800 | 162384 | 162384 | 156891.6 | 156891.6 | 0 | 95556.7 | 61334.9 | 61334.9 |  | 68% | 60.91%
23-PC-34171 | Timber Gap Rail Siding - Built Environment Survey | In Progress | Time and material | Great Lakes | Jeff Pugh | 221100 | 150348 | 150348 | 154858.44 | 154858.44 | 0 | 75735.59 | 79122.85 | 79122.85 |  | 68% | 48.91%
23-PC-34229 | Creosote Draw Mixed-Use Development Paleontological Monitoring | In Progress | Time and material | Great Lakes | Jeff Pugh | 48800 | 33184 | 33184 | 34427.85 | 31880.18 | 2547.67 | 25157.23 | 9270.62 | 6722.95 |  | 68% | 73.07%
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | In Progress | Time and material | Great Lakes | Kathleen Galvan | 373100 | 253708 | 253708 | 247626.47 | 247626.47 | 0 | 184659.6 | 62966.87 | 62966.87 |  | 68% | 74.57%
23-PC-34403 | Plover Cove Built Environment Survey | In Progress | Time and material | Great Lakes | Kathleen Galvan | 46200 | 31416 | 31416 | 30187.08 | 30187.08 | 0 | 23628.2 | 6558.88 | 6558.88 |  | 68% | 78.27%
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes | 477000 | 347303.7 | 347303.7 | 333756.9 | 333756.9 | 0 | 243019.93 | 90736.97 | 90736.97 |  | 72.8% | 72.81%
23-PC-34473 | Aspen Ridge Cell Tower Phase I Survey | In Progress | Time and material | Great Lakes | Leonard Mejia | 52300 | 35564 | 35564 | 36353.73 | 36353.73 | 0 | 23508.92 | 12844.81 | 12844.81 |  | 68% | 64.67%
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Final Reporting/Review | Time and material | Great Lakes | Geoffrey Fernandez | 70000 | 47600 | 47600 | 50246 | 50246 | 0 | 45814.41 | 4431.59 | 4431.59 |  | 68% | 91.18%
23-PC-34522 | Foxglove GIS Mapping | In Progress | Time and material | Great Lakes | Brendan Padilla | 192200 | 130696 | 130696 | 131503.24 | 131503.24 | 0 | 75113.75 | 56389.49 | 56389.49 |  | 68% | 57.12%
23-PC-34745 | Slate Ridge Battery Storage Environmental Review Support | In Progress | Fixed fee | Great Lakes | Robin Mercado | 614200 | 408504.42 | 408504.42 | 440258.56 | 440258.56 | 0 | 292800.8 | 147457.76 | 147457.76 |  | 66.5% | 66.51%
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Sean Jennings | 46100 | 32472.84 | 32472.84 | 31721.41 | 31721.41 | 0 | 22343.25 | 9378.16 | 9378.16 |  | 70.4% | 70.44%
23-PC-34811 | Task Order 2: Saltgrass Airport Apron Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Gulf Coast West | Courtney Daugherty | 112600 | 92917.52 | 92917.52 | 80883.68 | 67188.42 | 13695.26 | 66744.54 | 14139.14 | 443.88 |  | 82.5% | 82.52%
23-PC-34826 | Task Order 13: Foxglove Canal Lining Cultural Resources Monitoring | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 168500 | 114580 | 114580 | 109642.95 | 109642.95 | 0 | 61763.3 | 47879.65 | 47879.65 |  | 68% | 56.33%
23-PC-34902 | Sumac Ridge Built Environment Survey | Final Reporting/Review | Time and material | Gulf Coast | Sean Jennings | 37000 | 25160 | 25160 | 26270 | 26270 | 0 | 17779.33 | 8490.67 | 8490.67 |  | 68% | 67.68%
23-PC-34939 | Maple Fork Maritime Remote Sensing Survey | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 145800 | 99144 | 99144 | 104172.04 | 89950 | 14222.04 | 74711.94 | 29460.1 | 15238.06 |  | 68% | 71.72%
23-PC-34947 | Aspen Ridge Cell Tower Architectural History Survey | In Progress | Fixed fee | Gulf Coast West | Wyatt Erickson | 285900 | 192753.78 | 192753.78 | 199615.38 | 199615.38 | 0 | 134588.76 | 65026.62 | 65026.62 |  | 67.4% | 67.42%
23-PC-35003 | Creosote Draw Archaeological Testing | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 187900 | 127772 | 127772 | 127170.72 | 127170.72 | 0 | 85671.58 | 41499.14 | 41499.14 |  | 68% | 67.37%
23-PC-35126 | Falcon Mesa Rail Siding Built Environment Survey | In Progress | Time and material | Gulf Coast West | Wyatt Erickson | 273100 | 185708 | 185708 | 197014.34 | 197014.34 | 0 | 105573.3 | 91441.04 | 91441.04 |  | 68% | 53.59%
23-PC-35176 | Plover Cove Mine Expansion Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Bernard Erickson | 74700 | 49496.22 | 49496.22 | 53388.09 | 53388.09 | 0 | 35373.34 | 18014.75 | 18014.75 |  | 66.3% | 66.26%
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | In Progress | Fixed fee | Gulf Coast East | Wyatt Erickson | 407900 | 303355.23 | 303355.23 | 321139.67 | 321139.67 | 0 | 238828.33 | 82311.34 | 82311.34 |  | 74.4% | 74.37%
23-PC-35425 | Yarrow Point Trail - GIS Mapping | Lab/Curation | Time and material | High Desert | Eileen Poole | 24000 | 16320 | 16320 | 15998.4 | 15998.4 | 0 | 13187.18 | 2811.22 | 2811.22 |  | 68% | 82.43%
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | In Progress | Time and material | High Desert | Jody Wang | 116200 | 79016 | 79016 | 87219.72 | 87219.72 | 0 | 78190.34 | 9029.38 | 9029.38 |  | 68% | 89.65%
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | In Progress | Fixed fee | High Desert | Eileen Poole | 11400 | 8681.1 | 8681.1 | 8206.86 | 8206.86 | 0 | 6249.46 | 1957.4 | 1957.4 |  | 76.2% | 76.15%
23-PC-35568 | Phase II: Coyote Springs Wind Farm Environmental Review Support | In Progress | Fixed fee | High Desert | Bridget Maddox | 253600 | 144374.48 | 144374.48 | 168365.04 | 168365.04 | 0 | 95853.64 | 72511.4 | 72511.4 |  | 56.9% | 56.93%
23-PC-35682 | Lantern Bay Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 290400 | 277361.04 | 277361.04 | 252938.4 | 252938.4 | 0 | 241578.4 | 11360 | 11360 |  | 95.5% | 95.51%
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 114600 | 104870.46 | 104870.46 | 77893.62 | 77893.62 | 0 | 71277.07 | 6616.55 | 6616.55 |  | 91.5% | 91.51%
23-PC-36385 | On-Call: Cedar Hollow Transmission Line Paleontological Monitoring | In Progress | Time and material | Island | Maurice Dodson | 392900 | 267172 | 267172 | 262008.61 | 207890.28 | 54118.33 | 185677.7 | 76330.91 | 22212.58 |  | 68% | 70.87%
23-PC-36422 | Hawk Point Phase I Survey | In Progress | Time and material | Island | Joan Mathis | 50700 | 34476 | 34476 | 36579.06 | 32790.93 | 3788.13 | 37409.59 | -830.53 | -4618.66 |  | 68% | 102.3%
23-PC-36530 | Lone Pine Architectural History Survey | In Progress | Time and material | Island | Joan Mathis | 141100 | 95948 | 95948 | 102823.29 | 89657.45 | 13165.84 | 97024.26 | 5799.03 | -7366.81 |  | 68% | 94.36%
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 201000 | 170226.9 | 170226.9 | 151513.8 | 151513.8 | 0 | 128322.24 | 23191.56 | 23191.56 |  | 84.7% | 84.69%
23-PC-36734 | Raven Rock Curation | In Progress | Fixed fee | Lakeshore | Terrence Gillespie | 38600 | 36284 | 36284 | 27753.4 | 27753.4 | 0 | 26089.14 | 1664.26 | 1664.26 |  | 94% | 94%
23-PC-36776 | On-Call: Twin Buttes Trail Phase I Survey | In Progress | Time and material | Hill Country | Danielle Villanueva | 457300 | 310964 | 310964 | 338564.86 | 268622.72 | 69942.14 | 214892.1 | 123672.76 | 53730.62 |  | 68% | 63.47%
23-PC-37105 | Foxglove Housing Development - Data Recovery | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 110800 | 82955.96 | 82955.96 | 80165.21 | 73023.16 | 7142.05 | 60019.34 | 20145.87 | 13003.82 |  | 74.9% | 74.87%
23-PC-37245 | Rushgrass Draw Wind Farm Archaeological Testing | In Progress | Fixed fee | Hill Country | Gail Meza | 425700 | 238392 | 238392 | 306248.58 | 306248.58 | 0 | 171495.1 | 134753.48 | 134753.48 |  | 56% | 56%
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | In Progress | Fixed fee | Piedmont - Inactive | Maria Parrish | 44500 | 31902.05 | 31902.05 | 35070.45 | 35070.45 | 0 | 25141.75 | 9928.7 | 9928.7 |  | 71.7% | 71.69%
23-PC-37590 | On-Call: Rushgrass Draw Water Main Environmental Review Support | In Progress | Fixed fee | PIEDMONT - INACTIVE | Annette Vaughan | 46500 | 28425.45 | 28425.45 | 36232.8 | 36232.8 | 0 | 22148.93 | 14083.87 | 14083.87 |  | 61.1% | 61.13%
23-PC-37763 | Bramble Creek School Campus - Environmental Review Support | In Progress | Time and material | PIEDMONT - INACTIVE | Megan Pineda | 35000 | 23800 | 23800 | 25056.5 | 25056.5 | 0 | 15144.42 | 9912.08 | 9912.08 |  | 68% | 60.44%
23-PC-38089 | Lone Pine Wastewater Plant - Phase I Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 110100 | 75132.24 | 75132.24 | 84001.75 | 72763.92 | 11237.83 | 57321.44 | 26680.31 | 15442.48 |  | 68.2% | 68.24%
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | In Progress | Time and material | Prairie | Sherry Lloyd | 128200 | 87176 | 87176 | 90073.32 | 90073.32 | 0 | 73724.08 | 16349.24 | 16349.24 |  | 68% | 81.85%
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 79800 | 57918.84 | 57918.84 | 53434.08 | 53434.08 | 0 | 38783.48 | 14650.6 | 14650.6 |  | 72.6% | 72.58%
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 67700 | 56556.58 | 56556.58 | 44688.77 | 44688.77 | 0 | 37332.05 | 7356.72 | 7356.72 |  | 83.5% | 83.54%
23-PC-38520 | On-Call: Larkspur Park Improvements Built Environment Survey | In Progress | Time and material | Red Rock | Marisa Odom | 148500 | 100980 | 100980 | 97074.45 | 97074.45 | 0 | 56211.48 | 40862.97 | 40862.97 |  | 68% | 57.91%
23-PC-38666 | Tamarack Paleontological Monitoring | In Progress | Fixed fee | Red Rock | Bruce Suarez | 390300 | 212479.32 | 212479.32 | 243898.47 | 243898.47 | 0 | 132781.77 | 111116.7 | 111116.7 |  | 54.4% | 54.44%
23-PC-38759 | Saltgrass Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Red Rock | Tina Aguirre | 52400 | 35632 | 35632 | 36847.68 | 36847.68 | 0 | 40372.44 | -3524.76 | -3524.76 |  | 68% | 109.6%
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | In Progress | Fixed fee | Red Rock | Tina Aguirre | 109400 | 86962.06 | 86962.06 | 83089.3 | 83089.3 | 0 | 66048.24 | 17041.06 | 17041.06 |  | 79.5% | 79.49%
23-PC-39063 | Task Order 21: Badger Hollow Substation Historic Resources Evaluation | Lab/Curation | Time and material | Red Rock | Lydia Cisneros | 24200 | 16456 | 16456 | 17235.24 | 17235.24 | 0 | 12296.83 | 4938.41 | 4938.41 |  | 68% | 71.35%
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | In Progress | Fixed fee | Red Rock | Jeanette Chung | 27800 | 20777.72 | 20777.72 | 18214.56 | 18214.56 | 0 | 13614.39 | 4600.17 | 4600.17 |  | 74.7% | 74.74%
23-PC-39323 | Silver Lake Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 550600 | 423136.1 | 423136.1 | 444994.92 | 444994.92 | 0 | 341994.21 | 103000.71 | 103000.71 |  | 76.8% | 76.85%
23-PC-39840 | Kestrel Butte Cell Tower - Curation | In Progress | Time and material | Red Rock | Bruce Suarez | 237700 | 164750.75 | 164750.75 | 173575 | 132634.88 | 40940.12 | 88754.16 | 84820.84 | 43880.72 |  | 69.3% | 51.13%
23-PC-39856 | Phase II: Thistle Down Transmission Line Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 91300 | 46718.21 | 46718.21 | 72285.79 | 62922.2 | 9363.59 | 36987.95 | 35297.84 | 25934.25 |  | 51.2% | 51.17%
23-PC-39857 | Copper Flats Highway Widening - Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez | 69000 | 40358.1 | 40358.1 | 58157.02 | 42210.52 | 15946.5 | 34016 | 24141.02 | 8194.52 |  | 58.5% | 58.49%
23-PC-40028 | Phase II: Sumac Ridge Mixed-Use Development Section 106 Consultation | In Progress | Fixed fee | Red Rock | Bruce Suarez | 100900 | 67905.7 | 67905.7 | 70256.67 | 70256.67 | 0 | 47284.49 | 22972.18 | 22972.18 |  | 67.3% | 67.3%
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | In Progress | Time and material | Red Rock | Javier Newman | 119500 | 103480.5 | 103480.5 | 80196.45 | 80196.45 | 0 | 70430.41 | 9766.04 | 9766.04 |  | 86.6% | 87.82%
23-PC-40150 | Juniper Wash Curation | In Progress | Time and material | Sierra North | Benjamin Mathis | 114700 | 90325.75 | 90325.75 | 73316.24 | 73316.24 | 0 | 47860.76 | 25455.48 | 25455.48 |  | 78.7% | 65.28%
23-PC-40387 | Copper Flats Trail Paleontological Monitoring | Lab/Curation | Fixed fee | Sierra North | Louis Huff | 145000 | 82244 | 82244 | 97266 | 97266 | 0 | 55173.29 | 42092.71 | 42092.71 |  | 56.7% | 56.72%
23-PC-40402 | Pebble Beach Road Architectural History Survey | In Progress | Fixed fee | Sierra North | Louis Huff | 411600 | 333190.2 | 333190.2 | 302937.6 | 302937.6 | 0 | 245232.54 | 57705.06 | 57705.06 |  | 80.9% | 80.95%
23-PC-40406 | Maple Fork Airport Apron Environmental Review Support | In Progress | Time and material | Sierra | Louis Huff | 60100 | 40868 | 40868 | 40631.14 | 34425.27 | 6205.87 | 33352.18 | 7278.96 | 1073.09 |  | 68% | 82.09%
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | In Progress | Fixed fee | Sierra South | Benjamin Mathis | 53900 | 38516.94 | 38516.94 | 40910.1 | 40910.1 | 0 | 29233.55 | 11676.55 | 11676.55 |  | 71.5% | 71.46%
23-PC-40493 | Phase III: Quail Run Rail Siding Phase I Survey | In Progress | Fixed fee | Sierra | Benjamin Mathis | 84700 | 53513.46 | 53513.46 | 57130.15 | 57130.15 | 0 | 36092.25 | 21037.9 | 21037.9 |  | 63.2% | 63.18%
23-PC-40519 | Windmill Flat Mixed-Use Development - Class III Survey | In Progress | Fixed fee | Sierra South | Donna Herring | 194700 | 140203.47 | 140203.47 | 157875.18 | 136847.52 | 21027.66 | 113693.31 | 44181.87 | 23154.21 |  | 72% | 72.01%
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Lab/Curation | Fixed fee | Sierra | Louis Huff | 76500 | 76500 | 76500 | 58746.94 | 55119.6 | 3627.34 | 63236.56 | -4489.62 | -8116.96 |  | 100% | 107.6%
23-PC-40627 | Ember Valley Solar - Phase I Survey | In Progress | Fixed fee | Sierra | Louis Huff | 71300 | 44163.22 | 44163.22 | 38273.84 | 38273.84 | 0 | 23707.44 | 14566.4 | 14566.4 |  | 61.9% | 61.94%
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | In Progress | Time and material | Coastal Bend | Steve Rubio | 56300 | 38284 | 38284 | 42714.81 | 42714.81 | 0 | 47948.89 | -5234.08 | -5234.08 |  | 68% | 112.2%
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 33100 | 24874.65 | 24874.65 | 29128 | 29128 | 0 | 21890.46 | 7237.54 | 7237.54 |  | 75.1% | 75.15%
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 349600 | 349600 | 349600 | 221087.04 | 221087.04 | 0 | 229204.35 | -8117.31 | -8117.31 |  | 100% | 103.7%
23-PC-41314 | Raven Rock Transmission Line - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 38800 | 28161.04 | 28161.04 | 29503.45 | 22168.08 | 7335.37 | 21412.36 | 8091.09 | 755.72 |  | 72.6% | 72.58%
23-PC-41378 | Thistle Down Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 170800 | 95511.36 | 95511.36 | 91151.1 | 67330.2 | 23820.9 | 50973.67 | 40177.43 | 16356.53 |  | 55.9% | 55.92%
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 132000 | 92584.8 | 92584.8 | 108108 | 108108 | 0 | 75830.35 | 32277.65 | 32277.65 |  | 70.1% | 70.14%
23-PC-41429 | Meadowlark Housing Development - Phase II Testing | In Progress | Time and material | Coastal Bend | Duane Ballard | 1924200 | 1308456 | 1308456 | 1334625.12 | 1334625.12 | 0 | 884955.35 | 449669.77 | 449669.77 |  | 68% | 66.31%
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Lab/Curation | Fixed fee | Coastal Bend | Alexis Nixon | 755000 | 705170 | 705170 | 444695 | 444695 | 0 | 415325.46 | 29369.54 | 29369.54 |  | 93.4% | 93.4%
23-PC-41613 | Tamarack School Campus Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 151900 | 128659.3 | 128659.3 | 105099.61 | 105099.61 | 0 | 89014.21 | 16085.4 | 16085.4 |  | 84.7% | 84.7%
23-PC-41802 | Plover Cove Paleontological Monitoring | In Progress | Fixed fee | Built Environment | Melody Holloway | 102400 | 67051.52 | 67051.52 | 66672.64 | 66672.64 | 0 | 43658.58 | 23014.06 | 23014.06 |  | 65.5% | 65.48%
23-PC-41827 | Task Order 9: Dove Canyon Bridge Replacement Section 106 Consultation | In Progress | Fixed fee | Built Environment | Rickey Salas | 646100 | 375771.76 | 375771.76 | 414881.21 | 355093.99 | 59787.22 | 241290.96 | 173590.25 | 113803.03 |  | 58.2% | 58.16%
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | In Progress | Time and material | Built Environment | Jesse Maynard | 18800 | 12784 | 12784 | 12705.04 | 12705.04 | 0 | 12736.47 | -31.43 | -31.43 |  | 68% | 100.2%
23-PC-41934 | Sea Oat Bridge Replacement - GIS Mapping | Final Reporting/Review | Fixed fee | Built Environment | Rickey Salas | 364700 | 208900.16 | 208900.16 | 228812.78 | 228812.78 | 0 | 131064.99 | 97747.79 | 97747.79 |  | 57.3% | 57.28%
23-PC-42154 | Task Order 25: Goldfinch School Campus Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Rickey Salas | 29200 | 19856 | 19856 | 20127.56 | 20127.56 | 0 | 12454.55 | 7673.01 | 7673.01 |  | 68% | 61.88%
23-PC-42237 | Foxglove Historic Resources Evaluation | In Progress | Time and material | Paleontology | Charlene Sparks | 82300 | 55964 | 55964 | 55519.51 | 46719.77 | 8799.74 | 30299.65 | 25219.86 | 16420.12 |  | 68% | 54.57%
23-PC-42377 | Sumac Ridge Curation | In Progress | Fixed fee | Paleontology | Travis Delgado | 68300 | 39088.09 | 39088.09 | 47215.79 | 47215.79 | 0 | 27022.26 | 20193.53 | 20193.53 |  | 57.2% | 57.23%
23-PC-42451 | Phase I: Oak Terrace Cell Tower Data Recovery | In Progress | Time and material | Paleontology | Travis Delgado | 101800 | 69224 | 69224 | 72208.06 | 64989 | 7219.06 | 49547.32 | 22660.74 | 15441.68 |  | 68% | 68.62%
23-PC-42771 | Redbud Housing Development GIS Mapping | In Progress | Fixed fee | Maritime | Kyle Maynard | 25200 | 19124.28 | 19124.28 | 18799.2 | 18799.2 | 0 | 14265.92 | 4533.28 | 4533.28 |  | 75.9% | 75.89%
23-PC-42907 | Heron Marsh Historic Resources Evaluation | In Progress | Fixed fee | Maritime | Rita Ayala | 1637200 | 1057303.76 | 1057303.76 | 977458.87 | 712768.92 | 264689.95 | 631212.64 | 346246.23 | 81556.28 |  | 64.6% | 64.58%
23-PC-42981 | Hawk Point Architectural History Survey | In Progress | Fixed fee | Maritime | Kyle Maynard | 175800 | 133203.66 | 133203.66 | 129494.28 | 129494.28 | 0 | 98123.54 | 31370.74 | 31370.74 |  | 75.8% | 75.77%
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | In Progress | Time and material | Maritime | Rita Ayala | 139700 | 94996 | 94996 | 93543.12 | 93543.12 | 0 | 67047.93 | 26495.19 | 26495.19 |  | 68% | 71.68%
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | In Progress | Fixed fee | Geospatial | Priscilla Pennington | 73300 | 66563.73 | 66563.73 | 53362.4 | 53362.4 | 0 | 48458.95 | 4903.45 | 4903.45 |  | 90.8% | 90.81%
23-PC-43209 | Sea Oat Harbor Dredging Curation | In Progress | Fixed fee | Meridian | Seth Zavala | 247500 | 137090.25 | 137090.25 | 178398 | 178398 | 0 | 98806.54 | 79591.46 | 79591.46 |  | 55.4% | 55.39%
23-PC-43238 | Thistle Down Fiber Route - Data Recovery | In Progress | Fixed fee | Meridian | Clinton Solis | 454300 | 283028.9 | 283028.9 | 287491.13 | 227977.2 | 59513.93 | 179098.38 | 108392.75 | 48878.82 |  | 62.3% | 62.3%
23-PC-43408 | Wildrye Solar - Built Environment Survey | In Progress | Time and material | Meridian | Mathew Shea | 176300 | 119884 | 119884 | 121964.34 | 121964.34 | 0 | 65842.99 | 56121.35 | 56121.35 |  | 68% | 53.99%
23-PC-43612 | Maple Fork Wind Farm Class III Survey | In Progress | Time and material | Meridian | Seth Zavala | 201800 | 137224 | 137224 | 135120.77 | 112489.92 | 22630.85 | 73233.08 | 61887.69 | 39256.84 |  | 68% | 54.2%
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran | 112600 | 91374.9 | 91374.9 | 77637.7 | 77637.7 | 0 | 63002.79 | 14634.91 | 14634.91 |  | 81.1% | 81.15%
23-PC-43829 | Task Order 34: Ember Valley Wastewater Plant Architectural History Survey | In Progress | Fixed fee | Meridian Southwest | Harold Chaney | 166500 | 100016.55 | 100016.55 | 125557.65 | 125557.65 | 0 | 75422.97 | 50134.68 | 50134.68 |  | 60.1% | 60.07%
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 93300 | 93300 | 90265.16 | 59544.06 | 59544.06 | 0 | 93708.96 | -34164.9 | -34164.9 |  | 100% | 157.4%
24-PC-30448 | Maple Fork Substation - Data Recovery | In Progress | Fixed fee | Big Sky | Bob Frye | 142600 | 97709.52 | 97709.52 | 105894.76 | 105894.76 | 0 | 72554.14 | 33340.62 | 33340.62 |  | 68.5% | 68.52%
24-PC-30509 | On-Call: Yarrow Point Mine Expansion Cultural Resources Monitoring | Lab/Curation | Fixed fee | Big Sky | Javier Estrada | 682700 | 417402.78 | 417402.78 | 517281.79 | 517281.79 | 0 | 316284.4 | 200997.39 | 200997.39 |  | 61.1% | 61.14%
24-PC-30620 | Task Order 31: Sumac Ridge Trail GIS Mapping | Lab/Curation | Fixed fee | Bluegrass | Kiara Gillespie | 104400 | 88729.56 | 88729.56 | 78268.68 | 78268.68 | 0 | 66519.65 | 11749.03 | 11749.03 |  | 85% | 84.99%
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 60600 | 60600 | 60600 | 45577.26 | 45577.26 | 0 | 50596.88 | -5019.62 | -5019.62 |  | 100% | 111%
24-PC-30751 | Windmill Flat Section 106 Consultation | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 90800 | 63314.84 | 63314.84 | 72034.09 | 57699.75 | 14334.34 | 50229.44 | 21804.65 | 7470.31 |  | 69.7% | 69.73%
24-PC-30850 | Tamarack Transmission Line - Data Recovery | Final Reporting/Review | Time and material | Bluegrass | Alice Galloway | 991800 | 674424 | 674424 | 689995.26 | 689995.26 | 0 | 423701.35 | 266293.91 | 266293.91 |  | 68% | 61.41%
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Cost Tracking on Closed Project | Time and material | Cascade | Preston Duarte | 94000 | 63920 | 63920 | 65640.2 | 65640.2 | 0 | 73270.02 | -7629.82 | -7629.82 |  | 68% | 111.6%
24-PC-31358 | Dove Canyon Archaeological Testing | Final Reporting/Review | Fixed fee | Cascade | Donald Lutz | 595100 | 572605.22 | 572605.22 | 484590.9 | 358002.83 | 126588.07 | 466249.95 | 18340.95 | -108247.12 |  | 96.2% | 96.22%
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Jean Cooke | 18200 | 13335.14 | 13335.14 | 12417.86 | 12417.86 | 0 | 9098.08 | 3319.78 | 3319.78 |  | 73.3% | 73.27%
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | In Progress | Time and material | Cascade | Gene Nixon | 18300 | 12444 | 12444 | 11931.6 | 11931.6 | 0 | 9112.04 | 2819.56 | 2819.56 |  | 68% | 76.37%
24-PC-31503 | North Fork Wind Farm Curation | Lab/Curation | Time and material | Cascade | Preston Duarte | 129900 | 88332 | 88332 | 87825.39 | 87825.39 | 0 | 98773.26 | -10947.87 | -10947.87 |  | 68% | 112.5%
24-PC-31663 | Fern Valley Section 106 Consultation | In Progress | Fixed fee | Cascade | Jean Cooke | 52600 | 43847.36 | 43847.36 | 37714.2 | 37714.2 | 0 | 31436.99 | 6277.21 | 6277.21 |  | 83.4% | 83.36%
24-PC-31750 | Kestrel Butte Park Improvements - Phase I Survey | Final Reporting/Review | Fixed fee | Cascade | Cassidy Gay | 257200 | 217488.32 | 212721.72 | 200024.44 | 200024.44 | 0 | 169133.72 | 30890.72 | 30890.72 |  | 84.6% | 84.56%
24-PC-31819 | Plover Cove Reservoir - Curation | Final Reporting/Review | Time and material | Cascade | Gene Nixon | 38600 | 26248 | 26248 | 26703.48 | 26703.48 | 0 | 15843.15 | 10860.33 | 10860.33 |  | 68% | 59.33%
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | In Progress | Time and material | Cascade | Gene Nixon | 15200 | 10871.15 | 10871.15 | 10676.48 | 10676.48 | 0 | 7665.21 | 3011.27 | 3011.27 |  | 71.5% | 71.8%
24-PC-31924 | Cedar Hollow Wind Farm - Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Gene Nixon | 186800 | 123811.04 | 123811.04 | 147262.72 | 122646.08 | 24616.64 | 97605.67 | 49657.05 | 25040.41 |  | 66.3% | 66.28%
24-PC-32088 | Elk Meadow Phase I Survey | In Progress | Time and material | Chesapeake | Jason Oconnor | 305100 | 207468 | 207468 | 228062.25 | 228062.25 | 0 | 135703.34 | 92358.91 | 92358.91 |  | 68% | 59.5%
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 51800 | 51800 | 50026.67 | 36731.38 | 36731.38 | 0 | 59530.75 | -22799.37 | -22799.37 |  | 100% | 162.1%
24-PC-32209 | Saltgrass Wastewater Plant - Phase I Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox | 13000 | 12785.5 | 12785.5 | 9029.25 | 7229.76 | 1799.49 | 8880.11 | 149.14 | -1650.35 |  | 98.4% | 98.35%
24-PC-32210 | Badger Hollow Transmission Line - Class III Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 114400 | 79496.56 | 79496.56 | 91211.12 | 91211.12 | 0 | 63386.97 | 27824.15 | 27824.15 |  | 69.5% | 69.49%
24-PC-32479 | Riverbend Transmission Line Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 94000 | 62594.6 | 62594.6 | 66890.4 | 66890.4 | 0 | 44542.3 | 22348.1 | 22348.1 |  | 66.6% | 66.59%
24-PC-32640 | Badger Hollow Harbor Dredging Architectural History Survey | Transferred Entity | Time and material | Chesapeake | Alexandria Wilkinson | 39000 | 26520 | 26520 | 28130.47 | 21303 | 6827.47 | 22328.99 | 5801.48 | -1025.99 |  | 68% | 79.38%
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Chesapeake | Alexandria Wilkinson | 84000 | 84000 | 83888.35 | 70198.8 | 70198.8 | 0 | 85361.67 | -15162.87 | -15162.87 |  | 100% | 121.6%
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox | 51700 | 44730.84 | 44730.84 | 45206.48 | 45206.48 | 0 | 39111.36 | 6095.12 | 6095.12 |  | 86.5% | 86.52%
24-PC-32954 | Redbud Substation - Historic Resources Evaluation | In Progress | Time and material | Front Range | Kimberly Daugherty | 331200 | 225216 | 225216 | 217532.16 | 217532.16 | 0 | 114290.35 | 103241.81 | 103241.81 |  | 68% | 52.54%
24-PC-33384 | Phase III: Pine Hollow Rail Siding Maritime Remote Sensing Survey | In Progress | Time and material | Front Range | Dean Velazquez | 288100 | 195908 | 195908 | 207230.33 | 207230.33 | 0 | 139777.64 | 67452.69 | 67452.69 |  | 68% | 67.45%
24-PC-33394 | Foxglove Park Improvements Cultural Resources Assessment | In Progress | Time and material | Front Range | Joanna Herrera | 298200 | 202776 | 202776 | 197617.14 | 197617.14 | 0 | 102377.3 | 95239.84 | 95239.84 |  | 68% | 51.81%
24-PC-33448 | Ember Valley Solar Architectural History Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 681000 | 563868 | 560235.94 | 419972.7 | 419972.7 | 0 | 347755.54 | 72217.16 | 72217.16 |  | 82.8% | 82.8%
24-PC-33531 | North Fork Park Improvements - Curation | Lab/Curation | Fixed fee | Front Range | Dean Velazquez | 31500 | 23965.2 | 23965.2 | 23760.45 | 23760.45 | 0 | 18077.06 | 5683.39 | 5683.39 |  | 76.1% | 76.08%
24-PC-33575 | On-Call: North Fork Trail Architectural History Survey | Final Reporting/Review | Time and material | Front Range | Devon Pitts | 589600 | 384232.95 | 369763.26 | 433356 | 433356 | 0 | 309438.42 | 123917.58 | 123917.58 |  | 65.2% | 71.41%
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Karl Valenzuela | 64500 | 59346.45 | 57224.04 | 49568.25 | 49568.25 | 0 | 45606.09 | 3962.16 | 3962.16 |  | 92% | 92.01%
24-PC-33927 | Aspen Ridge Solar Class III Survey | Final Reporting/Review | Fixed fee | Great Lakes | Nathan Lambert | 104000 | 57012.8 | 57012.8 | 77001.6 | 77001.6 | 0 | 42209.16 | 34792.44 | 34792.44 |  | 54.8% | 54.82%
24-PC-33981 | Yarrow Point Airport Apron - Phase II Testing | Lab/Curation | Time and material | Great Lakes | Nathan Lambert | 47500 | 36664.5 | 36664.5 | 29944 | 29944 | 0 | 26339.43 | 3604.57 | 3604.57 |  | 77.2% | 87.96%
24-PC-33985 | Thistle Down Substation Curation | In Progress | Time and material | Great Lakes | Angelica Cervantes | 78300 | 53244 | 53244 | 57863.7 | 57863.7 | 0 | 50630.38 | 7233.32 | 7233.32 |  | 68% | 87.5%
24-PC-34263 | Cedar Hollow Airport Apron Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Robin Mercado | 199300 | 127292.91 | 127292.91 | 147800.88 | 147800.88 | 0 | 94406.95 | 53393.93 | 53393.93 |  | 63.9% | 63.87%
24-PC-34320 | Sage Flat Canal Lining Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 388400 | 279492.64 | 279492.64 | 253927.23 | 209652.52 | 44274.71 | 182728.59 | 71198.64 | 26923.93 |  | 72% | 71.96%
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Karl Valenzuela | 38700 | 26316 | 26316 | 26644.95 | 26644.95 | 0 | 19241.81 | 7403.14 | 7403.14 |  | 68% | 72.22%
24-PC-34499 | Dove Canyon Trail - GIS Mapping | In Progress | Time and material | Great Lakes | Brendan Padilla | 104200 | 70856 | 70856 | 76427.58 | 70842.85 | 5584.73 | 75193.06 | 1234.52 | -4350.21 |  | 68% | 98.38%
24-PC-34593 | Riverbend Park Improvements - Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 43500 | 25308.3 | 25308.3 | 33447.15 | 33447.15 | 0 | 19459.27 | 13987.88 | 13987.88 |  | 58.2% | 58.18%
24-PC-34654 | Timber Gap Phase II Testing | Final Reporting/Review | Time and material | Great Lakes | Brendan Padilla | 115400 | 82959.15 | 82899.95 | 87787.28 | 70825.08 | 16962.2 | 47046.35 | 40740.93 | 23778.73 |  | 71.9% | 53.59%
24-PC-34663 | Redbud Airport Apron - GIS Mapping | In Progress | Time and material | Great Lakes | Kathleen Galvan | 505100 | 343468 | 343468 | 342760.86 | 342760.86 | 0 | 286062.16 | 56698.7 | 56698.7 |  | 68% | 83.46%
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | In Progress | Time and material | Gulf Coast | Courtney Daugherty | 176500 | 120020 | 120020 | 121414.35 | 121414.35 | 0 | 122080.25 | -665.9 | -665.9 |  | 68% | 100.6%
24-PC-34975 | Foxglove Fiber Route GIS Mapping | In Progress | Fixed fee | Gulf Coast West | Bernard Erickson | 205900 | 175159.13 | 175159.13 | 181192 | 181192 | 0 | 154132.44 | 27059.56 | 27059.56 |  | 85.1% | 85.07%
24-PC-35267 | Falcon Mesa Trail - Phase II Testing | Final Reporting/Review | Fixed fee | Gulf Coast | Sean Jennings | 56700 | 33226.2 | 33226.2 | 42581.7 | 42581.7 | 0 | 24952.14 | 17629.56 | 17629.56 |  | 58.6% | 58.6%
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | In Progress | Time and material | High Desert | Kathy Hurley | 301200 | 204816 | 204816 | 217496.52 | 217496.52 | 0 | 196030.1 | 21466.42 | 21466.42 |  | 68% | 90.13%
24-PC-35474 | Larkspur Curation | In Progress | Fixed fee | High Desert | Eileen Poole | 369600 | 284148.48 | 284148.48 | 278295.85 | 215699.64 | 62596.21 | 213962.17 | 64333.68 | 1737.47 |  | 76.9% | 76.88%
24-PC-35559 | Phase III: Fern Valley Battery Storage Curation | Final Reporting/Review | Fixed fee | High Desert | Eileen Poole | 218200 | 185797.3 | 185797.3 | 144252.02 | 144252.02 | 0 | 122823.72 | 21428.3 | 21428.3 |  | 85.2% | 85.15%
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | In Progress | Fixed fee | High Desert | Eileen Poole | 119200 | 90150.96 | 90150.96 | 88243.76 | 88243.76 | 0 | 66735.14 | 21508.62 | 21508.62 |  | 75.6% | 75.63%
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | In Progress | Time and material | High Desert | Kathy Hurley | 69900 | 69900 | 66597.48 | 49013.31 | 40696.6 | 8316.71 | 53862.59 | -4849.28 | -13165.99 |  | 100% | 109.9%
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | In Progress | Time and material | High Desert | Kathy Hurley | 225100 | 200102.05 | 200102.05 | 153743.3 | 153743.3 | 0 | 140872.8 | 12870.5 | 12870.5 |  | 88.9% | 91.63%
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 12900 | 10859.22 | 10859.22 | 9094.5 | 9094.5 | 0 | 7655.43 | 1439.07 | 1439.07 |  | 84.2% | 84.18%
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Cost Tracking on Closed Project | Fixed fee | High Desert | Kathy Hurley | 58300 | 58300 | 58300 | 39072.66 | 39072.66 | 0 | 45518.79 | -6446.13 | -6446.13 |  | 100% | 116.5%
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | In Progress | Time and material | High Desert | Kathy Hurley | 5700 | 3876 | 3876 | 4244.79 | 4244.79 | 0 | 3255.04 | 989.75 | 989.75 |  | 68% | 76.68%
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Island | Rodney Mcguire | 56300 | 52077.5 | 52077.5 | 37721 | 37721 | 0 | 34891.33 | 2829.67 | 2829.67 |  | 92.5% | 92.5%
24-PC-36620 | Silver Lake Cultural Resources Assessment | In Progress | Time and material | Lakeshore | Terrence Gillespie | 368100 | 290535 | 290535 | 252295.74 | 252295.74 | 0 | 163066.37 | 89229.37 | 89229.37 |  | 78.9% | 64.63%
24-PC-36932 | Badger Hollow Canal Lining - Section 106 Consultation | Final Reporting/Review | Time and material | Hill Country | Marcus Shea | 12200 | 9992.5 | 9992.5 | 7733.58 | 7733.58 | 0 | 6430.16 | 1303.42 | 1303.42 |  | 81.9% | 83.15%
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | In Progress | Fixed fee | Hill Country | Glen Delacruz | 141000 | 141000 | 141000 | 113970.3 | 113970.3 | 0 | 138124.06 | -24153.76 | -24153.76 |  | 100% | 121.2%
24-PC-37107 | Hawk Point Mixed-Use Development Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 259400 | 176106.66 | 176106.66 | 186117.89 | 175095.48 | 11022.41 | 126346.85 | 59771.04 | 48748.63 |  | 67.9% | 67.89%
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | In Progress | Fixed fee | Hill Country | Gail Meza | 1259200 | 928785.92 | 928785.92 | 853989.44 | 853989.44 | 0 | 629919.62 | 224069.82 | 224069.82 |  | 73.8% | 73.76%
24-PC-37167 | Saltgrass Curation | Lab/Curation | Time and material | Hill Country | Marcus Shea | 65600 | 44608 | 44608 | 48603.04 | 48603.04 | 0 | 33605.6 | 14997.44 | 14997.44 |  | 68% | 69.14%
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | In Progress | Time and material | Hill Country | Samuel Wilkerson | 67000 | 51564 | 51564 | 40709.2 | 40709.2 | 0 | 34240.46 | 6468.74 | 6468.74 |  | 77% | 84.11%
24-PC-37266 | Granite Pass Cell Tower Phase I Survey | In Progress | Time and material | Hill Country | Marcus Shea | 41400 | 29169.9 | 29169.9 | 24587.46 | 24587.46 | 0 | 17096.42 | 7491.04 | 7491.04 |  | 70.5% | 69.53%
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 298500 | 213069.3 | 213069.3 | 243904.35 | 243904.35 | 0 | 174092.01 | 69812.34 | 69812.34 |  | 71.4% | 71.38%
24-PC-37372 | Harbor View Harbor Dredging Paleontological Monitoring | Final Reporting/Review | Fixed fee | Piedmont - Inactive | Maria Parrish | 272100 | 244563.48 | 237896.12 | 221924.76 | 221924.76 | 0 | 199459.24 | 22465.52 | 22465.52 |  | 89.9% | 89.88%
24-PC-37415 | Sage Flat Mine Expansion Maritime Remote Sensing Survey | In Progress | Fixed fee | PIEDMONT - INACTIVE | Megan Pineda | 191000 | 115994.3 | 115994.3 | 147948.6 | 147948.6 | 0 | 89853.11 | 58095.49 | 58095.49 |  | 60.7% | 60.73%
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | In Progress | Time and material | PIEDMONT - INACTIVE | Jody Chung | 309400 | 210392 | 210392 | 184093 | 184093 | 0 | 149432.06 | 34660.94 | 34660.94 |  | 68% | 81.17%
24-PC-37686 | Twin Buttes Mixed-Use Development Paleontological Monitoring | In Progress | Fixed fee | Piedmont - Inactive | Annette Vaughan | 50600 | 41385.74 | 41385.74 | 39155.85 | 28376.76 | 10779.09 | 32027.2 | 7128.65 | -3650.44 |  | 81.8% | 81.79%
24-PC-37823 | Granite Pass Pipeline Cultural Resources Monitoring | Lab/Curation | Fixed fee | Piedmont - Inactive | Jody Chung | 28900 | 21070.99 | 21070.99 | 21651.88 | 21651.88 | 0 | 15787.12 | 5864.76 | 5864.76 |  | 72.9% | 72.91%
24-PC-37942 | Task Order 39: Meadowlark Mine Expansion Curation | Final Reporting/Review | Time and material | Piedmont - Inactive | Annette Vaughan | 241400 | 199259.4 | 199259.4 | 173542.46 | 173542.46 | 0 | 141494.45 | 32048.01 | 32048.01 |  | 82.5% | 81.53%
24-PC-38054 | On-Call: Willow Springs Highway Widening GIS Mapping | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd | 60700 | 41373.12 | 41373.12 | 51516.09 | 51516.09 | 0 | 35113.87 | 16402.22 | 16402.22 |  | 68.2% | 68.16%
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Prairie | Sherry Lloyd | 132200 | 121663.66 | 121663.66 | 95580.6 | 95580.6 | 0 | 87961.2 | 7619.4 | 7619.4 |  | 92% | 92.03%
24-PC-38374 | On-Call: Riverbend Highway Widening Archaeological Testing | In Progress | Time and material | Prairie | Sherry Lloyd | 481100 | 327148 | 327148 | 330082.71 | 330082.71 | 0 | 229684.73 | 100397.98 | 100397.98 |  | 68% | 69.58%
24-PC-38469 | Falcon Mesa Harbor Dredging - Built Environment Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 656700 | 527658.45 | 515845.1 | 435290.48 | 364918.68 | 70371.8 | 349739.21 | 85551.27 | 15179.47 |  | 80.3% | 80.35%
24-PC-38486 | Kestrel Butte Phase I Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 153600 | 153600 | 153600 | 105043.81 | 77500.98 | 27542.83 | 119866.24 | -14822.43 | -42365.26 |  | 100% | 114.1%
24-PC-38687 | Lantern Bay GIS Mapping | In Progress | Time and material | Red Rock | Javier Newman | 68600 | 46648 | 46648 | 49542.92 | 49542.92 | 0 | 28559.72 | 20983.2 | 20983.2 |  | 68% | 57.65%
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Red Rock | Marisa Odom | 168200 | 168200 | 168200 | 130489.56 | 130489.56 | 0 | 132230.67 | -1741.11 | -1741.11 |  | 100% | 101.3%
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 100200 | 100200 | 93737.19 | 72685.08 | 72685.08 | 0 | 103671 | -30985.92 | -30985.92 |  | 100% | 142.6%
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | In Progress | Time and material | Red Rock | Lydia Cisneros | 126600 | 86088 | 86088 | 82581.18 | 82581.18 | 0 | 59856.61 | 22724.57 | 22724.57 |  | 68% | 72.48%
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Javier Newman | 597800 | 458990.84 | 458990.84 | 435557.08 | 435557.08 | 0 | 334422.57 | 101134.51 | 101134.51 |  | 76.8% | 76.78%
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Red Rock | Shelia Horne | 11000 | 11000 | 11000 | 7227 | 7227 | 0 | 7427.79 | -200.79 | -200.79 |  | 100% | 102.8%
24-PC-39479 | Granite Pass Solar - Cultural Resources Assessment | Final Reporting/Review | Time and material | Red Rock | Javier Newman | 233000 | 165185 | 165185 | 164777.6 | 164777.6 | 0 | 116733.87 | 48043.73 | 48043.73 |  | 70.9% | 70.84%
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | In Progress | Time and material | Red Rock | Tina Aguirre | 33000 | 29186 | 29186 | 23227.58 | 20462.4 | 2765.18 | 29633.53 | -6405.95 | -9171.13 |  | 88.4% | 127.6%
24-PC-39533 | Elk Meadow Architectural History Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 67000 | 63536.1 | 63536.1 | 52641.9 | 52641.9 | 0 | 49919.2 | 2722.7 | 2722.7 |  | 94.8% | 94.83%
24-PC-39694 | Task Order 35: Sandpiper Trail Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 136500 | 92820 | 92820 | 93075.52 | 70843.68 | 22231.84 | 77289.3 | 15786.22 | -6445.62 |  | 68% | 83.04%
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | In Progress | Fixed fee | Red Rock | Bruce Suarez | 17800 | 17800 | 17800 | 14308.95 | 10538.95 | 3770 | 14659.16 | -350.21 | -4120.21 |  | 100% | 102.5%
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | In Progress | Time and material | Red Rock | Lydia Cisneros | 414900 | 339174.65 | 331243.28 | 270722.25 | 270722.25 | 0 | 215589.53 | 55132.72 | 55132.72 |  | 81.7% | 79.63%
24-PC-39940 | Riverbend Levee Repair - Curation | In Progress | Fixed fee | Red Rock | Marisa Odom | 20400 | 13135.56 | 13135.56 | 16397.52 | 16397.52 | 0 | 10559.17 | 5838.35 | 5838.35 |  | 64.4% | 64.39%
24-PC-40067 | Saltgrass Fiber Route Class III Survey | In Progress | Time and material | Red Rock | Marisa Odom | 218100 | 148308 | 148308 | 163684.05 | 163684.05 | 0 | 137568.33 | 26115.72 | 26115.72 |  | 68% | 84.05%
24-PC-40102 | Redbud Class III Survey | Final Reporting/Review | Fixed fee | Sierra | Benjamin Mathis | 453900 | 453900 | 453900 | 322187.01 | 278794.4 | 43392.61 | 359994.61 | -37807.6 | -81200.21 |  | 100% | 111.7%
24-PC-40218 | North Fork Bridge Replacement - Built Environment Survey | In Progress | Time and material | Sierra North | Angelica Poole | 141000 | 95880 | 95880 | 95626.2 | 95626.2 | 0 | 51169.2 | 44457 | 44457 |  | 68% | 53.51%
24-PC-40317 | Sumac Ridge Harbor Dredging Curation | In Progress | Time and material | Sierra | Angelica Poole | 225800 | 153544 | 153544 | 153318.2 | 153318.2 | 0 | 86572.73 | 66745.47 | 66745.47 |  | 68% | 56.47%
24-PC-40479 | Quail Run Rail Siding - Built Environment Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 139600 | 89036.88 | 89036.88 | 110619.04 | 110619.04 | 0 | 70556.04 | 40063 | 40063 |  | 63.8% | 63.78%
24-PC-40561 | Task Order 39: Aspen Ridge Housing Development GIS Mapping | In Progress | Fixed fee | Sierra | Benjamin Mathis | 2335800 | 1666359.72 | 1651216.14 | 1746045.15 | 1301909.91 | 444135.24 | 1245666.04 | 500379.11 | 56243.87 |  | 71.3% | 71.34%
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Angelica Poole | 460500 | 326540.55 | 326540.55 | 381017.7 | 381017.7 | 0 | 270177.47 | 110840.23 | 110840.23 |  | 70.9% | 70.91%
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Sierra North | Louis Huff | 50300 | 46200.55 | 46200.55 | 35350.84 | 35350.84 | 0 | 32471.24 | 2879.6 | 2879.6 |  | 91.8% | 91.85%
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Sierra North | Donna Herring | 22100 | 22100 | 22100 | 17918.68 | 17918.68 | 0 | 33602.1 | -15683.42 | -15683.42 |  | 100% | 187.5%
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Alexis Nixon | 48400 | 48400 | 47376.63 | 37137.32 | 37137.32 | 0 | 47362.38 | -10225.06 | -10225.06 |  | 100% | 127.5%
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 31800 | 31800 | 31800 | 20975.28 | 20975.28 | 0 | 22323.11 | -1347.83 | -1347.83 |  | 100% | 106.4%
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Lab/Curation | Fixed fee | Coastal Bend | Diane Daniels | 579300 | 579300 | 579300 | 392475.75 | 392475.75 | 0 | 413750.74 | -21274.99 | -21274.99 |  | 100% | 105.4%
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 8800 | 8800 | 8800 | 6914.16 | 6914.16 | 0 | 7269.9 | -355.74 | -355.74 |  | 100% | 105.2%
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | In Progress | Time and material | Coastal Bend | Alexis Nixon | 60600 | 41208 | 41208 | 39983.88 | 39983.88 | 0 | 31771.04 | 8212.84 | 8212.84 |  | 68% | 79.46%
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Alexis Nixon | 18000 | 18000 | 15244.1 | 12312 | 12312 | 0 | 22722.22 | -10410.22 | -10410.22 |  | 100% | 184.5%
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 194900 | 187591.25 | 187591.25 | 131089.74 | 131089.74 | 0 | 126178.41 | 4911.33 | 4911.33 |  | 96.3% | 96.25%
24-PC-41886 | On-Call: Pebble Beach Road Canal Lining Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Melody Holloway | 67500 | 43694 | 43694 | 46824.75 | 46824.75 | 0 | 29307.2 | 17517.55 | 17517.55 |  | 64.7% | 62.59%
24-PC-41969 | Windmill Flat Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Built Environment | Melody Holloway | 216500 | 143864.25 | 143864.25 | 161335.8 | 161335.8 | 0 | 107206.67 | 54129.13 | 54129.13 |  | 66.4% | 66.45%
24-PC-42121 | Oak Terrace Substation Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Kathleen Cabrera | 267300 | 240703.65 | 240703.65 | 208453.84 | 189453.96 | 18999.88 | 187719.43 | 20734.41 | 1734.53 |  | 90% | 90.05%
24-PC-42184 | Phase II: Granite Pass Substation Environmental Review Support | In Progress | Fixed fee | Built Environment | Rickey Salas | 25600 | 11246.08 | 11246.08 | 17986.56 | 17986.56 | 0 | 7901.19 | 10085.37 | 10085.37 |  | 43.9% | 43.93%
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 263500 | 179180 | 179180 | 173567.45 | 173567.45 | 0 | 177335 | -3767.55 | -3767.55 |  | 68% | 102.2%
24-PC-42495 | Kestrel Butte Battery Storage - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Paleontology | Charlene Sparks | 45900 | 28875.69 | 28875.69 | 35246.61 | 35246.61 | 0 | 22172.99 | 13073.62 | 13073.62 |  | 62.9% | 62.91%
24-PC-42550 | Yarrow Point Paleontological Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado | 301300 | 201810.74 | 200636.36 | 216936 | 216936 | 0 | 145304.58 | 71631.42 | 71631.42 |  | 67% | 66.98%
24-PC-42674 | Foxglove Canal Lining Architectural History Survey | Lab/Curation | Time and material | Maritime | Rita Ayala | 156100 | 106148 | 106148 | 111589.34 | 92586.34 | 19003 | 57675.71 | 53913.63 | 34910.63 |  | 68% | 51.69%
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 639100 | 451268.51 | 451268.51 | 498050.63 | 498050.63 | 0 | 351673.07 | 146377.56 | 146377.56 |  | 70.6% | 70.61%
24-PC-43116 | On-Call: Larkspur Airport Apron Phase II Testing | Final Reporting/Review | Fixed fee | Geospatial | Sylvia Callahan | 424400 | 287318.8 | 287318.8 | 314395.52 | 314395.52 | 0 | 212843.45 | 101552.07 | 101552.07 |  | 67.7% | 67.7%
24-PC-43150 | Rushgrass Draw Architectural History Survey | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 301500 | 244848.15 | 244848.15 | 222689.15 | 196120.08 | 26569.07 | 180855.17 | 41833.98 | 15264.91 |  | 81.2% | 81.21%
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Geospatial | Sylvia Callahan | 19700 | 13396 | 13396 | 14170.21 | 14170.21 | 0 | 18919.28 | -4749.07 | -4749.07 |  | 68% | 133.5%
24-PC-43670 | Granite Pass Archaeological Testing | Final Reporting/Review | Fixed fee | Meridian Southwest | Lynn Tran | 220400 | 155514.24 | 155514.24 | 168565.52 | 153066.64 | 15498.88 | 118945.86 | 49619.66 | 34120.78 |  | 70.6% | 70.56%
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | In Progress | Time and material | Meridian Southwest | Lynn Tran | 1003600 | 682448 | 682448 | 771166.24 | 771166.24 | 0 | 614867.84 | 156298.4 | 156298.4 |  | 68% | 79.73%
24-PC-43719 | On-Call: Juniper Wash Wastewater Plant Historic Resources Evaluation | Final Reporting/Review | Time and material | Meridian Southwest | Harold Chaney | 382100 | 259828 | 259828 | 239599.17 | 197376 | 42223.17 | 170624.75 | 68974.42 | 26751.25 |  | 68% | 71.21%
24-PC-43786 | Task Order 3: Wren Hollow Canal Lining Architectural History Survey | Lab/Curation | Fixed fee | Meridian Southwest | Alan Gay | 220400 | 144053.44 | 144053.44 | 123791.36 | 113687.28 | 10104.08 | 80906.2 | 42885.16 | 32781.08 |  | 65.4% | 65.36%
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 213100 | 152792.6987 | 152792.6987 | 187528 | 187528 | 0 | 134454.77 | 53073.23 | 53073.23 |  | 71.7% | 71.7%
24-PC-44022 | Sea Oat Historic Resources Evaluation | Transferred Entity | Time and material | NH Gulf (USD) | Vanessa Duarte | 1072900 | 729572 | 729572 | 625022.97 | 541701.35 | 83321.62 | 345106.15 | 279916.82 | 196595.2 |  | 68% | 55.21%
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 264500 | 264500 | 256769.1787 | 194222.35 | 194222.35 | 0 | 246339.6193 | -52117.2693 | -52117.2693 |  | 100% | 126.8%
24-PC-44158 | Saltgrass Environmental Review Support | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 23200 | 23200 | 23148.0107 | 15583.44 | 15583.44 | 0 | 16044.04 | -460.6 | -460.6 |  | 100% | 103%
25-PC-30034 | On-Call: Wren Hollow Wastewater Plant GIS Mapping | Final Reporting/Review | Fixed fee | Big Sky | Bob Frye | 101900 | 69842.26 | 69842.26 | 74162.82 | 74162.82 | 0 | 50829.46 | 23333.36 | 23333.36 |  | 68.5% | 68.54%
25-PC-30077 | Phase II: Tamarack Housing Development Phase I Survey | In Progress | Time and material | Big Sky | Carl Barajas | 103400 | 103400 | 103400 | 71293.1 | 51740.95 | 19552.15 | 65644.01 | 5649.09 | -13903.06 |  | 100% | 92.08%
25-PC-30140 | Windmill Flat Cell Tower - GIS Mapping | In Progress | Time and material | Big Sky | Carl Barajas | 257200 | 121129.05 | 121129.05 | 165353.88 | 165353.88 | 0 | 95517.33 | 69836.55 | 69836.55 |  | 47.1% | 57.77%
25-PC-30254 | Task Order 16: Coyote Springs Reservoir Class III Survey | Final Reporting/Review | Time and material | Big Sky | Brendan Melton | 77100 | 51372.6 | 51372.6 | 49529.04 | 49529.04 | 0 | 35308.95 | 14220.09 | 14220.09 |  | 66.6% | 71.29%
25-PC-30345 | Wildrye Phase II Testing | In Progress | Fixed fee | Big Sky | Brendan Melton | 160400 | 130998.68 | 130998.68 | 92631 | 92631 | 0 | 75656.14 | 16974.86 | 16974.86 |  | 81.7% | 81.67%
25-PC-30348 | Phase II: Pine Hollow Wind Farm Environmental Review Support | In Progress | Fixed fee | Big Sky | Carl Barajas | 20800 | 13345.28 | 13345.28 | 15194.4 | 15194.4 | 0 | 9749.45 | 5444.95 | 5444.95 |  | 64.2% | 64.16%
25-PC-30418 | Dove Canyon Wind Farm Class III Survey | Final Reporting/Review | Fixed fee | Big Sky | Brendan Melton | 344800 | 249221.44 | 249221.44 | 233309.47 | 170518.18 | 62791.29 | 168637.5 | 64671.97 | 1880.68 |  | 72.3% | 72.28%
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway | 19700 | 19700 | 17105.05 | 13027.61 | 13027.61 | 0 | 13683.52 | -655.91 | -655.91 |  | 100% | 105%
25-PC-30717 | Phase II: Riverbend Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 324100 | 274771.98 | 255801.54 | 205678.64 | 166411.98 | 39266.66 | 174373.12 | 31305.52 | -7961.14 |  | 84.8% | 84.78%
25-PC-30739 | Saltgrass Solar Class III Survey | Final Reporting/Review | Fixed fee | Bluegrass | Alice Galloway | 244200 | 124346.64 | 124346.64 | 214896 | 214896 | 0 | 109432.28 | 105463.72 | 105463.72 |  | 50.9% | 50.92%
25-PC-30772 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 63300 | 63300 | 63300 | 43065.84 | 35870.85 | 7194.99 | 56416.91 | -13351.07 | -20546.06 |  | 100% | 131%
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 131000 | 131000 | 122522.64 | 85464.4 | 85464.4 | 0 | 90183.9 | -4719.5 | -4719.5 |  | 100% | 105.5%
25-PC-30824 | Task Order 2: Lantern Bay Fiber Route Environmental Review Support | In Progress | Fixed fee | Bluegrass | Alice Galloway | 206400 | 142477.92 | 142477.92 | 145641.07 | 109553 | 36088.07 | 100541.75 | 45099.32 | 9011.25 |  | 69% | 69.03%
25-PC-31109 | Riverbend GIS Mapping | In Progress | Time and material | Cascade | Cassidy Gay | 174700 | 174700 | 154905.3 | 109484.49 | 109484.49 | 0 | 162892.26 | -53407.77 | -53407.77 |  | 100% | 148.8%
25-PC-31114 | Granite Pass Built Environment Survey | In Progress | Time and material | Cascade | Jean Cooke | 229400 | 179308.8 | 179308.8 | 157964.84 | 157964.84 | 0 | 127618.8 | 30346.04 | 30346.04 |  | 78.2% | 80.79%
25-PC-31180 | Blue Heron Environmental Review Support | In Progress | Fixed fee | Cascade | Preston Duarte | 80000 | 80000 | 69747.43 | 60701.89 | 45712.3 | 14989.59 | 64096.36 | -3394.47 | -18384.06 |  | 100% | 105.6%
25-PC-31242 | Sage Flat Fiber Route - Class III Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 398600 | 143216.98 | 139744.36 | 273446.93 | 244020.48 | 29426.45 | 98245.95 | 175200.98 | 145774.53 |  | 35.9% | 35.93%
25-PC-31263 | Dove Canyon Water Main Phase I Survey | Lab/Curation | Time and material | Cascade | Cassidy Gay | 203400 | 177142 | 173315.81 | 139410.36 | 139410.36 | 0 | 122334.3 | 17076.06 | 17076.06 |  | 87.1% | 87.75%
25-PC-31298 | On-Call: Lone Pine Water Main Class III Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 48100 | 41495.87 | 41495.87 | 35361.72 | 33111 | 2250.72 | 30507.93 | 4853.79 | 2603.07 |  | 86.3% | 86.27%
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 23500 | 23500 | 23419.06 | 17263.1 | 17263.1 | 0 | 22123.1 | -4860 | -4860 |  | 100% | 128.2%
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 52000 | 52000 | 49983.77 | 38781.6 | 38781.6 | 0 | 51500.29 | -12718.69 | -12718.69 |  | 100% | 132.8%
25-PC-31420 | Cedar Hollow Wind Farm Archaeological Testing | Final Reporting/Review | Fixed fee | Cascade | Jeff Spence | 102200 | 55310.64 | 48011.31 | 68753.09 | 50928.84 | 17824.25 | 37206.7 | 31546.39 | 13722.14 |  | 54.1% | 54.12%
25-PC-31555 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 69300 | 66417.12 | 60877.3 | 53097.66 | 53097.66 | 0 | 50888.1 | 2209.56 | 2209.56 |  | 95.8% | 95.84%
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 16800 | 16800 | 16756.9 | 11810.4 | 11810.4 | 0 | 15531.6 | -3721.2 | -3721.2 |  | 100% | 131.5%
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Final Reporting/Review | Time and material | Cascade | Jeff Spence | 30300 | 30300 | 30300 | 22049.31 | 22049.31 | 0 | 34568.28 | -12518.97 | -12518.97 |  | 100% | 156.8%
25-PC-31775 | Task Order 26: Pine Hollow Bridge Replacement Cultural Resources Monitoring | In Progress | Time and material | Cascade | Cassidy Gay | 163200 | 89880 | 89880 | 98279.04 | 98279.04 | 0 | 45032.99 | 53246.05 | 53246.05 |  | 55.1% | 45.82%
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | In Progress | Fixed fee | Cascade | Preston Duarte | 216800 | 216800 | 202009.7 | 171337.04 | 171337.04 | 0 | 185663.62 | -14326.58 | -14326.58 |  | 100% | 108.4%
25-PC-31821 | Millbrook Environmental Review Support | Final Reporting/Review | Fixed fee | Cascade | Preston Duarte | 211400 | 171635.66 | 156607.64 | 183932.36 | 145726.92 | 38205.44 | 149340.49 | 34591.87 | -3613.57 |  | 81.2% | 81.19%
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 40900 | 13987.8 | 13987.8 | 28728.16 | 28728.16 | 0 | 33002.57 | -4274.41 | -4274.41 |  | 34.2% | 114.9%
25-PC-31905 | Raven Rock Mixed-Use Development Phase II Testing | Final Reporting/Review | Time and material | Cascade | Cassidy Gay | 331600 | 201880.85 | 185324.62 | 228107.64 | 228107.64 | 0 | 134532.55 | 93575.09 | 93575.09 |  | 60.9% | 58.98%
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Jason Oconnor | 35200 | 35200 | 35200 | 24481.6 | 24481.6 | 0 | 39794.35 | -15312.75 | -15312.75 |  | 100% | 162.5%
25-PC-32021 | Oak Terrace Cultural Resources Monitoring | In Progress | Time and material | Chesapeake | Alexandria Wilkinson | 148200 | 97677.05 | 95737.05 | 111253.74 | 111253.74 | 0 | 57713.28 | 53540.46 | 53540.46 |  | 65.9% | 51.88%
25-PC-32024 | Pine Hollow Historic Resources Evaluation | In Progress | Time and material | Chesapeake | Ian Maddox | 79500 | 57058 | 51094.33 | 57637.5 | 57637.5 | 0 | 41962.52 | 15674.98 | 15674.98 |  | 71.8% | 72.8%
25-PC-32241 | Sumac Ridge Canal Lining Cultural Resources Monitoring | Final Reporting/Review | Time and material | Chesapeake | Bryan Mann | 331500 | 258073.5 | 253304.76 | 231983.7 | 231983.7 | 0 | 169942.8 | 62040.9 | 62040.9 |  | 77.9% | 73.26%
25-PC-32264 | Tansy Flat Wastewater Plant Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Sandy Kerr | 736000 | 500480 | 500480 | 420550.4 | 420550.4 | 0 | 341293.64 | 79256.76 | 79256.76 |  | 68% | 81.15%
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | In Progress | Time and material | Chesapeake | Ian Maddox | 201300 | 196916.6 | 185059.24 | 150874.35 | 150874.35 | 0 | 161800.48 | -10926.13 | -10926.13 |  | 97.8% | 107.2%
25-PC-32402 | Hawk Point Highway Widening - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Chesapeake | Sandy Kerr | 401300 | 237088.04 | 229423.8 | 353144 | 353144 | 0 | 208637.11 | 144506.89 | 144506.89 |  | 59.1% | 59.08%
25-PC-32447 | Pebble Beach Road Archaeological Testing | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 88200 | 88200 | 88200 | 61772.24 | 55626.38 | 6145.86 | 76703.23 | -14930.99 | -21076.85 |  | 100% | 124.2%
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | In Progress | Time and material | Chesapeake | Sandy Kerr | 118800 | 118800 | 111029.5 | 85013.28 | 85013.28 | 0 | 117591.53 | -32578.25 | -32578.25 |  | 100% | 138.3%
25-PC-32750 | Elk Meadow Fiber Route Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Bryan Mann | 35500 | 27132.65 | 27028.9 | 25187.75 | 22000.77 | 3186.98 | 19250.92 | 5936.83 | 2749.85 |  | 76.4% | 76.43%
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran | 86500 | 83279.75 | 75767.65 | 62245.4 | 62245.4 | 0 | 49276.48 | 12968.92 | 12968.92 |  | 96.3% | 79.16%
25-PC-32795 | North Fork Water Main Architectural History Survey | In Progress | Time and material | Front Range | Reginald Vargas | 16900 | 16900 | 16900 | 11650.86 | 11650.86 | 0 | 12884.7 | -1233.84 | -1233.84 |  | 100% | 110.6%
25-PC-32838 | Aspen Ridge Canal Lining - Curation | In Progress | Fixed fee | Front Range | Jeremy Tran | 42600 | 39204.78 | 39204.78 | 33543.24 | 33543.24 | 0 | 30870.45 | 2672.79 | 2672.79 |  | 92% | 92.03%
25-PC-32861 | Yarrow Point Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 59200 | 59200 | 54224.79 | 41555.52 | 31694.67 | 9860.85 | 49895.36 | -8339.84 | -18200.69 |  | 100% | 120.1%
25-PC-32867 | Larkspur Levee Repair Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 144100 | 87944.23 | 85641.73 | 82727.81 | 82727.81 | 0 | 50486.75 | 32241.06 | 32241.06 |  | 61% | 61.03%
25-PC-32885 | Maple Fork Reservoir Historic Resources Evaluation | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 1706300 | 419067.28 | 394166.15 | 1213962.27 | 1090543.53 | 123418.74 | 298115.17 | 915847.1 | 792428.36 |  | 24.6% | 24.56%
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 59600 | 59600 | 57228.13 | 51399.04 | 51399.04 | 0 | 74823.59 | -23424.55 | -23424.55 |  | 100% | 145.6%
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Lab/Curation | Time and material | Front Range | Jeremy Tran | 13300 | 13300 | 13300 | 8727.43 | 6386.48 | 2340.95 | 16463.41 | -7735.98 | -10076.93 |  | 100% | 188.6%
25-PC-32926 | Tamarack Pipeline - Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran | 328400 | 68635.6 | 68635.6 | 212343.44 | 212343.44 | 0 | 61274.18 | 151069.26 | 151069.26 |  | 20.9% | 28.86%
25-PC-32952 | Eagle Bend Wastewater Plant - Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 299000 | 149649.5 | 143659.49 | 202368.34 | 160514.68 | 41853.66 | 101282.84 | 101085.5 | 59231.84 |  | 50% | 50.05%
25-PC-33065 | Wren Hollow GIS Mapping | In Progress | Fixed fee | Front Range | Dean Velazquez | 50400 | 45596.88 | 45596.88 | 40748.4 | 40748.4 | 0 | 36866.22 | 3882.18 | 3882.18 |  | 90.5% | 90.47%
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | In Progress | Fixed fee | Front Range | Reginald Vargas | 767800 | 603874.7 | 603874.7 | 553046.34 | 553046.34 | 0 | 434972.87 | 118073.47 | 118073.47 |  | 78.6% | 78.65%
25-PC-33105 | Redbud Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 3500 | 3500 | 0 | 2324 | 2324 | 0 | 9006.2 | -6682.2 | -6682.2 |  | 100% | 387.5%
25-PC-33136 | North Fork Historic Resources Evaluation | In Progress | Time and material | Front Range | Dean Velazquez | 33200 | 18065.15 | 17533.17 | 22378.06 | 19895.67 | 2482.39 | 12542.52 | 9835.54 | 7353.15 |  | 54.4% | 56.05%
25-PC-33183 | Saltgrass Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 104500 | 101009.7 | 95400.33 | 79399.1 | 79399.1 | 0 | 76745.43 | 2653.67 | 2653.67 |  | 96.7% | 96.66%
25-PC-33206 | Larkspur Water Main - Phase II Testing | In Progress | Fixed fee | Front Range | Mindy Galvan | 48800 | 27459.76 | 25370.03 | 39449.92 | 39449.92 | 0 | 22196.74 | 17253.18 | 17253.18 |  | 56.3% | 56.27%
25-PC-33294 | Fern Valley Substation - Built Environment Survey | In Progress | Fixed fee | Front Range | Joanna Herrera | 137200 | 83746.88 | 77650.18 | 91032.2 | 91032.2 | 0 | 55566.27 | 35465.93 | 35465.93 |  | 61% | 61.04%
25-PC-33332 | Willow Springs Cultural Resources Assessment | In Progress | Fixed fee | Front Range | Dean Velazquez | 91000 | 57721.3 | 54760.99 | 69587.7 | 69587.7 | 0 | 44141.81 | 25445.89 | 25445.89 |  | 63.4% | 63.43%
25-PC-33348 | Dove Canyon Cell Tower Phase II Testing | In Progress | Fixed fee | Front Range | Mindy Galvan | 161700 | 90374.13 | 90374.13 | 117749.94 | 117749.94 | 0 | 65815.88 | 51934.06 | 51934.06 |  | 55.9% | 55.89%
25-PC-33367 | Slate Ridge Rail Siding Archaeological Testing | Lab/Curation | Time and material | Front Range | Dean Velazquez | 150800 | 55445.9 | 52242.62 | 100689.16 | 100689.16 | 0 | 32787.21 | 67901.95 | 67901.95 |  | 36.8% | 32.56%
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Front Range | Devon Pitts | 41600 | 32406.4 | 32210.19 | 29136.64 | 29136.64 | 0 | 22697.51 | 6439.13 | 6439.13 |  | 77.9% | 77.9%
25-PC-33522 | Yarrow Point Architectural History Survey | Final Reporting/Review | Time and material | Front Range | Jeremy Tran | 61800 | 52972.45 | 50630.64 | 42270.22 | 36352.08 | 5918.14 | 34825.45 | 7444.77 | 1526.63 |  | 85.7% | 82.39%
25-PC-33640 | Tamarack Canal Lining - Cultural Resources Assessment | In Progress | Fixed fee | Front Range | Dean Velazquez | 1444500 | 432049.95 | 417334.9 | 1192145.85 | 1192145.85 | 0 | 356520.28 | 835625.57 | 835625.57 |  | 29.9% | 29.91%
25-PC-33680 | Quail Run School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 106800 | 42570.48 | 37483.28 | 80014.56 | 80014.56 | 0 | 31893.67 | 48120.89 | 48120.89 |  | 39.9% | 39.86%
25-PC-33744 | Blue Heron Canal Lining - Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 87100 | 64332.06 | 64332.06 | 60133.84 | 60133.84 | 0 | 44412.55 | 15721.29 | 15721.29 |  | 73.9% | 73.86%
25-PC-33750 | Kestrel Butte Archaeological Testing | Transferred Entity | Fixed fee | Great Lakes | Kathleen Galvan | 69600 | 69600 | 64460.42 | 51302.16 | 51302.16 | 0 | 60286.74 | -8984.58 | -8984.58 |  | 100% | 117.5%
25-PC-33798 | On-Call: Harbor View Wind Farm Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Great Lakes | Brendan Padilla | 155300 | 82914.67 | 80025.19 | 128215.68 | 128215.68 | 0 | 68449.64 | 59766.04 | 59766.04 |  | 53.4% | 53.39%
25-PC-33841 | Juniper Wash Built Environment Survey | In Progress | Fixed fee | Great Lakes | Kathleen Galvan | 586500 | 366034.65 | 366034.65 | 416356.35 | 416356.35 | 0 | 259867.95 | 156488.4 | 156488.4 |  | 62.4% | 62.41%
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Final Reporting/Review | Fixed fee | Great Lakes | Geoffrey Fernandez | 15200 | 15200 | 15200 | 11021.49 | 9579.99 | 1441.5 | 11383.28 | -361.79 | -1803.29 |  | 100% | 103.3%
25-PC-33855 | Creosote Draw Rail Siding - Paleontological Monitoring | Final Reporting/Review | Time and material | Great Lakes | Karl Valenzuela | 34000 | 19618 | 18919.13 | 23930.44 | 21188.35 | 2742.09 | 13640.31 | 10290.13 | 7548.04 |  | 57.7% | 57%
25-PC-33915 | Sage Flat Archaeological Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes | 272400 | 183216.24 | 176595.09 | 198225.48 | 198225.48 | 0 | 133333.04 | 64892.44 | 64892.44 |  | 67.3% | 67.26%
25-PC-33922 | Slate Ridge Data Recovery | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 22100 | 22100 | 22100 | 16113.11 | 16113.11 | 0 | 33890.09 | -17776.98 | -17776.98 |  | 100% | 210.3%
25-PC-33969 | Sumac Ridge Archaeological Testing | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 13200 | 7814.4 | 7814.4 | 10134.96 | 10134.96 | 0 | 5999.73 | 4135.23 | 4135.23 |  | 59.2% | 59.2%
25-PC-34036 | Kestrel Butte Battery Storage - Phase I Survey | Lab/Curation | Time and material | Great Lakes | Gina Beltran | 62300 | 54230.15 | 47936.1 | 41495.74 | 36709.53 | 4786.21 | 38677.3 | 2818.44 | -1967.77 |  | 87% | 93.21%
25-PC-34077 | Sage Flat Levee Repair Class III Survey | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 580500 | 289843.65 | 272107.91 | 459697.95 | 459697.95 | 0 | 229510.93 | 230187.02 | 230187.02 |  | 49.9% | 49.93%
25-PC-34088 | Timber Gap Harbor Dredging Cultural Resources Monitoring | In Progress | Time and material | Great Lakes | Leonard Mejia | 47300 | 32164 | 32164 | 29041.82 | 26577.06 | 2464.76 | 17359.62 | 11682.2 | 9217.44 |  | 68% | 59.77%
25-PC-34090 | Thistle Down Data Recovery | In Progress | Time and material | Great Lakes | Geoffrey Fernandez | 66200 | 34066.3 | 34066.3 | 46862.98 | 46862.98 | 0 | 24068 | 22794.98 | 22794.98 |  | 51.5% | 51.36%
25-PC-34151 | Bramble Creek Fiber Route Cultural Resources Monitoring | In Progress | Time and material | Great Lakes | Angelica Cervantes | 505100 | 190049.9 | 181895.54 | 334224.67 | 334224.67 | 0 | 126809.68 | 207414.99 | 207414.99 |  | 37.6% | 37.94%
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Geoffrey Fernandez | 53000 | 53000 | 53000 | 36718.4 | 36718.4 | 0 | 42629.29 | -5910.89 | -5910.89 |  | 100% | 116.1%
25-PC-34374 | Tansy Flat Reservoir Cultural Resources Assessment | In Progress | Time and material | Great Lakes | Gina Beltran | 14100 | 5160.6 | 5160.6 | 9871.41 | 9871.41 | 0 | 3661.74 | 6209.67 | 6209.67 |  | 36.6% | 37.09%
25-PC-34451 | North Fork Curation | In Progress | Time and material | Great Lakes | Robin Mercado | 46400 | 46400 | 46400 | 32526.4 | 32526.4 | 0 | 41685.4 | -9159 | -9159 |  | 100% | 128.2%
25-PC-34652 | Coyote Springs Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Gina Beltran | 210700 | 176145.2 | 157854.18 | 180928.09 | 180928.09 | 0 | 151256.79 | 29671.3 | 29671.3 |  | 83.6% | 83.6%
25-PC-34681 | Hawk Point Pipeline Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Brendan Padilla | 715200 | 264695.52 | 240939.56 | 430908 | 430908 | 0 | 159498.08 | 271409.92 | 271409.92 |  | 37% | 37.01%
25-PC-34732 | Thistle Down Trail Architectural History Survey | In Progress | Fixed fee | Great Lakes | Geoffrey Fernandez | 101800 | 62433.94 | 62433.94 | 76441.62 | 76441.62 | 0 | 46880.67 | 29560.95 | 29560.95 |  | 61.3% | 61.33%
25-PC-34772 | Windmill Flat Paleontological Monitoring | Final Reporting/Review | Time and material | Great Lakes | Brendan Padilla | 186900 | 20889.75 | 18840.73 | 126437.85 | 126437.85 | 0 | 11925.12 | 114512.73 | 114512.73 |  | 11.2% | 9.43%
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | In Progress | Time and material | Great Lakes | Gina Beltran | 82200 | 82200 | 65071.92 | 51638.04 | 51638.04 | 0 | 83204.3 | -31566.26 | -31566.26 |  | 100% | 161.1%
25-PC-34850 | Thistle Down Section 106 Consultation | In Progress | Time and material | Gulf Coast East | Wyatt Erickson | 201300 | 129963.25 | 120850.25 | 117035.82 | 117035.82 | 0 | 94500.26 | 22535.56 | 22535.56 |  | 64.6% | 80.74%
25-PC-34871 | Willow Springs GIS Mapping | Lab/Curation | Fixed fee | Gulf Coast East | Sean Jennings | 338100 | 194779.41 | 173584.4 | 260979.39 | 260979.39 | 0 | 150361.8 | 110617.59 | 110617.59 |  | 57.6% | 57.61%
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Wyatt Erickson | 224400 | 157798.08 | 157798.08 | 165046.2 | 165046.2 | 0 | 116067.93 | 48978.27 | 48978.27 |  | 70.3% | 70.32%
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 71400 | 71400 | 71400 | 48880.44 | 48880.44 | 0 | 56947.79 | -8067.35 | -8067.35 |  | 100% | 116.5%
25-PC-35084 | On-Call: Fern Valley Wastewater Plant Class III Survey | Final Reporting/Review | Fixed fee | Gulf Coast East | Bernard Erickson | 204900 | 142528.44 | 137085.87 | 133588.01 | 98343.72 | 35244.29 | 92924.36 | 40663.65 | 5419.36 |  | 69.6% | 69.56%
25-PC-35131 | Tamarack Phase II Testing | In Progress | Fixed fee | Gulf Coast | Bernard Erickson | 311900 | 130966.81 | 130966.81 | 227562.24 | 227562.24 | 0 | 95549.55 | 132012.69 | 132012.69 |  | 42% | 41.99%
25-PC-35138 | Foxglove Mixed-Use Development - Data Recovery | In Progress | Time and material | Gulf Coast East | Sean Jennings | 815000 | 593702.25 | 590691.86 | 517757.75 | 477272.64 | 40485.11 | 425247 | 92510.75 | 52025.64 |  | 72.8% | 82.13%
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | In Progress | Time and material | Gulf Coast | Wyatt Erickson | 33200 | 33200 | 31529.2 | 23495.64 | 23495.64 | 0 | 28098.77 | -4603.13 | -4603.13 |  | 100% | 119.6%
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 49900 | 49900 | 47494.52 | 35982.89 | 35982.89 | 0 | 42125.73 | -6142.84 | -6142.84 |  | 100% | 117.1%
25-PC-35295 | Copper Flats Architectural History Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 80400 | 54672 | 54672 | 54551.4 | 54551.4 | 0 | 39686.68 | 14864.72 | 14864.72 |  | 68% | 72.75%
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 19400 | 19400 | 15409.48 | 13919.5 | 13919.5 | 0 | 36287.62 | -22368.12 | -22368.12 |  | 100% | 260.7%
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Courtney Daugherty | 25100 | 25100 | 24927.65 | 20032.31 | 20032.31 | 0 | 27206.94 | -7174.63 | -7174.63 |  | 100% | 135.8%
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | In Progress | Time and material | High Desert | Kathy Hurley | 136900 | 136900 | 132838.07 | 90994.45 | 78522.66 | 12471.79 | 119032.95 | -28038.5 | -40510.29 |  | 100% | 130.8%
25-PC-35496 | Silver Lake Airport Apron Class III Survey | In Progress | Time and material | High Desert | Kathy Hurley | 15200 | 14910.4 | 14910.4 | 10132.32 | 10132.32 | 0 | 10426.69 | -294.37 | -294.37 |  | 98.1% | 102.9%
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox | 98800 | 77370.28 | 77370.28 | 78447.2 | 78447.2 | 0 | 61430.39 | 17016.81 | 17016.81 |  | 78.3% | 78.31%
25-PC-35553 | Rushgrass Draw Rail Siding - Data Recovery | In Progress | Time and material | High Desert | Eileen Poole | 589900 | 446922.5 | 421582.2 | 444589.27 | 356163.6 | 88425.67 | 314340.18 | 130249.09 | 41823.42 |  | 75.8% | 70.7%
25-PC-35740 | Oak Terrace Transmission Line - Historic Resources Evaluation | In Progress | Fixed fee | High Desert | Kathy Hurley | 28600 | 572 | 572 | 15121.1 | 12638.3 | 2482.8 | 303.1 | 14818 | 12335.2 |  | 2% | 2%
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 204800 | 204800 | 187347.98 | 136396.8 | 136396.8 | 0 | 140077.69 | -3680.89 | -3680.89 |  | 100% | 102.7%
25-PC-35779 | Task Order 9: Juniper Wash Wastewater Plant Built Environment Survey | In Progress | Fixed fee | High Desert | Bridget Maddox | 124800 | 103584 | 101478.5 | 84973.75 | 63196.65 | 21777.1 | 70526.09 | 14447.66 | -7329.44 |  | 83% | 83%
25-PC-35850 | Pebble Beach Road Environmental Review Support | Cost Tracking on Closed Project | Time and material | High Desert | Bridget Maddox | 53400 | 36312 | 36312 | 37978.08 | 37978.08 | 0 | 32074.27 | 5903.81 | 5903.81 |  | 68% | 84.45%
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | In Progress | Fixed fee | High Desert | Jody Wang | 83700 | 76761.27 | 76761.27 | 61050.78 | 61050.78 | 0 | 55992.16 | 5058.62 | 5058.62 |  | 91.7% | 91.71%
25-PC-35963 | Quail Run Substation - Section 106 Consultation | In Progress | Time and material | High Desert | Kathy Hurley | 320000 | 290771 | 290771 | 216192 | 216192 | 0 | 202041.59 | 14150.41 | 14150.41 |  | 90.9% | 93.45%
25-PC-35970 | Eagle Bend Wind Farm Phase II Testing | In Progress | Fixed fee | High Desert | Bridget Maddox | 53200 | 16359 | 16359 | 38886.26 | 35417.28 | 3468.98 | 11957.7 | 26928.56 | 23459.58 |  | 30.7% | 30.75%
25-PC-36051 | Riverbend Levee Repair Archaeological Testing | In Progress | Fixed fee | High Desert | Bridget Maddox | 405400 | 274617.96 | 274617.96 | 250415.58 | 250415.58 | 0 | 169641.96 | 80773.62 | 80773.62 |  | 67.7% | 67.74%
25-PC-36093 | Pine Hollow Pipeline Cultural Resources Assessment | Lab/Curation | Fixed fee | High Desert | Jody Wang | 213300 | 150611.13 | 149533.07 | 157884.66 | 157884.66 | 0 | 111476.29 | 46408.37 | 46408.37 |  | 70.6% | 70.61%
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | In Progress | Time and material | High Desert | Kathy Hurley | 114200 | 114200 | 114200 | 78124.22 | 78124.22 | 0 | 79562.79 | -1438.57 | -1438.57 |  | 100% | 101.8%
25-PC-36251 | Kestrel Butte Environmental Review Support | Lab/Curation | Fixed fee | Island | Joan Mathis | 39200 | 39200 | 39200 | 30446.64 | 30446.64 | 0 | 49335.55 | -18888.91 | -18888.91 |  | 100% | 162%
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | In Progress | Time and material | Island | Joan Mathis | 28100 | 24522.2 | 24500.73 | 19141.72 | 19141.72 | 0 | 16573.11 | 2568.61 | 2568.61 |  | 87.3% | 86.58%
25-PC-36332 | Goldfinch Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 871000 | 472953 | 455814.95 | 618958.05 | 566005.77 | 52952.28 | 336119.33 | 282838.72 | 229886.44 |  | 54.3% | 54.3%
25-PC-36336 | Sea Oat Canal Lining Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 36400 | 33364.24 | 29544.7 | 25854.92 | 25854.92 | 0 | 23699.14 | 2155.78 | 2155.78 |  | 91.7% | 91.66%
25-PC-36352 | Phase I: Plover Cove Substation Paleontological Monitoring | In Progress | Fixed fee | Island | Joan Mathis | 3262900 | 451585.36 | 413628.97 | 2263196.88 | 1903101.18 | 360095.7 | 313300.73 | 1949896.15 | 1589800.45 |  | 13.8% | 13.84%
25-PC-36366 | Lone Pine Solar Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 119500 | 45517.55 | 41825.58 | 101598.9 | 101598.9 | 0 | 38701.28 | 62897.62 | 62897.62 |  | 38.1% | 38.09%
25-PC-36464 | Larkspur Highway Widening Cultural Resources Assessment | In Progress | Time and material | Island | Joan Mathis | 102300 | 76761.1 | 76761.1 | 72751.63 | 53089.29 | 19662.34 | 60185.29 | 12566.34 | -7096 |  | 75% | 82.73%
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | In Progress | Fixed fee | Island | Becky Velazquez | 33100 | 33100 | 33100 | 25870.96 | 25870.96 | 0 | 34277.75 | -8406.79 | -8406.79 |  | 100% | 132.5%
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | In Progress | Fixed fee | Island | Joan Mathis | 88300 | 68397.18 | 67497.4 | 54269.18 | 54269.18 | 0 | 42036.07 | 12233.11 | 12233.11 |  | 77.5% | 77.46%
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Becky Velazquez | 116000 | 85573.2 | 85573.2 | 66050.4 | 66050.4 | 0 | 48723.63 | 17326.77 | 17326.77 |  | 73.8% | 73.77%
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | In Progress | Time and material | Lakeshore | Lucas Benson | 181300 | 181300 | 174825.53 | 117609.31 | 117609.31 | 0 | 164790.18 | -47180.87 | -47180.87 |  | 100% | 140.1%
25-PC-36645 | Falcon Mesa Archaeological Testing | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 25400 | 25400 | 24158.24 | 20302.22 | 20302.22 | 0 | 38922.61 | -18620.39 | -18620.39 |  | 100% | 191.7%
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | In Progress | Time and material | Lakeshore | Lucas Benson | 137400 | 108023.85 | 108023.85 | 99958.5 | 99958.5 | 0 | 83440.54 | 16517.96 | 16517.96 |  | 78.6% | 83.48%
25-PC-36657 | Stone Mill Park Improvements Phase II Testing | Final Reporting/Review | Time and material | Lakeshore | Jeanette Riddle | 255700 | 128243.4 | 121473 | 186833.25 | 150017.49 | 36815.76 | 88980.55 | 97852.7 | 61036.94 |  | 50.2% | 47.63%
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Final Reporting/Review | Fixed fee | Lakeshore | Jeanette Riddle | 74000 | 74000 | 66065.35 | 56358.4 | 56358.4 | 0 | 66079.16 | -9720.76 | -9720.76 |  | 100% | 117.3%
25-PC-36799 | Meadowlark Substation Phase I Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 32900 | 32900 | 30883.36 | 26389.09 | 26389.09 | 0 | 33048.52 | -6659.43 | -6659.43 |  | 100% | 125.2%
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 24200 | 24200 | 22550.8 | 16235.78 | 16235.78 | 0 | 26420.57 | -10184.79 | -10184.79 |  | 100% | 162.7%
25-PC-36832 | Stone Mill Phase I Survey | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 78400 | 44029.44 | 44029.44 | 52449.6 | 52449.6 | 0 | 29456.38 | 22993.22 | 22993.22 |  | 56.2% | 56.16%
25-PC-36838 | Phase II: Granite Pass Highway Widening Environmental Review Support | Final Reporting/Review | Time and material | Hill Country | Samuel Wilkerson | 216400 | 216400 | 203236.1 | 160499.18 | 119267.1 | 41232.08 | 158776.88 | 1722.3 | -39509.78 |  | 100% | 98.93%
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | In Progress | Time and material | Hill Country | Glen Delacruz | 75400 | 75400 | 71354.11 | 50299.34 | 50299.34 | 0 | 90901.92 | -40602.58 | -40602.58 |  | 100% | 180.7%
25-PC-37188 | On-Call: Lone Pine Airport Apron Cultural Resources Assessment | In Progress | Time and material | Hill Country | Suzanne Mcmillan | 131600 | 103670.5 | 103670.5 | 95554.76 | 95554.76 | 0 | 53871.13 | 41683.63 | 41683.63 |  | 78.8% | 56.38%
25-PC-37371 | Phase II: Ember Valley Water Main Class III Survey | In Progress | Fixed fee | Piedmont | Maria Parrish | 292700 | 126329.32 | 120692.53 | 199428.52 | 154432.08 | 44996.44 | 86077.44 | 113351.08 | 68354.64 |  | 43.2% | 43.16%
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | In Progress | Fixed fee | Piedmont | Maria Parrish | 59200 | 54913.92 | 54913.92 | 50698.88 | 50698.88 | 0 | 47030.53 | 3668.35 | 3668.35 |  | 92.8% | 92.76%
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Cost Tracking on Closed Project | Time and material | Piedmont | Megan Pineda | 83200 | 22297.6 | 22297.6 | 60186.88 | 60186.88 | 0 | 78242.94 | -18056.06 | -18056.06 |  | 26.8% | 130%
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | In Progress | Time and material | Piedmont | Jody Chung | 458200 | 311576 | 311576 | 301449.78 | 301449.78 | 0 | 240796.49 | 60653.29 | 60653.29 |  | 68% | 79.88%
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Lab/Curation | Fixed fee | Piedmont | Jody Chung | 21500 | 21500 | 20397.5 | 15617.6 | 15617.6 | 0 | 19499.41 | -3881.81 | -3881.81 |  | 100% | 124.9%
25-PC-37544 | Sparrow Hill Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 1009600 | 789709.12 | 789709.12 | 644730.56 | 644730.56 | 0 | 504318.97 | 140411.59 | 140411.59 |  | 78.2% | 78.22%
25-PC-37732 | Hawk Point Housing Development Class III Survey | In Progress | Fixed fee | Piedmont | Megan Pineda | 72900 | 64100.97 | 59413.97 | 45824.94 | 45824.94 | 0 | 40294.47 | 5530.47 | 5530.47 |  | 87.9% | 87.93%
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Final Reporting/Review | Time and material | Piedmont | Maria Parrish | 72200 | 69466.7 | 69466.7 | 44893.96 | 44893.96 | 0 | 57390.52 | -12496.56 | -12496.56 |  | 96.2% | 127.8%
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Megan Pineda | 7900 | 7900 | 7900 | 6020.59 | 6020.59 | 0 | 6629.3 | -608.71 | -608.71 |  | 100% | 110.1%
25-PC-37920 | Heron Marsh Mine Expansion Class III Survey | In Progress | Time and material | Piedmont | Maria Parrish | 138600 | 69844.2 | 64957.08 | 92806.56 | 92806.56 | 0 | 44711.28 | 48095.28 | 48095.28 |  | 50.4% | 48.18%
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd | 148100 | 109890.2 | 107447.04 | 106809.72 | 106809.72 | 0 | 79254.52 | 27555.2 | 27555.2 |  | 74.2% | 74.2%
25-PC-38006 | Timber Gap Wastewater Plant Archaeological Testing | In Progress | Time and material | Prairie | Sherry Lloyd | 112000 | 46616.5 | 46616.5 | 75667.2 | 75667.2 | 0 | 36469.16 | 39198.04 | 39198.04 |  | 41.6% | 48.2%
25-PC-38042 | Oak Terrace School Campus GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 24300 | 20144.7 | 20144.7 | 19082.79 | 19082.79 | 0 | 15820.03 | 3262.76 | 3262.76 |  | 82.9% | 82.9%
25-PC-38070 | Phase III: Willow Springs Wastewater Plant Historic Resources Evaluation | In Progress | Fixed fee | Prairie | Sherry Lloyd | 132800 | 82601.6 | 82601.6 | 116864 | 116864 | 0 | 72689.82 | 44174.18 | 44174.18 |  | 62.2% | 62.2%
25-PC-38107 | Task Order 13: Pebble Beach Road Substation Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd | 234600 | 77957.58 | 71933.85 | 208913.08 | 154792 | 54121.08 | 69422.07 | 139491.01 | 85369.93 |  | 33.2% | 33.23%
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | In Progress | Fixed fee | Prairie | Sherry Lloyd | 25300 | 20781.42 | 19246.71 | 16961.12 | 16961.12 | 0 | 13931.44 | 3029.68 | 3029.68 |  | 82.1% | 82.14%
25-PC-38196 | Sea Oat Cell Tower Built Environment Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 1160700 | 688295.1 | 688295.1 | 717428.67 | 717428.67 | 0 | 425399.95 | 292028.72 | 292028.72 |  | 59.3% | 59.3%
25-PC-38282 | Task Order 16: Fern Valley Reservoir Architectural History Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 1334100 | 672386.4 | 672386.4 | 876348.58 | 703000.66 | 173347.92 | 522008.11 | 354340.47 | 180992.55 |  | 50.4% | 59.57%
25-PC-38296 | Ember Valley Pipeline - GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 173000 | 83922.3 | 73131.65 | 111169.8 | 111169.8 | 0 | 53923.32 | 57246.48 | 57246.48 |  | 48.5% | 48.51%
25-PC-38332 | Redbud GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 899800 | 706522.96 | 706522.96 | 754394.62 | 682213.35 | 72181.27 | 592323.19 | 162071.43 | 89890.16 |  | 78.5% | 78.52%
25-PC-38333 | Pine Hollow Cell Tower Phase II Testing | In Progress | Fixed fee | Prairie | Sherry Lloyd | 78300 | 56861.46 | 56861.46 | 51450.4 | 46958.73 | 4491.67 | 37360.87 | 14089.53 | 9597.86 |  | 72.6% | 72.62%
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd | 136400 | 99080.96 | 99080.96 | 86736.76 | 86736.76 | 0 | 63001.3 | 23735.46 | 23735.46 |  | 72.6% | 72.64%
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | In Progress | Time and material | Red Rock | Jeanette Chung | 496400 | 481730.55 | 460087.32 | 357705.84 | 357705.84 | 0 | 311579.9 | 46125.94 | 46125.94 |  | 97% | 87.11%
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 176400 | 154297.08 | 154297.08 | 137697.84 | 137697.84 | 0 | 120438.25 | 17259.59 | 17259.59 |  | 87.5% | 87.47%
25-PC-38596 | Tansy Flat Pipeline Data Recovery | In Progress | Fixed fee | Red Rock | Bruce Suarez | 178000 | 91848 | 91848 | 148416.4 | 148416.4 | 0 | 76585.73 | 71830.67 | 71830.67 |  | 51.6% | 51.6%
25-PC-38606 | Silver Lake School Campus - Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 34800 | 20358 | 20358 | 26816.2 | 23301.12 | 3515.08 | 15688.36 | 11127.84 | 7612.76 |  | 58.5% | 58.5%
25-PC-38701 | Slate Ridge Curation | In Progress | Time and material | Red Rock | Javier Newman | 156400 | 109600.75 | 102197.06 | 98735.32 | 98735.32 | 0 | 71024.19 | 27711.13 | 27711.13 |  | 70.1% | 71.93%
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | In Progress | Fixed fee | Red Rock | Javier Newman | 63900 | 63900 | 60446.65 | 41637.24 | 41637.24 | 0 | 60770.39 | -19133.15 | -19133.15 |  | 100% | 145.9%
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 10400 | 10400 | 9781.64 | 5866.64 | 5866.64 | 0 | 18017.52 | -12150.88 | -12150.88 |  | 100% | 307.1%
25-PC-38879 | Kestrel Butte Built Environment Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 119700 | 88482.24 | 88482.24 | 70323.75 | 70323.75 | 0 | 51984.23 | 18339.52 | 18339.52 |  | 73.9% | 73.92%
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | In Progress | Time and material | Red Rock | Tina Aguirre | 244000 | 201680 | 201680 | 174704 | 174704 | 0 | 157468.07 | 17235.93 | 17235.93 |  | 82.7% | 90.13%
25-PC-39085 | Slate Ridge Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez | 120700 | 119806.82 | 119806.82 | 69209.38 | 69209.38 | 0 | 68696.85 | 512.53 | 512.53 |  | 99.3% | 99.26%
25-PC-39093 | Goldfinch Canal Lining Phase I Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 100100 | 49219.17 | 45898.43 | 73673.6 | 73673.6 | 0 | 36221.91 | 37451.69 | 37451.69 |  | 49.2% | 49.17%
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Shelia Horne | 90300 | 67986.87 | 62928.94 | 58198.35 | 58198.35 | 0 | 43819.98 | 14378.37 | 14378.37 |  | 75.3% | 75.29%
25-PC-39187 | Windmill Flat Trail - Architectural History Survey | Lab/Curation | Fixed fee | Red Rock | Javier Newman | 28100 | 13811.15 | 13811.15 | 19470.49 | 19470.49 | 0 | 9569.28 | 9901.21 | 9901.21 |  | 49.1% | 49.15%
25-PC-39318 | Lone Pine Fiber Route - Class III Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 104300 | 71143.03 | 70186.4 | 69818.42 | 69818.42 | 0 | 47626.24 | 22192.18 | 22192.18 |  | 68.2% | 68.21%
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Final Reporting/Review | Time and material | Red Rock | Tina Aguirre | 55900 | 55900 | 54034.56 | 39633.1 | 39633.1 | 0 | 38428.92 | 1204.18 | 1204.18 |  | 100% | 96.96%
25-PC-39398 | Silver Lake Housing Development - Data Recovery | Final Reporting/Review | Fixed fee | Red Rock | Marisa Odom | 103300 | 66783.45 | 66783.45 | 81096.61 | 66453.3 | 14643.31 | 52431.07 | 28665.54 | 14022.23 |  | 64.6% | 64.65%
25-PC-39422 | Willow Springs Historic Resources Evaluation | In Progress | Fixed fee | Red Rock | Bruce Suarez | 56900 | 14731.41 | 14948.37 | 45036.35 | 45036.35 | 0 | 11658.25 | 33378.1 | 33378.1 |  | 25.9% | 25.89%
25-PC-39424 | Tansy Flat Cultural Resources Assessment | In Progress | Fixed fee | Red Rock | Shelia Horne | 19700 | 19700 | 17614.13 | 13882.59 | 13882.59 | 0 | 16267.84 | -2385.25 | -2385.25 |  | 100% | 117.2%
25-PC-39458 | Larkspur Park Improvements Paleontological Monitoring | In Progress | Time and material | Red Rock | Bruce Suarez | 345000 | 230912.25 | 222777.3 | 242983.5 | 242983.5 | 0 | 143586.3 | 99397.2 | 99397.2 |  | 66.9% | 59.09%
25-PC-39554 | Thistle Down Archaeological Testing | In Progress | Fixed fee | Red Rock | Tina Aguirre | 86700 | 75628.41 | 63747.46 | 63594.45 | 63594.45 | 0 | 55476.01 | 8118.44 | 8118.44 |  | 87.2% | 87.23%
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | In Progress | Time and material | Red Rock | Javier Newman | 51000 | 51000 | 51000 | 36551.7 | 36551.7 | 0 | 75197.04 | -38645.34 | -38645.34 |  | 100% | 205.7%
25-PC-39808 | On-Call: Pine Hollow Rail Siding Architectural History Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 140600 | 77597.14 | 77597.14 | 88846.16 | 68571.9 | 20274.26 | 49031.18 | 39814.98 | 19540.72 |  | 55.2% | 55.19%
25-PC-39873 | On-Call: Eagle Bend Battery Storage Phase II Testing | In Progress | Fixed fee | Red Rock | Marisa Odom | 93300 | 44364.15 | 41424.71 | 70478.82 | 70478.82 | 0 | 33515.14 | 36963.68 | 36963.68 |  | 47.6% | 47.55%
25-PC-39885 | Bramble Creek Phase I Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 85600 | 55357.52 | 55221.19 | 54047.84 | 54047.84 | 0 | 34953.01 | 19094.83 | 19094.83 |  | 64.7% | 64.67%
25-PC-39896 | Task Order 8: Raven Rock Highway Widening Archaeological Testing | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 730900 | 541743.08 | 541743.08 | 540257.83 | 458118.4 | 82139.43 | 400441.47 | 139816.36 | 57676.93 |  | 74.1% | 74.12%
25-PC-39951 | Falcon Mesa Reservoir - Phase II Testing | Cost Tracking on Closed Project | Fixed fee | Red Rock | Javier Newman | 87200 | 69358.88 | 69358.88 | 65277.92 | 65277.92 | 0 | 51921.91 | 13356.01 | 13356.01 |  | 79.5% | 79.54%
25-PC-40231 | Goldfinch Pipeline - Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring | 88300 | 65426.7 | 60462.94 | 59478.88 | 59478.88 | 0 | 40234.79 | 19244.09 | 19244.09 |  | 74.1% | 67.65%
25-PC-40383 | North Fork Archaeological Testing | In Progress | Fixed fee | Sierra | Donna Herring | 193200 | 161148.12 | 161148.12 | 144185.16 | 144185.16 | 0 | 120262.61 | 23922.55 | 23922.55 |  | 83.4% | 83.41%
25-PC-40465 | Task Order 32: Copper Flats Solar Historic Resources Evaluation | In Progress | Fixed fee | Sierra | Benjamin Mathis | 127600 | 80860.12 | 77042.86 | 94627.43 | 86041.09 | 8586.34 | 59968.41 | 34659.02 | 26072.68 |  | 63.4% | 63.37%
25-PC-40482 | Task Order 33: Tamarack Cell Tower Cultural Resources Assessment | In Progress | Fixed fee | Sierra South | Louis Huff | 73200 | 32705.76 | 32090.81 | 60199.68 | 60199.68 | 0 | 26897 | 33302.68 | 33302.68 |  | 44.7% | 44.68%
25-PC-40503 | Copper Flats Phase I Survey | Lab/Curation | Time and material | Sierra | Benjamin Mathis | 43400 | 43400 | 43400 | 30119.6 | 30119.6 | 0 | 42364.23 | -12244.63 | -12244.63 |  | 100% | 140.7%
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring | 71000 | 71000 | 67104.25 | 49579.3 | 49579.3 | 0 | 76399.6 | -26820.3 | -26820.3 |  | 100% | 154.1%
25-PC-40541 | Eagle Bend Airport Apron - Archaeological Testing | In Progress | Fixed fee | Sierra | Louis Huff | 25000 | 16595 | 16595 | 16850 | 16850 | 0 | 11185.54 | 5664.46 | 5664.46 |  | 66.4% | 66.38%
25-PC-40572 | Maple Fork Cell Tower Environmental Review Support | In Progress | Fixed fee | Sierra | Benjamin Mathis | 88300 | 34887.33 | 34769.84 | 67293.43 | 67293.43 | 0 | 26589.42 | 40704.01 | 40704.01 |  | 39.5% | 39.51%
25-PC-40595 | Willow Springs Levee Repair - Built Environment Survey | Final Reporting/Review | Fixed fee | Sierra South | Angelica Poole | 1568300 | 611950.66 | 594232.15 | 1302159.49 | 1302159.49 | 0 | 508068.66 | 794090.83 | 794090.83 |  | 39% | 39.02%
25-PC-40677 | Quail Run Paleontological Monitoring | Transferred Entity | Time and material | Sierra South | Louis Huff | 225000 | 192903.25 | 192903.25 | 157612.5 | 157612.5 | 0 | 153698.04 | 3914.46 | 3914.46 |  | 85.7% | 97.52%
25-PC-40680 | On-Call: Eagle Bend Battery Storage Cultural Resources Assessment | Lab/Curation | Time and material | Sierra | Donna Herring | 10100 | 8386.75 | 8386.75 | 6706.4 | 6706.4 | 0 | 5628.16 | 1078.24 | 1078.24 |  | 83% | 83.92%
25-PC-40722 | Goldfinch Canal Lining - Archaeological Testing | In Progress | Time and material | Coastal Bend | Duane Ballard | 166600 | 128119.75 | 128119.75 | 119491.23 | 103318.2 | 16173.03 | 80423 | 39068.23 | 22895.2 |  | 76.9% | 67.3%
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 50100 | 50100 | 47994.45 | 34844.55 | 34844.55 | 0 | 37556.22 | -2711.67 | -2711.67 |  | 100% | 107.8%
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 46800 | 46800 | 46800 | 34243.56 | 34243.56 | 0 | 37494.89 | -3251.33 | -3251.33 |  | 100% | 109.5%
25-PC-40880 | Pebble Beach Road Bridge Replacement Cultural Resources Assessment | In Progress | Time and material | Coastal Bend | Diane Daniels | 45800 | 28954.35 | 26615.83 | 30347.08 | 30347.08 | 0 | 18281.09 | 12065.99 | 12065.99 |  | 63.2% | 60.24%
25-PC-40925 | Harbor View Airport Apron - Data Recovery | Final Reporting/Review | Time and material | Coastal Bend | Alexis Nixon | 35000 | 23800 | 23800 | 23562 | 23562 | 0 | 20240.75 | 3321.25 | 3321.25 |  | 68% | 85.9%
25-PC-41075 | Phase I: Cedar Hollow Airport Apron Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 82100 | 46534.28 | 45582.42 | 61304.07 | 61304.07 | 0 | 34747.46 | 26556.61 | 26556.61 |  | 56.7% | 56.68%
25-PC-41097 | On-Call: Falcon Mesa Wastewater Plant Phase II Testing | Final Reporting/Review | Time and material | Coastal Bend | Duane Ballard | 197800 | 157477.05 | 151428.7 | 128154.62 | 128154.62 | 0 | 105966.35 | 22188.27 | 22188.27 |  | 79.6% | 82.69%
25-PC-41187 | Hackberry Bend Trail GIS Mapping | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 98900 | 75510.15 | 72782.09 | 55621.36 | 55621.36 | 0 | 42469.63 | 13151.73 | 13151.73 |  | 76.3% | 76.35%
25-PC-41252 | Oak Terrace Wastewater Plant Curation | Final Reporting/Review | Fixed fee | Coastal Bend | Steve Rubio | 33000 | 30736.2 | 30524.42 | 25325 | 22089.27 | 3235.73 | 23587.72 | 1737.28 | -1498.45 |  | 93.1% | 93.14%
25-PC-41265 | Larkspur Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 89800 | 85318.98 | 85318.98 | 71911.84 | 71911.84 | 0 | 68323.14 | 3588.7 | 3588.7 |  | 95% | 95.01%
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 167900 | 133782.72 | 130782.09 | 131616.81 | 131616.81 | 0 | 104866.5 | 26750.31 | 26750.31 |  | 79.7% | 79.68%
25-PC-41383 | Harbor View Reservoir - Cultural Resources Assessment | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 342200 | 263870.42 | 263870.42 | 223902.7 | 185978.46 | 37924.24 | 172645.04 | 51257.66 | 13333.42 |  | 77.1% | 77.11%
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 179800 | 179800 | 170811.36 | 119171.44 | 119171.44 | 0 | 171055.95 | -51884.51 | -51884.51 |  | 100% | 143.5%
25-PC-41479 | Hawk Point Trail Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 633600 | 203892.48 | 200991.35 | 405123.84 | 405123.84 | 0 | 130355.73 | 274768.11 | 274768.11 |  | 32.2% | 32.18%
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Jared Choi | 130200 | 121022.45 | 121022.45 | 94156.73 | 81265.42 | 12891.31 | 105548.13 | -11391.4 | -24282.71 |  | 93% | 112.1%
25-PC-41514 | Lantern Bay Levee Repair Historic Resources Evaluation | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 48700 | 38575.27 | 38543.24 | 31123.36 | 29237.6 | 1885.76 | 24653.59 | 6469.77 | 4584.01 |  | 79.2% | 79.21%
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | In Progress | Time and material | Coastal Bend | Jared Choi | 412300 | 300806.95 | 290386.6 | 281889.51 | 281889.51 | 0 | 224531.7 | 57357.81 | 57357.81 |  | 73% | 79.65%
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | In Progress | Time and material | Built Environment | Jenny Wilkinson | 152100 | 112187.4 | 112187.4 | 108599.4 | 108599.4 | 0 | 90984.66 | 17614.74 | 17614.74 |  | 73.8% | 83.78%
25-PC-41764 | Stone Mill Environmental Review Support | In Progress | Time and material | Built Environment | Jenny Wilkinson | 20700 | 16684.25 | 16684.25 | 15642.78 | 13328.34 | 2314.44 | 14549.83 | 1092.95 | -1221.49 |  | 80.6% | 93.01%
25-PC-41834 | Pebble Beach Road Data Recovery | In Progress | Fixed fee | Built Environment | Rickey Salas | 170100 | 63736.47 | 58480.85 | 145401.48 | 145401.48 | 0 | 54475.63 | 90925.85 | 90925.85 |  | 37.5% | 37.47%
25-PC-41843 | Wren Hollow Rail Siding - Section 106 Consultation | Final Reporting/Review | Time and material | Built Environment | Jesse Maynard | 54000 | 36720 | 36720 | 35988.02 | 26607.55 | 9380.47 | 23655.15 | 12332.87 | 2952.4 |  | 68% | 65.73%
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | In Progress | Time and material | Built Environment | Rickey Salas | 39700 | 39700 | 38010.35 | 25920.13 | 25920.13 | 0 | 29882.88 | -3962.75 | -3962.75 |  | 100% | 115.3%
25-PC-42076 | Bramble Creek Highway Widening Curation | In Progress | Time and material | Built Environment | Jesse Maynard | 319600 | 155773.55 | 147831.26 | 227746.96 | 227746.96 | 0 | 98992.02 | 128754.94 | 128754.94 |  | 48.7% | 43.47%
25-PC-42084 | Foxglove Built Environment Survey | In Progress | Time and material | Built Environment | Kathleen Cabrera | 1294200 | 344257.2 | 344257.2 | 847312.74 | 847312.74 | 0 | 296024.06 | 551288.68 | 551288.68 |  | 26.6% | 34.94%
25-PC-42097 | Tansy Flat Solar Data Recovery | In Progress | Fixed fee | Built Environment | Jenny Wilkinson | 179700 | 84315.24 | 72979.58 | 138548.7 | 138548.7 | 0 | 65000.81 | 73547.89 | 73547.89 |  | 46.9% | 46.92%
25-PC-42115 | Hawk Point Reservoir Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Built Environment | Jesse Maynard | 110400 | 70534.56 | 70534.56 | 90660.48 | 90660.48 | 0 | 57919.11 | 32741.37 | 32741.37 |  | 63.9% | 63.89%
25-PC-42136 | Phase III: Granite Pass Mixed-Use Development Maritime Remote Sensing Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 31700 | 23670.39 | 20580.8 | 23936.32 | 17555.9 | 6380.42 | 17873.56 | 6062.76 | -317.66 |  | 74.7% | 74.67%
25-PC-42163 | Foxglove Historic Resources Evaluation | Final Reporting/Review | Time and material | Built Environment | Rickey Salas | 50700 | 38724.35 | 38724.35 | 34430.37 | 34430.37 | 0 | 27262.05 | 7168.32 | 7168.32 |  | 76.4% | 79.18%
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Cost Tracking on Closed Project | Time and material | Built Environment | Kathleen Cabrera | 17900 | 161.1 | 161.1 | 12066.39 | 12066.39 | 0 | 14332.43 | -2266.04 | -2266.04 |  | 0.9% | 118.8%
25-PC-42253 | On-Call: Plover Cove Substation Phase I Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 67000 | 47935 | 47935 | 45781.1 | 45781.1 | 0 | 27198.17 | 18582.93 | 18582.93 |  | 71.5% | 59.41%
25-PC-42282 | Dove Canyon Levee Repair - Phase I Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 33000 | 20116.8 | 20116.8 | 19255.5 | 19255.5 | 0 | 11737.58 | 7517.92 | 7517.92 |  | 61% | 60.96%
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 41200 | 32304.92 | 29924.09 | 29239.64 | 29239.64 | 0 | 22925.4 | 6314.24 | 6314.24 |  | 78.4% | 78.41%
25-PC-42323 | Millbrook Cultural Resources Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado | 79800 | 46355.82 | 46355.82 | 58357.74 | 58357.74 | 0 | 33900.56 | 24457.18 | 24457.18 |  | 58.1% | 58.09%
25-PC-42343 | Phase III: Coyote Springs Pipeline Phase II Testing | In Progress | Fixed fee | Paleontology | Travis Delgado | 6100 | 4126.04 | 4126.04 | 4038.38 | 3787.65 | 250.73 | 2731.5 | 1306.88 | 1056.15 |  | 67.6% | 67.64%
25-PC-42364 | Sparrow Hill Fiber Route - Phase I Survey | In Progress | Fixed fee | Paleontology | Travis Delgado | 594900 | 375917.31 | 375917.31 | 426353.2 | 400715.25 | 25637.95 | 269416.69 | 156936.51 | 131298.56 |  | 63.2% | 63.19%
25-PC-42399 | Task Order 7: Aspen Ridge Housing Development Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 683800 | 385594.82 | 364616.3 | 509225.86 | 509225.86 | 0 | 287162.01 | 222063.85 | 222063.85 |  | 56.4% | 56.39%
25-PC-42528 | Slate Ridge Park Improvements - Phase I Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 132000 | 37144.8 | 36898.14 | 93601.2 | 93601.2 | 0 | 26336.22 | 67264.98 | 67264.98 |  | 28.1% | 28.14%
25-PC-42601 | Lantern Bay Park Improvements - Cultural Resources Monitoring | Transferred Entity | Time and material | Paleontology | Charlene Sparks | 302100 | 108000.1 | 100989.07 | 213521.46 | 177364.48 | 36156.98 | 62873.17 | 150648.29 | 114491.31 |  | 35.7% | 29.45%
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | In Progress | Time and material | Maritime | Kyle Maynard | 130300 | 128601.35 | 128601.35 | 95796.56 | 95796.56 | 0 | 79985.69 | 15810.87 | 15810.87 |  | 98.7% | 83.5%
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Transferred Entity | Time and material | Geospatial | Sylvia Callahan | 62000 | 54684.75 | 54684.75 | 44404.4 | 44404.4 | 0 | 44584.79 | -180.39 | -180.39 |  | 88.2% | 100.4%
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | In Progress | Fixed fee | Meridian Central | Seth Zavala | 128400 | 128400 | 128209.36 | 106315.2 | 106315.2 | 0 | 195734.3 | -89419.1 | -89419.1 |  | 100% | 184.1%
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | In Progress | Time and material | Meridian Central | Seth Zavala | 15700 | 15700 | 11349.21 | 10903.65 | 10903.65 | 0 | 71168.37 | -60264.72 | -60264.72 |  | 100% | 652.7%
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Clinton Solis | 715500 | 650818.8 | 650818.8 | 625275.45 | 625275.45 | 0 | 568777.84 | 56497.61 | 56497.61 |  | 91% | 90.96%
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Seth Zavala | 551800 | 551800 | 551800 | 378424.44 | 378424.44 | 0 | 405626.36 | -27201.92 | -27201.92 |  | 100% | 107.2%
25-PC-43566 | Copper Flats Solar - Phase II Testing | In Progress | Fixed fee | Meridian Central | Mathew Shea | 114200 | 114200 | 114200 | 73887.4 | 73887.4 | 0 | 131458.02 | -57570.62 | -57570.62 |  | 100% | 177.9%
25-PC-43590 | Task Order 37: Elk Meadow Harbor Dredging Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Meridian Central | Mathew Shea | 24800 | 16978.08 | 16978.08 | 16619.52 | 14642.64 | 1976.88 | 11377.59 | 5241.93 | 3265.05 |  | 68.5% | 68.46%
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 52800 | 52800 | 52800 | 37979.04 | 37979.04 | 0 | 37986.88 | -7.84 | -7.84 |  | 100% | 100%
25-PC-43639 | Windmill Flat Battery Storage Curation | Final Reporting/Review | Fixed fee | Meridian Southwest | Harold Chaney | 137000 | 137000 | 133193.26 | 91502.3 | 91502.3 | 0 | 100918.9 | -9416.6 | -9416.6 |  | 100% | 110.3%
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Lab/Curation | Fixed fee | Meridian Southwest | Reginald Kerr | 92800 | 92800 | 80044.54 | 78211.84 | 78211.84 | 0 | 103245.03 | -25033.19 | -25033.19 |  | 100% | 132%
25-PC-43771 | Granite Pass Reservoir - Built Environment Survey | Lab/Curation | Time and material | Meridian Southwest | Lynn Tran | 31500 | 15790.5 | 15172.4 | 20147.4 | 20147.4 | 0 | 11344.38 | 8803.02 | 8803.02 |  | 50.1% | 56.31%
25-PC-43844 | Slate Ridge Battery Storage Class III Survey | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 50700 | 47891.22 | 43959.81 | 33907.9 | 26087.6 | 7820.3 | 32031.03 | 1876.87 | -5943.43 |  | 94.5% | 94.46%
25-PC-43853 | Heron Marsh Battery Storage - Phase II Testing | Final Reporting/Review | Time and material | Meridian Southwest | Alan Gay | 162800 | 159982.25 | 146251.97 | 115799.64 | 115799.64 | 0 | 99239.21 | 16560.43 | 16560.43 |  | 98.3% | 85.7%
25-PC-43863 | Yarrow Point Cultural Resources Assessment | In Progress | Fixed fee | Meridian Southwest | Reginald Kerr | 545200 | 101298.16 | 95002.43 | 450335.2 | 450335.2 | 0 | 83664.45 | 366670.75 | 366670.75 |  | 18.6% | 18.58%
25-PC-43932 | Blue Heron Built Environment Survey | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 35900 | 24136.5493 | 23610.32 | 24656.25 | 18135 | 6521.25 | 14873.81 | 9782.44 | 3261.19 |  | 67.23% | 60.32%
25-PC-43944 | Elk Meadow Data Recovery | In Progress | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 74800 | 26741 | 26741 | 60460.84 | 60460.84 | 0 | 21611.75 | 38849.09 | 38849.09 |  | 35.7% | 35.75%
25-PC-43966 | Silver Lake Rail Siding - Cultural Resources Monitoring | Transferred Entity | Fixed fee | NH Gulf (USD) | Tonya Spence | 47800 | 37848.04 | 34241.6987 | 34547.14 | 30211.65 | 4335.49 | 27353.2173 | 7193.9227 | 2858.4327 |  | 79.18% | 79.18%
25-PC-43993 | Timber Gap GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Javier Rangel | 27900 | 20428.3787 | 19158.5307 | 19669.5 | 19669.5 | 0 | 14401.75 | 5267.75 | 5267.75 |  | 73.22% | 73.22%
25-PC-44046 | Kestrel Butte Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu | 320300 | 320300 | 320300 | 220526.55 | 220526.55 | 0 | 276639.9 | -56113.35 | -56113.35 |  | 100% | 125.4%
25-PC-44186 | Falcon Mesa Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu | 537000 | 342015.3013 | 342015.3013 | 338148.9 | 338148.9 | 0 | 215370.94 | 122777.96 | 122777.96 |  | 63.69% | 63.69%
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 31100 | 31100 | 30922.8613 | 17934.14 | 13115.76 | 4818.38 | 31276.1173 | -13341.9773 | -18160.3573 |  | 100% | 174.4%
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 97000 | 97000 | 91499.34 | 71004 | 71004 | 0 | 79042.17 | -8038.17 | -8038.17 |  | 100% | 111.3%
26-PC-30013 | Windmill Flat Mine Expansion - Architectural History Survey | Final Reporting/Review | Time and material | Big Sky | Bob Frye | 62300 | 13942 | 8607.19 | 43902.81 | 43902.81 | 0 | 9546.49 | 34356.32 | 34356.32 |  | 22.4% | 21.74%
26-PC-30057 | Sparrow Hill Environmental Review Support | In Progress | Time and material | Big Sky | Brendan Melton | 197500 | 104876.75 | 81807.77 | 144017 | 144017 | 0 | 68917.84 | 75099.16 | 75099.16 |  | 53.1% | 47.85%
26-PC-30065 | Granite Pass Water Main - Cultural Resources Assessment | In Progress | Fixed fee | Big Sky | Javier Estrada | 132100 | 26367.16 | 20607.73 | 104411.84 | 104411.84 | 0 | 20838.3 | 83573.54 | 83573.54 |  | 20% | 19.96%
26-PC-30094 | Sumac Ridge Wastewater Plant Paleontological Monitoring | In Progress | Fixed fee | Big Sky | Carl Barajas | 98400 | 3906.48 | 1293.62 | 82193.52 | 82193.52 | 0 | 3266.46 | 78927.06 | 78927.06 |  | 4% | 3.97%
26-PC-30123 | Eagle Bend Park Improvements - Class III Survey | In Progress | Fixed fee | Big Sky | Bob Frye | 277200 | 59237.64 | 45677.97 | 210477.96 | 210477.96 | 0 | 44970.8 | 165507.16 | 165507.16 |  | 21.4% | 21.37%
26-PC-30139 | Quail Run Canal Lining Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 239600 | 19168 | 19168 | 198628.4 | 198628.4 | 0 | 15884.69 | 182743.71 | 182743.71 |  | 8% | 8%
26-PC-30180 | Willow Springs Architectural History Survey | Lab/Curation | Fixed fee | Big Sky | Carl Barajas | 115700 | 30024.15 | 24550.75 | 79798.29 | 79798.29 | 0 | 20705.53 | 59092.76 | 59092.76 |  | 26% | 25.95%
26-PC-30185 | Task Order 40: Cedar Hollow Cell Tower Curation | Final Reporting/Review | Fixed fee | Big Sky | Javier Estrada | 53400 | 3102.54 | 0 | 42447.66 | 42447.66 | 0 | 2466.42 | 39981.24 | 39981.24 |  | 5.8% | 5.81%
26-PC-30203 | Millbrook Pipeline Data Recovery | In Progress | Fixed fee | Big Sky | Carl Barajas | 134800 | 8721.56 | 7426.17 | 102421.04 | 102421.04 | 0 | 6626.59 | 95794.45 | 95794.45 |  | 6.5% | 6.47%
26-PC-30211 | Copper Flats Paleontological Monitoring | Lab/Curation | Fixed fee | Big Sky | Javier Estrada | 736100 | 0 | 0 | 498404.34 | 394730.97 | 103673.37 | 0 | 498404.34 | 394730.97 |  | 0% | 0%
26-PC-30273 | Task Order 40: Copper Flats Trail Class III Survey | Lab/Curation | Fixed fee | Big Sky | Bob Frye | 77200 | 6901.68 | 6811.24 | 53522.76 | 53522.76 | 0 | 4782.94 | 48739.82 | 48739.82 |  | 8.9% | 8.94%
26-PC-30287 | Task Order 40: Maple Fork Solar Historic Resources Evaluation | In Progress | Fixed fee | Big Sky | Javier Estrada | 10100 | 5081.31 | 5081.31 | 6193.32 | 6193.32 | 0 | 3115.89 | 3077.43 | 3077.43 |  | 50.3% | 50.31%
26-PC-30329 | Hackberry Bend Rail Siding Built Environment Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 483600 | 122060.64 | 103417.88 | 313904.76 | 313904.76 | 0 | 79237.08 | 234667.68 | 234667.68 |  | 25.2% | 25.24%
26-PC-30338 | On-Call: Saltgrass Mixed-Use Development Phase II Testing | Lab/Curation | Fixed fee | Big Sky | Brendan Melton | 268300 | 1529.31 | 1529.31 | 189811.91 | 146074.38 | 43737.53 | 1089.39 | 188722.52 | 144984.99 |  | 0.6% | 0.57%
26-PC-30349 | Phase I: Copper Flats Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Big Sky | Brendan Melton | 184200 | 30853.5 | 24917.81 | 105343.98 | 105343.98 | 0 | 17644.68 | 87699.3 | 87699.3 |  | 16.8% | 16.75%
26-PC-30351 | Wildrye Architectural History Survey | In Progress | Fixed fee | Big Sky | Bob Frye | 393800 | 132710.6 | 114207.61 | 262900.88 | 262900.88 | 0 | 88597.25 | 174303.63 | 174303.63 |  | 33.7% | 33.7%
26-PC-30396 | Tamarack Historic Resources Evaluation | In Progress | Fixed fee | Big Sky | Brendan Melton | 31300 | 0 | 0 | 23853.73 | 23853.73 | 0 | 0 | 23853.73 | 23853.73 |  | 0% | 0%
26-PC-30402 | On-Call: Cedar Hollow Highway Widening Paleontological Monitoring | Transferred Entity | Time and material | Big Sky | Carl Barajas | 151000 | 0 | 0 | 118603.52 | 90316.94 | 28286.58 | 0 | 118603.52 | 90316.94 |  | 0% | 0%
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Big Sky | Javier Estrada | 93100 | 0 | 0 | 63801.43 | 63801.43 | 0 | 65021.47 | -1220.04 | -1220.04 |  | 0% | 101.9%
26-PC-30457 | Wren Hollow Transmission Line - Data Recovery | Final Reporting/Review | Fixed fee | Big Sky | Bob Frye | 719800 | 120350.56 | 120350.56 | 547191.96 | 547191.96 | 0 | 91469.2 | 455722.76 | 455722.76 |  | 16.7% | 16.72%
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | In Progress | Fixed fee | Big Sky | Brendan Melton | 19900 | 19900 | 19400.11 | 14258.19 | 12707.2 | 1550.99 | 18074.33 | -3816.14 | -5367.13 |  | 100% | 126.8%
26-PC-30528 | Plover Cove School Campus Architectural History Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 112900 | 77009.09 | 71440.49 | 74017.24 | 74017.24 | 0 | 50490.81 | 23526.43 | 23526.43 |  | 68.2% | 68.21%
26-PC-30554 | Thistle Down Airport Apron Curation | In Progress | Fixed fee | Big Sky | Bob Frye | 139800 | 16678.14 | 9641.87 | 79741.92 | 79741.92 | 0 | 9511.95 | 70229.97 | 70229.97 |  | 11.9% | 11.93%
26-PC-30588 | Bramble Creek Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Bluegrass | Alice Galloway | 97000 | 11795.2 | 8704.54 | 75388.4 | 75388.4 | 0 | 9168.73 | 66219.67 | 66219.67 |  | 12.2% | 12.16%
26-PC-30602 | On-Call: Hawk Point Solar Cultural Resources Assessment | In Progress | Time and material | Bluegrass | Kiara Gillespie | 211900 | 55300 | 46785.39 | 152752.98 | 141361.45 | 11391.53 | 35317.52 | 117435.46 | 106043.93 |  | 26.1% | 23.12%
26-PC-30754 | On-Call: Kestrel Butte Highway Widening Archaeological Testing | Final Reporting/Review | Fixed fee | Bluegrass | Alice Galloway | 153300 | 12585.93 | 3576.72 | 106834.77 | 106834.77 | 0 | 8772.63 | 98062.14 | 98062.14 |  | 8.2% | 8.21%
26-PC-30815 | Juniper Wash Water Main Archaeological Testing | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 236000 | 41040.4 | 26899.17 | 177731.6 | 177731.6 | 0 | 30899.89 | 146831.71 | 146831.71 |  | 17.4% | 17.39%
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 209800 | 0 | 0 | 135467.86 | 135467.86 | 0 | 134699.95 | 767.91 | 767.91 |  | 0% | 99.43%
26-PC-30945 | Wildrye Reservoir Architectural History Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 179500 | 83772.65 | 69601.09 | 120265 | 120265 | 0 | 56121.76 | 64143.24 | 64143.24 |  | 46.7% | 46.67%
26-PC-30967 | Timber Gap Pipeline - Built Environment Survey | Final Reporting/Review | Time and material | Bluegrass | Alice Galloway | 173400 | 145618.75 | 132862.73 | 108877.86 | 108877.86 | 0 | 91606.15 | 17271.71 | 17271.71 |  | 84% | 84.14%
26-PC-31002 | North Fork Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway | 211500 | 29144.7 | 13311.23 | 164758.5 | 164758.5 | 0 | 22695.69 | 142062.81 | 142062.81 |  | 13.8% | 13.78%
26-PC-31037 | Cedar Hollow Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 168500 | 63086.4 | 52530.72 | 131345.75 | 131345.75 | 0 | 49181.51 | 82164.24 | 82164.24 |  | 37.4% | 37.44%
26-PC-31064 | Quail Run Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Gene Nixon | 74500 | 74500 | 74500 | 60394.3 | 53043.19 | 7351.11 | 76340.83 | -15946.53 | -23297.64 |  | 100% | 126.4%
26-PC-31174 | Task Order 33: Tamarack Housing Development Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 4400 | 0 | 0 | 2984.25 | 2426.55 | 557.7 | 2714.71 | 269.54 | -288.16 |  | 0% | 90.97%
26-PC-31182 | Elk Meadow School Campus Curation | In Progress | Fixed fee | Cascade | Jeff Spence | 73400 | 8925.44 | 5265.51 | 57596.98 | 57596.98 | 0 | 7004.67 | 50592.31 | 50592.31 |  | 12.2% | 12.16%
26-PC-31216 | On-Call: Saltgrass Fiber Route Environmental Review Support | In Progress | Time and material | Cascade | Preston Duarte | 172400 | 25313.25 | 6773.41 | 111025.6 | 111025.6 | 0 | 16381.13 | 94644.47 | 94644.47 |  | 14.7% | 14.75%
26-PC-31238 | Task Order 27: Wren Hollow Bridge Replacement Built Environment Survey | In Progress | Time and material | Cascade | Preston Duarte | 832700 | 154708.25 | 129716.05 | 533060.12 | 386912.7 | 146147.42 | 91086.67 | 441973.45 | 295826.03 |  | 18.6% | 17.09%
26-PC-31316 | Sparrow Hill Trail Architectural History Survey | Final Reporting/Review | Fixed fee | Cascade | Cassidy Gay | 148200 | 38117.04 | 29984.37 | 109860.66 | 109860.66 | 0 | 28261.6 | 81599.06 | 81599.06 |  | 25.7% | 25.72%
26-PC-31448 | Foxglove Class III Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 25800 | 7216.26 | 6639.74 | 20065.31 | 16136.4 | 3928.91 | 5612.5 | 14452.81 | 10523.9 |  | 28% | 27.97%
26-PC-31473 | Plover Cove Mixed-Use Development - Curation | In Progress | Fixed fee | Cascade | Cassidy Gay | 180800 | 11119.2 | 2976.07 | 112403.36 | 112403.36 | 0 | 6908.42 | 105494.94 | 105494.94 |  | 6.2% | 6.15%
26-PC-31484 | Maple Fork Wastewater Plant Data Recovery | In Progress | Fixed fee | Cascade | Jean Cooke | 31800 | 8223.48 | 7336.57 | 23427.06 | 23427.06 | 0 | 6057.36 | 17369.7 | 17369.7 |  | 25.9% | 25.86%
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | In Progress | Fixed fee | Cascade | Donald Lutz | 44400 | 31128.84 | 30936.04 | 34032.6 | 34032.6 | 0 | 23861.11 | 10171.49 | 10171.49 |  | 70.1% | 70.11%
26-PC-31537 | Raven Rock Park Improvements - Maritime Remote Sensing Survey | In Progress | Fixed fee | Cascade | Preston Duarte | 87300 | 4522.14 | 3456.58 | 54449.01 | 54449.01 | 0 | 2823.15 | 51625.86 | 51625.86 |  | 5.2% | 5.18%
26-PC-31568 | Sea Oat Housing Development - Section 106 Consultation | In Progress | Fixed fee | Cascade | Donald Lutz | 229100 | 38374.25 | 31669.56 | 148678.02 | 119301 | 29377.02 | 24897.44 | 123780.58 | 94403.56 |  | 16.8% | 16.75%
26-PC-31638 | Kestrel Butte Highway Widening - Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Gene Nixon | 170300 | 21611.07 | 13959.16 | 108060.44 | 100421.9 | 7638.54 | 13711.23 | 94349.21 | 86710.67 |  | 12.7% | 12.69%
26-PC-31648 | Rushgrass Draw Solar Data Recovery | In Progress | Fixed fee | Cascade | Jeff Spence | 388400 | 167672.28 | 138803.11 | 288425.84 | 288425.84 | 0 | 124527.73 | 163898.11 | 163898.11 |  | 43.2% | 43.17%
26-PC-31678 | Heron Marsh Wind Farm Phase I Survey | In Progress | Fixed fee | Cascade | Preston Duarte | 892800 | 297302.4 | 267319.35 | 641923.2 | 641923.2 | 0 | 213779.38 | 428143.82 | 428143.82 |  | 33.3% | 33.3%
26-PC-31692 | Phase III: Meadowlark Reservoir Paleontological Monitoring | In Progress | Fixed fee | Cascade | Preston Duarte | 615300 | 36733.41 | 14836.74 | 423803.64 | 362956.1 | 60847.54 | 25309.14 | 398494.5 | 337646.96 |  | 6% | 5.97%
26-PC-31716 | Saltgrass Wind Farm Data Recovery | In Progress | Fixed fee | Cascade | Donald Lutz | 13300 | 3517.85 | 2027.4 | 9413.74 | 9413.74 | 0 | 2489.99 | 6923.75 | 6923.75 |  | 26.5% | 26.45%
26-PC-31728 | On-Call: Slate Ridge Housing Development Data Recovery | In Progress | Fixed fee | Cascade | Jeff Spence | 38500 | 1963.5 | 332.4 | 31042.55 | 31042.55 | 0 | 1583.43 | 29459.12 | 29459.12 |  | 5.1% | 5.1%
26-PC-31802 | Bramble Creek Environmental Review Support | Lab/Curation | Fixed fee | Cascade | Jean Cooke | 53700 | 30651.96 | 28674.1 | 41655.09 | 41655.09 | 0 | 23774.89 | 17880.2 | 17880.2 |  | 57.1% | 57.08%
26-PC-31823 | Slate Ridge Phase II Testing | Final Reporting/Review | Fixed fee | Cascade | Jeff Spence | 173900 | 16068.36 | 5114.84 | 122721.23 | 122721.23 | 0 | 11344.92 | 111376.31 | 111376.31 |  | 9.2% | 9.24%
26-PC-31830 | Ember Valley Archaeological Testing | Transferred Entity | Fixed fee | Cascade | Cassidy Gay | 86700 | 40211.46 | 31491.18 | 59425.39 | 54460.35 | 4965.04 | 27563.45 | 31861.94 | 26896.9 |  | 46.4% | 46.38%
26-PC-31872 | Sumac Ridge Water Main Archaeological Testing | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 63800 | 33546.04 | 30533.41 | 45642.52 | 45642.52 | 0 | 24000.95 | 21641.57 | 21641.57 |  | 52.6% | 52.58%
26-PC-31881 | Fern Valley Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 125300 | 0 | 0 | 94955.6 | 80579.84 | 14375.76 | 0 | 94955.6 | 80579.84 |  | 0% | 0%
26-PC-32047 | On-Call: Sumac Ridge Mine Expansion Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox | 73200 | 51181.44 | 43002 | 51825.6 | 51825.6 | 0 | 36238.56 | 15587.04 | 15587.04 |  | 69.9% | 69.92%
26-PC-32069 | Task Order 25: Heron Marsh Wind Farm Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Chesapeake | Sandy Kerr | 844700 | 65802.13 | 59477.56 | 646026.56 | 646026.56 | 0 | 50316.32 | 595710.24 | 595710.24 |  | 7.8% | 7.79%
26-PC-32094 | Maple Fork Trail - Phase II Testing | In Progress | Time and material | Chesapeake | Bryan Mann | 19000 | 8805.75 | 8805.75 | 11274.6 | 11274.6 | 0 | 5989.44 | 5285.16 | 5285.16 |  | 46.3% | 53.12%
26-PC-32165 | Juniper Wash Park Improvements - Data Recovery | In Progress | Time and material | Chesapeake | Jason Oconnor | 501000 | 13806 | 3832.67 | 394086.6 | 394086.6 | 0 | 10370.06 | 383716.54 | 383716.54 |  | 2.8% | 2.63%
26-PC-32188 | Creosote Draw Reservoir Curation | In Progress | Fixed fee | Chesapeake | Ian Maddox | 91500 | 0 | 0 | 74856.15 | 74856.15 | 0 | 0 | 74856.15 | 74856.15 |  | 0% | 0%
26-PC-32288 | Quail Run Solar - Architectural History Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox | 400500 | 4365.45 | 2126.22 | 287318.7 | 287318.7 | 0 | 3140.21 | 284178.49 | 284178.49 |  | 1.1% | 1.09%
26-PC-32303 | Lone Pine Housing Development - Archaeological Testing | In Progress | Time and material | Chesapeake | Ian Maddox | 18700 | 816 | 277.36 | 13411.64 | 13411.64 | 0 | 852.48 | 12559.16 | 12559.16 |  | 4.4% | 6.36%
26-PC-32322 | Foxglove Fiber Route - Curation | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 317500 | 39751 | 37103.87 | 244665.5 | 244665.5 | 0 | 30629.91 | 214035.59 | 214035.59 |  | 12.5% | 12.52%
26-PC-32369 | Twin Buttes Water Main - Phase I Survey | In Progress | Fixed fee | Chesapeake | Ian Maddox | 730600 | 71233.5 | 65269.21 | 470798.64 | 470798.64 | 0 | 45896.51 | 424902.13 | 424902.13 |  | 9.8% | 9.75%
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann | 13700 | 13700 | 13641.82 | 9522.87 | 9522.87 | 0 | 31103.81 | -21580.94 | -21580.94 |  | 100% | 326.6%
26-PC-32396 | On-Call: Copper Flats Mixed-Use Development Curation | Final Reporting/Review | Time and material | Chesapeake | Sandy Kerr | 205600 | 5224.75 | 2772.21 | 152123.45 | 136826.23 | 15297.22 | 3555.36 | 148568.09 | 133270.87 |  | 2.5% | 2.34%
26-PC-32420 | Phase I: Copper Flats Water Main Architectural History Survey | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 324200 | 13843.34 | 4463.06 | 246926.01 | 225112.5 | 21813.51 | 10551.41 | 236374.6 | 214561.09 |  | 4.3% | 4.27%
26-PC-32442 | Sumac Ridge Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 53400 | 17088 | 14860.55 | 33316.26 | 33316.26 | 0 | 10661.31 | 22654.95 | 22654.95 |  | 32% | 32%
26-PC-32453 | Quail Run Housing Development Phase II Testing | In Progress | Time and material | Chesapeake | Ian Maddox | 103800 | 6785.75 | 1853.51 | 74927.88 | 58312.8 | 16615.08 | 4515.47 | 70412.41 | 53797.33 |  | 6.5% | 6.03%
26-PC-32540 | Task Order 36: Granite Pass Mixed-Use Development Phase II Testing | Lab/Curation | Time and material | Chesapeake | Bryan Mann | 846100 | 79570 | 49253.92 | 625775.56 | 625775.56 | 0 | 55637.33 | 570138.23 | 570138.23 |  | 9.4% | 8.89%
26-PC-32556 | Maple Fork Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 45700 | 15771.07 | 13650.9 | 32259.63 | 32259.63 | 0 | 11132.77 | 21126.86 | 21126.86 |  | 34.5% | 34.51%
26-PC-32563 | On-Call: Creosote Draw Substation Phase I Survey | Transferred Entity | Fixed fee | Chesapeake | Bryan Mann | 534900 | 133136.61 | 127694.45 | 344315.13 | 344315.13 | 0 | 85685.88 | 258629.25 | 258629.25 |  | 24.9% | 24.89%
26-PC-32594 | On-Call: Tamarack Rail Siding Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 94400 | 51193.12 | 38376.64 | 71536.32 | 71536.32 | 0 | 38790.59 | 32745.73 | 32745.73 |  | 54.2% | 54.23%
26-PC-32614 | Fern Valley Architectural History Survey | In Progress | Time and material | Chesapeake | Ian Maddox | 29700 | 0 | 0 | 20748.42 | 20748.42 | 0 | 0 | 20748.42 | 20748.42 |  | 0% | 0%
26-PC-32646 | Goldfinch Historic Resources Evaluation | In Progress | Time and material | Chesapeake | Ian Maddox | 48600 | 24344.25 | 19074.93 | 33922.8 | 33922.8 | 0 | 15954.4 | 17968.4 | 17968.4 |  | 50.1% | 47.03%
26-PC-32707 | On-Call: Creosote Draw Transmission Line Cultural Resources Monitoring | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 327400 | 152306.48 | 137397.62 | 229376.44 | 229376.44 | 0 | 106701.23 | 122675.21 | 122675.21 |  | 46.5% | 46.52%
26-PC-32711 | Creosote Draw Phase I Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 62100 | 12997.53 | 10647.65 | 44997.66 | 44997.66 | 0 | 9419.95 | 35577.71 | 35577.71 |  | 20.9% | 20.93%
26-PC-32725 | Willow Springs Wind Farm - GIS Mapping | Final Reporting/Review | Fixed fee | Chesapeake | Bryan Mann | 26300 | 16079.82 | 12170.12 | 18699.3 | 18699.3 | 0 | 11432.01 | 7267.29 | 7267.29 |  | 61.1% | 61.14%
26-PC-32727 | North Fork Mine Expansion - Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Chesapeake | Alexandria Wilkinson | 70100 | 57594.16 | 57594.16 | 47310.49 | 47310.49 | 0 | 38868.52 | 8441.97 | 8441.97 |  | 82.2% | 82.16%
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Cost Tracking on Closed Project | Time and material | Chesapeake | Sandy Kerr | 137100 | 0 | 0 | 100617.66 | 93287.5 | 7330.16 | 122245.29 | -21627.63 | -28957.79 |  | 0% | 121.5%
26-PC-32745 | Task Order 37: Hawk Point Park Improvements Phase II Testing | In Progress | Fixed fee | Chesapeake | Ian Maddox | 135300 | 56149.5 | 34745.99 | 89758.02 | 89758.02 | 0 | 37247.73 | 52510.29 | 52510.29 |  | 41.5% | 41.5%
26-PC-32773 | Oak Terrace Paleontological Monitoring | In Progress | Fixed fee | Front Range | Mindy Galvan | 48100 | 21236.15 | 16486.92 | 32496.36 | 32496.36 | 0 | 14347.77 | 18148.59 | 18148.59 |  | 44.2% | 44.15%
26-PC-32852 | Task Order 39: Foxglove Highway Widening Data Recovery | In Progress | Time and material | Front Range | Joanna Herrera | 148800 | 31449.25 | 18923.38 | 95395.68 | 95395.68 | 0 | 18228.56 | 77167.12 | 77167.12 |  | 21.1% | 19.11%
26-PC-32985 | Pine Hollow Built Environment Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 106500 | 64783.95 | 55174.32 | 89214.38 | 75741.38 | 13473 | 54267.06 | 34947.32 | 21474.32 |  | 60.8% | 60.83%
26-PC-33017 | Redbud Battery Storage - Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Mindy Galvan | 588600 | 188116.56 | 188116.56 | 441413.1 | 336449.96 | 104963.14 | 141067.52 | 300345.58 | 195382.44 |  | 32% | 31.96%
26-PC-33099 | Eagle Bend Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Joanna Herrera | 164900 | 29055.38 | 16045.73 | 122091.96 | 122091.96 | 0 | 21510.66 | 100581.3 | 100581.3 |  | 17.6% | 17.62%
26-PC-33127 | Fern Valley Phase I Survey | In Progress | Time and material | Front Range | Kimberly Daugherty | 179500 | 46153.5 | 39555.28 | 119968.02 | 92441.25 | 27526.77 | 30425.42 | 89542.6 | 62015.83 |  | 25.7% | 25.36%
26-PC-33162 | Phase III: Yarrow Point Airport Apron GIS Mapping | In Progress | Time and material | Front Range | Dean Velazquez | 81900 | 9863.25 | 8708.14 | 55036.8 | 55036.8 | 0 | 6614.56 | 48422.24 | 48422.24 |  | 12% | 12.02%
26-PC-33276 | Quail Run Housing Development Archaeological Testing | In Progress | Time and material | Front Range | Jeremy Tran | 64200 | 15702.5 | 15096.5 | 42609.54 | 42609.54 | 0 | 10124.5 | 32485.04 | 32485.04 |  | 24.5% | 23.76%
26-PC-33485 | Sea Oat Harbor Dredging GIS Mapping | In Progress | Time and material | Front Range | Dean Velazquez | 563800 | 45105.5 | 22501.56 | 406950.84 | 406950.84 | 0 | 29789.86 | 377160.98 | 377160.98 |  | 8% | 7.32%
26-PC-33505 | Stone Mill Park Improvements - Maritime Remote Sensing Survey | In Progress | Fixed fee | Front Range | Mindy Galvan | 105100 | 1492.42 | 398.58 | 81200.26 | 81200.26 | 0 | 1152.87 | 80047.39 | 80047.39 |  | 1.4% | 1.42%
26-PC-33563 | Foxglove Phase I Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 61100 | 0 | 0 | 42098.14 | 35698.3 | 6399.84 | 0 | 42098.14 | 35698.3 |  | 0% | 0%
26-PC-33588 | Fern Valley Trail - Cultural Resources Assessment | Lab/Curation | Time and material | Front Range | Joanna Herrera | 207400 | 38333.25 | 35440.47 | 141868.32 | 122263.6 | 19604.72 | 25436.79 | 116431.53 | 96826.81 |  | 18.5% | 17.93%
26-PC-33660 | Task Order 33: Fern Valley Water Main Section 106 Consultation | In Progress | Fixed fee | Front Range | Dean Velazquez | 108400 | 24216.56 | 7479.68 | 94229.41 | 77792 | 16437.41 | 21052.74 | 73176.67 | 56739.26 |  | 22.3% | 22.34%
26-PC-33684 | On-Call: Juniper Wash Airport Apron Paleontological Monitoring | Final Reporting/Review | Time and material | Front Range | Kimberly Daugherty | 24000 | 4253.75 | 1910.97 | 17450.4 | 17450.4 | 0 | 2500.59 | 14949.81 | 14949.81 |  | 17.7% | 14.33%
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Final Reporting/Review | Fixed fee | Great Lakes | Karl Valenzuela | 21700 | 21700 | 11375.68 | 18501.42 | 18501.42 | 0 | 21928.62 | -3427.2 | -3427.2 |  | 100% | 118.5%
26-PC-33705 | Twin Buttes Phase I Survey | In Progress | Fixed fee | Great Lakes | Karl Valenzuela | 211200 | 101629.44 | 84698.25 | 166784.64 | 166784.64 | 0 | 80257.44 | 86527.2 | 86527.2 |  | 48.1% | 48.12%
26-PC-33719 | Saltgrass GIS Mapping | In Progress | Fixed fee | Great Lakes | Gina Beltran | 394200 | 11274.12 | 4081.27 | 310235.4 | 310235.4 | 0 | 8878.32 | 301357.08 | 301357.08 |  | 2.9% | 2.86%
26-PC-33743 | Raven Rock Canal Lining Architectural History Survey | In Progress | Fixed fee | Great Lakes | Brendan Padilla | 111800 | 61277.58 | 58305.85 | 75766.86 | 75766.86 | 0 | 41526.74 | 34240.12 | 34240.12 |  | 54.8% | 54.81%
26-PC-33834 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 204800 | 48885.76 | 40950.62 | 158052.15 | 136321.79 | 21730.36 | 37725.67 | 120326.48 | 98596.12 |  | 23.9% | 23.87%
26-PC-33896 | Maple Fork Trail Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 69800 | 21798.54 | 14218.1 | 48734.36 | 48734.36 | 0 | 15222.15 | 33512.21 | 33512.21 |  | 31.2% | 31.23%
26-PC-33913 | Windmill Flat Section 106 Consultation | Final Reporting/Review | Time and material | Great Lakes | Angelica Cervantes | 31100 | 1702.75 | 828.06 | 20015.96 | 20015.96 | 0 | 1134.5 | 18881.46 | 18881.46 |  | 5.5% | 5.67%
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 76400 | 76400 | 70250.02 | 53087.85 | 46646.64 | 6441.21 | 80951.18 | -27863.33 | -34304.54 |  | 100% | 152.5%
26-PC-34114 | Granite Pass Canal Lining - Section 106 Consultation | In Progress | Time and material | Great Lakes | Brendan Padilla | 216500 | 17201 | 12093.51 | 145812.75 | 145812.75 | 0 | 9715.07 | 136097.68 | 136097.68 |  | 7.9% | 6.66%
26-PC-34198 | Tansy Flat Pipeline - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Brendan Padilla | 65600 | 16223.25 | 16223.25 | 47297.6 | 47297.6 | 0 | 9004.51 | 38293.09 | 38293.09 |  | 24.7% | 19.04%
26-PC-34297 | Badger Hollow Historic Resources Evaluation | In Progress | Fixed fee | Great Lakes | Reginald Koch | 41700 | 3494.46 | 3494.46 | 29306.76 | 29306.76 | 0 | 2455.17 | 26851.59 | 26851.59 |  | 8.4% | 8.38%
26-PC-34336 | Pine Hollow Solar Architectural History Survey | In Progress | Fixed fee | Great Lakes | Robin Mercado | 56500 | 17159.05 | 16619.72 | 40414.45 | 40414.45 | 0 | 12273.01 | 28141.44 | 28141.44 |  | 30.4% | 30.37%
26-PC-34394 | Ember Valley Battery Storage Maritime Remote Sensing Survey | In Progress | Time and material | Great Lakes | Angelica Cervantes | 134200 | 0 | 0 | 94370.11 | 80628.03 | 13742.08 | 0 | 94370.11 | 80628.03 |  | 0% | 0%
26-PC-34400 | Wren Hollow Curation | In Progress | Fixed fee | Great Lakes | Leonard Mejia | 34200 | 2072.52 | 1844.21 | 23833.56 | 20735.65 | 3097.91 | 1444.35 | 22389.21 | 19291.3 |  | 6.1% | 6.06%
26-PC-34432 | Stone Mill Bridge Replacement - GIS Mapping | Final Reporting/Review | Fixed fee | Great Lakes | Reginald Koch | 117900 | 10245.51 | 6103.62 | 80620.02 | 80620.02 | 0 | 7006.23 | 73613.79 | 73613.79 |  | 8.7% | 8.69%
26-PC-34477 | Willow Springs Pipeline - Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Geoffrey Fernandez | 212500 | 23481.25 | 15454.44 | 157143.75 | 157143.75 | 0 | 17368.48 | 139775.27 | 139775.27 |  | 11.1% | 11.05%
26-PC-34487 | Quail Run Airport Apron - Phase I Survey | In Progress | Time and material | Great Lakes | Jeff Pugh | 488600 | 212913.75 | 171542.56 | 348176.36 | 348176.36 | 0 | 135902.87 | 212273.49 | 212273.49 |  | 43.6% | 39.03%
26-PC-34552 | Blue Heron Mine Expansion Phase I Survey | Lab/Curation | Fixed fee | Great Lakes | Geoffrey Fernandez | 245500 | 4639.95 | 2962.54 | 205115.25 | 205115.25 | 0 | 3881.67 | 201233.58 | 201233.58 |  | 1.9% | 1.89%
26-PC-34602 | Phase III: Sandpiper Park Improvements Historic Resources Evaluation | In Progress | Fixed fee | Great Lakes | Brendan Padilla | 36800 | 32321.44 | 28986.41 | 26501.12 | 21328.5 | 5172.62 | 23274.94 | 3226.18 | -1946.44 |  | 87.8% | 87.83%
26-PC-34611 | Wren Hollow Pipeline Environmental Review Support | In Progress | Time and material | Great Lakes | Robin Mercado | 365800 | 0 | 0 | 264180.76 | 264180.76 | 0 | 0 | 264180.76 | 264180.76 |  | 0% | 0%
26-PC-34725 | Redbud Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Kathleen Galvan | 107600 | 12083.48 | 8872.18 | 89211.16 | 89211.16 | 0 | 10016.64 | 79194.52 | 79194.52 |  | 11.2% | 11.23%
26-PC-34757 | Kestrel Butte Data Recovery | In Progress | Time and material | Great Lakes | Angelica Cervantes | 43800 | 43800 | 29653.46 | 30230.76 | 30230.76 | 0 | 49508.25 | -19277.49 | -19277.49 |  | 100% | 163.8%
26-PC-34906 | Cedar Hollow Harbor Dredging - Curation | In Progress | Fixed fee | Gulf Coast | Sean Jennings | 81100 | 41961.14 | 34013.4 | 60821.43 | 44369.15 | 16452.28 | 31471.96 | 29349.47 | 12897.19 |  | 51.7% | 51.74%
26-PC-34965 | On-Call: Pebble Beach Road Fiber Route Section 106 Consultation | Final Reporting/Review | Fixed fee | Gulf Coast East | Wyatt Erickson | 131600 | 0 | 0 | 95225.76 | 95225.76 | 0 | 0 | 95225.76 | 95225.76 |  | 0% | 0%
26-PC-34982 | Sandpiper Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 10600 | 10600 | 7692.83 | 7895.94 | 7895.94 | 0 | 18818.09 | -10922.15 | -10922.15 |  | 100% | 238.3%
26-PC-35056 | Yarrow Point Cell Tower - Section 106 Consultation | Lab/Curation | Fixed fee | Gulf Coast West | Sean Jennings | 92800 | 46381.44 | 43606.66 | 78555.2 | 78555.2 | 0 | 39261.22 | 39293.98 | 39293.98 |  | 50% | 49.98%
26-PC-35062 | Phase I: Falcon Mesa Park Improvements Data Recovery | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 267300 | 30659.31 | 4507.74 | 207542.06 | 185979.15 | 21562.91 | 23807.74 | 183734.32 | 162171.41 |  | 11.5% | 11.47%
26-PC-35063 | Meadowlark School Campus - Phase I Survey | Final Reporting/Review | Fixed fee | Gulf Coast East | Bernard Erickson | 112100 | 59166.38 | 53777.48 | 70129.76 | 70129.76 | 0 | 37016.5 | 33113.26 | 33113.26 |  | 52.8% | 52.78%
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 29600 | 29600 | 22003.12 | 19287.36 | 19287.36 | 0 | 56287.28 | -36999.92 | -36999.92 |  | 100% | 291.8%
26-PC-35158 | Sparrow Hill Trail Phase I Survey | In Progress | Fixed fee | Gulf Coast | Bernard Erickson | 41600 | 12629.76 | 5669.01 | 27755.93 | 24147.48 | 3608.45 | 8426.77 | 19329.16 | 15720.71 |  | 30.4% | 30.36%
26-PC-35193 | Heron Marsh Reservoir - Phase II Testing | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 102600 | 82510.92 | 71608.18 | 74022.89 | 54115.25 | 19907.64 | 59527.5 | 14495.39 | -5412.25 |  | 80.4% | 80.42%
26-PC-35201 | Plover Cove Transmission Line Data Recovery | Lab/Curation | Fixed fee | Gulf Coast | Sean Jennings | 51600 | 1558.32 | 145.25 | 40057.08 | 40057.08 | 0 | 1211.47 | 38845.61 | 38845.61 |  | 3% | 3.02%
26-PC-35220 | Badger Hollow Highway Widening GIS Mapping | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 109500 | 4400.75 | 1288.42 | 69598.2 | 69598.2 | 0 | 3074.48 | 66523.72 | 66523.72 |  | 4% | 4.42%
26-PC-35302 | Task Order 37: Hackberry Bend Battery Storage Cultural Resources Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 82400 | 32292.56 | 21108.58 | 69199.52 | 69199.52 | 0 | 27118.13 | 42081.39 | 42081.39 |  | 39.2% | 39.19%
26-PC-35318 | Copper Flats Curation | In Progress | Fixed fee | Gulf Coast West | Wyatt Erickson | 153900 | 37289.97 | 27419.19 | 103851.72 | 103851.72 | 0 | 25162.21 | 78689.51 | 78689.51 |  | 24.2% | 24.23%
26-PC-35381 | Badger Hollow Mine Expansion Archaeological Testing | In Progress | Fixed fee | High Desert | Bridget Maddox | 77800 | 56210.5 | 45584.74 | 51064.93 | 45374 | 5690.93 | 36896.81 | 14168.12 | 8477.19 |  | 72.3% | 72.25%
26-PC-35401 | Raven Rock Phase II Testing | In Progress | Time and material | High Desert | Bridget Maddox | 312900 | 35485.5 | 8384.38 | 205376.26 | 152268.46 | 53107.8 | 21093.83 | 184282.43 | 131174.63 |  | 11.3% | 10.27%
26-PC-35449 | Saltgrass Cultural Resources Monitoring | In Progress | Time and material | High Desert | Bridget Maddox | 145800 | 31446 | 7978.96 | 103226.4 | 103226.4 | 0 | 22115.43 | 81110.97 | 81110.97 |  | 21.6% | 21.42%
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 68900 | 59529.6 | 49947.75 | 53679.99 | 53679.99 | 0 | 46380.29 | 7299.7 | 7299.7 |  | 86.4% | 86.4%
26-PC-35583 | On-Call: Eagle Bend Highway Widening Phase II Testing | In Progress | Time and material | High Desert | Jody Wang | 39700 | 2479.5 | 721.99 | 28536.36 | 28536.36 | 0 | 1470.29 | 27066.07 | 27066.07 |  | 6.2% | 5.15%
26-PC-35596 | Millbrook Solar GIS Mapping | Lab/Curation | Fixed fee | High Desert | Eileen Poole | 197200 | 42141.64 | 27554.12 | 149142.36 | 149142.36 | 0 | 31870.85 | 117271.51 | 117271.51 |  | 21.4% | 21.37%
26-PC-35635 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 223600 | 64486.24 | 42964.82 | 138900.32 | 138900.32 | 0 | 40059.7 | 98840.62 | 98840.62 |  | 28.8% | 28.84%
26-PC-35650 | Aspen Ridge Harbor Dredging - Maritime Remote Sensing Survey | In Progress | Time and material | High Desert | Jody Wang | 155300 | 0 | 0 | 100626.66 | 93441.15 | 7185.51 | 0 | 100626.66 | 93441.15 |  | 0% | 0%
26-PC-35730 | Larkspur Solar Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 74800 | 3179 | 1495.98 | 50078.6 | 50078.6 | 0 | 2126.96 | 47951.64 | 47951.64 |  | 4.3% | 4.25%
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | High Desert | Jody Wang | 26300 | 26300 | 26300 | 19575.09 | 19575.09 | 0 | 22787.95 | -3212.86 | -3212.86 |  | 100% | 116.4%
26-PC-35789 | Cedar Hollow Environmental Review Support | In Progress | Time and material | High Desert | Eileen Poole | 3800 | 159.5 | 27.38 | 2575.26 | 2575.26 | 0 | 95.95 | 2479.31 | 2479.31 |  | 4.2% | 3.73%
26-PC-35803 | Tamarack Airport Apron GIS Mapping | In Progress | Time and material | High Desert | Jody Wang | 82900 | 217.5 | 87.2 | 52144.1 | 52144.1 | 0 | 123.8 | 52020.3 | 52020.3 |  | 0.3% | 0.24%
26-PC-35811 | Phase III: Wildrye Solar Architectural History Survey | In Progress | Time and material | High Desert | Eileen Poole | 19500 | 0 | 0 | 12897.3 | 12897.3 | 0 | 0 | 12897.3 | 12897.3 |  | 0% | 0%
26-PC-35828 | Aspen Ridge Park Improvements - Class III Survey | In Progress | Time and material | High Desert | Jody Wang | 48300 | 27612.25 | 23270.14 | 31733.1 | 31733.1 | 0 | 19018.68 | 12714.42 | 12714.42 |  | 57.2% | 59.93%
26-PC-35920 | Phase I: Creosote Draw Park Improvements Historic Resources Evaluation | In Progress | Time and material | High Desert | Eileen Poole | 61600 | 0 | 0 | 42591.82 | 34150 | 8441.82 | 0 | 42591.82 | 34150 |  | 0% | 0%
26-PC-35937 | Pebble Beach Road Built Environment Survey | Transferred Entity | Fixed fee | High Desert | Kathy Hurley | 73700 | 7274.19 | 1654.38 | 51155.17 | 51155.17 | 0 | 5050.91 | 46104.26 | 46104.26 |  | 9.9% | 9.87%
26-PC-35984 | Timber Gap Bridge Replacement Archaeological Testing | Final Reporting/Review | Time and material | High Desert | Bridget Maddox | 75200 | 13619.25 | 7059.33 | 47215.34 | 40029.6 | 7185.74 | 10159.66 | 37055.68 | 29869.94 |  | 18.1% | 21.52%
26-PC-36110 | Blue Heron Canal Lining - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox | 776100 | 55413.54 | 49922.17 | 567018.66 | 567018.66 | 0 | 40481.07 | 526537.59 | 526537.59 |  | 7.1% | 7.14%
26-PC-36247 | Harbor View Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Maurice Dodson | 44300 | 522.74 | 202 | 33455.36 | 33455.36 | 0 | 394.65 | 33060.71 | 33060.71 |  | 1.2% | 1.18%
26-PC-36281 | Saltgrass Mixed-Use Development Architectural History Survey | In Progress | Time and material | Island | Becky Velazquez | 25900 | 202.5 | 109.61 | 16954.14 | 16954.14 | 0 | 138.86 | 16815.28 | 16815.28 |  | 0.8% | 0.82%
26-PC-36394 | Meadowlark Cultural Resources Monitoring | In Progress | Fixed fee | Island | Briana Melton | 61900 | 3237.37 | 1344.78 | 39879.42 | 32483.92 | 7395.5 | 2084.51 | 37794.91 | 30399.41 |  | 5.2% | 5.23%
26-PC-36396 | Task Order 9: Twin Buttes Solar Architectural History Survey | In Progress | Fixed fee | Island | Briana Melton | 77700 | 9759.12 | 7129.67 | 47283.31 | 43484.4 | 3798.91 | 5937.18 | 41346.13 | 37547.22 |  | 12.6% | 12.56%
26-PC-36416 | Task Order 2: Thistle Down Wind Farm Archaeological Testing | Lab/Curation | Fixed fee | Island | Maurice Dodson | 589600 | 270626.4 | 239675.91 | 462173.13 | 351925 | 110248.13 | 212155.53 | 250017.6 | 139769.47 |  | 45.9% | 45.9%
26-PC-36537 | Yarrow Point Park Improvements Built Environment Survey | In Progress | Fixed fee | Island | Becky Velazquez | 125300 | 39544.68 | 36421.55 | 86482.06 | 86482.06 | 0 | 27291.85 | 59190.21 | 59190.21 |  | 31.6% | 31.56%
26-PC-36581 | Harbor View Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Briana Melton | 127600 | 48755.96 | 43545.62 | 76674.84 | 76674.84 | 0 | 29299.63 | 47375.21 | 47375.21 |  | 38.2% | 38.21%
26-PC-36602 | Sea Oat Airport Apron Cultural Resources Monitoring | In Progress | Fixed fee | Lakeshore | Terrence Gillespie | 396600 | 57269.04 | 42958.07 | 288646.28 | 223565.16 | 65081.12 | 41680.56 | 246965.72 | 181884.6 |  | 14.4% | 14.44%
26-PC-36726 | Willow Springs Cultural Resources Assessment | In Progress | Fixed fee | Lakeshore | Lucas Benson | 153200 | 16668.16 | 0 | 110288.68 | 110288.68 | 0 | 12003.91 | 98284.77 | 98284.77 |  | 10.9% | 10.88%
26-PC-36749 | Windmill Flat Water Main - Cultural Resources Assessment | In Progress | Fixed fee | Lakeshore | Lucas Benson | 199000 | 95321 | 85531.32 | 173567.8 | 173567.8 | 0 | 83133.93 | 90433.87 | 90433.87 |  | 47.9% | 47.9%
26-PC-36750 | Task Order 15: North Fork Canal Lining Data Recovery | In Progress | Time and material | Lakeshore | Terrence Gillespie | 121800 | 24027.5 | 11545.83 | 80948.28 | 80948.28 | 0 | 13368.46 | 67579.82 | 67579.82 |  | 19.7% | 16.51%
26-PC-36775 | Falcon Mesa Cultural Resources Monitoring | Transferred Entity | Fixed fee | Hill Country | Gail Meza | 90800 | 190.68 | 37.35 | 77565.54 | 58243.86 | 19321.68 | 160.5 | 77405.04 | 58083.36 |  | 0.2% | 0.21%
26-PC-36802 | Thistle Down Canal Lining - Cultural Resources Assessment | Final Reporting/Review | Time and material | Hill Country | Gail Meza | 71600 | 0 | 0 | 52303.8 | 52303.8 | 0 | 0 | 52303.8 | 52303.8 |  | 0% | 0%
26-PC-36828 | Phase III: Rushgrass Draw Canal Lining GIS Mapping | In Progress | Time and material | Hill Country | Gail Meza | 28100 | 1368.5 | 1198.92 | 19006.84 | 19006.84 | 0 | 844.43 | 18162.41 | 18162.41 |  | 4.9% | 4.44%
26-PC-36861 | North Fork Park Improvements - Cultural Resources Assessment | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 463900 | 11411.94 | 8632.46 | 337255.3 | 337255.3 | 0 | 8285.6 | 328969.7 | 328969.7 |  | 2.5% | 2.46%
26-PC-36944 | Copper Flats Levee Repair - Data Recovery | Final Reporting/Review | Fixed fee | Hill Country | Marcus Shea | 102000 | 18278.4 | 15058.85 | 68921.4 | 68921.4 | 0 | 12352.09 | 56569.31 | 56569.31 |  | 17.9% | 17.92%
26-PC-36945 | Hawk Point Fiber Route - Maritime Remote Sensing Survey | In Progress | Fixed fee | Hill Country | Gail Meza | 496500 | 211211.1 | 185861.75 | 329824.95 | 329824.95 | 0 | 140294.42 | 189530.53 | 189530.53 |  | 42.5% | 42.54%
26-PC-37024 | Hackberry Bend Mine Expansion - Maritime Remote Sensing Survey | In Progress | Fixed fee | Hill Country | Danielle Villanueva | 78900 | 12979.05 | 10889.26 | 63394.72 | 59087.34 | 4307.38 | 10425.9 | 52968.82 | 48661.44 |  | 16.5% | 16.45%
26-PC-37051 | On-Call: Sandpiper Rail Siding Section 106 Consultation | Lab/Curation | Fixed fee | Hill Country | Theresa Fernandez | 365900 | 10903.82 | 7006.96 | 243543.04 | 243543.04 | 0 | 7245.79 | 236297.25 | 236297.25 |  | 3% | 2.98%
26-PC-37073 | Kestrel Butte Pipeline Curation | In Progress | Fixed fee | Hill Country | Marcus Shea | 441700 | 11219.18 | 512.97 | 346822.84 | 346822.84 | 0 | 8825.19 | 337997.65 | 337997.65 |  | 2.5% | 2.54%
26-PC-37089 | Rushgrass Draw GIS Mapping | In Progress | Time and material | Hill Country | Gail Meza | 28900 | 1656.25 | 1656.25 | 19054.14 | 14854.2 | 4199.94 | 1063.17 | 17990.97 | 13791.03 |  | 5.7% | 5.58%
26-PC-37136 | Yarrow Point Housing Development - Section 106 Consultation | In Progress | Fixed fee | Hill Country | Marcus Shea | 153700 | 54271.47 | 51231.02 | 109797.26 | 86150.47 | 23646.79 | 38767.55 | 71029.71 | 47382.92 |  | 35.3% | 35.31%
26-PC-37138 | Granite Pass Canal Lining - Environmental Review Support | Final Reporting/Review | Time and material | Hill Country | Gail Meza | 315800 | 49327.5 | 44944.82 | 223705.16 | 164829.33 | 58875.83 | 33971.44 | 189733.72 | 130857.89 |  | 15.6% | 15.19%
26-PC-37139 | Goldfinch Reservoir Environmental Review Support | In Progress | Time and material | Hill Country | Theresa Fernandez | 1070500 | 113864.25 | 91019.47 | 734587.52 | 579542.04 | 155045.48 | 66797.88 | 667789.64 | 512744.16 |  | 10.6% | 9.09%
26-PC-37196 | Sea Oat Built Environment Survey | In Progress | Fixed fee | Hill Country | Suzanne Mcmillan | 26900 | 0 | 0 | 22881.14 | 22881.14 | 0 | 0 | 22881.14 | 22881.14 |  | 0% | 0%
26-PC-37204 | On-Call: Saltgrass Housing Development Built Environment Survey | In Progress | Time and material | Hill Country | Gail Meza | 201900 | 73828.25 | 69269.36 | 145630.47 | 145630.47 | 0 | 45387.98 | 100242.49 | 100242.49 |  | 36.6% | 31.17%
26-PC-37271 | Maple Fork Wind Farm Built Environment Survey | In Progress | Time and material | Hill Country | Gail Meza | 879900 | 258254.5 | 204281.16 | 587259.92 | 482467.22 | 104792.7 | 171065.39 | 416194.53 | 311401.83 |  | 29.4% | 29.13%
26-PC-37282 | Windmill Flat Harbor Dredging GIS Mapping | In Progress | Fixed fee | Hill Country | Suzanne Mcmillan | 48800 | 761.28 | 644.79 | 41616.64 | 41616.64 | 0 | 649.35 | 40967.29 | 40967.29 |  | 1.6% | 1.56%
26-PC-37317 | Hackberry Bend Environmental Review Support | In Progress | Time and material | Hill Country | Danielle Villanueva | 348700 | 11592.75 | 10796.07 | 224737.15 | 224737.15 | 0 | 7817.14 | 216920.01 | 216920.01 |  | 3.3% | 3.48%
26-PC-37322 | Maple Fork Canal Lining Built Environment Survey | In Progress | Time and material | Hill Country | Danielle Villanueva | 30900 | 5098.25 | 1737.78 | 21095.43 | 21095.43 | 0 | 2933.98 | 18161.45 | 18161.45 |  | 16.5% | 13.91%
26-PC-37329 | Stone Mill Battery Storage Built Environment Survey | Final Reporting/Review | Fixed fee | Hill Country | Glen Delacruz | 32600 | 20707.52 | 14930.69 | 25463.86 | 25463.86 | 0 | 16175.73 | 9288.13 | 9288.13 |  | 63.5% | 63.52%
26-PC-37368 | Cedar Hollow Mine Expansion - Section 106 Consultation | In Progress | Fixed fee | Piedmont | Maria Parrish | 201100 | 9069.61 | 2512.18 | 123555.84 | 123555.84 | 0 | 5568.91 | 117986.93 | 117986.93 |  | 4.5% | 4.51%
26-PC-37428 | Ember Valley Section 106 Consultation | In Progress | Fixed fee | Piedmont | Megan Pineda | 57900 | 16895.22 | 2174.77 | 44206.65 | 44206.65 | 0 | 12898.79 | 31307.86 | 31307.86 |  | 29.2% | 29.18%
26-PC-37513 | Harbor View Housing Development Paleontological Monitoring | Final Reporting/Review | Fixed fee | Piedmont | Jody Chung | 34700 | 0 | 0 | 23634.17 | 23634.17 | 0 | 0 | 23634.17 | 23634.17 |  | 0% | 0%
26-PC-37543 | Pebble Beach Road Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Maria Parrish | 330200 | 149382.48 | 133334.89 | 218394.28 | 218394.28 | 0 | 98791.1 | 119603.18 | 119603.18 |  | 45.2% | 45.24%
26-PC-37559 | Badger Hollow Paleontological Monitoring | In Progress | Time and material | Piedmont | Jody Chung | 44300 | 44300 | 33494.39 | 28024.18 | 28024.18 | 0 | 45539.17 | -17514.99 | -17514.99 |  | 100% | 162.5%
26-PC-37671 | Harbor View Mixed-Use Development Architectural History Survey | In Progress | Time and material | Piedmont | Annette Vaughan | 145900 | 9234.5 | 9234.5 | 92486.01 | 92486.01 | 0 | 6017.12 | 86468.89 | 86468.89 |  | 6.3% | 6.51%
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Piedmont | Jody Chung | 40300 | 31772.52 | 24174.36 | 32312.54 | 32312.54 | 0 | 25475.14 | 6837.4 | 6837.4 |  | 78.8% | 78.84%
26-PC-37709 | Sage Flat Phase I Survey | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 31500 | 31500 | 16533.22 | 21725.55 | 21725.55 | 0 | 30289.1 | -8563.55 | -8563.55 |  | 100% | 139.4%
26-PC-37788 | Sumac Ridge Cultural Resources Assessment | In Progress | Fixed fee | Piedmont | Jody Chung | 1112800 | 22812.4 | 20528.14 | 826476.56 | 826476.56 | 0 | 16908.48 | 809568.08 | 809568.08 |  | 2.1% | 2.05%
26-PC-37965 | Redbud Cultural Resources Assessment | In Progress | Time and material | Piedmont | Annette Vaughan | 55400 | 50946.25 | 31520.73 | 34625 | 34625 | 0 | 31687.21 | 2937.79 | 2937.79 |  | 92% | 91.52%
26-PC-38025 | Granite Pass Section 106 Consultation | In Progress | Time and material | Prairie | Sherry Lloyd | 92200 | 12549.75 | 10628.35 | 64982.56 | 64982.56 | 0 | 8252.26 | 56730.3 | 56730.3 |  | 13.6% | 12.7%
26-PC-38153 | Harbor View Reservoir Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd | 109100 | 61521.49 | 54072.6 | 89766.43 | 69277.74 | 20488.69 | 50619.25 | 39147.18 | 18658.49 |  | 56.4% | 56.39%
26-PC-38215 | Phase I: Juniper Wash Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Prairie | Sherry Lloyd | 42800 | 14868.72 | 8160.18 | 37664 | 37664 | 0 | 13083.31 | 24580.69 | 24580.69 |  | 34.7% | 34.74%
26-PC-38264 | On-Call: Coyote Springs Battery Storage Phase II Testing | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd | 25500 | 11801.4 | 4418.43 | 17926.43 | 15639.32 | 2287.11 | 8296.03 | 9630.4 | 7343.29 |  | 46.3% | 46.28%
26-PC-38304 | Yarrow Point Cultural Resources Assessment | In Progress | Time and material | Prairie | Sherry Lloyd | 177100 | 0 | 0 | 125191.99 | 125191.99 | 0 | 0 | 125191.99 | 125191.99 |  | 0% | 0%
26-PC-38315 | Task Order 21: Larkspur Bridge Replacement Paleontological Monitoring | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd | 735000 | 41601 | 41601 | 578298 | 578298 | 0 | 32709.7 | 545588.3 | 545588.3 |  | 5.7% | 5.66%
26-PC-38367 | Stone Mill Architectural History Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 416500 | 110801 | 73148.86 | 276097.85 | 276097.85 | 0 | 80601.22 | 195496.63 | 195496.63 |  | 26.6% | 29.19%
26-PC-38387 | Granite Pass Section 106 Consultation | In Progress | Time and material | Prairie | Sherry Lloyd | 182500 | 92777.25 | 89223.77 | 120358.75 | 120358.75 | 0 | 52528.86 | 67829.89 | 67829.89 |  | 50.8% | 43.64%
26-PC-38390 | Redbud Curation | Final Reporting/Review | Fixed fee | Prairie | Sherry Lloyd | 85100 | 2101.97 | 436.07 | 53630.02 | 53630.02 | 0 | 1324.1 | 52305.92 | 52305.92 |  | 2.5% | 2.47%
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 48300 | 38345.25 | 38154.33 | 32887.47 | 32887.47 | 0 | 24978.26 | 7909.21 | 7909.21 |  | 79.4% | 75.95%
26-PC-38438 | Slate Ridge Fiber Route Phase I Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 41000 | 0 | 0 | 32762.53 | 25331.09 | 7431.44 | 0 | 32762.53 | 25331.09 |  | 0% | 0%
26-PC-38573 | Cedar Hollow School Campus - Class III Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 100100 | 1111.11 | 405.7 | 74784.71 | 74784.71 | 0 | 833.24 | 73951.47 | 73951.47 |  | 1.1% | 1.11%
26-PC-38624 | Juniper Wash Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Red Rock | Bruce Suarez | 77900 | 77900 | 77900 | 56578.77 | 56578.77 | 0 | 73552.4 | -16973.63 | -16973.63 |  | 100% | 130%
26-PC-38647 | Meadowlark Cultural Resources Assessment | In Progress | Time and material | Red Rock | Bruce Suarez | 793800 | 281862.75 | 232307.63 | 517795.74 | 517795.74 | 0 | 177498.27 | 340297.47 | 340297.47 |  | 35.5% | 34.28%
26-PC-38675 | On-Call: Lone Pine School Campus Data Recovery | Final Reporting/Review | Fixed fee | Red Rock | Jeanette Chung | 289700 | 84476.52 | 82918.83 | 228167.72 | 228167.72 | 0 | 66526.14 | 161641.58 | 161641.58 |  | 29.2% | 29.16%
26-PC-38709 | Timber Gap Airport Apron Phase I Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez | 14100 | 6839.91 | 6778.98 | 11415.36 | 11415.36 | 0 | 5537.78 | 5877.58 | 5877.58 |  | 48.5% | 48.51%
26-PC-38719 | Willow Springs Housing Development - Environmental Review Support | In Progress | Fixed fee | Red Rock | Javier Newman | 298600 | 1552.72 | 1508.75 | 193522.66 | 193522.66 | 0 | 1014.83 | 192507.83 | 192507.83 |  | 0.5% | 0.52%
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 97700 | 97700 | 80334.37 | 60828.02 | 60828.02 | 0 | 76641.91 | -15813.89 | -15813.89 |  | 100% | 126%
26-PC-38898 | Redbud Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez | 150100 | 36234.14 | 19826.4 | 87478.28 | 87478.28 | 0 | 21117.75 | 66360.53 | 66360.53 |  | 24.1% | 24.14%
26-PC-38924 | Wildrye Harbor Dredging - Architectural History Survey | In Progress | Time and material | Red Rock | Shelia Horne | 117200 | 64940 | 57207.78 | 83798 | 83798 | 0 | 43360.21 | 40437.79 | 40437.79 |  | 55.4% | 51.74%
26-PC-38943 | Task Order 34: Fern Valley Wastewater Plant Archaeological Testing | In Progress | Fixed fee | Red Rock | Marisa Odom | 129100 | 110303.04 | 95459.09 | 80272.12 | 59881.52 | 20390.6 | 68583.92 | 11688.2 | -8702.4 |  | 85.4% | 85.44%
26-PC-38966 | Task Order 12: Bramble Creek Battery Storage Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Bruce Suarez | 269400 | 11988.3 | 7999.35 | 193052.04 | 193052.04 | 0 | 8599.9 | 184452.14 | 184452.14 |  | 4.4% | 4.45%
26-PC-38993 | Willow Springs Airport Apron - Section 106 Consultation | In Progress | Time and material | Red Rock | Lydia Cisneros | 201400 | 57707.5 | 50428.33 | 131514.2 | 131514.2 | 0 | 37610.38 | 93903.82 | 93903.82 |  | 28.7% | 28.6%
26-PC-39024 | On-Call: Goldfinch Water Main Phase I Survey | In Progress | Time and material | Red Rock | Marisa Odom | 211800 | 7879 | 1334.82 | 149416.47 | 113681.55 | 35734.92 | 5901.64 | 143514.83 | 107779.91 |  | 3.7% | 3.95%
26-PC-39043 | Twin Buttes Reservoir - Archaeological Testing | In Progress | Fixed fee | Red Rock | Bruce Suarez | 123200 | 19736.64 | 14790.45 | 96884.48 | 96884.48 | 0 | 15516.2 | 81368.28 | 81368.28 |  | 16% | 16.02%
26-PC-39143 | Meadowlark Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Bruce Suarez | 500400 | 5404.32 | 3639.56 | 366543 | 366543 | 0 | 3965.11 | 362577.89 | 362577.89 |  | 1.1% | 1.08%
26-PC-39165 | Pebble Beach Road Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre | 94300 | 87472.68 | 76455.85 | 63218.72 | 63218.72 | 0 | 58643.27 | 4575.45 | 4575.45 |  | 92.8% | 92.76%
26-PC-39230 | Maple Fork Cultural Resources Assessment | In Progress | Time and material | Red Rock | Bruce Suarez | 575400 | 64571.5 | 42537.62 | 432643.26 | 432643.26 | 0 | 40379.79 | 392263.47 | 392263.47 |  | 11.2% | 9.33%
26-PC-39249 | On-Call: Millbrook Levee Repair Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre | 126200 | 0 | 0 | 95785.8 | 95785.8 | 0 | 0 | 95785.8 | 95785.8 |  | 0% | 0%
26-PC-39277 | Larkspur Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 520900 | 208.36 | 42.86 | 341710.4 | 341710.4 | 0 | 124.3 | 341586.1 | 341586.1 |  | 0% | 0.04%
26-PC-39303 | Maple Fork Wind Farm Historic Resources Evaluation | Transferred Entity | Fixed fee | Red Rock | Javier Newman | 41200 | 9488.36 | 5457.06 | 35687.44 | 35687.44 | 0 | 8218.46 | 27468.98 | 27468.98 |  | 23% | 23.03%
26-PC-39372 | Tamarack Environmental Review Support | Lab/Curation | Time and material | Red Rock | Shelia Horne | 12300 | 25.25 | 6.19 | 7953.18 | 7953.18 | 0 | 14.5 | 7938.68 | 7938.68 |  | 0.2% | 0.18%
26-PC-39390 | Juniper Wash Fiber Route Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Javier Newman | 59600 | 8504.92 | 7212.74 | 37810.24 | 37810.24 | 0 | 5396.14 | 32414.1 | 32414.1 |  | 14.3% | 14.27%
26-PC-39446 | On-Call: Tamarack Bridge Replacement Architectural History Survey | Transferred Entity | Fixed fee | Red Rock | Jeanette Chung | 131200 | 36696.64 | 14737.81 | 102152.32 | 102152.32 | 0 | 28568.41 | 73583.91 | 73583.91 |  | 28% | 27.97%
26-PC-39537 | Badger Hollow Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Tina Aguirre | 82700 | 6888.91 | 4164.55 | 63951.91 | 63951.91 | 0 | 5327.47 | 58624.44 | 58624.44 |  | 8.3% | 8.33%
26-PC-39565 | On-Call: Aspen Ridge Battery Storage Maritime Remote Sensing Survey | In Progress | Time and material | Red Rock | Lydia Cisneros | 97600 | 32668 | 27241.61 | 60541.28 | 60541.28 | 0 | 19109.38 | 41431.9 | 41431.9 |  | 33.5% | 31.56%
26-PC-39587 | Ember Valley Curation | Cost Tracking on Closed Project | Time and material | Red Rock | Javier Newman | 288900 | 0 | 0 | 211965.93 | 211965.93 | 0 | 213449.22 | -1483.29 | -1483.29 |  | 0% | 100.7%
26-PC-39619 | Hackberry Bend Transmission Line - Paleontological Monitoring | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 79000 | 2630.7 | 609.56 | 54115 | 54115 | 0 | 1801.57 | 52313.43 | 52313.43 |  | 3.3% | 3.33%
26-PC-39638 | On-Call: North Fork Transmission Line Historic Resources Evaluation | In Progress | Time and material | Red Rock | Shelia Horne | 131700 | 34411.5 | 20382.48 | 85748.9 | 62865.33 | 22883.57 | 23512.46 | 62236.44 | 39352.87 |  | 26.1% | 27.42%
26-PC-39699 | Thistle Down Reservoir - Data Recovery | In Progress | Fixed fee | Red Rock | Jeanette Chung | 88200 | 9931.32 | 5211.57 | 62269.2 | 62269.2 | 0 | 7012.08 | 55257.12 | 55257.12 |  | 11.3% | 11.26%
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Cost Tracking on Closed Project | Fixed fee | Red Rock | Tina Aguirre | 115900 | 115900 | 115900 | 86530.94 | 86530.94 | 0 | 99694.97 | -13164.03 | -13164.03 |  | 100% | 115.2%
26-PC-39744 | Phase III: Sumac Ridge Wastewater Plant Archaeological Testing | In Progress | Time and material | Red Rock | Bruce Suarez | 351100 | 25000.75 | 16051.84 | 225441.31 | 225441.31 | 0 | 14063.62 | 211377.69 | 211377.69 |  | 7.1% | 6.24%
26-PC-39778 | Thistle Down Battery Storage - Architectural History Survey | In Progress | Time and material | Red Rock | Marisa Odom | 35700 | 2505.25 | 2429.52 | 26613.7 | 20089.92 | 6523.78 | 1536.44 | 25077.26 | 18553.48 |  | 7% | 5.77%
26-PC-39780 | Phase I: Rushgrass Draw Mine Expansion Maritime Remote Sensing Survey | In Progress | Time and material | Red Rock | Shelia Horne | 113500 | 9446.75 | 4440.96 | 76714.65 | 76714.65 | 0 | 5533.85 | 71180.8 | 71180.8 |  | 8.3% | 7.21%
26-PC-39880 | Larkspur Section 106 Consultation | In Progress | Time and material | Red Rock | Jeanette Chung | 100200 | 37315.75 | 16949.07 | 73772.32 | 69374.59 | 4397.73 | 27101.22 | 46671.1 | 42273.37 |  | 37.2% | 36.74%
26-PC-39971 | Pebble Beach Road Environmental Review Support | Final Reporting/Review | Time and material | Red Rock | Marisa Odom | 114600 | 102477.5 | 83845.05 | 79406.34 | 79406.34 | 0 | 65080 | 14326.34 | 14326.34 |  | 89.4% | 81.96%
26-PC-39990 | Falcon Mesa Solar - Phase I Survey | In Progress | Time and material | Red Rock | Tina Aguirre | 15600 | 710.5 | 363.28 | 10693.8 | 10693.8 | 0 | 417.69 | 10276.11 | 10276.11 |  | 4.6% | 3.91%
26-PC-40009 | Oak Terrace Harbor Dredging Curation | In Progress | Fixed fee | Red Rock | Shelia Horne | 63600 | 23188.56 | 20141.14 | 43349.76 | 43349.76 | 0 | 15804.89 | 27544.87 | 27544.87 |  | 36.5% | 36.46%
26-PC-40055 | Twin Buttes Pipeline Architectural History Survey | In Progress | Time and material | Red Rock | Shelia Horne | 22000 | 8813.5 | 2605.35 | 14259.29 | 12788.18 | 1471.11 | 4910.87 | 9348.42 | 7877.31 |  | 40.1% | 34.44%
26-PC-40092 | Eagle Bend Environmental Review Support | In Progress | Fixed fee | Sierra South | Angelica Poole | 3672000 | 15422.4 | 7215.21 | 2369908.8 | 2369908.8 | 0 | 9935.54 | 2359973.26 | 2359973.26 |  | 0.4% | 0.42%
26-PC-40176 | On-Call: Twin Buttes Harbor Dredging Phase I Survey | Final Reporting/Review | Time and material | Sierra South | Louis Huff | 143600 | 39852 | 33027.78 | 93138.96 | 93138.96 | 0 | 23412.97 | 69725.99 | 69725.99 |  | 27.8% | 25.14%
26-PC-40296 | Twin Buttes Class III Survey | In Progress | Fixed fee | Sierra South | Donna Herring | 6400 | 1088.64 | 1006.05 | 4648.32 | 4648.32 | 0 | 790.8 | 3857.52 | 3857.52 |  | 17% | 17.01%
26-PC-40304 | Willow Springs Fiber Route Archaeological Testing | In Progress | Fixed fee | Sierra | Donna Herring | 132900 | 18100.98 | 15168.63 | 101283.22 | 73563.57 | 27719.65 | 13790.75 | 87492.47 | 59772.82 |  | 13.6% | 13.62%
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 96900 | 96900 | 90582.43 | 68401.71 | 68401.71 | 0 | 75128.43 | -6726.72 | -6726.72 |  | 100% | 109.8%
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Final Reporting/Review | Fixed fee | Sierra | Louis Huff | 19200 | 19200 | 16759.26 | 14098.56 | 14098.56 | 0 | 18399.82 | -4301.26 | -4301.26 |  | 100% | 130.5%
26-PC-40361 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Donna Herring | 156300 | 117897.09 | 95830.05 | 102829.77 | 102829.77 | 0 | 77565.49 | 25264.28 | 25264.28 |  | 75.4% | 75.43%
26-PC-40384 | Maple Fork Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Sierra North | Donna Herring | 102900 | 49138.25 | 47047.68 | 62220.33 | 48730.76 | 13489.57 | 30693.53 | 31526.8 | 18037.23 |  | 47.8% | 49.33%
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Final Reporting/Review | Fixed fee | Sierra South | Donna Herring | 5900 | 5900 | 5708.22 | 4379.73 | 3449.54 | 930.19 | 8489.9 | -4110.17 | -5040.36 |  | 100% | 193.8%
26-PC-40443 | Pine Hollow Wastewater Plant - Built Environment Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 424500 | 65288.1 | 27486.99 | 299781.9 | 299781.9 | 0 | 46117.81 | 253664.09 | 253664.09 |  | 15.4% | 15.38%
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | In Progress | Fixed fee | Sierra North | Donna Herring | 7500 | 7500 | 7376.17 | 5493 | 5493 | 0 | 8125.76 | -2632.76 | -2632.76 |  | 100% | 147.9%
26-PC-40590 | Wildrye Highway Widening - Environmental Review Support | Final Reporting/Review | Fixed fee | Sierra North | Angelica Poole | 1002000 | 153406.2 | 121067.73 | 809716.2 | 809716.2 | 0 | 123942.06 | 685774.14 | 685774.14 |  | 15.3% | 15.31%
26-PC-40605 | Willow Springs Mixed-Use Development Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Sierra | Louis Huff | 138400 | 0 | 0 | 95191.52 | 95191.52 | 0 | 81646.35 | 13545.17 | 13545.17 |  | 0% | 85.77%
26-PC-40690 | Pine Hollow Wastewater Plant - Paleontological Monitoring | In Progress | Time and material | Coastal Bend | Duane Ballard | 252500 | 101574 | 100069.43 | 171094 | 171094 | 0 | 65638.21 | 105455.79 | 105455.79 |  | 40.2% | 38.36%
26-PC-40729 | On-Call: Dove Canyon Cell Tower Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 92500 | 7797.75 | 4889.9 | 58081.13 | 53482.09 | 4599.04 | 4896.28 | 53184.85 | 48585.81 |  | 8.4% | 8.43%
26-PC-40750 | On-Call: Willow Springs Highway Widening Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Steve Rubio | 494600 | 24206.25 | 9568.26 | 310521.94 | 245535.75 | 64986.19 | 17521.7 | 293000.24 | 228014.05 |  | 4.9% | 5.64%
26-PC-40760 | Foxglove Canal Lining - Archaeological Testing | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 77500 | 22064.25 | 19509.79 | 63893.46 | 46765.44 | 17128.02 | 18190.84 | 45702.62 | 28574.6 |  | 28.5% | 28.47%
26-PC-40860 | Fern Valley Solar Data Recovery | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 181300 | 41481.44 | 31148.81 | 145148.78 | 145148.78 | 0 | 33204.32 | 111944.46 | 111944.46 |  | 22.9% | 22.88%
26-PC-40966 | Harbor View Trail - GIS Mapping | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 225100 | 53236.15 | 41568.68 | 146315 | 146315 | 0 | 34610.68 | 111704.32 | 111704.32 |  | 23.6% | 23.65%
26-PC-40983 | Falcon Mesa Data Recovery | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 7200 | 5618.88 | 4989.63 | 6217.91 | 4906.72 | 1311.19 | 4852.67 | 1365.24 | 54.05 |  | 78% | 78.04%
26-PC-41005 | Juniper Wash Architectural History Survey | In Progress | Time and material | Coastal Bend | Duane Ballard | 60000 | 4026 | 2895.23 | 38934 | 38934 | 0 | 2404.38 | 36529.62 | 36529.62 |  | 6.7% | 6.18%
26-PC-41048 | Task Order 33: Granite Pass Battery Storage Phase I Survey | In Progress | Time and material | Coastal Bend | Jared Choi | 458200 | 126518.5 | 82360.74 | 315149.96 | 315149.96 | 0 | 88143.15 | 227006.81 | 227006.81 |  | 27.6% | 27.97%
26-PC-41130 | Harbor View Highway Widening Data Recovery | Cost Tracking on Closed Project | Time and material | Coastal Bend | Steve Rubio | 290300 | 0 | 0 | 219699.04 | 219699.04 | 0 | 201136.18 | 18562.86 | 18562.86 |  | 0% | 91.55%
26-PC-41176 | Wildrye Park Improvements - Environmental Review Support | Final Reporting/Review | Fixed fee | Coastal Bend | Steve Rubio | 109400 | 40401.42 | 34591.32 | 81568.64 | 81568.64 | 0 | 30126.95 | 51441.69 | 51441.69 |  | 36.9% | 36.93%
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 41400 | 41400 | 41400 | 27278.33 | 19877.52 | 7400.81 | 30232.83 | -2954.5 | -10355.31 |  | 100% | 110.8%
26-PC-41222 | Sage Flat Transmission Line - Cultural Resources Assessment | In Progress | Time and material | Coastal Bend | Alexis Nixon | 26000 | 5460 | 3035.93 | 18522.4 | 18522.4 | 0 | 3158.62 | 15363.78 | 15363.78 |  | 21% | 17.05%
26-PC-41230 | Phase I: Slate Ridge Battery Storage Phase I Survey | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 46400 | 16425.6 | 9235.19 | 35769.76 | 35769.76 | 0 | 12661.46 | 23108.3 | 23108.3 |  | 35.4% | 35.4%
26-PC-41334 | Fern Valley Housing Development - Data Recovery | In Progress | Fixed fee | Coastal Bend | Duane Ballard | 154000 | 105967.4 | 97190.14 | 99198.32 | 88810.04 | 10388.28 | 68260.63 | 30937.69 | 20549.41 |  | 68.8% | 68.81%
26-PC-41386 | Task Order 11: Slate Ridge Harbor Dredging Class III Survey | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 302700 | 11260.44 | 5037.07 | 209680.29 | 209680.29 | 0 | 7795.4 | 201884.89 | 201884.89 |  | 3.7% | 3.72%
26-PC-41394 | Maple Fork Bridge Replacement - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Duane Ballard | 15700 | 14005.97 | 14005.97 | 11219.22 | 11219.22 | 0 | 10008.86 | 1210.36 | 1210.36 |  | 89.2% | 89.21%
26-PC-41406 | Task Order 27: Dove Canyon Battery Storage Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 381600 | 155540.16 | 139465.09 | 257192.06 | 187803.42 | 69388.64 | 104836.49 | 152355.57 | 82966.93 |  | 40.8% | 40.76%
26-PC-41425 | Pebble Beach Road GIS Mapping | Transferred Entity | Time and material | Coastal Bend | Steve Rubio | 268700 | 99208 | 55597.03 | 183253.4 | 183253.4 | 0 | 63737.62 | 119515.78 | 119515.78 |  | 36.9% | 34.78%
26-PC-41446 | Stone Mill Levee Repair Archaeological Testing | In Progress | Time and material | Coastal Bend | Jared Choi | 263000 | 0 | 0 | 172291.3 | 172291.3 | 0 | 0 | 172291.3 | 172291.3 |  | 0% | 0%
26-PC-41466 | Millbrook Cultural Resources Assessment | Lab/Curation | Time and material | Coastal Bend | Alexis Nixon | 857800 | 255216.5 | 255216.5 | 634085.76 | 634085.76 | 0 | 178651.18 | 455434.58 | 455434.58 |  | 29.8% | 28.17%
26-PC-41575 | Juniper Wash Highway Widening - Section 106 Consultation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 131400 | 13613.04 | 5545.27 | 100941.48 | 100941.48 | 0 | 10453.11 | 90488.37 | 90488.37 |  | 10.4% | 10.36%
26-PC-41644 | Granite Pass Built Environment Survey | Transferred Entity | Fixed fee | Coastal Bend | Alexis Nixon | 330600 | 66384.48 | 36012.37 | 258297.78 | 258297.78 | 0 | 51878.28 | 206419.5 | 206419.5 |  | 20.1% | 20.08%
26-PC-41661 | Ember Valley Levee Repair Data Recovery | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 4800 | 4800 | 1827.9 | 4028.16 | 4028.16 | 0 | 4393.64 | -365.48 | -365.48 |  | 100% | 109.1%
26-PC-41667 | Kestrel Butte Transmission Line - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Duane Ballard | 131800 | 127576.25 | 93060.18 | 98659.54 | 84109.2 | 14550.34 | 81942.27 | 16717.27 | 2166.93 |  | 96.8% | 83.06%
26-PC-41683 | On-Call: Slate Ridge Levee Repair Built Environment Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 250100 | 6877.75 | 1667.12 | 169042.59 | 169042.59 | 0 | 4642.33 | 164400.26 | 164400.26 |  | 2.8% | 2.75%
26-PC-41707 | Quail Run Solar Environmental Review Support | Final Reporting/Review | Fixed fee | Built Environment | Jenny Wilkinson | 27000 | 6966 | 3982.77 | 20358 | 20358 | 0 | 5252.61 | 15105.39 | 15105.39 |  | 25.8% | 25.8%
26-PC-41721 | Thistle Down Curation | In Progress | Time and material | Built Environment | Melody Holloway | 67700 | 36183 | 31888.77 | 46692.69 | 46692.69 | 0 | 23748.7 | 22943.99 | 22943.99 |  | 53.4% | 50.86%
26-PC-41739 | Slate Ridge Historic Resources Evaluation | In Progress | Fixed fee | Built Environment | Melody Holloway | 240100 | 27731.55 | 23121.15 | 163268 | 163268 | 0 | 18858.88 | 144409.12 | 144409.12 |  | 11.6% | 11.55%
26-PC-41776 | Sandpiper Battery Storage GIS Mapping | Lab/Curation | Time and material | Built Environment | Jenny Wilkinson | 457800 | 40229.25 | 36984.05 | 310067.94 | 310067.94 | 0 | 25479.07 | 284588.87 | 284588.87 |  | 8.8% | 8.22%
26-PC-41803 | Copper Flats Section 106 Consultation | Lab/Curation | Fixed fee | Built Environment | Jenny Wilkinson | 554800 | 67130.8 | 55086.8 | 392021.68 | 392021.68 | 0 | 47452.96 | 344568.72 | 344568.72 |  | 12.1% | 12.1%
26-PC-41821 | Blue Heron School Campus Curation | In Progress | Time and material | Built Environment | Jenny Wilkinson | 152400 | 38727 | 35011.46 | 98770.44 | 98770.44 | 0 | 25864.78 | 72905.66 | 72905.66 |  | 25.4% | 26.19%
26-PC-41863 | Silver Lake Canal Lining Cultural Resources Assessment | In Progress | Fixed fee | Built Environment | Jenny Wilkinson | 322500 | 9255.75 | 8208.44 | 224460 | 224460 | 0 | 6449.34 | 218010.66 | 218010.66 |  | 2.9% | 2.87%
26-PC-41865 | Phase II: Copper Flats Reservoir Class III Survey | In Progress | Time and material | Built Environment | Jenny Wilkinson | 67100 | 0 | 0 | 48325.42 | 48325.42 | 0 | 0 | 48325.42 | 48325.42 |  | 0% | 0%
26-PC-41884 | Foxglove Trail - Curation | In Progress | Time and material | Built Environment | Melody Holloway | 1099300 | 100170 | 75305.17 | 743556.08 | 550430.95 | 193125.13 | 69536.27 | 674019.81 | 480894.68 |  | 9.1% | 9.35%
26-PC-41918 | Plover Cove Data Recovery | In Progress | Fixed fee | Built Environment | Melody Holloway | 121100 | 9058.28 | 7963.02 | 81064.34 | 81064.34 | 0 | 6059.97 | 75004.37 | 75004.37 |  | 7.5% | 7.48%
26-PC-41947 | Juniper Wash Trail - Cultural Resources Monitoring | Lab/Curation | Fixed fee | Built Environment | Rickey Salas | 64400 | 37178.12 | 30400.25 | 52073.84 | 52073.84 | 0 | 30061.9 | 22011.94 | 22011.94 |  | 57.7% | 57.73%
26-PC-41961 | Eagle Bend Data Recovery | In Progress | Fixed fee | Built Environment | Melody Holloway | 463200 | 104822.16 | 104822.16 | 369077.76 | 369077.76 | 0 | 83505.48 | 285572.28 | 285572.28 |  | 22.6% | 22.63%
26-PC-41970 | North Fork School Campus - Cultural Resources Monitoring | Final Reporting/Review | Time and material | Built Environment | Melody Holloway | 292200 | 93249.75 | 93249.75 | 212405.41 | 172247.04 | 40158.37 | 60262.35 | 152143.06 | 111984.69 |  | 31.9% | 28.37%
26-PC-42007 | On-Call: Wren Hollow Mixed-Use Development Architectural History Survey | In Progress | Fixed fee | Built Environment | Jesse Maynard | 341700 | 37587 | 31519.6 | 215752.53 | 179922 | 35830.53 | 23729.27 | 192023.26 | 156192.73 |  | 11% | 11%
26-PC-42008 | Millbrook GIS Mapping | In Progress | Time and material | Built Environment | Kathleen Cabrera | 79400 | 0 | 0 | 54793.94 | 54793.94 | 0 | 0 | 54793.94 | 54793.94 |  | 0% | 0%
26-PC-42023 | North Fork Historic Resources Evaluation | Transferred Entity | Fixed fee | Built Environment | Jenny Wilkinson | 157000 | 16673.4 | 14885.86 | 111815.4 | 111815.4 | 0 | 11876.63 | 99938.77 | 99938.77 |  | 10.6% | 10.62%
26-PC-42040 | Millbrook Phase II Testing | In Progress | Time and material | Built Environment | Jenny Wilkinson | 129700 | 14359.5 | 9132.09 | 89350.33 | 89350.33 | 0 | 9591.8 | 79758.53 | 79758.53 |  | 11.1% | 10.74%
26-PC-42099 | Fern Valley Substation Cultural Resources Monitoring | In Progress | Time and material | Built Environment | Jesse Maynard | 661800 | 124275.5 | 110235.78 | 445656.12 | 445656.12 | 0 | 74965.47 | 370690.65 | 370690.65 |  | 18.8% | 16.82%
26-PC-42108 | Sumac Ridge Mixed-Use Development Curation | In Progress | Fixed fee | Built Environment | Kathleen Cabrera | 1000600 | 57834.68 | 51120.33 | 761256.48 | 761256.48 | 0 | 43963.83 | 717292.65 | 717292.65 |  | 5.8% | 5.78%
26-PC-42293 | Eagle Bend Water Main Phase II Testing | In Progress | Fixed fee | Paleontology | Charlene Sparks | 100800 | 24685.92 | 22746.35 | 88704 | 88704 | 0 | 21724.75 | 66979.25 | 66979.25 |  | 24.5% | 24.49%
26-PC-42427 | Phase II: Stone Mill Mine Expansion Section 106 Consultation | In Progress | Time and material | Paleontology | Travis Delgado | 926100 | 199575 | 182757.68 | 644195.16 | 644195.16 | 0 | 140019.29 | 504175.87 | 504175.87 |  | 21.6% | 21.74%
26-PC-42428 | Phase II: Yarrow Point Levee Repair Architectural History Survey | Final Reporting/Review | Fixed fee | Paleontology | Charlene Sparks | 921200 | 23214.24 | 7402.27 | 680214.08 | 680214.08 | 0 | 17174.43 | 663039.65 | 663039.65 |  | 2.5% | 2.52%
26-PC-42472 | Kestrel Butte Cultural Resources Monitoring | In Progress | Fixed fee | Paleontology | Travis Delgado | 129200 | 4405.72 | 1825.8 | 94328.92 | 94328.92 | 0 | 3220.98 | 91107.94 | 91107.94 |  | 3.4% | 3.41%
26-PC-42492 | Tamarack Class III Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 60100 | 15520.75 | 14528.76 | 39629.94 | 39629.94 | 0 | 9610.68 | 30019.26 | 30019.26 |  | 25.8% | 24.25%
26-PC-42510 | Lantern Bay Data Recovery | In Progress | Time and material | Paleontology | Charlene Sparks | 1304200 | 147490.25 | 138984.13 | 949196.76 | 949196.76 | 0 | 96292.2 | 852904.56 | 852904.56 |  | 11.3% | 10.14%
26-PC-42554 | Task Order 36: Larkspur Pipeline Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 138900 | 9750.78 | 3241.35 | 102674.88 | 102674.88 | 0 | 7211.42 | 95463.46 | 95463.46 |  | 7% | 7.02%
26-PC-42598 | Badger Hollow Phase II Testing | In Progress | Time and material | Paleontology | Travis Delgado | 99400 | 52925.75 | 46544.43 | 74509.83 | 55811.54 | 18698.29 | 31770.68 | 42739.15 | 24040.86 |  | 53.2% | 42.64%
26-PC-42664 | Foxglove Cell Tower GIS Mapping | In Progress | Fixed fee | Paleontology | Travis Delgado | 50700 | 3199.17 | 1164.27 | 32903.41 | 29535.99 | 3367.42 | 2075.33 | 30828.08 | 27460.66 |  | 6.3% | 6.31%
26-PC-42679 | Aspen Ridge Phase I Survey | Final Reporting/Review | Fixed fee | Maritime | Kyle Maynard | 214600 | 103072.38 | 88132.28 | 144103.9 | 144103.9 | 0 | 69217.42 | 74886.48 | 74886.48 |  | 48% | 48.03%
26-PC-42692 | Quail Run Curation | In Progress | Fixed fee | Maritime | Rita Ayala | 300500 | 39666 | 29809.72 | 203889.25 | 203889.25 | 0 | 26905.99 | 176983.26 | 176983.26 |  | 13.2% | 13.2%
26-PC-42734 | On-Call: Lantern Bay Reservoir Architectural History Survey | In Progress | Time and material | Maritime | Rita Ayala | 77500 | 41132.25 | 38532.58 | 51615 | 51615 | 0 | 25950.9 | 25664.1 | 25664.1 |  | 53.1% | 50.28%
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | In Progress | Fixed fee | Maritime | Kyle Maynard | 347000 | 252477.2 | 226595.93 | 256363.6 | 256363.6 | 0 | 186528.08 | 69835.52 | 69835.52 |  | 72.8% | 72.76%
26-PC-42832 | Task Order 39: Saltgrass Levee Repair Class III Survey | Final Reporting/Review | Time and material | Maritime | Rita Ayala | 343600 | 38736.25 | 32806.18 | 243097 | 243097 | 0 | 23563.54 | 219533.46 | 219533.46 |  | 11.3% | 9.69%
26-PC-42838 | Phase III: Oak Terrace Pipeline Phase II Testing | In Progress | Fixed fee | Maritime | Rita Ayala | 47400 | 19865.34 | 19865.34 | 31824.36 | 31824.36 | 0 | 13337.82 | 18486.54 | 18486.54 |  | 41.9% | 41.91%
26-PC-42880 | Phase I: Quail Run Harbor Dredging Curation | In Progress | Fixed fee | Maritime | Rita Ayala | 107200 | 12145.76 | 7389.46 | 87904 | 87904 | 0 | 9955.87 | 77948.13 | 77948.13 |  | 11.3% | 11.33%
26-PC-42926 | Juniper Wash Transmission Line - Class III Survey | In Progress | Fixed fee | Maritime | Rita Ayala | 87800 | 4644.62 | 1775.48 | 68132.8 | 68132.8 | 0 | 3601.54 | 64531.26 | 64531.26 |  | 5.3% | 5.29%
26-PC-42962 | Lone Pine Curation | In Progress | Time and material | Maritime | Rita Ayala | 1041700 | 12393.75 | 4165.92 | 704293.37 | 704293.37 | 0 | 7965.32 | 696328.05 | 696328.05 |  | 1.2% | 1.13%
26-PC-42989 | North Fork Cultural Resources Monitoring | In Progress | Time and material | Maritime | Rita Ayala | 24000 | 1482 | 1076.33 | 15241.71 | 11972.82 | 3268.89 | 928.45 | 14313.26 | 11044.37 |  | 6.2% | 6.09%
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Final Reporting/Review | Time and material | Geospatial | Sylvia Callahan | 107600 | 107600 | 99262.67 | 77827.43 | 68885.46 | 8941.97 | 89098.75 | -11271.32 | -20213.29 |  | 100% | 114.5%
26-PC-43086 | On-Call: Silver Lake Transmission Line Archaeological Testing | In Progress | Time and material | Geospatial | Sylvia Callahan | 2118800 | 0 | 0 | 1431461.28 | 1431461.28 | 0 | 0 | 1431461.28 | 1431461.28 |  | 0% | 0%
26-PC-43132 | Phase III: Ember Valley Highway Widening Phase II Testing | Lab/Curation | Fixed fee | Geospatial | Priscilla Pennington | 140700 | 47036.01 | 43252.63 | 112756.98 | 112756.98 | 0 | 37690.1 | 75066.88 | 75066.88 |  | 33.4% | 33.43%
26-PC-43136 | Phase III: Harbor View Highway Widening Section 106 Consultation | In Progress | Time and material | Geospatial | Priscilla Pennington | 3831800 | 168416.5 | 138596.66 | 2564623.74 | 2564623.74 | 0 | 120256.61 | 2444367.13 | 2444367.13 |  | 4.4% | 4.69%
26-PC-43168 | Task Order 35: Aspen Ridge Transmission Line Architectural History Survey | Final Reporting/Review | Fixed fee | Geospatial | Sylvia Callahan | 281200 | 84050.68 | 79022.62 | 164749.65 | 145548.52 | 19201.13 | 49236.49 | 115513.16 | 96312.03 |  | 29.9% | 29.89%
26-PC-43199 | Thistle Down Airport Apron Phase I Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Mathew Shea | 42200 | 38937.94 | 38937.94 | 26341.24 | 26341.24 | 0 | 24305.56 | 2035.68 | 2035.68 |  | 92.3% | 92.27%
26-PC-43266 | Silver Lake Curation | In Progress | Fixed fee | Meridian Central | Mathew Shea | 21300 | 464.34 | 217.28 | 13227.3 | 13227.3 | 0 | 288.09 | 12939.21 | 12939.21 |  | 2.2% | 2.18%
26-PC-43307 | Phase III: Aspen Ridge Mine Expansion Maritime Remote Sensing Survey | In Progress | Time and material | Meridian Central | Raymond Hensley | 239600 | 71378.75 | 71378.75 | 189451.72 | 189451.72 | 0 | 52539.33 | 136912.39 | 136912.39 |  | 29.8% | 27.73%
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | In Progress | Fixed fee | Meridian Central | Mathew Shea | 41200 | 30945.32 | 29998.17 | 27426.84 | 27426.84 | 0 | 20599.46 | 6827.38 | 6827.38 |  | 75.1% | 75.11%
26-PC-43338 | Sparrow Hill Bridge Replacement Section 106 Consultation | In Progress | Time and material | Meridian Central | Raymond Hensley | 121900 | 0 | 0 | 79125.29 | 79125.29 | 0 | 0 | 79125.29 | 79125.29 |  | 0% | 0%
26-PC-43364 | Goldfinch Class III Survey | Transferred Entity | Fixed fee | Meridian Central | Raymond Hensley | 24900 | 24900 | 23821.32 | 16624.07 | 15142.4 | 1481.67 | 22825.96 | -6201.89 | -7683.56 |  | 100% | 137.3%
26-PC-43381 | Lantern Bay Canal Lining Archaeological Testing | In Progress | Fixed fee | Meridian Central | Clinton Solis | 309600 | 23684.4 | 7401.4 | 249847.2 | 249847.2 | 0 | 19118.33 | 230728.87 | 230728.87 |  | 7.6% | 7.65%
26-PC-43429 | Stone Mill Highway Widening Curation | Transferred Entity | Fixed fee | Meridian Central | Clinton Solis | 202600 | 10514.94 | 5068.52 | 115400.96 | 115400.96 | 0 | 5994.77 | 109406.19 | 109406.19 |  | 5.2% | 5.19%
26-PC-43478 | Tamarack Airport Apron Phase II Testing | In Progress | Time and material | Meridian Central | Clinton Solis | 531800 | 167292.25 | 118587.81 | 378109.8 | 378109.8 | 0 | 117552.59 | 260557.21 | 260557.21 |  | 31.5% | 31.09%
26-PC-43493 | Millbrook Pipeline Cultural Resources Monitoring | In Progress | Time and material | Meridian Central | Raymond Hensley | 1164300 | 96389 | 74613.99 | 893116.35 | 726254.3 | 166862.05 | 66672.18 | 826444.17 | 659582.12 |  | 8.3% | 7.47%
26-PC-43527 | Maple Fork School Campus Phase II Testing | In Progress | Time and material | Meridian Central | Raymond Hensley | 333700 | 77471 | 72040.32 | 224680.21 | 224680.21 | 0 | 53521.21 | 171159 | 171159 |  | 23.2% | 23.82%
26-PC-43528 | Quail Run Cell Tower GIS Mapping | Final Reporting/Review | Fixed fee | Meridian Central | Mathew Shea | 21800 | 18639 | 5521.71 | 14869.78 | 14869.78 | 0 | 12713.55 | 2156.23 | 2156.23 |  | 85.5% | 85.5%
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | In Progress | Fixed fee | Meridian Central | Clinton Solis | 136900 | 131026.99 | 130552.64 | 105043.37 | 105043.37 | 0 | 100533.21 | 4510.16 | 4510.16 |  | 95.7% | 95.71%
26-PC-43563 | Thistle Down Section 106 Consultation | In Progress | Time and material | Meridian Central | Mathew Shea | 79800 | 25811.25 | 19196.62 | 52393.25 | 45333 | 7060.25 | 16759.41 | 35633.84 | 28573.59 |  | 32.3% | 31.99%
26-PC-43575 | On-Call: Fern Valley Substation Data Recovery | Lab/Curation | Fixed fee | Meridian Central | Mathew Shea | 113100 | 79645.02 | 74740.94 | 87831.71 | 66733.2 | 21098.51 | 61848.22 | 25983.49 | 4884.98 |  | 70.4% | 70.42%
26-PC-43584 | On-Call: Wren Hollow Solar Architectural History Survey | In Progress | Fixed fee | Meridian Central | Mathew Shea | 223700 | 0 | 0 | 185536.78 | 185536.78 | 0 | 0 | 185536.78 | 185536.78 |  | 0% | 0%
26-PC-43695 | Willow Springs Maritime Remote Sensing Survey | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 104700 | 36027.27 | 27395.63 | 73750.68 | 73750.68 | 0 | 25376.37 | 48374.31 | 48374.31 |  | 34.4% | 34.41%
26-PC-43731 | Task Order 32: Dove Canyon Transmission Line Paleontological Monitoring | In Progress | Time and material | Meridian Southwest | Alan Gay | 17700 | 0 | 0 | 12905.07 | 12905.07 | 0 | 0 | 12905.07 | 12905.07 |  | 0% | 0%
26-PC-43762 | Hawk Point Substation Paleontological Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran | 17500 | 946.75 | 335.45 | 15400 | 15400 | 0 | 832.67 | 14567.33 | 14567.33 |  | 5.4% | 5.41%
26-PC-43818 | Plover Cove Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Meridian Southwest | Lynn Tran | 277600 | 32062.8 | 22111.94 | 226882.48 | 226882.48 | 0 | 26203.95 | 200678.53 | 200678.53 |  | 11.6% | 11.55%
26-PC-43874 | Oak Terrace Cell Tower - Class III Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Justin Mejia | 72100 | 0 | 0 | 51991.31 | 51991.31 | 0 | 0 | 51991.31 | 51991.31 |  | 0% | 0%
26-PC-43899 | On-Call: Foxglove Reservoir Cultural Resources Monitoring | In Progress | Time and material | NH Gulf (USD) | Justin Mejia | 154600 | 17698 | 9002.14 | 103767.52 | 103767.52 | 0 | 12573.63 | 91193.89 | 91193.89 |  | 11.4% | 12.12%
26-PC-43915 | Task Order 5: Twin Buttes Bridge Replacement Phase I Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Javier Rangel | 202200 | 1233.4213 | 311.5893 | 177936 | 177936 | 0 | 1086.4773 | 176849.5227 | 176849.5227 |  | 0.61% | 0.6106%
26-PC-43927 | On-Call: Millbrook Cell Tower Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 60000 | 3540.2507 | 1412.8693 | 39334.64 | 35895.35 | 3439.29 | 2279.19 | 37055.45 | 33616.16 |  | 5.9% | 5.794%
26-PC-43961 | On-Call: Sparrow Hill Fiber Route Architectural History Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 264600 | 118778.9413 | 98585.1893 | 211627.08 | 211627.08 | 0 | 94998.526 | 116628.554 | 116628.554 |  | 44.89% | 44.89%
26-PC-43963 | On-Call: Foxglove Trail Data Recovery | In Progress | Fixed fee | NH Gulf (USD) | Javier Rangel | 532600 | 133842.38 | 117842.42 | 335058.66 | 335058.66 | 0 | 84187.73 | 250870.93 | 250870.93 |  | 25.1% | 25.13%
26-PC-43979 | Pine Hollow Harbor Dredging - Historic Resources Evaluation | Transferred Entity | Fixed fee | NH Gulf (USD) | Justin Mejia | 98500 | 0 | 0 | 72742.25 | 72742.25 | 0 | 0 | 72742.25 | 72742.25 |  | 0% | 0%
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Justin Mejia | 220800 | 218771.2507 | 195354 | 146699.52 | 146699.52 | 0 | 136849.0807 | 9850.4393 | 9850.4393 |  | 99.08% | 93.29%
26-PC-43991 | Saltgrass Water Main - Archaeological Testing | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence | 22500 | 13819.5 | 10534.3 | 13335.87 | 10433.28 | 2902.59 | 8191.4 | 5144.47 | 2241.88 |  | 61.4% | 61.42%
26-PC-44007 | Goldfinch Battery Storage Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Randy Cantu | 226900 | 14790 | 14790 | 149799.38 | 149799.38 | 0 | 8751.52 | 141047.86 | 141047.86 |  | 6.518% | 5.842%
26-PC-44050 | On-Call: Hawk Point Canal Lining Archaeological Testing | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 670400 | 37341.28 | 21973.44 | 477190.72 | 477190.72 | 0 | 26569.3213 | 450621.3987 | 450621.3987 |  | 5.57% | 5.568%
26-PC-44072 | Oak Terrace Water Main GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Susan Wilkins | 106200 | 55447.0213 | 48383.9013 | 79469.46 | 79469.46 | 0 | 41489.462 | 37979.998 | 37979.998 |  | 52.21% | 52.21%
26-PC-44090 | Eagle Bend Phase I Survey | Transferred Entity | Time and material | NH Gulf (USD) | Tonya Spence | 6300 | 1040.7493 | 227.2987 | 4404.16 | 3266.03 | 1138.13 | 565.68 | 3838.48 | 2700.35 |  | 16.52% | 12.84%
26-PC-44129 | Tamarack Airport Apron - Section 106 Consultation | In Progress | Fixed fee | NH Gulf (USD) | Javier Rangel | 40400 | 0 | 0 | 30324.24 | 30324.24 | 0 | 0 | 30324.24 | 30324.24 |  | 0% | 0%
26-PC-44173 | Timber Gap Harbor Dredging - Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Susan Wilkins | 160600 | 29197.08 | 21934.3307 | 111038.84 | 111038.84 | 0 | 20184.098 | 90854.742 | 90854.742 |  | 18.18% | 18.18%
26-PC-44201 | Plover Cove Section 106 Consultation | Transferred Entity | Time and material | NH Gulf (USD) | Javier Rangel | 165400 | 67195 | 60276.1493 | 115267.26 | 115267.26 | 0 | 39551.8467 | 75715.4133 | 75715.4133 |  | 40.63% | 34.31%
26-PC-44220 | Dove Canyon GIS Mapping | Transferred Entity | Time and material | NH Gulf (USD) | Justin Mejia | 59700 | 7761.4987 | 5425.72 | 47634.63 | 47634.63 | 0 | 4924.66 | 42709.97 | 42709.97 |  | 13% | 10.34%
26-PC-44256 | On-Call: Twin Buttes Rail Siding Environmental Review Support | Transferred Entity | Fixed fee | NH Gulf (USD) | Susan Wilkins | 810700 | 321442.5493 | 283600.6987 | 574867.37 | 574867.37 | 0 | 227909.552 | 346957.818 | 346957.818 |  | 39.65% | 39.65%
26-PC-44277 | Phase I: Sea Oat Harbor Dredging Architectural History Survey | In Progress | Fixed fee | NH Gulf (USD) | Tonya Spence | 49100 | 28482.91 | 25401.55 | 39677.71 | 39677.71 | 0 | 23018.4 | 16659.31 | 16659.31 |  | 58% | 58.01%
26-PC-44290 | On-Call: Larkspur Park Improvements GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Justin Mejia | 206100 | 43651.9787 | 38613.6907 | 160077.87 | 160077.87 | 0 | 33903.5247 | 126174.3453 | 126174.3453 |  | 21.18% | 21.18%
26-PC-44302 | Dove Canyon Cell Tower - Built Environment Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 90200 | 40102.92 | 28689.2693 | 67334.3 | 67334.3 | 0 | 29937.6113 | 37396.6887 | 37396.6887 |  | 44.46% | 44.46%
25-PC-44140 | Stone Mill Archaeological Testing | In Progress | Fixed fee | NH Gulf | Tonya Spence | 149900 | 149510.2587 | 130809.0507 | 100298.0907 | 100298.0907 | 0 | 100035.4533 | 262.6373 | 262.6373 |  | 99.74% | 99.74%

## Projects >70% Exec View
Summary:
Removed projects with ETC>1% budget remaining
Removed $0 Contract Value projects
Removed previously identified ETC in final/reportingstatus
Removed projects in final reporting with >10% budget remaining
Total: 273
[5 empty] | Contract Value | Total Revised Budget | Original Budget | ETC | Revenue Recognized | Rev Rec % | Cost | Budget Remaining | Budget Spent % | Project Gross Profit
[5 empty] | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026
Project ID | Project Name | Project Billing type | Project status | Project Manager Name | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Location Name
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | Time and material | In Progress | Kiara Gillespie | 49800 | 34501.44 | 34501.44 | 0 | 33864 | 68% | 28656.36 | 5845.08 |  |  | Bluegrass
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Time and material | Cost Tracking on Closed Project | Alice Galloway | 86200 | 58650.48 | 58650.48 | 0 | 58616 | 68% | 61318.15 | -2667.67 |  |  | Bluegrass
23-PC-31003 | Windmill Flat Environmental Review Support | Fixed fee | In Progress | Kiara Gillespie | 19300 | 10568.68 | 10568.68 | 0 | 15445.79 | 80% | 8458.51 | 2110.17 |  |  | Bluegrass
23-PC-31042 | Stone Mill Historic Resources Evaluation | Time and material | In Progress | Donald Lutz | 299700 | 202896.9 | 202896.9 | 0 | 203796 | 68% | 147919.88 | 54977.02 |  |  | Cascade
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | Time and material | In Progress | Donald Lutz | 255700 | 168225.03 | 168225.03 | 0 | 173876 | 68% | 202903.45 | -34678.42 |  |  | Cascade
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | Fixed fee | In Progress | Jeff Spence | 108000 | 82404 | 82404 | 0 | 76528.8 | 70.9% | 58391.35 | 24012.65 |  |  | Cascade
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | Fixed fee | In Progress | Gene Nixon | 34800 | 28779.6 | 28779.6 | 0 | 34800 | 100% | 31540.76 | -2761.16 |  |  | Cascade
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | Fixed fee | In Progress | Jeff Spence | 460600 | 390957.28 | 390957.28 | 0 | 348674.2 | 75.7% | 295973.9 | 94983.38 |  |  | Cascade
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | Jeff Spence | 175300 | 93481.01 | 71376.84 | 22104.17 | 175300 | 100% | 112759.17 | -19278.16 |  |  | Cascade
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | Fixed fee | In Progress | Sandy Kerr | 149100 | 111109.32 | 111109.32 | 0 | 132892.83 | 89.1% | 99032.78 | 12076.54 |  |  | Chesapeake
23-PC-32635 | Rushgrass Draw Curation | Time and material | Cost Tracking on Closed Project | Jason Oconnor | 36800 | 24644.96 | 24644.96 | 0 | 25024 | 68% | 27323.95 | -2678.99 |  |  | Chesapeake
23-PC-33070 | Meadowlark Curation | Fixed fee | In Progress | Reginald Vargas | 55100 | 34299.75 | 34299.75 | 0 | 46377.67 | 84.2% | 28871.53 | 5428.22 |  |  | Front Range
23-PC-33151 | Sandpiper Class III Survey | Fixed fee | In Progress | Kimberly Daugherty | 637100 | 497638.81 | 497638.81 | 0 | 540961.61 | 84.9% | 422546.87 | 75091.94 |  |  | Front Range
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | Fixed fee | In Progress | Kimberly Daugherty | 21600 | 15245.28 | 15245.28 | 0 | 21600 | 100% | 16551.79 | -1306.51 |  |  | Front Range
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | Time and material | In Progress | Jeff Pugh | 300600 | 219257.64 | 219257.64 | 0 | 204408 | 68% | 176674.59 | 42583.05 |  |  | Great Lakes
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | Time and material | In Progress | Kathleen Galvan | 373100 | 247626.47 | 247626.47 | 0 | 253708 | 68% | 184659.6 | 62966.87 |  |  | Great Lakes
23-PC-34403 | Plover Cove Built Environment Survey | Time and material | In Progress | Kathleen Galvan | 46200 | 30187.08 | 30187.08 | 0 | 31416 | 68% | 23628.2 | 6558.88 |  |  | Great Lakes
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | Fixed fee | In Progress | Angelica Cervantes | 477000 | 333756.9 | 333756.9 | 0 | 347303.7 | 72.8% | 243019.93 | 90736.97 |  |  | Great Lakes
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Time and material | Final Reporting/Review | Geoffrey Fernandez | 70000 | 50246 | 50246 | 0 | 47600 | 68% | 45814.41 | 4431.59 |  |  | Great Lakes
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | Fixed fee | In Progress | Sean Jennings | 46100 | 31721.41 | 31721.41 | 0 | 32472.84 | 70.4% | 22343.25 | 9378.16 |  |  | Gulf Coast
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | Fixed fee | In Progress | Wyatt Erickson | 407900 | 321139.67 | 321139.67 | 0 | 303355.23 | 74.4% | 238828.33 | 82311.34 |  |  | Gulf Coast East
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | Time and material | In Progress | Jody Wang | 116200 | 87219.72 | 87219.72 | 0 | 79016 | 68% | 78190.34 | 9029.38 |  |  | High Desert
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | Fixed fee | In Progress | Eileen Poole | 11400 | 8206.86 | 8206.86 | 0 | 8681.1 | 76.2% | 6249.46 | 1957.4 |  |  | High Desert
23-PC-35682 | Lantern Bay Class III Survey | Fixed fee | In Progress | Eileen Poole | 290400 | 252938.4 | 252938.4 | 0 | 277361.04 | 95.5% | 241578.4 | 11360 |  |  | High Desert
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | Fixed fee | In Progress | Kathy Hurley | 114600 | 77893.62 | 77893.62 | 0 | 104870.46 | 91.5% | 71277.07 | 6616.55 |  |  | High Desert
23-PC-36422 | Hawk Point Phase I Survey | Time and material | In Progress | Joan Mathis | 50700 | 36579.06 | 32790.93 | 3788.13 | 34476 | 68% | 37409.59 | -830.53 |  |  | Island
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | Fixed fee | In Progress | Jeanette Riddle | 201000 | 151513.8 | 151513.8 | 0 | 170226.9 | 84.7% | 128322.24 | 23191.56 |  |  | Lakeshore
23-PC-36734 | Raven Rock Curation | Fixed fee | In Progress | Terrence Gillespie | 38600 | 27753.4 | 27753.4 | 0 | 36284 | 94% | 26089.14 | 1664.26 |  |  | Lakeshore
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | Fixed fee | In Progress | Maria Parrish | 44500 | 35070.45 | 35070.45 | 0 | 31902.05 | 71.7% | 25141.75 | 9928.7 |  |  | Piedmont - Inactive
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | Time and material | In Progress | Sherry Lloyd | 128200 | 90073.32 | 90073.32 | 0 | 87176 | 68% | 73724.08 | 16349.24 |  |  | Prairie
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | Sherry Lloyd | 79800 | 53434.08 | 53434.08 | 0 | 57918.84 | 72.6% | 38783.48 | 14650.6 |  |  | Prairie
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | Fixed fee | In Progress | Shelia Horne | 67700 | 44688.77 | 44688.77 | 0 | 56556.58 | 83.5% | 37332.05 | 7356.72 |  |  | Red Rock
23-PC-38759 | Saltgrass Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | Tina Aguirre | 52400 | 36847.68 | 36847.68 | 0 | 35632 | 68% | 40372.44 | -3524.76 |  |  | Red Rock
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | Fixed fee | In Progress | Tina Aguirre | 109400 | 83089.3 | 83089.3 | 0 | 86962.06 | 79.5% | 66048.24 | 17041.06 |  |  | Red Rock
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | Fixed fee | In Progress | Jeanette Chung | 27800 | 18214.56 | 18214.56 | 0 | 20777.72 | 74.7% | 13614.39 | 4600.17 |  |  | Red Rock
23-PC-39323 | Silver Lake Battery Storage Class III Survey | Fixed fee | In Progress | Tina Aguirre | 550600 | 444994.92 | 444994.92 | 0 | 423136.1 | 76.8% | 341994.21 | 103000.71 |  |  | Red Rock
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | Time and material | In Progress | Javier Newman | 119500 | 80196.45 | 80196.45 | 0 | 103480.5 | 86.6% | 70430.41 | 9766.04 |  |  | Red Rock
23-PC-40402 | Pebble Beach Road Architectural History Survey | Fixed fee | In Progress | Louis Huff | 411600 | 302937.6 | 302937.6 | 0 | 333190.2 | 80.9% | 245232.54 | 57705.06 |  |  | Sierra North
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | Fixed fee | In Progress | Benjamin Mathis | 53900 | 40910.1 | 40910.1 | 0 | 38516.94 | 71.5% | 29233.55 | 11676.55 |  |  | Sierra South
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Fixed fee | Lab/Curation | Louis Huff | 76500 | 58746.94 | 55119.6 | 3627.34 | 76500 | 100% | 63236.56 | -4489.62 |  |  | Sierra
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | Time and material | In Progress | Steve Rubio | 56300 | 42714.81 | 42714.81 | 0 | 38284 | 68% | 47948.89 | -5234.08 |  |  | Coastal Bend
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | Fixed fee | In Progress | Jared Choi | 33100 | 29128 | 29128 | 0 | 24874.65 | 75.1% | 21890.46 | 7237.54 |  |  | Coastal Bend
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Fixed fee | Cost Tracking on Closed Project | Diane Daniels | 349600 | 221087.04 | 221087.04 | 0 | 349600 | 100% | 229204.35 | -8117.31 |  |  | Coastal Bend
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | Fixed fee | Transferred Entity | Duane Ballard | 132000 | 108108 | 108108 | 0 | 92584.8 | 70.1% | 75830.35 | 32277.65 |  |  | Coastal Bend
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Fixed fee | Lab/Curation | Alexis Nixon | 755000 | 444695 | 444695 | 0 | 705170 | 93.4% | 415325.46 | 29369.54 |  |  | Coastal Bend
23-PC-41613 | Tamarack School Campus Archaeological Testing | Fixed fee | In Progress | Steve Rubio | 151900 | 105099.61 | 105099.61 | 0 | 128659.3 | 84.7% | 89014.21 | 16085.4 |  |  | Coastal Bend
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | Time and material | In Progress | Jesse Maynard | 18800 | 12705.04 | 12705.04 | 0 | 12784 | 68% | 12736.47 | -31.43 |  |  | Built Environment
23-PC-42771 | Redbud Housing Development GIS Mapping | Fixed fee | In Progress | Kyle Maynard | 25200 | 18799.2 | 18799.2 | 0 | 19124.28 | 75.9% | 14265.92 | 4533.28 |  |  | Maritime
23-PC-42981 | Hawk Point Architectural History Survey | Fixed fee | In Progress | Kyle Maynard | 175800 | 129494.28 | 129494.28 | 0 | 133203.66 | 75.8% | 98123.54 | 31370.74 |  |  | Maritime
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | Time and material | In Progress | Rita Ayala | 139700 | 93543.12 | 93543.12 | 0 | 94996 | 68% | 67047.93 | 26495.19 |  |  | Maritime
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | Fixed fee | In Progress | Priscilla Pennington | 73300 | 53362.4 | 53362.4 | 0 | 66563.73 | 90.8% | 48458.95 | 4903.45 |  |  | Geospatial
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | Fixed fee | In Progress | Lynn Tran | 112600 | 77637.7 | 77637.7 | 0 | 91374.9 | 81.1% | 63002.79 | 14634.91 |  |  | Meridian Southwest
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | Fixed fee | In Progress | Javier Estrada | 93300 | 59544.06 | 59544.06 | 0 | 93300 | 100% | 93708.96 | -34164.9 |  |  | Big Sky
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | Fixed fee | In Progress | Kiara Gillespie | 60600 | 45577.26 | 45577.26 | 0 | 60600 | 100% | 50596.88 | -5019.62 |  |  | Bluegrass
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Time and material | Cost Tracking on Closed Project | Preston Duarte | 94000 | 65640.2 | 65640.2 | 0 | 63920 | 68% | 73270.02 | -7629.82 |  |  | Cascade
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | Fixed fee | In Progress | Jean Cooke | 18200 | 12417.86 | 12417.86 | 0 | 13335.14 | 73.3% | 9098.08 | 3319.78 |  |  | Cascade
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | Time and material | In Progress | Gene Nixon | 18300 | 11931.6 | 11931.6 | 0 | 12444 | 68% | 9112.04 | 2819.56 |  |  | Cascade
24-PC-31503 | North Fork Wind Farm Curation | Time and material | Lab/Curation | Preston Duarte | 129900 | 87825.39 | 87825.39 | 0 | 88332 | 68% | 98773.26 | -10947.87 |  |  | Cascade
24-PC-31663 | Fern Valley Section 106 Consultation | Fixed fee | In Progress | Jean Cooke | 52600 | 37714.2 | 37714.2 | 0 | 43847.36 | 83.4% | 31436.99 | 6277.21 |  |  | Cascade
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | Time and material | In Progress | Gene Nixon | 15200 | 10676.48 | 10676.48 | 0 | 10871.15 | 71.5% | 7665.21 | 3011.27 |  |  | Cascade
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | In Progress | Jason Oconnor | 51800 | 36731.38 | 36731.38 | 0 | 51800 | 100% | 59530.75 | -22799.37 |  |  | Chesapeake
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | Alexandria Wilkinson | 84000 | 70198.8 | 70198.8 | 0 | 84000 | 100% | 85361.67 | -15162.87 |  |  | Chesapeake
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | Fixed fee | In Progress | Ian Maddox | 51700 | 45206.48 | 45206.48 | 0 | 44730.84 | 86.5% | 39111.36 | 6095.12 |  |  | Chesapeake
24-PC-33448 | Ember Valley Solar Architectural History Survey | Fixed fee | In Progress | Devon Pitts | 681000 | 419972.7 | 419972.7 | 0 | 563868 | 82.8% | 347755.54 | 72217.16 |  |  | Front Range
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | Fixed fee | In Progress | Karl Valenzuela | 64500 | 49568.25 | 49568.25 | 0 | 59346.45 | 92% | 45606.09 | 3962.16 |  |  | Great Lakes
24-PC-33985 | Thistle Down Substation Curation | Time and material | In Progress | Angelica Cervantes | 78300 | 57863.7 | 57863.7 | 0 | 53244 | 68% | 50630.38 | 7233.32 |  |  | Great Lakes
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | Time and material | In Progress | Karl Valenzuela | 38700 | 26644.95 | 26644.95 | 0 | 26316 | 68% | 19241.81 | 7403.14 |  |  | Great Lakes
24-PC-34663 | Redbud Airport Apron - GIS Mapping | Time and material | In Progress | Kathleen Galvan | 505100 | 342760.86 | 342760.86 | 0 | 343468 | 68% | 286062.16 | 56698.7 |  |  | Great Lakes
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | Time and material | In Progress | Courtney Daugherty | 176500 | 121414.35 | 121414.35 | 0 | 120020 | 68% | 122080.25 | -665.9 |  |  | Gulf Coast
24-PC-34975 | Foxglove Fiber Route GIS Mapping | Fixed fee | In Progress | Bernard Erickson | 205900 | 181192 | 181192 | 0 | 175159.13 | 85.1% | 154132.44 | 27059.56 |  |  | Gulf Coast West
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | Time and material | In Progress | Kathy Hurley | 301200 | 217496.52 | 217496.52 | 0 | 204816 | 68% | 196030.1 | 21466.42 |  |  | High Desert
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | Fixed fee | In Progress | Eileen Poole | 119200 | 88243.76 | 88243.76 | 0 | 90150.96 | 75.6% | 66735.14 | 21508.62 |  |  | High Desert
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | Time and material | In Progress | Kathy Hurley | 69900 | 49013.31 | 40696.6 | 8316.71 | 69900 | 100% | 53862.59 | -4849.28 |  |  | High Desert
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | Time and material | In Progress | Kathy Hurley | 225100 | 153743.3 | 153743.3 | 0 | 200102.05 | 88.9% | 140872.8 | 12870.5 |  |  | High Desert
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | Fixed fee | In Progress | Eileen Poole | 12900 | 9094.5 | 9094.5 | 0 | 10859.22 | 84.2% | 7655.43 | 1439.07 |  |  | High Desert
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Fixed fee | Cost Tracking on Closed Project | Kathy Hurley | 58300 | 39072.66 | 39072.66 | 0 | 58300 | 100% | 45518.79 | -6446.13 |  |  | High Desert
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | Time and material | In Progress | Kathy Hurley | 5700 | 4244.79 | 4244.79 | 0 | 3876 | 68% | 3255.04 | 989.75 |  |  | High Desert
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Fixed fee | Cost Tracking on Closed Project | Rodney Mcguire | 56300 | 37721 | 37721 | 0 | 52077.5 | 92.5% | 34891.33 | 2829.67 |  |  | Island
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | Fixed fee | In Progress | Glen Delacruz | 141000 | 113970.3 | 113970.3 | 0 | 141000 | 100% | 138124.06 | -24153.76 |  |  | Hill Country
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | Fixed fee | In Progress | Gail Meza | 1259200 | 853989.44 | 853989.44 | 0 | 928785.92 | 73.8% | 629919.62 | 224069.82 |  |  | Hill Country
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | Time and material | In Progress | Samuel Wilkerson | 67000 | 40709.2 | 40709.2 | 0 | 51564 | 77% | 34240.46 | 6468.74 |  |  | Hill Country
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | Fixed fee | In Progress | Theresa Fernandez | 298500 | 243904.35 | 243904.35 | 0 | 213069.3 | 71.4% | 174092.01 | 69812.34 |  |  | Hill Country
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | Time and material | In Progress | Jody Chung | 309400 | 184093 | 184093 | 0 | 210392 | 68% | 149432.06 | 34660.94 |  |  | PIEDMONT - INACTIVE
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | Fixed fee | In Progress | Sherry Lloyd | 132200 | 95580.6 | 95580.6 | 0 | 121663.66 | 92% | 87961.2 | 7619.4 |  |  | Prairie
24-PC-38486 | Kestrel Butte Phase I Survey | Fixed fee | In Progress | Jeanette Chung | 153600 | 105043.81 | 77500.98 | 27542.83 | 153600 | 100% | 119866.24 | -14822.43 |  |  | Red Rock
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | Marisa Odom | 168200 | 130489.56 | 130489.56 | 0 | 168200 | 100% | 132230.67 | -1741.11 |  |  | Red Rock
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | Fixed fee | In Progress | Shelia Horne | 100200 | 72685.08 | 72685.08 | 0 | 100200 | 100% | 103671 | -30985.92 |  |  | Red Rock
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | Time and material | In Progress | Lydia Cisneros | 126600 | 82581.18 | 82581.18 | 0 | 86088 | 68% | 59856.61 | 22724.57 |  |  | Red Rock
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | Fixed fee | In Progress | Javier Newman | 597800 | 435557.08 | 435557.08 | 0 | 458990.84 | 76.8% | 334422.57 | 101134.51 |  |  | Red Rock
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Fixed fee | Cost Tracking on Closed Project | Shelia Horne | 11000 | 7227 | 7227 | 0 | 11000 | 100% | 7427.79 | -200.79 |  |  | Red Rock
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | Time and material | In Progress | Tina Aguirre | 33000 | 23227.58 | 20462.4 | 2765.18 | 29186 | 88.4% | 29633.53 | -6405.95 |  |  | Red Rock
24-PC-39533 | Elk Meadow Architectural History Survey | Fixed fee | In Progress | Jeanette Chung | 67000 | 52641.9 | 52641.9 | 0 | 63536.1 | 94.8% | 49919.2 | 2722.7 |  |  | Red Rock
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | Fixed fee | In Progress | Bruce Suarez | 17800 | 14308.95 | 10538.95 | 3770 | 17800 | 100% | 14659.16 | -350.21 |  |  | Red Rock
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | Time and material | In Progress | Lydia Cisneros | 414900 | 270722.25 | 270722.25 | 0 | 339174.65 | 81.7% | 215589.53 | 55132.72 |  |  | Red Rock
24-PC-40067 | Saltgrass Fiber Route Class III Survey | Time and material | In Progress | Marisa Odom | 218100 | 163684.05 | 163684.05 | 0 | 148308 | 68% | 137568.33 | 26115.72 |  |  | Red Rock
24-PC-40102 | Redbud Class III Survey | Fixed fee | Final Reporting/Review | Benjamin Mathis | 453900 | 322187.01 | 278794.4 | 43392.61 | 453900 | 100% | 359994.61 | -37807.6 |  |  | Sierra
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | Fixed fee | In Progress | Angelica Poole | 460500 | 381017.7 | 381017.7 | 0 | 326540.55 | 70.9% | 270177.47 | 110840.23 |  |  | Sierra
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Fixed fee | Cost Tracking on Closed Project | Louis Huff | 50300 | 35350.84 | 35350.84 | 0 | 46200.55 | 91.8% | 32471.24 | 2879.6 |  |  | Sierra North
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Fixed fee | Final Reporting/Review | Donna Herring | 22100 | 17918.68 | 17918.68 | 0 | 22100 | 100% | 33602.1 | -15683.42 |  |  | Sierra North
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | Time and material | In Progress | Alexis Nixon | 48400 | 37137.32 | 37137.32 | 0 | 48400 | 100% | 47362.38 | -10225.06 |  |  | Coastal Bend
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Fixed fee | Final Reporting/Review | Duane Ballard | 31800 | 20975.28 | 20975.28 | 0 | 31800 | 100% | 22323.11 | -1347.83 |  |  | Coastal Bend
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Fixed fee | Lab/Curation | Diane Daniels | 579300 | 392475.75 | 392475.75 | 0 | 579300 | 100% | 413750.74 | -21274.99 |  |  | Coastal Bend
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | Fixed fee | In Progress | Diane Daniels | 8800 | 6914.16 | 6914.16 | 0 | 8800 | 100% | 7269.9 | -355.74 |  |  | Coastal Bend
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | Time and material | In Progress | Alexis Nixon | 60600 | 39983.88 | 39983.88 | 0 | 41208 | 68% | 31771.04 | 8212.84 |  |  | Coastal Bend
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Fixed fee | Transferred Entity | Alexis Nixon | 18000 | 12312 | 12312 | 0 | 18000 | 100% | 22722.22 | -10410.22 |  |  | Coastal Bend
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | Fixed fee | In Progress | Alexis Nixon | 194900 | 131089.74 | 131089.74 | 0 | 187591.25 | 96.3% | 126178.41 | 4911.33 |  |  | Coastal Bend
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | Time and material | In Progress | Charlene Sparks | 263500 | 173567.45 | 173567.45 | 0 | 179180 | 68% | 177335 | -3767.55 |  |  | Paleontology
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | Fixed fee | In Progress | Sylvia Callahan | 639100 | 498050.63 | 498050.63 | 0 | 451268.51 | 70.6% | 351673.07 | 146377.56 |  |  | Geospatial
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | Time and material | In Progress | Sylvia Callahan | 19700 | 14170.21 | 14170.21 | 0 | 13396 | 68% | 18919.28 | -4749.07 |  |  | Geospatial
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | Time and material | In Progress | Lynn Tran | 1003600 | 771166.24 | 771166.24 | 0 | 682448 | 68% | 614867.84 | 156298.4 |  |  | Meridian Southwest
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | Fixed fee | Transferred Entity | Vanessa Duarte | 213100 | 187528 | 187528 | 0 | 152792.6987 | 71.7% | 134454.77 | 53073.23 |  |  | NH Gulf (USD)
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Time and material | Transferred Entity | Susan Wilkins | 264500 | 194222.35 | 194222.35 | 0 | 264500 | 100% | 246339.6193 | -52117.2693 |  |  | NH Gulf (USD)
24-PC-44158 | Saltgrass Environmental Review Support | Fixed fee | Transferred Entity | Vanessa Duarte | 23200 | 15583.44 | 15583.44 | 0 | 23200 | 100% | 16044.04 | -460.6 |  |  | NH Gulf (USD)
25-PC-30345 | Wildrye Phase II Testing | Fixed fee | In Progress | Brendan Melton | 160400 | 92631 | 92631 | 0 | 130998.68 | 81.7% | 75656.14 | 16974.86 |  |  | Big Sky
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | Fixed fee | In Progress | Alice Galloway | 19700 | 13027.61 | 13027.61 | 0 | 19700 | 100% | 13683.52 | -655.91 |  |  | Bluegrass
25-PC-30772 | Sea Oat Cultural Resources Assessment | Fixed fee | In Progress | Alice Galloway | 63300 | 43065.84 | 35870.85 | 7194.99 | 63300 | 100% | 56416.91 | -13351.07 |  |  | Bluegrass
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | Fixed fee | In Progress | Alice Galloway | 131000 | 85464.4 | 85464.4 | 0 | 131000 | 100% | 90183.9 | -4719.5 |  |  | Bluegrass
25-PC-31109 | Riverbend GIS Mapping | Time and material | In Progress | Cassidy Gay | 174700 | 109484.49 | 109484.49 | 0 | 174700 | 100% | 162892.26 | -53407.77 |  |  | Cascade
25-PC-31114 | Granite Pass Built Environment Survey | Time and material | In Progress | Jean Cooke | 229400 | 157964.84 | 157964.84 | 0 | 179308.8 | 78.2% | 127618.8 | 30346.04 |  |  | Cascade
25-PC-31180 | Blue Heron Environmental Review Support | Fixed fee | In Progress | Preston Duarte | 80000 | 60701.89 | 45712.3 | 14989.59 | 80000 | 100% | 64096.36 | -3394.47 |  |  | Cascade
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Fixed fee | Lab/Curation | Donald Lutz | 23500 | 17263.1 | 17263.1 | 0 | 23500 | 100% | 22123.1 | -4860 |  |  | Cascade
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | Fixed fee | In Progress | Cassidy Gay | 52000 | 38781.6 | 38781.6 | 0 | 52000 | 100% | 51500.29 | -12718.69 |  |  | Cascade
25-PC-31555 | Wren Hollow Architectural History Survey | Fixed fee | In Progress | Gene Nixon | 69300 | 53097.66 | 53097.66 | 0 | 66417.12 | 95.8% | 50888.1 | 2209.56 |  |  | Cascade
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | Fixed fee | In Progress | Jean Cooke | 16800 | 11810.4 | 11810.4 | 0 | 16800 | 100% | 15531.6 | -3721.2 |  |  | Cascade
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Time and material | Final Reporting/Review | Jeff Spence | 30300 | 22049.31 | 22049.31 | 0 | 30300 | 100% | 34568.28 | -12518.97 |  |  | Cascade
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | Fixed fee | In Progress | Preston Duarte | 216800 | 171337.04 | 171337.04 | 0 | 216800 | 100% | 185663.62 | -14326.58 |  |  | Cascade
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Time and material | Cost Tracking on Closed Project | Donald Lutz | 40900 | 28728.16 | 28728.16 | 0 | 13987.8 | 34.2% | 33002.57 | -4274.41 |  |  | Cascade
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Time and material | Final Reporting/Review | Jason Oconnor | 35200 | 24481.6 | 24481.6 | 0 | 35200 | 100% | 39794.35 | -15312.75 |  |  | Chesapeake
25-PC-32024 | Pine Hollow Historic Resources Evaluation | Time and material | In Progress | Ian Maddox | 79500 | 57637.5 | 57637.5 | 0 | 57058 | 71.8% | 41962.52 | 15674.98 |  |  | Chesapeake
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | Time and material | In Progress | Ian Maddox | 201300 | 150874.35 | 150874.35 | 0 | 196916.6 | 97.8% | 161800.48 | -10926.13 |  |  | Chesapeake
25-PC-32447 | Pebble Beach Road Archaeological Testing | Fixed fee | In Progress | Alexandria Wilkinson | 88200 | 61772.24 | 55626.38 | 6145.86 | 88200 | 100% | 76703.23 | -14930.99 |  |  | Chesapeake
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | Time and material | In Progress | Sandy Kerr | 118800 | 85013.28 | 85013.28 | 0 | 118800 | 100% | 117591.53 | -32578.25 |  |  | Chesapeake
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | Time and material | In Progress | Jeremy Tran | 86500 | 62245.4 | 62245.4 | 0 | 83279.75 | 96.3% | 49276.48 | 12968.92 |  |  | Front Range
25-PC-32795 | North Fork Water Main Architectural History Survey | Time and material | In Progress | Reginald Vargas | 16900 | 11650.86 | 11650.86 | 0 | 16900 | 100% | 12884.7 | -1233.84 |  |  | Front Range
25-PC-32838 | Aspen Ridge Canal Lining - Curation | Fixed fee | In Progress | Jeremy Tran | 42600 | 33543.24 | 33543.24 | 0 | 39204.78 | 92% | 30870.45 | 2672.79 |  |  | Front Range
25-PC-32861 | Yarrow Point Architectural History Survey | Fixed fee | In Progress | Dean Velazquez | 59200 | 41555.52 | 31694.67 | 9860.85 | 59200 | 100% | 49895.36 | -8339.84 |  |  | Front Range
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | Fixed fee | In Progress | Jeremy Tran | 59600 | 51399.04 | 51399.04 | 0 | 59600 | 100% | 74823.59 | -23424.55 |  |  | Front Range
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Time and material | Lab/Curation | Jeremy Tran | 13300 | 8727.43 | 6386.48 | 2340.95 | 13300 | 100% | 16463.41 | -7735.98 |  |  | Front Range
25-PC-33065 | Wren Hollow GIS Mapping | Fixed fee | In Progress | Dean Velazquez | 50400 | 40748.4 | 40748.4 | 0 | 45596.88 | 90.5% | 36866.22 | 3882.18 |  |  | Front Range
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | Fixed fee | In Progress | Reginald Vargas | 767800 | 553046.34 | 553046.34 | 0 | 603874.7 | 78.6% | 434972.87 | 118073.47 |  |  | Front Range
25-PC-33105 | Redbud Data Recovery | Fixed fee | In Progress | Kimberly Daugherty | 3500 | 2324 | 2324 | 0 | 3500 | 100% | 9006.2 | -6682.2 |  |  | Front Range
25-PC-33183 | Saltgrass Architectural History Survey | Fixed fee | In Progress | Dean Velazquez | 104500 | 79399.1 | 79399.1 | 0 | 101009.7 | 96.7% | 76745.43 | 2653.67 |  |  | Front Range
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | Fixed fee | In Progress | Devon Pitts | 41600 | 29136.64 | 29136.64 | 0 | 32406.4 | 77.9% | 22697.51 | 6439.13 |  |  | Front Range
25-PC-33744 | Blue Heron Canal Lining - Curation | Fixed fee | In Progress | Nathan Lambert | 87100 | 60133.84 | 60133.84 | 0 | 64332.06 | 73.9% | 44412.55 | 15721.29 |  |  | Great Lakes
25-PC-33750 | Kestrel Butte Archaeological Testing | Fixed fee | Transferred Entity | Kathleen Galvan | 69600 | 51302.16 | 51302.16 | 0 | 69600 | 100% | 60286.74 | -8984.58 |  |  | Great Lakes
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Fixed fee | Final Reporting/Review | Geoffrey Fernandez | 15200 | 11021.49 | 9579.99 | 1441.5 | 15200 | 100% | 11383.28 | -361.79 |  |  | Great Lakes
25-PC-33922 | Slate Ridge Data Recovery | Fixed fee | In Progress | Nathan Lambert | 22100 | 16113.11 | 16113.11 | 0 | 22100 | 100% | 33890.09 | -17776.98 |  |  | Great Lakes
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | Time and material | In Progress | Geoffrey Fernandez | 53000 | 36718.4 | 36718.4 | 0 | 53000 | 100% | 42629.29 | -5910.89 |  |  | Great Lakes
25-PC-34451 | North Fork Curation | Time and material | In Progress | Robin Mercado | 46400 | 32526.4 | 32526.4 | 0 | 46400 | 100% | 41685.4 | -9159 |  |  | Great Lakes
25-PC-34652 | Coyote Springs Section 106 Consultation | Fixed fee | In Progress | Gina Beltran | 210700 | 180928.09 | 180928.09 | 0 | 176145.2 | 83.6% | 151256.79 | 29671.3 |  |  | Great Lakes
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | Time and material | In Progress | Gina Beltran | 82200 | 51638.04 | 51638.04 | 0 | 82200 | 100% | 83204.3 | -31566.26 |  |  | Great Lakes
25-PC-34850 | Thistle Down Section 106 Consultation | Time and material | In Progress | Wyatt Erickson | 201300 | 117035.82 | 117035.82 | 0 | 129963.25 | 64.6% | 94500.26 | 22535.56 |  |  | Gulf Coast East
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | Fixed fee | In Progress | Wyatt Erickson | 224400 | 165046.2 | 165046.2 | 0 | 157798.08 | 70.3% | 116067.93 | 48978.27 |  |  | Gulf Coast
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | Time and material | In Progress | Bernard Erickson | 71400 | 48880.44 | 48880.44 | 0 | 71400 | 100% | 56947.79 | -8067.35 |  |  | Gulf Coast East
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | Time and material | In Progress | Wyatt Erickson | 33200 | 23495.64 | 23495.64 | 0 | 33200 | 100% | 28098.77 | -4603.13 |  |  | Gulf Coast
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | Time and material | In Progress | Bernard Erickson | 49900 | 35982.89 | 35982.89 | 0 | 49900 | 100% | 42125.73 | -6142.84 |  |  | Gulf Coast West
25-PC-35295 | Copper Flats Architectural History Survey | Time and material | In Progress | Bernard Erickson | 80400 | 54551.4 | 54551.4 | 0 | 54672 | 68% | 39686.68 | 14864.72 |  |  | Gulf Coast East
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | Fixed fee | In Progress | Bernard Erickson | 19400 | 13919.5 | 13919.5 | 0 | 19400 | 100% | 36287.62 | -22368.12 |  |  | Gulf Coast East
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | Fixed fee | In Progress | Courtney Daugherty | 25100 | 20032.31 | 20032.31 | 0 | 25100 | 100% | 27206.94 | -7174.63 |  |  | Gulf Coast
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | Time and material | In Progress | Kathy Hurley | 136900 | 90994.45 | 78522.66 | 12471.79 | 136900 | 100% | 119032.95 | -28038.5 |  |  | High Desert
25-PC-35496 | Silver Lake Airport Apron Class III Survey | Time and material | In Progress | Kathy Hurley | 15200 | 10132.32 | 10132.32 | 0 | 14910.4 | 98.1% | 10426.69 | -294.37 |  |  | High Desert
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | Fixed fee | In Progress | Bridget Maddox | 98800 | 78447.2 | 78447.2 | 0 | 77370.28 | 78.3% | 61430.39 | 17016.81 |  |  | High Desert
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | Fixed fee | In Progress | Kathy Hurley | 204800 | 136396.8 | 136396.8 | 0 | 204800 | 100% | 140077.69 | -3680.89 |  |  | High Desert
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | Fixed fee | In Progress | Jody Wang | 83700 | 61050.78 | 61050.78 | 0 | 76761.27 | 91.7% | 55992.16 | 5058.62 |  |  | High Desert
25-PC-35963 | Quail Run Substation - Section 106 Consultation | Time and material | In Progress | Kathy Hurley | 320000 | 216192 | 216192 | 0 | 290771 | 90.9% | 202041.59 | 14150.41 |  |  | High Desert
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | Time and material | In Progress | Kathy Hurley | 114200 | 78124.22 | 78124.22 | 0 | 114200 | 100% | 79562.79 | -1438.57 |  |  | High Desert
25-PC-36251 | Kestrel Butte Environmental Review Support | Fixed fee | Lab/Curation | Joan Mathis | 39200 | 30446.64 | 30446.64 | 0 | 39200 | 100% | 49335.55 | -18888.91 |  |  | Island
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | Time and material | In Progress | Joan Mathis | 28100 | 19141.72 | 19141.72 | 0 | 24522.2 | 87.3% | 16573.11 | 2568.61 |  |  | Island
25-PC-36336 | Sea Oat Canal Lining Data Recovery | Fixed fee | In Progress | Briana Melton | 36400 | 25854.92 | 25854.92 | 0 | 33364.24 | 91.7% | 23699.14 | 2155.78 |  |  | Island
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | Fixed fee | In Progress | Becky Velazquez | 33100 | 25870.96 | 25870.96 | 0 | 33100 | 100% | 34277.75 | -8406.79 |  |  | Island
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | Fixed fee | In Progress | Joan Mathis | 88300 | 54269.18 | 54269.18 | 0 | 68397.18 | 77.5% | 42036.07 | 12233.11 |  |  | Island
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | Fixed fee | In Progress | Becky Velazquez | 116000 | 66050.4 | 66050.4 | 0 | 85573.2 | 73.8% | 48723.63 | 17326.77 |  |  | Island
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | Time and material | In Progress | Lucas Benson | 181300 | 117609.31 | 117609.31 | 0 | 181300 | 100% | 164790.18 | -47180.87 |  |  | Lakeshore
25-PC-36645 | Falcon Mesa Archaeological Testing | Fixed fee | In Progress | Jeanette Riddle | 25400 | 20302.22 | 20302.22 | 0 | 25400 | 100% | 38922.61 | -18620.39 |  |  | Lakeshore
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | Time and material | In Progress | Lucas Benson | 137400 | 99958.5 | 99958.5 | 0 | 108023.85 | 78.6% | 83440.54 | 16517.96 |  |  | Lakeshore
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Fixed fee | Final Reporting/Review | Jeanette Riddle | 74000 | 56358.4 | 56358.4 | 0 | 74000 | 100% | 66079.16 | -9720.76 |  |  | Lakeshore
25-PC-36799 | Meadowlark Substation Phase I Survey | Fixed fee | Final Reporting/Review | Gail Meza | 32900 | 26389.09 | 26389.09 | 0 | 32900 | 100% | 33048.52 | -6659.43 |  |  | Hill Country
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | Fixed fee | In Progress | Samuel Wilkerson | 24200 | 16235.78 | 16235.78 | 0 | 24200 | 100% | 26420.57 | -10184.79 |  |  | Hill Country
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | Time and material | In Progress | Glen Delacruz | 75400 | 50299.34 | 50299.34 | 0 | 75400 | 100% | 90901.92 | -40602.58 |  |  | Hill Country
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | Fixed fee | In Progress | Maria Parrish | 59200 | 50698.88 | 50698.88 | 0 | 54913.92 | 92.8% | 47030.53 | 3668.35 |  |  | Piedmont
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Time and material | Cost Tracking on Closed Project | Megan Pineda | 83200 | 60186.88 | 60186.88 | 0 | 22297.6 | 26.8% | 78242.94 | -18056.06 |  |  | Piedmont
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | Time and material | In Progress | Jody Chung | 458200 | 301449.78 | 301449.78 | 0 | 311576 | 68% | 240796.49 | 60653.29 |  |  | Piedmont
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Fixed fee | Lab/Curation | Jody Chung | 21500 | 15617.6 | 15617.6 | 0 | 21500 | 100% | 19499.41 | -3881.81 |  |  | Piedmont
25-PC-37732 | Hawk Point Housing Development Class III Survey | Fixed fee | In Progress | Megan Pineda | 72900 | 45824.94 | 45824.94 | 0 | 64100.97 | 87.9% | 40294.47 | 5530.47 |  |  | Piedmont
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Time and material | Final Reporting/Review | Maria Parrish | 72200 | 44893.96 | 44893.96 | 0 | 69466.7 | 96.2% | 57390.52 | -12496.56 |  |  | Piedmont
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | Fixed fee | In Progress | Megan Pineda | 7900 | 6020.59 | 6020.59 | 0 | 7900 | 100% | 6629.3 | -608.71 |  |  | Piedmont
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | Fixed fee | In Progress | Sherry Lloyd | 148100 | 106809.72 | 106809.72 | 0 | 109890.2 | 74.2% | 79254.52 | 27555.2 |  |  | Prairie
25-PC-38042 | Oak Terrace School Campus GIS Mapping | Fixed fee | In Progress | Sherry Lloyd | 24300 | 19082.79 | 19082.79 | 0 | 20144.7 | 82.9% | 15820.03 | 3262.76 |  |  | Prairie
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | Fixed fee | In Progress | Sherry Lloyd | 25300 | 16961.12 | 16961.12 | 0 | 20781.42 | 82.1% | 13931.44 | 3029.68 |  |  | Prairie
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | Fixed fee | In Progress | Sherry Lloyd | 136400 | 86736.76 | 86736.76 | 0 | 99080.96 | 72.6% | 63001.3 | 23735.46 |  |  | Prairie
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | Time and material | In Progress | Jeanette Chung | 496400 | 357705.84 | 357705.84 | 0 | 481730.55 | 97% | 311579.9 | 46125.94 |  |  | Red Rock
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | Fixed fee | In Progress | Lydia Cisneros | 176400 | 137697.84 | 137697.84 | 0 | 154297.08 | 87.5% | 120438.25 | 17259.59 |  |  | Red Rock
25-PC-38701 | Slate Ridge Curation | Time and material | In Progress | Javier Newman | 156400 | 98735.32 | 98735.32 | 0 | 109600.75 | 70.1% | 71024.19 | 27711.13 |  |  | Red Rock
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | Fixed fee | In Progress | Javier Newman | 63900 | 41637.24 | 41637.24 | 0 | 63900 | 100% | 60770.39 | -19133.15 |  |  | Red Rock
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Fixed fee | Final Reporting/Review | Bruce Suarez | 10400 | 5866.64 | 5866.64 | 0 | 10400 | 100% | 18017.52 | -12150.88 |  |  | Red Rock
25-PC-38879 | Kestrel Butte Built Environment Survey | Fixed fee | In Progress | Marisa Odom | 119700 | 70323.75 | 70323.75 | 0 | 88482.24 | 73.9% | 51984.23 | 18339.52 |  |  | Red Rock
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | Time and material | In Progress | Tina Aguirre | 244000 | 174704 | 174704 | 0 | 201680 | 82.7% | 157468.07 | 17235.93 |  |  | Red Rock
25-PC-39085 | Slate Ridge Environmental Review Support | Fixed fee | In Progress | Bruce Suarez | 120700 | 69209.38 | 69209.38 | 0 | 119806.82 | 99.3% | 68696.85 | 512.53 |  |  | Red Rock
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | Fixed fee | In Progress | Shelia Horne | 90300 | 58198.35 | 58198.35 | 0 | 67986.87 | 75.3% | 43819.98 | 14378.37 |  |  | Red Rock
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Time and material | Final Reporting/Review | Tina Aguirre | 55900 | 39633.1 | 39633.1 | 0 | 55900 | 100% | 38428.92 | 1204.18 |  |  | Red Rock
25-PC-39424 | Tansy Flat Cultural Resources Assessment | Fixed fee | In Progress | Shelia Horne | 19700 | 13882.59 | 13882.59 | 0 | 19700 | 100% | 16267.84 | -2385.25 |  |  | Red Rock
25-PC-39554 | Thistle Down Archaeological Testing | Fixed fee | In Progress | Tina Aguirre | 86700 | 63594.45 | 63594.45 | 0 | 75628.41 | 87.2% | 55476.01 | 8118.44 |  |  | Red Rock
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | Time and material | In Progress | Javier Newman | 51000 | 36551.7 | 36551.7 | 0 | 51000 | 100% | 75197.04 | -38645.34 |  |  | Red Rock
25-PC-40383 | North Fork Archaeological Testing | Fixed fee | In Progress | Donna Herring | 193200 | 144185.16 | 144185.16 | 0 | 161148.12 | 83.4% | 120262.61 | 23922.55 |  |  | Sierra
25-PC-40503 | Copper Flats Phase I Survey | Time and material | Lab/Curation | Benjamin Mathis | 43400 | 30119.6 | 30119.6 | 0 | 43400 | 100% | 42364.23 | -12244.63 |  |  | Sierra
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | Time and material | In Progress | Donna Herring | 71000 | 49579.3 | 49579.3 | 0 | 71000 | 100% | 76399.6 | -26820.3 |  |  | Sierra
25-PC-40677 | Quail Run Paleontological Monitoring | Time and material | Transferred Entity | Louis Huff | 225000 | 157612.5 | 157612.5 | 0 | 192903.25 | 85.7% | 153698.04 | 3914.46 |  |  | Sierra South
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Fixed fee | Transferred Entity | Duane Ballard | 50100 | 34844.55 | 34844.55 | 0 | 50100 | 100% | 37556.22 | -2711.67 |  |  | Coastal Bend
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Fixed fee | Final Reporting/Review | Jared Choi | 46800 | 34243.56 | 34243.56 | 0 | 46800 | 100% | 37494.89 | -3251.33 |  |  | Coastal Bend
25-PC-41187 | Hackberry Bend Trail GIS Mapping | Fixed fee | In Progress | Diane Daniels | 98900 | 55621.36 | 55621.36 | 0 | 75510.15 | 76.3% | 42469.63 | 13151.73 |  |  | Coastal Bend
25-PC-41265 | Larkspur Class III Survey | Fixed fee | Cost Tracking on Closed Project | Diane Daniels | 89800 | 71911.84 | 71911.84 | 0 | 85318.98 | 95% | 68323.14 | 3588.7 |  |  | Coastal Bend
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | Fixed fee | In Progress | Diane Daniels | 167900 | 131616.81 | 131616.81 | 0 | 133782.72 | 79.7% | 104866.5 | 26750.31 |  |  | Coastal Bend
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | Fixed fee | In Progress | Diane Daniels | 179800 | 119171.44 | 119171.44 | 0 | 179800 | 100% | 171055.95 | -51884.51 |  |  | Coastal Bend
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | Time and material | In Progress | Jared Choi | 130200 | 94156.73 | 81265.42 | 12891.31 | 121022.45 | 93% | 105548.13 | -11391.4 |  |  | Coastal Bend
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | Time and material | In Progress | Jared Choi | 412300 | 281889.51 | 281889.51 | 0 | 300806.95 | 73% | 224531.7 | 57357.81 |  |  | Coastal Bend
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | Time and material | In Progress | Jenny Wilkinson | 152100 | 108599.4 | 108599.4 | 0 | 112187.4 | 73.8% | 90984.66 | 17614.74 |  |  | Built Environment
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | Time and material | In Progress | Rickey Salas | 39700 | 25920.13 | 25920.13 | 0 | 39700 | 100% | 29882.88 | -3962.75 |  |  | Built Environment
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Time and material | Cost Tracking on Closed Project | Kathleen Cabrera | 17900 | 12066.39 | 12066.39 | 0 | 161.1 | 0.9% | 14332.43 | -2266.04 |  |  | Built Environment
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | Fixed fee | In Progress | Charlene Sparks | 41200 | 29239.64 | 29239.64 | 0 | 32304.92 | 78.4% | 22925.4 | 6314.24 |  |  | Paleontology
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | Time and material | In Progress | Kyle Maynard | 130300 | 95796.56 | 95796.56 | 0 | 128601.35 | 98.7% | 79985.69 | 15810.87 |  |  | Maritime
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Time and material | Transferred Entity | Sylvia Callahan | 62000 | 44404.4 | 44404.4 | 0 | 54684.75 | 88.2% | 44584.79 | -180.39 |  |  | Geospatial
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | Fixed fee | In Progress | Seth Zavala | 128400 | 106315.2 | 106315.2 | 0 | 128400 | 100% | 195734.3 | -89419.1 |  |  | Meridian Central
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | Time and material | In Progress | Seth Zavala | 15700 | 10903.65 | 10903.65 | 0 | 15700 | 100% | 71168.37 | -60264.72 |  |  | Meridian Central
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Fixed fee | Cost Tracking on Closed Project | Clinton Solis | 715500 | 625275.45 | 625275.45 | 0 | 650818.8 | 91% | 568777.84 | 56497.61 |  |  | Meridian Central
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Fixed fee | Cost Tracking on Closed Project | Seth Zavala | 551800 | 378424.44 | 378424.44 | 0 | 551800 | 100% | 405626.36 | -27201.92 |  |  | Meridian Central
25-PC-43566 | Copper Flats Solar - Phase II Testing | Fixed fee | In Progress | Mathew Shea | 114200 | 73887.4 | 73887.4 | 0 | 114200 | 100% | 131458.02 | -57570.62 |  |  | Meridian Central
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | Fixed fee | In Progress | Alan Gay | 52800 | 37979.04 | 37979.04 | 0 | 52800 | 100% | 37986.88 | -7.84 |  |  | Meridian Southwest
25-PC-43639 | Windmill Flat Battery Storage Curation | Fixed fee | Final Reporting/Review | Harold Chaney | 137000 | 91502.3 | 91502.3 | 0 | 137000 | 100% | 100918.9 | -9416.6 |  |  | Meridian Southwest
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Fixed fee | Lab/Curation | Reginald Kerr | 92800 | 78211.84 | 78211.84 | 0 | 92800 | 100% | 103245.03 | -25033.19 |  |  | Meridian Southwest
25-PC-43993 | Timber Gap GIS Mapping | Fixed fee | Transferred Entity | Javier Rangel | 27900 | 19669.5 | 19669.5 | 0 | 20428.3787 | 73.22% | 14401.75 | 5267.75 |  |  | NH Gulf (USD)
25-PC-44046 | Kestrel Butte Section 106 Consultation | Fixed fee | Transferred Entity | Randy Cantu | 320300 | 220526.55 | 220526.55 | 0 | 320300 | 100% | 276639.9 | -56113.35 |  |  | NH Gulf (USD)
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | Time and material | Transferred Entity | Susan Wilkins | 31100 | 17934.14 | 13115.76 | 4818.38 | 31100 | 100% | 31276.1173 | -13341.9773 |  |  | NH Gulf (USD)
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | Fixed fee | In Progress | Randy Cantu | 97000 | 71004 | 71004 | 0 | 97000 | 100% | 79042.17 | -8038.17 |  |  | NH Gulf (USD)
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Time and material | Cost Tracking on Closed Project | Javier Estrada | 93100 | 63801.43 | 63801.43 | 0 | 0 | 0% | 65021.47 | -1220.04 |  |  | Big Sky
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | Fixed fee | In Progress | Brendan Melton | 19900 | 14258.19 | 12707.2 | 1550.99 | 19900 | 100% | 18074.33 | -3816.14 |  |  | Big Sky
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Time and material | Cost Tracking on Closed Project | Alice Galloway | 209800 | 135467.86 | 135467.86 | 0 | 0 | 0% | 134699.95 | 767.91 |  |  | Bluegrass
26-PC-31064 | Quail Run Archaeological Testing | Fixed fee | Cost Tracking on Closed Project | Gene Nixon | 74500 | 60394.3 | 53043.19 | 7351.11 | 74500 | 100% | 76340.83 | -15946.53 |  |  | Cascade
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | Fixed fee | In Progress | Donald Lutz | 44400 | 34032.6 | 34032.6 | 0 | 31128.84 | 70.1% | 23861.11 | 10171.49 |  |  | Cascade
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | Time and material | In Progress | Bryan Mann | 13700 | 9522.87 | 9522.87 | 0 | 13700 | 100% | 31103.81 | -21580.94 |  |  | Chesapeake
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Time and material | Cost Tracking on Closed Project | Sandy Kerr | 137100 | 100617.66 | 93287.5 | 7330.16 | 0 | 0% | 122245.29 | -21627.63 |  |  | Chesapeake
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Fixed fee | Final Reporting/Review | Karl Valenzuela | 21700 | 18501.42 | 18501.42 | 0 | 21700 | 100% | 21928.62 | -3427.2 |  |  | Great Lakes
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | Fixed fee | In Progress | Nathan Lambert | 76400 | 53087.85 | 46646.64 | 6441.21 | 76400 | 100% | 80951.18 | -27863.33 |  |  | Great Lakes
26-PC-34757 | Kestrel Butte Data Recovery | Time and material | In Progress | Angelica Cervantes | 43800 | 30230.76 | 30230.76 | 0 | 43800 | 100% | 49508.25 | -19277.49 |  |  | Great Lakes
26-PC-34982 | Sandpiper Historic Resources Evaluation | Time and material | In Progress | Bernard Erickson | 10600 | 7895.94 | 7895.94 | 0 | 10600 | 100% | 18818.09 | -10922.15 |  |  | Gulf Coast West
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | Fixed fee | In Progress | Courtney Daugherty | 29600 | 19287.36 | 19287.36 | 0 | 29600 | 100% | 56287.28 | -36999.92 |  |  | Gulf Coast East
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | Fixed fee | In Progress | Eileen Poole | 68900 | 53679.99 | 53679.99 | 0 | 59529.6 | 86.4% | 46380.29 | 7299.7 |  |  | High Desert
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Fixed fee | Cost Tracking on Closed Project | Jody Wang | 26300 | 19575.09 | 19575.09 | 0 | 26300 | 100% | 22787.95 | -3212.86 |  |  | High Desert
26-PC-37559 | Badger Hollow Paleontological Monitoring | Time and material | In Progress | Jody Chung | 44300 | 28024.18 | 28024.18 | 0 | 44300 | 100% | 45539.17 | -17514.99 |  |  | Piedmont
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | Fixed fee | In Progress | Jody Chung | 40300 | 32312.54 | 32312.54 | 0 | 31772.52 | 78.8% | 25475.14 | 6837.4 |  |  | Piedmont
26-PC-37709 | Sage Flat Phase I Survey | Fixed fee | Final Reporting/Review | Maria Parrish | 31500 | 21725.55 | 21725.55 | 0 | 31500 | 100% | 30289.1 | -8563.55 |  |  | Piedmont
26-PC-37965 | Redbud Cultural Resources Assessment | Time and material | In Progress | Annette Vaughan | 55400 | 34625 | 34625 | 0 | 50946.25 | 92% | 31687.21 | 2937.79 |  |  | Piedmont
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | Time and material | In Progress | Sherry Lloyd | 48300 | 32887.47 | 32887.47 | 0 | 38345.25 | 79.4% | 24978.26 | 7909.21 |  |  | Prairie
26-PC-38624 | Juniper Wash Built Environment Survey | Fixed fee | Cost Tracking on Closed Project | Bruce Suarez | 77900 | 56578.77 | 56578.77 | 0 | 77900 | 100% | 73552.4 | -16973.63 |  |  | Red Rock
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | Time and material | In Progress | Tina Aguirre | 97700 | 60828.02 | 60828.02 | 0 | 97700 | 100% | 76641.91 | -15813.89 |  |  | Red Rock
26-PC-39165 | Pebble Beach Road Phase I Survey | Fixed fee | Final Reporting/Review | Tina Aguirre | 94300 | 63218.72 | 63218.72 | 0 | 87472.68 | 92.8% | 58643.27 | 4575.45 |  |  | Red Rock
26-PC-39587 | Ember Valley Curation | Time and material | Cost Tracking on Closed Project | Javier Newman | 288900 | 211965.93 | 211965.93 | 0 | 0 | 0% | 213449.22 | -1483.29 |  |  | Red Rock
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Fixed fee | Cost Tracking on Closed Project | Tina Aguirre | 115900 | 86530.94 | 86530.94 | 0 | 115900 | 100% | 99694.97 | -13164.03 |  |  | Red Rock
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | Fixed fee | In Progress | Donna Herring | 96900 | 68401.71 | 68401.71 | 0 | 96900 | 100% | 75128.43 | -6726.72 |  |  | Sierra North
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Fixed fee | Final Reporting/Review | Louis Huff | 19200 | 14098.56 | 14098.56 | 0 | 19200 | 100% | 18399.82 | -4301.26 |  |  | Sierra
26-PC-40361 | Sea Oat Cultural Resources Assessment | Fixed fee | In Progress | Donna Herring | 156300 | 102829.77 | 102829.77 | 0 | 117897.09 | 75.4% | 77565.49 | 25264.28 |  |  | Sierra
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Fixed fee | Final Reporting/Review | Donna Herring | 5900 | 4379.73 | 3449.54 | 930.19 | 5900 | 100% | 8489.9 | -4110.17 |  |  | Sierra South
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | Fixed fee | In Progress | Donna Herring | 7500 | 5493 | 5493 | 0 | 7500 | 100% | 8125.76 | -2632.76 |  |  | Sierra North
26-PC-41130 | Harbor View Highway Widening Data Recovery | Time and material | Cost Tracking on Closed Project | Steve Rubio | 290300 | 219699.04 | 219699.04 | 0 | 0 | 0% | 201136.18 | 18562.86 |  |  | Coastal Bend
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | Fixed fee | In Progress | Jared Choi | 41400 | 27278.33 | 19877.52 | 7400.81 | 41400 | 100% | 30232.83 | -2954.5 |  |  | Coastal Bend
26-PC-41661 | Ember Valley Levee Repair Data Recovery | Fixed fee | In Progress | Diane Daniels | 4800 | 4028.16 | 4028.16 | 0 | 4800 | 100% | 4393.64 | -365.48 |  |  | Coastal Bend
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | Fixed fee | In Progress | Kyle Maynard | 347000 | 256363.6 | 256363.6 | 0 | 252477.2 | 72.8% | 186528.08 | 69835.52 |  |  | Maritime
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Time and material | Final Reporting/Review | Sylvia Callahan | 107600 | 77827.43 | 68885.46 | 8941.97 | 107600 | 100% | 89098.75 | -11271.32 |  |  | Geospatial
26-PC-43199 | Thistle Down Airport Apron Phase I Survey | Fixed fee | Cost Tracking on Closed Project | Mathew Shea | 42200 | 26341.24 | 26341.24 | 0 | 38937.94 | 92.3% | 24305.56 | 2035.68 |  |  | Meridian Central
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | Fixed fee | In Progress | Mathew Shea | 41200 | 27426.84 | 27426.84 | 0 | 30945.32 | 75.1% | 20599.46 | 6827.38 |  |  | Meridian Central
26-PC-43364 | Goldfinch Class III Survey | Fixed fee | Transferred Entity | Raymond Hensley | 24900 | 16624.07 | 15142.4 | 1481.67 | 24900 | 100% | 22825.96 | -6201.89 |  |  | Meridian Central
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | Fixed fee | In Progress | Clinton Solis | 136900 | 105043.37 | 105043.37 | 0 | 131026.99 | 95.7% | 100533.21 | 4510.16 |  |  | Meridian Central
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Time and material | Transferred Entity | Justin Mejia | 220800 | 146699.52 | 146699.52 | 0 | 218771.2507 | 99.08% | 136849.0807 | 9850.4393 |  |  | NH Gulf (USD)
25-PC-44140 | Stone Mill Archaeological Testing | Fixed fee | In Progress | Tonya Spence | 149900 | 100298.0907 | 100298.0907 | 0 | 149510.2587 | 99.74% | 100035.4533 | 262.6373 |  |  | NH Gulf

## Projects >70%
Summary:
Removed projects with ETC>1% budget remaining
Removed $0 Contract Value projects
Removed previously identified ETC in final/reportingstatus
Removed projects in final reporting with >10% budget remaining
Total: 273
[6 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Total Budget | Total Budget Adjustment | Total Costs |  | Recognized %
[6 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Inception To Date | REV REC % | Budget Spent %
[6 empty] | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026
| Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Actual | Summary
23-PC-30869 | Lone Pine Housing Development - Paleontological Monitoring | In Progress | Time and material | Bluegrass | Kiara Gillespie | 49800 | 33864 | 33864 | 34501.44 | 34501.44 | 0 | 28656.36 | 5845.08 | 68% | 83.06%
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 86200 | 58616 | 58616 | 58650.48 | 58650.48 | 0 | 61318.15 | -2667.67 | 68% | 104.6%
23-PC-31003 | Windmill Flat Environmental Review Support | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 19300 | 15445.79 | 15445.79 | 10568.68 | 10568.68 | 0 | 8458.51 | 2110.17 | 80% | 80.03%
23-PC-31042 | Stone Mill Historic Resources Evaluation | In Progress | Time and material | Cascade | Donald Lutz | 299700 | 203796 | 203796 | 202896.9 | 202896.9 | 0 | 147919.88 | 54977.02 | 68% | 72.9%
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | In Progress | Time and material | Cascade | Donald Lutz | 255700 | 173876 | 173876 | 168225.03 | 168225.03 | 0 | 202903.45 | -34678.42 | 68% | 120.6%
23-PC-31405 | Phase II: Maple Fork Mixed-Use Development Built Environment Survey | In Progress | Fixed fee | Cascade | Jeff Spence | 108000 | 76528.8 | 76528.8 | 82404 | 82404 | 0 | 58391.35 | 24012.65 | 70.9% | 70.86%
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | In Progress | Fixed fee | Cascade | Gene Nixon | 34800 | 34800 | 34800 | 28779.6 | 28779.6 | 0 | 31540.76 | -2761.16 | 100% | 109.6%
23-PC-31812 | On-Call: Granite Pass Mine Expansion Phase II Testing | In Progress | Fixed fee | Cascade | Jeff Spence | 460600 | 348674.2 | 348674.2 | 390957.28 | 390957.28 | 0 | 295973.9 | 94983.38 | 75.7% | 75.7%
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Jeff Spence | 175300 | 175300 | 175300 | 93481.01 | 71376.84 | 22104.17 | 112759.17 | -19278.16 | 100% | 120.6%
23-PC-32329 | Rushgrass Draw Historic Resources Evaluation | In Progress | Fixed fee | Chesapeake | Sandy Kerr | 149100 | 132892.83 | 132892.83 | 111109.32 | 111109.32 | 0 | 99032.78 | 12076.54 | 89.1% | 89.13%
23-PC-32635 | Rushgrass Draw Curation | Cost Tracking on Closed Project | Time and material | Chesapeake | Jason Oconnor | 36800 | 25024 | 25024 | 24644.96 | 24644.96 | 0 | 27323.95 | -2678.99 | 68% | 110.9%
23-PC-33070 | Meadowlark Curation | In Progress | Fixed fee | Front Range | Reginald Vargas | 55100 | 46377.67 | 46377.67 | 34299.75 | 34299.75 | 0 | 28871.53 | 5428.22 | 84.2% | 84.17%
23-PC-33151 | Sandpiper Class III Survey | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 637100 | 540961.61 | 540961.61 | 497638.81 | 497638.81 | 0 | 422546.87 | 75091.94 | 84.9% | 84.91%
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 21600 | 21600 | 21600 | 15245.28 | 15245.28 | 0 | 16551.79 | -1306.51 | 100% | 108.6%
23-PC-33879 | Phase III: Twin Buttes Canal Lining GIS Mapping | In Progress | Time and material | Great Lakes | Jeff Pugh | 300600 | 204408 | 204408 | 219257.64 | 219257.64 | 0 | 176674.59 | 42583.05 | 68% | 80.58%
23-PC-34353 | Cedar Hollow Levee Repair Phase II Testing | In Progress | Time and material | Great Lakes | Kathleen Galvan | 373100 | 253708 | 253708 | 247626.47 | 247626.47 | 0 | 184659.6 | 62966.87 | 68% | 74.57%
23-PC-34403 | Plover Cove Built Environment Survey | In Progress | Time and material | Great Lakes | Kathleen Galvan | 46200 | 31416 | 31416 | 30187.08 | 30187.08 | 0 | 23628.2 | 6558.88 | 68% | 78.27%
23-PC-34440 | Dove Canyon Bridge Replacement - Phase II Testing | In Progress | Fixed fee | Great Lakes | Angelica Cervantes | 477000 | 347303.7 | 347303.7 | 333756.9 | 333756.9 | 0 | 243019.93 | 90736.97 | 72.8% | 72.81%
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Final Reporting/Review | Time and material | Great Lakes | Geoffrey Fernandez | 70000 | 47600 | 47600 | 50246 | 50246 | 0 | 45814.41 | 4431.59 | 68% | 91.18%
23-PC-34789 | On-Call: Sea Oat Cell Tower Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Sean Jennings | 46100 | 32472.84 | 32472.84 | 31721.41 | 31721.41 | 0 | 22343.25 | 9378.16 | 70.4% | 70.44%
23-PC-35225 | Tansy Flat Rail Siding - Archaeological Testing | In Progress | Fixed fee | Gulf Coast East | Wyatt Erickson | 407900 | 303355.23 | 303355.23 | 321139.67 | 321139.67 | 0 | 238828.33 | 82311.34 | 74.4% | 74.37%
23-PC-35486 | On-Call: Saltgrass Airport Apron Maritime Remote Sensing Survey | In Progress | Time and material | High Desert | Jody Wang | 116200 | 79016 | 79016 | 87219.72 | 87219.72 | 0 | 78190.34 | 9029.38 | 68% | 89.65%
23-PC-35533 | Task Order 19: Granite Pass Reservoir Section 106 Consultation | In Progress | Fixed fee | High Desert | Eileen Poole | 11400 | 8681.1 | 8681.1 | 8206.86 | 8206.86 | 0 | 6249.46 | 1957.4 | 76.2% | 76.15%
23-PC-35682 | Lantern Bay Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 290400 | 277361.04 | 277361.04 | 252938.4 | 252938.4 | 0 | 241578.4 | 11360 | 95.5% | 95.51%
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 114600 | 104870.46 | 104870.46 | 77893.62 | 77893.62 | 0 | 71277.07 | 6616.55 | 91.5% | 91.51%
23-PC-36422 | Hawk Point Phase I Survey | In Progress | Time and material | Island | Joan Mathis | 50700 | 34476 | 34476 | 36579.06 | 32790.93 | 3788.13 | 37409.59 | -830.53 | 68% | 102.3%
23-PC-36687 | On-Call: Pine Hollow Transmission Line Environmental Review Support | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 201000 | 170226.9 | 170226.9 | 151513.8 | 151513.8 | 0 | 128322.24 | 23191.56 | 84.7% | 84.69%
23-PC-36734 | Raven Rock Curation | In Progress | Fixed fee | Lakeshore | Terrence Gillespie | 38600 | 36284 | 36284 | 27753.4 | 27753.4 | 0 | 26089.14 | 1664.26 | 94% | 94%
23-PC-37568 | On-Call: Eagle Bend Housing Development Data Recovery | In Progress | Fixed fee | Piedmont - Inactive | Maria Parrish | 44500 | 31902.05 | 31902.05 | 35070.45 | 35070.45 | 0 | 25141.75 | 9928.7 | 71.7% | 71.69%
23-PC-38231 | On-Call: Copper Flats Rail Siding Curation | In Progress | Time and material | Prairie | Sherry Lloyd | 128200 | 87176 | 87176 | 90073.32 | 90073.32 | 0 | 73724.08 | 16349.24 | 68% | 81.85%
23-PC-38246 | Maple Fork Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Prairie | Sherry Lloyd | 79800 | 57918.84 | 57918.84 | 53434.08 | 53434.08 | 0 | 38783.48 | 14650.6 | 72.6% | 72.58%
23-PC-38498 | Tansy Flat Wind Farm Built Environment Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 67700 | 56556.58 | 56556.58 | 44688.77 | 44688.77 | 0 | 37332.05 | 7356.72 | 83.5% | 83.54%
23-PC-38759 | Saltgrass Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Red Rock | Tina Aguirre | 52400 | 35632 | 35632 | 36847.68 | 36847.68 | 0 | 40372.44 | -3524.76 | 68% | 109.6%
23-PC-38849 | Phase III: Copper Flats Levee Repair Curation | In Progress | Fixed fee | Red Rock | Tina Aguirre | 109400 | 86962.06 | 86962.06 | 83089.3 | 83089.3 | 0 | 66048.24 | 17041.06 | 79.5% | 79.49%
23-PC-39135 | Phase I: Oak Terrace Reservoir Archaeological Testing | In Progress | Fixed fee | Red Rock | Jeanette Chung | 27800 | 20777.72 | 20777.72 | 18214.56 | 18214.56 | 0 | 13614.39 | 4600.17 | 74.7% | 74.74%
23-PC-39323 | Silver Lake Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Tina Aguirre | 550600 | 423136.1 | 423136.1 | 444994.92 | 444994.92 | 0 | 341994.21 | 103000.71 | 76.8% | 76.85%
23-PC-40052 | Oak Terrace Transmission Line Cultural Resources Monitoring | In Progress | Time and material | Red Rock | Javier Newman | 119500 | 103480.5 | 103480.5 | 80196.45 | 80196.45 | 0 | 70430.41 | 9766.04 | 86.6% | 87.82%
23-PC-40402 | Pebble Beach Road Architectural History Survey | In Progress | Fixed fee | Sierra North | Louis Huff | 411600 | 333190.2 | 333190.2 | 302937.6 | 302937.6 | 0 | 245232.54 | 57705.06 | 80.9% | 80.95%
23-PC-40469 | On-Call: Badger Hollow School Campus Built Environment Survey | In Progress | Fixed fee | Sierra South | Benjamin Mathis | 53900 | 38516.94 | 38516.94 | 40910.1 | 40910.1 | 0 | 29233.55 | 11676.55 | 71.5% | 71.46%
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Lab/Curation | Fixed fee | Sierra | Louis Huff | 76500 | 76500 | 76500 | 58746.94 | 55119.6 | 3627.34 | 63236.56 | -4489.62 | 100% | 107.6%
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | In Progress | Time and material | Coastal Bend | Steve Rubio | 56300 | 38284 | 38284 | 42714.81 | 42714.81 | 0 | 47948.89 | -5234.08 | 68% | 112.2%
23-PC-41207 | Goldfinch Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 33100 | 24874.65 | 24874.65 | 29128 | 29128 | 0 | 21890.46 | 7237.54 | 75.1% | 75.15%
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 349600 | 349600 | 349600 | 221087.04 | 221087.04 | 0 | 229204.35 | -8117.31 | 100% | 103.7%
23-PC-41424 | Harbor View Park Improvements - Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 132000 | 92584.8 | 92584.8 | 108108 | 108108 | 0 | 75830.35 | 32277.65 | 70.1% | 70.14%
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Lab/Curation | Fixed fee | Coastal Bend | Alexis Nixon | 755000 | 705170 | 705170 | 444695 | 444695 | 0 | 415325.46 | 29369.54 | 93.4% | 93.4%
23-PC-41613 | Tamarack School Campus Archaeological Testing | In Progress | Fixed fee | Coastal Bend | Steve Rubio | 151900 | 128659.3 | 128659.3 | 105099.61 | 105099.61 | 0 | 89014.21 | 16085.4 | 84.7% | 84.7%
23-PC-41897 | Elk Meadow Fiber Route Archaeological Testing | In Progress | Time and material | Built Environment | Jesse Maynard | 18800 | 12784 | 12784 | 12705.04 | 12705.04 | 0 | 12736.47 | -31.43 | 68% | 100.2%
23-PC-42771 | Redbud Housing Development GIS Mapping | In Progress | Fixed fee | Maritime | Kyle Maynard | 25200 | 19124.28 | 19124.28 | 18799.2 | 18799.2 | 0 | 14265.92 | 4533.28 | 75.9% | 75.89%
23-PC-42981 | Hawk Point Architectural History Survey | In Progress | Fixed fee | Maritime | Kyle Maynard | 175800 | 133203.66 | 133203.66 | 129494.28 | 129494.28 | 0 | 98123.54 | 31370.74 | 75.8% | 75.77%
23-PC-43008 | Sea Oat Mixed-Use Development - Cultural Resources Monitoring | In Progress | Time and material | Maritime | Rita Ayala | 139700 | 94996 | 94996 | 93543.12 | 93543.12 | 0 | 67047.93 | 26495.19 | 68% | 71.68%
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | In Progress | Fixed fee | Geospatial | Priscilla Pennington | 73300 | 66563.73 | 66563.73 | 53362.4 | 53362.4 | 0 | 48458.95 | 4903.45 | 90.8% | 90.81%
23-PC-43692 | Riverbend Levee Repair - Cultural Resources Monitoring | In Progress | Fixed fee | Meridian Southwest | Lynn Tran | 112600 | 91374.9 | 91374.9 | 77637.7 | 77637.7 | 0 | 63002.79 | 14634.91 | 81.1% | 81.15%
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 93300 | 93300 | 90265.16 | 59544.06 | 59544.06 | 0 | 93708.96 | -34164.9 | 100% | 157.4%
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 60600 | 60600 | 60600 | 45577.26 | 45577.26 | 0 | 50596.88 | -5019.62 | 100% | 111%
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Cost Tracking on Closed Project | Time and material | Cascade | Preston Duarte | 94000 | 63920 | 63920 | 65640.2 | 65640.2 | 0 | 73270.02 | -7629.82 | 68% | 111.6%
24-PC-31434 | Pebble Beach Road Cultural Resources Assessment | In Progress | Fixed fee | Cascade | Jean Cooke | 18200 | 13335.14 | 13335.14 | 12417.86 | 12417.86 | 0 | 9098.08 | 3319.78 | 73.3% | 73.27%
24-PC-31453 | Timber Gap Cell Tower Paleontological Monitoring | In Progress | Time and material | Cascade | Gene Nixon | 18300 | 12444 | 12444 | 11931.6 | 11931.6 | 0 | 9112.04 | 2819.56 | 68% | 76.37%
24-PC-31503 | North Fork Wind Farm Curation | Lab/Curation | Time and material | Cascade | Preston Duarte | 129900 | 88332 | 88332 | 87825.39 | 87825.39 | 0 | 98773.26 | -10947.87 | 68% | 112.5%
24-PC-31663 | Fern Valley Section 106 Consultation | In Progress | Fixed fee | Cascade | Jean Cooke | 52600 | 43847.36 | 43847.36 | 37714.2 | 37714.2 | 0 | 31436.99 | 6277.21 | 83.4% | 83.36%
24-PC-31857 | Falcon Mesa Airport Apron Environmental Review Support | In Progress | Time and material | Cascade | Gene Nixon | 15200 | 10871.15 | 10871.15 | 10676.48 | 10676.48 | 0 | 7665.21 | 3011.27 | 71.5% | 71.8%
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 51800 | 51800 | 50026.67 | 36731.38 | 36731.38 | 0 | 59530.75 | -22799.37 | 100% | 162.1%
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Chesapeake | Alexandria Wilkinson | 84000 | 84000 | 83888.35 | 70198.8 | 70198.8 | 0 | 85361.67 | -15162.87 | 100% | 121.6%
24-PC-32688 | Phase II: Tamarack Reservoir Paleontological Monitoring | In Progress | Fixed fee | Chesapeake | Ian Maddox | 51700 | 44730.84 | 44730.84 | 45206.48 | 45206.48 | 0 | 39111.36 | 6095.12 | 86.5% | 86.52%
24-PC-33448 | Ember Valley Solar Architectural History Survey | In Progress | Fixed fee | Front Range | Devon Pitts | 681000 | 563868 | 560235.94 | 419972.7 | 419972.7 | 0 | 347755.54 | 72217.16 | 82.8% | 82.8%
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Karl Valenzuela | 64500 | 59346.45 | 57224.04 | 49568.25 | 49568.25 | 0 | 45606.09 | 3962.16 | 92% | 92.01%
24-PC-33985 | Thistle Down Substation Curation | In Progress | Time and material | Great Lakes | Angelica Cervantes | 78300 | 53244 | 53244 | 57863.7 | 57863.7 | 0 | 50630.38 | 7233.32 | 68% | 87.5%
24-PC-34330 | On-Call: Harbor View Highway Widening Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Karl Valenzuela | 38700 | 26316 | 26316 | 26644.95 | 26644.95 | 0 | 19241.81 | 7403.14 | 68% | 72.22%
24-PC-34663 | Redbud Airport Apron - GIS Mapping | In Progress | Time and material | Great Lakes | Kathleen Galvan | 505100 | 343468 | 343468 | 342760.86 | 342760.86 | 0 | 286062.16 | 56698.7 | 68% | 83.46%
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | In Progress | Time and material | Gulf Coast | Courtney Daugherty | 176500 | 120020 | 120020 | 121414.35 | 121414.35 | 0 | 122080.25 | -665.9 | 68% | 100.6%
24-PC-34975 | Foxglove Fiber Route GIS Mapping | In Progress | Fixed fee | Gulf Coast West | Bernard Erickson | 205900 | 175159.13 | 175159.13 | 181192 | 181192 | 0 | 154132.44 | 27059.56 | 85.1% | 85.07%
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | In Progress | Time and material | High Desert | Kathy Hurley | 301200 | 204816 | 204816 | 217496.52 | 217496.52 | 0 | 196030.1 | 21466.42 | 68% | 90.13%
24-PC-35586 | Quail Run Harbor Dredging - Data Recovery | In Progress | Fixed fee | High Desert | Eileen Poole | 119200 | 90150.96 | 90150.96 | 88243.76 | 88243.76 | 0 | 66735.14 | 21508.62 | 75.6% | 75.63%
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | In Progress | Time and material | High Desert | Kathy Hurley | 69900 | 69900 | 66597.48 | 49013.31 | 40696.6 | 8316.71 | 53862.59 | -4849.28 | 100% | 109.9%
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | In Progress | Time and material | High Desert | Kathy Hurley | 225100 | 200102.05 | 200102.05 | 153743.3 | 153743.3 | 0 | 140872.8 | 12870.5 | 88.9% | 91.63%
24-PC-36099 | Copper Flats Rail Siding - Built Environment Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 12900 | 10859.22 | 10859.22 | 9094.5 | 9094.5 | 0 | 7655.43 | 1439.07 | 84.2% | 84.18%
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Cost Tracking on Closed Project | Fixed fee | High Desert | Kathy Hurley | 58300 | 58300 | 58300 | 39072.66 | 39072.66 | 0 | 45518.79 | -6446.13 | 100% | 116.5%
24-PC-36161 | Phase II: Saltgrass Mine Expansion Data Recovery | In Progress | Time and material | High Desert | Kathy Hurley | 5700 | 3876 | 3876 | 4244.79 | 4244.79 | 0 | 3255.04 | 989.75 | 68% | 76.68%
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Island | Rodney Mcguire | 56300 | 52077.5 | 52077.5 | 37721 | 37721 | 0 | 34891.33 | 2829.67 | 92.5% | 92.5%
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | In Progress | Fixed fee | Hill Country | Glen Delacruz | 141000 | 141000 | 141000 | 113970.3 | 113970.3 | 0 | 138124.06 | -24153.76 | 100% | 121.2%
24-PC-37125 | Task Order 3: Elk Meadow Cell Tower Phase II Testing | In Progress | Fixed fee | Hill Country | Gail Meza | 1259200 | 928785.92 | 928785.92 | 853989.44 | 853989.44 | 0 | 629919.62 | 224069.82 | 73.8% | 73.76%
24-PC-37235 | Coyote Springs Bridge Replacement - Phase II Testing | In Progress | Time and material | Hill Country | Samuel Wilkerson | 67000 | 51564 | 51564 | 40709.2 | 40709.2 | 0 | 34240.46 | 6468.74 | 77% | 84.11%
24-PC-37336 | Kestrel Butte Reservoir - Historic Resources Evaluation | In Progress | Fixed fee | Hill Country | Theresa Fernandez | 298500 | 213069.3 | 213069.3 | 243904.35 | 243904.35 | 0 | 174092.01 | 69812.34 | 71.4% | 71.38%
24-PC-37442 | Cedar Hollow Cultural Resources Monitoring | In Progress | Time and material | PIEDMONT - INACTIVE | Jody Chung | 309400 | 210392 | 210392 | 184093 | 184093 | 0 | 149432.06 | 34660.94 | 68% | 81.17%
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Prairie | Sherry Lloyd | 132200 | 121663.66 | 121663.66 | 95580.6 | 95580.6 | 0 | 87961.2 | 7619.4 | 92% | 92.03%
24-PC-38486 | Kestrel Butte Phase I Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 153600 | 153600 | 153600 | 105043.81 | 77500.98 | 27542.83 | 119866.24 | -14822.43 | 100% | 114.1%
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Red Rock | Marisa Odom | 168200 | 168200 | 168200 | 130489.56 | 130489.56 | 0 | 132230.67 | -1741.11 | 100% | 101.3%
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 100200 | 100200 | 93737.19 | 72685.08 | 72685.08 | 0 | 103671 | -30985.92 | 100% | 142.6%
24-PC-39206 | Task Order 19: Plover Cove Water Main GIS Mapping | In Progress | Time and material | Red Rock | Lydia Cisneros | 126600 | 86088 | 86088 | 82581.18 | 82581.18 | 0 | 59856.61 | 22724.57 | 68% | 72.48%
24-PC-39213 | Task Order 17: Sage Flat School Campus Maritime Remote Sensing Survey | In Progress | Fixed fee | Red Rock | Javier Newman | 597800 | 458990.84 | 458990.84 | 435557.08 | 435557.08 | 0 | 334422.57 | 101134.51 | 76.8% | 76.78%
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Red Rock | Shelia Horne | 11000 | 11000 | 11000 | 7227 | 7227 | 0 | 7427.79 | -200.79 | 100% | 102.8%
24-PC-39511 | Juniper Wash Pipeline - Archaeological Testing | In Progress | Time and material | Red Rock | Tina Aguirre | 33000 | 29186 | 29186 | 23227.58 | 20462.4 | 2765.18 | 29633.53 | -6405.95 | 88.4% | 127.6%
24-PC-39533 | Elk Meadow Architectural History Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 67000 | 63536.1 | 63536.1 | 52641.9 | 52641.9 | 0 | 49919.2 | 2722.7 | 94.8% | 94.83%
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | In Progress | Fixed fee | Red Rock | Bruce Suarez | 17800 | 17800 | 17800 | 14308.95 | 10538.95 | 3770 | 14659.16 | -350.21 | 100% | 102.5%
24-PC-39923 | Fern Valley Fiber Route - Data Recovery | In Progress | Time and material | Red Rock | Lydia Cisneros | 414900 | 339174.65 | 331243.28 | 270722.25 | 270722.25 | 0 | 215589.53 | 55132.72 | 81.7% | 79.63%
24-PC-40067 | Saltgrass Fiber Route Class III Survey | In Progress | Time and material | Red Rock | Marisa Odom | 218100 | 148308 | 148308 | 163684.05 | 163684.05 | 0 | 137568.33 | 26115.72 | 68% | 84.05%
24-PC-40102 | Redbud Class III Survey | Final Reporting/Review | Fixed fee | Sierra | Benjamin Mathis | 453900 | 453900 | 453900 | 322187.01 | 278794.4 | 43392.61 | 359994.61 | -37807.6 | 100% | 111.7%
24-PC-40634 | Phase I: Windmill Flat Solar Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Angelica Poole | 460500 | 326540.55 | 326540.55 | 381017.7 | 381017.7 | 0 | 270177.47 | 110840.23 | 70.9% | 70.91%
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Sierra North | Louis Huff | 50300 | 46200.55 | 46200.55 | 35350.84 | 35350.84 | 0 | 32471.24 | 2879.6 | 91.8% | 91.85%
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Sierra North | Donna Herring | 22100 | 22100 | 22100 | 17918.68 | 17918.68 | 0 | 33602.1 | -15683.42 | 100% | 187.5%
24-PC-40782 | Saltgrass Battery Storage - Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Alexis Nixon | 48400 | 48400 | 47376.63 | 37137.32 | 37137.32 | 0 | 47362.38 | -10225.06 | 100% | 127.5%
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 31800 | 31800 | 31800 | 20975.28 | 20975.28 | 0 | 22323.11 | -1347.83 | 100% | 106.4%
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Lab/Curation | Fixed fee | Coastal Bend | Diane Daniels | 579300 | 579300 | 579300 | 392475.75 | 392475.75 | 0 | 413750.74 | -21274.99 | 100% | 105.4%
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 8800 | 8800 | 8800 | 6914.16 | 6914.16 | 0 | 7269.9 | -355.74 | 100% | 105.2%
24-PC-41023 | Phase I: Bramble Creek Levee Repair Phase I Survey | In Progress | Time and material | Coastal Bend | Alexis Nixon | 60600 | 41208 | 41208 | 39983.88 | 39983.88 | 0 | 31771.04 | 8212.84 | 68% | 79.46%
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Alexis Nixon | 18000 | 18000 | 15244.1 | 12312 | 12312 | 0 | 22722.22 | -10410.22 | 100% | 184.5%
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 194900 | 187591.25 | 187591.25 | 131089.74 | 131089.74 | 0 | 126178.41 | 4911.33 | 96.3% | 96.25%
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 263500 | 179180 | 179180 | 173567.45 | 173567.45 | 0 | 177335 | -3767.55 | 68% | 102.2%
24-PC-43044 | Plover Cove Airport Apron Historic Resources Evaluation | In Progress | Fixed fee | Geospatial | Sylvia Callahan | 639100 | 451268.51 | 451268.51 | 498050.63 | 498050.63 | 0 | 351673.07 | 146377.56 | 70.6% | 70.61%
24-PC-43157 | Thistle Down Solar - Maritime Remote Sensing Survey | In Progress | Time and material | Geospatial | Sylvia Callahan | 19700 | 13396 | 13396 | 14170.21 | 14170.21 | 0 | 18919.28 | -4749.07 | 68% | 133.5%
24-PC-43715 | Tamarack Fiber Route - Cultural Resources Monitoring | In Progress | Time and material | Meridian Southwest | Lynn Tran | 1003600 | 682448 | 682448 | 771166.24 | 771166.24 | 0 | 614867.84 | 156298.4 | 68% | 79.73%
24-PC-43877 | Wren Hollow Canal Lining Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 213100 | 152792.6987 | 152792.6987 | 187528 | 187528 | 0 | 134454.77 | 53073.23 | 71.7% | 71.7%
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 264500 | 264500 | 256769.1787 | 194222.35 | 194222.35 | 0 | 246339.6193 | -52117.2693 | 100% | 126.8%
24-PC-44158 | Saltgrass Environmental Review Support | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 23200 | 23200 | 23148.0107 | 15583.44 | 15583.44 | 0 | 16044.04 | -460.6 | 100% | 103%
25-PC-30345 | Wildrye Phase II Testing | In Progress | Fixed fee | Big Sky | Brendan Melton | 160400 | 130998.68 | 130998.68 | 92631 | 92631 | 0 | 75656.14 | 16974.86 | 81.7% | 81.67%
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway | 19700 | 19700 | 17105.05 | 13027.61 | 13027.61 | 0 | 13683.52 | -655.91 | 100% | 105%
25-PC-30772 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 63300 | 63300 | 63300 | 43065.84 | 35870.85 | 7194.99 | 56416.91 | -13351.07 | 100% | 131%
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 131000 | 131000 | 122522.64 | 85464.4 | 85464.4 | 0 | 90183.9 | -4719.5 | 100% | 105.5%
25-PC-31109 | Riverbend GIS Mapping | In Progress | Time and material | Cascade | Cassidy Gay | 174700 | 174700 | 154905.3 | 109484.49 | 109484.49 | 0 | 162892.26 | -53407.77 | 100% | 148.8%
25-PC-31114 | Granite Pass Built Environment Survey | In Progress | Time and material | Cascade | Jean Cooke | 229400 | 179308.8 | 179308.8 | 157964.84 | 157964.84 | 0 | 127618.8 | 30346.04 | 78.2% | 80.79%
25-PC-31180 | Blue Heron Environmental Review Support | In Progress | Fixed fee | Cascade | Preston Duarte | 80000 | 80000 | 69747.43 | 60701.89 | 45712.3 | 14989.59 | 64096.36 | -3394.47 | 100% | 105.6%
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 23500 | 23500 | 23419.06 | 17263.1 | 17263.1 | 0 | 22123.1 | -4860 | 100% | 128.2%
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 52000 | 52000 | 49983.77 | 38781.6 | 38781.6 | 0 | 51500.29 | -12718.69 | 100% | 132.8%
25-PC-31555 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 69300 | 66417.12 | 60877.3 | 53097.66 | 53097.66 | 0 | 50888.1 | 2209.56 | 95.8% | 95.84%
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 16800 | 16800 | 16756.9 | 11810.4 | 11810.4 | 0 | 15531.6 | -3721.2 | 100% | 131.5%
25-PC-31616 | On-Call: Foxglove Fiber Route GIS Mapping | Final Reporting/Review | Time and material | Cascade | Jeff Spence | 30300 | 30300 | 30300 | 22049.31 | 22049.31 | 0 | 34568.28 | -12518.97 | 100% | 156.8%
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | In Progress | Fixed fee | Cascade | Preston Duarte | 216800 | 216800 | 202009.7 | 171337.04 | 171337.04 | 0 | 185663.62 | -14326.58 | 100% | 108.4%
25-PC-31895 | Task Order 27: Hawk Point Pipeline Data Recovery | Cost Tracking on Closed Project | Time and material | Cascade | Donald Lutz | 40900 | 13987.8 | 13987.8 | 28728.16 | 28728.16 | 0 | 33002.57 | -4274.41 | 34.2% | 114.9%
25-PC-31961 | Sandpiper Canal Lining - Phase I Survey | Final Reporting/Review | Time and material | Chesapeake | Jason Oconnor | 35200 | 35200 | 35200 | 24481.6 | 24481.6 | 0 | 39794.35 | -15312.75 | 100% | 162.5%
25-PC-32024 | Pine Hollow Historic Resources Evaluation | In Progress | Time and material | Chesapeake | Ian Maddox | 79500 | 57058 | 51094.33 | 57637.5 | 57637.5 | 0 | 41962.52 | 15674.98 | 71.8% | 72.8%
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | In Progress | Time and material | Chesapeake | Ian Maddox | 201300 | 196916.6 | 185059.24 | 150874.35 | 150874.35 | 0 | 161800.48 | -10926.13 | 97.8% | 107.2%
25-PC-32447 | Pebble Beach Road Archaeological Testing | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 88200 | 88200 | 88200 | 61772.24 | 55626.38 | 6145.86 | 76703.23 | -14930.99 | 100% | 124.2%
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | In Progress | Time and material | Chesapeake | Sandy Kerr | 118800 | 118800 | 111029.5 | 85013.28 | 85013.28 | 0 | 117591.53 | -32578.25 | 100% | 138.3%
25-PC-32776 | Plover Cove Mixed-Use Development Cultural Resources Monitoring | In Progress | Time and material | Front Range | Jeremy Tran | 86500 | 83279.75 | 75767.65 | 62245.4 | 62245.4 | 0 | 49276.48 | 12968.92 | 96.3% | 79.16%
25-PC-32795 | North Fork Water Main Architectural History Survey | In Progress | Time and material | Front Range | Reginald Vargas | 16900 | 16900 | 16900 | 11650.86 | 11650.86 | 0 | 12884.7 | -1233.84 | 100% | 110.6%
25-PC-32838 | Aspen Ridge Canal Lining - Curation | In Progress | Fixed fee | Front Range | Jeremy Tran | 42600 | 39204.78 | 39204.78 | 33543.24 | 33543.24 | 0 | 30870.45 | 2672.79 | 92% | 92.03%
25-PC-32861 | Yarrow Point Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 59200 | 59200 | 54224.79 | 41555.52 | 31694.67 | 9860.85 | 49895.36 | -8339.84 | 100% | 120.1%
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 59600 | 59600 | 57228.13 | 51399.04 | 51399.04 | 0 | 74823.59 | -23424.55 | 100% | 145.6%
25-PC-32911 | Twin Buttes Wind Farm - Cultural Resources Monitoring | Lab/Curation | Time and material | Front Range | Jeremy Tran | 13300 | 13300 | 13300 | 8727.43 | 6386.48 | 2340.95 | 16463.41 | -7735.98 | 100% | 188.6%
25-PC-33065 | Wren Hollow GIS Mapping | In Progress | Fixed fee | Front Range | Dean Velazquez | 50400 | 45596.88 | 45596.88 | 40748.4 | 40748.4 | 0 | 36866.22 | 3882.18 | 90.5% | 90.47%
25-PC-33088 | On-Call: Silver Lake Fiber Route Architectural History Survey | In Progress | Fixed fee | Front Range | Reginald Vargas | 767800 | 603874.7 | 603874.7 | 553046.34 | 553046.34 | 0 | 434972.87 | 118073.47 | 78.6% | 78.65%
25-PC-33105 | Redbud Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 3500 | 3500 | 0 | 2324 | 2324 | 0 | 9006.2 | -6682.2 | 100% | 387.5%
25-PC-33183 | Saltgrass Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 104500 | 101009.7 | 95400.33 | 79399.1 | 79399.1 | 0 | 76745.43 | 2653.67 | 96.7% | 96.66%
25-PC-33473 | Dove Canyon Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Front Range | Devon Pitts | 41600 | 32406.4 | 32210.19 | 29136.64 | 29136.64 | 0 | 22697.51 | 6439.13 | 77.9% | 77.9%
25-PC-33744 | Blue Heron Canal Lining - Curation | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 87100 | 64332.06 | 64332.06 | 60133.84 | 60133.84 | 0 | 44412.55 | 15721.29 | 73.9% | 73.86%
25-PC-33750 | Kestrel Butte Archaeological Testing | Transferred Entity | Fixed fee | Great Lakes | Kathleen Galvan | 69600 | 69600 | 64460.42 | 51302.16 | 51302.16 | 0 | 60286.74 | -8984.58 | 100% | 117.5%
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Final Reporting/Review | Fixed fee | Great Lakes | Geoffrey Fernandez | 15200 | 15200 | 15200 | 11021.49 | 9579.99 | 1441.5 | 11383.28 | -361.79 | 100% | 103.3%
25-PC-33922 | Slate Ridge Data Recovery | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 22100 | 22100 | 22100 | 16113.11 | 16113.11 | 0 | 33890.09 | -17776.98 | 100% | 210.3%
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Geoffrey Fernandez | 53000 | 53000 | 53000 | 36718.4 | 36718.4 | 0 | 42629.29 | -5910.89 | 100% | 116.1%
25-PC-34451 | North Fork Curation | In Progress | Time and material | Great Lakes | Robin Mercado | 46400 | 46400 | 46400 | 32526.4 | 32526.4 | 0 | 41685.4 | -9159 | 100% | 128.2%
25-PC-34652 | Coyote Springs Section 106 Consultation | In Progress | Fixed fee | Great Lakes | Gina Beltran | 210700 | 176145.2 | 157854.18 | 180928.09 | 180928.09 | 0 | 151256.79 | 29671.3 | 83.6% | 83.6%
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | In Progress | Time and material | Great Lakes | Gina Beltran | 82200 | 82200 | 65071.92 | 51638.04 | 51638.04 | 0 | 83204.3 | -31566.26 | 100% | 161.1%
25-PC-34850 | Thistle Down Section 106 Consultation | In Progress | Time and material | Gulf Coast East | Wyatt Erickson | 201300 | 129963.25 | 120850.25 | 117035.82 | 117035.82 | 0 | 94500.26 | 22535.56 | 64.6% | 80.74%
25-PC-35024 | Sandpiper Water Main - Section 106 Consultation | In Progress | Fixed fee | Gulf Coast | Wyatt Erickson | 224400 | 157798.08 | 157798.08 | 165046.2 | 165046.2 | 0 | 116067.93 | 48978.27 | 70.3% | 70.32%
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 71400 | 71400 | 71400 | 48880.44 | 48880.44 | 0 | 56947.79 | -8067.35 | 100% | 116.5%
25-PC-35182 | Rushgrass Draw Battery Storage Architectural History Survey | In Progress | Time and material | Gulf Coast | Wyatt Erickson | 33200 | 33200 | 31529.2 | 23495.64 | 23495.64 | 0 | 28098.77 | -4603.13 | 100% | 119.6%
25-PC-35272 | Thistle Down Cell Tower - Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 49900 | 49900 | 47494.52 | 35982.89 | 35982.89 | 0 | 42125.73 | -6142.84 | 100% | 117.1%
25-PC-35295 | Copper Flats Architectural History Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 80400 | 54672 | 54672 | 54551.4 | 54551.4 | 0 | 39686.68 | 14864.72 | 68% | 72.75%
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 19400 | 19400 | 15409.48 | 13919.5 | 13919.5 | 0 | 36287.62 | -22368.12 | 100% | 260.7%
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Courtney Daugherty | 25100 | 25100 | 24927.65 | 20032.31 | 20032.31 | 0 | 27206.94 | -7174.63 | 100% | 135.8%
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | In Progress | Time and material | High Desert | Kathy Hurley | 136900 | 136900 | 132838.07 | 90994.45 | 78522.66 | 12471.79 | 119032.95 | -28038.5 | 100% | 130.8%
25-PC-35496 | Silver Lake Airport Apron Class III Survey | In Progress | Time and material | High Desert | Kathy Hurley | 15200 | 14910.4 | 14910.4 | 10132.32 | 10132.32 | 0 | 10426.69 | -294.37 | 98.1% | 102.9%
25-PC-35525 | Dove Canyon Rail Siding - Section 106 Consultation | In Progress | Fixed fee | High Desert | Bridget Maddox | 98800 | 77370.28 | 77370.28 | 78447.2 | 78447.2 | 0 | 61430.39 | 17016.81 | 78.3% | 78.31%
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 204800 | 204800 | 187347.98 | 136396.8 | 136396.8 | 0 | 140077.69 | -3680.89 | 100% | 102.7%
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | In Progress | Fixed fee | High Desert | Jody Wang | 83700 | 76761.27 | 76761.27 | 61050.78 | 61050.78 | 0 | 55992.16 | 5058.62 | 91.7% | 91.71%
25-PC-35963 | Quail Run Substation - Section 106 Consultation | In Progress | Time and material | High Desert | Kathy Hurley | 320000 | 290771 | 290771 | 216192 | 216192 | 0 | 202041.59 | 14150.41 | 90.9% | 93.45%
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | In Progress | Time and material | High Desert | Kathy Hurley | 114200 | 114200 | 114200 | 78124.22 | 78124.22 | 0 | 79562.79 | -1438.57 | 100% | 101.8%
25-PC-36251 | Kestrel Butte Environmental Review Support | Lab/Curation | Fixed fee | Island | Joan Mathis | 39200 | 39200 | 39200 | 30446.64 | 30446.64 | 0 | 49335.55 | -18888.91 | 100% | 162%
25-PC-36263 | Creosote Draw Highway Widening - Class III Survey | In Progress | Time and material | Island | Joan Mathis | 28100 | 24522.2 | 24500.73 | 19141.72 | 19141.72 | 0 | 16573.11 | 2568.61 | 87.3% | 86.58%
25-PC-36336 | Sea Oat Canal Lining Data Recovery | In Progress | Fixed fee | Island | Briana Melton | 36400 | 33364.24 | 29544.7 | 25854.92 | 25854.92 | 0 | 23699.14 | 2155.78 | 91.7% | 91.66%
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | In Progress | Fixed fee | Island | Becky Velazquez | 33100 | 33100 | 33100 | 25870.96 | 25870.96 | 0 | 34277.75 | -8406.79 | 100% | 132.5%
25-PC-36507 | Saltgrass Cell Tower Phase II Testing | In Progress | Fixed fee | Island | Joan Mathis | 88300 | 68397.18 | 67497.4 | 54269.18 | 54269.18 | 0 | 42036.07 | 12233.11 | 77.5% | 77.46%
25-PC-36573 | Eagle Bend Rail Siding - Maritime Remote Sensing Survey | In Progress | Fixed fee | Island | Becky Velazquez | 116000 | 85573.2 | 85573.2 | 66050.4 | 66050.4 | 0 | 48723.63 | 17326.77 | 73.8% | 73.77%
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | In Progress | Time and material | Lakeshore | Lucas Benson | 181300 | 181300 | 174825.53 | 117609.31 | 117609.31 | 0 | 164790.18 | -47180.87 | 100% | 140.1%
25-PC-36645 | Falcon Mesa Archaeological Testing | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 25400 | 25400 | 24158.24 | 20302.22 | 20302.22 | 0 | 38922.61 | -18620.39 | 100% | 191.7%
25-PC-36646 | Copper Flats Pipeline Section 106 Consultation | In Progress | Time and material | Lakeshore | Lucas Benson | 137400 | 108023.85 | 108023.85 | 99958.5 | 99958.5 | 0 | 83440.54 | 16517.96 | 78.6% | 83.48%
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Final Reporting/Review | Fixed fee | Lakeshore | Jeanette Riddle | 74000 | 74000 | 66065.35 | 56358.4 | 56358.4 | 0 | 66079.16 | -9720.76 | 100% | 117.3%
25-PC-36799 | Meadowlark Substation Phase I Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 32900 | 32900 | 30883.36 | 26389.09 | 26389.09 | 0 | 33048.52 | -6659.43 | 100% | 125.2%
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 24200 | 24200 | 22550.8 | 16235.78 | 16235.78 | 0 | 26420.57 | -10184.79 | 100% | 162.7%
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | In Progress | Time and material | Hill Country | Glen Delacruz | 75400 | 75400 | 71354.11 | 50299.34 | 50299.34 | 0 | 90901.92 | -40602.58 | 100% | 180.7%
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | In Progress | Fixed fee | Piedmont | Maria Parrish | 59200 | 54913.92 | 54913.92 | 50698.88 | 50698.88 | 0 | 47030.53 | 3668.35 | 92.8% | 92.76%
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Cost Tracking on Closed Project | Time and material | Piedmont | Megan Pineda | 83200 | 22297.6 | 22297.6 | 60186.88 | 60186.88 | 0 | 78242.94 | -18056.06 | 26.8% | 130%
25-PC-37509 | On-Call: Wildrye Bridge Replacement Section 106 Consultation | In Progress | Time and material | Piedmont | Jody Chung | 458200 | 311576 | 311576 | 301449.78 | 301449.78 | 0 | 240796.49 | 60653.29 | 68% | 79.88%
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Lab/Curation | Fixed fee | Piedmont | Jody Chung | 21500 | 21500 | 20397.5 | 15617.6 | 15617.6 | 0 | 19499.41 | -3881.81 | 100% | 124.9%
25-PC-37732 | Hawk Point Housing Development Class III Survey | In Progress | Fixed fee | Piedmont | Megan Pineda | 72900 | 64100.97 | 59413.97 | 45824.94 | 45824.94 | 0 | 40294.47 | 5530.47 | 87.9% | 87.93%
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Final Reporting/Review | Time and material | Piedmont | Maria Parrish | 72200 | 69466.7 | 69466.7 | 44893.96 | 44893.96 | 0 | 57390.52 | -12496.56 | 96.2% | 127.8%
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Megan Pineda | 7900 | 7900 | 7900 | 6020.59 | 6020.59 | 0 | 6629.3 | -608.71 | 100% | 110.1%
25-PC-37975 | Hackberry Bend Battery Storage Environmental Review Support | In Progress | Fixed fee | Prairie | Sherry Lloyd | 148100 | 109890.2 | 107447.04 | 106809.72 | 106809.72 | 0 | 79254.52 | 27555.2 | 74.2% | 74.2%
25-PC-38042 | Oak Terrace School Campus GIS Mapping | In Progress | Fixed fee | Prairie | Sherry Lloyd | 24300 | 20144.7 | 20144.7 | 19082.79 | 19082.79 | 0 | 15820.03 | 3262.76 | 82.9% | 82.9%
25-PC-38180 | Task Order 22: Willow Springs Bridge Replacement Data Recovery | In Progress | Fixed fee | Prairie | Sherry Lloyd | 25300 | 20781.42 | 19246.71 | 16961.12 | 16961.12 | 0 | 13931.44 | 3029.68 | 82.1% | 82.14%
25-PC-38352 | Phase III: Willow Springs Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Prairie | Sherry Lloyd | 136400 | 99080.96 | 99080.96 | 86736.76 | 86736.76 | 0 | 63001.3 | 23735.46 | 72.6% | 72.64%
25-PC-38540 | Ember Valley Park Improvements - Class III Survey | In Progress | Time and material | Red Rock | Jeanette Chung | 496400 | 481730.55 | 460087.32 | 357705.84 | 357705.84 | 0 | 311579.9 | 46125.94 | 97% | 87.11%
25-PC-38563 | Elk Meadow Highway Widening - Architectural History Survey | In Progress | Fixed fee | Red Rock | Lydia Cisneros | 176400 | 154297.08 | 154297.08 | 137697.84 | 137697.84 | 0 | 120438.25 | 17259.59 | 87.5% | 87.47%
25-PC-38701 | Slate Ridge Curation | In Progress | Time and material | Red Rock | Javier Newman | 156400 | 109600.75 | 102197.06 | 98735.32 | 98735.32 | 0 | 71024.19 | 27711.13 | 70.1% | 71.93%
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | In Progress | Fixed fee | Red Rock | Javier Newman | 63900 | 63900 | 60446.65 | 41637.24 | 41637.24 | 0 | 60770.39 | -19133.15 | 100% | 145.9%
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 10400 | 10400 | 9781.64 | 5866.64 | 5866.64 | 0 | 18017.52 | -12150.88 | 100% | 307.1%
25-PC-38879 | Kestrel Butte Built Environment Survey | In Progress | Fixed fee | Red Rock | Marisa Odom | 119700 | 88482.24 | 88482.24 | 70323.75 | 70323.75 | 0 | 51984.23 | 18339.52 | 73.9% | 73.92%
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | In Progress | Time and material | Red Rock | Tina Aguirre | 244000 | 201680 | 201680 | 174704 | 174704 | 0 | 157468.07 | 17235.93 | 82.7% | 90.13%
25-PC-39085 | Slate Ridge Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez | 120700 | 119806.82 | 119806.82 | 69209.38 | 69209.38 | 0 | 68696.85 | 512.53 | 99.3% | 99.26%
25-PC-39118 | Harbor View Harbor Dredging Cultural Resources Monitoring | In Progress | Fixed fee | Red Rock | Shelia Horne | 90300 | 67986.87 | 62928.94 | 58198.35 | 58198.35 | 0 | 43819.98 | 14378.37 | 75.3% | 75.29%
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Final Reporting/Review | Time and material | Red Rock | Tina Aguirre | 55900 | 55900 | 54034.56 | 39633.1 | 39633.1 | 0 | 38428.92 | 1204.18 | 100% | 96.96%
25-PC-39424 | Tansy Flat Cultural Resources Assessment | In Progress | Fixed fee | Red Rock | Shelia Horne | 19700 | 19700 | 17614.13 | 13882.59 | 13882.59 | 0 | 16267.84 | -2385.25 | 100% | 117.2%
25-PC-39554 | Thistle Down Archaeological Testing | In Progress | Fixed fee | Red Rock | Tina Aguirre | 86700 | 75628.41 | 63747.46 | 63594.45 | 63594.45 | 0 | 55476.01 | 8118.44 | 87.2% | 87.23%
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | In Progress | Time and material | Red Rock | Javier Newman | 51000 | 51000 | 51000 | 36551.7 | 36551.7 | 0 | 75197.04 | -38645.34 | 100% | 205.7%
25-PC-40383 | North Fork Archaeological Testing | In Progress | Fixed fee | Sierra | Donna Herring | 193200 | 161148.12 | 161148.12 | 144185.16 | 144185.16 | 0 | 120262.61 | 23922.55 | 83.4% | 83.41%
25-PC-40503 | Copper Flats Phase I Survey | Lab/Curation | Time and material | Sierra | Benjamin Mathis | 43400 | 43400 | 43400 | 30119.6 | 30119.6 | 0 | 42364.23 | -12244.63 | 100% | 140.7%
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring | 71000 | 71000 | 67104.25 | 49579.3 | 49579.3 | 0 | 76399.6 | -26820.3 | 100% | 154.1%
25-PC-40677 | Quail Run Paleontological Monitoring | Transferred Entity | Time and material | Sierra South | Louis Huff | 225000 | 192903.25 | 192903.25 | 157612.5 | 157612.5 | 0 | 153698.04 | 3914.46 | 85.7% | 97.52%
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 50100 | 50100 | 47994.45 | 34844.55 | 34844.55 | 0 | 37556.22 | -2711.67 | 100% | 107.8%
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 46800 | 46800 | 46800 | 34243.56 | 34243.56 | 0 | 37494.89 | -3251.33 | 100% | 109.5%
25-PC-41187 | Hackberry Bend Trail GIS Mapping | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 98900 | 75510.15 | 72782.09 | 55621.36 | 55621.36 | 0 | 42469.63 | 13151.73 | 76.3% | 76.35%
25-PC-41265 | Larkspur Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 89800 | 85318.98 | 85318.98 | 71911.84 | 71911.84 | 0 | 68323.14 | 3588.7 | 95% | 95.01%
25-PC-41341 | Phase II: Coyote Springs Highway Widening Curation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 167900 | 133782.72 | 130782.09 | 131616.81 | 131616.81 | 0 | 104866.5 | 26750.31 | 79.7% | 79.68%
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 179800 | 179800 | 170811.36 | 119171.44 | 119171.44 | 0 | 171055.95 | -51884.51 | 100% | 143.5%
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Jared Choi | 130200 | 121022.45 | 121022.45 | 94156.73 | 81265.42 | 12891.31 | 105548.13 | -11391.4 | 93% | 112.1%
25-PC-41635 | Plover Cove Rail Siding GIS Mapping | In Progress | Time and material | Coastal Bend | Jared Choi | 412300 | 300806.95 | 290386.6 | 281889.51 | 281889.51 | 0 | 224531.7 | 57357.81 | 73% | 79.65%
25-PC-41722 | Willow Springs Canal Lining Built Environment Survey | In Progress | Time and material | Built Environment | Jenny Wilkinson | 152100 | 112187.4 | 112187.4 | 108599.4 | 108599.4 | 0 | 90984.66 | 17614.74 | 73.8% | 83.78%
25-PC-41854 | Hackberry Bend Rail Siding - Section 106 Consultation | In Progress | Time and material | Built Environment | Rickey Salas | 39700 | 39700 | 38010.35 | 25920.13 | 25920.13 | 0 | 29882.88 | -3962.75 | 100% | 115.3%
25-PC-42227 | Task Order 22: Lantern Bay School Campus Data Recovery | Cost Tracking on Closed Project | Time and material | Built Environment | Kathleen Cabrera | 17900 | 161.1 | 161.1 | 12066.39 | 12066.39 | 0 | 14332.43 | -2266.04 | 0.9% | 118.8%
25-PC-42315 | Sage Flat Bridge Replacement Class III Survey | In Progress | Fixed fee | Paleontology | Charlene Sparks | 41200 | 32304.92 | 29924.09 | 29239.64 | 29239.64 | 0 | 22925.4 | 6314.24 | 78.4% | 78.41%
25-PC-42717 | Task Order 24: Sea Oat Cell Tower Data Recovery | In Progress | Time and material | Maritime | Kyle Maynard | 130300 | 128601.35 | 128601.35 | 95796.56 | 95796.56 | 0 | 79985.69 | 15810.87 | 98.7% | 83.5%
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Transferred Entity | Time and material | Geospatial | Sylvia Callahan | 62000 | 54684.75 | 54684.75 | 44404.4 | 44404.4 | 0 | 44584.79 | -180.39 | 88.2% | 100.4%
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | In Progress | Fixed fee | Meridian Central | Seth Zavala | 128400 | 128400 | 128209.36 | 106315.2 | 106315.2 | 0 | 195734.3 | -89419.1 | 100% | 184.1%
25-PC-43286 | Riverbend Highway Widening - Phase II Testing | In Progress | Time and material | Meridian Central | Seth Zavala | 15700 | 15700 | 11349.21 | 10903.65 | 10903.65 | 0 | 71168.37 | -60264.72 | 100% | 652.7%
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Clinton Solis | 715500 | 650818.8 | 650818.8 | 625275.45 | 625275.45 | 0 | 568777.84 | 56497.61 | 91% | 90.96%
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Seth Zavala | 551800 | 551800 | 551800 | 378424.44 | 378424.44 | 0 | 405626.36 | -27201.92 | 100% | 107.2%
25-PC-43566 | Copper Flats Solar - Phase II Testing | In Progress | Fixed fee | Meridian Central | Mathew Shea | 114200 | 114200 | 114200 | 73887.4 | 73887.4 | 0 | 131458.02 | -57570.62 | 100% | 177.9%
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 52800 | 52800 | 52800 | 37979.04 | 37979.04 | 0 | 37986.88 | -7.84 | 100% | 100%
25-PC-43639 | Windmill Flat Battery Storage Curation | Final Reporting/Review | Fixed fee | Meridian Southwest | Harold Chaney | 137000 | 137000 | 133193.26 | 91502.3 | 91502.3 | 0 | 100918.9 | -9416.6 | 100% | 110.3%
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Lab/Curation | Fixed fee | Meridian Southwest | Reginald Kerr | 92800 | 92800 | 80044.54 | 78211.84 | 78211.84 | 0 | 103245.03 | -25033.19 | 100% | 132%
25-PC-43993 | Timber Gap GIS Mapping | Transferred Entity | Fixed fee | NH Gulf (USD) | Javier Rangel | 27900 | 20428.3787 | 19158.5307 | 19669.5 | 19669.5 | 0 | 14401.75 | 5267.75 | 73.22% | 73.22%
25-PC-44046 | Kestrel Butte Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu | 320300 | 320300 | 320300 | 220526.55 | 220526.55 | 0 | 276639.9 | -56113.35 | 100% | 125.4%
25-PC-44198 | Task Order 2: Redbud Highway Widening GIS Mapping | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 31100 | 31100 | 30922.8613 | 17934.14 | 13115.76 | 4818.38 | 31276.1173 | -13341.9773 | 100% | 174.4%
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 97000 | 97000 | 91499.34 | 71004 | 71004 | 0 | 79042.17 | -8038.17 | 100% | 111.3%
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Big Sky | Javier Estrada | 93100 | 0 | 0 | 63801.43 | 63801.43 | 0 | 65021.47 | -1220.04 | 0% | 101.9%
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | In Progress | Fixed fee | Big Sky | Brendan Melton | 19900 | 19900 | 19400.11 | 14258.19 | 12707.2 | 1550.99 | 18074.33 | -3816.14 | 100% | 126.8%
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 209800 | 0 | 0 | 135467.86 | 135467.86 | 0 | 134699.95 | 767.91 | 0% | 99.43%
26-PC-31064 | Quail Run Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Gene Nixon | 74500 | 74500 | 74500 | 60394.3 | 53043.19 | 7351.11 | 76340.83 | -15946.53 | 100% | 126.4%
26-PC-31505 | Raven Rock Levee Repair - Built Environment Survey | In Progress | Fixed fee | Cascade | Donald Lutz | 44400 | 31128.84 | 30936.04 | 34032.6 | 34032.6 | 0 | 23861.11 | 10171.49 | 70.1% | 70.11%
26-PC-32394 | Timber Gap Highway Widening Paleontological Monitoring | In Progress | Time and material | Chesapeake | Bryan Mann | 13700 | 13700 | 13641.82 | 9522.87 | 9522.87 | 0 | 31103.81 | -21580.94 | 100% | 326.6%
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Cost Tracking on Closed Project | Time and material | Chesapeake | Sandy Kerr | 137100 | 0 | 0 | 100617.66 | 93287.5 | 7330.16 | 122245.29 | -21627.63 | 0% | 121.5%
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Final Reporting/Review | Fixed fee | Great Lakes | Karl Valenzuela | 21700 | 21700 | 11375.68 | 18501.42 | 18501.42 | 0 | 21928.62 | -3427.2 | 100% | 118.5%
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 76400 | 76400 | 70250.02 | 53087.85 | 46646.64 | 6441.21 | 80951.18 | -27863.33 | 100% | 152.5%
26-PC-34757 | Kestrel Butte Data Recovery | In Progress | Time and material | Great Lakes | Angelica Cervantes | 43800 | 43800 | 29653.46 | 30230.76 | 30230.76 | 0 | 49508.25 | -19277.49 | 100% | 163.8%
26-PC-34982 | Sandpiper Historic Resources Evaluation | In Progress | Time and material | Gulf Coast West | Bernard Erickson | 10600 | 10600 | 7692.83 | 7895.94 | 7895.94 | 0 | 18818.09 | -10922.15 | 100% | 238.3%
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 29600 | 29600 | 22003.12 | 19287.36 | 19287.36 | 0 | 56287.28 | -36999.92 | 100% | 291.8%
26-PC-35510 | Blue Heron Wind Farm - Phase I Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 68900 | 59529.6 | 49947.75 | 53679.99 | 53679.99 | 0 | 46380.29 | 7299.7 | 86.4% | 86.4%
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | High Desert | Jody Wang | 26300 | 26300 | 26300 | 19575.09 | 19575.09 | 0 | 22787.95 | -3212.86 | 100% | 116.4%
26-PC-37559 | Badger Hollow Paleontological Monitoring | In Progress | Time and material | Piedmont | Jody Chung | 44300 | 44300 | 33494.39 | 28024.18 | 28024.18 | 0 | 45539.17 | -17514.99 | 100% | 162.5%
26-PC-37705 | On-Call: Silver Lake Canal Lining Curation | In Progress | Fixed fee | Piedmont | Jody Chung | 40300 | 31772.52 | 24174.36 | 32312.54 | 32312.54 | 0 | 25475.14 | 6837.4 | 78.8% | 78.84%
26-PC-37709 | Sage Flat Phase I Survey | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 31500 | 31500 | 16533.22 | 21725.55 | 21725.55 | 0 | 30289.1 | -8563.55 | 100% | 139.4%
26-PC-37965 | Redbud Cultural Resources Assessment | In Progress | Time and material | Piedmont | Annette Vaughan | 55400 | 50946.25 | 31520.73 | 34625 | 34625 | 0 | 31687.21 | 2937.79 | 92% | 91.52%
26-PC-38410 | On-Call: Tamarack Park Improvements Class III Survey | In Progress | Time and material | Prairie | Sherry Lloyd | 48300 | 38345.25 | 38154.33 | 32887.47 | 32887.47 | 0 | 24978.26 | 7909.21 | 79.4% | 75.95%
26-PC-38624 | Juniper Wash Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Red Rock | Bruce Suarez | 77900 | 77900 | 77900 | 56578.77 | 56578.77 | 0 | 73552.4 | -16973.63 | 100% | 130%
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 97700 | 97700 | 80334.37 | 60828.02 | 60828.02 | 0 | 76641.91 | -15813.89 | 100% | 126%
26-PC-39165 | Pebble Beach Road Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre | 94300 | 87472.68 | 76455.85 | 63218.72 | 63218.72 | 0 | 58643.27 | 4575.45 | 92.8% | 92.76%
26-PC-39587 | Ember Valley Curation | Cost Tracking on Closed Project | Time and material | Red Rock | Javier Newman | 288900 | 0 | 0 | 211965.93 | 211965.93 | 0 | 213449.22 | -1483.29 | 0% | 100.7%
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Cost Tracking on Closed Project | Fixed fee | Red Rock | Tina Aguirre | 115900 | 115900 | 115900 | 86530.94 | 86530.94 | 0 | 99694.97 | -13164.03 | 100% | 115.2%
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 96900 | 96900 | 90582.43 | 68401.71 | 68401.71 | 0 | 75128.43 | -6726.72 | 100% | 109.8%
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Final Reporting/Review | Fixed fee | Sierra | Louis Huff | 19200 | 19200 | 16759.26 | 14098.56 | 14098.56 | 0 | 18399.82 | -4301.26 | 100% | 130.5%
26-PC-40361 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Sierra | Donna Herring | 156300 | 117897.09 | 95830.05 | 102829.77 | 102829.77 | 0 | 77565.49 | 25264.28 | 75.4% | 75.43%
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Final Reporting/Review | Fixed fee | Sierra South | Donna Herring | 5900 | 5900 | 5708.22 | 4379.73 | 3449.54 | 930.19 | 8489.9 | -4110.17 | 100% | 193.8%
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | In Progress | Fixed fee | Sierra North | Donna Herring | 7500 | 7500 | 7376.17 | 5493 | 5493 | 0 | 8125.76 | -2632.76 | 100% | 147.9%
26-PC-41130 | Harbor View Highway Widening Data Recovery | Cost Tracking on Closed Project | Time and material | Coastal Bend | Steve Rubio | 290300 | 0 | 0 | 219699.04 | 219699.04 | 0 | 201136.18 | 18562.86 | 0% | 91.55%
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 41400 | 41400 | 41400 | 27278.33 | 19877.52 | 7400.81 | 30232.83 | -2954.5 | 100% | 110.8%
26-PC-41661 | Ember Valley Levee Repair Data Recovery | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 4800 | 4800 | 1827.9 | 4028.16 | 4028.16 | 0 | 4393.64 | -365.48 | 100% | 109.1%
26-PC-42757 | Task Order 4: Tansy Flat Wind Farm Archaeological Testing | In Progress | Fixed fee | Maritime | Kyle Maynard | 347000 | 252477.2 | 226595.93 | 256363.6 | 256363.6 | 0 | 186528.08 | 69835.52 | 72.8% | 72.76%
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Final Reporting/Review | Time and material | Geospatial | Sylvia Callahan | 107600 | 107600 | 99262.67 | 77827.43 | 68885.46 | 8941.97 | 89098.75 | -11271.32 | 100% | 114.5%
26-PC-43199 | Thistle Down Airport Apron Phase I Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Mathew Shea | 42200 | 38937.94 | 38937.94 | 26341.24 | 26341.24 | 0 | 24305.56 | 2035.68 | 92.3% | 92.27%
26-PC-43329 | Sumac Ridge Cell Tower Built Environment Survey | In Progress | Fixed fee | Meridian Central | Mathew Shea | 41200 | 30945.32 | 29998.17 | 27426.84 | 27426.84 | 0 | 20599.46 | 6827.38 | 75.1% | 75.11%
26-PC-43364 | Goldfinch Class III Survey | Transferred Entity | Fixed fee | Meridian Central | Raymond Hensley | 24900 | 24900 | 23821.32 | 16624.07 | 15142.4 | 1481.67 | 22825.96 | -6201.89 | 100% | 137.3%
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | In Progress | Fixed fee | Meridian Central | Clinton Solis | 136900 | 131026.99 | 130552.64 | 105043.37 | 105043.37 | 0 | 100533.21 | 4510.16 | 95.7% | 95.71%
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Justin Mejia | 220800 | 218771.2507 | 195354 | 146699.52 | 146699.52 | 0 | 136849.0807 | 9850.4393 | 99.08% | 93.29%
25-PC-44140 | Stone Mill Archaeological Testing | In Progress | Fixed fee | NH Gulf | Tonya Spence | 149900 | 149510.2587 | 130809.0507 | 100298.0907 | 100298.0907 | 0 | 100035.4533 | 262.6373 | 99.74% | 99.74%

## Projects 90% & > $50k
Summary:
Removed projects with ETC>1% budget remaining
Removed $0 Contract Value projects
Removed previously identified ETC in final/reportingstatus
Removed projects in final reporting with >10% budget remaining
Total: 105
[6 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Total Budget | Total Budget Adjustment | Total Costs |  | Recognized %
[6 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Inception To Date | REV REC % | Budget Spent %
[6 empty] | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026
| Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Actual | Summary
23-PC-30881 | Dove Canyon Mixed-Use Development Archaeological Testing | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 86200 | 58616 | 58616 | 58650.48 | 58650.48 | 0 | 61318.15 | -2667.67 | 68% | 104.6%
23-PC-31374 | Juniper Wash Canal Lining Environmental Review Support | In Progress | Time and material | Cascade | Donald Lutz | 255700 | 173876 | 173876 | 168225.03 | 168225.03 | 0 | 202903.45 | -34678.42 | 68% | 120.6%
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Jeff Spence | 175300 | 175300 | 175300 | 93481.01 | 71376.84 | 22104.17 | 112759.17 | -19278.16 | 100% | 120.6%
23-PC-34510 | Millbrook Mixed-Use Development Class III Survey | Final Reporting/Review | Time and material | Great Lakes | Geoffrey Fernandez | 70000 | 47600 | 47600 | 50246 | 50246 | 0 | 45814.41 | 4431.59 | 68% | 91.18%
23-PC-35682 | Lantern Bay Class III Survey | In Progress | Fixed fee | High Desert | Eileen Poole | 290400 | 277361.04 | 277361.04 | 252938.4 | 252938.4 | 0 | 241578.4 | 11360 | 95.5% | 95.51%
23-PC-36063 | Plover Cove Mine Expansion - Phase II Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 114600 | 104870.46 | 104870.46 | 77893.62 | 77893.62 | 0 | 71277.07 | 6616.55 | 91.5% | 91.51%
23-PC-36422 | Hawk Point Phase I Survey | In Progress | Time and material | Island | Joan Mathis | 50700 | 34476 | 34476 | 36579.06 | 32790.93 | 3788.13 | 37409.59 | -830.53 | 68% | 102.3%
23-PC-38759 | Saltgrass Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Red Rock | Tina Aguirre | 52400 | 35632 | 35632 | 36847.68 | 36847.68 | 0 | 40372.44 | -3524.76 | 68% | 109.6%
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Lab/Curation | Fixed fee | Sierra | Louis Huff | 76500 | 76500 | 76500 | 58746.94 | 55119.6 | 3627.34 | 63236.56 | -4489.62 | 100% | 107.6%
23-PC-41134 | Creosote Draw Park Improvements Class III Survey | In Progress | Time and material | Coastal Bend | Steve Rubio | 56300 | 38284 | 38284 | 42714.81 | 42714.81 | 0 | 47948.89 | -5234.08 | 68% | 112.2%
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 349600 | 349600 | 349600 | 221087.04 | 221087.04 | 0 | 229204.35 | -8117.31 | 100% | 103.7%
23-PC-41602 | Wren Hollow Cultural Resources Monitoring | Lab/Curation | Fixed fee | Coastal Bend | Alexis Nixon | 755000 | 705170 | 705170 | 444695 | 444695 | 0 | 415325.46 | 29369.54 | 93.4% | 93.4%
23-PC-43158 | Twin Buttes Wind Farm - Archaeological Testing | In Progress | Fixed fee | Geospatial | Priscilla Pennington | 73300 | 66563.73 | 66563.73 | 53362.4 | 53362.4 | 0 | 48458.95 | 4903.45 | 90.8% | 90.81%
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 93300 | 93300 | 90265.16 | 59544.06 | 59544.06 | 0 | 93708.96 | -34164.9 | 100% | 157.4%
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 60600 | 60600 | 60600 | 45577.26 | 45577.26 | 0 | 50596.88 | -5019.62 | 100% | 111%
24-PC-31282 | Phase III: Timber Gap Mixed-Use Development GIS Mapping | Cost Tracking on Closed Project | Time and material | Cascade | Preston Duarte | 94000 | 63920 | 63920 | 65640.2 | 65640.2 | 0 | 73270.02 | -7629.82 | 68% | 111.6%
24-PC-31503 | North Fork Wind Farm Curation | Lab/Curation | Time and material | Cascade | Preston Duarte | 129900 | 88332 | 88332 | 87825.39 | 87825.39 | 0 | 98773.26 | -10947.87 | 68% | 112.5%
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 51800 | 51800 | 50026.67 | 36731.38 | 36731.38 | 0 | 59530.75 | -22799.37 | 100% | 162.1%
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Chesapeake | Alexandria Wilkinson | 84000 | 84000 | 83888.35 | 70198.8 | 70198.8 | 0 | 85361.67 | -15162.87 | 100% | 121.6%
24-PC-33822 | Task Order 36: Windmill Flat School Campus Cultural Resources Monitoring | In Progress | Fixed fee | Great Lakes | Karl Valenzuela | 64500 | 59346.45 | 57224.04 | 49568.25 | 49568.25 | 0 | 45606.09 | 3962.16 | 92% | 92.01%
24-PC-34803 | Cedar Hollow Highway Widening - Section 106 Consultation | In Progress | Time and material | Gulf Coast | Courtney Daugherty | 176500 | 120020 | 120020 | 121414.35 | 121414.35 | 0 | 122080.25 | -665.9 | 68% | 100.6%
24-PC-35412 | Sumac Ridge Reservoir - Historic Resources Evaluation | In Progress | Time and material | High Desert | Kathy Hurley | 301200 | 204816 | 204816 | 217496.52 | 217496.52 | 0 | 196030.1 | 21466.42 | 68% | 90.13%
24-PC-35661 | On-Call: Willow Springs Reservoir Archaeological Testing | In Progress | Time and material | High Desert | Kathy Hurley | 69900 | 69900 | 66597.48 | 49013.31 | 40696.6 | 8316.71 | 53862.59 | -4849.28 | 100% | 109.9%
24-PC-35872 | Wren Hollow Cultural Resources Monitoring | In Progress | Time and material | High Desert | Kathy Hurley | 225100 | 200102.05 | 200102.05 | 153743.3 | 153743.3 | 0 | 140872.8 | 12870.5 | 88.9% | 91.63%
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Cost Tracking on Closed Project | Fixed fee | High Desert | Kathy Hurley | 58300 | 58300 | 58300 | 39072.66 | 39072.66 | 0 | 45518.79 | -6446.13 | 100% | 116.5%
24-PC-36290 | Task Order 12: Lone Pine Battery Storage GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Island | Rodney Mcguire | 56300 | 52077.5 | 52077.5 | 37721 | 37721 | 0 | 34891.33 | 2829.67 | 92.5% | 92.5%
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | In Progress | Fixed fee | Hill Country | Glen Delacruz | 141000 | 141000 | 141000 | 113970.3 | 113970.3 | 0 | 138124.06 | -24153.76 | 100% | 121.2%
24-PC-38141 | Phase II: Willow Springs Airport Apron Cultural Resources Assessment | In Progress | Fixed fee | Prairie | Sherry Lloyd | 132200 | 121663.66 | 121663.66 | 95580.6 | 95580.6 | 0 | 87961.2 | 7619.4 | 92% | 92.03%
24-PC-38486 | Kestrel Butte Phase I Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 153600 | 153600 | 153600 | 105043.81 | 77500.98 | 27542.83 | 119866.24 | -14822.43 | 100% | 114.1%
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Red Rock | Marisa Odom | 168200 | 168200 | 168200 | 130489.56 | 130489.56 | 0 | 132230.67 | -1741.11 | 100% | 101.3%
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 100200 | 100200 | 93737.19 | 72685.08 | 72685.08 | 0 | 103671 | -30985.92 | 100% | 142.6%
24-PC-39533 | Elk Meadow Architectural History Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 67000 | 63536.1 | 63536.1 | 52641.9 | 52641.9 | 0 | 49919.2 | 2722.7 | 94.8% | 94.83%
24-PC-40102 | Redbud Class III Survey | Final Reporting/Review | Fixed fee | Sierra | Benjamin Mathis | 453900 | 453900 | 453900 | 322187.01 | 278794.4 | 43392.61 | 359994.61 | -37807.6 | 100% | 111.7%
24-PC-40659 | Phase III: Meadowlark Water Main Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Sierra North | Louis Huff | 50300 | 46200.55 | 46200.55 | 35350.84 | 35350.84 | 0 | 32471.24 | 2879.6 | 91.8% | 91.85%
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Lab/Curation | Fixed fee | Coastal Bend | Diane Daniels | 579300 | 579300 | 579300 | 392475.75 | 392475.75 | 0 | 413750.74 | -21274.99 | 100% | 105.4%
24-PC-41154 | Lantern Bay Mine Expansion Data Recovery | In Progress | Fixed fee | Coastal Bend | Alexis Nixon | 194900 | 187591.25 | 187591.25 | 131089.74 | 131089.74 | 0 | 126178.41 | 4911.33 | 96.3% | 96.25%
24-PC-42437 | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | In Progress | Time and material | Paleontology | Charlene Sparks | 263500 | 179180 | 179180 | 173567.45 | 173567.45 | 0 | 177335 | -3767.55 | 68% | 102.2%
24-PC-44113 | Cedar Hollow Airport Apron - Paleontological Monitoring | Transferred Entity | Time and material | NH Gulf (USD) | Susan Wilkins | 264500 | 264500 | 256769.1787 | 194222.35 | 194222.35 | 0 | 246339.6193 | -52117.2693 | 100% | 126.8%
25-PC-30772 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 63300 | 63300 | 63300 | 43065.84 | 35870.85 | 7194.99 | 56416.91 | -13351.07 | 100% | 131%
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 131000 | 131000 | 122522.64 | 85464.4 | 85464.4 | 0 | 90183.9 | -4719.5 | 100% | 105.5%
25-PC-31109 | Riverbend GIS Mapping | In Progress | Time and material | Cascade | Cassidy Gay | 174700 | 174700 | 154905.3 | 109484.49 | 109484.49 | 0 | 162892.26 | -53407.77 | 100% | 148.8%
25-PC-31180 | Blue Heron Environmental Review Support | In Progress | Fixed fee | Cascade | Preston Duarte | 80000 | 80000 | 69747.43 | 60701.89 | 45712.3 | 14989.59 | 64096.36 | -3394.47 | 100% | 105.6%
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 52000 | 52000 | 49983.77 | 38781.6 | 38781.6 | 0 | 51500.29 | -12718.69 | 100% | 132.8%
25-PC-31555 | Wren Hollow Architectural History Survey | In Progress | Fixed fee | Cascade | Gene Nixon | 69300 | 66417.12 | 60877.3 | 53097.66 | 53097.66 | 0 | 50888.1 | 2209.56 | 95.8% | 95.84%
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | In Progress | Fixed fee | Cascade | Preston Duarte | 216800 | 216800 | 202009.7 | 171337.04 | 171337.04 | 0 | 185663.62 | -14326.58 | 100% | 108.4%
25-PC-32323 | Hackberry Bend Canal Lining Data Recovery | In Progress | Time and material | Chesapeake | Ian Maddox | 201300 | 196916.6 | 185059.24 | 150874.35 | 150874.35 | 0 | 161800.48 | -10926.13 | 97.8% | 107.2%
25-PC-32447 | Pebble Beach Road Archaeological Testing | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 88200 | 88200 | 88200 | 61772.24 | 55626.38 | 6145.86 | 76703.23 | -14930.99 | 100% | 124.2%
25-PC-32495 | Oak Terrace Canal Lining - Phase I Survey | In Progress | Time and material | Chesapeake | Sandy Kerr | 118800 | 118800 | 111029.5 | 85013.28 | 85013.28 | 0 | 117591.53 | -32578.25 | 100% | 138.3%
25-PC-32861 | Yarrow Point Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 59200 | 59200 | 54224.79 | 41555.52 | 31694.67 | 9860.85 | 49895.36 | -8339.84 | 100% | 120.1%
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 59600 | 59600 | 57228.13 | 51399.04 | 51399.04 | 0 | 74823.59 | -23424.55 | 100% | 145.6%
25-PC-33065 | Wren Hollow GIS Mapping | In Progress | Fixed fee | Front Range | Dean Velazquez | 50400 | 45596.88 | 45596.88 | 40748.4 | 40748.4 | 0 | 36866.22 | 3882.18 | 90.5% | 90.47%
25-PC-33183 | Saltgrass Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 104500 | 101009.7 | 95400.33 | 79399.1 | 79399.1 | 0 | 76745.43 | 2653.67 | 96.7% | 96.66%
25-PC-33750 | Kestrel Butte Archaeological Testing | Transferred Entity | Fixed fee | Great Lakes | Kathleen Galvan | 69600 | 69600 | 64460.42 | 51302.16 | 51302.16 | 0 | 60286.74 | -8984.58 | 100% | 117.5%
25-PC-34176 | Meadowlark Mixed-Use Development - Historic Resources Evaluation | In Progress | Time and material | Great Lakes | Geoffrey Fernandez | 53000 | 53000 | 53000 | 36718.4 | 36718.4 | 0 | 42629.29 | -5910.89 | 100% | 116.1%
25-PC-34780 | Sumac Ridge Canal Lining Paleontological Monitoring | In Progress | Time and material | Great Lakes | Gina Beltran | 82200 | 82200 | 65071.92 | 51638.04 | 51638.04 | 0 | 83204.3 | -31566.26 | 100% | 161.1%
25-PC-35040 | Hackberry Bend Rail Siding Class III Survey | In Progress | Time and material | Gulf Coast East | Bernard Erickson | 71400 | 71400 | 71400 | 48880.44 | 48880.44 | 0 | 56947.79 | -8067.35 | 100% | 116.5%
25-PC-35485 | Wren Hollow Transmission Line - Phase I Survey | In Progress | Time and material | High Desert | Kathy Hurley | 136900 | 136900 | 132838.07 | 90994.45 | 78522.66 | 12471.79 | 119032.95 | -28038.5 | 100% | 130.8%
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 204800 | 204800 | 187347.98 | 136396.8 | 136396.8 | 0 | 140077.69 | -3680.89 | 100% | 102.7%
25-PC-35897 | Phase I: Riverbend Wastewater Plant Class III Survey | In Progress | Fixed fee | High Desert | Jody Wang | 83700 | 76761.27 | 76761.27 | 61050.78 | 61050.78 | 0 | 55992.16 | 5058.62 | 91.7% | 91.71%
25-PC-35963 | Quail Run Substation - Section 106 Consultation | In Progress | Time and material | High Desert | Kathy Hurley | 320000 | 290771 | 290771 | 216192 | 216192 | 0 | 202041.59 | 14150.41 | 90.9% | 93.45%
25-PC-36129 | Larkspur Rail Siding Environmental Review Support | In Progress | Time and material | High Desert | Kathy Hurley | 114200 | 114200 | 114200 | 78124.22 | 78124.22 | 0 | 79562.79 | -1438.57 | 100% | 101.8%
25-PC-36641 | Sparrow Hill Airport Apron Phase II Testing | In Progress | Time and material | Lakeshore | Lucas Benson | 181300 | 181300 | 174825.53 | 117609.31 | 117609.31 | 0 | 164790.18 | -47180.87 | 100% | 140.1%
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Final Reporting/Review | Fixed fee | Lakeshore | Jeanette Riddle | 74000 | 74000 | 66065.35 | 56358.4 | 56358.4 | 0 | 66079.16 | -9720.76 | 100% | 117.3%
25-PC-37164 | Yarrow Point Wastewater Plant - Phase I Survey | In Progress | Time and material | Hill Country | Glen Delacruz | 75400 | 75400 | 71354.11 | 50299.34 | 50299.34 | 0 | 90901.92 | -40602.58 | 100% | 180.7%
25-PC-37392 | Eagle Bend Wind Farm - Phase I Survey | In Progress | Fixed fee | Piedmont | Maria Parrish | 59200 | 54913.92 | 54913.92 | 50698.88 | 50698.88 | 0 | 47030.53 | 3668.35 | 92.8% | 92.76%
25-PC-37461 | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | Cost Tracking on Closed Project | Time and material | Piedmont | Megan Pineda | 83200 | 22297.6 | 22297.6 | 60186.88 | 60186.88 | 0 | 78242.94 | -18056.06 | 26.8% | 130%
25-PC-37786 | Fern Valley Wastewater Plant Paleontological Monitoring | Final Reporting/Review | Time and material | Piedmont | Maria Parrish | 72200 | 69466.7 | 69466.7 | 44893.96 | 44893.96 | 0 | 57390.52 | -12496.56 | 96.2% | 127.8%
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | In Progress | Fixed fee | Red Rock | Javier Newman | 63900 | 63900 | 60446.65 | 41637.24 | 41637.24 | 0 | 60770.39 | -19133.15 | 100% | 145.9%
25-PC-39035 | Rushgrass Draw School Campus - Built Environment Survey | In Progress | Time and material | Red Rock | Tina Aguirre | 244000 | 201680 | 201680 | 174704 | 174704 | 0 | 157468.07 | 17235.93 | 82.7% | 90.13%
25-PC-39085 | Slate Ridge Environmental Review Support | In Progress | Fixed fee | Red Rock | Bruce Suarez | 120700 | 119806.82 | 119806.82 | 69209.38 | 69209.38 | 0 | 68696.85 | 512.53 | 99.3% | 99.26%
25-PC-39358 | Task Order 1: Hawk Point Wastewater Plant Archaeological Testing | Final Reporting/Review | Time and material | Red Rock | Tina Aguirre | 55900 | 55900 | 54034.56 | 39633.1 | 39633.1 | 0 | 38428.92 | 1204.18 | 100% | 96.96%
25-PC-39765 | Phase II: Windmill Flat Wind Farm Built Environment Survey | In Progress | Time and material | Red Rock | Javier Newman | 51000 | 51000 | 51000 | 36551.7 | 36551.7 | 0 | 75197.04 | -38645.34 | 100% | 205.7%
25-PC-40523 | On-Call: Oak Terrace Reservoir Section 106 Consultation | In Progress | Time and material | Sierra | Donna Herring | 71000 | 71000 | 67104.25 | 49579.3 | 49579.3 | 0 | 76399.6 | -26820.3 | 100% | 154.1%
25-PC-40677 | Quail Run Paleontological Monitoring | Transferred Entity | Time and material | Sierra South | Louis Huff | 225000 | 192903.25 | 192903.25 | 157612.5 | 157612.5 | 0 | 153698.04 | 3914.46 | 85.7% | 97.52%
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 50100 | 50100 | 47994.45 | 34844.55 | 34844.55 | 0 | 37556.22 | -2711.67 | 100% | 107.8%
25-PC-41265 | Larkspur Class III Survey | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 89800 | 85318.98 | 85318.98 | 71911.84 | 71911.84 | 0 | 68323.14 | 3588.7 | 95% | 95.01%
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 179800 | 179800 | 170811.36 | 119171.44 | 119171.44 | 0 | 171055.95 | -51884.51 | 100% | 143.5%
25-PC-41500 | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | In Progress | Time and material | Coastal Bend | Jared Choi | 130200 | 121022.45 | 121022.45 | 94156.73 | 81265.42 | 12891.31 | 105548.13 | -11391.4 | 93% | 112.1%
25-PC-43073 | Elk Meadow Highway Widening Phase I Survey | Transferred Entity | Time and material | Geospatial | Sylvia Callahan | 62000 | 54684.75 | 54684.75 | 44404.4 | 44404.4 | 0 | 44584.79 | -180.39 | 88.2% | 100.4%
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | In Progress | Fixed fee | Meridian Central | Seth Zavala | 128400 | 128400 | 128209.36 | 106315.2 | 106315.2 | 0 | 195734.3 | -89419.1 | 100% | 184.1%
25-PC-43315 | Phase III: Hackberry Bend Bridge Replacement Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Clinton Solis | 715500 | 650818.8 | 650818.8 | 625275.45 | 625275.45 | 0 | 568777.84 | 56497.61 | 91% | 90.96%
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Seth Zavala | 551800 | 551800 | 551800 | 378424.44 | 378424.44 | 0 | 405626.36 | -27201.92 | 100% | 107.2%
25-PC-43566 | Copper Flats Solar - Phase II Testing | In Progress | Fixed fee | Meridian Central | Mathew Shea | 114200 | 114200 | 114200 | 73887.4 | 73887.4 | 0 | 131458.02 | -57570.62 | 100% | 177.9%
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 52800 | 52800 | 52800 | 37979.04 | 37979.04 | 0 | 37986.88 | -7.84 | 100% | 100%
25-PC-43639 | Windmill Flat Battery Storage Curation | Final Reporting/Review | Fixed fee | Meridian Southwest | Harold Chaney | 137000 | 137000 | 133193.26 | 91502.3 | 91502.3 | 0 | 100918.9 | -9416.6 | 100% | 110.3%
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Lab/Curation | Fixed fee | Meridian Southwest | Reginald Kerr | 92800 | 92800 | 80044.54 | 78211.84 | 78211.84 | 0 | 103245.03 | -25033.19 | 100% | 132%
25-PC-44046 | Kestrel Butte Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu | 320300 | 320300 | 320300 | 220526.55 | 220526.55 | 0 | 276639.9 | -56113.35 | 100% | 125.4%
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 97000 | 97000 | 91499.34 | 71004 | 71004 | 0 | 79042.17 | -8038.17 | 100% | 111.3%
26-PC-30432 | On-Call: Foxglove Substation Cultural Resources Assessment | Cost Tracking on Closed Project | Time and material | Big Sky | Javier Estrada | 93100 | 0 | 0 | 63801.43 | 63801.43 | 0 | 65021.47 | -1220.04 | 0% | 101.9%
26-PC-30917 | Heron Marsh Harbor Dredging Environmental Review Support | Cost Tracking on Closed Project | Time and material | Bluegrass | Alice Galloway | 209800 | 0 | 0 | 135467.86 | 135467.86 | 0 | 134699.95 | 767.91 | 0% | 99.43%
26-PC-31064 | Quail Run Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Gene Nixon | 74500 | 74500 | 74500 | 60394.3 | 53043.19 | 7351.11 | 76340.83 | -15946.53 | 100% | 126.4%
26-PC-32744 | Sea Oat Airport Apron Phase II Testing | Cost Tracking on Closed Project | Time and material | Chesapeake | Sandy Kerr | 137100 | 0 | 0 | 100617.66 | 93287.5 | 7330.16 | 122245.29 | -21627.63 | 0% | 121.5%
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 76400 | 76400 | 70250.02 | 53087.85 | 46646.64 | 6441.21 | 80951.18 | -27863.33 | 100% | 152.5%
26-PC-37965 | Redbud Cultural Resources Assessment | In Progress | Time and material | Piedmont | Annette Vaughan | 55400 | 50946.25 | 31520.73 | 34625 | 34625 | 0 | 31687.21 | 2937.79 | 92% | 91.52%
26-PC-38624 | Juniper Wash Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Red Rock | Bruce Suarez | 77900 | 77900 | 77900 | 56578.77 | 56578.77 | 0 | 73552.4 | -16973.63 | 100% | 130%
26-PC-38737 | Pebble Beach Road Wind Farm Historic Resources Evaluation | In Progress | Time and material | Red Rock | Tina Aguirre | 97700 | 97700 | 80334.37 | 60828.02 | 60828.02 | 0 | 76641.91 | -15813.89 | 100% | 126%
26-PC-39165 | Pebble Beach Road Phase I Survey | Final Reporting/Review | Fixed fee | Red Rock | Tina Aguirre | 94300 | 87472.68 | 76455.85 | 63218.72 | 63218.72 | 0 | 58643.27 | 4575.45 | 92.8% | 92.76%
26-PC-39587 | Ember Valley Curation | Cost Tracking on Closed Project | Time and material | Red Rock | Javier Newman | 288900 | 0 | 0 | 211965.93 | 211965.93 | 0 | 213449.22 | -1483.29 | 0% | 100.7%
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Cost Tracking on Closed Project | Fixed fee | Red Rock | Tina Aguirre | 115900 | 115900 | 115900 | 86530.94 | 86530.94 | 0 | 99694.97 | -13164.03 | 100% | 115.2%
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 96900 | 96900 | 90582.43 | 68401.71 | 68401.71 | 0 | 75128.43 | -6726.72 | 100% | 109.8%
26-PC-41130 | Harbor View Highway Widening Data Recovery | Cost Tracking on Closed Project | Time and material | Coastal Bend | Steve Rubio | 290300 | 0 | 0 | 219699.04 | 219699.04 | 0 | 201136.18 | 18562.86 | 0% | 91.55%
26-PC-43039 | On-Call: Foxglove Reservoir Phase I Survey | Final Reporting/Review | Time and material | Geospatial | Sylvia Callahan | 107600 | 107600 | 99262.67 | 77827.43 | 68885.46 | 8941.97 | 89098.75 | -11271.32 | 100% | 114.5%
26-PC-43546 | Stone Mill Wastewater Plant - GIS Mapping | In Progress | Fixed fee | Meridian Central | Clinton Solis | 136900 | 131026.99 | 130552.64 | 105043.37 | 105043.37 | 0 | 100533.21 | 4510.16 | 95.7% | 95.71%
26-PC-43986 | Sage Flat Airport Apron Architectural History Survey | Transferred Entity | Time and material | NH Gulf (USD) | Justin Mejia | 220800 | 218771.2507 | 195354 | 146699.52 | 146699.52 | 0 | 136849.0807 | 9850.4393 | 99.08% | 93.29%
25-PC-44140 | Stone Mill Archaeological Testing | In Progress | Fixed fee | NH Gulf | Tonya Spence | 149900 | 149510.2587 | 130809.0507 | 100298.0907 | 100298.0907 | 0 | 100035.4533 | 262.6373 | 99.74% | 99.74%

## 100% Rev Rec FF
Summary:
Total: 79
[6 empty] | Contract Value | Revenue | Invoiced Amount | Total Revised Budget | Total Budget | Total Budget Adjustment | Total Costs |  | Recognized %
[6 empty] | Inception To Date | Inception To Date | Inception To Date | Orig Budget + Adjustments | Original | ETC | Inception To Date | Inception To Date | REV REC % | Budget Spent %
[6 empty] | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026 | September 29, 2026
| Dimension name | Project status | Project Billing type | Location Name | Project Manager Name | EOP | Actual | Actual | Actual | Actual | Actual | Actual | Remaining Budget | Actual | Summary
23-PC-31769 | Rushgrass Draw Paleontological Monitoring | In Progress | Fixed fee | Cascade | Gene Nixon | 34800 | 34800 | 34800 | 28779.6 | 28779.6 | 0 | 31540.76 | -2761.16 | 100% | 109.6%
23-PC-31844 | Task Order 37: Sea Oat Water Main Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Jeff Spence | 175300 | 175300 | 175300 | 93481.01 | 71376.84 | 22104.17 | 112759.17 | -19278.16 | 100% | 120.6%
23-PC-33553 | Phase III: Yarrow Point Reservoir Archaeological Testing | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 21600 | 21600 | 21600 | 15245.28 | 15245.28 | 0 | 16551.79 | -1306.51 | 100% | 108.6%
23-PC-40537 | Phase I: Tamarack Airport Apron Section 106 Consultation | Lab/Curation | Fixed fee | Sierra | Louis Huff | 76500 | 76500 | 76500 | 58746.94 | 55119.6 | 3627.34 | 63236.56 | -4489.62 | 100% | 107.6%
23-PC-41285 | Phase III: Ember Valley Park Improvements Data Recovery | Cost Tracking on Closed Project | Fixed fee | Coastal Bend | Diane Daniels | 349600 | 349600 | 349600 | 221087.04 | 221087.04 | 0 | 229204.35 | -8117.31 | 100% | 103.7%
24-PC-30233 | Bramble Creek Mine Expansion Phase I Survey | In Progress | Fixed fee | Big Sky | Javier Estrada | 93300 | 93300 | 90265.16 | 59544.06 | 59544.06 | 0 | 93708.96 | -34164.9 | 100% | 157.4%
24-PC-30679 | Kestrel Butte Maritime Remote Sensing Survey | In Progress | Fixed fee | Bluegrass | Kiara Gillespie | 60600 | 60600 | 60600 | 45577.26 | 45577.26 | 0 | 50596.88 | -5019.62 | 100% | 111%
24-PC-32201 | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | In Progress | Fixed fee | Chesapeake | Jason Oconnor | 51800 | 51800 | 50026.67 | 36731.38 | 36731.38 | 0 | 59530.75 | -22799.37 | 100% | 162.1%
24-PC-32647 | On-Call: Granite Pass Substation Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Chesapeake | Alexandria Wilkinson | 84000 | 84000 | 83888.35 | 70198.8 | 70198.8 | 0 | 85361.67 | -15162.87 | 100% | 121.6%
24-PC-36146 | Sea Oat Bridge Replacement Phase II Testing | Cost Tracking on Closed Project | Fixed fee | High Desert | Kathy Hurley | 58300 | 58300 | 58300 | 39072.66 | 39072.66 | 0 | 45518.79 | -6446.13 | 100% | 116.5%
24-PC-36978 | Slate Ridge Water Main Archaeological Testing | In Progress | Fixed fee | Hill Country | Glen Delacruz | 141000 | 141000 | 141000 | 113970.3 | 113970.3 | 0 | 138124.06 | -24153.76 | 100% | 121.2%
24-PC-38486 | Kestrel Butte Phase I Survey | In Progress | Fixed fee | Red Rock | Jeanette Chung | 153600 | 153600 | 153600 | 105043.81 | 77500.98 | 27542.83 | 119866.24 | -14822.43 | 100% | 114.1%
24-PC-38790 | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | Transferred Entity | Fixed fee | Red Rock | Marisa Odom | 168200 | 168200 | 168200 | 130489.56 | 130489.56 | 0 | 132230.67 | -1741.11 | 100% | 101.3%
24-PC-39091 | Phase I: Dove Canyon Battery Storage Class III Survey | In Progress | Fixed fee | Red Rock | Shelia Horne | 100200 | 100200 | 93737.19 | 72685.08 | 72685.08 | 0 | 103671 | -30985.92 | 100% | 142.6%
24-PC-39308 | Pebble Beach Road Reservoir GIS Mapping | Cost Tracking on Closed Project | Fixed fee | Red Rock | Shelia Horne | 11000 | 11000 | 11000 | 7227 | 7227 | 0 | 7427.79 | -200.79 | 100% | 102.8%
24-PC-39825 | On-Call: Twin Buttes Housing Development GIS Mapping | In Progress | Fixed fee | Red Rock | Bruce Suarez | 17800 | 17800 | 17800 | 14308.95 | 10538.95 | 3770 | 14659.16 | -350.21 | 100% | 102.5%
24-PC-40102 | Redbud Class III Survey | Final Reporting/Review | Fixed fee | Sierra | Benjamin Mathis | 453900 | 453900 | 453900 | 322187.01 | 278794.4 | 43392.61 | 359994.61 | -37807.6 | 100% | 111.7%
24-PC-40670 | Sumac Ridge Cultural Resources Monitoring | Final Reporting/Review | Fixed fee | Sierra North | Donna Herring | 22100 | 22100 | 22100 | 17918.68 | 17918.68 | 0 | 33602.1 | -15683.42 | 100% | 187.5%
24-PC-40824 | Slate Ridge Water Main Maritime Remote Sensing Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Duane Ballard | 31800 | 31800 | 31800 | 20975.28 | 20975.28 | 0 | 22323.11 | -1347.83 | 100% | 106.4%
24-PC-40888 | Pine Hollow Battery Storage - Archaeological Testing | Lab/Curation | Fixed fee | Coastal Bend | Diane Daniels | 579300 | 579300 | 579300 | 392475.75 | 392475.75 | 0 | 413750.74 | -21274.99 | 100% | 105.4%
24-PC-40956 | Foxglove Airport Apron - Maritime Remote Sensing Survey | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 8800 | 8800 | 8800 | 6914.16 | 6914.16 | 0 | 7269.9 | -355.74 | 100% | 105.2%
24-PC-41119 | Rushgrass Draw Cultural Resources Assessment | Transferred Entity | Fixed fee | Coastal Bend | Alexis Nixon | 18000 | 18000 | 15244.1 | 12312 | 12312 | 0 | 22722.22 | -10410.22 | 100% | 184.5%
24-PC-44158 | Saltgrass Environmental Review Support | Transferred Entity | Fixed fee | NH Gulf (USD) | Vanessa Duarte | 23200 | 23200 | 23148.0107 | 15583.44 | 15583.44 | 0 | 16044.04 | -460.6 | 100% | 103%
25-PC-30581 | Phase II: Foxglove Harbor Dredging Data Recovery | In Progress | Fixed fee | Bluegrass | Alice Galloway | 19700 | 19700 | 17105.05 | 13027.61 | 13027.61 | 0 | 13683.52 | -655.91 | 100% | 105%
25-PC-30772 | Sea Oat Cultural Resources Assessment | In Progress | Fixed fee | Bluegrass | Alice Galloway | 63300 | 63300 | 63300 | 43065.84 | 35870.85 | 7194.99 | 56416.91 | -13351.07 | 100% | 131%
25-PC-30803 | Saltgrass Cell Tower Built Environment Survey | In Progress | Fixed fee | Bluegrass | Alice Galloway | 131000 | 131000 | 122522.64 | 85464.4 | 85464.4 | 0 | 90183.9 | -4719.5 | 100% | 105.5%
25-PC-31180 | Blue Heron Environmental Review Support | In Progress | Fixed fee | Cascade | Preston Duarte | 80000 | 80000 | 69747.43 | 60701.89 | 45712.3 | 14989.59 | 64096.36 | -3394.47 | 100% | 105.6%
25-PC-31330 | Phase I: Kestrel Butte Substation Data Recovery | Lab/Curation | Fixed fee | Cascade | Donald Lutz | 23500 | 23500 | 23419.06 | 17263.1 | 17263.1 | 0 | 22123.1 | -4860 | 100% | 128.2%
25-PC-31417 | Sandpiper Park Improvements Phase I Survey | In Progress | Fixed fee | Cascade | Cassidy Gay | 52000 | 52000 | 49983.77 | 38781.6 | 38781.6 | 0 | 51500.29 | -12718.69 | 100% | 132.8%
25-PC-31590 | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | In Progress | Fixed fee | Cascade | Jean Cooke | 16800 | 16800 | 16756.9 | 11810.4 | 11810.4 | 0 | 15531.6 | -3721.2 | 100% | 131.5%
25-PC-31784 | On-Call: Badger Hollow Pipeline Archaeological Testing | In Progress | Fixed fee | Cascade | Preston Duarte | 216800 | 216800 | 202009.7 | 171337.04 | 171337.04 | 0 | 185663.62 | -14326.58 | 100% | 108.4%
25-PC-32447 | Pebble Beach Road Archaeological Testing | In Progress | Fixed fee | Chesapeake | Alexandria Wilkinson | 88200 | 88200 | 88200 | 61772.24 | 55626.38 | 6145.86 | 76703.23 | -14930.99 | 100% | 124.2%
25-PC-32861 | Yarrow Point Architectural History Survey | In Progress | Fixed fee | Front Range | Dean Velazquez | 59200 | 59200 | 54224.79 | 41555.52 | 31694.67 | 9860.85 | 49895.36 | -8339.84 | 100% | 120.1%
25-PC-32899 | Lone Pine Mixed-Use Development Phase I Survey | In Progress | Fixed fee | Front Range | Jeremy Tran | 59600 | 59600 | 57228.13 | 51399.04 | 51399.04 | 0 | 74823.59 | -23424.55 | 100% | 145.6%
25-PC-33105 | Redbud Data Recovery | In Progress | Fixed fee | Front Range | Kimberly Daugherty | 3500 | 3500 | 0 | 2324 | 2324 | 0 | 9006.2 | -6682.2 | 100% | 387.5%
25-PC-33750 | Kestrel Butte Archaeological Testing | Transferred Entity | Fixed fee | Great Lakes | Kathleen Galvan | 69600 | 69600 | 64460.42 | 51302.16 | 51302.16 | 0 | 60286.74 | -8984.58 | 100% | 117.5%
25-PC-33846 | Task Order 30: Bramble Creek Pipeline Environmental Review Support | Final Reporting/Review | Fixed fee | Great Lakes | Geoffrey Fernandez | 15200 | 15200 | 15200 | 11021.49 | 9579.99 | 1441.5 | 11383.28 | -361.79 | 100% | 103.3%
25-PC-33922 | Slate Ridge Data Recovery | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 22100 | 22100 | 22100 | 16113.11 | 16113.11 | 0 | 33890.09 | -17776.98 | 100% | 210.3%
25-PC-35340 | Goldfinch Bridge Replacement Paleontological Monitoring | In Progress | Fixed fee | Gulf Coast East | Bernard Erickson | 19400 | 19400 | 15409.48 | 13919.5 | 13919.5 | 0 | 36287.62 | -22368.12 | 100% | 260.7%
25-PC-35361 | Millbrook Fiber Route - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast | Courtney Daugherty | 25100 | 25100 | 24927.65 | 20032.31 | 20032.31 | 0 | 27206.94 | -7174.63 | 100% | 135.8%
25-PC-35761 | Hackberry Bend Transmission Line Archaeological Testing | In Progress | Fixed fee | High Desert | Kathy Hurley | 204800 | 204800 | 187347.98 | 136396.8 | 136396.8 | 0 | 140077.69 | -3680.89 | 100% | 102.7%
25-PC-36251 | Kestrel Butte Environmental Review Support | Lab/Curation | Fixed fee | Island | Joan Mathis | 39200 | 39200 | 39200 | 30446.64 | 30446.64 | 0 | 49335.55 | -18888.91 | 100% | 162%
25-PC-36485 | Task Order 2: Larkspur Substation Historic Resources Evaluation | In Progress | Fixed fee | Island | Becky Velazquez | 33100 | 33100 | 33100 | 25870.96 | 25870.96 | 0 | 34277.75 | -8406.79 | 100% | 132.5%
25-PC-36645 | Falcon Mesa Archaeological Testing | In Progress | Fixed fee | Lakeshore | Jeanette Riddle | 25400 | 25400 | 24158.24 | 20302.22 | 20302.22 | 0 | 38922.61 | -18620.39 | 100% | 191.7%
25-PC-36761 | Copper Flats Mine Expansion Built Environment Survey | Final Reporting/Review | Fixed fee | Lakeshore | Jeanette Riddle | 74000 | 74000 | 66065.35 | 56358.4 | 56358.4 | 0 | 66079.16 | -9720.76 | 100% | 117.3%
25-PC-36799 | Meadowlark Substation Phase I Survey | Final Reporting/Review | Fixed fee | Hill Country | Gail Meza | 32900 | 32900 | 30883.36 | 26389.09 | 26389.09 | 0 | 33048.52 | -6659.43 | 100% | 125.2%
25-PC-36809 | Sandpiper Park Improvements - Archaeological Testing | In Progress | Fixed fee | Hill Country | Samuel Wilkerson | 24200 | 24200 | 22550.8 | 16235.78 | 16235.78 | 0 | 26420.57 | -10184.79 | 100% | 162.7%
25-PC-37522 | Sparrow Hill Canal Lining Built Environment Survey | Lab/Curation | Fixed fee | Piedmont | Jody Chung | 21500 | 21500 | 20397.5 | 15617.6 | 15617.6 | 0 | 19499.41 | -3881.81 | 100% | 124.9%
25-PC-37881 | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | In Progress | Fixed fee | Piedmont | Megan Pineda | 7900 | 7900 | 7900 | 6020.59 | 6020.59 | 0 | 6629.3 | -608.71 | 100% | 110.1%
25-PC-38754 | On-Call: Sparrow Hill Solar Section 106 Consultation | In Progress | Fixed fee | Red Rock | Javier Newman | 63900 | 63900 | 60446.65 | 41637.24 | 41637.24 | 0 | 60770.39 | -19133.15 | 100% | 145.9%
25-PC-38835 | Phase I: Windmill Flat Battery Storage Archaeological Testing | Final Reporting/Review | Fixed fee | Red Rock | Bruce Suarez | 10400 | 10400 | 9781.64 | 5866.64 | 5866.64 | 0 | 18017.52 | -12150.88 | 100% | 307.1%
25-PC-39424 | Tansy Flat Cultural Resources Assessment | In Progress | Fixed fee | Red Rock | Shelia Horne | 19700 | 19700 | 17614.13 | 13882.59 | 13882.59 | 0 | 16267.84 | -2385.25 | 100% | 117.2%
25-PC-40810 | Goldfinch Mine Expansion Archaeological Testing | Transferred Entity | Fixed fee | Coastal Bend | Duane Ballard | 50100 | 50100 | 47994.45 | 34844.55 | 34844.55 | 0 | 37556.22 | -2711.67 | 100% | 107.8%
25-PC-40847 | Quail Run Harbor Dredging - Built Environment Survey | Final Reporting/Review | Fixed fee | Coastal Bend | Jared Choi | 46800 | 46800 | 46800 | 34243.56 | 34243.56 | 0 | 37494.89 | -3251.33 | 100% | 109.5%
25-PC-41385 | Tamarack Levee Repair - Historic Resources Evaluation | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 179800 | 179800 | 170811.36 | 119171.44 | 119171.44 | 0 | 171055.95 | -51884.51 | 100% | 143.5%
25-PC-43203 | Bramble Creek Mine Expansion Archaeological Testing | In Progress | Fixed fee | Meridian Central | Seth Zavala | 128400 | 128400 | 128209.36 | 106315.2 | 106315.2 | 0 | 195734.3 | -89419.1 | 100% | 184.1%
25-PC-43434 | Riverbend Airport Apron - Class III Survey | Cost Tracking on Closed Project | Fixed fee | Meridian Central | Seth Zavala | 551800 | 551800 | 551800 | 378424.44 | 378424.44 | 0 | 405626.36 | -27201.92 | 100% | 107.2%
25-PC-43566 | Copper Flats Solar - Phase II Testing | In Progress | Fixed fee | Meridian Central | Mathew Shea | 114200 | 114200 | 114200 | 73887.4 | 73887.4 | 0 | 131458.02 | -57570.62 | 100% | 177.9%
25-PC-43621 | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | In Progress | Fixed fee | Meridian Southwest | Alan Gay | 52800 | 52800 | 52800 | 37979.04 | 37979.04 | 0 | 37986.88 | -7.84 | 100% | 100%
25-PC-43639 | Windmill Flat Battery Storage Curation | Final Reporting/Review | Fixed fee | Meridian Southwest | Harold Chaney | 137000 | 137000 | 133193.26 | 91502.3 | 91502.3 | 0 | 100918.9 | -9416.6 | 100% | 110.3%
25-PC-43653 | Ember Valley Housing Development Paleontological Monitoring | Lab/Curation | Fixed fee | Meridian Southwest | Reginald Kerr | 92800 | 92800 | 80044.54 | 78211.84 | 78211.84 | 0 | 103245.03 | -25033.19 | 100% | 132%
25-PC-44046 | Kestrel Butte Section 106 Consultation | Transferred Entity | Fixed fee | NH Gulf (USD) | Randy Cantu | 320300 | 320300 | 320300 | 220526.55 | 220526.55 | 0 | 276639.9 | -56113.35 | 100% | 125.4%
25-PC-44312 | Task Order 19: Millbrook Bridge Replacement Class III Survey | In Progress | Fixed fee | NH Gulf (USD) | Randy Cantu | 97000 | 97000 | 91499.34 | 71004 | 71004 | 0 | 79042.17 | -8038.17 | 100% | 111.3%
26-PC-30501 | Hackberry Bend Bridge Replacement Architectural History Survey | In Progress | Fixed fee | Big Sky | Brendan Melton | 19900 | 19900 | 19400.11 | 14258.19 | 12707.2 | 1550.99 | 18074.33 | -3816.14 | 100% | 126.8%
26-PC-31064 | Quail Run Archaeological Testing | Cost Tracking on Closed Project | Fixed fee | Cascade | Gene Nixon | 74500 | 74500 | 74500 | 60394.3 | 53043.19 | 7351.11 | 76340.83 | -15946.53 | 100% | 126.4%
26-PC-33703 | Plover Cove Mixed-Use Development - GIS Mapping | Final Reporting/Review | Fixed fee | Great Lakes | Karl Valenzuela | 21700 | 21700 | 11375.68 | 18501.42 | 18501.42 | 0 | 21928.62 | -3427.2 | 100% | 118.5%
26-PC-34101 | North Fork Rail Siding Paleontological Monitoring | In Progress | Fixed fee | Great Lakes | Nathan Lambert | 76400 | 76400 | 70250.02 | 53087.85 | 46646.64 | 6441.21 | 80951.18 | -27863.33 | 100% | 152.5%
26-PC-35103 | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | In Progress | Fixed fee | Gulf Coast East | Courtney Daugherty | 29600 | 29600 | 22003.12 | 19287.36 | 19287.36 | 0 | 56287.28 | -36999.92 | 100% | 291.8%
26-PC-35766 | Eagle Bend Solar - Architectural History Survey | Cost Tracking on Closed Project | Fixed fee | High Desert | Jody Wang | 26300 | 26300 | 26300 | 19575.09 | 19575.09 | 0 | 22787.95 | -3212.86 | 100% | 116.4%
26-PC-37709 | Sage Flat Phase I Survey | Final Reporting/Review | Fixed fee | Piedmont | Maria Parrish | 31500 | 31500 | 16533.22 | 21725.55 | 21725.55 | 0 | 30289.1 | -8563.55 | 100% | 139.4%
26-PC-38624 | Juniper Wash Built Environment Survey | Cost Tracking on Closed Project | Fixed fee | Red Rock | Bruce Suarez | 77900 | 77900 | 77900 | 56578.77 | 56578.77 | 0 | 73552.4 | -16973.63 | 100% | 130%
26-PC-39725 | Kestrel Butte Mine Expansion Cultural Resources Assessment | Cost Tracking on Closed Project | Fixed fee | Red Rock | Tina Aguirre | 115900 | 115900 | 115900 | 86530.94 | 86530.94 | 0 | 99694.97 | -13164.03 | 100% | 115.2%
26-PC-40334 | Stone Mill Airport Apron - Class III Survey | In Progress | Fixed fee | Sierra North | Donna Herring | 96900 | 96900 | 90582.43 | 68401.71 | 68401.71 | 0 | 75128.43 | -6726.72 | 100% | 109.8%
26-PC-40344 | Tansy Flat Housing Development - Archaeological Testing | Final Reporting/Review | Fixed fee | Sierra | Louis Huff | 19200 | 19200 | 16759.26 | 14098.56 | 14098.56 | 0 | 18399.82 | -4301.26 | 100% | 130.5%
26-PC-40422 | Oak Terrace Mixed-Use Development - Architectural History Survey | Final Reporting/Review | Fixed fee | Sierra South | Donna Herring | 5900 | 5900 | 5708.22 | 4379.73 | 3449.54 | 930.19 | 8489.9 | -4110.17 | 100% | 193.8%
26-PC-40464 | Slate Ridge Trail - Paleontological Monitoring | In Progress | Fixed fee | Sierra North | Donna Herring | 7500 | 7500 | 7376.17 | 5493 | 5493 | 0 | 8125.76 | -2632.76 | 100% | 147.9%
26-PC-41202 | Quail Run Bridge Replacement Phase I Survey | In Progress | Fixed fee | Coastal Bend | Jared Choi | 41400 | 41400 | 41400 | 27278.33 | 19877.52 | 7400.81 | 30232.83 | -2954.5 | 100% | 110.8%
26-PC-41661 | Ember Valley Levee Repair Data Recovery | In Progress | Fixed fee | Coastal Bend | Diane Daniels | 4800 | 4800 | 1827.9 | 4028.16 | 4028.16 | 0 | 4393.64 | -365.48 | 100% | 109.1%
26-PC-43364 | Goldfinch Class III Survey | Transferred Entity | Fixed fee | Meridian Central | Raymond Hensley | 24900 | 24900 | 23821.32 | 16624.07 | 15142.4 | 1481.67 | 22825.96 | -6201.89 | 100% | 137.3%

## Weighted Overrun Calculation
PMO | Project | Amount | PMO | Overrun Amount | Total Revised Budgets | Weighted Overrun
Meridian Central | Bramble Creek Mine Expansion Archaeological Testing | -89419.1 | Meridian Central
Meridian Central | Riverbend Highway Widening - Phase II Testing | -60264.72 | Cascade
Meridian Central | Copper Flats Solar - Phase II Testing | -57570.62 | Red Rock
NH Gulf (USD) | Kestrel Butte Section 106 Consultation | -56113.35 | Chesapeake
Cascade | Riverbend GIS Mapping | -53407.77 | NH Gulf (USD)
NH Gulf (USD) | Cedar Hollow Airport Apron - Paleontological Monitoring | -52117.2693 | Coastal Bend
Coastal Bend | Tamarack Levee Repair - Historic Resources Evaluation | -51884.51 | Great Lakes
Lakeshore | Sparrow Hill Airport Apron Phase II Testing | -47180.87 | Sierra
Hill Country | Yarrow Point Wastewater Plant - Phase I Survey | -40602.58 | Hill Country
Red Rock | Phase II: Windmill Flat Wind Farm Built Environment Survey | -38645.34 | Lakeshore
Sierra | Redbud Class III Survey | -37807.6 | Gulf Coast East
Gulf Coast East | Kestrel Butte Harbor Dredging - Historic Resources Evaluation | -36999.92 | Piedmont
Cascade | Juniper Wash Canal Lining Environmental Review Support | -34678.42 | Front Range
Big Sky | Bramble Creek Mine Expansion Phase I Survey | -34164.9 | High Desert
Chesapeake | Oak Terrace Canal Lining - Phase I Survey | -32578.25 | Big Sky
Great Lakes | Sumac Ridge Canal Lining Paleontological Monitoring | -31566.26 | Meridian Southwest
Red Rock | Phase I: Dove Canyon Battery Storage Class III Survey | -30985.92 | Island
High Desert | Wren Hollow Transmission Line - Phase I Survey | -28038.5 | Bluegrass
Great Lakes | North Fork Rail Siding Paleontological Monitoring | -27863.33 | Sierra North
Meridian Central | Riverbend Airport Apron - Class III Survey | -27201.92 | Gulf Coast West
Sierra | On-Call: Oak Terrace Reservoir Section 106 Consultation | -26820.3 | Geospatial
Meridian Southwest | Ember Valley Housing Development Paleontological Monitoring | -25033.19 | Gulf Coast
Hill Country | Slate Ridge Water Main Archaeological Testing | -24153.76 | Built Environment
Front Range | Lone Pine Mixed-Use Development Phase I Survey | -23424.55 | Sierra South
Chesapeake | Task Order 14: Hawk Point Harbor Dredging Maritime Remote Sensing Survey | -22799.37 | Paleontology
Gulf Coast East | Goldfinch Bridge Replacement Paleontological Monitoring | -22368.12
Chesapeake | Sea Oat Airport Apron Phase II Testing | -21627.63
Chesapeake | Timber Gap Highway Widening Paleontological Monitoring | -21580.94
Coastal Bend | Pine Hollow Battery Storage - Archaeological Testing | -21274.99
Cascade | Task Order 37: Sea Oat Water Main Archaeological Testing | -19278.16
Great Lakes | Kestrel Butte Data Recovery | -19277.49
Red Rock | On-Call: Sparrow Hill Solar Section 106 Consultation | -19133.15
Island | Kestrel Butte Environmental Review Support | -18888.91
Lakeshore | Falcon Mesa Archaeological Testing | -18620.39
Piedmont | On-Call: Dove Canyon Fiber Route Cultural Resources Monitoring | -18056.06
Great Lakes | Slate Ridge Data Recovery | -17776.98
Piedmont | Badger Hollow Paleontological Monitoring | -17514.99
Red Rock | Juniper Wash Built Environment Survey | -16973.63
Cascade | Quail Run Archaeological Testing | -15946.53
Red Rock | Pebble Beach Road Wind Farm Historic Resources Evaluation | -15813.89
Sierra North | Sumac Ridge Cultural Resources Monitoring | -15683.42
Chesapeake | Sandpiper Canal Lining - Phase I Survey | -15312.75
Chesapeake | On-Call: Granite Pass Substation Cultural Resources Monitoring | -15162.87
Chesapeake | Pebble Beach Road Archaeological Testing | -14930.99
Red Rock | Kestrel Butte Phase I Survey | -14822.43
Cascade | On-Call: Badger Hollow Pipeline Archaeological Testing | -14326.58
Bluegrass | Sea Oat Cultural Resources Assessment | -13351.07
NH Gulf (USD) | Task Order 2: Redbud Highway Widening GIS Mapping | -13341.9773
Red Rock | Kestrel Butte Mine Expansion Cultural Resources Assessment | -13164.03
Cascade | Sandpiper Park Improvements Phase I Survey | -12718.69
Cascade | On-Call: Foxglove Fiber Route GIS Mapping | -12518.97
Piedmont | Fern Valley Wastewater Plant Paleontological Monitoring | -12496.56
Sierra | Copper Flats Phase I Survey | -12244.63
Red Rock | Phase I: Windmill Flat Battery Storage Archaeological Testing | -12150.88
Coastal Bend | Task Order 24: Elk Meadow Mixed-Use Development Historic Resources Evaluation | -11391.4
Geospatial | On-Call: Foxglove Reservoir Phase I Survey | -11271.32
Cascade | North Fork Wind Farm Curation | -10947.87
Chesapeake | Hackberry Bend Canal Lining Data Recovery | -10926.13
Gulf Coast West | Sandpiper Historic Resources Evaluation | -10922.15
Coastal Bend | Rushgrass Draw Cultural Resources Assessment | -10410.22
Coastal Bend | Saltgrass Battery Storage - Historic Resources Evaluation | -10225.06
Hill Country | Sandpiper Park Improvements - Archaeological Testing | -10184.79
Lakeshore | Copper Flats Mine Expansion Built Environment Survey | -9720.76
Meridian Southwest | Windmill Flat Battery Storage Curation | -9416.6
Great Lakes | North Fork Curation | -9159
Great Lakes | Kestrel Butte Archaeological Testing | -8984.58
Piedmont | Sage Flat Phase I Survey | -8563.55
Island | Task Order 2: Larkspur Substation Historic Resources Evaluation | -8406.79
Front Range | Yarrow Point Architectural History Survey | -8339.84
Coastal Bend | Phase III: Ember Valley Park Improvements Data Recovery | -8117.31
Gulf Coast East | Hackberry Bend Rail Siding Class III Survey | -8067.35
NH Gulf (USD) | Task Order 19: Millbrook Bridge Replacement Class III Survey | -8038.17
Front Range | Twin Buttes Wind Farm - Cultural Resources Monitoring | -7735.98
Cascade | Phase III: Timber Gap Mixed-Use Development GIS Mapping | -7629.82
Gulf Coast | Millbrook Fiber Route - Historic Resources Evaluation | -7174.63
Sierra North | Stone Mill Airport Apron - Class III Survey | -6726.72
Front Range | Redbud Data Recovery | -6682.2
Hill Country | Meadowlark Substation Phase I Survey | -6659.43
High Desert | Sea Oat Bridge Replacement Phase II Testing | -6446.13
Red Rock | Juniper Wash Pipeline - Archaeological Testing | -6405.95
Meridian Central | Goldfinch Class III Survey | -6201.89
Gulf Coast West | Thistle Down Cell Tower - Historic Resources Evaluation | -6142.84
Great Lakes | Meadowlark Mixed-Use Development - Historic Resources Evaluation | -5910.89
Coastal Bend | Creosote Draw Park Improvements Class III Survey | -5234.08
Bluegrass | Kestrel Butte Maritime Remote Sensing Survey | -5019.62
Cascade | Phase I: Kestrel Butte Substation Data Recovery | -4860
High Desert | On-Call: Willow Springs Reservoir Archaeological Testing | -4849.28
Geospatial | Thistle Down Solar - Maritime Remote Sensing Survey | -4749.07
Bluegrass | Saltgrass Cell Tower Built Environment Survey | -4719.5
Gulf Coast | Rushgrass Draw Battery Storage Architectural History Survey | -4603.13
Sierra | Phase I: Tamarack Airport Apron Section 106 Consultation | -4489.62
Sierra | Tansy Flat Housing Development - Archaeological Testing | -4301.26
Cascade | Task Order 27: Hawk Point Pipeline Data Recovery | -4274.41
Sierra South | Oak Terrace Mixed-Use Development - Architectural History Survey | -4110.17
Built Environment | Hackberry Bend Rail Siding - Section 106 Consultation | -3962.75
Piedmont | Sparrow Hill Canal Lining Built Environment Survey | -3881.81
Big Sky | Hackberry Bend Bridge Replacement Architectural History Survey | -3816.14
Paleontology | Task Order 36: Wren Hollow Water Main Maritime Remote Sensing Survey | -3767.55
Cascade | Task Order 11: Kestrel Butte Mine Expansion Cultural Resources Monitoring | -3721.2
High Desert | Hackberry Bend Transmission Line Archaeological Testing | -3680.89
Red Rock | Saltgrass Cultural Resources Assessment | -3524.76
Great Lakes | Plover Cove Mixed-Use Development - GIS Mapping | -3427.2
Cascade | Blue Heron Environmental Review Support | -3394.47
Coastal Bend | Quail Run Harbor Dredging - Built Environment Survey | -3251.33
High Desert | Eagle Bend Solar - Architectural History Survey | -3212.86
Coastal Bend | Quail Run Bridge Replacement Phase I Survey | -2954.5
Cascade | Rushgrass Draw Paleontological Monitoring | -2761.16
Coastal Bend | Goldfinch Mine Expansion Archaeological Testing | -2711.67
Chesapeake | Rushgrass Draw Curation | -2678.99
Bluegrass | Dove Canyon Mixed-Use Development Archaeological Testing | -2667.67
Sierra North | Slate Ridge Trail - Paleontological Monitoring | -2632.76
Red Rock | Tansy Flat Cultural Resources Assessment | -2385.25
Built Environment | Task Order 22: Lantern Bay School Campus Data Recovery | -2266.04
Red Rock | Twin Buttes Harbor Dredging Maritime Remote Sensing Survey | -1741.11
Red Rock | Ember Valley Curation | -1483.29
High Desert | Larkspur Rail Siding Environmental Review Support | -1438.57
Coastal Bend | Slate Ridge Water Main Maritime Remote Sensing Survey | -1347.83
Front Range | Phase III: Yarrow Point Reservoir Archaeological Testing | -1306.51
Front Range | North Fork Water Main Architectural History Survey | -1233.84
Big Sky | On-Call: Foxglove Substation Cultural Resources Assessment | -1220.04
Island | Hawk Point Phase I Survey | -830.53
Gulf Coast | Cedar Hollow Highway Widening - Section 106 Consultation | -665.9
Bluegrass | Phase II: Foxglove Harbor Dredging Data Recovery | -655.91
Piedmont | Phase II: Heron Marsh Mine Expansion Historic Resources Evaluation | -608.71
NH Gulf (USD) | Saltgrass Environmental Review Support | -460.6
Coastal Bend | Ember Valley Levee Repair Data Recovery | -365.48
Great Lakes | Task Order 30: Bramble Creek Pipeline Environmental Review Support | -361.79
Coastal Bend | Foxglove Airport Apron - Maritime Remote Sensing Survey | -355.74
Red Rock | On-Call: Twin Buttes Housing Development GIS Mapping | -350.21
High Desert | Silver Lake Airport Apron Class III Survey | -294.37
Red Rock | Pebble Beach Road Reservoir GIS Mapping | -200.79
Geospatial | Elk Meadow Highway Widening Phase I Survey | -180.39
Built Environment | Elk Meadow Fiber Route Archaeological Testing | -31.43
Meridian Southwest | Task Order 8: Pine Hollow Highway Widening Historic Resources Evaluation | -7.84